## Read me
TICVAI backend build plan: first release (POS, Guest App web and mobile, White Labelling)
Services | 16
Operations (APIs) to build | 760
API schemas they send or return | 469
Tables | 493
Migrations | 34
Backend and DevOps tasks | 1729
Points | 6628
How to read it
Build plan | Every backend and DevOps task. Step 1 can start now; a task at step N waits for at least one task at step N-1. Wave is when the screens need it.
Migrations | One forward-only migration per database schema, in the order they run. Each only references tables created before it; keys that would point forward are added by the last migration.
Tables | Every table the first release reads or writes, plus the tables their foreign keys reach, with the migration that creates each.
Services / APIs / API schemas | What each service builds, every operation to build, and the request and response schemas those operations use, with where each is stored.
Assignees | From docs/active/team.json, balanced by points. Points are relative size (1, 2, 3, 5, 8), not hours.
Generated by tools/build-service-docs.py from the contracts, the delivery slice, the lineage and the DDL in backend/. Re-run it; do not edit this file.

## Build plan
Step | Wave | Key | Parent | Task | Points | Assignee | Service | Depends on | Description
1 | 1 | SETUP-CI | AM-FOUNDATION-SETUP | [DevOps] CI pipelines for the backend and frontend repositories | 3 | Hrushikant Patkar |  |  | CI pipelines for the backend and frontend repositories. In **ticvai-backend** and **ticvai-frontend** (the repositories the setup zip creates). CI is GitHub Actions (decided 28 September, audit R057). Done when: every merge request runs build, tests and lint in both, a red run blocks the merge, and a failing test on a branch shows in the MR. Tool versions per setup/dependencies.md.
1 | 1 | SETUP-ENV | AM-FOUNDATION-SETUP | [DevOps] Dev and staging environments (Terraform, ADR-0007 infra repository) | 5 | Hrushikant Patkar |  |  | Dev and staging environments (Terraform, ADR-0007 infra repository). In **ticvai-infra** (ADR-0007: one parameterised `cell` module, one tfvars per environment). The provider is Azure in a UAE region, Terraform `azurerm`, with each cell's secrets in its Azure Key Vault (decided 28 September, audit R057). Done when: `terraform plan` and `apply` build dev and staging from nothing, state is remote and locked, and the cell mapping and Azure region are written in the infra README.
2 | 1 | SETUP-CLIENTS | AM-FOUNDATION-SETUP | [DevOps] Generate the typed API clients from contracts/ for the frontend workspace | 3 | Pranay Shinde |  | SETUP-CI | Generate the typed API clients from contracts/ for the frontend workspace. In **ticvai-frontend** `packages/api-client`: generated from the package's `contracts/`, re-generated by one command and checked in CI on GitHub Actions (audit R057). Done when: every in-release operation has a typed call, the build fails if the contracts change without a re-generate, and screen tickets stop stubbing calls.
2 | 1 | SETUP-DB | AM-FOUNDATION-SETUP | [DevOps] PostgreSQL (tenant and control databases) and a forward-only migration runner that applies the MIG epic in order | 5 | Pranay Shinde |  | SETUP-ENV | PostgreSQL (tenant and control databases) and a forward-only migration runner that applies the MIG epic in order. In **ticvai-backend**: `SqlMigrationRunner` (in the starter) applies `db/tenant` and `db/control` - the package's derived DDL - in file order and records each file with its checksum in `platform.schema_version`. The databases run on Azure in the UAE region, connection strings from the cell's Key Vault (audit R057). Done when: both databases exist in dev, the runner applies every MIG file to an empty database, and a second run applies nothing.
2 | 1 | SETUP-OBS | AM-FOUNDATION-SETUP | [DevOps] Logging and monitoring basics | 2 | Hrushikant Patkar |  | SETUP-ENV | Logging and monitoring basics. In **ticvai-infra** (Terraform, in the `cell` module) and **ticvai-backend**: the OpenTelemetry SDK (already referenced by the starter) in each of the five deployables of ADR-0055 (commerce, access, operations, workers and ticvai-ai), exporting traces, metrics and logs over OTLP to an OpenTelemetry Collector in the cell, which writes them to the cell's Log Analytics workspace in Azure UAE North (audit R057; nothing leaves the region). Logs are structured, never concatenated, and carry the trace and correlation ids; they never hold guest names, emails, phone numbers, document numbers, card data or biometric templates, only the opaque subject id (docs/architecture/observability.md; ADR-0009: PII-free by construction, not by filtering). Metrics are Prometheus-compatible. One alert rule to start with (the 5xx rate of each host) goes to an Azure Monitor action group that emails the on-call person (DevOps until a rota exists). Dev and staging only; production is built before the first live tenant. Done when: a request to a dev host can be followed from its log line to its trace by the correlation id; a deliberate 500 on a dev host raises an alert the on-call person receives within five minutes; and a search of a day's dev logs after the seeded test run finds no email address, phone number or card number.
2 | 1 | SETUP-HOSTS | AM-FOUNDATION-SETUP | [BE] Hosts for the deployables on .NET 10: commerce, access, operations and workers, each composing its modules | 3 | Hrushikant Patkar |  | SETUP-CI | Hosts for the deployables on .NET 10: commerce, access, operations and workers, each composing its modules. Builds: `adr ADR-0055`. In **ticvai-backend**, on .NET 10 LTS (decided 30 September; ADR-0055). Four .NET hosts in one solution: commerce (Identity, Tenancy, Catalogue, Order, Ledger, Wallet), access (Access), operations (F&B, Retail, Inventory, VenueOps, Marketing, WhiteLabel, Reporting, Platform, CrossRegion) and workers (the outbox relay, every module's event consumers, scheduled jobs), each composing its modules through IModule. ticvai-ai stays the Python service. Done when: each host starts locally with its modules registered and a health endpoint, CI builds one image per host, and moving a module to another host is a change of one registration.
2 | 1 | SETUP-QDRANT | AM-FOUNDATION-SETUP | [BE] Qdrant cluster in dev and staging: 3 nodes, TLS, snapshots, monitoring | 3 | Hrushikant Patkar |  | SETUP-ENV | Qdrant cluster in dev and staging: 3 nodes, TLS, snapshots, monitoring. Builds: `adr ADR-0049`, `adr ADR-0021`. In **ticvai-infra** (Terraform): a self-hosted 3-node Qdrant cluster in Azure UAE North for dev and staging (ADR-0049), pinned to 1.16 or later, with TLS, JWT RBAC on and the signing key in the cell's Key Vault, snapshot storage in the UAE, and monitoring and alerts on node health, disk and latency. Check Qdrant Hybrid Cloud on our own AKS as an alternative before building. Done when: the cluster survives the loss of one node, a snapshot of a test collection restores into a fresh cluster, and a request without a valid token is refused.
3 | 1 | MIG-BASELINE | AM-FOUNDATION-DATABASE | [DB] Migration V0001__baseline.sql: schemas, extensions, migration register, RLS helper functions and the monthly partition helpers (ADR-0056) | 3 | Hrushikant Patkar |  | SETUP-DB | Tables: platform.schema_version. Source DDL: backend/tenant/000-schemas.sql, 001-extensions.sql, 002-migration-register.sql, the helper functions at the top of 920-row-level-security.sql and 930-partitioning.sql; the control database's own 000-002. Everything else in the MIG epic runs after this. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. The baseline file named in the subject is one you write in our repository; the package keeps no baseline file of its own. It creates the helper functions every later migration calls, copied as they are from the top of 920-row-level-security.sql: platform.current_scope_paths, platform.in_scope, platform.rls_policy_name, platform.apply_scope_rls, platform.apply_shared_scope_rls, platform.venue_in_scope, platform.apply_venue_rls, platform.apply_parent_rls, platform.tenant_root_in_scope, platform.subject_in_scope, platform.apply_tenant_rls, platform.apply_subject_rls; from the top of 930-partitioning.sql: platform.uuidv7_floor, platform.ensure_month_partition, platform.ensure_month_partitions (the row-level security of each schema migration calls the platform.apply_* functions, so they come first). Done when the migration for `platform.schema_version` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
4 | 1 | MIG-CONTROL | AM-FOUNDATION-DATABASE | [DB] Migration V0002__control.sql: control (19 tables) | 8 | Hrushikant Patkar | PlatformService | MIG-BASELINE | Control database. Tables: control.api_client, control.api_licence, control.api_version, control.cell_tenant, control.content_block, control.developer_account, control.developer_member, control.integration_listing, control.licence_add_on, control.licence_add_on_limit, control.outbox_relay, control.partner, control.partner_agreement, control.partner_application, control.partner_change_request, control.production_access_request, control.seo_metadata, control.tenant, control.url_redirect. Source DDL: backend/control/010-control.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `control.api_client`, `control.api_licence`, `control.api_version`, `control.cell_tenant`, `control.content_block`, `control.developer_account`, `control.developer_member`, `control.integration_listing` and 11 more runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
4 | 1 | MIG-KERNEL | AM-FOUNDATION-DATABASE | [DB] Migration V0003__kernel.sql: kernel (1 tables) | 1 | Hrushikant Patkar | TenancyService | MIG-BASELINE | Tenant database. Tables: kernel.inbox. Source DDL: backend/tenant/010-kernel.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `kernel.inbox` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
4 | 1 | MIG-PARTITIONS | AM-FOUNDATION-DATABASE | [DB] Monthly partitions: create three months ahead, detach what retention has expired | 3 | Hrushikant Patkar |  | MIG-BASELINE SETUP-HOSTS | Monthly partitions: create three months ahead, detach what retention has expired. Builds: `table access.scan_event`, `table kernel.inbox`, `table ledger.journal_line`, `table marketing.message_dispatch`, `table platform.audit_record`, `table platform.dead_letter`, `table platform.outbox`, `adr ADR-0044`, `adr ADR-0047`, `adr ADR-0056`. A job in the workers host that keeps monthly range partitions three months ahead on the time-partitioned tables (access.scan_event, platform.outbox, platform.dead_letter, platform.audit_record, ledger.journal_line, marketing.message_dispatch, kernel.inbox; ADR-0056) in every tenant database, and detaches and archives partitions past their retention (ADR-0047). Source DDL: backend/tenant/930-partitioning.sql (the monthly partitions and default partitions of the time-partitioned tables; its helper functions platform.uuidv7_floor, platform.ensure_month_partition and platform.ensure_month_partitions are already in the baseline, MIG-BASELINE). Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when: a new tenant database has partitions three months ahead, a run with the clock moved forward creates the next month, and an expired partition is detached, not deleted row by row.
4 | 1 | MIG-PII | AM-FOUNDATION-DATABASE | [DB] Migration V0007__pii.sql: pii (5 tables) | 3 | Hrushikant Patkar | IdentityService | MIG-BASELINE | Tenant database. Tables: pii.consent_identifier, pii.subject, pii.subject_biometric, pii.subject_contact, pii.subject_document. Source DDL: backend/tenant/010-pii.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (2) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `pii.consent_identifier`, `pii.subject`, `pii.subject_biometric`, `pii.subject_contact`, `pii.subject_document` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
4 | 1 | MIG-SUBSCRIPTION | AM-FOUNDATION-DATABASE | [DB] Migration V0005__subscription.sql: subscription (5 tables) | 3 | Hrushikant Patkar | PlatformService | MIG-BASELINE | Tenant database. Tables: subscription.contract, subscription.module_listing, subscription.plan, subscription.plan_limit, subscription.plan_module. Source DDL: backend/tenant/010-subscription.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (1) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `subscription.contract`, `subscription.module_listing`, `subscription.plan`, `subscription.plan_limit`, `subscription.plan_module` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
4 | 1 | MIG-TENANCY | AM-FOUNDATION-DATABASE | [DB] Migration V0004__tenancy.sql: tenancy (1 tables) | 1 | Hrushikant Patkar | TenancyService | MIG-BASELINE | Tenant database. Tables: tenancy.device_assignment. Source DDL: backend/tenant/010-tenancy.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `tenancy.device_assignment` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
4 | 1 | MIG-TRANSPORT | AM-FOUNDATION-DATABASE | [DB] Migration V0006__transport.sql: transport (12 tables) | 8 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE | Tenant database. Tables: transport.departure, transport.fare_matrix_cell, transport.fare_passenger_type, transport.fare_table, transport.favourite_route, transport.network_import, transport.pass_type, transport.route, transport.route_stop, transport.station, transport.timetable, transport.timetable_run. Source DDL: backend/tenant/010-transport.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (1) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `transport.departure`, `transport.fare_matrix_cell`, `transport.fare_passenger_type`, `transport.fare_table`, `transport.favourite_route`, `transport.network_import`, `transport.pass_type`, `transport.route` and 4 more runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
4 | 1 | DB-READ-VIEWS | AM-FOUNDATION-DATABASE | [BE] Published read views for cross-module reads, generated from the lineage | 5 | Hrushikant Patkar |  | MIG-BASELINE | Published read views for cross-module reads, generated from the lineage. Builds: `adr ADR-0055`, `adr ADR-0016`. A deriver reads handoff/api-data-lineage.json and generates, per owning module, the views other modules may read (894 cross-schema reads on 30 September; ADR-0055), applied by the migrations. Done when: every cross-schema read in the Block A slice goes through a published view, the views regenerate with one command, and a raw cross-schema read is reported by the lineage check. Spec (4 October, CHG-FXP-005), ADR-0055 rule 2: another module reads a schema only through views its owner publishes (or the owner's in-process query interface), never raw tables; the owner is the schema's module in handoff/service-decomposition.json. Default for the shape: one view per (reader module, owned table) pair the lineage actually reads, in the owner's schema, named `<table>_for_<reader module>`, exposing only the columns the reader's operations read, with SELECT granted to the reader's deployable role (DB-ROLES). Reads routed `analytical` go to the reporting replica, never the primary (ADR-0016).
4 | 1 | DB-ROLES | AM-FOUNDATION-DATABASE | [BE] One Postgres role per deployable; the AI role read-only | 2 | Hrushikant Patkar |  | MIG-BASELINE | One Postgres role per deployable; the AI role read-only. Builds: `adr ADR-0055`, `adr ADR-0020`. In ticvai-backend, created by the baseline migration (MIG-BASELINE), one PostgreSQL login role per deployable of ADR-0055: commerce, access, operations, workers and ticvai_ai, each reading its password or token from the cell's Key Vault. Each role gets USAGE and SELECT, INSERT, UPDATE, DELETE on the schemas its modules own (the schema owners in handoff/service-decomposition.json; workers runs every module's consumers, the outbox relay and the scheduled jobs, so it gets the schemas those touch), SELECT on the published read views of DB-READ-VIEWS, and nothing else: no CREATE, no ownership, no BYPASSRLS, so FORCE row-level security applies to every host. ticvai_ai writes only the ai schema (and ai.inbox; ADR-0058) and is read-only on the transactional schemas (ADR-0020). The tables are owned by a separate migration role that only SqlMigrationRunner uses. Done when: each host connects with its own role from Key Vault; an INSERT from the ticvai_ai role into a transactional table, and from the commerce role into an operations schema (fnb), are each refused by PostgreSQL; no host role has BYPASSRLS or owns a table (a query on pg_roles and pg_tables in CI shows it); and a host role with no scope set on its session reads no rows from a table under FORCE row-level security. The schemas each role owns (handoff/service-decomposition.json under ADR-0055's five deployables, 4 October, CHG-FXP-005): commerce: identity, pii, platform, workforce, approvals, accreditation, tenancy, kernel, catalogue, pricing, promotions, seating, orders, payments, ledger, wallet; access: access; operations: inventory, fnb, retail, marketing, queue, maintenance, resources, venuemap, assets, games, rental, transport, subscription, whitelabel, reporting, sync (and control, in the control database, ADR-0039); ticvai_ai: ai (and ai.inbox), read-only on the rest; workers: the schemas its consumers, the outbox relay and the scheduled jobs write, which is every module's.
5 | 1 | MIG-GAMES | AM-FOUNDATION-DATABASE | [DB] Migration V0008__games.sql: games (2 tables) | 2 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE MIG-PII | Tenant database. Tables: games.card, games.credit_ledger. Source DDL: backend/tenant/010-games.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (1) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `games.card`, `games.credit_ledger` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
5 | 1 | MIG-IDENTITY | AM-FOUNDATION-DATABASE | [DB] Migration V0009__identity.sql: identity (18 tables) | 8 | Hrushikant Patkar | IdentityService | MIG-BASELINE MIG-PII | Tenant database. Tables: identity.capability_template, identity.delegated_access, identity.guest_credential, identity.guest_identity_verification, identity.guest_verification_policy, identity.mfa_challenge, identity.mfa_method, identity.mfa_recovery_code, identity.otp_challenge, identity.password_policy, identity.platform_staff_grant, identity.principal, identity.principal_credential, identity.refresh_token, identity.role, identity.role_permission, identity.segregation_rule, identity.session. Source DDL: backend/tenant/010-identity.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (2) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `identity.capability_template`, `identity.delegated_access`, `identity.guest_credential`, `identity.guest_identity_verification`, `identity.guest_verification_policy`, `identity.mfa_challenge`, `identity.mfa_method`, `identity.mfa_recovery_code` and 10 more runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
6 | 1 | MIG-APPROVALS | AM-FOUNDATION-DATABASE | [DB] Migration V0010__approvals.sql: approvals (6 tables) | 5 | Hrushikant Patkar | TenancyService | MIG-BASELINE MIG-IDENTITY | Tenant database. Tables: approvals.decision, approvals.delegation, approvals.external_provider, approvals.matrix, approvals.request, approvals.rule. Source DDL: backend/tenant/010-approvals.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `approvals.decision`, `approvals.delegation`, `approvals.external_provider`, `approvals.matrix`, `approvals.request`, `approvals.rule` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
6 | 1 | MIG-ASSETS | AM-FOUNDATION-DATABASE | [DB] Migration V0013__assets.sql: assets (7 tables) | 5 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE MIG-IDENTITY | Tenant database. Tables: assets.asset_version, assets.media_asset, assets.media_collection, assets.media_collection_member, assets.media_fingerprint, assets.media_upload, assets.media_usage. Source DDL: backend/tenant/010-assets.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (2) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `assets.asset_version`, `assets.media_asset`, `assets.media_collection`, `assets.media_collection_member`, `assets.media_fingerprint`, `assets.media_upload`, `assets.media_usage` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
6 | 1 | MIG-REPORTING | AM-FOUNDATION-DATABASE | [DB] Migration V0011__reporting.sql: reporting (15 tables) | 8 | Hrushikant Patkar | ReportingService | MIG-BASELINE MIG-IDENTITY | Tenant database. Tables: reporting.alert, reporting.alert_rule, reporting.dashboard, reporting.dashboard_tile, reporting.dashboard_view, reporting.execution, reporting.kpi_definition, reporting.natural_language_query, reporting.report_column, reporting.report_definition, reporting.report_definition_version, reporting.report_filter, reporting.report_parameter, reporting.schedule, reporting.semantic_model. Source DDL: backend/tenant/010-reporting.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (1) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `reporting.alert`, `reporting.alert_rule`, `reporting.dashboard`, `reporting.dashboard_tile`, `reporting.dashboard_view`, `reporting.execution`, `reporting.kpi_definition`, `reporting.natural_language_query` and 7 more runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
6 | 1 | MIG-RESOURCES | AM-FOUNDATION-DATABASE | [DB] Migration V0015__resources.sql: resources (7 tables) | 5 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE MIG-IDENTITY MIG-PII | Tenant database. Tables: resources.booking, resources.resource, resources.resource_block, resources.resource_package, resources.resource_requirement, resources.resource_reservation, resources.resource_schedule. Source DDL: backend/tenant/010-resources.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (2) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `resources.booking`, `resources.resource`, `resources.resource_block`, `resources.resource_package`, `resources.resource_requirement`, `resources.resource_reservation`, `resources.resource_schedule` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
6 | 1 | MIG-SYNC | AM-FOUNDATION-DATABASE | [DB] Migration V0012__sync.sql: sync (1 tables) | 1 | Hrushikant Patkar | CrossRegionService | MIG-BASELINE MIG-IDENTITY | Tenant database. Tables: sync.rejection. Source DDL: backend/tenant/010-sync.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (1) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `sync.rejection` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
6 | 1 | MIG-WHITELABEL | AM-FOUNDATION-DATABASE | [DB] Migration V0016__whitelabel.sql: whitelabel (29 tables) | 8 | Hrushikant Patkar | WhiteLabelService | MIG-BASELINE MIG-IDENTITY | Tenant database. Tables: whitelabel.analytics_provider, whitelabel.app_build, whitelabel.banner, whitelabel.booking_flow, whitelabel.booking_flow_step, whitelabel.config_version, whitelabel.content_page, whitelabel.custom_domain, whitelabel.faq_category, whitelabel.faq_entry, whitelabel.feature_toggle, whitelabel.footer_config, whitelabel.footer_config_column, whitelabel.footer_config_social_link, whitelabel.guided_choice, whitelabel.guided_choice_answer, whitelabel.guided_choice_question, whitelabel.homepage_layout, whitelabel.homepage_section, whitelabel.module_enablement, whitelabel.navigation_config, whitelabel.navigation_item, whitelabel.policy, whitelabel.promo_block, whitelabel.publish_review_policy, whitelabel.site_package, whitelabel.site_setup_progress, whitelabel.store_account, whitelabel.tenant_config. Source DDL: backend/tenant/010-whitelabel.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (2) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/tenant/V0102__after_r1_20261013.sql (whitelabel.store_account: columns pass_type_identifier, pass_certificate_secret_ref, has_pass_certificate and pass_certificate_expires_at); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `whitelabel.analytics_provider`, `whitelabel.app_build`, `whitelabel.banner`, `whitelabel.booking_flow`, `whitelabel.booking_flow_step`, `whitelabel.config_version`, `whitelabel.content_page`, `whitelabel.custom_domain` and 21 more runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
7 | 1 | MIG-AI | AM-FOUNDATION-DATABASE | [DB] Migration V0014__ai.sql: ai (49 tables) | 8 | Hrushikant Patkar | AiService | MIG-ASSETS MIG-BASELINE MIG-IDENTITY MIG-PII | Tenant database. Tables: ai.action_plan, ai.activity, ai.anomaly_detector, ai.answer_feedback, ai.assistant_profile, ai.byok_enablement, ai.capability, ai.capability_maturity, ai.chunk_embedding, ai.conversation, ai.decision_record, ai.eval_run, ai.eval_suite, ai.forecast_accuracy, ai.forecast_definition, ai.forecast_point, ai.forecast_scenario, ai.forecast_version, ai.governance_alert, ai.governance_policy, ai.governance_policy_version, ai.guided_choice_suggestion, ai.history_import, ai.history_observation, ai.inbox, ai.incident, ai.index_entry, ai.index_job, ai.index_source, ai.insight, ai.intervention, ai.knowledge_collection, ai.knowledge_document, ai.knowledge_gap, ai.message, ai.model, ai.operational_requirement, ai.policy, ai.policy_exception, ai.prompt_template, ai.proposed_action, ai.provider, ai.rec_decision, ai.rec_decline, ai.rec_event, ai.release, ai.suggestion, ai.training_run, ai.venue_settings. Source DDL: backend/tenant/010-ai.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (2) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `ai.action_plan`, `ai.activity`, `ai.anomaly_detector`, `ai.answer_feedback`, `ai.assistant_profile`, `ai.byok_enablement`, `ai.capability`, `ai.capability_maturity` and 41 more runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
7 | 1 | MIG-PLATFORM | AM-FOUNDATION-DATABASE | [DB] Migration V0017__platform.sql: platform (17 tables) | 8 | Hrushikant Patkar | TenancyService | MIG-APPROVALS MIG-BASELINE MIG-IDENTITY | Tenant database. Tables: platform.audit_record, platform.denomination, platform.device, platform.device_heartbeat, platform.dsar_request, platform.guest_link, platform.idempotency_record, platform.outbox, platform.outlet, platform.region_settings, platform.sale_board, platform.sale_board_page, platform.sale_board_tile, platform.scope, platform.tenant, platform.venue_settings, platform.workstation. Source DDL: backend/tenant/010-platform.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (3) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/tenant/V0102__after_r1_20261013.sql (platform.scope: indexes scope_path_uniq, scope_parent_id_idx and scope_tenant_root_uniq; platform.venue_settings: column business_day_cutoff); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `platform.audit_record`, `platform.denomination`, `platform.device`, `platform.device_heartbeat`, `platform.dsar_request`, `platform.guest_link`, `platform.idempotency_record`, `platform.outbox` and 9 more runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
8 | 1 | SETUP-AUTH | AM-FOUNDATION-SETUP | [DevOps] Sign-in working end to end against IdentityService | 5 | Pranay Shinde |  | MIG-BASELINE MIG-IDENTITY MIG-PII MIG-PLATFORM | Sign-in working end to end against IdentityService. Builds: `operation login`, `operation refreshToken`, `operation logout`, `operation getCurrentSession`. The staff sign-in path of contracts/spine/identity.yaml: `login` issues the session and refresh token, `getCurrentSession` returns the Session with `effectivePermissions` and `permissionsByScope` (the effective permissions the done-when reads), `refreshToken` and `logout` end the loop; the operations themselves are built on their IdentityService tickets, this task wires them through the host. In **ticvai-backend** and **ticvai-frontend**: the identity sign-in operations, `ICurrentPrincipal` and `ITenantContext` filled from the session, signing keys from the cell's Azure Key Vault (audit R057). Done when: a seeded staff member signs in from a web app and an app, gets their effective permissions, and a request without a session gets 401.
8 | 1 | MIG-MAINTENANCE | AM-FOUNDATION-DATABASE | [DB] Migration V0020__maintenance.sql: maintenance (6 tables) | 5 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE MIG-IDENTITY MIG-PLATFORM | Tenant database. Tables: maintenance.asset, maintenance.incident, maintenance.inspection, maintenance.inspection_template, maintenance.inspection_template_item, maintenance.work_order. Source DDL: backend/tenant/010-maintenance.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (2) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `maintenance.asset`, `maintenance.incident`, `maintenance.inspection`, `maintenance.inspection_template`, `maintenance.inspection_template_item`, `maintenance.work_order` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
8 | 1 | MIG-SEATING | AM-FOUNDATION-DATABASE | [DB] Migration V0019__seating.sql: seating (11 tables) | 5 | Hrushikant Patkar | CatalogueService | MIG-ASSETS MIG-BASELINE MIG-IDENTITY MIG-PII MIG-PLATFORM | Tenant database. Tables: seating.accessible, seating.recommendation_rule, seating.seat, seating.seat_block, seating.seat_block_item, seating.seat_category, seating.seat_map, seating.seat_price_band, seating.seat_reservation, seating.seat_reservation_item, seating.section. Source DDL: backend/tenant/010-seating.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (2) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/tenant/V0102__after_r1_20261013.sql (seating.seat: index seat_seat_map_id_section_code_row_label_seat_number_uniq; seating.seat_category: index seat_category_venue_id_code_uniq; seating.seat_price_band: index seat_price_band_seat_category_id_code_uniq); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `seating.accessible`, `seating.recommendation_rule`, `seating.seat`, `seating.seat_block`, `seating.seat_block_item`, `seating.seat_category`, `seating.seat_map`, `seating.seat_price_band` and 3 more runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
8 | 1 | MIG-WALLET | AM-FOUNDATION-DATABASE | [DB] Migration V0021__wallet.sql: wallet (22 tables) | 8 | Hrushikant Patkar | WalletService | MIG-BASELINE MIG-IDENTITY MIG-PII MIG-PLATFORM | Tenant database. Tables: wallet.accounting_mapping, wallet.authentication_policy, wallet.auto_reload_setting, wallet.balance, wallet.channel_rule, wallet.configuration_version, wallet.configuration_version_snapshot, wallet.consumption_policy, wallet.credit_lot, wallet.credit_type, wallet.exit_settlement, wallet.fund_reservation, wallet.funding_rule, wallet.gift_card, wallet.integration_mapping, wallet.reconciliation_source, wallet.refund_policy, wallet.risk_rule_set, wallet.transfer_rule, wallet.wallet, wallet.wallet_transaction, wallet.wallet_type. Source DDL: backend/tenant/010-wallet.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (2) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `wallet.accounting_mapping`, `wallet.authentication_policy`, `wallet.auto_reload_setting`, `wallet.balance`, `wallet.channel_rule`, `wallet.configuration_version`, `wallet.configuration_version_snapshot`, `wallet.consumption_policy` and 14 more runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
8 | 1 | MIG-WORKFORCE | AM-FOUNDATION-DATABASE | [DB] Migration V0018__workforce.sql: workforce (3 tables) | 2 | Hrushikant Patkar | TenancyService | MIG-BASELINE MIG-IDENTITY MIG-PLATFORM | Tenant database. Tables: workforce.attendance, workforce.attendance_amendment, workforce.rota_assignment. Source DDL: backend/tenant/010-workforce.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (1) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `workforce.attendance`, `workforce.attendance_amendment`, `workforce.rota_assignment` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
9 | 1 | MIG-CATALOGUE | AM-FOUNDATION-DATABASE | [DB] Migration V0022__catalogue.sql: catalogue (23 tables) | 8 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-IDENTITY MIG-PII MIG-PLATFORM MIG-SEATING | Tenant database. Tables: catalogue.alternative_code, catalogue.channel_capacity, catalogue.channel_envelope, catalogue.entitlement_template, catalogue.event, catalogue.event_capacity_profile, catalogue.event_registration, catalogue.event_resource_plan, catalogue.event_schedule, catalogue.group_package, catalogue.import_job, catalogue.inventory_reservation, catalogue.performance, catalogue.price, catalogue.price_list, catalogue.product, catalogue.product_category, catalogue.product_eligibility_rule, catalogue.product_media, catalogue.product_version, catalogue.published_bundle, catalogue.variant, catalogue.waitlist_entry. Source DDL: backend/tenant/010-catalogue.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (3) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/tenant/V0101__after_r1_20261006.sql (catalogue.performance: column minutes_on_screen; catalogue.product: columns name_localised and description_localised); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Source DDL after r1: backend/tenant/V0102__after_r1_20261013.sql (catalogue.product_media: column product_id, constraint product_media_product_id_fkey, index product_media_product_id_idx); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `catalogue.alternative_code`, `catalogue.channel_capacity`, `catalogue.channel_envelope`, `catalogue.entitlement_template`, `catalogue.event`, `catalogue.event_capacity_profile`, `catalogue.event_registration`, `catalogue.event_resource_plan` and 15 more runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
10 | 1 | MIG-LEDGER | AM-FOUNDATION-DATABASE | [DB] Migration V0023__ledger.sql: ledger (18 tables) | 8 | Hrushikant Patkar | LedgerService | MIG-BASELINE MIG-CATALOGUE MIG-IDENTITY MIG-PLATFORM | Tenant database. Tables: ledger.account, ledger.cost_center, ledger.credit_memo, ledger.credit_memo_line, ledger.einvoice_transmission, ledger.einvoicing_provider, ledger.fiscal_period, ledger.fx_provider_assignment, ledger.fx_rate, ledger.journal_entry, ledger.journal_line, ledger.legal_entity, ledger.posting, ledger.price_variance, ledger.tax_code, ledger.tax_invoice, ledger.tax_invoice_line, ledger.tax_invoice_template. Source DDL: backend/tenant/010-ledger.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (2) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/tenant/V0102__after_r1_20261013.sql (ledger.account: index account_code_uniq; ledger.credit_memo: index credit_memo_credit_memo_number_uniq; ledger.journal_entry: index journal_entry_entry_number_uniq; ledger.tax_code: index tax_code_code_uniq; ledger.tax_invoice: index tax_invoice_invoice_number_uniq); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `ledger.account`, `ledger.cost_center`, `ledger.credit_memo`, `ledger.credit_memo_line`, `ledger.einvoice_transmission`, `ledger.einvoicing_provider`, `ledger.fiscal_period`, `ledger.fx_provider_assignment` and 10 more runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 1 | MIG-INVENTORY | AM-FOUNDATION-DATABASE | [DB] Migration V0024__inventory.sql: inventory (12 tables) | 8 | Hrushikant Patkar | InventoryService | MIG-BASELINE MIG-IDENTITY MIG-LEDGER MIG-PLATFORM | Tenant database. Tables: inventory.goods_receipt, inventory.goods_receipt_line, inventory.inventory_item, inventory.kit_component, inventory.location, inventory.movement, inventory.purchase_order, inventory.requisition, inventory.serialised_item, inventory.stock_batch, inventory.stock_earmark, inventory.supplier. Source DDL: backend/tenant/010-inventory.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `inventory.goods_receipt`, `inventory.goods_receipt_line`, `inventory.inventory_item`, `inventory.kit_component`, `inventory.location`, `inventory.movement`, `inventory.purchase_order`, `inventory.requisition` and 4 more runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 1 | MIG-PROMOTIONS | AM-FOUNDATION-DATABASE | [DB] Migration V0025__promotions.sql: promotions (16 tables) | 8 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-LEDGER MIG-PII MIG-PLATFORM | Tenant database. Tables: promotions.allocation_component, promotions.allocation_split, promotions.bundle, promotions.bundle_choice_group, promotions.bundle_choice_option, promotions.bundle_component, promotions.code_assignment, promotions.coupon_campaign, promotions.coupon_code, promotions.coupon_code_batch, promotions.promotion, promotions.promotion_audit, promotions.promotion_channel_publication, promotions.promotion_evaluation_trace, promotions.promotion_rule, promotions.promotion_variant. Source DDL: backend/tenant/010-promotions.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (1) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/tenant/V0101__after_r1_20261006.sql (promotions.promotion: index promotion_code_uniq); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `promotions.allocation_component`, `promotions.allocation_split`, `promotions.bundle`, `promotions.bundle_choice_group`, `promotions.bundle_choice_option`, `promotions.bundle_component`, `promotions.code_assignment`, `promotions.coupon_campaign` and 8 more runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
12 | 1 | MIG-ORDERS | AM-FOUNDATION-DATABASE | [DB] Migration V0026__orders.sql: orders (39 tables) | 8 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-CATALOGUE MIG-IDENTITY MIG-LEDGER MIG-PII MIG-PLATFORM MIG-PROMOTIONS | Tenant database. Tables: orders.cart, orders.cart_line, orders.cash_count_line, orders.cash_movement, orders.deposit_box, orders.deposit_box_foreign_holding, orders.deposit_box_opening_denomination, orders.fraud_rule, orders.group_booking, orders.group_customer_organisation, orders.group_customer_organisation_contact, orders.group_participant, orders.group_participant_list, orders.group_visit_plan, orders.invitation, orders.no_sale_event, orders.order_event, orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.payment, orders.payment_link, orders.pos_shift, orders.pos_shift_approval, orders.pos_shift_incident, orders.refund, orders.refund_policy, orders.refund_policy_time_band, orders.resale_listing, orders.reservation, orders.reservation_line, orders.sales_order, orders.stored_value_authorisation, orders.ticket_template, orders.ticket_template_channel, orders.ticket_transfer, orders.till_shift_policy, orders.visit_reminder, orders.wallet_pass. Source DDL: backend/tenant/010-orders.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Its keys into schemas created later (2) go in MIG-FOREIGN-KEYS. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/tenant/V0102__after_r1_20261013.sql (orders.pos_shift: column business_date; orders.sales_order: column channel_profile_id, index sales_order_order_number_uniq); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `orders.cart`, `orders.cart_line`, `orders.cash_count_line`, `orders.cash_movement`, `orders.deposit_box`, `orders.deposit_box_foreign_holding`, `orders.deposit_box_opening_denomination`, `orders.fraud_rule` and 31 more runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
13 | 1 | MIG-ACCESS | AM-FOUNDATION-DATABASE | [DB] Migration V0027__access.sql: access (19 tables) | 8 | Hrushikant Patkar | AccessService | MIG-BASELINE MIG-CATALOGUE MIG-IDENTITY MIG-ORDERS MIG-PII MIG-PLATFORM | Tenant database. Tables: access.access_incident, access.access_point, access.access_point_group, access.admission_rules, access.biometric_audit_event, access.biometric_profile, access.blacklist, access.configuration_change, access.credential_policy, access.device_binding, access.device_placement, access.entitlement, access.entry_rule_point, access.face_reenrolment_attempt, access.gate_mode_change, access.gate_mode_policy, access.parking_entitlement, access.parking_facility, access.scan_event. Source DDL: backend/tenant/010-access.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Source DDL after r1: backend/tenant/V0102__after_r1_20261013.sql (access.entitlement: column credential_format); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `access.access_incident`, `access.access_point`, `access.access_point_group`, `access.admission_rules`, `access.biometric_audit_event`, `access.biometric_profile`, `access.blacklist`, `access.configuration_change` and 11 more runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
13 | 1 | MIG-MARKETING | AM-FOUNDATION-DATABASE | [DB] Migration V0028__marketing.sql: marketing (55 tables) | 8 | Hrushikant Patkar | MarketingService | MIG-AI MIG-BASELINE MIG-CATALOGUE MIG-IDENTITY MIG-LEDGER MIG-ORDERS MIG-PII MIG-PLATFORM | Tenant database. Tables: marketing.agent_availability, marketing.attribution_touch, marketing.booking_consent_record, marketing.campaign, marketing.campaign_target, marketing.campaign_variant, marketing.case, marketing.case_message, marketing.challenge, marketing.challenge_progress, marketing.consent_propagation, marketing.consent_purpose, marketing.consent_purpose_channel, marketing.consent_question, marketing.consent_question_version, marketing.consent_record, marketing.conversation, marketing.conversation_message, marketing.conversation_message_attachment, marketing.cookie_banner_design, marketing.customer_badge, marketing.device_consent, marketing.device_consent_category, marketing.form_definition, marketing.form_definition_field, marketing.form_submission, marketing.guest_device, marketing.guest_document, marketing.guest_preference, marketing.guest_profile, marketing.invitation, marketing.invitation_campaign, marketing.journey, marketing.lost_item, marketing.loyalty_position, marketing.loyalty_programme, marketing.loyalty_rule, marketing.message_dispatch, marketing.message_template, marketing.message_template_version, marketing.points_earning_rule, marketing.points_redemption_rule, marketing.privacy_notice_governance, marketing.programme_tier, marketing.referral, marketing.review, marketing.reward, marketing.segment, marketing.segment_criterion, marketing.subscription, marketing.tracking_technology, marketing.waiver_field_rule, marketing.waiver_requirement, marketing.waiver_requirement_event, marketing.wishlist_item. Source DDL: backend/tenant/010-marketing.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `marketing.agent_availability`, `marketing.attribution_touch`, `marketing.booking_consent_record`, `marketing.campaign`, `marketing.campaign_target`, `marketing.campaign_variant`, `marketing.case`, `marketing.case_message` and 47 more runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
14 | 1 | MIG-FNB | AM-FOUNDATION-DATABASE | [DB] Migration V0029__fnb.sql: fnb (41 tables) | 8 | Hrushikant Patkar | FnbService | MIG-ACCESS MIG-BASELINE MIG-CATALOGUE MIG-IDENTITY MIG-INVENTORY MIG-ORDERS MIG-PII MIG-PLATFORM MIG-SEATING | Tenant database. Tables: fnb.allergen_verdict, fnb.bill_split, fnb.cold_chain_event, fnb.corrective_action, fnb.course_rule, fnb.delivery_location, fnb.delivery_location_outlet, fnb.delivery_policy, fnb.dining_table, fnb.kitchen_exception, fnb.kitchen_sla, fnb.kitchen_station, fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.location_session, fnb.menu, fnb.menu_item, fnb.menu_item_modifier, fnb.menu_schedule, fnb.menu_section, fnb.menu_version, fnb.modifier_group, fnb.modifier_option, fnb.order_fulfilment, fnb.production_plan, fnb.production_plan_line, fnb.production_run, fnb.recipe, fnb.recipe_ingredient, fnb.reservation_table, fnb.service_order, fnb.service_order_line, fnb.sold_out_item, fnb.sub_bill, fnb.substitution_rule, fnb.table_combination, fnb.table_reservation, fnb.table_session, fnb.table_visit, fnb.temperature_log, fnb.waitlist_entry. Source DDL: backend/tenant/010-fnb.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `fnb.allergen_verdict`, `fnb.bill_split`, `fnb.cold_chain_event`, `fnb.corrective_action`, `fnb.course_rule`, `fnb.delivery_location`, `fnb.delivery_location_outlet`, `fnb.delivery_policy` and 33 more runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
14 | 1 | MIG-PAYMENTS | AM-FOUNDATION-DATABASE | [DB] Migration V0030__payments.sql: payments (12 tables) | 8 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-MARKETING MIG-ORDERS MIG-PII | Tenant database. Tables: payments.dunning_case, payments.dunning_policy, payments.instalment, payments.instalment_plan, payments.instalment_policy, payments.method, payments.payment_attempt, payments.provider, payments.provider_connection, payments.routing_rule, payments.stored_forward, payments.token. Source DDL: backend/tenant/010-payments.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `payments.dunning_case`, `payments.dunning_policy`, `payments.instalment`, `payments.instalment_plan`, `payments.instalment_policy`, `payments.method`, `payments.payment_attempt`, `payments.provider` and 4 more runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
14 | 1 | MIG-QUEUE | AM-FOUNDATION-DATABASE | [DB] Migration V0031__queue.sql: queue (4 tables) | 3 | Hrushikant Patkar | VenueOpsService | MIG-ACCESS MIG-BASELINE MIG-CATALOGUE MIG-MAINTENANCE MIG-PII MIG-PLATFORM | Tenant database. Tables: queue.entry, queue.queue, queue.queue_operating_window, queue.reading. Source DDL: backend/tenant/010-queue.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `queue.entry`, `queue.queue`, `queue.queue_operating_window`, `queue.reading` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
14 | 1 | MIG-VENUEMAP | AM-FOUNDATION-DATABASE | [DB] Migration V0033__venuemap.sql: venuemap (8 tables) | 5 | Hrushikant Patkar | VenueOpsService | MIG-ACCESS MIG-ASSETS MIG-BASELINE MIG-CATALOGUE MIG-MARKETING MIG-ORDERS MIG-PLATFORM MIG-PROMOTIONS MIG-RESOURCES | Tenant database. Tables: venuemap.import_job, venuemap.map, venuemap.map_version, venuemap.path, venuemap.placed_resource, venuemap.point, venuemap.visit_plan, venuemap.visit_plan_item. Source DDL: backend/tenant/010-venuemap.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `venuemap.import_job`, `venuemap.map`, `venuemap.map_version`, `venuemap.path`, `venuemap.placed_resource`, `venuemap.point`, `venuemap.visit_plan`, `venuemap.visit_plan_item` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
15 | 1 | MIG-RETAIL | AM-FOUNDATION-DATABASE | [DB] Migration V0032__retail.sql: retail (10 tables) | 5 | Hrushikant Patkar | RetailService | MIG-ACCESS MIG-BASELINE MIG-CATALOGUE MIG-FNB MIG-IDENTITY MIG-INVENTORY MIG-ORDERS MIG-PII MIG-PLATFORM | Tenant database. Tables: retail.merchandise, retail.reservation, retail.reservation_line, retail.return, retail.return_line, retail.return_policy, retail.sale, retail.sale_line, retail.shop_and_drop, retail.shop_and_drop_line. Source DDL: backend/tenant/010-retail.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. Applied forward by SqlMigrationRunner; test that it applies to a database with its Follows applied and that a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `retail.merchandise`, `retail.reservation`, `retail.reservation_line`, `retail.return`, `retail.return_line`, `retail.return_policy`, `retail.sale`, `retail.sale_line` and 2 more runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
16 | 1 | MIG-FOREIGN-KEYS | AM-FOUNDATION-DATABASE | [DB] Migration V0034__cross_schema_foreign_keys.sql (35 keys) | 2 | Hrushikant Patkar |  | MIG-ACCESS MIG-AI MIG-APPROVALS MIG-ASSETS MIG-CATALOGUE MIG-CONTROL MIG-FNB MIG-GAMES MIG-IDENTITY MIG-INVENTORY MIG-KERNEL MIG-LEDGER MIG-MAINTENANCE MIG-MARKETING MIG-ORDERS MIG-PAYMENTS MIG-PII MIG-PLATFORM MIG-PROMOTIONS MIG-QUEUE MIG-REPORTING MIG-RESOURCES MIG-RETAIL MIG-SEATING MIG-SUBSCRIPTION MIG-SYNC MIG-TENANCY MIG-TRANSPORT MIG-VENUEMAP MIG-WALLET MIG-WHITELABEL MIG-WORKFORCE | Builds: `table ai.policy`, `table ai.provider`, `table assets.media_asset`, `table assets.media_collection`, `table catalogue.entitlement_template`, `table catalogue.performance`, `table catalogue.price`, `table games.card`, `table identity.delegated_access`, `table identity.principal`, `table ledger.price_variance`, `table maintenance.asset`, `table orders.resale_listing`, `table orders.wallet_pass`, `table pii.subject_biometric`, `table platform.outlet`, `table platform.workstation`, `table promotions.coupon_code`, `table reporting.dashboard`, `table resources.booking`, `table resources.resource`, `table seating.seat_block`, `table subscription.contract`, `table sync.rejection`, `table transport.network_import`, `table wallet.wallet_transaction`, `table whitelabel.promo_block`, `table whitelabel.tenant_config`, `table workforce.attendance`. The foreign keys that point from a schema into one created after it: ai (2), assets (2), catalogue (3), games (1), identity (2), ledger (2), maintenance (2), orders (2), pii (2), platform (3), promotions (1), reporting (1), resources (2), seating (2), subscription (1), sync (1), transport (1), wallet (2), whitelabel (2), workforce (1). Each is the ALTER TABLE ... ADD CONSTRAINT line of backend/<db>/900-foreign-keys.sql with that constraint name, unchanged (each linked table's record lists its keys with ON DELETE): ai.policy(tenant_id) -> platform.tenant as policy_tenant_id_fkey; ai.provider(region_id) -> platform.scope as provider_region_id_fkey; assets.media_asset(venue_id) -> platform.scope as media_asset_venue_id_fkey; assets.media_collection(venue_id) -> platform.scope as media_collection_venue_id_fkey; catalogue.entitlement_template(admission_rules_id) -> access.admission_rules as entitlement_template_admission_rules_id_fkey; catalogue.performance(admission_rules_id) -> access.admission_rules as performance_admission_rules_id_fkey; catalogue.price(tax_code_id) -> ledger.tax_code as price_tax_code_id_fkey; games.card(venue_id) -> platform.scope as card_venue_id_fkey; identity.delegated_access(scope_id) -> platform.scope as delegated_access_scope_id_fkey; identity.principal(home_scope_id) -> platform.scope as principal_home_scope_id_fkey; ledger.price_variance(order_line_id) -> orders.order_line as price_variance_order_line_id_fkey; ledger.price_variance(venue_id,order_id) -> orders.sales_order as price_variance_venue_id_order_id_fkey; maintenance.asset(supplier_id) -> inventory.supplier as asset_supplier_id_fkey; maintenance.asset(venue_id,linked_access_point_id) -> access.access_point as asset_venue_id_linked_access_point_id_fkey; orders.resale_listing(entitlement_id) -> access.entitlement as resale_listing_entitlement_id_fkey; orders.wallet_pass(entitlement_id) -> access.entitlement as wallet_pass_entitlement_id_fkey; pii.subject_biometric(consent_purpose_id) -> marketing.consent_purpose as subject_biometric_consent_purpose_id_fkey; pii.subject_biometric(entitlement_id) -> access.entitlement as subject_biometric_entitlement_id_fkey; platform.outlet(cost_center_id) -> ledger.cost_center as outlet_cost_center_id_fkey; platform.outlet(venue_id,stock_location_id) -> inventory.location as outlet_venue_id_stock_location_id_fkey; platform.workstation(venue_id,access_point_id) -> access.access_point as workstation_venue_id_access_point_id_fkey; promotions.coupon_code(redeemed_order_id) -> orders.sales_order as coupon_code_redeemed_order_id_fkey; reporting.dashboard(venue_id) -> platform.scope as dashboard_venue_id_fkey; resources.booking(order_id) -> orders.sales_order as booking_order_id_fkey; resources.resource(venue_id) -> platform.scope as resource_venue_id_fkey; seating.seat_block(performance_id) -> catalogue.performance as seat_block_performance_id_fkey; subscription.contract(tenant_id) -> platform.tenant as contract_tenant_id_fkey; sync.rejection(workstation_id) -> platform.workstation as rejection_workstation_id_fkey; transport.network_import(source_ref) -> assets.media_asset as network_import_source_ref_fkey; wallet.wallet_transaction(order_id) -> orders.sales_order as wallet_transaction_order_id_fkey; whitelabel.promo_block(promotion_id) -> promotions.promotion as promo_block_promotion_id_fkey; whitelabel.tenant_config(tenant_id) -> platform.tenant as tenant_config_tenant_id_fkey; workforce.attendance(access_point_id) -> access.access_point as attendance_access_point_id_fkey. Source DDL: backend/tenant/900-foreign-keys.sql and backend/control/900-foreign-keys.sql (the constraints named here, nothing else from those files). Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when: after every schema migration, this one adds exactly these keys on an empty database and on the previous release's schema, a second run applies nothing, and a row pointing at a missing parent is refused.
17 | 1 | SETUP-SEED | AM-FOUNDATION-SETUP | [DevOps] Seed data: the reference fixture (two brands, three regions, AED and OMR) every test runs against | 5 | Pranay Shinde |  | MIG-ACCESS MIG-AI MIG-APPROVALS MIG-ASSETS MIG-BASELINE MIG-CATALOGUE MIG-CONTROL MIG-FNB MIG-FOREIGN-KEYS MIG-GAMES MIG-IDENTITY MIG-INVENTORY MIG-KERNEL MIG-LEDGER MIG-MAINTENANCE MIG-MARKETING MIG-ORDERS MIG-PAYMENTS MIG-PII MIG-PLATFORM MIG-PROMOTIONS MIG-QUEUE MIG-REPORTING MIG-RESOURCES MIG-RETAIL MIG-SEATING MIG-SUBSCRIPTION MIG-SYNC MIG-TENANCY MIG-TRANSPORT MIG-VENUEMAP MIG-WALLET MIG-WHITELABEL MIG-WORKFORCE | Seed data: the reference fixture (two brands, three regions, AED and OMR) every test runs against. In **ticvai-backend** `db/seed`: the reference fixture quality-gates 8 requires - two brands, three regions across two countries, AED and OMR - with products, prices, events, tills, staff, roles and denominations, so apps can be built before the Back Office setup screens exist. The denominations and roles seed from docs/active/seed-data-proposal.md (proposed, client to correct - audit R229). Done when: it loads on a migrated database, integration tests run against it, and the frontend mock server serves the same data.
3 | 1 | ARCH-TESTS | AM-FOUNDATION-PLATFORM | [BE] Architecture tests for 17 modules: no module references another, and no module's SQL names another's schema | 3 | Pranay Shinde |  | SETUP-HOSTS | Architecture tests for 17 modules: no module references another, and no module's SQL names another's schema. Builds: `adr ADR-0055`, `adr ADR-0028`. Extend tests/Ticvai.ArchitectureTests/ModuleBoundaryTests.cs from six modules to 17 (ADR-0055), and add a test that fails when a module's SQL names another module's schema other than through a published read view. Done when: a deliberate cross-module reference and a raw cross-schema query each fail the build in CI.
3 | 1 | KERNEL-ID | AM-FOUNDATION-PLATFORM | [BE] One id type: UUIDv7 from Id.New() in the kernel and in offline-core | 2 | Pranay Shinde |  | SETUP-HOSTS | One id type: UUIDv7 from Id.New() in the kernel and in offline-core. Builds: `adr ADR-0056`. Replace the kernel's ULID generator (Ticvai.Shared.Kernel Primitives/Ulid.cs) with Id.New(), a UUIDv7 Guid (RFC 9562) written big-endian so PostgreSQL's uuid order is time order (ADR-0056), and the same generator in ticvai-frontend packages/offline-core for ids created offline. Done when: ids made by the server and by an offline till sort by creation time in PostgreSQL, a .NET-to-TypeScript round-trip test agrees byte for byte, and no ULID string is generated anywhere.
3 | 1 | PLATFORM-MIGRATE | AM-FOUNDATION-PLATFORM | [BE] Migration fan-out across tenant databases, and expand-then-contract changes | 5 | Pranay Shinde |  | SETUP-DB | Migration fan-out across tenant databases, and expand-then-contract changes. Builds: `table control.migration`, `table control.migration_run`, `table control.migration_run_cell`, `table control.migration_run_tenant`, `table control.migration_plan_cell`, `adr ADR-0039`. Apply a migration to every tenant database with progress and resume, and the rule that a schema change ships in two steps so old and new code both run (SD-049). Done when: a column rename reaches three seeded tenant databases with no downtime. Spec (4 October, CHG-FXP-005), ADR-0039 section 3: the fan-out unit is a tenant database and the canary is a tenant inside a canary cell; one `control.migration_run_tenant` row per tenant per run (status, from_version, to_version, error, timings), with `control.migration_run_cell` as the rollup; `control.migration_plan_cell` names all tenants of a cell or a named set. A failed tenant stops its wave and is resumed from its row; tenants already done stay done.
3 | 1 | PLATFORM-OBSERVE | AM-FOUNDATION-PLATFORM | [BE] Observability with tenant and venue on every trace, and the first dashboards | 5 | Pranay Shinde |  | SETUP-OBS | Observability with tenant and venue on every trace, and the first dashboards. Builds: `operation orders#createOrder`, `operation orders#createPayment`, `operation orders#syncOrders`, `operation access#syncScans`, `operation access#validateAccess`. OpenTelemetry attributes for tenant, venue and workstation; dashboards for the sale path and sync; alerts on error rate and latency (SD-048). Done when: a failed POS sale can be found by venue and till within a minute. Spec (4 October, CHG-FXP-005), docs/architecture/observability.md: every log, metric and span carries tenant_id, region_id and venue_id (plus cell, correlation and session id on traces, and workstation on POS metrics), set by the kernel from the resolved session and the workstation. The sale path is the operations linked here (createOrder and createPayment in OrderService, validateAccess in AccessService); sync is syncOrders and syncScans. The first alerts are that document's list (outbox backlog per device, replication lag per cell, PgBouncer pool saturation, Redis-Postgres capacity divergence, the venue edge heartbeat) on the stack SETUP-OBS sets up.
9 | 1 | PLATFORM-KERNEL | AM-FOUNDATION-PLATFORM | [BE] Request kernel: hostname to tenant routing, per-transaction scope, error model and 429 | 8 | Pranay Shinde |  | SETUP-AUTH SETUP-DB | Request kernel: hostname to tenant routing, per-transaction scope, error model and 429. Builds: `table control.tenant_domain`, `table control.tenant`, `table control.cell_tenant`, `table platform.scope`, `adr ADR-0038`, `adr ADR-0039`, `adr ADR-0005`. In ticvai-backend. Resolve the tenant from the hostname (control-plane routing table, SD-021), open every transaction with the tenant and scope settings the row-level policies read (SD-059), one problem-details error model, and 429 with Retry-After on the hot public operations (SD-043). Done when: two seeded tenants on two hostnames cannot read each other's rows, and a flood test returns 429 instead of 500. Spec (4 October, CHG-FXP-005): the routing table is `control.tenant_domain` (hostname, verified, redirect) in the control database, joined to `control.tenant` and `control.cell_tenant` for the tenant's cell and database (ADR-0038: one database per tenant inside its region's cell; ADR-0039: `control` is a database of its own and `control.cell` has no tenant_id, the relation is `control.cell_tenant`). The row-level policies of backend/tenant/920-row-level-security.sql read two session settings, set with SET LOCAL at the start of every transaction from the resolved session: `ticvai.scope_paths` (the comma-separated ltree scope paths the principal may see; unset or empty means no rows) and `ticvai.subject_id` (the guest's own rows). Venues stay partitions of the tenant database (ADR-0005), not databases.
10 | 1 | KERNEL-TENANT-LIMITS | AM-FOUNDATION-PLATFORM | [BE] Per-tenant request budgets: a token bucket per tenant and audience, and a load-aware share per replica | 3 | Pranay Shinde |  | PLATFORM-KERNEL | Per-tenant request budgets: a token bucket per tenant and audience, and a load-aware share per replica. Builds: `operation subscription#getPlan`, `adr ADR-0032`, `adr ADR-0064`. ADR-0064 (accepted 1 October), in the kernel middleware of the commerce, access and operations hosts: a token bucket per tenant and audience (guest/public, staff, service, partner) with counts shared through Azure Managed Redis, sustained rate and a 2x burst for 10 seconds from the tenant's plan (Plan.requestLimits) or the platform default; one tenant held to 25% of a replica's request slots only while the replica is above 70% of its limit; shedding guest and public first, staff and service last (ADR-0032); 429 with Retry-After and the RateLimit-* headers; if Redis is unavailable each replica falls back to its own in-process buckets (the limit divided by the replica count). Done when: in a test with two tenants on one replica, the busy tenant gets the whole replica while the other is quiet, is held to 25% of the slots once the replica passes 70% while the quiet tenant's requests still succeed, a guest burst never spends a till's staff budget, and stopping Redis leaves requests served under the in-process limits. Contract (4 October, CHG-FXP-005): the plan's limits are `Plan.requestLimits` in contracts/satellite/subscription.yaml (read with `subscription#getPlan`); the refusal is the shared `rate-limited` problem (429) of contracts/shared/common.yaml with `Retry-After` and the RateLimit-Limit, RateLimit-Remaining and RateLimit-Reset headers it defines.
10 | 1 | PLATFORM-AUDIT | AM-FOUNDATION-PLATFORM | [BE] Audit interceptor for every write | 3 | Pranay Shinde |  | PLATFORM-KERNEL | Audit interceptor for every write. Builds: `table platform.audit_record`. Who, what, when, tenant and venue for every write, written once by an interceptor rather than per operation (SD-057). Done when: any write in the Block A slice leaves one audit row a support user can read.
10 | 1 | PLATFORM-FLAGS | AM-FOUNDATION-PLATFORM | [BE] Release flags per tenant | 2 | Hrushikant Patkar |  | PLATFORM-KERNEL | Release flags per tenant. Half-built features stay dark per tenant between sprints (SD-051). Spec (default taken 4 October, CHG-FXP-005; for the lead to confirm): flags live in Azure App Configuration in the cell's region, read by every .NET host through Microsoft.FeatureManagement with a tenant targeting filter; a flag's key is an app-module key of the plan (for example `AM-MARKETING-CRM-P01`) and covers that app-module's screens and the operations they bind (their `apis` in screens/*.yaml). Off for a tenant: the apps leave its screens out of that tenant's navigation, and the kernel answers its operations with the shared 404 problem of contracts/shared/common.yaml, as if absent. Done when: with one app-module's flag off for tenant A only, A's guest web no longer shows that module's screens and its operations return 404 for A, while tenant B still sees and calls them; switching it back on restores A within a minute.
10 | 1 | PLATFORM-IDEMPOTENCY | AM-FOUNDATION-PLATFORM | [BE] Durable idempotency: the Idempotency-Key store and middleware | 5 | Pranay Shinde |  | PLATFORM-KERNEL | Durable idempotency: the Idempotency-Key store and middleware. Builds: `table platform.idempotency_record`. Idempotency records in PostgreSQL with Redis as a cache only (SD-024), so a retried payment or sale after a restart returns the first answer. Done when: replaying a createOrder with the same key after a service restart returns the original response and creates nothing.
10 | 1 | PLATFORM-OUTBOX | AM-FOUNDATION-PLATFORM | [BE] Outbox, relay and inbox behind the kernel broker interface, on a local RabbitMQ | 8 | Pranay Shinde |  | PLATFORM-KERNEL SETUP-HOSTS | Outbox, relay and inbox behind the kernel broker interface, on a local RabbitMQ. Builds: `table platform.outbox`, `table kernel.inbox`, `table platform.dead_letter`, `table control.outbox_relay`, `adr ADR-0033`, `adr ADR-0057`, `adr ADR-0058`. The transactional outbox per tenant database; one relay per region in the workers host, with a lease and a polling loop per tenant database, and an inbox per tenant database for exactly-once handling (ADR-0058); modules enqueue through IOutbox inside their own transaction, the relay publishes through IBrokerPublisher and consumers subscribe through IEventSubscriber (ADR-0058 amendment, 1 October); the relay drains a full batch at once and its batch size is configuration (Relay:BatchSize, 1,000 in the flash-sale environment). The broker per ADR-0057 is the client's choice between RabbitMQ and Kafka: build behind the kernel interface on a local RabbitMQ until they answer, with ordering per aggregate by an ordering key and dead letters drained into platform.dead_letter. A relay-lag dashboard and alert per tenant database (SD-030, SD-031, SD-032). Done when: an event written in a transaction reaches its consumer once, survives a relay restart and a redelivery, a poison message lands in platform.dead_letter, and relay lag shows on the dashboard and alerts when unpublished rows are older than 60 seconds.
10 | 1 | PLATFORM-RLS | AM-FOUNDATION-PLATFORM | [BE] Row-level policies without a per-row subquery on hot tables | 3 | Hrushikant Patkar |  | PLATFORM-KERNEL | Row-level policies without a per-row subquery on hot tables. Builds: `table orders.sales_order`, `table access.scan_event`, `table platform.scope`, `adr ADR-0005`, `adr ADR-0044`. Scope predicates read session settings instead of joining per row (SD-016). Done when: the order and scan-event queries keep their plan with policies on, measured on the seed data. Spec (4 October, CHG-FXP-005): the policies are generated in backend/tenant/920-row-level-security.sql by `platform.apply_scope_rls` and its siblings; today each USING clause calls `platform.in_scope(scope_path)`, which unnests `ticvai.scope_paths` for every row. On the hot tables (the order and scan-event tables linked here, partitioned by venue_id with venue_id leading the key: ADR-0044, ADR-0005), rewrite the predicate so the planner evaluates the session setting once per statement (an InitPlan over `platform.current_scope_paths()`, or a `venue_id = ANY(...)` predicate that keeps partition pruning) instead of per row; the policy names and deny-by-default stay. Measured with EXPLAIN (ANALYZE) on the seed data before and after.
11 | 1 | PLATFORM-PAYMENTS | AM-FOUNDATION-PLATFORM | [BE] Payment adapter and signed webhook against the provider's test mode | 8 | Hrushikant Patkar |  | PLATFORM-OUTBOX | Payment adapter and signed webhook against the provider's test mode. Builds: `operation payments#receivePaymentProviderWebhook`, `table payments.provider_event`. The provider adapter, the inbound signed webhook, the provider reference on payments, 3-D Secure redirect states and the card-terminal flow for the POS (SD-034). Done when: an approved, a declined and a 3-D Secure payment each end in the right order state from the webhook alone, with polling only as the fallback. Acceptance of the declined, unknown and reconcile paths waits on the client's payment sandbox credentials: see the client's answer in the Decisions Register. Until the client's sandbox credentials arrive (CLIENT-PAY-SANDBOX), the three outcomes are proven with signed webhook fixtures built from the provider's documented test payloads and a locally generated signing secret (CHG-FXP-006); the run against the provider's test mode follows when they arrive and is the acceptance of those paths.
11 | 1 | PLATFORM-REPUBLISH | AM-FOUNDATION-PLATFORM | [BE] Republish from the outbox by tenant and time range | 3 | Hrushikant Patkar |  | PLATFORM-OUTBOX | Republish from the outbox by tenant and time range. Builds: `operation platform-ops#republishOutbox`, `operation platform-ops#getOutboxRepublish`, `operation platform-ops#listOutboxRepublishes`, `operation platform-ops#cancelOutboxRepublish`, `table control.outbox_republish`, `adr ADR-0058`. The recovery path for a lost broker (ADR-0058 amendment, 1 October; the DR design in ADR-0060 relies on it): republishOutbox, listOutboxRepublishes, getOutboxRepublish and cancelOutboxRepublish in the operations host, carried out by the relay in workers with a keyset cursor over the outbox, published_at left untouched and live batches first; one job per tenant (control.outbox_republish). Done when: after a simulated broker loss, a republish of one tenant's last hour redelivers every event once to each consumer, the inbox drops the duplicates, and a second request for the same tenant while one runs is refused with 409.
11 | 1 | PLATFORM-SAGA-PAID | AM-FOUNDATION-PLATFORM | [BE] Order paid to tickets issued: the saga proven end to end | 5 | Hrushikant Patkar |  | PLATFORM-OUTBOX | Order paid to tickets issued: the saga proven end to end. Builds: `operation orders#createPayment`, `operation catalogue#convertInventoryHold`, `operation access#issueOrderEntitlements`, `table access.entitlement`, `table catalogue.inventory_hold`, `table catalogue.channel_capacity`, `table ledger.journal_entry`, `table ledger.journal_line`, `adr ADR-0055`, `adr ADR-0058`. order.paid consumed by the entitlement owner, tickets issued, the ledger posting once from the event, and holds converted with capacity decremented (SD-026, SD-023). Done when: a web purchase in the sandbox ends with a ticket, one ledger posting and sold capacity reduced, and a replayed event changes nothing. Spec (4 October, CHG-FXP-005), from events/order-paid.yaml and events/entitlement-issued.yaml (adam_search order.paid): the payment transaction (createPayment, or the provider webhook) converts the inventory holds (`catalogue#convertInventoryHold`: the hold becomes sold capacity), posts the cash receipt to ledger.journal_entry and ledger.journal_line, and writes `order.paid` to the outbox in the same transaction; AccessService consumes it (`access#issueOrderEntitlements`, idempotency key orderId + lineId; on failure retry, then dead-letter, which pages) and publishes `entitlement.issued`; the orders consumer of that completes the order. A dead-lettered issuance is replayed, never compensated by an automatic refund. ADR-0055: modules in different deployables talk by event; ADR-0058: one relay per region and an inbox per tenant database, so a replayed event is a no-op.
11 | 1 | OBS-TENANT-POOL | AM-FOUNDATION-PLATFORM | [BE] Alerts on one tenant's share of its connection pool and on max_connections | 1 | Pranay Shinde |  | KERNEL-TENANT-LIMITS PLATFORM-OBSERVE | Alerts on one tenant's share of its connection pool and on max_connections. Builds: `adr ADR-0032`, `adr ADR-0064`. ADR-0064 item 4: per-tenant pool caps stay, and two alerts watch them: one tenant holding more than 60% of its pool for five minutes, and the instance passing 80% of max_connections; plus a dashboard panel of 429s per tenant and audience from KERNEL-TENANT-LIMITS. Done when: a load run that holds one tenant's pool fires the first alert after five minutes naming the tenant, and opening connections past 80% of max_connections fires the second. Where the numbers come from (4 October, CHG-FXP-005): one tenant's share is PgBouncer's SHOW POOLS for that tenant database (cl_active plus cl_waiting against pool_size); the instance figure is the count of pg_stat_activity against max_connections; both are scraped into the Prometheus-compatible metrics of SETUP-OBS and alert through its Azure Monitor action group, labelled with tenant_id and cell.
3 | 1 | OFFLINE-JOURNAL | AM-FOUNDATION-OFFLINE | [BE] Offline journal in packages/offline-core: record, replay and the conflict policies | 8 | Pradnya Yeram |  | SETUP-CLIENTS | Offline journal in packages/offline-core: record, replay and the conflict policies. Builds: `operation orders#createOrder`, `operation orders#createPayment`, `operation shift#createCashMovement`, `operation access#validateAccess`, `operation orders#syncOrders`, `operation access#syncScans`, `adr ADR-0013`, `adr ADR-0022`. In ticvai-frontend packages/offline-core: an append-only journal of sales and scans taken offline, replay on reconnect, and the conflict policies the contracts declare (SD-047). Done when: a POS takes ten cash sales with the network off and all ten reach the server once when it returns. Spec (4 October, CHG-FXP-005): the conflict policies are the `x-ticvai-conflict-policy` of each operation the journal records (linked here): `append` for createOrder, createPayment, createCashMovement and validateAccess (nothing is overwritten, so a replayed entry is a new fact, deduplicated by its idempotency key); `lastWriterWins` only where an operation declares it (holdOrder); `serverWins` for everything else (the server's version stands and the till re-reads). Replay goes through `orders#syncOrders` and `access#syncScans` in journal order, each entry with the idempotency key it was taken with. ADR-0013: the catalogue is read locally on every transaction, online or not, and contended inventory sells only from a lease; ADR-0022: the four policies and why the set is closed.
10 | 1 | OFFLINE-BUNDLE | AM-FOUNDATION-OFFLINE | [BE] Signed catalogue and entitlement bundles, and the lease client | 8 | Hrushikant Patkar |  | PLATFORM-KERNEL | Signed catalogue and entitlement bundles, and the lease client. Builds: `operation catalogue#getLatestBundle`, `operation catalogue#reportBundleApplied`, `operation catalogue#acquireInventoryHold`, `table catalogue.published_bundle`, `table catalogue.inventory_hold`, `operation access#getOfflinePackage`, `adr ADR-0013`. The signed bundle a till or scanner trades from offline, including entitlements and dynamic access policy for the scanner (SD-052), and the lease each workstation holds (SD-047). Two bundles: the till's signed catalogue bundle (`catalogue#getLatestBundle`, applied whole or not at all and acknowledged with `catalogue#reportBundleApplied`; table catalogue.published_bundle) and the scanner's offline package (`access#getOfflinePackage`). The lease is ADR-0013 section 2: a till holds N units of contended timed capacity for a TTL through `catalogue#acquireInventoryHold` (catalogue.inventory_hold), renewed while the link is up; unsold units return on expiry; seated inventory stays blocked offline (CHG-FXP-005). Done when: a till whose lease has expired refuses the next offline sale of that capacity and the POS-002 sale drawer says why (the offline allowance has expired; reconnect to sell more) instead of selling; a till with a valid lease sells down to zero and then refuses the same way; it never oversells.
11 | 1 | OFFLINE-SYNC | AM-FOUNDATION-OFFLINE | [BE] syncOrders: a result per entry, and a bad entry quarantined instead of blocking the till | 5 | Hrushikant Patkar |  | OFFLINE-BUNDLE | syncOrders: a result per entry, and a bad entry quarantined instead of blocking the till. Builds: `operation orders#syncOrders`, `adr ADR-0022`. Per-entry outcomes, a quarantine a supervisor resolves, and the till carrying on with the rest (SD-028). Done when: one malformed sale in a batch of twenty is quarantined and the other nineteen are accepted.
11 | 1 | POS-KDS-ROUTING | AM-FOUNDATION-OFFLINE | [BE] A POS sale reaches the kitchen: routing online, and the LAN path decision | 8 | Hrushikant Patkar |  | PLATFORM-OUTBOX | A POS sale reaches the kitchen: routing online, and the LAN path decision. Builds: `operation fnb#createFnbOrder`, `table fnb.kitchen_ticket`, `table fnb.kitchen_routing_rule`, `table fnb.kitchen_station`. createFnbOrder from the POS creates the kitchen ticket as the guest order does, routed to the right station (SD-046). The offline LAN path to the Kitchen Display is an ADR decision; this task implements the online path and the stub the decision fills. Done when: a POS sale of a burger and a drink shows on the grill and bar stations. 2 October (Chinmay, DEC-187/189): kitchen printers are in release 1 (print template, printer routing) and routing takes category rules with a default/fallback station per outlet. 8 points (was 5).
11 | 1 | SVC-AI-ACTIONS-1 | AM-AI-ENGINE-A | [BE] AiService: overrideAiDecision | 2 | Chinmay Patkar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: overrideAiDecision. Spec: handoff/service-docs/backend/AiService.md#group-actions Helper task: Tanmay Dukhande owns the service and reviews. Done when `ai#overrideAiDecision` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-AI-AI-2 | AM-AI-ENGINE-A | [BE] AiService: setSuggestionProvider, testAiProvider | 3 | Sanket Keluskar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setSuggestionProvider, testAiProvider. Spec: handoff/service-docs/backend/AiService.md#group-ai Helper task: Tanmay Dukhande owns the service and reviews. Done when `ai#setSuggestionProvider`, `ai#testAiProvider` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-AI-FORECAST-2 | AM-AI-ENGINE-A | [BE] AiService: getForecastAccuracy, getVenueHistoryImport, importVenueHistory, listForecastVersions | 5 | Hrushikant Patkar | AiService | MIG-AI MIG-ASSETS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getForecastAccuracy, getVenueHistoryImport, importVenueHistory, listForecastVersions. Spec: handoff/service-docs/backend/AiService.md#group-forecast Helper task: Tanmay Dukhande owns the service and reviews. Done when `ai#getForecastAccuracy`, `ai#getVenueHistoryImport`, `ai#importVenueHistory`, `ai#listForecastVersions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-AI-GOVERNANCE-2 | AM-AI-ENGINE-A | [BE] AiService: getEffectiveAiPolicy, listAiCapabilities, listAiGovernancePolicyVersions, pauseAiCapability | 8 | Sanket Keluskar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getEffectiveAiPolicy, listAiCapabilities, listAiGovernancePolicyVersions, pauseAiCapability. Spec: handoff/service-docs/backend/AiService.md#group-governance. Done when `ai#getEffectiveAiPolicy`, `ai#listAiCapabilities`, `ai#listAiGovernancePolicyVersions`, `ai#pauseAiCapability` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-AI-RETRIEVAL-2 | AM-AI-ENGINE-A | [BE] AiService: setIndexSource | 2 | Chinmay Patkar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setIndexSource. Spec: handoff/service-docs/backend/AiService.md#group-retrieval Helper task: Tanmay Dukhande owns the service and reviews. Done when `ai#setIndexSource` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-IDENTITY-GUESTAUTH-1 | AM-IDENTITY-SECURITY-P01 | [BE] IdentityService: deleteGuestAccount, getGuestSession, getMyIdentityVerification, guestLogout | 5 | Deep Khanvilkar | IdentityService | MIG-IDENTITY MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: deleteGuestAccount, getGuestSession, getMyIdentityVerification, guestLogout. Spec: handoff/service-docs/backend/IdentityService.md#group-guestauth Helper task: Pranay Shinde owns the service and reviews. Done when `identity#deleteGuestAccount`, `identity#getGuestSession`, `identity#getMyIdentityVerification`, `identity#guestLogout` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-IDENTITY-GUESTAUTH-3 | AM-IDENTITY-SECURITY-P01 | [BE] IdentityService: registerGuest, requestGuestOtp, submitGuestIdentityDocument, verifyGuestOtp | 8 | Hrushikant Patkar | IdentityService | MIG-ASSETS MIG-IDENTITY MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: registerGuest, requestGuestOtp, submitGuestIdentityDocument, verifyGuestOtp. Spec: handoff/service-docs/backend/IdentityService.md#group-guestauth. Done when `identity#registerGuest`, `identity#requestGuestOtp`, `identity#submitGuestIdentityDocument`, `identity#verifyGuestOtp` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-IDENTITY-MFA-1 | AM-IDENTITY-SECURITY-P01 | [BE] IdentityService: createMfaChallenge, enrolMfaMethod, listMfaMethods, removeMfaMethod | 3 | Sanket Keluskar | IdentityService | MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createMfaChallenge, enrolMfaMethod, listMfaMethods, removeMfaMethod. Spec: handoff/service-docs/backend/IdentityService.md#group-mfa Helper task: Pranay Shinde owns the service and reviews. Done when `identity#createMfaChallenge`, `identity#enrolMfaMethod`, `identity#listMfaMethods`, `identity#removeMfaMethod` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-IDENTITY-MFA-2 | AM-IDENTITY-SECURITY-P01 | [BE] IdentityService: verifyMfaChallenge, verifyMfaEnrolment | 3 | Sanket Keluskar | IdentityService | MIG-IDENTITY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: verifyMfaChallenge, verifyMfaEnrolment. Spec: handoff/service-docs/backend/IdentityService.md#group-mfa Helper task: Pranay Shinde owns the service and reviews. Done when `identity#verifyMfaChallenge`, `identity#verifyMfaEnrolment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 1 | SVC-IDENTITY-GUESTAUTH-2 | AM-IDENTITY-SECURITY-P01 | [BE] IdentityService: guestPasswordLogin, guestSocialLogin, guestUaePassLogin, linkGuestCheckout | 8 | Hrushikant Patkar | IdentityService | MIG-IDENTITY MIG-ORDERS MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: guestPasswordLogin, guestSocialLogin, guestUaePassLogin, linkGuestCheckout. Spec: handoff/service-docs/backend/IdentityService.md#group-guestauth. Done when `identity#guestPasswordLogin`, `identity#guestSocialLogin`, `identity#guestUaePassLogin`, `identity#linkGuestCheckout` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-IDENTITY-IDENTITY-2 | AM-IDENTITY-SECURITY-P01 | [BE] IdentityService: grantDelegation, listDelegations, login, refreshToken | 8 | Hrushikant Patkar | IdentityService | MIG-IDENTITY MIG-MARKETING MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: grantDelegation, listDelegations, login, refreshToken. Spec: handoff/service-docs/backend/IdentityService.md#group-identity. Done when `identity#grantDelegation`, `identity#listDelegations`, `identity#login`, `identity#refreshToken` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-IDENTITY-IDENTITY-4 | AM-IDENTITY-SECURITY-P01 | [BE] IdentityService: verifyGuestEmail | 2 | Chinmay Patkar | IdentityService | MIG-IDENTITY MIG-MARKETING MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: verifyGuestEmail. Spec: handoff/service-docs/backend/IdentityService.md#group-identity Helper task: Pranay Shinde owns the service and reviews. Done when `identity#verifyGuestEmail` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 1 | SVC-ORDER-ORDER-4 | AM-IDENTITY-SECURITY-P01 | [BE] OrderService: listTicketTransfers, modifyOrder, reprintOrder, rescheduleOrder | 8 | Tanmay Dukhande | OrderService | MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listTicketTransfers, modifyOrder, reprintOrder, rescheduleOrder. Spec: handoff/service-docs/backend/OrderService.md#group-order. Done when `orders#listTicketTransfers`, `orders#modifyOrder`, `orders#reprintOrder`, `orders#rescheduleOrder` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-ORDER-CART-2 | AM-IDENTITY-SECURITY-P01 | [BE] OrderService: claimCart, createCart, extendCart, getCart | 8 | Pranay Shinde | OrderService | MIG-CATALOGUE MIG-MARKETING MIG-ORDERS MIG-PII MIG-PLATFORM MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: claimCart, createCart, extendCart, getCart. Spec: handoff/service-docs/backend/OrderService.md#group-cart. Done when `orders#claimCart`, `orders#createCart`, `orders#extendCart`, `orders#getCart` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-ORDER-ORDER-2 | AM-IDENTITY-SECURITY-P01 | [BE] OrderService: exchangeOrderLines, getMediaEntitlements, getOrder, getOrderCalendarEvent | 8 | Pranay Shinde | OrderService | MIG-ACCESS MIG-CATALOGUE MIG-ORDERS MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: exchangeOrderLines, getMediaEntitlements, getOrder, getOrderCalendarEvent. Spec: handoff/service-docs/backend/OrderService.md#group-order. Done when `orders#exchangeOrderLines`, `orders#getMediaEntitlements`, `orders#getOrder`, `orders#getOrderCalendarEvent` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-MARKETING-CONSENT-1 | AM-IDENTITY-SECURITY-P01 | [BE] MarketingService: claimDeviceConsent, createConsentQuestion, getCookieConsentRuntime, getDeviceConsentHistory | 8 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: claimDeviceConsent, createConsentQuestion, getCookieConsentRuntime, getDeviceConsentHistory. Spec: handoff/service-docs/backend/MarketingService.md#group-consent. Done when `marketing-crm#claimDeviceConsent`, `marketing-crm#createConsentQuestion`, `marketing-crm#getCookieConsentRuntime`, `marketing-crm#getDeviceConsentHistory` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-MARKETING-GUEST-1 | AM-IDENTITY-SECURITY-P02 | [BE] MarketingService: addToWishlist, getWishlist, listGuestDevices, registerGuestDevice | 5 | Deep Khanvilkar | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: addToWishlist, getWishlist, listGuestDevices, registerGuestDevice. Spec: handoff/service-docs/backend/MarketingService.md#group-guest. Done when `marketing-crm#addToWishlist`, `marketing-crm#getWishlist`, `marketing-crm#listGuestDevices`, `marketing-crm#registerGuestDevice` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-MARKETING-GUEST-2 | AM-IDENTITY-SECURITY-P02 | [BE] MarketingService: removeFromWishlist, revokeGuestDevice, searchGuests | 3 | Sanket Keluskar | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: removeFromWishlist, revokeGuestDevice, searchGuests. Spec: handoff/service-docs/backend/MarketingService.md#group-guest Helper task: Pranay Shinde owns the service and reviews. Done when `marketing-crm#removeFromWishlist`, `marketing-crm#revokeGuestDevice`, `marketing-crm#searchGuests` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-IDENTITY-IDENTITY-3 | AM-IDENTITY-SECURITY-P04 | [BE] IdentityService: selectRole, setGuestVerificationPolicy, setPasswordPolicy, setSegregationRules | 8 | Hrushikant Patkar | IdentityService | MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: selectRole, setGuestVerificationPolicy, setPasswordPolicy, setSegregationRules. Spec: handoff/service-docs/backend/IdentityService.md#group-identity. Done when `identity#selectRole`, `identity#setGuestVerificationPolicy`, `identity#setPasswordPolicy`, `identity#setSegregationRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-IDENTITY-IDENTITY-1 | AM-IDENTITY-SECURITY-P04 | [BE] IdentityService: changeOwnCredential, exportSubjectData, forceLogout, getCurrentSession | 8 | Deep Khanvilkar | IdentityService | MIG-ACCESS MIG-IDENTITY MIG-MARKETING MIG-ORDERS MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: changeOwnCredential, exportSubjectData, forceLogout, getCurrentSession. Spec: handoff/service-docs/backend/IdentityService.md#group-identity. Done when `identity#changeOwnCredential`, `identity#exportSubjectData`, `identity#forceLogout`, `identity#getCurrentSession` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
6 | 2 | VM-MIG-IDENTITY | AM-IDENTITY-SECURITY-P06-BLOCK-A | [DB] Forward migration V1000__identity.sql: identity for Venue Management (1 tables) | 1 | Hrushikant Patkar |  | MIG-IDENTITY | Tables: identity.access_decision. Source DDL: backend/tenant/010-identity.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `identity.access_decision` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
8 | 3 | MIG-IDENTITY-2 | AM-IDENTITY-SECURITY-P06-BLOCK-A | [DB] Forward migration V1001__identity.sql: identity for Identity & Security · Staff App (Block A) (2 tables) | 2 | Hrushikant Patkar | IdentityService | MIG-BASELINE MIG-IDENTITY MIG-PLATFORM VM-MIG-IDENTITY | Tables: identity.sso_group_mapping, identity.sso_provider. Source DDL: backend/tenant/010-identity.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `identity.sso_group_mapping`, `identity.sso_provider` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-IDENTITY-SSO-1 | AM-IDENTITY-SECURITY-P06-BLOCK-A | [BE] IdentityService: completeSsoAuthorization, listSsoProviders, startSsoAuthorization | 5 | Deep Khanvilkar | IdentityService | MIG-IDENTITY MIG-IDENTITY-2 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: completeSsoAuthorization, listSsoProviders, startSsoAuthorization. Spec: contracts (identity) at the release tag, served by ADAM. Built for Identity & Security · Staff App (Block A); additive to IdentityService, whose first-release owner (Pranay Shinde) reviews. Done when `identity#completeSsoAuthorization`, `identity#listSsoProviders`, `identity#startSsoAuthorization` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-IDENTITY-ADMINISTRATION-1 | AM-IDENTITY-SECURITY-P13 | [BE] IdentityService: createRole, listOwnPlatformStaffGrants, listPrincipals, listRoles | 5 | Deep Khanvilkar | IdentityService | MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createRole, listOwnPlatformStaffGrants, listPrincipals, listRoles. Spec: handoff/service-docs/backend/IdentityService.md#group-administration Helper task: Pranay Shinde owns the service and reviews. Done when `identity#createRole`, `identity#listOwnPlatformStaffGrants`, `identity#listPrincipals`, `identity#listRoles` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-IDENTITY-ADMINISTRATION-2 | AM-IDENTITY-SECURITY-P13 | [BE] IdentityService: openPlatformStaffGrant, setCapabilityTemplate, updatePrincipal, updateRole | 5 | Sanket Keluskar | IdentityService | MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: openPlatformStaffGrant, setCapabilityTemplate, updatePrincipal, updateRole. Spec: handoff/service-docs/backend/IdentityService.md#group-administration Helper task: Pranay Shinde owns the service and reviews. Done when `identity#openPlatformStaffGrant`, `identity#setCapabilityTemplate`, `identity#updatePrincipal`, `identity#updateRole` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-IDENTITY-SESSION-1 | AM-IDENTITY-SECURITY-P04 | [BE] IdentityService: listActiveSessions | 2 | Chinmay Patkar | IdentityService | MIG-IDENTITY PLATFORM-KERNEL SVC-IDENTITY-ADMINISTRATION-2 SVC-IDENTITY-IDENTITY-1 SVC-IDENTITY-IDENTITY-2 SVC-IDENTITY-IDENTITY-3 SVC-IDENTITY-MFA-2 | Operations: listActiveSessions. Spec: handoff/service-docs/backend/IdentityService.md#group-session Helper task: Pranay Shinde owns the service and reviews. Done when `identity#listActiveSessions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-PLATFORM-TENANT-1 | AM-IDENTITY-SECURITY-P09 | [BE] PlatformService: createTenant, listTenants, reactivateTenant, suspendTenant | 8 | Tanmay Dukhande | PlatformService | MIG-CONTROL MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: createTenant, listTenants, reactivateTenant, suspendTenant. Spec: handoff/service-docs/backend/PlatformService.md#group-tenant. Done when `subscription#createTenant`, `subscription#listTenants`, `subscription#reactivateTenant`, `subscription#suspendTenant` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-MODULES-1 | AM-IDENTITY-SECURITY-P09 | [BE] WhiteLabelService: getFeatureToggles, getModuleEnablement, setFeatureToggles, setLanguages | 3 | Sanket Keluskar | WhiteLabelService | MIG-CONTROL MIG-SUBSCRIPTION MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getFeatureToggles, getModuleEnablement, setFeatureToggles, setLanguages. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-modules Helper task: Tanmay Dukhande owns the service and reviews. Done when `white-label#getFeatureToggles`, `white-label#getModuleEnablement`, `white-label#setFeatureToggles`, `white-label#setLanguages` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-OVERVIEW-2 | AM-IDENTITY-SECURITY-P09 | [BE] WhiteLabelService: recordStorefrontSessionEvents, setAnalyticsProvider, setMaintenanceMode | 5 | Deep Khanvilkar | WhiteLabelService | MIG-PLATFORM MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: recordStorefrontSessionEvents, setAnalyticsProvider, setMaintenanceMode. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-overview Helper task: Tanmay Dukhande owns the service and reviews. Done when `white-label#recordStorefrontSessionEvents`, `white-label#setAnalyticsProvider`, `white-label#setMaintenanceMode` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-PUBLISHING-1 | AM-IDENTITY-SECURITY-P09 | [BE] WhiteLabelService: createPreview, diffConfigVersion, exportSitePackage, getPublishReviewPolicy | 5 | Deep Khanvilkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createPreview, diffConfigVersion, exportSitePackage, getPublishReviewPolicy. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-publishing Helper task: Tanmay Dukhande owns the service and reviews. Done when `white-label#createPreview`, `white-label#diffConfigVersion`, `white-label#exportSitePackage`, `white-label#getPublishReviewPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-PUBLISHING-2 | AM-IDENTITY-SECURITY-P09 | [BE] WhiteLabelService: getSitePackage, getSiteSetupProgress, listConfigVersions, publishTenantConfig | 5 | Tanmay Dukhande | WhiteLabelService | MIG-PLATFORM MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: getSitePackage, getSiteSetupProgress, listConfigVersions, publishTenantConfig. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-publishing Helper task: Tanmay Dukhande owns the service and reviews. Done when `white-label#getSitePackage`, `white-label#getSiteSetupProgress`, `white-label#listConfigVersions`, `white-label#publishTenantConfig` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-PUBLISHING-3 | AM-IDENTITY-SECURITY-P09 | [BE] WhiteLabelService: restoreConfigVersion, setPublishReviewPolicy, setSiteSetupProgress, validateTenantConfig | 8 | Tanmay Dukhande | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: restoreConfigVersion, setPublishReviewPolicy, setSiteSetupProgress, validateTenantConfig. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-publishing. Done when `white-label#restoreConfigVersion`, `white-label#setPublishReviewPolicy`, `white-label#setSiteSetupProgress`, `white-label#validateTenantConfig` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-THEME-1 | AM-IDENTITY-SECURITY-P09 | [BE] WhiteLabelService: getFonts, getTheme, setFonts, setTheme | 5 | Hrushikant Patkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getFonts, getTheme, setFonts, setTheme. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-theme Helper task: Tanmay Dukhande owns the service and reviews. Done when `white-label#getFonts`, `white-label#getTheme`, `white-label#setFonts`, `white-label#setTheme` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-WHITELABEL-WHITELABEL-1 | AM-IDENTITY-SECURITY-P09 | [BE] WhiteLabelService: createContentBlock, listContentBlocks, publishContentBlock, setFooter | 8 | Hrushikant Patkar | WhiteLabelService | MIG-CONTROL MIG-IDENTITY MIG-MARKETING MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createContentBlock, listContentBlocks, publishContentBlock, setFooter. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-whitelabel. Done when `white-label#createContentBlock`, `white-label#listContentBlocks`, `white-label#publishContentBlock`, `white-label#setFooter` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-TENANCY-DEVICES-1 | AM-TENANCY-VENUES-P04 | [BE] TenancyService: setDeviceAssignment | 2 | Deep Khanvilkar | TenancyService | MIG-TENANCY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setDeviceAssignment. Spec: handoff/service-docs/backend/TenancyService.md#group-devices Helper task: Hrushikant Patkar owns the service and reviews. Done when `tenancy#setDeviceAssignment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-TENANCY-WORKSTATION-1 | AM-TENANCY-VENUES-P04 | [BE] TenancyService: configureWorkstation, createOutlet, createSaleBoard, getOutlet | 8 | Pranay Shinde | TenancyService | MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: configureWorkstation, createOutlet, createSaleBoard, getOutlet. Spec: handoff/service-docs/backend/TenancyService.md#group-workstation. Done when `tenancy#configureWorkstation`, `tenancy#createOutlet`, `tenancy#createSaleBoard`, `tenancy#getOutlet` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-TENANCY-WORKSTATION-2 | AM-TENANCY-VENUES-P04 | [BE] TenancyService: listDevices, listSaleBoards, updateOutlet, updateSaleBoard | 8 | Sanket Keluskar | TenancyService | MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listDevices, listSaleBoards, updateOutlet, updateSaleBoard. Spec: handoff/service-docs/backend/TenancyService.md#group-workstation. Done when `tenancy#listDevices`, `tenancy#listSaleBoards`, `tenancy#updateOutlet`, `tenancy#updateSaleBoard` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 1 | SVC-TENANCY-GENERAL-1 | AM-TENANCY-VENUES-P04 | [BE] TenancyService: getDeviceAssignment | 1 | Chinmay Patkar | TenancyService | MIG-TENANCY PLATFORM-KERNEL SVC-TENANCY-DEVICES-1 | Operations: getDeviceAssignment. Spec: handoff/service-docs/backend/TenancyService.md#group-general Helper task: Hrushikant Patkar owns the service and reviews. Done when `tenancy#getDeviceAssignment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 1 | SVC-ORDER-SHIFT-1 | AM-TENANCY-VENUES-P04 | [BE] OrderService: acceptShiftVariance, allocateDepositBox, approveShiftOpen, closeShift | 8 | Pranay Shinde | OrderService | MIG-IDENTITY MIG-LEDGER MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: acceptShiftVariance, allocateDepositBox, approveShiftOpen, closeShift. Spec: handoff/service-docs/backend/OrderService.md#group-shift. Done when `shift#acceptShiftVariance`, `shift#allocateDepositBox`, `shift#approveShiftOpen`, `shift#closeShift` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
5 | 2 | VM-MIG-TENANCY | AM-TENANCY-VENUES-P08-BLOCK-A | [DB] Forward migration V1073__tenancy.sql: tenancy for Venue Management (4 tables) | 2 | Hrushikant Patkar |  | MIG-TENANCY | Tables: tenancy.device_audit, tenancy.device_credential, tenancy.device_firmware, tenancy.device_rollout. Source DDL: backend/tenant/010-tenancy.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `tenancy.device_audit`, `tenancy.device_credential`, `tenancy.device_firmware`, `tenancy.device_rollout` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
8 | 2 | VM-MIG-PLATFORM | AM-TENANCY-VENUES-P08-BLOCK-A | [DB] Forward migration V1002__platform.sql: platform for Venue Management (5 tables) | 2 | Hrushikant Patkar |  | MIG-PLATFORM | Tables: platform.audit_read, platform.configuration_profile, platform.connectivity_policy, platform.offline_policy, platform.profile_deployment. Source DDL: backend/tenant/010-platform.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `platform.audit_read`, `platform.configuration_profile`, `platform.connectivity_policy`, `platform.offline_policy`, `platform.profile_deployment` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
6 | 3 | MIG-TENANCY-2 | AM-TENANCY-VENUES-P08-BLOCK-A | [DB] Forward migration V1075__tenancy.sql: tenancy for Tenancy & Venues · Venue Management (Block A) (1 tables) | 1 | Hrushikant Patkar | TenancyService | MIG-BASELINE MIG-TENANCY VM-MIG-TENANCY | Tables: tenancy.device_tamper_event. Source DDL: backend/tenant/010-tenancy.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `tenancy.device_tamper_event` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
9 | 3 | MIG-PLATFORM-2 | AM-TENANCY-VENUES-P08-BLOCK-A | [DB] Forward migration V1076__platform.sql: platform for Tenancy & Venues · Venue Management (Block A) (1 tables) | 1 | Hrushikant Patkar | TenancyService | MIG-BASELINE MIG-PLATFORM VM-MIG-PLATFORM | Tables: platform.cell_endpoint. Source DDL: backend/tenant/010-platform.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `platform.cell_endpoint` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 2 | VM-TENANCY-TENANCY-1 | AM-TENANCY-VENUES-P08-BLOCK-A | [BE] TenancyService: deployConfigurationProfile, getOfflinePolicy, getVenueSettings, listAuditRecords | 8 | Pranay Shinde | TenancyService | MIG-IDENTITY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-PLATFORM | Operations beyond the first release: deployConfigurationProfile, getOfflinePolicy, getVenueSettings, listAuditRecords. Additive to TenancyService; its first-release owner (Hrushikant Patkar) reviews. Done when `tenancy#deployConfigurationProfile`, `tenancy#getOfflinePolicy`, `tenancy#getVenueSettings`, `tenancy#listAuditRecords` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-TENANCY-TENANCY-2 | AM-TENANCY-VENUES-P08-BLOCK-A | [BE] TenancyService: setConfigurationProfile, setConnectivityThresholds, setOfflinePolicy | 5 | Sanket Keluskar | TenancyService | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-PLATFORM | Operations beyond the first release: setConfigurationProfile, setConnectivityThresholds, setOfflinePolicy. Additive to TenancyService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `tenancy#setConfigurationProfile`, `tenancy#setConnectivityThresholds`, `tenancy#setOfflinePolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-DEVICES-3 | AM-TENANCY-VENUES-P08-BLOCK-A | [BE] TenancyService: listDeviceAuditRecords, listDeviceTamperEvents, recordDeviceTamperEvent | 3 | Pranay Shinde | TenancyService | MIG-PLATFORM MIG-TENANCY-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-TENANCY | Operations: listDeviceAuditRecords, listDeviceTamperEvents, recordDeviceTamperEvent. Spec: contracts (tenancy) at the release tag, served by ADAM. Built for Tenancy & Venues · Venue Management (Block A); additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `tenancy#listDeviceAuditRecords`, `tenancy#listDeviceTamperEvents`, `tenancy#recordDeviceTamperEvent` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-WORKSTATION-3 | AM-TENANCY-VENUES-P08-BLOCK-A | [BE] TenancyService: recordDeviceHeartbeat | 2 | Deep Khanvilkar | TenancyService | MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: recordDeviceHeartbeat. Spec: contracts (tenancy) at the release tag, served by ADAM. Built for Tenancy & Venues · Venue Management (Block A); additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `tenancy#recordDeviceHeartbeat` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-TENANCY-TENANCY-3 | AM-TENANCY-VENUES-P08-BLOCK-A | [BE] TenancyService: getConfigurationProfile, getConnectivityPolicy, listCellEndpoints, listProfileDeployments | 3 | Deep Khanvilkar | TenancyService | MIG-PLATFORM-2 PLATFORM-KERNEL VM-MIG-PLATFORM VM-TENANCY-TENANCY-1 VM-TENANCY-TENANCY-2 | Operations: getConfigurationProfile, getConnectivityPolicy, listCellEndpoints, listProfileDeployments. Spec: contracts (tenancy) at the release tag, served by ADAM. Built for Tenancy & Venues · Venue Management (Block A); additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `tenancy#getConfigurationProfile`, `tenancy#getConnectivityPolicy`, `tenancy#listCellEndpoints`, `tenancy#listProfileDeployments` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-ORDER-SYNC-1 | AM-TENANCY-VENUES-P08-BLOCK-A | [BE] OrderService: resolveSyncRejection | 2 | Chinmay Patkar | OrderService | MIG-SYNC PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: resolveSyncRejection. Additive to OrderService; its first-release owner (Pranay Shinde) reviews. Helper task: Pranay Shinde owns the service and reviews. Done when `orders#resolveSyncRejection` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-PLATFORM-LICENSING-1 | AM-SUBSCRIPTION-LICENSING-P09 | [BE] PlatformService: addLicenceAddOn, getTenantLicences | 3 | Sanket Keluskar | PlatformService | MIG-CONTROL MIG-SUBSCRIPTION PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: addLicenceAddOn, getTenantLicences. Spec: handoff/service-docs/backend/PlatformService.md#group-licensing Helper task: Pranay Shinde owns the service and reviews. Done when `subscription#addLicenceAddOn`, `subscription#getTenantLicences` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-PLATFORM-SUBSCRIPTION-1 | AM-SUBSCRIPTION-LICENSING-P09 | [BE] PlatformService: listModuleCatalogue, setModuleListing, setSubscription | 3 | Sanket Keluskar | PlatformService | MIG-SUBSCRIPTION PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listModuleCatalogue, setModuleListing, setSubscription. Spec: handoff/service-docs/backend/PlatformService.md#group-subscription Helper task: Pranay Shinde owns the service and reviews. Done when `subscription#listModuleCatalogue`, `subscription#setModuleListing`, `subscription#setSubscription` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-MODULES-2 | AM-SUBSCRIPTION-LICENSING-P09 | [BE] WhiteLabelService: setModuleEnablement | 1 | Chinmay Patkar | WhiteLabelService | MIG-CONTROL MIG-SUBSCRIPTION MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setModuleEnablement. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-modules Helper task: Tanmay Dukhande owns the service and reviews. Done when `white-label#setModuleEnablement` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-TENANCY-APPROVALS-1 | AM-APPROVALS-P04 | [BE] TenancyService: approveMatrixMultiLevel, approveRoleAuthorityDelegation | 5 | Deep Khanvilkar | TenancyService | MIG-APPROVALS MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: approveMatrixMultiLevel, approveRoleAuthorityDelegation. Spec: handoff/service-docs/backend/TenancyService.md#group-approvals Helper task: Hrushikant Patkar owns the service and reviews. Done when `approvals#approveMatrixMultiLevel`, `approvals#approveRoleAuthorityDelegation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-TENANCY-REQUEST-1 | AM-APPROVALS-P04 | [BE] TenancyService: createApprovalRequest, decideApprovalRequest, evaluateApprovalRequirement, listApprovalRequests | 8 | Pranay Shinde | TenancyService | MIG-APPROVALS MIG-CONTROL MIG-IDENTITY MIG-MARKETING MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: createApprovalRequest, decideApprovalRequest, evaluateApprovalRequirement, listApprovalRequests. Spec: handoff/service-docs/backend/TenancyService.md#group-request. Done when `approvals#createApprovalRequest`, `approvals#decideApprovalRequest`, `approvals#evaluateApprovalRequirement`, `approvals#listApprovalRequests` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WALLET-CARD-1 | AM-APPROVALS-P04 | [BE] WalletService: loadGameCredits | 5 | Sanket Keluskar | WalletService | MIG-GAMES MIG-PLATFORM MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: loadGameCredits. Spec: handoff/service-docs/backend/WalletService.md#group-card Helper task: Pranay Shinde owns the service and reviews. Done when `wallet#loadGameCredits` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WALLET-RETAIL-2 | AM-APPROVALS-P04 | [BE] WalletService: transferWalletBalance | 3 | Sanket Keluskar | WalletService | MIG-PII MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: transferWalletBalance. Spec: handoff/service-docs/backend/WalletService.md#group-retail Helper task: Pranay Shinde owns the service and reviews. Done when `wallet#transferWalletBalance` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WALLET-WALLET-1 | AM-APPROVALS-P04 | [BE] WalletService: getWallet, listWalletTransactions, publishWalletConfiguration, restoreWalletConfigurationVersion | 8 | Pranay Shinde | WalletService | MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getWallet, listWalletTransactions, publishWalletConfiguration, restoreWalletConfigurationVersion. Spec: handoff/service-docs/backend/WalletService.md#group-wallet. Done when `wallet#getWallet`, `wallet#listWalletTransactions`, `wallet#publishWalletConfiguration`, `wallet#restoreWalletConfigurationVersion` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WALLET-WALLET-2 | AM-APPROVALS-P04 | [BE] WalletService: setWalletFundingRules, setWalletRefundPolicy, topUpWallet | 8 | Pranay Shinde | WalletService | MIG-PLATFORM MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: setWalletFundingRules, setWalletRefundPolicy, topUpWallet. Spec: handoff/service-docs/backend/WalletService.md#group-wallet. Done when `wallet#setWalletFundingRules`, `wallet#setWalletRefundPolicy`, `wallet#topUpWallet` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 1 | SVC-ORDER-SHIFT-4 | AM-APPROVALS-P04 | [BE] OrderService: openShift, recordNoSale, rejectShiftVariance, reopenShift | 8 | Pranay Shinde | OrderService | MIG-IDENTITY MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: openShift, recordNoSale, rejectShiftVariance, reopenShift. Spec: handoff/service-docs/backend/OrderService.md#group-shift. Done when `shift#openShift`, `shift#recordNoSale`, `shift#rejectShiftVariance`, `shift#reopenShift` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-WALLET-RETAIL-1 | AM-APPROVALS-P04 | [BE] WalletService: getWalletAutoReloadSetting, getWalletExitBalance, setWalletAutoReloadSetting, settleWalletAtExit | 8 | Pranay Shinde | WalletService | MIG-ORDERS MIG-PAYMENTS MIG-PLATFORM MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: getWalletAutoReloadSetting, getWalletExitBalance, setWalletAutoReloadSetting, settleWalletAtExit. Spec: handoff/service-docs/backend/WalletService.md#group-retail. Done when `wallet#getWalletAutoReloadSetting`, `wallet#getWalletExitBalance`, `wallet#setWalletAutoReloadSetting`, `wallet#settleWalletAtExit` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 1 | SVC-RETAIL-FLOOR-1 | AM-APPROVALS-P04 | [BE] RetailService: collectShopAndDrop, createShopAndDrop, lookupMerchandise, lookupShopAndDrop | 5 | Deep Khanvilkar | RetailService | MIG-RETAIL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: collectShopAndDrop, createShopAndDrop, lookupMerchandise, lookupShopAndDrop. Spec: handoff/service-docs/backend/RetailService.md#group-floor. Done when `retail#collectShopAndDrop`, `retail#createShopAndDrop`, `retail#lookupMerchandise`, `retail#lookupShopAndDrop` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 1 | SVC-RETAIL-FLOOR-2 | AM-APPROVALS-P04 | [BE] RetailService: reserveMerchandise | 2 | Chinmay Patkar | RetailService | MIG-INVENTORY MIG-RETAIL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: reserveMerchandise. Spec: handoff/service-docs/backend/RetailService.md#group-floor Helper task: Hrushikant Patkar owns the service and reviews. Done when `retail#reserveMerchandise` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 1 | SVC-RETAIL-MERCHANDISE-1 | AM-APPROVALS-P04 | [BE] RetailService: createMerchandise, listMerchandise, updateMerchandise | 5 | Pranay Shinde | RetailService | MIG-RETAIL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createMerchandise, listMerchandise, updateMerchandise. Spec: handoff/service-docs/backend/RetailService.md#group-merchandise. Done when `retail#createMerchandise`, `retail#listMerchandise`, `retail#updateMerchandise` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 1 | SVC-RETAIL-RETURN-1 | AM-APPROVALS-P04 | [BE] RetailService: createRetailReturn, getReturnPolicy, lookupRetailSale, setReturnPolicy | 8 | Pranay Shinde | RetailService | MIG-INVENTORY MIG-RETAIL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createRetailReturn, getReturnPolicy, lookupRetailSale, setReturnPolicy. Spec: handoff/service-docs/backend/RetailService.md#group-return. Done when `retail#createRetailReturn`, `retail#getReturnPolicy`, `retail#lookupRetailSale`, `retail#setReturnPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 1 | SVC-RETAIL-SALE-1 | AM-APPROVALS-P04 | [BE] RetailService: createRetailSale, getRetailSale, listRetailSales, reprintReceipt | 8 | Pranay Shinde | RetailService | MIG-INVENTORY MIG-RETAIL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createRetailSale, getRetailSale, listRetailSales, reprintReceipt. Spec: handoff/service-docs/backend/RetailService.md#group-sale. Done when `retail#createRetailSale`, `retail#getRetailSale`, `retail#listRetailSales`, `retail#reprintReceipt` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
7 | 2 | VM-MIG-APPROVALS | AM-APPROVALS-P08-BLOCK-A | [DB] Forward migration V1005__approvals.sql: approvals for Venue Management (1 tables) | 1 | Hrushikant Patkar |  | MIG-APPROVALS | Tables: approvals.escalation. Source DDL: backend/tenant/010-approvals.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `approvals.escalation` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
8 | 2 | VM-MIG-AI | AM-APPROVALS-P08-BLOCK-A | [DB] Forward migration V1006__ai.sql: ai for Venue Management (1 tables) | 1 | Hrushikant Patkar |  | MIG-AI | Tables: ai.approval_request_score. Source DDL: backend/tenant/010-ai.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `ai.approval_request_score` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
8 | 3 | MIG-APPROVALS-5 | AM-APPROVALS-P08-BLOCK-A | [DB] Forward migration V1009__approvals.sql: approvals for Approvals · Venue Management (Block A) (3 tables) | 2 | Hrushikant Patkar | TenancyService | MIG-APPROVALS MIG-BASELINE VM-MIG-APPROVALS | Tables: approvals.automation_execution, approvals.external_dispatch, approvals.step_up_policy. Source DDL: backend/tenant/010-approvals.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `approvals.automation_execution`, `approvals.external_dispatch`, `approvals.step_up_policy` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 2 | VM-TENANCY-REQUEST-1 | AM-APPROVALS-P08-BLOCK-A | [BE] TenancyService: escalateApprovalRequest, getApprovalRequest, resubmitApprovalRequest, withdrawApprovalRequest | 8 | Pranay Shinde | TenancyService | MIG-APPROVALS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-APPROVALS | Operations beyond the first release: escalateApprovalRequest, getApprovalRequest, resubmitApprovalRequest, withdrawApprovalRequest. Additive to TenancyService; its first-release owner (Hrushikant Patkar) reviews. Done when `approvals#escalateApprovalRequest`, `approvals#getApprovalRequest`, `approvals#resubmitApprovalRequest`, `approvals#withdrawApprovalRequest` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-APPROVALS-4 | AM-APPROVALS-P08-BLOCK-A | [BE] TenancyService: approveUnifiedDecision, listAutomationExecutions | 3 | Deep Khanvilkar | TenancyService | MIG-APPROVALS MIG-APPROVALS-5 MIG-IDENTITY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: approveUnifiedDecision, listAutomationExecutions. Spec: contracts (approvals) at the release tag, served by ADAM. Built for Approvals · Venue Management (Block A); additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `approvals#approveUnifiedDecision`, `approvals#listAutomationExecutions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-REQUEST-2 | AM-APPROVALS-P08-BLOCK-A | [BE] TenancyService: assignApprovalRequest, cancelApprovalRequest, recordExternalApprovalDecision, reopenApprovalRequest | 8 | Tanmay Dukhande | TenancyService | MIG-APPROVALS MIG-APPROVALS-5 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: assignApprovalRequest, cancelApprovalRequest, recordExternalApprovalDecision, reopenApprovalRequest. Spec: contracts (approvals) at the release tag, served by ADAM. Built for Approvals · Venue Management (Block A); additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `approvals#assignApprovalRequest`, `approvals#cancelApprovalRequest`, `approvals#recordExternalApprovalDecision`, `approvals#reopenApprovalRequest` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-REQUEST-3 | AM-APPROVALS-P08-BLOCK-A | [BE] TenancyService: submitApprovalRequest | 3 | Deep Khanvilkar | TenancyService | MIG-APPROVALS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: submitApprovalRequest. Spec: contracts (approvals) at the release tag, served by ADAM. Built for Approvals · Venue Management (Block A); additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `approvals#submitApprovalRequest` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 2 | VM-AI-RISK-1 | AM-APPROVALS-P08-BLOCK-A | [BE] AiService: getApprovalRequestScore | 1 | Chinmay Patkar | AiService | PLATFORM-KERNEL VM-MIG-AI | Operations beyond the first release: getApprovalRequestScore. Additive to AiService; its first-release owner (Tanmay Dukhande) reviews. Helper task: Tanmay Dukhande owns the service and reviews. Done when `ai#getApprovalRequestScore` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-VENUEOPS-ASSET-1 | AM-DIGITAL-ASSETS-P13 | [BE] VenueOpsService: deleteMediaAsset, getMediaAsset, replaceMediaAsset, searchMedia | 8 | Tanmay Dukhande | VenueOpsService | MIG-ASSETS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: deleteMediaAsset, getMediaAsset, replaceMediaAsset, searchMedia. Spec: handoff/service-docs/backend/VenueOpsService.md#group-asset. Done when `assets#deleteMediaAsset`, `assets#getMediaAsset`, `assets#replaceMediaAsset`, `assets#searchMedia` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-VENUEOPS-ASSET-2 | AM-DIGITAL-ASSETS-P13 | [BE] VenueOpsService: updateMediaAsset | 3 | Chinmay Patkar | VenueOpsService | MIG-ASSETS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updateMediaAsset. Spec: handoff/service-docs/backend/VenueOpsService.md#group-asset Helper task: Hrushikant Patkar owns the service and reviews. Done when `assets#updateMediaAsset` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-VENUEOPS-COLLECTION-1 | AM-DIGITAL-ASSETS-P13 | [BE] VenueOpsService: createCollection, listCollections | 2 | Chinmay Patkar | VenueOpsService | MIG-ASSETS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createCollection, listCollections. Spec: handoff/service-docs/backend/VenueOpsService.md#group-collection Helper task: Hrushikant Patkar owns the service and reviews. Done when `assets#createCollection`, `assets#listCollections` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-VENUEOPS-UPLOAD-1 | AM-DIGITAL-ASSETS-P13 | [BE] VenueOpsService: completeUpload, createUpload | 5 | Tanmay Dukhande | VenueOpsService | MIG-ASSETS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: completeUpload, createUpload. Spec: handoff/service-docs/backend/VenueOpsService.md#group-upload Helper task: Hrushikant Patkar owns the service and reviews. Done when `assets#completeUpload`, `assets#createUpload` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 1 | SVC-VENUEOPS-RIGHTS-1 | AM-DIGITAL-ASSETS-P13 | [BE] VenueOpsService: getExpiringRights | 1 | Chinmay Patkar | VenueOpsService | MIG-ASSETS PLATFORM-KERNEL SVC-VENUEOPS-ASSET-1 SVC-VENUEOPS-ASSET-2 SVC-VENUEOPS-UPLOAD-1 | Operations: getExpiringRights. Spec: handoff/service-docs/backend/VenueOpsService.md#group-rights Helper task: Hrushikant Patkar owns the service and reviews. Done when `assets#getExpiringRights` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 1 | SVC-AI-RETRIEVAL-1 | AM-DIGITAL-ASSETS-P13 | [BE] AiService: createKnowledgeCollection, ingestKnowledgeDocument, reindexSource, semanticSearch | 8 | Hrushikant Patkar | AiService | MIG-AI MIG-ASSETS MIG-CATALOGUE MIG-FNB MIG-MAINTENANCE MIG-MARKETING MIG-REPORTING MIG-RETAIL MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createKnowledgeCollection, ingestKnowledgeDocument, reindexSource, semanticSearch. Spec: handoff/service-docs/backend/AiService.md#group-retrieval. Done when `ai#createKnowledgeCollection`, `ai#ingestKnowledgeDocument`, `ai#reindexSource`, `ai#semanticSearch` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-CONTENT-1 | AM-WHITE-LABEL-P01 | [BE] WhiteLabelService: createBanner, createContentPage, createGuidedChoice, createPromoBlock | 8 | Hrushikant Patkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createBanner, createContentPage, createGuidedChoice, createPromoBlock. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-content. Done when `white-label#createBanner`, `white-label#createContentPage`, `white-label#createGuidedChoice`, `white-label#createPromoBlock` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-CONTENT-2 | AM-WHITE-LABEL-P01 | [BE] WhiteLabelService: deleteBanner, deleteContentPage, deleteGuidedChoice, deletePromoBlock | 5 | Hrushikant Patkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: deleteBanner, deleteContentPage, deleteGuidedChoice, deletePromoBlock. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-content Helper task: Tanmay Dukhande owns the service and reviews. Done when `white-label#deleteBanner`, `white-label#deleteContentPage`, `white-label#deleteGuidedChoice`, `white-label#deletePromoBlock` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-CONTENT-5 | AM-WHITE-LABEL-P01 | [BE] WhiteLabelService: listPublishedPolicies, proposeGuidedChoice, publishGuidedChoice, setFaqs | 8 | Hrushikant Patkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listPublishedPolicies, proposeGuidedChoice, publishGuidedChoice, setFaqs. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-content. Done when `white-label#listPublishedPolicies`, `white-label#proposeGuidedChoice`, `white-label#publishGuidedChoice`, `white-label#setFaqs` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-CONTENT-6 | AM-WHITE-LABEL-P01 | [BE] WhiteLabelService: setPolicy, unpublishGuidedChoice, updateBanner, updateContentPage | 8 | Hrushikant Patkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setPolicy, unpublishGuidedChoice, updateBanner, updateContentPage. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-content. Done when `white-label#setPolicy`, `white-label#unpublishGuidedChoice`, `white-label#updateBanner`, `white-label#updateContentPage` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-CONTENT-7 | AM-WHITE-LABEL-P01 | [BE] WhiteLabelService: updateGuidedChoice, updatePromoBlock | 5 | Deep Khanvilkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updateGuidedChoice, updatePromoBlock. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-content Helper task: Tanmay Dukhande owns the service and reviews. Done when `white-label#updateGuidedChoice`, `white-label#updatePromoBlock` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 1 | SVC-WHITELABEL-CONTENT-4 | AM-WHITE-LABEL-P01 | [BE] WhiteLabelService: listPolicies, listPromoBlocks, listPublishedContentPages, listPublishedFaqs | 3 | Sanket Keluskar | WhiteLabelService | MIG-WHITELABEL PLATFORM-KERNEL SVC-WHITELABEL-CONTENT-1 SVC-WHITELABEL-CONTENT-2 SVC-WHITELABEL-CONTENT-6 SVC-WHITELABEL-CONTENT-7 | Operations: listPolicies, listPromoBlocks, listPublishedContentPages, listPublishedFaqs. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-content Helper task: Tanmay Dukhande owns the service and reviews. Done when `white-label#listPolicies`, `white-label#listPromoBlocks`, `white-label#listPublishedContentPages`, `white-label#listPublishedFaqs` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-CATALOGUE-ENTITLEMENT-1 | AM-WHITE-LABEL-P01 | [BE] CatalogueService: createEntitlementTemplate, setEntitlementTemplateBlackoutDates | 5 | Chinmay Patkar | CatalogueService | MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createEntitlementTemplate, setEntitlementTemplateBlackoutDates. Spec: handoff/service-docs/backend/CatalogueService.md#group-entitlement Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#createEntitlementTemplate`, `catalogue#setEntitlementTemplateBlackoutDates` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-CATALOGUE-PRODUCT-3 | AM-WHITE-LABEL-P01 | [BE] CatalogueService: resolveProductByCode, setAlternativeCodes, setGroupPackageDefinition, setProductEligibilityRule | 5 | Deep Khanvilkar | CatalogueService | MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: resolveProductByCode, setAlternativeCodes, setGroupPackageDefinition, setProductEligibilityRule. Spec: handoff/service-docs/backend/CatalogueService.md#group-product Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#resolveProductByCode`, `catalogue#setAlternativeCodes`, `catalogue#setGroupPackageDefinition`, `catalogue#setProductEligibilityRule` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-CATALOGUE-PRODUCT-4 | AM-WHITE-LABEL-P01 | [BE] CatalogueService: updateProduct, updateProductVariant | 5 | Sanket Keluskar | CatalogueService | MIG-CATALOGUE MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updateProduct, updateProductVariant. Spec: handoff/service-docs/backend/CatalogueService.md#group-product Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#updateProduct`, `catalogue#updateProductVariant` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-ACCESS-ACCESS-4 | AM-WHITE-LABEL-P01 | [BE] AccessService: revokeFacePass, setAccessPointGroup, setBiometricVerificationProfile, setBleBeaconGeofence | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: revokeFacePass, setAccessPointGroup, setBiometricVerificationProfile, setBleBeaconGeofence. Spec: handoff/service-docs/backend/AccessService.md#group-access. Done when `access#revokeFacePass`, `access#setAccessPointGroup`, `access#setBiometricVerificationProfile`, `access#setBleBeaconGeofence` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-ACCESS-ACCESS-6 | AM-WHITE-LABEL-P01 | [BE] AccessService: setFaceTagTemporaryEnrollment, setGateModePolicy, setParkingFacility, setVirtualTicketIdentity | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setFaceTagTemporaryEnrollment, setGateModePolicy, setParkingFacility, setVirtualTicketIdentity. Spec: handoff/service-docs/backend/AccessService.md#group-access. Done when `access#setFaceTagTemporaryEnrollment`, `access#setGateModePolicy`, `access#setParkingFacility`, `access#setVirtualTicketIdentity` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-ACCESS-ACCESS-7 | AM-WHITE-LABEL-P01 | [BE] AccessService: setVisualAccessRule, updateParkingEntitlement | 3 | Sanket Keluskar | AccessService | MIG-ACCESS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setVisualAccessRule, updateParkingEntitlement. Spec: handoff/service-docs/backend/AccessService.md#group-access Helper task: Hrushikant Patkar owns the service and reviews. Done when `access#setVisualAccessRule`, `access#updateParkingEntitlement` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-ACCESS-ACCESSPOINT-1 | AM-WHITE-LABEL-P01 | [BE] AccessService: addBlacklistEntry, createAccessPoint, createAdmissionRules, setAccessPointDirection | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: addBlacklistEntry, createAccessPoint, createAdmissionRules, setAccessPointDirection. Spec: handoff/service-docs/backend/AccessService.md#group-accesspoint. Done when `access#addBlacklistEntry`, `access#createAccessPoint`, `access#createAdmissionRules`, `access#setAccessPointDirection` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-ACCESS-ACCESSPOINT-2 | AM-WHITE-LABEL-P01 | [BE] AccessService: setAccessPointGeofence, setTurnstileMode, updateAccessPoint, updateAdmissionRules | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setAccessPointGeofence, setTurnstileMode, updateAccessPoint, updateAdmissionRules. Spec: handoff/service-docs/backend/AccessService.md#group-accesspoint. Done when `access#setAccessPointGeofence`, `access#setTurnstileMode`, `access#updateAccessPoint`, `access#updateAdmissionRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-CATALOGUE-CATALOGUE-1 | AM-WHITE-LABEL-P01 | [BE] CatalogueService: bulkChangePrices, cloneProduct, commitCatalogueImport, getMyMemberships | 8 | Tanmay Dukhande | CatalogueService | MIG-ACCESS MIG-CATALOGUE MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: bulkChangePrices, cloneProduct, commitCatalogueImport, getMyMemberships. Spec: handoff/service-docs/backend/CatalogueService.md#group-catalogue. Done when `catalogue#bulkChangePrices`, `catalogue#cloneProduct`, `catalogue#commitCatalogueImport`, `catalogue#getMyMemberships` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-ORDER-ORDER-1 | AM-WHITE-LABEL-P01 | [BE] OrderService: appendEntitlementToMedia, applyManualDiscount, claimTicketTransfer, createOrder | 8 | Pranay Shinde | OrderService | MIG-ACCESS MIG-ORDERS MIG-PLATFORM MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: appendEntitlementToMedia, applyManualDiscount, claimTicketTransfer, createOrder. Spec: handoff/service-docs/backend/OrderService.md#group-order. Done when `orders#appendEntitlementToMedia`, `orders#applyManualDiscount`, `orders#claimTicketTransfer`, `orders#createOrder` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-ORDER-ORDER-5 | AM-WHITE-LABEL-P01 | [BE] OrderService: resumeOrder, setVisitReminder, transferOrderTickets, voidOrder | 8 | Pranay Shinde | OrderService | MIG-ACCESS MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: resumeOrder, setVisitReminder, transferOrderTickets, voidOrder. Spec: handoff/service-docs/backend/OrderService.md#group-order. Done when `orders#resumeOrder`, `orders#setVisitReminder`, `orders#transferOrderTickets`, `orders#voidOrder` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-ORDER-ORDERS-4 | AM-WHITE-LABEL-P01 | [BE] OrderService: previewProductTickets, recordGroupCheckIn, reissueEntitlement, requestGroupBooking | 8 | Pranay Shinde | OrderService | MIG-ACCESS MIG-CATALOGUE MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: previewProductTickets, recordGroupCheckIn, reissueEntitlement, requestGroupBooking. Spec: handoff/service-docs/backend/OrderService.md#group-orders. Done when `orders#previewProductTickets`, `orders#recordGroupCheckIn`, `orders#reissueEntitlement`, `orders#requestGroupBooking` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-ORDER-ORDERS-3 | AM-WHITE-LABEL-P01 | [BE] OrderService: listBillingStatements, listMyOrders, listPaymentTokens, payByLink | 8 | Deep Khanvilkar | OrderService | MIG-ACCESS MIG-ORDERS MIG-PAYMENTS MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: listBillingStatements, listMyOrders, listPaymentTokens, payByLink. Spec: handoff/service-docs/backend/OrderService.md#group-orders. Done when `orders#listBillingStatements`, `orders#listMyOrders`, `orders#listPaymentTokens`, `orders#payByLink` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-ORDER-ORDERS-5 | AM-WHITE-LABEL-P01 | [BE] OrderService: setPaymentProvider, shareEntitlement, storePaymentToken, updateTicketTemplate | 8 | Pranay Shinde | OrderService | MIG-ACCESS MIG-CATALOGUE MIG-IDENTITY MIG-MARKETING MIG-ORDERS MIG-PAYMENTS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: setPaymentProvider, shareEntitlement, storePaymentToken, updateTicketTemplate. Spec: handoff/service-docs/backend/OrderService.md#group-orders. Done when `orders#setPaymentProvider`, `orders#shareEntitlement`, `orders#storePaymentToken`, `orders#updateTicketTemplate` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-AI-RECOMMEND-1 | AM-WHITE-LABEL-P01 | [BE] AiService: decideRecommendations, recordRecommendationEvents | 3 | Sanket Keluskar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: decideRecommendations, recordRecommendationEvents. Spec: handoff/service-docs/backend/AiService.md#group-recommend Helper task: Tanmay Dukhande owns the service and reviews. Done when `ai#decideRecommendations`, `ai#recordRecommendationEvents` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-MARKETING-CONSENT-3 | AM-WHITE-LABEL-P01 | [BE] MarketingService: listPublishedTrackingTechnologies, recordConsent, recordConsentAnswers, recordDeviceConsent | 8 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: listPublishedTrackingTechnologies, recordConsent, recordConsentAnswers, recordDeviceConsent. Spec: handoff/service-docs/backend/MarketingService.md#group-consent. Done when `marketing-crm#listPublishedTrackingTechnologies`, `marketing-crm#recordConsent`, `marketing-crm#recordConsentAnswers`, `marketing-crm#recordDeviceConsent` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-CATALOGUE-CATALOGUE-2 | AM-WHITE-LABEL-P02 | [BE] CatalogueService: listProductCategories, searchCatalogue, setProductCategories | 5 | Tanmay Dukhande | CatalogueService | MIG-CATALOGUE MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listProductCategories, searchCatalogue, setProductCategories. Spec: handoff/service-docs/backend/CatalogueService.md#group-catalogue Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#listProductCategories`, `catalogue#searchCatalogue`, `catalogue#setProductCategories` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-CATALOGUE-PRODUCT-2 | AM-WHITE-LABEL-P01 | [BE] CatalogueService: listAlternativeCodes, listGroupPackages, listProductVariants, listProducts | 8 | Tanmay Dukhande | CatalogueService | MIG-CATALOGUE MIG-WHITELABEL PLATFORM-KERNEL SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-2 SVC-CATALOGUE-PRODUCT-3 SVC-CATALOGUE-PRODUCT-4 SVC-WHITELABEL-CONTENT-1 SVC-WHITELABEL-CONTENT-2 SVC-WHITELABEL-CONTENT-5 SVC-WHITELABEL-CONTENT-7 | Operations: listAlternativeCodes, listGroupPackages, listProductVariants, listProducts. Spec: handoff/service-docs/backend/CatalogueService.md#group-product. Done when `catalogue#listAlternativeCodes`, `catalogue#listGroupPackages`, `catalogue#listProductVariants`, `catalogue#listProducts` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-MARKETING-MARKETING-3 | AM-WHITE-LABEL-P02 | [BE] MarketingService: getMyProfile, getSeoMetadata, getWaiverStatus, handoverToAgent | 8 | Pranay Shinde | MarketingService | MIG-ACCESS MIG-CATALOGUE MIG-CONTROL MIG-MARKETING MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: getMyProfile, getSeoMetadata, getWaiverStatus, handoverToAgent. Spec: handoff/service-docs/backend/MarketingService.md#group-marketing. Done when `marketing-crm#getMyProfile`, `marketing-crm#getSeoMetadata`, `marketing-crm#getWaiverStatus`, `marketing-crm#handoverToAgent` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-MARKETING-MARKETING-5 | AM-WHITE-LABEL-P02 | [BE] MarketingService: redeemLoyaltyPoints, replyToMyCase, respondToInvitation, sendConversationMessage | 8 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: redeemLoyaltyPoints, replyToMyCase, respondToInvitation, sendConversationMessage. Spec: handoff/service-docs/backend/MarketingService.md#group-marketing. Done when `marketing-crm#redeemLoyaltyPoints`, `marketing-crm#replyToMyCase`, `marketing-crm#respondToInvitation`, `marketing-crm#sendConversationMessage` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-MARKETING-MARKETING-4 | AM-WHITE-LABEL-P02 | [BE] MarketingService: identifyGuest, listMyCases, raiseMyCase, recordLostItem | 8 | Pranay Shinde | MarketingService | MIG-ACCESS MIG-MARKETING MIG-PII MIG-VENUEMAP PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: identifyGuest, listMyCases, raiseMyCase, recordLostItem. Spec: handoff/service-docs/backend/MarketingService.md#group-marketing. Done when `marketing-crm#identifyGuest`, `marketing-crm#listMyCases`, `marketing-crm#raiseMyCase`, `marketing-crm#recordLostItem` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-TENANCY-SCOPE-1 | AM-WHITE-LABEL-P13 | [BE] TenancyService: createOrgUnit, listOrgUnits, updateOrgUnit | 3 | Sanket Keluskar | TenancyService | MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createOrgUnit, listOrgUnits, updateOrgUnit. Spec: handoff/service-docs/backend/TenancyService.md#group-scope Helper task: Hrushikant Patkar owns the service and reviews. Done when `tenancy#createOrgUnit`, `tenancy#listOrgUnits`, `tenancy#updateOrgUnit` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-APPPUBLISHING-1 | AM-WHITE-LABEL-P13 | [BE] WhiteLabelService: getAppBuild, getStoreAccounts, listAppBuilds, requestAppBuild | 5 | Deep Khanvilkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getAppBuild, getStoreAccounts, listAppBuilds, requestAppBuild. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-apppublishing Helper task: Tanmay Dukhande owns the service and reviews. Done when `white-label#getAppBuild`, `white-label#getStoreAccounts`, `white-label#listAppBuilds`, `white-label#requestAppBuild` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-APPPUBLISHING-2 | AM-WHITE-LABEL-P13 | [BE] WhiteLabelService: setStoreAccounts | 2 | Chinmay Patkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setStoreAccounts. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-apppublishing Helper task: Tanmay Dukhande owns the service and reviews. Done when `white-label#setStoreAccounts` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-BOOKINGFLOWS-1 | AM-WHITE-LABEL-P13 | [BE] WhiteLabelService: createBookingFlowDefinition, deleteBookingFlow, getBookingFlow, getPublishedBookingFlow | 8 | Hrushikant Patkar | WhiteLabelService | MIG-CATALOGUE MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createBookingFlowDefinition, deleteBookingFlow, getBookingFlow, getPublishedBookingFlow. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-bookingflows. Done when `white-label#createBookingFlowDefinition`, `white-label#deleteBookingFlow`, `white-label#getBookingFlow`, `white-label#getPublishedBookingFlow` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-BOOKINGFLOWS-2 | AM-WHITE-LABEL-P13 | [BE] WhiteLabelService: listBookingFlowTypes, listBookingFlows, updateBookingFlowDefinition, validateBookingFlow | 8 | Hrushikant Patkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listBookingFlowTypes, listBookingFlows, updateBookingFlowDefinition, validateBookingFlow. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-bookingflows. Done when `white-label#listBookingFlowTypes`, `white-label#listBookingFlows`, `white-label#updateBookingFlowDefinition`, `white-label#validateBookingFlow` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-BRAND-1 | AM-WHITE-LABEL-P13 | [BE] WhiteLabelService: getAppIcons, getBrandIdentity, setAppIcons, setBrandIdentity | 5 | Deep Khanvilkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getAppIcons, getBrandIdentity, setAppIcons, setBrandIdentity. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-brand Helper task: Tanmay Dukhande owns the service and reviews. Done when `white-label#getAppIcons`, `white-label#getBrandIdentity`, `white-label#setAppIcons`, `white-label#setBrandIdentity` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-BRANDING-1 | AM-WHITE-LABEL-P13 | [BE] WhiteLabelService: getBookingFlowConfig, setBookingFlowConfig | 5 | Hrushikant Patkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getBookingFlowConfig, setBookingFlowConfig. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-branding Helper task: Tanmay Dukhande owns the service and reviews. Done when `white-label#getBookingFlowConfig`, `white-label#setBookingFlowConfig` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-HOMEPAGE-1 | AM-WHITE-LABEL-P13 | [BE] WhiteLabelService: getHomepageLayout, listLandingPageTemplates, setHomepageLayout | 3 | Sanket Keluskar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getHomepageLayout, listLandingPageTemplates, setHomepageLayout. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-homepage Helper task: Tanmay Dukhande owns the service and reviews. Done when `white-label#getHomepageLayout`, `white-label#listLandingPageTemplates`, `white-label#setHomepageLayout` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-NAVIGATION-1 | AM-WHITE-LABEL-P13 | [BE] WhiteLabelService: buildDeepLink, getDeepLinkScheme, getNavigation, setHeader | 3 | Sanket Keluskar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: buildDeepLink, getDeepLinkScheme, getNavigation, setHeader. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-navigation Helper task: Tanmay Dukhande owns the service and reviews. Done when `white-label#buildDeepLink`, `white-label#getDeepLinkScheme`, `white-label#getNavigation`, `white-label#setHeader` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-NAVIGATION-2 | AM-WHITE-LABEL-P13 | [BE] WhiteLabelService: setNavigation | 2 | Chinmay Patkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setNavigation. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-navigation Helper task: Tanmay Dukhande owns the service and reviews. Done when `white-label#setNavigation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-WHITELABEL-OVERVIEW-1 | AM-IDENTITY-SECURITY-P09 | [BE] WhiteLabelService: getPublishedTenantConfig, getTenantAppStatus, getTenantConfig, listAnalyticsProviders | 8 | Hrushikant Patkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-KERNEL SVC-WHITELABEL-BOOKINGFLOWS-1 SVC-WHITELABEL-BOOKINGFLOWS-2 SVC-WHITELABEL-BRAND-1 SVC-WHITELABEL-BRANDING-1 SVC-WHITELABEL-CONTENT-2 SVC-WHITELABEL-HOMEPAGE-1 SVC-WHITELABEL-MODULES-1 SVC-WHITELABEL-MODULES-2 SVC-WHITELABEL-NAVIGATION-1 SVC-WHITELABEL-NAVIGATION-2 SVC-WHITELABEL-OVERVIEW-2 SVC-WHITELABEL-PUBLISHING-1 SVC-WHITELABEL-PUBLISHING-2 SVC-WHITELABEL-PUBLISHING-3 SVC-WHITELABEL-THEME-1 SVC-WHITELABEL-WHITELABEL-1 | Operations: getPublishedTenantConfig, getTenantAppStatus, getTenantConfig, listAnalyticsProviders. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-overview. Done when `white-label#getPublishedTenantConfig`, `white-label#getTenantAppStatus`, `white-label#getTenantConfig`, `white-label#listAnalyticsProviders` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-WHITE-LABEL-1 | AM-WHITE-LABEL-P13 | [BE] WhiteLabelService: claimCustomDomain, getPlatformSubdomain, listCustomDomains, regenerateDomainToken | 5 | Deep Khanvilkar | WhiteLabelService | MIG-CONTROL MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: claimCustomDomain, getPlatformSubdomain, listCustomDomains, regenerateDomainToken. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-white-label Helper task: Tanmay Dukhande owns the service and reviews. Done when `white-label#claimCustomDomain`, `white-label#getPlatformSubdomain`, `white-label#listCustomDomains`, `white-label#regenerateDomainToken` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-WHITE-LABEL-2 | AM-WHITE-LABEL-P13 | [BE] WhiteLabelService: relinquishCustomDomain, setPrimaryDomain, verifyCustomDomain | 5 | Deep Khanvilkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: relinquishCustomDomain, setPrimaryDomain, verifyCustomDomain. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-white-label Helper task: Tanmay Dukhande owns the service and reviews. Done when `white-label#relinquishCustomDomain`, `white-label#setPrimaryDomain`, `white-label#verifyCustomDomain` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-WHITELABEL-WHITELABEL-2 | AM-WHITE-LABEL-P13 | [BE] WhiteLabelService: updateContentBlock | 2 | Chinmay Patkar | WhiteLabelService | MIG-CONTROL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updateContentBlock. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-whitelabel Helper task: Tanmay Dukhande owns the service and reviews. Done when `white-label#updateContentBlock` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 1 | SVC-WHITELABEL-CONTENT-3 | AM-WHITE-LABEL-P13 | [BE] WhiteLabelService: getPublishedGuidedChoice, listBanners, listContentPages, listGuidedChoices | 5 | Deep Khanvilkar | WhiteLabelService | MIG-WHITELABEL PLATFORM-KERNEL SVC-WHITELABEL-CONTENT-1 SVC-WHITELABEL-CONTENT-2 SVC-WHITELABEL-CONTENT-5 SVC-WHITELABEL-CONTENT-6 SVC-WHITELABEL-CONTENT-7 | Operations: getPublishedGuidedChoice, listBanners, listContentPages, listGuidedChoices. Spec: handoff/service-docs/backend/WhiteLabelService.md#group-content Helper task: Tanmay Dukhande owns the service and reviews. Done when `white-label#getPublishedGuidedChoice`, `white-label#listBanners`, `white-label#listContentPages`, `white-label#listGuidedChoices` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-CATALOGUE-EVENT-2 | AM-WHITE-LABEL-P13 | [BE] CatalogueService: getWaitingRoomPosition, listEvents, listPerformances, updateEvent | 5 | Chinmay Patkar | CatalogueService | MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getWaitingRoomPosition, listEvents, listPerformances, updateEvent. Spec: handoff/service-docs/backend/CatalogueService.md#group-event Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#getWaitingRoomPosition`, `catalogue#listEvents`, `catalogue#listPerformances`, `catalogue#updateEvent` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-ORDER-CART-1 | AM-WHITE-LABEL-P13 | [BE] OrderService: abandonCart, addCartLine, applyCartPromoCode, checkoutCart | 8 | Pranay Shinde | OrderService | MIG-CATALOGUE MIG-MARKETING MIG-ORDERS MIG-PLATFORM MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: abandonCart, addCartLine, applyCartPromoCode, checkoutCart. Spec: handoff/service-docs/backend/OrderService.md#group-cart. Done when `orders#abandonCart`, `orders#addCartLine`, `orders#applyCartPromoCode`, `orders#checkoutCart` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-AI-ASSIST-1 | AM-WHITE-LABEL-P13 | [BE] AiService: createAiConversation, listAiConversations, sendAiMessage | 5 | Deep Khanvilkar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createAiConversation, listAiConversations, sendAiMessage. Spec: handoff/service-docs/backend/AiService.md#group-assist Helper task: Tanmay Dukhande owns the service and reviews. Done when `ai#createAiConversation`, `ai#listAiConversations`, `ai#sendAiMessage` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-AI-CONFIGURE-1 | AM-WHITE-LABEL-P13 | [BE] AiService: getGuidedChoiceSuggestion, suggestGuidedChoice | 3 | Sanket Keluskar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getGuidedChoiceSuggestion, suggestGuidedChoice. Spec: handoff/service-docs/backend/AiService.md#group-configure Helper task: Tanmay Dukhande owns the service and reviews. Done when `ai#getGuidedChoiceSuggestion`, `ai#suggestGuidedChoice` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-AI-GOVERNANCE-1 | AM-WHITE-LABEL-P13 | [BE] AiService: createAiGovernancePolicyDraft, decideProposedAction, evaluateAiGovernance, getAiUsage | 8 | Tanmay Dukhande | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createAiGovernancePolicyDraft, decideProposedAction, evaluateAiGovernance, getAiUsage. Spec: handoff/service-docs/backend/AiService.md#group-governance. Done when `ai#createAiGovernancePolicyDraft`, `ai#decideProposedAction`, `ai#evaluateAiGovernance`, `ai#getAiUsage` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-AI-GENERATE-1 | AM-WHITE-LABEL-P13 | [BE] AiService: proposeMarketingContent | 3 | Sanket Keluskar | AiService | MIG-AI MIG-CATALOGUE MIG-CONTROL MIG-MARKETING MIG-PROMOTIONS MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: proposeMarketingContent. Spec: handoff/service-docs/backend/AiService.md#group-generate Helper task: Tanmay Dukhande owns the service and reviews. Done when `ai#proposeMarketingContent` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-MARKETING-CONSENT-4 | AM-WHITE-LABEL-P13 | [BE] MarketingService: setConsentPurposes, setCookieBannerDesign, setDynamicFieldQuestion, setTrackingTechnology | 8 | Pranay Shinde | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setConsentPurposes, setCookieBannerDesign, setDynamicFieldQuestion, setTrackingTechnology. Spec: handoff/service-docs/backend/MarketingService.md#group-consent. Done when `marketing-crm#setConsentPurposes`, `marketing-crm#setCookieBannerDesign`, `marketing-crm#setDynamicFieldQuestion`, `marketing-crm#setTrackingTechnology` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-MARKETING-CONSENT-5 | AM-WHITE-LABEL-P13 | [BE] MarketingService: updateConsentQuestion | 2 | Chinmay Patkar | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updateConsentQuestion. Spec: handoff/service-docs/backend/MarketingService.md#group-consent Helper task: Pranay Shinde owns the service and reviews. Done when `marketing-crm#updateConsentQuestion` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-MARKETING-MARKETING-6 | AM-WHITE-LABEL-P13 | [BE] MarketingService: setAgentAvailability, setSeoMetadata, submitForm, updateGuestPreferences | 8 | Pranay Shinde | MarketingService | MIG-CATALOGUE MIG-CONTROL MIG-IDENTITY MIG-MARKETING MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setAgentAvailability, setSeoMetadata, submitForm, updateGuestPreferences. Spec: handoff/service-docs/backend/MarketingService.md#group-marketing. Done when `marketing-crm#setAgentAvailability`, `marketing-crm#setSeoMetadata`, `marketing-crm#submitForm`, `marketing-crm#updateGuestPreferences` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-MARKETING-MARKETING-7 | AM-WHITE-LABEL-P13 | [BE] MarketingService: updateMyProfile, uploadGuestDocument | 3 | Sanket Keluskar | MarketingService | MIG-MARKETING MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updateMyProfile, uploadGuestDocument. Spec: handoff/service-docs/backend/MarketingService.md#group-marketing Helper task: Pranay Shinde owns the service and reviews. Done when `marketing-crm#updateMyProfile`, `marketing-crm#uploadGuestDocument` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-AI-AI-1 | AM-WHITE-LABEL-P13 | [BE] AiService: getTranslationProposals, proposeTranslations, proposeVenueLabels, requestSuggestion | 8 | Pranay Shinde | AiService | MIG-AI MIG-CONTROL MIG-FNB MIG-INVENTORY MIG-MARKETING MIG-QUEUE MIG-VENUEMAP PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getTranslationProposals, proposeTranslations, proposeVenueLabels, requestSuggestion. Spec: handoff/service-docs/backend/AiService.md#group-ai. Done when `ai#getTranslationProposals`, `ai#proposeTranslations`, `ai#proposeVenueLabels`, `ai#requestSuggestion` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-TENANCY-DELEGATION-1 | AM-SETUP-PLATFORM-FOUNDATION-P08 | [BE] TenancyService: createApprovalDelegation | 2 | Chinmay Patkar | TenancyService | MIG-APPROVALS MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createApprovalDelegation. Spec: handoff/service-docs/backend/TenancyService.md#group-delegation Helper task: Hrushikant Patkar owns the service and reviews. Done when `approvals#createApprovalDelegation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-TENANCY-IDENTITY-1 | AM-SETUP-PLATFORM-FOUNDATION-P08 | [BE] TenancyService: setRolePermissions | 2 | Chinmay Patkar | TenancyService | MIG-IDENTITY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setRolePermissions. Spec: handoff/service-docs/backend/TenancyService.md#group-identity Helper task: Hrushikant Patkar owns the service and reviews. Done when `tenancy#setRolePermissions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-TENANCY-MATRIX-1 | AM-SETUP-PLATFORM-FOUNDATION-P08 | [BE] TenancyService: setApprovalExternalProvider, setApprovalMatrix | 5 | Deep Khanvilkar | TenancyService | MIG-APPROVALS MIG-CONTROL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setApprovalExternalProvider, setApprovalMatrix. Spec: handoff/service-docs/backend/TenancyService.md#group-matrix Helper task: Hrushikant Patkar owns the service and reviews. Done when `approvals#setApprovalExternalProvider`, `approvals#setApprovalMatrix` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-TENANCY-TENANCY-1 | AM-SETUP-PLATFORM-FOUNDATION-P08 | [BE] TenancyService: getWorkstationHealth, setVenueSettings, setVenueSettingsDefaults | 5 | Deep Khanvilkar | TenancyService | MIG-ACCESS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getWorkstationHealth, setVenueSettings, setVenueSettingsDefaults. Spec: handoff/service-docs/backend/TenancyService.md#group-tenancy. Done when `tenancy#getWorkstationHealth`, `tenancy#setVenueSettings`, `tenancy#setVenueSettingsDefaults` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-FNB-9 | AM-SETUP-PLATFORM-FOUNDATION-P08 | [BE] FnbService: setCourseRules, setKitchenSla, setSubstitutionRules, setTableCombinations | 5 | Tanmay Dukhande | FnbService | MIG-FNB PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setCourseRules, setKitchenSla, setSubstitutionRules, setTableCombinations. Spec: handoff/service-docs/backend/FnbService.md#group-fnb. Done when `fnb#setCourseRules`, `fnb#setKitchenSla`, `fnb#setSubstitutionRules`, `fnb#setTableCombinations` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
9 | 2 | VM-MIG-WORKFORCE | AM-SETUP-PLATFORM-FOUNDATION-P08-REST | [DB] Forward migration V1036__workforce.sql: workforce for Venue Management (6 tables) | 3 | Hrushikant Patkar |  | MIG-WORKFORCE | Tables: workforce.announcement, workforce.announcement_receipt, workforce.employee, workforce.job_title, workforce.shift, workforce.work_assignment. Source DDL: backend/tenant/010-workforce.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `workforce.announcement`, `workforce.announcement_receipt`, `workforce.employee`, `workforce.job_title`, `workforce.shift`, `workforce.work_assignment` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
7 | 3 | MIG-IDENTITY-3 | AM-SETUP-PLATFORM-FOUNDATION-P08-REST | [DB] Forward migration V1058__identity.sql: identity for Identity & Security · Venue Management (12 tables) | 8 | Hrushikant Patkar | IdentityService | MIG-BASELINE MIG-IDENTITY VM-MIG-IDENTITY | Tables: identity.access_override, identity.access_review_campaign, identity.access_review_item, identity.authorisation_policy, identity.authorisation_policy_version, identity.authz_audit, identity.benefit_usage, identity.customer_membership, identity.membership_history, identity.module, identity.module_access, identity.permission. Source DDL: backend/tenant/010-identity.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `identity.access_override`, `identity.access_review_campaign`, `identity.access_review_item`, `identity.authorisation_policy`, `identity.authorisation_policy_version`, `identity.authz_audit`, `identity.benefit_usage`, `identity.customer_membership` and 4 more runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 2 | VM-IDENTITY-ADMINISTRATION-1 | AM-SETUP-PLATFORM-FOUNDATION-P08-REST | [BE] IdentityService: createPrincipal, getPrincipal, listPlatformStaffGrants, resetPrincipalCredential | 5 | Hrushikant Patkar | IdentityService | MIG-IDENTITY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations beyond the first release: createPrincipal, getPrincipal, listPlatformStaffGrants, resetPrincipalCredential. Additive to IdentityService; its first-release owner (Pranay Shinde) reviews. Helper task: Pranay Shinde owns the service and reviews. Done when `identity#createPrincipal`, `identity#getPrincipal`, `identity#listPlatformStaffGrants`, `identity#resetPrincipalCredential` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 2 | VM-TENANCY-MATRIX-1 | AM-SETUP-PLATFORM-FOUNDATION-P08-REST | [BE] TenancyService: listApprovalMatrices | 1 | Chinmay Patkar | TenancyService | MIG-APPROVALS PLATFORM-KERNEL SVC-TENANCY-APPROVALS-1 SVC-TENANCY-MATRIX-1 | Operations beyond the first release: listApprovalMatrices. Additive to TenancyService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `approvals#listApprovalMatrices` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-DELEGATION-2 | AM-SETUP-PLATFORM-FOUNDATION-P08-REST | [BE] TenancyService: listApprovalDelegations, revokeApprovalDelegation | 2 | Pranay Shinde | TenancyService | MIG-APPROVALS MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listApprovalDelegations, revokeApprovalDelegation. Spec: contracts (approvals) at the release tag, served by ADAM. Built for Platform Foundation · Venue Management (setup, the rest of the screens); additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `approvals#listApprovalDelegations`, `approvals#revokeApprovalDelegation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-MATRIX-2 | AM-SETUP-PLATFORM-FOUNDATION-P08-REST | [BE] TenancyService: listApprovalExternalProviders, listStepUpPolicies, setStepUpPolicy | 3 | Tanmay Dukhande | TenancyService | MIG-APPROVALS MIG-APPROVALS-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listApprovalExternalProviders, listStepUpPolicies, setStepUpPolicy. Spec: contracts (approvals) at the release tag, served by ADAM. Built for Platform Foundation · Venue Management (setup, the rest of the screens); additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `approvals#listApprovalExternalProviders`, `approvals#listStepUpPolicies`, `approvals#setStepUpPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-IDENTITY-IDENTITY-10 | AM-SETUP-PLATFORM-FOUNDATION-P08-REST | [BE] IdentityService: getGuestVerificationPolicy, getPasswordPolicy | 2 | Pranay Shinde | IdentityService | MIG-IDENTITY PLATFORM-KERNEL SVC-IDENTITY-IDENTITY-3 | Operations: getGuestVerificationPolicy, getPasswordPolicy. Spec: contracts (identity) at the release tag, served by ADAM. Built for Platform Foundation · Venue Management (setup, the rest of the screens); additive to IdentityService, whose first-release owner (Pranay Shinde) reviews. Done when `identity#getGuestVerificationPolicy`, `identity#getPasswordPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-TENANCY-REQUEST-5 | AM-SETUP-PLATFORM-FOUNDATION-P08-REST | [BE] TenancyService: listApprovalExternalDispatches | 1 | Chinmay Patkar | TenancyService | MIG-APPROVALS-5 PLATFORM-KERNEL SVC-TENANCY-REQUEST-2 | Operations: listApprovalExternalDispatches. Spec: contracts (approvals) at the release tag, served by ADAM. Built for Platform Foundation · Venue Management (setup, the rest of the screens); additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `approvals#listApprovalExternalDispatches` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-TENANCY-SCOPE-2 | AM-SETUP-PLATFORM-FOUNDATION-P08-REST | [BE] TenancyService: getOrgUnit | 1 | Deep Khanvilkar | TenancyService | MIG-PLATFORM PLATFORM-KERNEL SVC-TENANCY-SCOPE-1 | Operations: getOrgUnit. Spec: contracts (tenancy) at the release tag, served by ADAM. Built for Platform Foundation · Venue Management (setup, the rest of the screens); additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `tenancy#getOrgUnit` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-TENANCY-TENANCY-6 | AM-SETUP-PLATFORM-FOUNDATION-P08-REST | [BE] TenancyService: getVenueSettingsDefaults | 2 | Surendra | TenancyService | MIG-PLATFORM PLATFORM-KERNEL SVC-TENANCY-TENANCY-1 | Operations: getVenueSettingsDefaults. Spec: contracts (tenancy) at the release tag, served by ADAM. Built for Platform Foundation · Venue Management (setup, the rest of the screens); additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `tenancy#getVenueSettingsDefaults` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-PLATFORM-PLAN-1 | AM-SETUP-PLATFORM-FOUNDATION-P09 | [BE] PlatformService: createPlan, createPlanVersion | 5 | Deep Khanvilkar | PlatformService | MIG-CONTROL MIG-SUBSCRIPTION PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createPlan, createPlanVersion. Spec: handoff/service-docs/backend/PlatformService.md#group-plan Helper task: Pranay Shinde owns the service and reviews. Done when `subscription#createPlan`, `subscription#createPlanVersion` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-PLATFORM-TENANT-2 | AM-SETUP-PLATFORM-FOUNDATION-P09 | [BE] PlatformService: terminateTenant, updateTenant | 3 | Sanket Keluskar | PlatformService | MIG-CONTROL MIG-SUBSCRIPTION PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: terminateTenant, updateTenant. Spec: handoff/service-docs/backend/PlatformService.md#group-tenant Helper task: Pranay Shinde owns the service and reviews. Done when `subscription#terminateTenant`, `subscription#updateTenant` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-IDENTITY-SSO-2 | AM-SETUP-PLATFORM-FOUNDATION-P09-REST | [BE] IdentityService: getSsoConfig, setSsoConfig | 3 | Pranay Shinde | IdentityService | MIG-IDENTITY-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getSsoConfig, setSsoConfig. Spec: contracts (identity) at the release tag, served by ADAM. Built for Platform Foundation · TICVAI Console (setup, the rest of the screens); additive to IdentityService, whose first-release owner (Pranay Shinde) reviews. Done when `identity#getSsoConfig`, `identity#setSsoConfig` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-LICENSING-3 | AM-SETUP-PLATFORM-FOUNDATION-P09-REST | [BE] PlatformService: removeLicenceAddOn | 2 | Tanmay Dukhande | PlatformService | MIG-CONTROL MIG-SUBSCRIPTION PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: removeLicenceAddOn. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Platform Foundation · TICVAI Console (setup, the rest of the screens); additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#removeLicenceAddOn` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-PLATFORM-PLAN-2 | AM-SETUP-PLATFORM-FOUNDATION-P09-REST | [BE] PlatformService: getPlan, listPlans | 2 | Tanmay Dukhande | PlatformService | MIG-SUBSCRIPTION PLATFORM-KERNEL SVC-PLATFORM-PLAN-1 | Operations: getPlan, listPlans. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Platform Foundation · TICVAI Console (setup, the rest of the screens); additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#getPlan`, `subscription#listPlans` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-PLATFORM-SUBSCRIPTION-19 | AM-SETUP-PLATFORM-FOUNDATION-P09-REST | [BE] PlatformService: getSubscription, previewSubscriptionChange | 3 | Tanmay Dukhande | PlatformService | MIG-PLATFORM MIG-SUBSCRIPTION PLATFORM-KERNEL SVC-PLATFORM-LICENSING-3 SVC-PLATFORM-PLAN-1 SVC-PLATFORM-SUBSCRIPTION-1 SVC-PLATFORM-TENANT-2 | Operations: getSubscription, previewSubscriptionChange. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Platform Foundation · TICVAI Console (setup, the rest of the screens); additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#getSubscription`, `subscription#previewSubscriptionChange` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-ORDER-ORDERS-7 | AM-SETUP-PLATFORM-FOUNDATION-P09-REST | [BE] OrderService: listPaymentProviders | 1 | Tanmay Dukhande | OrderService | MIG-PAYMENTS PLATFORM-KERNEL SVC-ORDER-ORDERS-5 | Operations: listPaymentProviders. Spec: contracts (orders) at the release tag, served by ADAM. Built for Platform Foundation · TICVAI Console (setup, the rest of the screens); additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listPaymentProviders` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-PLATFORM-PUBLICAPI-2 | AM-SETUP-PLATFORM-FOUNDATION-P14 | [BE] PlatformService: registerDeveloper, rotateApiCredential, setApiClientStatus, setApiLicensing | 5 | Deep Khanvilkar | PlatformService | MIG-CONTROL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: registerDeveloper, rotateApiCredential, setApiClientStatus, setApiLicensing. Spec: handoff/service-docs/backend/PlatformService.md#group-publicapi Helper task: Pranay Shinde owns the service and reviews. Done when `public-api#registerDeveloper`, `public-api#rotateApiCredential`, `public-api#setApiClientStatus`, `public-api#setApiLicensing` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-PLATFORM-PUBLICAPI-3 | AM-SETUP-PLATFORM-FOUNDATION-P14 | [BE] PlatformService: setDeveloperMembers | 1 | Sanket Keluskar | PlatformService | MIG-CONTROL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setDeveloperMembers. Spec: handoff/service-docs/backend/PlatformService.md#group-publicapi Helper task: Pranay Shinde owns the service and reviews. Done when `public-api#setDeveloperMembers` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-PLATFORM-PUBLICAPI-1 | AM-SETUP-PLATFORM-FOUNDATION-P14 | [BE] PlatformService: certifyIntegration, createApiClient, decideProductionAccess, deprecateApiVersion | 8 | Tanmay Dukhande | PlatformService | MIG-CONTROL MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: certifyIntegration, createApiClient, decideProductionAccess, deprecateApiVersion. Spec: handoff/service-docs/backend/PlatformService.md#group-publicapi. Done when `public-api#certifyIntegration`, `public-api#createApiClient`, `public-api#decideProductionAccess`, `public-api#deprecateApiVersion` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-PLATFORM-PUBLICAPI-7 | AM-PUBLIC-API-P14-BLOCK-A | [BE] PlatformService: listApiScopes, listApiVersions | 2 | Pranay Shinde | PlatformService | MIG-CONTROL PLATFORM-KERNEL SVC-PLATFORM-PUBLICAPI-1 SVC-PLATFORM-PUBLICAPI-2 | Operations: listApiScopes, listApiVersions. Spec: contracts (public-api) at the release tag, served by ADAM. Built for Public API · Developer Portal (Block A); additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `public-api#listApiScopes`, `public-api#listApiVersions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
5 | 2 | VM-MIG-CONTROL | AM-SETUP-PLATFORM-FOUNDATION-P14-REST | [DB] Forward migration V1003__control.sql: control for Venue Management (2 tables) | 1 | Hrushikant Patkar |  | MIG-CONTROL | Tables: control.webhook_delivery, control.webhook_subscription. Source DDL: backend/control/010-control.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `control.webhook_delivery`, `control.webhook_subscription` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
6 | 3 | MIG-CONTROL-4 | AM-TENANCY-VENUES-P08-BLOCK-A | [DB] Forward migration V1074__control.sql: control for Tenancy & Venues · Venue Management (Block A) (1 tables) | 1 | Hrushikant Patkar | PlatformService | MIG-BASELINE MIG-CONTROL VM-MIG-CONTROL | Tables: control.tenant_domain. Source DDL: backend/control/010-control.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `control.tenant_domain` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-TENANCY-TENANCY-4 | AM-TENANCY-VENUES-P08-BLOCK-A | [BE] TenancyService: resolveTenantHost, setTenantDomainMapping | 3 | Surendra | TenancyService | MIG-CONTROL MIG-CONTROL-4 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: resolveTenantHost, setTenantDomainMapping. Spec: contracts (tenancy) at the release tag, served by ADAM. Built for Tenancy & Venues · Venue Management (Block A); additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `tenancy#resolveTenantHost`, `tenancy#setTenantDomainMapping` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
6 | 3 | MIG-CONTROL-6 | AM-SUBSCRIPTION-LICENSING-P09 | [DB] Forward migration V1004__control.sql: control for Platform Operations · TICVAI Console 1 of 2 (17 tables) | 8 | Hrushikant Patkar | PlatformService | MIG-BASELINE MIG-CONTROL VM-MIG-CONTROL | Tables: control.cell, control.config_package, control.config_package_application, control.config_package_diff, control.environment, control.migration, control.migration_plan, control.migration_plan_cell, control.migration_run, control.migration_run_cell, control.migration_run_tenant, control.outbox_republish, control.release_component, control.rollout_cell, control.rollout_tenant, control.support_notice, control.upgrade_schedule. Source DDL: backend/control/010-control.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `control.cell`, `control.config_package`, `control.config_package_application`, `control.config_package_diff`, `control.environment`, `control.migration`, `control.migration_plan`, `control.migration_plan_cell` and 9 more runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
6 | 3 | MIG-CONTROL-7 | AM-SUBSCRIPTION-LICENSING-P09 | [DB] Forward migration V1090__control.sql: control for Subscription & Licensing · Venue Management 1 of 3 (21 tables) | 8 | Hrushikant Patkar | PlatformService | MIG-BASELINE MIG-CONTROL VM-MIG-CONTROL | Tables: control.burst_environment, control.cell_cluster, control.invoice, control.partner_application_review_task, control.partner_capability_grant, control.partner_case, control.partner_commission_line, control.partner_commission_rule, control.partner_commission_rule_tier, control.partner_contact, control.partner_credit_profile, control.partner_distribution_right, control.partner_document, control.partner_rate, control.partner_reconciliation_exception, control.partner_scope_assignment, control.partner_security, control.partner_settlement_batch, control.tenant_migration, control.tenant_migration_plan, control.usage_record. Source DDL: backend/control/010-control.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `control.burst_environment`, `control.cell_cluster`, `control.invoice`, `control.partner_application_review_task`, `control.partner_capability_grant`, `control.partner_case`, `control.partner_commission_line`, `control.partner_commission_rule` and 13 more runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
6 | 3 | MIG-CONTROL-8 | AM-SUBSCRIPTION-LICENSING-P09 | [DB] Forward migration V1092__control.sql: control for Subscription & Licensing · TICVAI Console 1 of 6 (2 tables) | 1 | Hrushikant Patkar | PlatformService | MIG-BASELINE MIG-CONTROL VM-MIG-CONTROL | Tables: control.cell_instance, control.cell_job. Source DDL: backend/control/010-control.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `control.cell_instance`, `control.cell_job` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-PLATFORM-CELL-5 | AM-SUBSCRIPTION-LICENSING-P09 | [BE] PlatformService: updateCellTier | 1 | Pranay Shinde | PlatformService | MIG-CONTROL-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updateCellTier. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · TICVAI Console 1 of 6; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#updateCellTier` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-CELL-3 | AM-SUBSCRIPTION-LICENSING-P09 | [BE] PlatformService: cancelDecommission, decommissionCell, getCell, getCellCapacity | 5 | Pranay Shinde | PlatformService | MIG-CONTROL MIG-CONTROL-6 MIG-CONTROL-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: cancelDecommission, decommissionCell, getCell, getCellCapacity. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · TICVAI Console 1 of 6; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#cancelDecommission`, `subscription#decommissionCell`, `subscription#getCell`, `subscription#getCellCapacity` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-PUBLICAPI-9 | AM-PUBLIC-API-API-BLOCK-A-COMPLETION | [BE] PlatformService: replayEvents | 1 | Sanket Keluskar | PlatformService | MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-CONTROL | Operations: replayEvents. Spec: contracts (public-api) at the release tag, served by ADAM. Built for Public API · API only (Block A completion); additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `public-api#replayEvents` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
6 | 3 | MIG-CONTROL-9 | AM-SETUP-PLATFORM-FOUNDATION-P09-REST | [DB] Forward migration V1098__control.sql: control for Subscription & Licensing · TICVAI Console 2 of 6 (3 tables) | 2 | Hrushikant Patkar | PlatformService | MIG-BASELINE MIG-CONTROL VM-MIG-CONTROL | Tables: control.credit_note, control.credit_note_line, control.invoice_line. Source DDL: backend/control/010-control.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `control.credit_note`, `control.credit_note_line`, `control.invoice_line` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-PLATFORM-BILLING-6 | AM-SETUP-PLATFORM-FOUNDATION-P09-REST | [BE] PlatformService: generateInvoice, listSubscriptionInvoices | 5 | Surendra | PlatformService | MIG-CONTROL-7 MIG-CONTROL-9 MIG-SUBSCRIPTION PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: generateInvoice, listSubscriptionInvoices. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Platform Foundation · TICVAI Console (setup, the rest of the screens); additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#generateInvoice`, `subscription#listSubscriptionInvoices` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-CELL-6 | AM-SETUP-PLATFORM-FOUNDATION-P09-REST | [BE] PlatformService: provisionCell | 2 | Pranay Shinde | PlatformService | MIG-CONTROL MIG-CONTROL-6 MIG-CONTROL-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: provisionCell. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Platform Foundation · TICVAI Console (setup, the rest of the screens); additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#provisionCell` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-PLATFORM-CELL-4 | AM-SUBSCRIPTION-LICENSING-P09 | [BE] PlatformService: getCellHealth, listCellJobs, listCells, listTenantCells | 5 | Tanmay Dukhande | PlatformService | MIG-CONTROL MIG-CONTROL-6 MIG-CONTROL-8 PLATFORM-KERNEL SVC-PLATFORM-CELL-3 SVC-PLATFORM-CELL-5 SVC-PLATFORM-CELL-6 | Operations: getCellHealth, listCellJobs, listCells, listTenantCells. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · TICVAI Console 1 of 6; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#getCellHealth`, `subscription#listCellJobs`, `subscription#listCells`, `subscription#listTenantCells` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-PLATFORM-TENANT-3 | AM-SUBSCRIPTION-LICENSING-P09 | [BE] PlatformService: getTenant | 2 | Pranay Shinde | PlatformService | MIG-CONTROL MIG-CONTROL-6 MIG-SUBSCRIPTION PLATFORM-KERNEL SVC-PLATFORM-CELL-3 SVC-PLATFORM-CELL-6 SVC-PLATFORM-LICENSING-3 SVC-PLATFORM-SUBSCRIPTION-1 SVC-PLATFORM-TENANT-1 SVC-PLATFORM-TENANT-2 | Operations: getTenant. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · TICVAI Console 1 of 6; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#getTenant` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-PLATFORM-METERING-2 | AM-SETUP-PLATFORM-FOUNDATION-P09-REST | [BE] PlatformService: getUsageMetering | 1 | Pranay Shinde | PlatformService | MIG-CONTROL-7 MIG-SUBSCRIPTION PLATFORM-KERNEL SVC-PLATFORM-LICENSING-3 SVC-PLATFORM-SUBSCRIPTION-1 SVC-PLATFORM-TENANT-2 | Operations: getUsageMetering. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Platform Foundation · TICVAI Console (setup, the rest of the screens); additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#getUsageMetering` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
6 | 3 | MIG-CONTROL-13 | AM-SETUP-PLATFORM-FOUNDATION-P14-REST | [DB] Forward migration V1181__control.sql: control for Platform Foundation · Developer Portal (setup, the rest of the screens) (2 tables) | 2 | Hrushikant Patkar | PlatformService | MIG-BASELINE MIG-CONTROL VM-MIG-CONTROL | Tables: control.api_anomaly_rule, control.api_limit. Source DDL: backend/control/010-control.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `control.api_anomaly_rule`, `control.api_limit` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 2 | VM-PLATFORM-PUBLICAPI-1 | AM-SETUP-PLATFORM-FOUNDATION-P14-REST | [BE] PlatformService: createWebhookSubscription, listApiClients, listWebhookDeliveries, listWebhookSubscriptions | 3 | Sanket Keluskar | PlatformService | MIG-CONTROL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-CONTROL | Operations beyond the first release: createWebhookSubscription, listApiClients, listWebhookDeliveries, listWebhookSubscriptions. Additive to PlatformService; its first-release owner (Pranay Shinde) reviews. Helper task: Pranay Shinde owns the service and reviews. Done when `public-api#createWebhookSubscription`, `public-api#listApiClients`, `public-api#listWebhookDeliveries`, `public-api#listWebhookSubscriptions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-PUBLICAPI-10 | AM-SETUP-PLATFORM-FOUNDATION-P14-REST | [BE] PlatformService: listDeveloperMembers, listIntegrationListings, listProductionAccessRequests, requestProductionAccess | 3 | Surendra | PlatformService | MIG-CONTROL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listDeveloperMembers, listIntegrationListings, listProductionAccessRequests, requestProductionAccess. Spec: contracts (public-api) at the release tag, served by ADAM. Built for Platform Foundation · Developer Portal (setup, the rest of the screens); additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `public-api#listDeveloperMembers`, `public-api#listIntegrationListings`, `public-api#listProductionAccessRequests`, `public-api#requestProductionAccess` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-PUBLICAPI-11 | AM-SETUP-PLATFORM-FOUNDATION-P14-REST | [BE] PlatformService: revokeApiCredential, setApiAnomalyRule, setApiQuota | 3 | Tanmay Dukhande | PlatformService | MIG-CONTROL MIG-CONTROL-13 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: revokeApiCredential, setApiAnomalyRule, setApiQuota. Spec: contracts (public-api) at the release tag, served by ADAM. Built for Platform Foundation · Developer Portal (setup, the rest of the screens); additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `public-api#revokeApiCredential`, `public-api#setApiAnomalyRule`, `public-api#setApiQuota` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-PLATFORM-GENERAL-1 | AM-SETUP-PLATFORM-FOUNDATION-P14-REST | [BE] PlatformService: getDeveloperAccount, listApiAnomalyRules, listApiLicences, listApiQuotas | 3 | Tanmay Dukhande | PlatformService | MIG-CONTROL MIG-CONTROL-13 PLATFORM-KERNEL SVC-PLATFORM-PUBLICAPI-11 SVC-PLATFORM-PUBLICAPI-2 SVC-PLATFORM-PUBLICAPI-3 | Operations: getDeveloperAccount, listApiAnomalyRules, listApiLicences, listApiQuotas. Spec: contracts (public-api) at the release tag, served by ADAM. Built for Platform Foundation · Developer Portal (setup, the rest of the screens); additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `public-api#getDeveloperAccount`, `public-api#listApiAnomalyRules`, `public-api#listApiLicences`, `public-api#listApiQuotas` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-CATALOGUE-CATEGORY-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] CatalogueService: createSeatCategory, updateSeatCategory | 5 | Chinmay Patkar | CatalogueService | MIG-SEATING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createSeatCategory, updateSeatCategory. Spec: handoff/service-docs/backend/CatalogueService.md#group-category Helper task: Hrushikant Patkar owns the service and reviews. Done when `seating#createSeatCategory`, `seating#updateSeatCategory` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-CATALOGUE-EVENT-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] CatalogueService: createEvent, createPerformances, enterWaitingRoom, getPerformance | 5 | Deep Khanvilkar | CatalogueService | MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createEvent, createPerformances, enterWaitingRoom, getPerformance. Spec: handoff/service-docs/backend/CatalogueService.md#group-event Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#createEvent`, `catalogue#createPerformances`, `catalogue#enterWaitingRoom`, `catalogue#getPerformance` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-CATALOGUE-EVENT-3 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] CatalogueService: updatePerformance | 2 | Chinmay Patkar | CatalogueService | MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updatePerformance. Spec: handoff/service-docs/backend/CatalogueService.md#group-event Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#updatePerformance` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-CATALOGUE-EVENTS-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] CatalogueService: cloneEvent, setEventLifecycleState | 5 | Deep Khanvilkar | CatalogueService | MIG-CATALOGUE MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: cloneEvent, setEventLifecycleState. Spec: handoff/service-docs/backend/CatalogueService.md#group-events Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#cloneEvent`, `catalogue#setEventLifecycleState` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-CATALOGUE-PRICING-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] CatalogueService: copyPriceList, createPriceList, setPrices, updatePriceList | 8 | Tanmay Dukhande | CatalogueService | MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: copyPriceList, createPriceList, setPrices, updatePriceList. Spec: handoff/service-docs/backend/CatalogueService.md#group-pricing. Done when `catalogue#copyPriceList`, `catalogue#createPriceList`, `catalogue#setPrices`, `catalogue#updatePriceList` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-CATALOGUE-SEATING-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] CatalogueService: setAccessibleSeating, setSeatRecommendationRules | 3 | Sanket Keluskar | CatalogueService | MIG-SEATING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setAccessibleSeating, setSeatRecommendationRules. Spec: handoff/service-docs/backend/CatalogueService.md#group-seating Helper task: Hrushikant Patkar owns the service and reviews. Done when `seating#setAccessibleSeating`, `seating#setSeatRecommendationRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-CATALOGUE-SEATMAP-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] CatalogueService: editSeatMapStructure | 3 | Sanket Keluskar | CatalogueService | MIG-SEATING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: editSeatMapStructure. Spec: handoff/service-docs/backend/CatalogueService.md#group-seatmap Helper task: Hrushikant Patkar owns the service and reviews. Done when `seating#editSeatMapStructure` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 1 | SVC-CATALOGUE-BUNDLE-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] CatalogueService: publishBundle, updateBundle | 5 | Deep Khanvilkar | CatalogueService | MIG-CATALOGUE MIG-PLATFORM MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: publishBundle, updateBundle. Spec: handoff/service-docs/backend/CatalogueService.md#group-bundle. Done when `catalogue#publishBundle`, `promotions#updateBundle` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 1 | SVC-CATALOGUE-COUPON-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] CatalogueService: createCouponCampaign, generateCouponCodes, getCouponCode | 8 | Tanmay Dukhande | CatalogueService | MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createCouponCampaign, generateCouponCodes, getCouponCode. Spec: handoff/service-docs/backend/CatalogueService.md#group-coupon. Done when `promotions#createCouponCampaign`, `promotions#generateCouponCodes`, `promotions#getCouponCode` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 1 | SVC-CATALOGUE-DRAFTED-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] CatalogueService: setCodeDistributionManager | 2 | Pranay Shinde | CatalogueService | MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setCodeDistributionManager. Spec: handoff/service-docs/backend/CatalogueService.md#group-drafted Helper task: Hrushikant Patkar owns the service and reviews. Done when `promotions#setCodeDistributionManager` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 1 | SVC-CATALOGUE-PROMOTION-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] CatalogueService: analysePromotionConflicts, createPromotion, getPromotion, getPromotionUsage | 5 | Tanmay Dukhande | CatalogueService | MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: analysePromotionConflicts, createPromotion, getPromotion, getPromotionUsage. Spec: handoff/service-docs/backend/CatalogueService.md#group-promotion. Done when `promotions#analysePromotionConflicts`, `promotions#createPromotion`, `promotions#getPromotion`, `promotions#getPromotionUsage` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 1 | SVC-CATALOGUE-PROMOTION-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] CatalogueService: listPromotions, publishPromotion, updatePromotion | 8 | Deep Khanvilkar | CatalogueService | MIG-PLATFORM MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: listPromotions, publishPromotion, updatePromotion. Spec: handoff/service-docs/backend/CatalogueService.md#group-promotion. Done when `promotions#listPromotions`, `promotions#publishPromotion`, `promotions#updatePromotion` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 1 | SVC-CATALOGUE-PROMOTIONS-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] CatalogueService: setPromotionVariants | 2 | Chinmay Patkar | CatalogueService | MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setPromotionVariants. Spec: handoff/service-docs/backend/CatalogueService.md#group-promotions Helper task: Hrushikant Patkar owns the service and reviews. Done when `promotions#setPromotionVariants` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-ORDER-ORDERS-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] OrderService: getGroupBooking, getPaymentLink, importTicketTemplate, issueWalletPass | 8 | Pranay Shinde | OrderService | MIG-ACCESS MIG-ORDERS MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getGroupBooking, getPaymentLink, importTicketTemplate, issueWalletPass. Spec: handoff/service-docs/backend/OrderService.md#group-orders. Done when `orders#getGroupBooking`, `orders#getPaymentLink`, `orders#importTicketTemplate`, `orders#issueWalletPass` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-CATALOGUE-BUNDLE-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] CatalogueService: createBundle, getBundle, getLatestBundle, listCatalogueBundles | 8 | Tanmay Dukhande | CatalogueService | MIG-CATALOGUE MIG-FNB MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createBundle, getBundle, getLatestBundle, listCatalogueBundles. Spec: handoff/service-docs/backend/CatalogueService.md#group-bundle. Done when `promotions#createBundle`, `promotions#getBundle`, `catalogue#getLatestBundle`, `catalogue#listCatalogueBundles` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-ORDER-ORDERS-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] OrderService: cloneTicketTemplate, createResaleListing, createTicketTemplate, getBillingStatement | 8 | Pranay Shinde | OrderService | MIG-ACCESS MIG-CATALOGUE MIG-LEDGER MIG-ORDERS MIG-PAYMENTS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: cloneTicketTemplate, createResaleListing, createTicketTemplate, getBillingStatement. Spec: handoff/service-docs/backend/OrderService.md#group-orders. Done when `orders#cloneTicketTemplate`, `orders#createResaleListing`, `orders#createTicketTemplate`, `orders#getBillingStatement` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-ORDER-PAYMENTS-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] OrderService: createInstalmentPlan, createPaymentProviderConnection, listInstalmentPlans, setDunningPolicy | 8 | Pranay Shinde | OrderService | MIG-ORDERS MIG-PAYMENTS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: createInstalmentPlan, createPaymentProviderConnection, listInstalmentPlans, setDunningPolicy. Spec: handoff/service-docs/backend/OrderService.md#group-payments. Done when `payments#createInstalmentPlan`, `payments#createPaymentProviderConnection`, `payments#listInstalmentPlans`, `payments#setDunningPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-ORDER-PAYMENTS-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] OrderService: setInstalmentPolicy | 2 | Chinmay Patkar | OrderService | MIG-PAYMENTS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setInstalmentPolicy. Spec: handoff/service-docs/backend/OrderService.md#group-payments Helper task: Pranay Shinde owns the service and reviews. Done when `payments#setInstalmentPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-VENUEOPS-DEPARTURE-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] VenueOpsService: getNextTransportDeparture, searchTransportDepartures, updateTransportDeparture | 5 | Sanket Keluskar | VenueOpsService | MIG-CATALOGUE MIG-TRANSPORT PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getNextTransportDeparture, searchTransportDepartures, updateTransportDeparture. Spec: handoff/service-docs/backend/VenueOpsService.md#group-departure Helper task: Hrushikant Patkar owns the service and reviews. Done when `transport#getNextTransportDeparture`, `transport#searchTransportDepartures`, `transport#updateTransportDeparture` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-VENUEOPS-FARE-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] VenueOpsService: getTransportFareTable, quoteTransportFare, setTransportFareTable | 8 | Tanmay Dukhande | VenueOpsService | MIG-TRANSPORT PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getTransportFareTable, quoteTransportFare, setTransportFareTable. Spec: handoff/service-docs/backend/VenueOpsService.md#group-fare. Done when `transport#getTransportFareTable`, `transport#quoteTransportFare`, `transport#setTransportFareTable` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-VENUEOPS-NETWORKIMPORT-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] VenueOpsService: applyTransportNetworkImport, importTransportNetwork | 5 | Tanmay Dukhande | VenueOpsService | MIG-TRANSPORT PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: applyTransportNetworkImport, importTransportNetwork. Spec: handoff/service-docs/backend/VenueOpsService.md#group-networkimport Helper task: Hrushikant Patkar owns the service and reviews. Done when `transport#applyTransportNetworkImport`, `transport#importTransportNetwork` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-VENUEOPS-PASS-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] VenueOpsService: createTransportPassType, listTransportPassOffers, updateTransportPassType | 5 | Sanket Keluskar | VenueOpsService | MIG-TRANSPORT PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createTransportPassType, listTransportPassOffers, updateTransportPassType. Spec: handoff/service-docs/backend/VenueOpsService.md#group-pass Helper task: Hrushikant Patkar owns the service and reviews. Done when `transport#createTransportPassType`, `transport#listTransportPassOffers`, `transport#updateTransportPassType` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-VENUEOPS-ROUTE-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] VenueOpsService: createTransportRoute, getTransportRoute, getTransportRouteMap, listTransportRoutes | 8 | Tanmay Dukhande | VenueOpsService | MIG-TRANSPORT PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createTransportRoute, getTransportRoute, getTransportRouteMap, listTransportRoutes. Spec: handoff/service-docs/backend/VenueOpsService.md#group-route. Done when `transport#createTransportRoute`, `transport#getTransportRoute`, `transport#getTransportRouteMap`, `transport#listTransportRoutes` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-VENUEOPS-ROUTE-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] VenueOpsService: setTransportRouteStatus, updateTransportRoute | 5 | Chinmay Patkar | VenueOpsService | MIG-TRANSPORT PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setTransportRouteStatus, updateTransportRoute. Spec: handoff/service-docs/backend/VenueOpsService.md#group-route Helper task: Hrushikant Patkar owns the service and reviews. Done when `transport#setTransportRouteStatus`, `transport#updateTransportRoute` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-VENUEOPS-STATION-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] VenueOpsService: createTransportStation, listTransportStations, updateTransportStation | 5 | Sanket Keluskar | VenueOpsService | MIG-TRANSPORT PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createTransportStation, listTransportStations, updateTransportStation. Spec: handoff/service-docs/backend/VenueOpsService.md#group-station Helper task: Hrushikant Patkar owns the service and reviews. Done when `transport#createTransportStation`, `transport#listTransportStations`, `transport#updateTransportStation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-VENUEOPS-TIMETABLE-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] VenueOpsService: createTransportTimetable, publishTransportTimetable, withdrawTransportTimetable | 5 | Sanket Keluskar | VenueOpsService | MIG-TRANSPORT PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createTransportTimetable, publishTransportTimetable, withdrawTransportTimetable. Spec: handoff/service-docs/backend/VenueOpsService.md#group-timetable Helper task: Hrushikant Patkar owns the service and reviews. Done when `transport#createTransportTimetable`, `transport#publishTransportTimetable`, `transport#withdrawTransportTimetable` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-VENUEOPS-VENUEMAP-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] VenueOpsService: createVenueMap, getVenueMap, getVenueMapGraph, importVenueGeometry | 8 | Tanmay Dukhande | VenueOpsService | MIG-ASSETS MIG-PLATFORM MIG-VENUEMAP PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createVenueMap, getVenueMap, getVenueMapGraph, importVenueGeometry. Spec: handoff/service-docs/backend/VenueOpsService.md#group-venuemap. Done when `venue-map#createVenueMap`, `venue-map#getVenueMap`, `venue-map#getVenueMapGraph`, `venue-map#importVenueGeometry` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-VENUEOPS-VENUEMAP-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] VenueOpsService: listBookableVenueMaps, publishVenueMap, setPlacedResource, setVenueMapArtwork | 8 | Tanmay Dukhande | VenueOpsService | MIG-ASSETS MIG-PLATFORM MIG-VENUEMAP PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listBookableVenueMaps, publishVenueMap, setPlacedResource, setVenueMapArtwork. Spec: handoff/service-docs/backend/VenueOpsService.md#group-venuemap. Done when `venue-map#listBookableVenueMaps`, `venue-map#publishVenueMap`, `venue-map#setPlacedResource`, `venue-map#setVenueMapArtwork` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-VENUEOPS-VENUEMAP-3 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08 | [BE] VenueOpsService: setVenuePoint | 3 | Sanket Keluskar | VenueOpsService | MIG-ACCESS MIG-ASSETS MIG-CATALOGUE MIG-PLATFORM MIG-PROMOTIONS MIG-VENUEMAP PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setVenuePoint. Spec: handoff/service-docs/backend/VenueOpsService.md#group-venuemap Helper task: Hrushikant Patkar owns the service and reviews. Done when `venue-map#setVenuePoint` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 2 | VM-MIG-CATALOGUE | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [DB] Forward migration V1088__catalogue.sql: catalogue for Venue Management (2 tables) | 2 | Hrushikant Patkar |  | MIG-CATALOGUE | Tables: catalogue.donation_campaign, catalogue.performance_template. Source DDL: backend/tenant/010-catalogue.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `catalogue.donation_campaign`, `catalogue.performance_template` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
12 | 2 | VM-MIG-PROMOTIONS | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [DB] Forward migration V1017__promotions.sql: promotions for Venue Management (2 tables) | 1 | Hrushikant Patkar |  | MIG-PROMOTIONS | Tables: promotions.upsell_rule, promotions.voucher. Source DDL: backend/tenant/010-promotions.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `promotions.upsell_rule`, `promotions.voucher` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
13 | 2 | VM-CATALOGUE-UPSELL-1 | AM-TENANCY-VENUES-P08-BLOCK-A | [BE] CatalogueService: createUpsellRule, deleteUpsellRule, listUpsellRules | 3 | Sanket Keluskar | CatalogueService | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-PROMOTIONS | Operations beyond the first release: createUpsellRule, deleteUpsellRule, listUpsellRules. Additive to CatalogueService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `promotions#createUpsellRule`, `promotions#deleteUpsellRule`, `promotions#listUpsellRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 2 | VM-MIG-FNB | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [DB] Forward migration V1033__fnb.sql: fnb for Venue Management (2 tables) | 1 | Hrushikant Patkar |  | MIG-FNB | Tables: fnb.temperature_checkpoint, fnb.waste_approval_policy. Source DDL: backend/tenant/010-fnb.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `fnb.temperature_checkpoint`, `fnb.waste_approval_policy` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
6 | 3 | MIG-CONTROL-3 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [DB] Forward migration V1072__control.sql: control for Identity & Security · Partner Portal (6 tables) | 5 | Hrushikant Patkar | PlatformService | MIG-BASELINE MIG-CONTROL VM-MIG-CONTROL | Tables: control.channel_listing, control.partner_allocation, control.partner_booking_limit, control.partner_commercial_exception, control.partner_status_history, control.partner_user. Source DDL: backend/control/010-control.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `control.channel_listing`, `control.partner_allocation`, `control.partner_booking_limit`, `control.partner_commercial_exception`, `control.partner_status_history`, `control.partner_user` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
9 | 3 | MIG-AI-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [DB] Forward migration V1010__ai.sql: ai for Identity & Security · TICVAI Console 2 of 3 (1 tables) | 1 | Hrushikant Patkar | AiService | MIG-AI MIG-BASELINE VM-MIG-AI | Tables: ai.action_step. Source DDL: backend/tenant/010-ai.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `ai.action_step` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
9 | 3 | MIG-AI-3 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [DB] Forward migration V1011__ai.sql: ai for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens) (1 tables) | 1 | Hrushikant Patkar | AiService | MIG-AI MIG-BASELINE VM-MIG-AI | Tables: ai.tool. Source DDL: backend/tenant/010-ai.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `ai.tool` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
9 | 3 | MIG-SEATING-3 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [DB] Forward migration V1111__seating.sql: seating for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens) (2 tables) | 1 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-SEATING | Tables: seating.seating_rules, seating.section_row. Source DDL: backend/tenant/010-seating.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `seating.seating_rules`, `seating.section_row` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
10 | 3 | MIG-PRICING-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [DB] Forward migration V1112__pricing.sql: pricing for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens) (3 tables) | 2 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-CATALOGUE | Tables: pricing.dynamic_price_action, pricing.dynamic_price_condition, pricing.dynamic_price_rule. Source DDL: backend/tenant/010-pricing.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `pricing.dynamic_price_action`, `pricing.dynamic_price_condition`, `pricing.dynamic_price_rule` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | MIG-CATALOGUE-3 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [DB] Forward migration V1104__catalogue.sql: catalogue for Approvals · Venue Management 2 of 5 (2 tables) | 2 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-CATALOGUE VM-MIG-CATALOGUE | Tables: catalogue.approval_policy, catalogue.audit_entry. Source DDL: backend/tenant/010-catalogue.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `catalogue.approval_policy`, `catalogue.audit_entry` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | MIG-CATALOGUE-4 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [DB] Forward migration V1113__catalogue.sql: catalogue for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens) (5 tables) | 3 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-CATALOGUE VM-MIG-CATALOGUE | Tables: catalogue.package_pricing, catalogue.price_assignment, catalogue.rate, catalogue.rollback_action, catalogue.variant_dimension. Source DDL: backend/tenant/010-catalogue.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `catalogue.package_pricing`, `catalogue.price_assignment`, `catalogue.rate`, `catalogue.rollback_action`, `catalogue.variant_dimension` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
13 | 3 | MIG-PROMOTIONS-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [DB] Forward migration V1114__promotions.sql: promotions for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens) (4 tables) | 3 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-PLATFORM MIG-PROMOTIONS VM-MIG-PROMOTIONS | Tables: promotions.campaign, promotions.campaign_budget, promotions.stacking_rule, promotions.voucher_batch. Source DDL: backend/tenant/010-promotions.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `promotions.campaign`, `promotions.campaign_budget`, `promotions.stacking_rule`, `promotions.voucher_batch` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
16 | 3 | MIG-FNB-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [DB] Forward migration V1117__fnb.sql: fnb for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens) (3 tables) | 2 | Hrushikant Patkar | FnbService | MIG-BASELINE MIG-FNB VM-MIG-FNB | Tables: fnb.combo, fnb.combo_slot, fnb.combo_slot_option. Source DDL: backend/tenant/010-fnb.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `fnb.combo`, `fnb.combo_slot`, `fnb.combo_slot_option` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-PLATFORM-SUBSCRIPTION-20 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] PlatformService: listChannelListings, setChannelListing | 3 | Pranay Shinde | PlatformService | MIG-CATALOGUE MIG-CONTROL-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listChannelListings, setChannelListing. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#listChannelListings`, `subscription#setChannelListing` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-CATALOGUE-CAPACITY-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: createChannelCapacity, getChannelAllocations, listChannelCapacities, relinquishChannelAllocation | 5 | Deep Khanvilkar | CatalogueService | MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: createChannelCapacity, getChannelAllocations, listChannelCapacities, relinquishChannelAllocation. Additive to CatalogueService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#createChannelCapacity`, `catalogue#getChannelAllocations`, `catalogue#listChannelCapacities`, `catalogue#relinquishChannelAllocation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-CATALOGUE-CAPACITY-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: setChannelAllocations, updateChannelCapacity | 3 | Sanket Keluskar | CatalogueService | MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: setChannelAllocations, updateChannelCapacity. Additive to CatalogueService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#setChannelAllocations`, `catalogue#updateChannelCapacity` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 2 | VM-CATALOGUE-PRICING-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: listPrices | 1 | New full-stack developer 1 | CatalogueService | MIG-CATALOGUE PLATFORM-KERNEL | Operations beyond the first release: listPrices. Additive to CatalogueService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#listPrices` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 2 | VM-CATALOGUE-PRODUCT-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: transitionProductLifecycle | 3 | Tanmay Dukhande | CatalogueService | MIG-ACCESS MIG-CATALOGUE MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations beyond the first release: transitionProductLifecycle. Additive to CatalogueService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#transitionProductLifecycle` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-CATALOGUE-SEATMAP-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: createSeatMap, getSeatMap, updateSeatMap | 8 | Hrushikant Patkar | CatalogueService | MIG-SEATING MIG-SEATING-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createSeatMap, getSeatMap, updateSeatMap. Spec: contracts (seating) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `seating#createSeatMap`, `seating#getSeatMap`, `seating#updateSeatMap` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-CATALOGUE-5 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: importProductCatalogue, listDynamicPriceRules, listProductVersions, restoreProductVersion | 8 | Tanmay Dukhande | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-3 MIG-CATALOGUE-4 MIG-PRICING-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: importProductCatalogue, listDynamicPriceRules, listProductVersions, restoreProductVersion. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#importProductCatalogue`, `catalogue#listDynamicPriceRules`, `catalogue#listProductVersions`, `catalogue#restoreProductVersion` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-CATALOGUE-6 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: setDynamicPriceRule, setPackagePricingDefinition | 5 | Tanmay Dukhande | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-3 MIG-CATALOGUE-4 MIG-PRICING-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setDynamicPriceRule, setPackagePricingDefinition. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#setDynamicPriceRule`, `catalogue#setPackagePricingDefinition` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-CATEGORY-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: listSeatCategories | 1 | Tanmay Dukhande | CatalogueService | MIG-SEATING PLATFORM-KERNEL SVC-CATALOGUE-CATEGORY-1 | Operations: listSeatCategories. Spec: contracts (seating) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `seating#listSeatCategories` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-COUPON-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: assignCoupon, listCouponCampaigns, listCouponCodes, voidCouponCode | 8 | Pranay Shinde | CatalogueService | MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: assignCoupon, listCouponCampaigns, listCouponCodes, voidCouponCode. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#assignCoupon`, `promotions#listCouponCampaigns`, `promotions#listCouponCodes`, `promotions#voidCouponCode` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-ENTITLEMENT-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: listEntitlementTemplates | 1 | Chinmay Patkar | CatalogueService | MIG-CATALOGUE PLATFORM-KERNEL SVC-CATALOGUE-ENTITLEMENT-1 | Operations: listEntitlementTemplates. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listEntitlementTemplates` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-PRODUCT-5 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: createProduct, setProductAttributes | 5 | Tanmay Dukhande | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-4 MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createProduct, setProductAttributes. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#createProduct`, `catalogue#setProductAttributes` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-SEATING-3 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: getAccessibleSeating, getSeatRecommendationRules | 2 | Deep Khanvilkar | CatalogueService | MIG-SEATING PLATFORM-KERNEL SVC-CATALOGUE-SEATING-1 | Operations: getAccessibleSeating, getSeatRecommendationRules. Spec: contracts (seating) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `seating#getAccessibleSeating`, `seating#getSeatRecommendationRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | SVC-CATALOGUE-GENERAL-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: getPackagePricingDefinition, getProductAttributes | 2 | Tanmay Dukhande | CatalogueService | MIG-CATALOGUE-4 PLATFORM-KERNEL SVC-CATALOGUE-CATALOGUE-6 SVC-CATALOGUE-PRODUCT-5 | Operations: getPackagePricingDefinition, getProductAttributes. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#getPackagePricingDefinition`, `catalogue#getProductAttributes` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | SVC-CATALOGUE-PROMOTIONS-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: simulatePromotion, voidVoucher | 2 | Chinmay Patkar | CatalogueService | MIG-CATALOGUE MIG-ORDERS MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-PROMOTIONS | Operations: simulatePromotion, voidVoucher. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#simulatePromotion`, `promotions#voidVoucher` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-CATALOGUE-CATALOGUE-4 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: assessProductChange, bulkUpdateCatalogueProducts, getCatalogueImportJob, getDynamicPriceRule | 8 | Pranay Shinde | CatalogueService | MIG-ACCESS MIG-CATALOGUE MIG-ORDERS MIG-PRICING-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: assessProductChange, bulkUpdateCatalogueProducts, getCatalogueImportJob, getDynamicPriceRule. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#assessProductChange`, `catalogue#bulkUpdateCatalogueProducts`, `catalogue#getCatalogueImportJob`, `catalogue#getDynamicPriceRule` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-CATALOGUE-DRAFTED-4 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: setPromotionStackingRule | 2 | Pranay Shinde | CatalogueService | MIG-PROMOTIONS MIG-PROMOTIONS-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setPromotionStackingRule. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#setPromotionStackingRule` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-CATALOGUE-PROMOTION-3 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: endPromotion, listCommercialCampaigns, pausePromotion, unschedulePromotion | 5 | Tanmay Dukhande | CatalogueService | MIG-PLATFORM MIG-PROMOTIONS MIG-PROMOTIONS-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: endPromotion, listCommercialCampaigns, pausePromotion, unschedulePromotion. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#endPromotion`, `promotions#listCommercialCampaigns`, `promotions#pausePromotion`, `promotions#unschedulePromotion` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-CATALOGUE-VOUCHER-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: createVoucherBatch, listVoucherBatches | 3 | Sanket Keluskar | CatalogueService | MIG-PROMOTIONS-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createVoucherBatch, listVoucherBatches. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#createVoucherBatch`, `promotions#listVoucherBatches` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-CATALOGUE-PRICING-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: getPriceList, listPriceLists | 3 | Tanmay Dukhande | CatalogueService | MIG-CATALOGUE PLATFORM-KERNEL SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-PRICING-1 | Operations: getPriceList, listPriceLists. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#getPriceList`, `catalogue#listPriceLists` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ORDER-ORDERS-8 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] OrderService: listTicketTemplates, printTicketProof | 3 | Pranay Shinde | OrderService | MIG-CATALOGUE MIG-ORDERS PLATFORM-KERNEL SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-ORDER-ORDERS-1 SVC-ORDER-ORDERS-2 SVC-ORDER-ORDERS-5 VM-CATALOGUE-PRODUCT-1 | Operations: listTicketTemplates, printTicketProof. Spec: contracts (orders) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listTicketTemplates`, `orders#printTicketProof` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-TIMETABLE-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] VenueOpsService: listTransportTimetables, updateTransportTimetable | 3 | Sanket Keluskar | VenueOpsService | MIG-TRANSPORT PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listTransportTimetables, updateTransportTimetable. Spec: contracts (transport) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `transport#listTransportTimetables`, `transport#updateTransportTimetable` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-VENUEOPS-DEPARTURE-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] VenueOpsService: listTransportRouteDepartures | 1 | Chinmay Patkar | VenueOpsService | MIG-TRANSPORT PLATFORM-KERNEL SVC-VENUEOPS-DEPARTURE-1 SVC-VENUEOPS-TIMETABLE-1 | Operations: listTransportRouteDepartures. Spec: contracts (transport) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `transport#listTransportRouteDepartures` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-VENUEOPS-NETWORKIMPORT-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] VenueOpsService: getTransportNetworkImport | 1 | Tanmay Dukhande | VenueOpsService | MIG-TRANSPORT PLATFORM-KERNEL SVC-VENUEOPS-NETWORKIMPORT-1 | Operations: getTransportNetworkImport. Spec: contracts (transport) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `transport#getTransportNetworkImport` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-VENUEOPS-PASS-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] VenueOpsService: listTransportPassTypes | 1 | Tanmay Dukhande | VenueOpsService | MIG-TRANSPORT PLATFORM-KERNEL SVC-VENUEOPS-PASS-1 | Operations: listTransportPassTypes. Spec: contracts (transport) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `transport#listTransportPassTypes` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-FNB-FNB-11 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] FnbService: createCombo, setComboSlots | 5 | Surendra | FnbService | MIG-CATALOGUE MIG-FNB MIG-FNB-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createCombo, setComboSlots. Spec: contracts (fnb) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to FnbService, whose first-release owner (Tanmay Dukhande) reviews. Done when `fnb#createCombo`, `fnb#setComboSlots` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-FNB-GENERAL-1 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] FnbService: listCombos | 1 | Chinmay Patkar | FnbService | MIG-FNB-2 PLATFORM-KERNEL SVC-FNB-FNB-11 | Operations: listCombos. Spec: contracts (fnb) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to FnbService, whose first-release owner (Tanmay Dukhande) reviews. Done when `fnb#listCombos` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-AI-GENERATE-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] AiService: generateConfiguration | 3 | Tanmay Dukhande | AiService | MIG-AI MIG-AI-2 MIG-AI-3 MIG-CATALOGUE MIG-CATALOGUE-4 MIG-MARKETING MIG-PLATFORM MIG-PROMOTIONS MIG-SEATING MIG-SEATING-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: generateConfiguration. Spec: contracts (ai) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#generateConfiguration` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-CATALOGUE-LEASE-1 | AM-TICKETING-P01 | [BE] CatalogueService: acquireInventoryHold, convertInventoryHold, listInventoryHolds | 8 | Deep Khanvilkar | CatalogueService | MIG-CATALOGUE MIG-PLATFORM MIG-SEATING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: acquireInventoryHold, convertInventoryHold, listInventoryHolds. Spec: handoff/service-docs/backend/CatalogueService.md#group-lease. Done when `catalogue#acquireInventoryHold`, `catalogue#convertInventoryHold`, `catalogue#listInventoryHolds` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 1 | SVC-CATALOGUE-EVALUATION-1 | AM-TICKETING-P01 | [BE] CatalogueService: evaluatePromotions | 3 | Sanket Keluskar | CatalogueService | MIG-CATALOGUE MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: evaluatePromotions. Spec: handoff/service-docs/backend/CatalogueService.md#group-evaluation Helper task: Hrushikant Patkar owns the service and reviews. Done when `promotions#evaluatePromotions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 1 | SVC-ORDER-SYNC-1 | AM-TICKETING-P01 | [BE] OrderService: listSyncRejections, syncOrders | 8 | Pranay Shinde | OrderService | MIG-CATALOGUE MIG-LEDGER MIG-ORDERS MIG-PLATFORM MIG-SYNC PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: listSyncRejections, syncOrders. Spec: handoff/service-docs/backend/OrderService.md#group-sync. Done when `orders#listSyncRejections`, `orders#syncOrders` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-ORDER-CART-3 | AM-TICKETING-P01 | [BE] OrderService: removeCartLine, updateCartLine | 8 | Pranay Shinde | OrderService | MIG-CATALOGUE MIG-MARKETING MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: removeCartLine, updateCartLine. Spec: handoff/service-docs/backend/OrderService.md#group-cart. Done when `orders#removeCartLine`, `orders#updateCartLine` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-CATALOGUE-PRODUCT-1 | AM-TICKETING-P01 | [BE] CatalogueService: checkBookingEligibility, getGroupPackageDefinition, getProduct, getProductEligibilityRule | 5 | Deep Khanvilkar | CatalogueService | MIG-CATALOGUE PLATFORM-KERNEL SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-PRODUCT-3 SVC-CATALOGUE-PRODUCT-4 | Operations: checkBookingEligibility, getGroupPackageDefinition, getProduct, getProductEligibilityRule. Spec: handoff/service-docs/backend/CatalogueService.md#group-product Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#checkBookingEligibility`, `catalogue#getGroupPackageDefinition`, `catalogue#getProduct`, `catalogue#getProductEligibilityRule` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-ORDER-PAYMENT-1 | AM-TICKETING-P01 | [BE] OrderService: addTip, capturePayment, createPayment, inquirePaymentStatus | 8 | Pranay Shinde | OrderService | MIG-CATALOGUE MIG-LEDGER MIG-ORDERS MIG-PAYMENTS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: addTip, capturePayment, createPayment, inquirePaymentStatus. Spec: handoff/service-docs/backend/OrderService.md#group-payment Acceptance of the declined, unknown and reconcile paths waits on the client's payment sandbox credentials: see the client's answer in the Decisions Register. Done when `orders#addTip`, `orders#capturePayment`, `orders#createPayment`, `orders#inquirePaymentStatus` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-VENUEOPS-RESOURCES-3 | AM-TICKETING-P01 | [BE] VenueOpsService: getResourceHold, listProductStartTimes, releaseResourceBlock, relinquishResourceHold | 3 | Sanket Keluskar | VenueOpsService | MIG-RESOURCES PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getResourceHold, listProductStartTimes, releaseResourceBlock, relinquishResourceHold. Spec: handoff/service-docs/backend/VenueOpsService.md#group-resources Helper task: Hrushikant Patkar owns the service and reviews. Done when `resources#getResourceHold`, `resources#listProductStartTimes`, `resources#releaseResourceBlock`, `resources#relinquishResourceHold` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-VENUEOPS-VISITPLAN-1 | AM-TICKETING-P01 | [BE] VenueOpsService: bookVisitPlan, generateVisitPlan, getVisitPlan, listVisitPlanAlternatives | 8 | Tanmay Dukhande | VenueOpsService | MIG-CATALOGUE MIG-ORDERS MIG-PROMOTIONS MIG-QUEUE MIG-VENUEMAP PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: bookVisitPlan, generateVisitPlan, getVisitPlan, listVisitPlanAlternatives. Spec: handoff/service-docs/backend/VenueOpsService.md#group-visitplan. Done when `venue-map#bookVisitPlan`, `venue-map#generateVisitPlan`, `venue-map#getVisitPlan`, `venue-map#listVisitPlanAlternatives` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 1 | SVC-CATALOGUE-CAPACITY-1 | AM-TICKETING-P01 | [BE] CatalogueService: getAvailability | 1 | Chinmay Patkar | CatalogueService | MIG-CATALOGUE PLATFORM-KERNEL SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-LEASE-1 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-CART-3 SVC-ORDER-PAYMENT-1 SVC-ORDER-SYNC-1 SVC-VENUEOPS-VISITPLAN-1 | Operations: getAvailability. Spec: handoff/service-docs/backend/CatalogueService.md#group-capacity Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#getAvailability` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-CATALOGUE-LEASE-2 | AM-TICKETING-P05-BLOCK-A | [BE] CatalogueService: relinquishInventoryHold | 2 | Sanket Keluskar | CatalogueService | MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: relinquishInventoryHold. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Kiosk (Block A); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#relinquishInventoryHold` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | MIG-CATALOGUE-2 | AM-TICKETING-P08-BLOCK-A | [DB] Forward migration V1091__catalogue.sql: catalogue for Subscription & Licensing · Venue Management 1 of 3 (2 tables) | 1 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-CATALOGUE VM-MIG-CATALOGUE | Tables: catalogue.membership_programme, catalogue.plan_benefit. Source DDL: backend/tenant/010-catalogue.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `catalogue.membership_programme`, `catalogue.plan_benefit` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | MIG-CATALOGUE-5 | AM-TICKETING-P08-BLOCK-A | [DB] Forward migration V1118__catalogue.sql: catalogue for Ticketing · Venue Management (Block A) (5 tables) | 3 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-CATALOGUE MIG-IDENTITY VM-MIG-CATALOGUE | Tables: catalogue.event_change_treatment_policy, catalogue.membership_benefit, catalogue.seat_pricing_rule, catalogue.tax_profile, catalogue.waiting_room_setting. Source DDL: backend/tenant/010-catalogue.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `catalogue.event_change_treatment_policy`, `catalogue.membership_benefit`, `catalogue.seat_pricing_rule`, `catalogue.tax_profile`, `catalogue.waiting_room_setting` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 2 | VM-CATALOGUE-EVENT-1 | AM-TICKETING-P08-BLOCK-A | [BE] CatalogueService: cancelPerformance, getEvent | 3 | Sanket Keluskar | CatalogueService | MIG-CATALOGUE MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations beyond the first release: cancelPerformance, getEvent. Additive to CatalogueService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#cancelPerformance`, `catalogue#getEvent` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-CATALOGUE-LEASE-3 | AM-TICKETING-P08-BLOCK-A | [BE] CatalogueService: renewInventoryHold | 2 | Tanmay Dukhande | CatalogueService | MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: renewInventoryHold. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management (Block A); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#renewInventoryHold` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-DRAFTED-5 | AM-TICKETING-P08-BLOCK-A | [BE] CatalogueService: listProductApprovalWorkflows, listSeatPricingRules, listTaxProfiles, setSeatPricingRule | 8 | New full-stack developer 2 | CatalogueService | MIG-CATALOGUE-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listProductApprovalWorkflows, listSeatPricingRules, listTaxProfiles, setSeatPricingRule. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management (Block A); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listProductApprovalWorkflows`, `catalogue#listSeatPricingRules`, `catalogue#listTaxProfiles`, `catalogue#setSeatPricingRule` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-EVENT-4 | AM-TICKETING-P08-BLOCK-A | [BE] CatalogueService: getWaitingRoomStatus, setWaitingRoomSetting | 3 | Tanmay Dukhande | CatalogueService | MIG-CATALOGUE-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getWaitingRoomStatus, setWaitingRoomSetting. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management (Block A); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#getWaitingRoomStatus`, `catalogue#setWaitingRoomSetting` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-EVENTS-2 | AM-TICKETING-P08-BLOCK-A | [BE] CatalogueService: getEventChangeTreatmentPolicy, setEventChangeTreatmentPolicy | 2 | Chinmay Patkar | CatalogueService | MIG-CATALOGUE-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getEventChangeTreatmentPolicy, setEventChangeTreatmentPolicy. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management (Block A); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#getEventChangeTreatmentPolicy`, `catalogue#setEventChangeTreatmentPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | SVC-CATALOGUE-CATALOGUE-7 | AM-TICKETING-P08-BLOCK-A | [BE] CatalogueService: getPlanBenefits, joinWaitlist, leaveWaitlist, listGuestMemberships | 5 | Tanmay Dukhande | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-2 MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getPlanBenefits, joinWaitlist, leaveWaitlist, listGuestMemberships. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management (Block A); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#getPlanBenefits`, `catalogue#joinWaitlist`, `catalogue#leaveWaitlist`, `catalogue#listGuestMemberships` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-CATALOGUE-CATALOGUE-8 | AM-TICKETING-P08-BLOCK-A | [BE] CatalogueService: listMembershipBenefits, listMembershipProgrammes | 1 | Sanket Keluskar | CatalogueService | MIG-CATALOGUE-2 MIG-CATALOGUE-5 PLATFORM-KERNEL | Operations: listMembershipBenefits, listMembershipProgrammes. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management (Block A); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listMembershipBenefits`, `catalogue#listMembershipProgrammes` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-CATALOGUE-HOLD-1 | AM-SEATING-MAPS-P01 | [BE] CatalogueService: createSeatHold, extendSeatHold, getSeatHold, relinquishSeatHold | 5 | Tanmay Dukhande | CatalogueService | MIG-PLATFORM MIG-SEATING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: createSeatHold, extendSeatHold, getSeatHold, relinquishSeatHold. Spec: handoff/service-docs/backend/CatalogueService.md#group-hold Helper task: Hrushikant Patkar owns the service and reviews. Done when `seating#createSeatHold`, `seating#extendSeatHold`, `seating#getSeatHold`, `seating#relinquishSeatHold` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 1 | SVC-CATALOGUE-AVAILABILITY-1 | AM-SEATING-MAPS-P01 | [BE] CatalogueService: getSeatAvailability | 2 | Chinmay Patkar | CatalogueService | MIG-SEATING PLATFORM-KERNEL SVC-CATALOGUE-CATEGORY-1 SVC-CATALOGUE-HOLD-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-SEATMAP-1 | Operations: getSeatAvailability. Spec: handoff/service-docs/backend/CatalogueService.md#group-availability Helper task: Hrushikant Patkar owns the service and reviews. Done when `seating#getSeatAvailability` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 1 | SVC-CATALOGUE-RECOMMENDATION-1 | AM-SEATING-MAPS-P01 | [BE] CatalogueService: recommendSeats | 1 | Chinmay Patkar | CatalogueService | MIG-CATALOGUE MIG-SEATING PLATFORM-KERNEL SVC-CATALOGUE-CATEGORY-1 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-HOLD-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-SEATING-1 SVC-CATALOGUE-SEATMAP-1 | Operations: recommendSeats. Spec: handoff/service-docs/backend/CatalogueService.md#group-recommendation Helper task: Hrushikant Patkar owns the service and reviews. Done when `seating#recommendSeats` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-VENUEOPS-QUEUE-1 | AM-SEATING-MAPS-P01 | [BE] VenueOpsService: createQueue, listQueues, updateQueue | 8 | Tanmay Dukhande | VenueOpsService | MIG-QUEUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createQueue, listQueues, updateQueue. Spec: handoff/service-docs/backend/VenueOpsService.md#group-queue. Done when `queue#createQueue`, `queue#listQueues`, `queue#updateQueue` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-VENUEOPS-VISITPLAN-2 | AM-SEATING-MAPS-P01 | [BE] VenueOpsService: updateVisitPlan | 3 | Sanket Keluskar | VenueOpsService | MIG-CATALOGUE MIG-QUEUE MIG-VENUEMAP PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updateVisitPlan. Spec: handoff/service-docs/backend/VenueOpsService.md#group-visitplan Helper task: Hrushikant Patkar owns the service and reviews. Done when `venue-map#updateVisitPlan` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-VENUEOPS-RESOURCES-2 | AM-SEATING-MAPS-P02 | [BE] VenueOpsService: createResourcePackage, extendResourceHold, getMapResourceAvailability, getResourceAvailability | 8 | Deep Khanvilkar | VenueOpsService | MIG-MAINTENANCE MIG-RESOURCES MIG-VENUEMAP PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createResourcePackage, extendResourceHold, getMapResourceAvailability, getResourceAvailability. Spec: handoff/service-docs/backend/VenueOpsService.md#group-resources. Done when `resources#createResourcePackage`, `resources#extendResourceHold`, `resources#getMapResourceAvailability`, `resources#getResourceAvailability` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 2 | VM-VENUEOPS-VENUEMAP-1 | AM-SEATING-MAPS-P08-BLOCK-A | [BE] VenueOpsService: setPathClosure | 2 | Chinmay Patkar | VenueOpsService | MIG-VENUEMAP PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: setPathClosure. Additive to VenueOpsService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `venue-map#setPathClosure` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-VENUEOPS-VENUEMAP-5 | AM-SEATING-MAPS-P08-BLOCK-A | [BE] VenueOpsService: acceptVenueLabelProposals, acceptWalkwayProposals, getVenueMapImportJob, getVenueNavigationFile | 8 | Pranay Shinde | VenueOpsService | MIG-AI MIG-VENUEMAP PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: acceptVenueLabelProposals, acceptWalkwayProposals, getVenueMapImportJob, getVenueNavigationFile. Spec: contracts (venue-map) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management (Block A); additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `venue-map#acceptVenueLabelProposals`, `venue-map#acceptWalkwayProposals`, `venue-map#getVenueMapImportJob`, `venue-map#getVenueNavigationFile` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-VENUEOPS-VENUEMAP-6 | AM-SEATING-MAPS-P08-BLOCK-A | [BE] VenueOpsService: listVenueMaps, validateVenueMapGraph | 2 | Tanmay Dukhande | VenueOpsService | MIG-VENUEMAP PLATFORM-KERNEL SVC-VENUEOPS-VENUEMAP-1 SVC-VENUEOPS-VENUEMAP-2 SVC-VENUEOPS-VENUEMAP-3 SVC-VENUEOPS-VENUEMAP-5 VM-VENUEOPS-VENUEMAP-1 | Operations: listVenueMaps, validateVenueMapGraph. Spec: contracts (venue-map) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management (Block A); additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `venue-map#listVenueMaps`, `venue-map#validateVenueMapGraph` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-AI-AI-3 | AM-SEATING-MAPS-P08-BLOCK-A | [BE] AiService: proposeWalkways | 2 | Surendra | AiService | MIG-AI MIG-ASSETS MIG-VENUEMAP PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: proposeWalkways. Spec: contracts (ai) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management (Block A); additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#proposeWalkways` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-AI-GOVERNANCE-4 | AM-SEATING-MAPS-P08-BLOCK-A | [BE] AiService: listProposedActions | 1 | Tanmay Dukhande | AiService | MIG-AI PLATFORM-KERNEL SVC-AI-AI-1 SVC-AI-AI-3 SVC-AI-ASSIST-1 SVC-AI-GENERATE-1 SVC-AI-GENERATE-2 SVC-AI-GOVERNANCE-1 | Operations: listProposedActions. Spec: contracts (ai) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management (Block A); additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#listProposedActions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 1 | SVC-ORDER-RESERVATION-1 | AM-ORDERS-RESERVATIONS-P01 | [BE] OrderService: cancelReservation, convertReservation, createReservation, extendReservation | 8 | Sanket Keluskar | OrderService | MIG-ORDERS MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: cancelReservation, convertReservation, createReservation, extendReservation. Spec: handoff/service-docs/backend/OrderService.md#group-reservation. Done when `orders#cancelReservation`, `orders#convertReservation`, `orders#createReservation`, `orders#extendReservation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 1 | SVC-ORDER-RESERVATION-2 | AM-ORDERS-RESERVATIONS-P01 | [BE] OrderService: getReservation, listReservations | 3 | Sanket Keluskar | OrderService | MIG-ORDERS PLATFORM-KERNEL SVC-ORDER-ORDERS-3 SVC-ORDER-RESERVATION-1 | Operations: getReservation, listReservations. Spec: handoff/service-docs/backend/OrderService.md#group-reservation Helper task: Pranay Shinde owns the service and reviews. Done when `orders#getReservation`, `orders#listReservations` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-FNB-10 | AM-ORDERS-RESERVATIONS-P01 | [BE] FnbService: signCorrectiveAction, transferTableVisit, updateTableReservation | 8 | Tanmay Dukhande | FnbService | MIG-FNB MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: signCorrectiveAction, transferTableVisit, updateTableReservation. Spec: handoff/service-docs/backend/FnbService.md#group-fnb. Done when `fnb#signCorrectiveAction`, `fnb#transferTableVisit`, `fnb#updateTableReservation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-FNB-4 | AM-ORDERS-RESERVATIONS-P01 | [BE] FnbService: leaveRestaurantWaitlist, list86Events, listMyTableReservations, listTableCombinations | 5 | Tanmay Dukhande | FnbService | MIG-FNB PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: leaveRestaurantWaitlist, list86Events, listMyTableReservations, listTableCombinations. Spec: handoff/service-docs/backend/FnbService.md#group-fnb. Done when `fnb#leaveRestaurantWaitlist`, `fnb#list86Events`, `fnb#listMyTableReservations`, `fnb#listTableCombinations` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 1 | SVC-ORDER-ORDER-3 | AM-ORDERS-RESERVATIONS-P02 | [BE] OrderService: getOrderStatement, getVisitReminder, holdOrder, listOrders | 8 | Pranay Shinde | OrderService | MIG-LEDGER MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getOrderStatement, getVisitReminder, holdOrder, listOrders. Spec: handoff/service-docs/backend/OrderService.md#group-order. Done when `orders#getOrderStatement`, `orders#getVisitReminder`, `orders#holdOrder`, `orders#listOrders` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 1 | SVC-ORDER-REFUND-1 | AM-ORDERS-RESERVATIONS-P02 | [BE] OrderService: createRefund, createRefundRequest, listOrderRefunds | 8 | Pranay Shinde | OrderService | MIG-LEDGER MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: createRefund, createRefundRequest, listOrderRefunds. Spec: handoff/service-docs/backend/OrderService.md#group-refund. Done when `orders#createRefund`, `orders#createRefundRequest`, `orders#listOrderRefunds` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-ORDER-DUNNING-1 | AM-ORDERS-RESERVATIONS-P02 | [BE] OrderService: listMyPaymentIssues, retryMyDunningPayment | 3 | Sanket Keluskar | OrderService | MIG-ORDERS MIG-PAYMENTS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listMyPaymentIssues, retryMyDunningPayment. Spec: handoff/service-docs/backend/OrderService.md#group-dunning Helper task: Pranay Shinde owns the service and reviews. Done when `payments#listMyPaymentIssues`, `payments#retryMyDunningPayment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-GUESTORDERING-1 | AM-ORDERS-RESERVATIONS-P02 | [BE] FnbService: claimLocationSession, createDeliveryLocation, createGuestFnbOrder, getFnbDeliveryPolicy | 8 | Tanmay Dukhande | FnbService | MIG-FNB MIG-INVENTORY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: claimLocationSession, createDeliveryLocation, createGuestFnbOrder, getFnbDeliveryPolicy. Spec: handoff/service-docs/backend/FnbService.md#group-guestordering. Done when `fnb#claimLocationSession`, `fnb#createDeliveryLocation`, `fnb#createGuestFnbOrder`, `fnb#getFnbDeliveryPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-GUESTORDERING-3 | AM-ORDERS-RESERVATIONS-P02 | [BE] FnbService: listDeliveryLocations, listDiningOutlets, listFulfilmentSlots, recordOrderHandover | 5 | Deep Khanvilkar | FnbService | MIG-FNB MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listDeliveryLocations, listDiningOutlets, listFulfilmentSlots, recordOrderHandover. Spec: handoff/service-docs/backend/FnbService.md#group-guestordering. Done when `fnb#listDeliveryLocations`, `fnb#listDiningOutlets`, `fnb#listFulfilmentSlots`, `fnb#recordOrderHandover` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-GUESTORDERING-4 | AM-ORDERS-RESERVATIONS-P02 | [BE] FnbService: setDeliveryLocationOutletMapping, setFnbDeliveryPolicy, updateDeliveryLocation | 5 | Sanket Keluskar | FnbService | MIG-FNB MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setDeliveryLocationOutletMapping, setFnbDeliveryPolicy, updateDeliveryLocation. Spec: handoff/service-docs/backend/FnbService.md#group-guestordering. Done when `fnb#setDeliveryLocationOutletMapping`, `fnb#setFnbDeliveryPolicy`, `fnb#updateDeliveryLocation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-KITCHEN-1 | AM-ORDERS-RESERVATIONS-P02 | [BE] FnbService: listKitchenStations, listKitchenTickets, prioritiseKitchenTicket, setKitchenTicketStatus | 8 | Deep Khanvilkar | FnbService | MIG-FNB MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: listKitchenStations, listKitchenTickets, prioritiseKitchenTicket, setKitchenTicketStatus. Spec: handoff/service-docs/backend/FnbService.md#group-kitchen. Done when `fnb#listKitchenStations`, `fnb#listKitchenTickets`, `fnb#prioritiseKitchenTicket`, `fnb#setKitchenTicketStatus` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-MODIFIER-1 | AM-ORDERS-RESERVATIONS-P02 | [BE] FnbService: createModifierGroup | 2 | Chinmay Patkar | FnbService | MIG-FNB PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createModifierGroup. Spec: handoff/service-docs/backend/FnbService.md#group-modifier Helper task: Tanmay Dukhande owns the service and reviews. Done when `fnb#createModifierGroup` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-ORDER-1 | AM-ORDERS-RESERVATIONS-P02 | [BE] FnbService: createFnbOrder, getFnbOrder, listFnbOrders | 8 | Tanmay Dukhande | FnbService | MIG-FNB MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: createFnbOrder, getFnbOrder, listFnbOrders. Spec: handoff/service-docs/backend/FnbService.md#group-order. Done when `fnb#createFnbOrder`, `fnb#getFnbOrder`, `fnb#listFnbOrders` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-SERVICE-1 | AM-ORDERS-RESERVATIONS-P02 | [BE] FnbService: acceptFnbOrder, cancelFnbOrder | 8 | Tanmay Dukhande | FnbService | MIG-FNB MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: acceptFnbOrder, cancelFnbOrder. Spec: handoff/service-docs/backend/FnbService.md#group-service. Done when `fnb#acceptFnbOrder`, `fnb#cancelFnbOrder` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-TABLE-1 | AM-ORDERS-RESERVATIONS-P02 | [BE] FnbService: clearTable, getTableMap, getTableVisit, openTableVisit | 8 | Tanmay Dukhande | FnbService | MIG-FNB PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: clearTable, getTableMap, getTableVisit, openTableVisit. Spec: handoff/service-docs/backend/FnbService.md#group-table. Done when `fnb#clearTable`, `fnb#getTableMap`, `fnb#getTableVisit`, `fnb#openTableVisit` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-TABLE-2 | AM-ORDERS-RESERVATIONS-P02 | [BE] FnbService: setTableLayout, updateTableVisit | 5 | Deep Khanvilkar | FnbService | MIG-FNB PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setTableLayout, updateTableVisit. Spec: handoff/service-docs/backend/FnbService.md#group-table. Done when `fnb#setTableLayout`, `fnb#updateTableVisit` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-AI-KNOWLEDGE-1 | AM-ORDERS-RESERVATIONS-P02 | [BE] AiService: configureAssistantProfile, recordAnswerFeedback | 3 | Sanket Keluskar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: configureAssistantProfile, recordAnswerFeedback. Spec: handoff/service-docs/backend/AiService.md#group-knowledge Helper task: Tanmay Dukhande owns the service and reviews. Done when `ai#configureAssistantProfile`, `ai#recordAnswerFeedback` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 1 | SVC-LEDGER-TAX-1 | AM-ORDERS-RESERVATIONS-P04 | [BE] LedgerService: createTaxCode, getTaxDocumentRendition, getTaxInvoice, issueCreditMemo | 8 | Tanmay Dukhande | LedgerService | MIG-LEDGER MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: createTaxCode, getTaxDocumentRendition, getTaxInvoice, issueCreditMemo. Spec: handoff/service-docs/backend/LedgerService.md#group-tax. Done when `finance#createTaxCode`, `finance#getTaxDocumentRendition`, `finance#getTaxInvoice`, `finance#issueCreditMemo` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 1 | SVC-LEDGER-TAX-2 | AM-ORDERS-RESERVATIONS-P04 | [BE] LedgerService: issueTaxInvoice, listCreditMemos, listTaxInvoices, setEInvoicingProvider | 8 | Tanmay Dukhande | LedgerService | MIG-LEDGER MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: issueTaxInvoice, listCreditMemos, listTaxInvoices, setEInvoicingProvider. Spec: handoff/service-docs/backend/LedgerService.md#group-tax. Done when `finance#issueTaxInvoice`, `finance#listCreditMemos`, `finance#listTaxInvoices`, `finance#setEInvoicingProvider` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-VENUEOPS-CARD-1 | AM-ORDERS-RESERVATIONS-P04 | [BE] VenueOpsService: getGameCard, issueGameCard | 3 | Sanket Keluskar | VenueOpsService | MIG-GAMES PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getGameCard, issueGameCard. Spec: handoff/service-docs/backend/VenueOpsService.md#group-card Helper task: Hrushikant Patkar owns the service and reviews. Done when `games#getGameCard`, `games#issueGameCard` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-MARKETING-LOYALTY-1 | AM-ORDERS-RESERVATIONS-P04 | [BE] MarketingService: awardBadge, createLoyaltyProgramme, getGuestLoyalty, listCustomerBadges | 5 | Deep Khanvilkar | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: awardBadge, createLoyaltyProgramme, getGuestLoyalty, listCustomerBadges. Spec: handoff/service-docs/backend/MarketingService.md#group-loyalty. Done when `marketing-crm#awardBadge`, `marketing-crm#createLoyaltyProgramme`, `marketing-crm#getGuestLoyalty`, `marketing-crm#listCustomerBadges` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-MIG-LEDGER | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [DB] Forward migration V1016__ledger.sql: ledger for Venue Management (7 tables) | 3 | Hrushikant Patkar |  | MIG-LEDGER | Tables: ledger.account_mapping, ledger.deposit, ledger.event_budget, ledger.fiscal_period_event, ledger.recognition_schedule, ledger.settlement, ledger.settlement_exception. Source DDL: backend/tenant/010-ledger.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `ledger.account_mapping`, `ledger.deposit`, `ledger.event_budget`, `ledger.fiscal_period_event`, `ledger.recognition_schedule`, `ledger.settlement`, `ledger.settlement_exception` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
13 | 2 | VM-MIG-ORDERS | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [DB] Forward migration V1018__orders.sql: orders for Venue Management (8 tables) | 5 | Hrushikant Patkar |  | MIG-ORDERS | Tables: orders.after_sale_policy, orders.after_sale_request, orders.chargeback, orders.chargeback_evidence, orders.chargeback_investigation_log, orders.deposit, orders.group_quote, orders.refund_batch. Source DDL: backend/tenant/010-orders.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `orders.after_sale_policy`, `orders.after_sale_request`, `orders.chargeback`, `orders.chargeback_evidence`, `orders.chargeback_investigation_log`, `orders.deposit`, `orders.group_quote`, `orders.refund_batch` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
14 | 3 | MIG-ORDERS-3 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [DB] Forward migration V1127__orders.sql: orders for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens) (1 tables) | 1 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-ORDERS VM-MIG-ORDERS | Tables: orders.discount. Source DDL: backend/tenant/010-orders.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `orders.discount` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
15 | 3 | SVC-CATALOGUE-DRAFTED-3 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] CatalogueService: listBundleCombo, listPackageBundleAdd, listPromotionLifecycleStatus, setProductServicePrice | 5 | Deep Khanvilkar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-3 MIG-CATALOGUE-4 MIG-ORDERS MIG-ORDERS-3 MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listBundleCombo, listPackageBundleAdd, listPromotionLifecycleStatus, setProductServicePrice. Spec: contracts (catalogue, promotions) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listBundleCombo`, `catalogue#listPackageBundleAdd`, `promotions#listPromotionLifecycleStatus`, `catalogue#setProductServicePrice` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 2 | VM-MIG-PAYMENTS | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [DB] Forward migration V1020__payments.sql: payments for Venue Management (1 tables) | 1 | Hrushikant Patkar |  | MIG-PAYMENTS | Tables: payments.provider_cost. Source DDL: backend/tenant/010-payments.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `payments.provider_cost` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
16 | 3 | MIG-PAYMENTS-4 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [DB] Forward migration V1139__payments.sql: payments for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens) (2 tables) | 2 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-PAYMENTS VM-MIG-PAYMENTS | Tables: payments.mixed_tender_rules, payments.payment_terms. Source DDL: backend/tenant/010-payments.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `payments.mixed_tender_rules`, `payments.payment_terms` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
17 | 3 | SVC-ORDER-PAYMENTS-6 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] OrderService: resolveDunningCase, setB2bPaymentTerms, setMixedTenderRules | 5 | Pranay Shinde | OrderService | MIG-PAYMENTS MIG-PAYMENTS-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: resolveDunningCase, setB2bPaymentTerms, setMixedTenderRules. Spec: contracts (payments) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `payments#resolveDunningCase`, `payments#setB2bPaymentTerms`, `payments#setMixedTenderRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-ORDER-PAYMENTS-5 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] OrderService: getB2bPaymentTerms, getDunningPolicy, getInstalmentPolicy, listDunningCases | 3 | Pranay Shinde | OrderService | MIG-PAYMENTS MIG-PAYMENTS-4 PLATFORM-KERNEL SVC-ORDER-DUNNING-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-PAYMENTS-2 SVC-ORDER-PAYMENTS-6 | Operations: getB2bPaymentTerms, getDunningPolicy, getInstalmentPolicy, listDunningCases. Spec: contracts (payments) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `payments#getB2bPaymentTerms`, `payments#getDunningPolicy`, `payments#getInstalmentPolicy`, `payments#listDunningCases` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | MIG-ORDERS-5 | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [DB] Forward migration V1027__orders.sql: orders for Orders & Reservations · Staff App (1 tables) | 1 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-ORDERS VM-MIG-ORDERS | Tables: orders.order_relationship. Source DDL: backend/tenant/010-orders.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `orders.order_relationship` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
14 | 3 | MIG-ORDERS-6 | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [DB] Forward migration V1028__orders.sql: orders for Orders & Reservations · Venue Management (Block A) (5 tables) | 3 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-IDENTITY MIG-LEDGER MIG-ORDERS VM-MIG-ORDERS | Tables: orders.b2b_credit, orders.credit_override, orders.guest_credit_account, orders.invitation_allowance, orders.order_fee. Source DDL: backend/tenant/010-orders.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `orders.b2b_credit`, `orders.credit_override`, `orders.guest_credit_account`, `orders.invitation_allowance`, `orders.order_fee` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
14 | 3 | MIG-ORDERS-2 | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [DB] Forward migration V1025__orders.sql: orders for Subscription & Licensing · Venue Management 2 of 3 (3 tables) | 2 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-ORDERS VM-MIG-ORDERS | Tables: orders.membership_activation_action, orders.membership_migration, orders.membership_renewal. Source DDL: backend/tenant/010-orders.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `orders.membership_activation_action`, `orders.membership_migration`, `orders.membership_renewal` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
12 | 2 | VM-LEDGER-FINANCE-1 | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [BE] LedgerService: settleDeposit, validateRecognitionSchedules | 3 | Sanket Keluskar | LedgerService | MIG-CATALOGUE MIG-LEDGER PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-LEDGER | Operations beyond the first release: settleDeposit, validateRecognitionSchedules. Additive to LedgerService; its first-release owner (Tanmay Dukhande) reviews. Helper task: Tanmay Dukhande owns the service and reviews. Done when `finance#settleDeposit`, `finance#validateRecognitionSchedules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 2 | VM-LEDGER-SETTLEMENT-2 | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [BE] LedgerService: resolveSettlementException | 2 | Chinmay Patkar | LedgerService | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-LEDGER | Operations beyond the first release: resolveSettlementException. Additive to LedgerService; its first-release owner (Tanmay Dukhande) reviews. Helper task: Tanmay Dukhande owns the service and reviews. Done when `finance#resolveSettlementException` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 2 | VM-ORDER-SHIFT-1 | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [BE] OrderService: closeDepositBoxes, getShift | 5 | Deep Khanvilkar | OrderService | MIG-LEDGER MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: closeDepositBoxes, getShift. Additive to OrderService; its first-release owner (Pranay Shinde) reviews. Helper task: Pranay Shinde owns the service and reviews. Done when `shift#closeDepositBoxes`, `shift#getShift` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 2 | VM-ORDER-ORDERS-2 | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [BE] OrderService: getChargebackAnalytics, listDeposits, recordChargeback, recordChargebackOutcome | 8 | Pranay Shinde | OrderService | MIG-CATALOGUE MIG-LEDGER MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-LEDGER VM-MIG-ORDERS | Operations beyond the first release: getChargebackAnalytics, listDeposits, recordChargeback, recordChargebackOutcome. Additive to OrderService; its first-release owner (Pranay Shinde) reviews. Done when `orders#getChargebackAnalytics`, `orders#listDeposits`, `orders#recordChargeback`, `orders#recordChargebackOutcome` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 2 | VM-ORDER-REFUND-1 | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [BE] OrderService: approveRefund, createBulkRefund | 5 | Deep Khanvilkar | OrderService | MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ORDERS | Operations beyond the first release: approveRefund, createBulkRefund. Additive to OrderService; its first-release owner (Pranay Shinde) reviews. Done when `orders#approveRefund`, `orders#createBulkRefund` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 2 | VM-LEDGER-SETTLEMENT-1 | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [BE] LedgerService: getSettlement, ingestSettlementFile, listSettlementExceptions, listSettlements | 8 | Tanmay Dukhande | LedgerService | MIG-PAYMENTS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-LEDGER VM-MIG-PAYMENTS | Operations beyond the first release: getSettlement, ingestSettlementFile, listSettlementExceptions, listSettlements. Additive to LedgerService; its first-release owner (Tanmay Dukhande) reviews. Done when `finance#getSettlement`, `finance#ingestSettlementFile`, `finance#listSettlementExceptions`, `finance#listSettlements` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 3 | SVC-ORDER-REFUND-2 | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [BE] OrderService: simulateRefund | 2 | Surendra | OrderService | MIG-BASELINE PLATFORM-KERNEL | Operations: simulateRefund. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management (Block A); additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#simulateRefund` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-ORDER-ORDERS-14 | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [BE] OrderService: revokeEntitlementShare | 2 | Surendra | OrderService | MIG-ACCESS MIG-IDENTITY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: revokeEntitlementShare. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management (Block A); additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#revokeEntitlementShare` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 2 | VM-IDENTITY-ADMINISTRATION-2 | AM-SETUP-PLATFORM-FOUNDATION-P08-REST | [BE] IdentityService: suggestRoleAssignment | 2 | Chinmay Patkar | IdentityService | MIG-IDENTITY PLATFORM-KERNEL SVC-IDENTITY-ADMINISTRATION-1 SVC-IDENTITY-ADMINISTRATION-2 SVC-IDENTITY-IDENTITY-2 SVC-IDENTITY-SSO-1 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-5 SVC-TENANCY-IDENTITY-1 VM-IDENTITY-ADMINISTRATION-1 VM-MIG-IDENTITY VM-MIG-WORKFORCE | Operations beyond the first release: suggestRoleAssignment. Additive to IdentityService; its first-release owner (Pranay Shinde) reviews. Helper task: Pranay Shinde owns the service and reviews. Done when `identity#suggestRoleAssignment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-IDENTITY-ADMINISTRATION-9 | AM-SETUP-PLATFORM-FOUNDATION-P08-REST | [BE] IdentityService: listAccessReviewCampaigns, listAccessReviewItems, listCapabilityTemplates, listPermissionFindings | 5 | Surendra | IdentityService | MIG-IDENTITY MIG-IDENTITY-3 PLATFORM-KERNEL SVC-IDENTITY-ADMINISTRATION-1 SVC-IDENTITY-ADMINISTRATION-2 SVC-IDENTITY-IDENTITY-2 SVC-IDENTITY-IDENTITY-3 SVC-IDENTITY-SSO-1 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-5 SVC-TENANCY-IDENTITY-1 VM-IDENTITY-ADMINISTRATION-1 VM-MIG-IDENTITY | Operations: listAccessReviewCampaigns, listAccessReviewItems, listCapabilityTemplates, listPermissionFindings. Spec: contracts (identity) at the release tag, served by ADAM. Built for Platform Foundation · Venue Management (setup, the rest of the screens); additive to IdentityService, whose first-release owner (Pranay Shinde) reviews. Done when `identity#listAccessReviewCampaigns`, `identity#listAccessReviewItems`, `identity#listCapabilityTemplates`, `identity#listPermissionFindings` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-IDENTITY-ADMINISTRATION-10 | AM-SETUP-PLATFORM-FOUNDATION-P08-REST | [BE] IdentityService: resolvePermissions | 1 | Deep Khanvilkar | IdentityService | MIG-IDENTITY MIG-PLATFORM PLATFORM-KERNEL SVC-IDENTITY-ADMINISTRATION-1 SVC-IDENTITY-ADMINISTRATION-2 SVC-IDENTITY-IDENTITY-2 SVC-IDENTITY-SSO-1 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-5 SVC-TENANCY-IDENTITY-1 SVC-TENANCY-SCOPE-1 VM-IDENTITY-ADMINISTRATION-1 | Operations: resolvePermissions. Spec: contracts (identity) at the release tag, served by ADAM. Built for Platform Foundation · Venue Management (setup, the rest of the screens); additive to IdentityService, whose first-release owner (Pranay Shinde) reviews. Done when `identity#resolvePermissions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-IDENTITY-IDENTITY-7 | AM-SETUP-PLATFORM-FOUNDATION-P08-REST | [BE] IdentityService: listModules, listSegregationRules, listSegregationViolations | 2 | Sanket Keluskar | IdentityService | MIG-IDENTITY MIG-IDENTITY-3 PLATFORM-KERNEL SVC-IDENTITY-ADMINISTRATION-1 SVC-IDENTITY-ADMINISTRATION-2 SVC-IDENTITY-IDENTITY-2 SVC-IDENTITY-IDENTITY-3 SVC-IDENTITY-SSO-1 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-5 SVC-TENANCY-IDENTITY-1 VM-IDENTITY-ADMINISTRATION-1 | Operations: listModules, listSegregationRules, listSegregationViolations. Spec: contracts (identity) at the release tag, served by ADAM. Built for Platform Foundation · Venue Management (setup, the rest of the screens); additive to IdentityService, whose first-release owner (Pranay Shinde) reviews. Done when `identity#listModules`, `identity#listSegregationRules`, `identity#listSegregationViolations` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-B2B-1 | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [BE] OrderService: overrideCreditLimit, setB2bCreditLimit | 5 | Pranay Shinde | OrderService | MIG-ORDERS-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: overrideCreditLimit, setB2bCreditLimit. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management (Block A); additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#overrideCreditLimit`, `orders#setB2bCreditLimit` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-DRAFTED-2 | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [BE] OrderService: setOrderAmendment, setOrderDetailTransaction | 8 | Pranay Shinde | OrderService | MIG-ACCESS MIG-CATALOGUE MIG-ORDERS MIG-ORDERS-3 MIG-ORDERS-5 MIG-ORDERS-6 MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ORDERS | Operations: setOrderAmendment, setOrderDetailTransaction. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management (Block A); additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#setOrderAmendment`, `orders#setOrderDetailTransaction` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-ORDERS-12 | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [BE] OrderService: convertToTermProduct, issueInvitation, listInvitationAllowances, listMembershipRenewals | 8 | Pranay Shinde | OrderService | MIG-ACCESS MIG-CATALOGUE MIG-IDENTITY MIG-ORDERS MIG-ORDERS-2 MIG-ORDERS-6 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: convertToTermProduct, issueInvitation, listInvitationAllowances, listMembershipRenewals. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management (Block A); additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#convertToTermProduct`, `orders#issueInvitation`, `orders#listInvitationAllowances`, `orders#listMembershipRenewals` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-ORDERS-13 | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [BE] OrderService: listOrderDiscounts, listOrderFees, openGuestCreditAccount, pushWalletPassUpdate | 5 | Tanmay Dukhande | OrderService | MIG-ACCESS MIG-ORDERS MIG-ORDERS-3 MIG-ORDERS-6 MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listOrderDiscounts, listOrderFees, openGuestCreditAccount, pushWalletPassUpdate. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management (Block A); additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listOrderDiscounts`, `orders#listOrderFees`, `orders#openGuestCreditAccount`, `orders#pushWalletPassUpdate` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | MIG-PAYMENTS-7 | AM-PAYMENTS-API-BLOCK-A | [DB] Forward migration V1030__payments.sql: payments for Payments · Venue Management 1 of 3 (5 tables) | 3 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-ORDERS MIG-PAYMENTS VM-MIG-PAYMENTS | Tables: payments.currency_rule, payments.eligibility_rule, payments.failover_policy, payments.fee_rule, payments.provider_event. Source DDL: backend/tenant/010-payments.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `payments.currency_rule`, `payments.eligibility_rule`, `payments.failover_policy`, `payments.fee_rule`, `payments.provider_event` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
16 | 3 | MIG-PAYMENTS-9 | AM-PAYMENTS-API-BLOCK-A | [DB] Forward migration V1071__payments.sql: payments for Payments · Venue Management 3 of 3 (4 tables) | 3 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-PAYMENTS VM-MIG-PAYMENTS | Tables: payments.chargeback_evidence, payments.credit_account, payments.matching_rules, payments.merchant_account. Source DDL: backend/tenant/010-payments.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `payments.chargeback_evidence`, `payments.credit_account`, `payments.matching_rules`, `payments.merchant_account` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
16 | 3 | MIG-PAYMENTS-10 | AM-PAYMENTS-API-BLOCK-A | [DB] Forward migration V1182__payments.sql: payments for Payments · API only (Block A) (1 tables) | 1 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-PAYMENTS VM-MIG-PAYMENTS | Tables: payments.method_config. Source DDL: backend/tenant/010-payments.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `payments.method_config` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
17 | 3 | SVC-ORDER-PAYMENTS-17 | AM-PAYMENTS-API-BLOCK-A | [BE] OrderService: listPaymentMethods, listPaymentProviderConnections, setPaymentRules, simulatePaymentConfiguration | 5 | Deep Khanvilkar | OrderService | MIG-PAYMENTS MIG-PAYMENTS-10 MIG-PAYMENTS-7 MIG-PAYMENTS-9 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listPaymentMethods, listPaymentProviderConnections, setPaymentRules, simulatePaymentConfiguration. Spec: contracts (payments) at the release tag, served by ADAM. Built for Payments · API only (Block A); additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `payments#listPaymentMethods`, `payments#listPaymentProviderConnections`, `payments#setPaymentRules`, `payments#simulatePaymentConfiguration` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ORDER-PAYMENTS-18 | AM-PAYMENTS-API-BLOCK-A | [BE] OrderService: testPaymentProviderConnection | 1 | Tanmay Dukhande | OrderService | MIG-PAYMENTS MIG-PAYMENTS-9 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: testPaymentProviderConnection. Spec: contracts (payments) at the release tag, served by ADAM. Built for Payments · API only (Block A); additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `payments#testPaymentProviderConnection` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 1 | SVC-WALLET-GIFTCARD-1 | AM-WALLET-CASHLESS-P01 | [BE] WalletService: getGiftCard | 1 | Chinmay Patkar | WalletService | MIG-WALLET PLATFORM-KERNEL | Operations: getGiftCard. Spec: handoff/service-docs/backend/WalletService.md#group-giftcard Helper task: Pranay Shinde owns the service and reviews. Done when `wallet#getGiftCard` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
9 | 2 | VM-MIG-WALLET | AM-WALLET-CASHLESS-P08-BLOCK-A-COMPLETION | [DB] Forward migration V1081__wallet.sql: wallet for Venue Management (1 tables) | 1 | Hrushikant Patkar |  | MIG-WALLET | Tables: wallet.adjustment. Source DDL: backend/tenant/010-wallet.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `wallet.adjustment` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
10 | 3 | MIG-WALLET-2 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [DB] Forward migration V1128__wallet.sql: wallet for Public API · Venue Management (1 tables) | 1 | Hrushikant Patkar | WalletService | MIG-BASELINE MIG-WALLET VM-MIG-WALLET | Tables: wallet.risk_rule. Source DDL: backend/tenant/010-wallet.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `wallet.risk_rule` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-WALLET-WALLET-5 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] WalletService: listWalletConfigurationVersions, listWalletTypes, setWalletRiskRuleStatus | 3 | Pranay Shinde | WalletService | MIG-WALLET MIG-WALLET-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listWalletConfigurationVersions, listWalletTypes, setWalletRiskRuleStatus. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#listWalletConfigurationVersions`, `wallet#listWalletTypes`, `wallet#setWalletRiskRuleStatus` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 3 | MIG-WALLET-3 | AM-WALLET-CASHLESS-P08-BLOCK-A-COMPLETION | [DB] Forward migration V1145__wallet.sql: wallet for Wallet & Cashless · Venue Management (Block A completion) (1 tables) | 1 | Hrushikant Patkar | WalletService | MIG-BASELINE MIG-WALLET VM-MIG-WALLET | Tables: wallet.dispute. Source DDL: backend/tenant/010-wallet.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `wallet.dispute` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 2 | VM-WALLET-WALLET-1 | AM-WALLET-CASHLESS-P08-BLOCK-A-COMPLETION | [BE] WalletService: expireCreditLots, listCreditLots | 3 | Sanket Keluskar | WalletService | MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-WALLET | Operations beyond the first release: expireCreditLots, listCreditLots. Additive to WalletService; its first-release owner (Pranay Shinde) reviews. Helper task: Pranay Shinde owns the service and reviews. Done when `wallet#expireCreditLots`, `wallet#listCreditLots` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-WALLET-WALLET-8 | AM-WALLET-CASHLESS-P08-BLOCK-A-COMPLETION | [BE] WalletService: captureWalletHold, holdWalletFunds, listWalletDisputes, releaseWalletHold | 8 | Pranay Shinde | WalletService | MIG-PLATFORM MIG-WALLET MIG-WALLET-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: captureWalletHold, holdWalletFunds, listWalletDisputes, releaseWalletHold. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Wallet & Cashless · Venue Management (Block A completion); additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#captureWalletHold`, `wallet#holdWalletFunds`, `wallet#listWalletDisputes`, `wallet#releaseWalletHold` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-WALLET-WALLET-9 | AM-WALLET-CASHLESS-P08-BLOCK-A-COMPLETION | [BE] WalletService: resolveWalletDispute, setWalletIntegrationMapping, withdrawWalletDispute | 5 | Pranay Shinde | WalletService | MIG-WALLET MIG-WALLET-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: resolveWalletDispute, setWalletIntegrationMapping, withdrawWalletDispute. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Wallet & Cashless · Venue Management (Block A completion); additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#resolveWalletDispute`, `wallet#setWalletIntegrationMapping`, `wallet#withdrawWalletDispute` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-WALLET-WALLET-4 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] WalletService: diffWalletConfigurationVersion, getWalletFundingRules, getWalletRefundPolicy, getWalletRiskRules | 5 | Pranay Shinde | WalletService | MIG-WALLET MIG-WALLET-2 PLATFORM-KERNEL SVC-WALLET-WALLET-1 SVC-WALLET-WALLET-2 SVC-WALLET-WALLET-5 SVC-WALLET-WALLET-9 | Operations: diffWalletConfigurationVersion, getWalletFundingRules, getWalletRefundPolicy, getWalletRiskRules. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#diffWalletConfigurationVersion`, `wallet#getWalletFundingRules`, `wallet#getWalletRefundPolicy`, `wallet#getWalletRiskRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-ACCESS-ACCESS-2 | AM-ADMISSION-ACCESS-P01 | [BE] AccessService: enrolFaceTag, getEntitlement, getEntitlementCredential, getEntitlementHistory | 8 | Tanmay Dukhande | AccessService | MIG-ACCESS MIG-CATALOGUE MIG-IDENTITY MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: enrolFaceTag, getEntitlement, getEntitlementCredential, getEntitlementHistory. Spec: handoff/service-docs/backend/AccessService.md#group-access. Done when `access#enrolFaceTag`, `access#getEntitlement`, `access#getEntitlementCredential`, `access#getEntitlementHistory` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-ACCESS-GENERAL-1 | AM-ADMISSION-ACCESS-P01 | [BE] AccessService: getParkingEntitlement | 1 | Chinmay Patkar | AccessService | MIG-ACCESS PLATFORM-KERNEL SVC-ACCESS-ACCESS-7 | Operations: getParkingEntitlement. Spec: handoff/service-docs/backend/AccessService.md#group-general Helper task: Hrushikant Patkar owns the service and reviews. Done when `access#getParkingEntitlement` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-ACCESS-ACCESS-1 | AM-ADMISSION-ACCESS-P02 | [BE] AccessService: approveManualOverrideSupervisor, bindCredentialDevice, deleteAccessPointGroup, enrolFacePass | 8 | Tanmay Dukhande | AccessService | MIG-ACCESS MIG-IDENTITY MIG-MARKETING MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: approveManualOverrideSupervisor, bindCredentialDevice, deleteAccessPointGroup, enrolFacePass. Spec: handoff/service-docs/backend/AccessService.md#group-access. Done when `access#approveManualOverrideSupervisor`, `access#bindCredentialDevice`, `access#deleteAccessPointGroup`, `access#enrolFacePass` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 1 | SVC-ACCESS-ACCESS-3 | AM-WHITE-LABEL-P01 | [BE] AccessService: getFacePassEnrolment, listEntitlements, listMyEntitlements, listParkingFacilities | 8 | Pranay Shinde | AccessService | MIG-ACCESS MIG-CATALOGUE MIG-IDENTITY MIG-PII PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-6 SVC-ACCESS-ACCESS-7 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-ENTITLEMENT-1 SVC-CATALOGUE-PRODUCT-4 SVC-IDENTITY-IDENTITY-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 | Operations: getFacePassEnrolment, listEntitlements, listMyEntitlements, listParkingFacilities. Spec: handoff/service-docs/backend/AccessService.md#group-access. Done when `access#getFacePassEnrolment`, `access#listEntitlements`, `access#listMyEntitlements`, `access#listParkingFacilities` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 1 | SVC-MARKETING-CONSENT-2 | AM-WHITE-LABEL-P13 | [BE] MarketingService: getGuestConsents, listConsentAnswers, listConsentPurposes, listConsentQuestions | 5 | Deep Khanvilkar | MarketingService | MIG-MARKETING MIG-PII PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-IDENTITY-GUESTAUTH-1 SVC-IDENTITY-GUESTAUTH-2 SVC-IDENTITY-GUESTAUTH-3 SVC-IDENTITY-IDENTITY-4 SVC-MARKETING-CONSENT-1 SVC-MARKETING-CONSENT-3 SVC-MARKETING-CONSENT-4 SVC-MARKETING-CONSENT-5 SVC-MARKETING-MARKETING-6 SVC-MARKETING-MARKETING-7 SVC-ORDER-CART-1 SVC-ORDER-ORDERS-5 | Operations: getGuestConsents, listConsentAnswers, listConsentPurposes, listConsentQuestions. Spec: handoff/service-docs/backend/MarketingService.md#group-consent Helper task: Pranay Shinde owns the service and reviews. Done when `marketing-crm#getGuestConsents`, `marketing-crm#listConsentAnswers`, `marketing-crm#listConsentPurposes`, `marketing-crm#listConsentQuestions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 1 | SVC-ORDER-DRAFTED-1 | AM-ORDERS-RESERVATIONS-P04 | [BE] OrderService: listGroupArrivalCheck | 1 | Chinmay Patkar | OrderService | MIG-ACCESS MIG-ORDERS PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 | Operations: listGroupArrivalCheck. Spec: handoff/service-docs/backend/OrderService.md#group-drafted Helper task: Pranay Shinde owns the service and reviews. Done when `orders#listGroupArrivalCheck` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | MIG-PLATFORM-3 | AM-ADMISSION-ACCESS-P07-BLOCK-A | [DB] Forward migration V1031__platform.sql: platform for Platform Operations · Scanner (2 tables) | 2 | Hrushikant Patkar | TenancyService | MIG-ACCESS MIG-BASELINE MIG-ORDERS MIG-PLATFORM MIG-WALLET VM-MIG-PLATFORM | Tables: platform.cross_region_entitlement, platform.wallet_authorisation. Source DDL: backend/tenant/010-platform.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `platform.cross_region_entitlement`, `platform.wallet_authorisation` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
15 | 3 | SVC-CROSSREGION-REDEMPTION-2 | AM-ADMISSION-ACCESS-P07-BLOCK-A | [BE] CrossRegionService: consumeCrossRegionEntitlement | 2 | Deep Khanvilkar | CrossRegionService | MIG-PLATFORM-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: consumeCrossRegionEntitlement. Spec: contracts (cross-region) at the release tag, served by ADAM. Built for Admission & Access · Scanner (Block A); additive to CrossRegionService, whose first-release owner (its owner) reviews. Done when `cross-region#consumeCrossRegionEntitlement` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
4 | 2 | VM-MIG-ACCREDITATION | AM-ADMISSION-ACCESS-P08-BLOCK-A | [DB] Forward migration V1041__accreditation.sql: accreditation for Venue Management (4 tables) | 3 | Hrushikant Patkar |  | MIG-BASELINE | Tables: accreditation.application, accreditation.credential, accreditation.holder, accreditation.validity. Source DDL: backend/tenant/010-accreditation.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `accreditation.application`, `accreditation.credential`, `accreditation.holder`, `accreditation.validity` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
5 | 3 | MIG-ACCREDITATION-3 | AM-ADMISSION-ACCESS-P07-BLOCK-A | [DB] Forward migration V1043__accreditation.sql: accreditation for Ticketing · Venue Management 9 of 10 (1 tables) | 1 | Hrushikant Patkar | TenancyService | MIG-BASELINE VM-MIG-ACCREDITATION | Tables: accreditation.access_profile. Source DDL: backend/tenant/010-accreditation.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `accreditation.access_profile` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
5 | 3 | MIG-ACCREDITATION-4 | AM-ADMISSION-ACCESS-P07-BLOCK-A | [DB] Forward migration V1044__accreditation.sql: accreditation for Admission & Access · Scanner (Block A) (2 tables) | 2 | Hrushikant Patkar | TenancyService | MIG-BASELINE VM-MIG-ACCREDITATION | Tables: accreditation.holder_access, accreditation.programme. Source DDL: backend/tenant/010-accreditation.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `accreditation.holder_access`, `accreditation.programme` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
7 | 2 | VM-MIG-REPORTING | AM-ADMISSION-ACCESS-P08-BLOCK-A | [DB] Forward migration V1048__reporting.sql: reporting for Venue Management (2 tables) | 1 | Hrushikant Patkar |  | MIG-REPORTING | Tables: reporting.kpi_target, reporting.schedule_recipient. Source DDL: backend/tenant/010-reporting.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `reporting.kpi_target`, `reporting.schedule_recipient` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
14 | 2 | VM-MIG-ACCESS | AM-ADMISSION-ACCESS-P08-BLOCK-A-COMPLETION | [DB] Forward migration V1019__access.sql: access for Venue Management (10 tables) | 5 | Hrushikant Patkar |  | MIG-ACCESS | Tables: access.access_change, access.accreditation_credential, access.credential_binding, access.credential_event, access.dynamic_policy, access.dynamic_policy_version, access.media_replacement_policy, access.media_template, access.media_type, access.policy_scope_assignment. Source DDL: backend/tenant/010-access.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `access.access_change`, `access.accreditation_credential`, `access.credential_binding`, `access.credential_event`, `access.dynamic_policy`, `access.dynamic_policy_version`, `access.media_replacement_policy`, `access.media_template` and 2 more runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
15 | 3 | MIG-ACCESS-3 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [DB] Forward migration V1115__access.sql: access for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens) (1 tables) | 1 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-BASELINE VM-MIG-ACCESS | Tables: access.companion_rule. Source DDL: backend/tenant/010-access.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `access.companion_rule` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
16 | 3 | SVC-ACCESS-ACCESS-9 | AM-SETUP-TICKETING-GUEST-COMMERCE-P08-REST | [BE] AccessService: archiveMediaTemplate, listGuestCompanionEligibility, listMediaDesign | 3 | Deep Khanvilkar | AccessService | MIG-ACCESS MIG-ACCESS-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCESS | Operations: archiveMediaTemplate, listGuestCompanionEligibility, listMediaDesign. Spec: contracts (access) at the release tag, served by ADAM. Built for Ticketing & Guest Commerce · Venue Management (setup, the rest of the screens); additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#archiveMediaTemplate`, `access#listGuestCompanionEligibility`, `access#listMediaDesign` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 2 | VM-ACCESS-SYNC-1 | AM-ADMISSION-ACCESS-P07-BLOCK-A | [BE] AccessService: getOfflinePackage, listScans, syncScans | 5 | Deep Khanvilkar | AccessService | MIG-ACCESS MIG-PLATFORM MIG-SYNC PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-ACCESS | Operations beyond the first release: getOfflinePackage, listScans, syncScans. Additive to AccessService; its first-release owner (Hrushikant Patkar) reviews. Done when `access#getOfflinePackage`, `access#listScans`, `access#syncScans` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 2 | VM-ACCESS-VALIDATION-1 | AM-ADMISSION-ACCESS-P07-BLOCK-A | [BE] AccessService: lookupTicket, overrideAccess, validateAccess, validateGroupAccess | 8 | Tanmay Dukhande | AccessService | MIG-ACCESS MIG-CATALOGUE MIG-IDENTITY MIG-ORDERS MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-ACCESS | Operations beyond the first release: lookupTicket, overrideAccess, validateAccess, validateGroupAccess. Additive to AccessService; its first-release owner (Hrushikant Patkar) reviews. Done when `access#lookupTicket`, `access#overrideAccess`, `access#validateAccess`, `access#validateGroupAccess` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | MIG-ACCESS-5 | AM-ADMISSION-ACCESS-P08-BLOCK-A | [DB] Forward migration V1148__access.sql: access for Admission & Access · Venue Management (Block A) (1 tables) | 1 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-BASELINE VM-MIG-ACCESS | Tables: access.hardware_certification. Source DDL: backend/tenant/010-access.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `access.hardware_certification` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
13 | 2 | VM-ORDER-ORDERS-3 | AM-ADMISSION-ACCESS-P08-BLOCK-A | [BE] OrderService: relinquishStoredValue, updateGroupBooking | 3 | Sanket Keluskar | OrderService | MIG-ORDERS MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: relinquishStoredValue, updateGroupBooking. Additive to OrderService; its first-release owner (Pranay Shinde) reviews. Helper task: Pranay Shinde owns the service and reviews. Done when `orders#relinquishStoredValue`, `orders#updateGroupBooking` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 2 | VM-ORDER-ORDERS-1 | AM-ADMISSION-ACCESS-P08-BLOCK-A | [BE] OrderService: assignChargeback, authoriseStoredValue, captureStoredValue, createGroupBooking | 8 | Pranay Shinde | OrderService | MIG-ORDERS MIG-PII MIG-PLATFORM MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ORDERS VM-MIG-PROMOTIONS | Operations beyond the first release: assignChargeback, authoriseStoredValue, captureStoredValue, createGroupBooking. Additive to OrderService; its first-release owner (Pranay Shinde) reviews. Done when `orders#assignChargeback`, `orders#authoriseStoredValue`, `orders#captureStoredValue`, `orders#createGroupBooking` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 2 | VM-ACCESS-ACCESS-1 | AM-ADMISSION-ACCESS-P08-BLOCK-A-COMPLETION | [BE] AccessService: listCredentialReplacementReissue, replaceCredential, setPdfPrintablePos | 5 | Sanket Keluskar | AccessService | MIG-ACCESS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCESS | Operations beyond the first release: listCredentialReplacementReissue, replaceCredential, setPdfPrintablePos. Additive to AccessService; its first-release owner (Hrushikant Patkar) reviews. Done when `access#listCredentialReplacementReissue`, `access#replaceCredential`, `access#setPdfPrintablePos` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 2 | VM-ACCESS-ACCESSPOINT-1 | AM-ADMISSION-ACCESS-P08-BLOCK-A | [BE] AccessService: listAccessPoints | 2 | Chinmay Patkar | AccessService | MIG-ACCESS PLATFORM-KERNEL SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 | Operations beyond the first release: listAccessPoints. Additive to AccessService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `access#listAccessPoints` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 2 | VM-ACCESS-GENERAL-1 | AM-ADMISSION-ACCESS-P08-BLOCK-A-COMPLETION | [BE] AccessService: getPdfPrintablePos | 1 | Chinmay Patkar | AccessService | PLATFORM-KERNEL SVC-ACCESS-ACCESS-9 VM-ACCESS-ACCESS-1 VM-MIG-ACCESS | Operations beyond the first release: getPdfPrintablePos. Additive to AccessService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `access#getPdfPrintablePos` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-ACCESS-VALIDATION-2 | AM-ADMISSION-ACCESS-P08-BLOCK-A | [BE] AccessService: issueOrderEntitlements | 2 | Deep Khanvilkar | AccessService | MIG-ACCESS MIG-CATALOGUE MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: issueOrderEntitlements. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management (Block A); additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#issueOrderEntitlements` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-PLATFORM-LICENSING-2 | AM-SUBSCRIPTION-LICENSING-P09 | [BE] PlatformService: getEntitlementUsage | 1 | Deep Khanvilkar | PlatformService | MIG-ACCESS MIG-CONTROL MIG-CONTROL-7 PLATFORM-KERNEL SVC-ACCESS-ACCESS-2 SVC-ACCESS-VALIDATION-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-PLATFORM-LICENSING-1 SVC-PLATFORM-LICENSING-3 VM-ACCESS-ACCESS-1 | Operations: getEntitlementUsage. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · TICVAI Console 1 of 6; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#getEntitlementUsage` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-11 | AM-ADMISSION-ACCESS-P08-BLOCK-A | [BE] AccessService: createParkingEntitlement, getHardwareModelCertification, listAccessChanges, listEntryExitRule | 5 | Tanmay Dukhande | AccessService | MIG-ACCESS MIG-ACCESS-5 MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCESS | Operations: createParkingEntitlement, getHardwareModelCertification, listAccessChanges, listEntryExitRule. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management (Block A); additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#createParkingEntitlement`, `access#getHardwareModelCertification`, `access#listAccessChanges`, `access#listEntryExitRule` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-12 | AM-ADMISSION-ACCESS-P08-BLOCK-A | [BE] AccessService: listEntryTemporaryExit, setHardwareModelCertification, setVirtualTicketCredential, verifyIdentity | 8 | Tanmay Dukhande | AccessService | MIG-ACCESS MIG-ACCESS-5 MIG-CATALOGUE MIG-ORDERS MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCESS | Operations: listEntryTemporaryExit, setHardwareModelCertification, setVirtualTicketCredential, verifyIdentity. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management (Block A); additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listEntryTemporaryExit`, `access#setHardwareModelCertification`, `access#setVirtualTicketCredential`, `access#verifyIdentity` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 2 | VM-FNB-MENU-1 | AM-ADMISSION-ACCESS-P08-BLOCK-A | [BE] FnbService: getMenu, setMenuItemDailyCount | 3 | Sanket Keluskar | FnbService | MIG-FNB PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: getMenu, setMenuItemDailyCount. Additive to FnbService; its first-release owner (Tanmay Dukhande) reviews. Helper task: Tanmay Dukhande owns the service and reviews. Done when `fnb#getMenu`, `fnb#setMenuItemDailyCount` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 2 | VM-RETAIL-RETAIL-1 | AM-ADMISSION-ACCESS-P08-BLOCK-A | [BE] RetailService: disposeShopAndDrop | 1 | Sanket Keluskar | RetailService | MIG-RETAIL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: disposeShopAndDrop. Additive to RetailService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `retail#disposeShopAndDrop` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-LEDGER-LEDGER-1 | AM-FINANCE-TAX-P01 | [BE] LedgerService: listFxRates, setFxRate | 3 | Sanket Keluskar | LedgerService | MIG-LEDGER PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listFxRates, setFxRate. Spec: handoff/service-docs/backend/LedgerService.md#group-ledger Helper task: Tanmay Dukhande owns the service and reviews. Done when `finance#listFxRates`, `finance#setFxRate` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | MIG-LEDGER-2 | AM-FINANCE-TAX-P08-BLOCK-A | [DB] Forward migration V1032__ledger.sql: ledger for Finance & Tax · Venue Management (Block A) (2 tables) | 2 | Hrushikant Patkar | LedgerService | MIG-ACCESS MIG-BASELINE MIG-LEDGER MIG-ORDERS VM-MIG-LEDGER | Tables: ledger.inter_entity_obligation, ledger.tax_exemption. Source DDL: backend/tenant/010-ledger.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `ledger.inter_entity_obligation`, `ledger.tax_exemption` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
12 | 2 | VM-LEDGER-LEDGER-1 | AM-FINANCE-TAX-P08-BLOCK-A | [BE] LedgerService: abandonPeriodClose, beginPeriodClose, getTrialBalance, listLedgerEntries | 5 | Deep Khanvilkar | LedgerService | MIG-LEDGER PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-LEDGER | Operations beyond the first release: abandonPeriodClose, beginPeriodClose, getTrialBalance, listLedgerEntries. Additive to LedgerService; its first-release owner (Tanmay Dukhande) reviews. Done when `finance#abandonPeriodClose`, `finance#beginPeriodClose`, `finance#getTrialBalance`, `finance#listLedgerEntries` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-LEDGER-FINANCE-3 | AM-FINANCE-TAX-P08-BLOCK-A | [BE] LedgerService: disputeObligation, recordWriteOff, resolveObligationDispute | 8 | Pranay Shinde | LedgerService | MIG-CONTROL MIG-LEDGER MIG-LEDGER-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: disputeObligation, recordWriteOff, resolveObligationDispute. Spec: contracts (finance) at the release tag, served by ADAM. Built for Finance & Tax · Venue Management (Block A); additive to LedgerService, whose first-release owner (Tanmay Dukhande) reviews. Done when `finance#disputeObligation`, `finance#recordWriteOff`, `finance#resolveObligationDispute` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-LEDGER-LEDGER-3 | AM-FINANCE-TAX-P08-BLOCK-A | [BE] LedgerService: listInterEntityObligations, postOrderRevenue, runFxRevaluation | 8 | Surendra | LedgerService | MIG-LEDGER MIG-LEDGER-2 MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: listInterEntityObligations, postOrderRevenue, runFxRevaluation. Spec: contracts (finance) at the release tag, served by ADAM. Built for Finance & Tax · Venue Management (Block A); additive to LedgerService, whose first-release owner (Tanmay Dukhande) reviews. Done when `finance#listInterEntityObligations`, `finance#postOrderRevenue`, `finance#runFxRevaluation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-LEDGER-TAX-4 | AM-FINANCE-TAX-P08-BLOCK-A | [BE] LedgerService: calculateTax, recordEInvoiceTransmissionStatus | 5 | Deep Khanvilkar | LedgerService | MIG-CATALOGUE-5 MIG-LEDGER MIG-LEDGER-2 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: calculateTax, recordEInvoiceTransmissionStatus. Spec: contracts (finance) at the release tag, served by ADAM. Built for Finance & Tax · Venue Management (Block A); additive to LedgerService, whose first-release owner (Tanmay Dukhande) reviews. Done when `finance#calculateTax`, `finance#recordEInvoiceTransmissionStatus` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 2 | VM-LEDGER-FISCAL-1 | AM-FINANCE-TAX-API-BLOCK-A-COMPLETION | [BE] LedgerService: closeFiscalPeriod, listFiscalPeriods | 3 | Sanket Keluskar | LedgerService | MIG-LEDGER MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-LEDGER | Operations beyond the first release: closeFiscalPeriod, listFiscalPeriods. Additive to LedgerService; its first-release owner (Tanmay Dukhande) reviews. Helper task: Tanmay Dukhande owns the service and reviews. Done when `finance#closeFiscalPeriod`, `finance#listFiscalPeriods` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-LEDGER-FINANCE-5 | AM-FINANCE-TAX-API-BLOCK-A-COMPLETION | [BE] LedgerService: getUnifiedReconciliation | 2 | Tanmay Dukhande | LedgerService | MIG-LEDGER MIG-ORDERS MIG-WALLET PLATFORM-KERNEL SVC-LEDGER-FINANCE-3 SVC-LEDGER-LEDGER-3 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-3 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-WALLET-CARD-1 SVC-WALLET-RETAIL-1 SVC-WALLET-RETAIL-2 SVC-WALLET-WALLET-2 SVC-WALLET-WALLET-8 VM-LEDGER-FINANCE-1 VM-LEDGER-SETTLEMENT-1 VM-MIG-LEDGER VM-ORDER-ORDERS-1 VM-ORDER-ORDERS-2 VM-ORDER-SHIFT-1 VM-WALLET-WALLET-1 | Operations: getUnifiedReconciliation. Spec: contracts (finance) at the release tag, served by ADAM. Built for Finance & Tax · API only (Block A completion); additive to LedgerService, whose first-release owner (Tanmay Dukhande) reviews. Done when `finance#getUnifiedReconciliation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-TENANCY-ROTA-1 | AM-SETUP-VENUE-OPERATIONS-P08 | [BE] TenancyService: createRotaAssignment, listRotaAssignments, updateRotaAssignment | 8 | Pranay Shinde | TenancyService | MIG-IDENTITY MIG-PLATFORM MIG-WORKFORCE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createRotaAssignment, listRotaAssignments, updateRotaAssignment. Spec: handoff/service-docs/backend/TenancyService.md#group-rota. Done when `workforce#createRotaAssignment`, `workforce#listRotaAssignments`, `workforce#updateRotaAssignment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-ACCESS-ACCESS-5 | AM-SETUP-VENUE-OPERATIONS-P08 | [BE] AccessService: setCredentialActivationDisplay, setDeviceBindingPolicy, setFaceMatchingVerification, setFacePassEnrollment | 8 | Tanmay Dukhande | AccessService | MIG-ACCESS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setCredentialActivationDisplay, setDeviceBindingPolicy, setFaceMatchingVerification, setFacePassEnrollment. Spec: handoff/service-docs/backend/AccessService.md#group-access. Done when `access#setCredentialActivationDisplay`, `access#setDeviceBindingPolicy`, `access#setFaceMatchingVerification`, `access#setFacePassEnrollment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-VENUEOPS-INSPECTION-1 | AM-SETUP-VENUE-OPERATIONS-P08 | [BE] VenueOpsService: createInspectionTemplate | 2 | Chinmay Patkar | VenueOpsService | MIG-MAINTENANCE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createInspectionTemplate. Spec: handoff/service-docs/backend/VenueOpsService.md#group-inspection Helper task: Hrushikant Patkar owns the service and reviews. Done when `maintenance#createInspectionTemplate` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-VENUEOPS-RESOURCES-4 | AM-SETUP-VENUE-OPERATIONS-P08 | [BE] VenueOpsService: setExperienceResourceRequirements, setResourceLifecycleState, setResourceSchedule, updateResource | 8 | Tanmay Dukhande | VenueOpsService | MIG-RESOURCES PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setExperienceResourceRequirements, setResourceLifecycleState, setResourceSchedule, updateResource. Spec: handoff/service-docs/backend/VenueOpsService.md#group-resources. Done when `resources#setExperienceResourceRequirements`, `resources#setResourceLifecycleState`, `resources#setResourceSchedule`, `resources#updateResource` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-VENUEOPS-RESOURCES-5 | AM-SETUP-VENUE-OPERATIONS-P08 | [BE] VenueOpsService: updateResourcePackage | 3 | Sanket Keluskar | VenueOpsService | MIG-RESOURCES PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updateResourcePackage. Spec: handoff/service-docs/backend/VenueOpsService.md#group-resources Helper task: Hrushikant Patkar owns the service and reviews. Done when `resources#updateResourcePackage` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-VENUEOPS-RESOURCES-1 | AM-SETUP-VENUE-OPERATIONS-P08 | [BE] VenueOpsService: cloneResource, createResource, createResourceBlock, createResourceHold | 8 | Tanmay Dukhande | VenueOpsService | MIG-RESOURCES MIG-VENUEMAP PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: cloneResource, createResource, createResourceBlock, createResourceHold. Spec: handoff/service-docs/backend/VenueOpsService.md#group-resources. Done when `resources#cloneResource`, `resources#createResource`, `resources#createResourceBlock`, `resources#createResourceHold` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
7 | 2 | VM-MIG-RESOURCES | AM-SETUP-VENUE-OPERATIONS-P08-REST | [DB] Forward migration V1015__resources.sql: resources for Venue Management (3 tables) | 2 | Hrushikant Patkar |  | MIG-RESOURCES | Tables: resources.performance_participant, resources.qualification, resources.selection_policy. Source DDL: backend/tenant/010-resources.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `resources.performance_participant`, `resources.qualification`, `resources.selection_policy` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
9 | 2 | VM-MIG-MAINTENANCE | AM-SETUP-VENUE-OPERATIONS-P08-REST | [DB] Forward migration V1037__maintenance.sql: maintenance for Venue Management (9 tables) | 5 | Hrushikant Patkar |  | MIG-MAINTENANCE | Tables: maintenance.asset_document, maintenance.asset_status_change, maintenance.incident_authority_notification, maintenance.incident_history, maintenance.incident_investigation_note, maintenance.incident_involved_party, maintenance.preventive_plan, maintenance.priority_scoring_model, maintenance.vendor_service_request. Source DDL: backend/tenant/010-maintenance.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `maintenance.asset_document`, `maintenance.asset_status_change`, `maintenance.incident_authority_notification`, `maintenance.incident_history`, `maintenance.incident_investigation_note`, `maintenance.incident_involved_party`, `maintenance.preventive_plan`, `maintenance.priority_scoring_model` and 1 more runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
8 | 3 | MIG-RESOURCES-2 | AM-SETUP-VENUE-OPERATIONS-P08-REST | [DB] Forward migration V1161__resources.sql: resources for Venue Operations · Venue Management (setup, the rest of the screens) (1 tables) | 1 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE MIG-RESOURCES VM-MIG-RESOURCES | Tables: resources.resource_type. Source DDL: backend/tenant/010-resources.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `resources.resource_type` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
10 | 3 | MIG-MAINTENANCE-2 | AM-SETUP-VENUE-OPERATIONS-P08-REST | [DB] Forward migration V1134__maintenance.sql: maintenance for Venue Operations · Venue Management (setup, the rest of the screens) (1 tables) | 1 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE MIG-MAINTENANCE VM-MIG-MAINTENANCE | Tables: maintenance.inspection_item. Source DDL: backend/tenant/010-maintenance.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `maintenance.inspection_item` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
10 | 3 | MIG-WORKFORCE-2 | AM-SETUP-VENUE-OPERATIONS-P08-REST | [DB] Forward migration V1059__workforce.sql: workforce for Venue Operations · Venue Management (setup, the rest of the screens) (1 tables) | 1 | Hrushikant Patkar | TenancyService | MIG-APPROVALS MIG-BASELINE MIG-WORKFORCE VM-MIG-WORKFORCE | Tables: workforce.shift_swap. Source DDL: backend/tenant/010-workforce.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `workforce.shift_swap` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
15 | 3 | MIG-ACCESS-8 | AM-SETUP-VENUE-OPERATIONS-P08-REST | [DB] Forward migration V1150__access.sql: access for Admission & Access · Venue Management 3 of 8 (6 tables) | 5 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-BASELINE VM-MIG-ACCESS | Tables: access.access_point_configuration, access.device_configuration, access.edge_node, access.edge_package, access.gate_outcome_profile, access.hardware_model. Source DDL: backend/tenant/010-access.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `access.access_point_configuration`, `access.device_configuration`, `access.edge_node`, `access.edge_package`, `access.gate_outcome_profile`, `access.hardware_model` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-TENANCY-ROTA-2 | AM-SETUP-VENUE-OPERATIONS-P08-REST | [BE] TenancyService: requestShiftSwap | 2 | Deep Khanvilkar | TenancyService | MIG-APPROVALS MIG-IDENTITY MIG-WORKFORCE MIG-WORKFORCE-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: requestShiftSwap. Spec: contracts (workforce) at the release tag, served by ADAM. Built for Venue Operations · Venue Management (setup, the rest of the screens); additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `workforce#requestShiftSwap` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-ACCESS-ACCESS-58 | AM-SETUP-VENUE-OPERATIONS-P08-REST | [BE] AccessService: cancelGateModeChange, listAccessLocationGrouping, listCredentialActivationDisplay, listDeviceBindingSession | 3 | Sanket Keluskar | AccessService | MIG-ACCESS MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: cancelGateModeChange, listAccessLocationGrouping, listCredentialActivationDisplay, listDeviceBindingSession. Spec: contracts (access) at the release tag, served by ADAM. Built for Venue Operations · Venue Management (setup, the rest of the screens); additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#cancelGateModeChange`, `access#listAccessLocationGrouping`, `access#listCredentialActivationDisplay`, `access#listDeviceBindingSession` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-ACCESS-ACCESSPOINT-3 | AM-SETUP-VENUE-OPERATIONS-P08-REST | [BE] AccessService: getAccessPoint, listAdmissionRules, listBlacklist, removeBlacklistEntry | 8 | Pranay Shinde | AccessService | MIG-ACCESS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getAccessPoint, listAdmissionRules, listBlacklist, removeBlacklistEntry. Spec: contracts (access) at the release tag, served by ADAM. Built for Venue Operations · Venue Management (setup, the rest of the screens); additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#getAccessPoint`, `access#listAdmissionRules`, `access#listBlacklist`, `access#removeBlacklistEntry` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-60 | AM-SETUP-VENUE-OPERATIONS-P08-REST | [BE] AccessService: listLiveGateMode, listVisualAccessRules, releaseCredentialDevice, setEntryRulePoints | 5 | Tanmay Dukhande | AccessService | MIG-ACCESS MIG-ACCESS-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCESS | Operations: listLiveGateMode, listVisualAccessRules, releaseCredentialDevice, setEntryRulePoints. Spec: contracts (access) at the release tag, served by ADAM. Built for Venue Operations · Venue Management (setup, the rest of the screens); additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listLiveGateMode`, `access#listVisualAccessRules`, `access#releaseCredentialDevice`, `access#setEntryRulePoints` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-59 | AM-SETUP-VENUE-OPERATIONS-P08-REST | [BE] AccessService: listEntryRulePoints, listFaceMatchingVerification, listFaceTagTemporary, listGateModeFree | 3 | Tanmay Dukhande | AccessService | MIG-ACCESS PLATFORM-KERNEL SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-5 SVC-ACCESS-ACCESS-6 SVC-ACCESS-ACCESS-60 SVC-ACCESS-ACCESS-7 | Operations: listEntryRulePoints, listFaceMatchingVerification, listFaceTagTemporary, listGateModeFree. Spec: contracts (access) at the release tag, served by ADAM. Built for Venue Operations · Venue Management (setup, the rest of the screens); additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listEntryRulePoints`, `access#listFaceMatchingVerification`, `access#listFaceTagTemporary`, `access#listGateModeFree` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-GENERAL-2 | AM-SETUP-VENUE-OPERATIONS-P08-REST | [BE] AccessService: getBiometricVerificationProfile, getBleBeaconGeofence, getFacePassEnrollmentConfiguration, getVirtualTicketIdentity | 3 | Tanmay Dukhande | AccessService | MIG-ACCESS PLATFORM-KERNEL SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-5 SVC-ACCESS-ACCESS-6 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 | Operations: getBiometricVerificationProfile, getBleBeaconGeofence, getFacePassEnrollmentConfiguration, getVirtualTicketIdentity. Spec: contracts (access) at the release tag, served by ADAM. Built for Venue Operations · Venue Management (setup, the rest of the screens); additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#getBiometricVerificationProfile`, `access#getBleBeaconGeofence`, `access#getFacePassEnrollmentConfiguration`, `access#getVirtualTicketIdentity` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-INSPECTION-2 | AM-SETUP-VENUE-OPERATIONS-P08-REST | [BE] VenueOpsService: listInspectionTemplates, listInspections, submitInspection | 5 | Tanmay Dukhande | VenueOpsService | MIG-MAINTENANCE MIG-MAINTENANCE-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listInspectionTemplates, listInspections, submitInspection. Spec: contracts (maintenance) at the release tag, served by ADAM. Built for Venue Operations · Venue Management (setup, the rest of the screens); additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `maintenance#listInspectionTemplates`, `maintenance#listInspections`, `maintenance#submitInspection` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-LEDGER-FINANCE-1 | AM-SETUP-FINANCE-INSIGHTS-P08 | [BE] LedgerService: ingestFxRates, setFxProvider | 3 | Sanket Keluskar | LedgerService | MIG-LEDGER MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: ingestFxRates, setFxProvider. Spec: handoff/service-docs/backend/LedgerService.md#group-finance Helper task: Tanmay Dukhande owns the service and reviews. Done when `finance#ingestFxRates`, `finance#setFxProvider` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-LEDGER-FISCAL-1 | AM-SETUP-FINANCE-INSIGHTS-P08 | [BE] LedgerService: createLegalEntity | 2 | Chinmay Patkar | LedgerService | MIG-LEDGER PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createLegalEntity. Spec: handoff/service-docs/backend/LedgerService.md#group-fiscal Helper task: Tanmay Dukhande owns the service and reviews. Done when `finance#createLegalEntity` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-LEDGER-TAX-3 | AM-SETUP-FINANCE-INSIGHTS-P08 | [BE] LedgerService: transmitEInvoices, updateTaxCode | 3 | Sanket Keluskar | LedgerService | MIG-LEDGER MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: transmitEInvoices, updateTaxCode. Spec: handoff/service-docs/backend/LedgerService.md#group-tax Helper task: Tanmay Dukhande owns the service and reviews. Done when `finance#transmitEInvoices`, `finance#updateTaxCode` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-REPORTING-CATALOGUE-1 | AM-SETUP-FINANCE-INSIGHTS-P08 | [BE] ReportingService: createReport, deleteReport, getReport, listReports | 8 | Tanmay Dukhande | ReportingService | MIG-REPORTING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createReport, deleteReport, getReport, listReports. Spec: handoff/service-docs/backend/ReportingService.md#group-catalogue. Done when `reporting#createReport`, `reporting#deleteReport`, `reporting#getReport`, `reporting#listReports` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-REPORTING-CATALOGUE-2 | AM-SETUP-FINANCE-INSIGHTS-P08 | [BE] ReportingService: updateReport | 3 | Sanket Keluskar | ReportingService | MIG-REPORTING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updateReport. Spec: handoff/service-docs/backend/ReportingService.md#group-catalogue Helper task: Tanmay Dukhande owns the service and reviews. Done when `reporting#updateReport` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | MIG-CATALOGUE-6 | AM-SETUP-FINANCE-INSIGHTS-P08-REST | [DB] Forward migration V1119__catalogue.sql: catalogue for Ticketing · Venue Management 1 of 10 (15 tables) | 8 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-CATALOGUE VM-MIG-CATALOGUE | Tables: catalogue.calculation_profile, catalogue.calculation_step, catalogue.demand_forecast, catalogue.dynamic_pricing_control, catalogue.dynamic_pricing_strategy, catalogue.fee, catalogue.fee_rule, catalogue.price_execution, catalogue.price_resolution_policy, catalogue.pricing_experiment, catalogue.pricing_recommendation, catalogue.pricing_recommendation_decision, catalogue.pricing_simulation, catalogue.rounding_profile, catalogue.tax_rule. Source DDL: backend/tenant/010-catalogue.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `catalogue.calculation_profile`, `catalogue.calculation_step`, `catalogue.demand_forecast`, `catalogue.dynamic_pricing_control`, `catalogue.dynamic_pricing_strategy`, `catalogue.fee`, `catalogue.fee_rule`, `catalogue.price_execution` and 7 more runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | MIG-CATALOGUE-13 | AM-SETUP-FINANCE-INSIGHTS-P08-REST | [DB] Forward migration V1130__catalogue.sql: catalogue for Ticketing · Venue Management 8 of 10 (3 tables) | 2 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-CATALOGUE MIG-PLATFORM VM-MIG-CATALOGUE | Tables: catalogue.event_type, catalogue.pricing_test_case, catalogue.space. Source DDL: backend/tenant/010-catalogue.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `catalogue.event_type`, `catalogue.pricing_test_case`, `catalogue.space` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-LEDGER-VARIANCE-1 | AM-SETUP-FINANCE-INSIGHTS-P08-REST | [BE] LedgerService: listPriceVariances, reviewPriceVariance | 3 | Deep Khanvilkar | LedgerService | MIG-LEDGER PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listPriceVariances, reviewPriceVariance. Spec: contracts (finance) at the release tag, served by ADAM. Built for Finance & Insights · Venue Management (setup, the rest of the screens); additive to LedgerService, whose first-release owner (Tanmay Dukhande) reviews. Done when `finance#listPriceVariances`, `finance#reviewPriceVariance` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-DRAFTED-56 | AM-SETUP-FINANCE-INSIGHTS-P08-REST | [BE] CatalogueService: listCalculationValidationReconciliation, setTaxProfileJurisdiction | 3 | Deep Khanvilkar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-13 MIG-CATALOGUE-3 MIG-CATALOGUE-5 MIG-CATALOGUE-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listCalculationValidationReconciliation, setTaxProfileJurisdiction. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Finance & Insights · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listCalculationValidationReconciliation`, `catalogue#setTaxProfileJurisdiction` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-LEDGER-ACCOUNTS-1 | AM-SETUP-FINANCE-INSIGHTS-P08-REST | [BE] LedgerService: createAccount, createCostCenter, getAccount, listAccountMappings | 5 | New full-stack developer 1 | LedgerService | MIG-LEDGER PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-LEDGER | Operations: createAccount, createCostCenter, getAccount, listAccountMappings. Spec: contracts (finance) at the release tag, served by ADAM. Built for Finance & Insights · Venue Management (setup, the rest of the screens); additive to LedgerService, whose first-release owner (Tanmay Dukhande) reviews. Done when `finance#createAccount`, `finance#createCostCenter`, `finance#getAccount`, `finance#listAccountMappings` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-LEDGER-ACCOUNTS-2 | AM-SETUP-FINANCE-INSIGHTS-P08-REST | [BE] LedgerService: listAccounts, listCostCenters, setAccountMappings, updateAccount | 5 | Pranay Shinde | LedgerService | MIG-LEDGER PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-LEDGER | Operations: listAccounts, listCostCenters, setAccountMappings, updateAccount. Spec: contracts (finance) at the release tag, served by ADAM. Built for Finance & Insights · Venue Management (setup, the rest of the screens); additive to LedgerService, whose first-release owner (Tanmay Dukhande) reviews. Done when `finance#listAccounts`, `finance#listCostCenters`, `finance#setAccountMappings`, `finance#updateAccount` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-LEDGER-FISCAL-2 | AM-SETUP-FINANCE-INSIGHTS-P08-REST | [BE] LedgerService: listLegalEntities | 1 | Tanmay Dukhande | LedgerService | MIG-LEDGER PLATFORM-KERNEL SVC-LEDGER-FISCAL-1 | Operations: listLegalEntities. Spec: contracts (finance) at the release tag, served by ADAM. Built for Finance & Insights · Venue Management (setup, the rest of the screens); additive to LedgerService, whose first-release owner (Tanmay Dukhande) reviews. Done when `finance#listLegalEntities` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | SVC-CATALOGUE-GENERAL-2 | AM-SETUP-FINANCE-INSIGHTS-P08-REST | [BE] CatalogueService: getTaxProfileJurisdiction | 1 | Deep Khanvilkar | CatalogueService | MIG-CATALOGUE-5 PLATFORM-KERNEL SVC-CATALOGUE-DRAFTED-56 | Operations: getTaxProfileJurisdiction. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Finance & Insights · Venue Management (setup, the rest of the screens); additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#getTaxProfileJurisdiction` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-LEDGER-TAX-5 | AM-SETUP-FINANCE-INSIGHTS-P08-REST | [BE] LedgerService: createTaxExemption, listEInvoiceTransmissions, listEInvoicingProviders, listTaxCodes | 5 | Surendra | LedgerService | MIG-LEDGER MIG-LEDGER-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createTaxExemption, listEInvoiceTransmissions, listEInvoicingProviders, listTaxCodes. Spec: contracts (finance) at the release tag, served by ADAM. Built for Finance & Insights · Venue Management (setup, the rest of the screens); additive to LedgerService, whose first-release owner (Tanmay Dukhande) reviews. Done when `finance#createTaxExemption`, `finance#listEInvoiceTransmissions`, `finance#listEInvoicingProviders`, `finance#listTaxCodes` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-LEDGER-TAX-6 | AM-SETUP-FINANCE-INSIGHTS-P08-REST | [BE] LedgerService: listTaxExemptions, listTaxInvoiceTemplates, setTaxInvoiceTemplate, verifyTaxExemption | 8 | Surendra | LedgerService | MIG-LEDGER MIG-LEDGER-2 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listTaxExemptions, listTaxInvoiceTemplates, setTaxInvoiceTemplate, verifyTaxExemption. Spec: contracts (finance) at the release tag, served by ADAM. Built for Finance & Insights · Venue Management (setup, the rest of the screens); additive to LedgerService, whose first-release owner (Tanmay Dukhande) reviews. Done when `finance#listTaxExemptions`, `finance#listTaxInvoiceTemplates`, `finance#setTaxInvoiceTemplate`, `finance#verifyTaxExemption` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-REPORTING-DASHBOARD-2 | AM-SETUP-FINANCE-INSIGHTS-P16 | [BE] ReportingService: updateDashboard | 2 | Chinmay Patkar | ReportingService | MIG-REPORTING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updateDashboard. Spec: handoff/service-docs/backend/ReportingService.md#group-dashboard Helper task: Tanmay Dukhande owns the service and reviews. Done when `reporting#updateDashboard` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-REPORTING-REPORTING-2 | AM-SETUP-FINANCE-INSIGHTS-P16 | [BE] ReportingService: setSemanticModel | 2 | Chinmay Patkar | ReportingService | MIG-REPORTING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setSemanticModel. Spec: handoff/service-docs/backend/ReportingService.md#group-reporting Helper task: Tanmay Dukhande owns the service and reviews. Done when `reporting#setSemanticModel` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-VENUEOPS-FAVOURITE-1 | AM-TRANSPORT-P01 | [BE] VenueOpsService: deleteFavouriteRoute, listMyFavouriteRoutes, saveFavouriteRoute | 3 | Sanket Keluskar | VenueOpsService | MIG-TRANSPORT PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: deleteFavouriteRoute, listMyFavouriteRoutes, saveFavouriteRoute. Spec: handoff/service-docs/backend/VenueOpsService.md#group-favourite Helper task: Hrushikant Patkar owns the service and reviews. Done when `transport#deleteFavouriteRoute`, `transport#listMyFavouriteRoutes`, `transport#saveFavouriteRoute` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 1 | SVC-VENUEOPS-GENERAL-1 | AM-TRANSPORT-P02 | [BE] VenueOpsService: getTransportDeparture | 1 | Chinmay Patkar | VenueOpsService | MIG-CATALOGUE MIG-TRANSPORT PLATFORM-KERNEL SVC-CATALOGUE-LEASE-1 SVC-ORDER-PAYMENT-1 SVC-ORDER-SYNC-1 SVC-VENUEOPS-DEPARTURE-1 SVC-VENUEOPS-FARE-1 SVC-VENUEOPS-NETWORKIMPORT-1 SVC-VENUEOPS-ROUTE-1 SVC-VENUEOPS-ROUTE-2 SVC-VENUEOPS-STATION-1 SVC-VENUEOPS-TIMETABLE-1 | Operations: getTransportDeparture. Spec: handoff/service-docs/backend/VenueOpsService.md#group-general Helper task: Hrushikant Patkar owns the service and reviews. Done when `transport#getTransportDeparture` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-FNB-1 | AM-FOOD-BEVERAGE-P01 | [BE] FnbService: attachModifierGroup, buildProductionPlan, chaseStation, createTableReservation | 8 | Tanmay Dukhande | FnbService | MIG-AI MIG-FNB PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: attachModifierGroup, buildProductionPlan, chaseStation, createTableReservation. Spec: handoff/service-docs/backend/FnbService.md#group-fnb. Done when `fnb#attachModifierGroup`, `fnb#buildProductionPlan`, `fnb#chaseStation`, `fnb#createTableReservation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-FNB-3 | AM-FOOD-BEVERAGE-P01 | [BE] FnbService: getHaccpStatus, getKitchenSla, holdCourse, joinRestaurantWaitlist | 8 | Tanmay Dukhande | FnbService | MIG-FNB MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getHaccpStatus, getKitchenSla, holdCourse, joinRestaurantWaitlist. Spec: handoff/service-docs/backend/FnbService.md#group-fnb. Done when `fnb#getHaccpStatus`, `fnb#getKitchenSla`, `fnb#holdCourse`, `fnb#joinRestaurantWaitlist` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 1 | SVC-ORDER-CASH-1 | AM-FOOD-BEVERAGE-P04 | [BE] OrderService: createCashMovement, listCashMovements | 5 | Deep Khanvilkar | OrderService | MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createCashMovement, listCashMovements. Spec: handoff/service-docs/backend/OrderService.md#group-cash Helper task: Pranay Shinde owns the service and reviews. Done when `shift#createCashMovement`, `shift#listCashMovements` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 1 | SVC-ORDER-SHIFT-3 | AM-FOOD-BEVERAGE-P04 | [BE] OrderService: giveShiftVarianceReason, listDenominations, listDepositBoxes, listShifts | 8 | Pranay Shinde | OrderService | MIG-IDENTITY MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: giveShiftVarianceReason, listDenominations, listDepositBoxes, listShifts. Spec: handoff/service-docs/backend/OrderService.md#group-shift. Done when `shift#giveShiftVarianceReason`, `shift#listDenominations`, `shift#listDepositBoxes`, `shift#listShifts` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 1 | SVC-ORDER-SHIFT-5 | AM-FOOD-BEVERAGE-P04 | [BE] OrderService: resumeShift, setDenominations, setTillShiftPolicy, submitShiftCount | 8 | Pranay Shinde | OrderService | MIG-LEDGER MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: resumeShift, setDenominations, setTillShiftPolicy, submitShiftCount. Spec: handoff/service-docs/backend/OrderService.md#group-shift. Done when `shift#resumeShift`, `shift#setDenominations`, `shift#setTillShiftPolicy`, `shift#submitShiftCount` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 1 | SVC-ORDER-SHIFT-6 | AM-FOOD-BEVERAGE-P04 | [BE] OrderService: suspendShift, withdrawFromDepositBox | 8 | Deep Khanvilkar | OrderService | MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: suspendShift, withdrawFromDepositBox. Spec: handoff/service-docs/backend/OrderService.md#group-shift. Done when `shift#suspendShift`, `shift#withdrawFromDepositBox` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-ORDER-SHIFT-2 | AM-FOOD-BEVERAGE-P04 | [BE] OrderService: getCurrentShift, getShiftCountLines, getTillShiftPolicy, getWorkstationShift | 8 | Deep Khanvilkar | OrderService | MIG-ORDERS PLATFORM-KERNEL SVC-ORDER-CASH-1 SVC-ORDER-SHIFT-1 SVC-ORDER-SHIFT-3 SVC-ORDER-SHIFT-4 SVC-ORDER-SHIFT-5 SVC-ORDER-SHIFT-6 | Operations: getCurrentShift, getShiftCountLines, getTillShiftPolicy, getWorkstationShift. Spec: handoff/service-docs/backend/OrderService.md#group-shift. Done when `shift#getCurrentShift`, `shift#getShiftCountLines`, `shift#getTillShiftPolicy`, `shift#getWorkstationShift` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-BILL-1 | AM-FOOD-BEVERAGE-P04 | [BE] FnbService: closeTableVisit, getBill, splitBill | 8 | Tanmay Dukhande | FnbService | MIG-FNB MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: closeTableVisit, getBill, splitBill. Spec: handoff/service-docs/backend/FnbService.md#group-bill. Done when `fnb#closeTableVisit`, `fnb#getBill`, `fnb#splitBill` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-FNB-2 | AM-FOOD-BEVERAGE-P04 | [BE] FnbService: createTableReservationForGuest, escalateCorrectiveAction, fireCourse, getCourseRules | 8 | Tanmay Dukhande | FnbService | MIG-FNB MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createTableReservationForGuest, escalateCorrectiveAction, fireCourse, getCourseRules. Spec: handoff/service-docs/backend/FnbService.md#group-fnb. Done when `fnb#createTableReservationForGuest`, `fnb#escalateCorrectiveAction`, `fnb#fireCourse`, `fnb#getCourseRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-FNB-5 | AM-FOOD-BEVERAGE-P04 | [BE] FnbService: listTableReservations, logColdChain, logKitchenException, logTemperature | 8 | Tanmay Dukhande | FnbService | MIG-FNB MIG-INVENTORY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listTableReservations, logColdChain, logKitchenException, logTemperature. Spec: handoff/service-docs/backend/FnbService.md#group-fnb. Done when `fnb#listTableReservations`, `fnb#logColdChain`, `fnb#logKitchenException`, `fnb#logTemperature` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-FNB-6 | AM-FOOD-BEVERAGE-P04 | [BE] FnbService: markOrderCollected, notifyServer, printOrderLabel, publishMenu | 8 | Tanmay Dukhande | FnbService | MIG-FNB MIG-IDENTITY MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: markOrderCollected, notifyServer, printOrderLabel, publishMenu. Spec: handoff/service-docs/backend/FnbService.md#group-fnb. Done when `fnb#markOrderCollected`, `fnb#notifyServer`, `fnb#printOrderLabel`, `fnb#publishMenu` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-FNB-8 | AM-FOOD-BEVERAGE-P04 | [BE] FnbService: requestBill, rollbackMenu, scheduleMenuPublish, seatTableReservation | 8 | Tanmay Dukhande | FnbService | MIG-FNB PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: requestBill, rollbackMenu, scheduleMenuPublish, seatTableReservation. Spec: handoff/service-docs/backend/FnbService.md#group-fnb. Done when `fnb#requestBill`, `fnb#rollbackMenu`, `fnb#scheduleMenuPublish`, `fnb#seatTableReservation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-MENU-1 | AM-FOOD-BEVERAGE-P04 | [BE] FnbService: createMenu, setItemAvailability, setMenuSections, updateMenu | 8 | Tanmay Dukhande | FnbService | MIG-FNB PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createMenu, setItemAvailability, setMenuSections, updateMenu. Spec: handoff/service-docs/backend/FnbService.md#group-menu. Done when `fnb#createMenu`, `fnb#setItemAvailability`, `fnb#setMenuSections`, `fnb#updateMenu` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-FNB-7 | AM-FOOD-BEVERAGE-P15 | [BE] FnbService: rebalanceStationLoad, recallKitchenTicket, refireItem, releaseProductionPlan | 8 | Tanmay Dukhande | FnbService | MIG-FNB MIG-INVENTORY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: rebalanceStationLoad, recallKitchenTicket, refireItem, releaseProductionPlan. Spec: handoff/service-docs/backend/FnbService.md#group-fnb. Done when `fnb#rebalanceStationLoad`, `fnb#recallKitchenTicket`, `fnb#refireItem`, `fnb#releaseProductionPlan` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 1 | SVC-FNB-GUESTORDERING-2 | AM-ORDERS-RESERVATIONS-P02 | [BE] FnbService: getGuestBill, getGuestMenu, getGuestOrderStatus, listBookableOutlets | 5 | Deep Khanvilkar | FnbService | MIG-FNB MIG-ORDERS PLATFORM-KERNEL SVC-FNB-BILL-1 SVC-FNB-FNB-2 SVC-FNB-FNB-3 SVC-FNB-FNB-6 SVC-FNB-FNB-7 SVC-FNB-FNB-8 SVC-FNB-GUESTORDERING-1 SVC-FNB-GUESTORDERING-3 SVC-FNB-GUESTORDERING-4 SVC-FNB-KITCHEN-1 SVC-FNB-MODIFIER-1 SVC-FNB-ORDER-1 SVC-FNB-SERVICE-1 SVC-FNB-TABLE-1 SVC-FNB-TABLE-2 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-3 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-WALLET-RETAIL-1 | Operations: getGuestBill, getGuestMenu, getGuestOrderStatus, listBookableOutlets. Spec: handoff/service-docs/backend/FnbService.md#group-guestordering. Done when `fnb#getGuestBill`, `fnb#getGuestMenu`, `fnb#getGuestOrderStatus`, `fnb#listBookableOutlets` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 2 | VM-INVENTORY-MOVEMENT-1 | AM-FOOD-BEVERAGE-P06-BLOCK-A | [BE] InventoryService: createStockMovement, listStockMovements | 3 | Sanket Keluskar | InventoryService | MIG-INVENTORY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: createStockMovement, listStockMovements. Additive to InventoryService; its first-release owner (Pranay Shinde) reviews. Helper task: Pranay Shinde owns the service and reviews. Done when `inventory#createStockMovement`, `inventory#listStockMovements` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 2 | VM-FNB-PRODUCTION-1 | AM-FOOD-BEVERAGE-P06-BLOCK-A | [BE] FnbService: getWasteApprovalPolicy, listRecipes, recordWaste, setWasteApprovalPolicy | 5 | Tanmay Dukhande | FnbService | MIG-FNB MIG-INVENTORY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-FNB | Operations beyond the first release: getWasteApprovalPolicy, listRecipes, recordWaste, setWasteApprovalPolicy. Additive to FnbService; its first-release owner (Tanmay Dukhande) reviews. Done when `fnb#getWasteApprovalPolicy`, `fnb#listRecipes`, `fnb#recordWaste`, `fnb#setWasteApprovalPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-FNB-FNB-12 | AM-FOOD-BEVERAGE-P06-BLOCK-A | [BE] FnbService: compItem, listCorrectiveActions, moveTableVisit, quoteWaitTime | 8 | Tanmay Dukhande | FnbService | MIG-FNB MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: compItem, listCorrectiveActions, moveTableVisit, quoteWaitTime. Spec: contracts (fnb) at the release tag, served by ADAM. Built for Food & Beverage · Staff App (Block A); additive to FnbService, whose first-release owner (Tanmay Dukhande) reviews. Done when `fnb#compItem`, `fnb#listCorrectiveActions`, `fnb#moveTableVisit`, `fnb#quoteWaitTime` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 2 | VM-ORDER-DRAFTED-1 | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [BE] OrderService: listPaymentReconciliationException, listTicketReissueFulfillment | 2 | Chinmay Patkar | OrderService | MIG-ACCESS MIG-ORDERS PLATFORM-KERNEL SVC-ACCESS-ACCESS-2 SVC-ACCESS-VALIDATION-2 SVC-FNB-FNB-12 SVC-IDENTITY-GUESTAUTH-2 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-13 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-2 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-WALLET-RETAIL-1 VM-ACCESS-ACCESS-1 VM-LEDGER-SETTLEMENT-1 VM-LEDGER-SETTLEMENT-2 VM-MIG-LEDGER VM-MIG-ORDERS | Operations beyond the first release: listPaymentReconciliationException, listTicketReissueFulfillment. Additive to OrderService; its first-release owner (Pranay Shinde) reviews. Helper task: Pranay Shinde owns the service and reviews. Done when `orders#listPaymentReconciliationException`, `orders#listTicketReissueFulfillment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-FNB-FNB-13 | AM-FOOD-BEVERAGE-P06-BLOCK-A | [BE] FnbService: reassignServer, setServiceStage, transferOrderItems | 8 | Surendra | FnbService | MIG-FNB MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: reassignServer, setServiceStage, transferOrderItems. Spec: contracts (fnb) at the release tag, served by ADAM. Built for Food & Beverage · Staff App (Block A); additive to FnbService, whose first-release owner (Tanmay Dukhande) reviews. Done when `fnb#reassignServer`, `fnb#setServiceStage`, `fnb#transferOrderItems` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-FNB-TABLE-3 | AM-FOOD-BEVERAGE-P06-BLOCK-A | [BE] FnbService: mergeTableVisits | 3 | Surendra | FnbService | MIG-FNB PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: mergeTableVisits. Spec: contracts (fnb) at the release tag, served by ADAM. Built for Food & Beverage · Staff App (Block A); additive to FnbService, whose first-release owner (Tanmay Dukhande) reviews. Done when `fnb#mergeTableVisits` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | MIG-FNB-3 | AM-FOOD-BEVERAGE-P08-BLOCK-A | [DB] Forward migration V1034__fnb.sql: fnb for Food & Beverage · Staff App (1 tables) | 1 | Hrushikant Patkar | FnbService | MIG-BASELINE MIG-FNB VM-MIG-FNB | Tables: fnb.reservation_policy. Source DDL: backend/tenant/010-fnb.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `fnb.reservation_policy` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
16 | 3 | MIG-FNB-4 | AM-FOOD-BEVERAGE-P08-BLOCK-A | [DB] Forward migration V1035__fnb.sql: fnb for Food & Beverage · Venue Management (Block A) (3 tables) | 2 | Hrushikant Patkar | FnbService | MIG-BASELINE MIG-FNB VM-MIG-FNB | Tables: fnb.ingredient_substitute, fnb.prep_sheet_template, fnb.product_recommendation. Source DDL: backend/tenant/010-fnb.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `fnb.ingredient_substitute`, `fnb.prep_sheet_template`, `fnb.product_recommendation` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 2 | VM-TENANCY-WORKSTATION-1 | AM-FOOD-BEVERAGE-P08-BLOCK-A | [BE] TenancyService: getWorkstation, listOutlets, listWorkstations, registerDevice | 8 | Pranay Shinde | TenancyService | MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: getWorkstation, listOutlets, listWorkstations, registerDevice. Additive to TenancyService; its first-release owner (Hrushikant Patkar) reviews. Done when `tenancy#getWorkstation`, `tenancy#listOutlets`, `tenancy#listWorkstations`, `tenancy#registerDevice` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | SVC-ORDER-SHIFT-7 | AM-FOOD-BEVERAGE-P08-BLOCK-A | [BE] OrderService: adjustDepositBoxFloat, approveShiftClose | 5 | Tanmay Dukhande | OrderService | MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: adjustDepositBoxFloat, approveShiftClose. Spec: contracts (shift) at the release tag, served by ADAM. Built for Food & Beverage · Venue Management (Block A); additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `shift#adjustDepositBoxFloat`, `shift#approveShiftClose` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-LEDGER-REPORTING-2 | AM-FINANCE-TAX-P08-BLOCK-A | [BE] LedgerService: getForeignTenderReport | 1 | Deep Khanvilkar | LedgerService | MIG-LEDGER MIG-ORDERS PLATFORM-KERNEL SVC-LEDGER-FINANCE-1 SVC-LEDGER-LEDGER-1 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-3 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SHIFT-1 SVC-ORDER-SHIFT-3 SVC-ORDER-SHIFT-4 SVC-ORDER-SHIFT-5 SVC-ORDER-SHIFT-6 SVC-ORDER-SHIFT-7 SVC-ORDER-SYNC-1 SVC-WALLET-RETAIL-1 | Operations: getForeignTenderReport. Spec: contracts (finance) at the release tag, served by ADAM. Built for Finance & Tax · Venue Management (Block A); additive to LedgerService, whose first-release owner (Tanmay Dukhande) reviews. Done when `finance#getForeignTenderReport` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 2 | VM-FNB-ORDER-1 | AM-FOOD-BEVERAGE-P08-BLOCK-A | [BE] FnbService: amendFnbOrder | 3 | Chinmay Patkar | FnbService | MIG-FNB PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: amendFnbOrder. Additive to FnbService; its first-release owner (Tanmay Dukhande) reviews. Helper task: Tanmay Dukhande owns the service and reviews. Done when `fnb#amendFnbOrder` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-FNB-FNB-16 | AM-FOOD-BEVERAGE-P08-BLOCK-A | [BE] FnbService: applyMenuActions, closeCorrectiveAction, createTable, getAllergenVerification | 5 | Tanmay Dukhande | FnbService | MIG-CATALOGUE MIG-FNB MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: applyMenuActions, closeCorrectiveAction, createTable, getAllergenVerification. Spec: contracts (fnb) at the release tag, served by ADAM. Built for Food & Beverage · Venue Management (Block A); additive to FnbService, whose first-release owner (Tanmay Dukhande) reviews. Done when `fnb#applyMenuActions`, `fnb#closeCorrectiveAction`, `fnb#createTable`, `fnb#getAllergenVerification` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-FNB-GENERAL-2 | AM-FOOD-BEVERAGE-P08-BLOCK-A | [BE] FnbService: listSubstitutionRules | 1 | Tanmay Dukhande | FnbService | MIG-FNB PLATFORM-KERNEL SVC-FNB-FNB-9 | Operations: listSubstitutionRules. Spec: contracts (fnb) at the release tag, served by ADAM. Built for Food & Beverage · Venue Management (Block A); additive to FnbService, whose first-release owner (Tanmay Dukhande) reviews. Done when `fnb#listSubstitutionRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-FNB-MODIFIER-2 | AM-FOOD-BEVERAGE-P08-BLOCK-A | [BE] FnbService: listModifierGroups | 1 | Deep Khanvilkar | FnbService | MIG-FNB PLATFORM-KERNEL SVC-FNB-MODIFIER-1 | Operations: listModifierGroups. Spec: contracts (fnb) at the release tag, served by ADAM. Built for Food & Beverage · Venue Management (Block A); additive to FnbService, whose first-release owner (Tanmay Dukhande) reviews. Done when `fnb#listModifierGroups` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-FNB-FNB-17 | AM-FOOD-BEVERAGE-P08-BLOCK-A | [BE] FnbService: listFnbRecommendations, listIngredientSubstitutes, recordCorrectiveAction, sendOrderNotification | 5 | Pranay Shinde | FnbService | MIG-FNB MIG-FNB-4 MIG-IDENTITY MIG-MARKETING MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listFnbRecommendations, listIngredientSubstitutes, recordCorrectiveAction, sendOrderNotification. Spec: contracts (fnb) at the release tag, served by ADAM. Built for Food & Beverage · Venue Management (Block A); additive to FnbService, whose first-release owner (Tanmay Dukhande) reviews. Done when `fnb#listFnbRecommendations`, `fnb#listIngredientSubstitutes`, `fnb#recordCorrectiveAction`, `fnb#sendOrderNotification` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-FNB-FNB-18 | AM-FOOD-BEVERAGE-P08-BLOCK-A | [BE] FnbService: setFnbReservationPolicy, setIngredientSubstitutes, updateTable, verifyAllergens | 5 | Surendra | FnbService | MIG-FNB MIG-FNB-3 MIG-FNB-4 MIG-INVENTORY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setFnbReservationPolicy, setIngredientSubstitutes, updateTable, verifyAllergens. Spec: contracts (fnb) at the release tag, served by ADAM. Built for Food & Beverage · Venue Management (Block A); additive to FnbService, whose first-release owner (Tanmay Dukhande) reviews. Done when `fnb#setFnbReservationPolicy`, `fnb#setIngredientSubstitutes`, `fnb#updateTable`, `fnb#verifyAllergens` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-FNB-PRODUCTION-2 | AM-FOOD-BEVERAGE-P08-BLOCK-A | [BE] FnbService: getPrepSheetTemplate, setPrepSheetTemplate | 2 | Sanket Keluskar | FnbService | MIG-FNB-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getPrepSheetTemplate, setPrepSheetTemplate. Spec: contracts (fnb) at the release tag, served by ADAM. Built for Food & Beverage · Venue Management (Block A); additive to FnbService, whose first-release owner (Tanmay Dukhande) reviews. Done when `fnb#getPrepSheetTemplate`, `fnb#setPrepSheetTemplate` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 1 | SVC-INVENTORY-ITEM-1 | AM-RETAIL-P04 | [BE] InventoryService: createInventoryItem, setInventoryKitDefinition, updateInventoryItem | 5 | Deep Khanvilkar | InventoryService | MIG-INVENTORY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createInventoryItem, setInventoryKitDefinition, updateInventoryItem. Spec: handoff/service-docs/backend/InventoryService.md#group-item Helper task: Pranay Shinde owns the service and reviews. Done when `inventory#createInventoryItem`, `inventory#setInventoryKitDefinition`, `inventory#updateInventoryItem` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 1 | SVC-INVENTORY-INVENTORY-1 | AM-RETAIL-P04 | [BE] InventoryService: listSerialisedItems | 2 | Sanket Keluskar | InventoryService | MIG-INVENTORY PLATFORM-KERNEL SVC-INVENTORY-ITEM-1 | Operations: listSerialisedItems. Spec: handoff/service-docs/backend/InventoryService.md#group-inventory Helper task: Pranay Shinde owns the service and reviews. Done when `inventory#listSerialisedItems` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
4 | 2 | VM-MIG-RENTAL | AM-RESOURCES-CAPACITY-P08-BLOCK-A | [DB] Forward migration V1014__rental.sql: rental for Venue Management (2 tables) | 2 | Hrushikant Patkar |  | MIG-BASELINE | Tables: rental.booking, rental.participant. Source DDL: backend/tenant/010-rental.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `rental.booking`, `rental.participant` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 2 | VM-VENUEOPS-RESOURCES-2 | AM-RESOURCES-CAPACITY-P08-BLOCK-A | [BE] VenueOpsService: getResourceBooking, getResourceQualifications, listResources, reorderPerformanceManifest | 3 | Deep Khanvilkar | VenueOpsService | MIG-RESOURCES PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-RESOURCES | Operations beyond the first release: getResourceBooking, getResourceQualifications, listResources, reorderPerformanceManifest. Additive to VenueOpsService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `resources#getResourceBooking`, `resources#getResourceQualifications`, `resources#listResources`, `resources#reorderPerformanceManifest` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 2 | VM-VENUEOPS-RESOURCES-1 | AM-RESOURCES-CAPACITY-P08-BLOCK-A | [BE] VenueOpsService: bookResource, checkInResource, checkOutResource, getPerformanceManifest | 8 | Tanmay Dukhande | VenueOpsService | MIG-MARKETING MIG-ORDERS MIG-PII MIG-RESOURCES PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-RESOURCES | Operations beyond the first release: bookResource, checkInResource, checkOutResource, getPerformanceManifest. Additive to VenueOpsService; its first-release owner (Hrushikant Patkar) reviews. Done when `resources#bookResource`, `resources#checkInResource`, `resources#checkOutResource`, `resources#getPerformanceManifest` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-VENUEOPS-RESOURCES-6 | AM-SETUP-VENUE-OPERATIONS-P08-REST | [BE] VenueOpsService: getExperienceResourceRequirements, getResource, getResourceSchedule, listResourceBlocks | 3 | Pranay Shinde | VenueOpsService | MIG-RESOURCES PLATFORM-KERNEL SVC-VENUEOPS-RESOURCES-1 SVC-VENUEOPS-RESOURCES-2 SVC-VENUEOPS-RESOURCES-3 SVC-VENUEOPS-RESOURCES-4 SVC-VENUEOPS-RESOURCES-5 VM-VENUEOPS-RESOURCES-1 | Operations: getExperienceResourceRequirements, getResource, getResourceSchedule, listResourceBlocks. Spec: contracts (resources) at the release tag, served by ADAM. Built for Venue Operations · Venue Management (setup, the rest of the screens); additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `resources#getExperienceResourceRequirements`, `resources#getResource`, `resources#getResourceSchedule`, `resources#listResourceBlocks` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-VENUEOPS-RESOURCES-7 | AM-SETUP-VENUE-OPERATIONS-P08-REST | [BE] VenueOpsService: listResourcePackages, suggestResources | 1 | Deep Khanvilkar | VenueOpsService | MIG-RESOURCES MIG-RESOURCES-2 PLATFORM-KERNEL SVC-VENUEOPS-RESOURCES-1 SVC-VENUEOPS-RESOURCES-2 SVC-VENUEOPS-RESOURCES-3 SVC-VENUEOPS-RESOURCES-4 SVC-VENUEOPS-RESOURCES-5 VM-VENUEOPS-RESOURCES-1 | Operations: listResourcePackages, suggestResources. Spec: contracts (resources) at the release tag, served by ADAM. Built for Venue Operations · Venue Management (setup, the rest of the screens); additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `resources#listResourcePackages`, `resources#suggestResources` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 2 | VM-VENUEOPS-RENTAL-1 | AM-RESOURCES-CAPACITY-P08-BLOCK-A | [BE] VenueOpsService: getRentalBooking | 2 | Chinmay Patkar | VenueOpsService | PLATFORM-KERNEL VM-MIG-RENTAL | Operations beyond the first release: getRentalBooking. Additive to VenueOpsService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `rental#getRentalBooking` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-TENANCY-ATTENDANCE-1 | AM-WORKFORCE-P04 | [BE] TenancyService: recordAttendance | 2 | Chinmay Patkar | TenancyService | MIG-ACCESS MIG-WORKFORCE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: recordAttendance. Spec: handoff/service-docs/backend/TenancyService.md#group-attendance Helper task: Hrushikant Patkar owns the service and reviews. Done when `workforce#recordAttendance` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 3 | MIG-MAINTENANCE-4 | AM-MAINTENANCE-SAFETY-P06-BLOCK-A | [DB] Forward migration V1165__maintenance.sql: maintenance for Maintenance & Safety · Staff App (Block A) (2 tables) | 1 | Hrushikant Patkar | VenueOpsService | MIG-ASSETS MIG-BASELINE MIG-MAINTENANCE VM-MIG-MAINTENANCE | Tables: maintenance.incident_media, maintenance.work_order_attachment. Source DDL: backend/tenant/010-maintenance.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `maintenance.incident_media`, `maintenance.work_order_attachment` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 2 | VM-VENUEOPS-INCIDENT-1 | AM-MAINTENANCE-SAFETY-P06-BLOCK-A | [BE] VenueOpsService: getIncident, listIncidents, recordAuthorityNotification, reportIncident | 8 | Tanmay Dukhande | VenueOpsService | MIG-MAINTENANCE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-MAINTENANCE | Operations beyond the first release: getIncident, listIncidents, recordAuthorityNotification, reportIncident. Additive to VenueOpsService; its first-release owner (Hrushikant Patkar) reviews. Done when `maintenance#getIncident`, `maintenance#listIncidents`, `maintenance#recordAuthorityNotification`, `maintenance#reportIncident` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-VENUEOPS-INCIDENT-2 | AM-MAINTENANCE-SAFETY-P06-BLOCK-A | [BE] VenueOpsService: updateIncident | 2 | Chinmay Patkar | VenueOpsService | MIG-MAINTENANCE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-MAINTENANCE | Operations beyond the first release: updateIncident. Additive to VenueOpsService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `maintenance#updateIncident` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-VENUEOPS-WORKORDER-2 | AM-MAINTENANCE-SAFETY-P06-BLOCK-A | [BE] VenueOpsService: listVendorServiceRequests, listWorkOrders, suggestWorkOrderAssignee, updateVendorServiceRequest | 8 | Tanmay Dukhande | VenueOpsService | MIG-MAINTENANCE MIG-RESOURCES PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-MAINTENANCE VM-MIG-RESOURCES VM-MIG-WORKFORCE | Operations beyond the first release: listVendorServiceRequests, listWorkOrders, suggestWorkOrderAssignee, updateVendorServiceRequest. Additive to VenueOpsService; its first-release owner (Hrushikant Patkar) reviews. Done when `maintenance#listVendorServiceRequests`, `maintenance#listWorkOrders`, `maintenance#suggestWorkOrderAssignee`, `maintenance#updateVendorServiceRequest` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 2 | VM-VENUEOPS-MAINTENANCE-1 | AM-MAINTENANCE-SAFETY-P06-BLOCK-A | [BE] VenueOpsService: closeWorkOrder, pauseWorkOrder, rejectWorkOrder | 8 | Tanmay Dukhande | VenueOpsService | MIG-INVENTORY MIG-MAINTENANCE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: closeWorkOrder, pauseWorkOrder, rejectWorkOrder. Additive to VenueOpsService; its first-release owner (Hrushikant Patkar) reviews. Done when `maintenance#closeWorkOrder`, `maintenance#pauseWorkOrder`, `maintenance#rejectWorkOrder` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 2 | VM-VENUEOPS-WORKORDER-1 | AM-MAINTENANCE-SAFETY-P06-BLOCK-A | [BE] VenueOpsService: completeWorkOrder, createVendorServiceRequest, createWorkOrder, getWorkOrder | 8 | Tanmay Dukhande | VenueOpsService | MIG-INVENTORY MIG-MAINTENANCE MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-MAINTENANCE | Operations beyond the first release: completeWorkOrder, createVendorServiceRequest, createWorkOrder, getWorkOrder. Additive to VenueOpsService; its first-release owner (Hrushikant Patkar) reviews. Done when `maintenance#completeWorkOrder`, `maintenance#createVendorServiceRequest`, `maintenance#createWorkOrder`, `maintenance#getWorkOrder` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-INCIDENT-3 | AM-MAINTENANCE-SAFETY-P06-BLOCK-A | [BE] VenueOpsService: addIncidentPerson, uploadIncidentMedia | 3 | Deep Khanvilkar | VenueOpsService | MIG-MAINTENANCE-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-MAINTENANCE | Operations: addIncidentPerson, uploadIncidentMedia. Spec: contracts (maintenance) at the release tag, served by ADAM. Built for Maintenance & Safety · Staff App (Block A); additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `maintenance#addIncidentPerson`, `maintenance#uploadIncidentMedia` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-MAINTENANCE-2 | AM-MAINTENANCE-SAFETY-P06-BLOCK-A | [BE] VenueOpsService: acceptWorkOrder, attachWorkOrderEvidence, resumeWorkOrder, startWorkOrder | 8 | Tanmay Dukhande | VenueOpsService | MIG-ASSETS MIG-MAINTENANCE MIG-MAINTENANCE-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: acceptWorkOrder, attachWorkOrderEvidence, resumeWorkOrder, startWorkOrder. Spec: contracts (maintenance) at the release tag, served by ADAM. Built for Maintenance & Safety · Staff App (Block A); additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `maintenance#acceptWorkOrder`, `maintenance#attachWorkOrderEvidence`, `maintenance#resumeWorkOrder`, `maintenance#startWorkOrder` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-INVENTORY-INVENTORY-3 | AM-MAINTENANCE-SAFETY-P06-BLOCK-A | [BE] InventoryService: createStockReservation, listStockReservations, releaseStockReservation | 3 | Sanket Keluskar | InventoryService | MIG-INVENTORY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createStockReservation, listStockReservations, releaseStockReservation. Spec: contracts (inventory) at the release tag, served by ADAM. Built for Maintenance & Safety · Staff App (Block A); additive to InventoryService, whose first-release owner (Pranay Shinde) reviews. Done when `inventory#createStockReservation`, `inventory#listStockReservations`, `inventory#releaseStockReservation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-VENUEOPS-WORKORDER-4 | AM-MAINTENANCE-SAFETY-P06-BLOCK-A | [BE] VenueOpsService: recordWorkOrderParts, recordWorkOrderTime | 5 | Pranay Shinde | VenueOpsService | MIG-INVENTORY MIG-MAINTENANCE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: recordWorkOrderParts, recordWorkOrderTime. Spec: contracts (maintenance) at the release tag, served by ADAM. Built for Maintenance & Safety · Staff App (Block A); additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `maintenance#recordWorkOrderParts`, `maintenance#recordWorkOrderTime` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-VENUEOPS-ASSET-1 | AM-MAINTENANCE-SAFETY-P08-BLOCK-A | [BE] VenueOpsService: createAsset, getAsset, getAssetHistory, listAssets | 8 | Tanmay Dukhande | VenueOpsService | MIG-MAINTENANCE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-MAINTENANCE | Operations beyond the first release: createAsset, getAsset, getAssetHistory, listAssets. Additive to VenueOpsService; its first-release owner (Hrushikant Patkar) reviews. Done when `maintenance#createAsset`, `maintenance#getAsset`, `maintenance#getAssetHistory`, `maintenance#listAssets` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-VENUEOPS-ASSET-2 | AM-MAINTENANCE-SAFETY-P08-BLOCK-A | [BE] VenueOpsService: lookupAsset, setAssetStatus, updateAsset | 8 | Tanmay Dukhande | VenueOpsService | MIG-MAINTENANCE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-MAINTENANCE | Operations beyond the first release: lookupAsset, setAssetStatus, updateAsset. Additive to VenueOpsService; its first-release owner (Hrushikant Patkar) reviews. Done when `maintenance#lookupAsset`, `maintenance#setAssetStatus`, `maintenance#updateAsset` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-VENUEOPS-WORKORDER-3 | AM-MAINTENANCE-SAFETY-P08-BLOCK-A | [BE] VenueOpsService: updateWorkOrder, verifyWorkOrder | 5 | Deep Khanvilkar | VenueOpsService | MIG-MAINTENANCE MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations beyond the first release: updateWorkOrder, verifyWorkOrder. Additive to VenueOpsService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `maintenance#updateWorkOrder`, `maintenance#verifyWorkOrder` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
6 | 2 | VM-MIG-GAMES | AM-GAMES-RIDES-P08-BLOCK-A | [DB] Forward migration V1039__games.sql: games for Venue Management (5 tables) | 3 | Hrushikant Patkar |  | MIG-GAMES | Tables: games.game, games.operational_config, games.play, games.pricing, games.reader_profile. Source DDL: backend/tenant/010-games.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `games.game`, `games.operational_config`, `games.play`, `games.pricing`, `games.reader_profile` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
7 | 3 | MIG-GAMES-2 | AM-GAMES-RIDES-P08-BLOCK-A | [DB] Forward migration V1040__games.sql: games for Games & Rides · Venue Management (Block A) (3 tables) | 2 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE MIG-GAMES VM-MIG-GAMES | Tables: games.authorisation, games.reader, games.reader_sync_status. Source DDL: backend/tenant/010-games.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `games.authorisation`, `games.reader`, `games.reader_sync_status` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 2 | VM-VENUEOPS-GAME-1 | AM-GAMES-RIDES-P08-BLOCK-A | [BE] VenueOpsService: cloneGame, createGame, listGames, updateGame | 8 | Pranay Shinde | VenueOpsService | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-GAMES | Operations beyond the first release: cloneGame, createGame, listGames, updateGame. Additive to VenueOpsService; its first-release owner (Hrushikant Patkar) reviews. Done when `games#cloneGame`, `games#createGame`, `games#listGames`, `games#updateGame` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-CARD-2 | AM-GAMES-RIDES-P08-BLOCK-A | [BE] VenueOpsService: transferGameCard | 1 | Deep Khanvilkar | VenueOpsService | MIG-GAMES PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: transferGameCard. Spec: contracts (games) at the release tag, served by ADAM. Built for Games & Rides · Venue Management (Block A); additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `games#transferGameCard` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-GAMES-1 | AM-GAMES-RIDES-P08-BLOCK-A | [BE] VenueOpsService: authoriseGameplay, reportReaderQueue | 3 | Pranay Shinde | VenueOpsService | MIG-GAMES-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: authoriseGameplay, reportReaderQueue. Spec: contracts (games) at the release tag, served by ADAM. Built for Games & Rides · Venue Management (Block A); additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `games#authoriseGameplay`, `games#reportReaderQueue` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-PLAY-1 | AM-GAMES-RIDES-P08-BLOCK-A | [BE] VenueOpsService: recordGamePlay, syncGamePlays | 5 | Pranay Shinde | VenueOpsService | MIG-GAMES MIG-GAMES-2 MIG-SYNC PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-GAMES | Operations: recordGamePlay, syncGamePlays. Spec: contracts (games) at the release tag, served by ADAM. Built for Games & Rides · Venue Management (Block A); additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `games#recordGamePlay`, `games#syncGamePlays` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-VENUEOPS-ENTRY-1 | AM-VIRTUAL-QUEUE-P01 | [BE] VenueOpsService: getWaitingGuest, joinQueue, leaveQueue | 5 | Tanmay Dukhande | VenueOpsService | MIG-MARKETING MIG-PROMOTIONS MIG-QUEUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getWaitingGuest, joinQueue, leaveQueue. Spec: handoff/service-docs/backend/VenueOpsService.md#group-entry. Done when `queue#getWaitingGuest`, `queue#joinQueue`, `queue#leaveQueue` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 1 | SVC-VENUEOPS-WAITTIME-1 | AM-WHITE-LABEL-P02 | [BE] VenueOpsService: getWaitTimes | 1 | Chinmay Patkar | VenueOpsService | MIG-QUEUE PLATFORM-KERNEL SVC-VENUEOPS-ENTRY-1 SVC-VENUEOPS-QUEUE-1 | Operations: getWaitTimes. Spec: handoff/service-docs/backend/VenueOpsService.md#group-waittime Helper task: Hrushikant Patkar owns the service and reviews. Done when `queue#getWaitTimes` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 2 | VM-VENUEOPS-QUEUE-1 | AM-VIRTUAL-QUEUE-P06-BLOCK-A | [BE] VenueOpsService: getQueue, setQueueStatus | 5 | Tanmay Dukhande | VenueOpsService | MIG-QUEUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: getQueue, setQueueStatus. Additive to VenueOpsService; its first-release owner (Hrushikant Patkar) reviews. Done when `queue#getQueue`, `queue#setQueueStatus` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 2 | VM-VENUEOPS-WAITTIME-1 | AM-VIRTUAL-QUEUE-P06-BLOCK-A | [BE] VenueOpsService: setWaitTime | 2 | Chinmay Patkar | VenueOpsService | MIG-QUEUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: setWaitTime. Additive to VenueOpsService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `queue#setWaitTime` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 2 | VM-MIG-QUEUE | AM-VIRTUAL-QUEUE-P08-BLOCK-A | [DB] Forward migration V1051__queue.sql: queue for Venue Management (1 tables) | 1 | Hrushikant Patkar |  | MIG-QUEUE | Tables: queue.feed. Source DDL: backend/tenant/010-queue.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `queue.feed` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
16 | 2 | VM-VENUEOPS-FEED-1 | AM-SETUP-VENUE-OPERATIONS-P08-REST | [BE] VenueOpsService: configureQueueFeed, getQueueFeedHealth, listQueueFeeds, testQueueFeed | 5 | Tanmay Dukhande | VenueOpsService | MIG-QUEUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-QUEUE | Operations beyond the first release: configureQueueFeed, getQueueFeedHealth, listQueueFeeds, testQueueFeed. Additive to VenueOpsService; its first-release owner (Hrushikant Patkar) reviews. Done when `queue#configureQueueFeed`, `queue#getQueueFeedHealth`, `queue#listQueueFeeds`, `queue#testQueueFeed` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 2 | VM-VENUEOPS-ENTRY-1 | AM-VIRTUAL-QUEUE-P08-BLOCK-A | [BE] VenueOpsService: callNextParties, listQueueEntries | 3 | Chinmay Patkar | VenueOpsService | MIG-QUEUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: callNextParties, listQueueEntries. Additive to VenueOpsService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `queue#callNextParties`, `queue#listQueueEntries` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-VENUEOPS-ENTRY-2 | AM-VIRTUAL-QUEUE-P08-BLOCK-A | [BE] VenueOpsService: listMyWaitingGuests, overrideWaitingGuest, redeemWaitingGuest | 5 | Surendra | VenueOpsService | MIG-QUEUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listMyWaitingGuests, overrideWaitingGuest, redeemWaitingGuest. Spec: contracts (queue) at the release tag, served by ADAM. Built for Virtual Queue · Venue Management (Block A); additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `queue#listMyWaitingGuests`, `queue#overrideWaitingGuest`, `queue#redeemWaitingGuest` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-VENUEOPS-FEED-2 | AM-VIRTUAL-QUEUE-P08-BLOCK-A | [BE] VenueOpsService: submitQueueReading | 1 | Deep Khanvilkar | VenueOpsService | MIG-QUEUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-QUEUE | Operations: submitQueueReading. Spec: contracts (queue) at the release tag, served by ADAM. Built for Virtual Queue · Venue Management (Block A); additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `queue#submitQueueReading` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-VENUEOPS-SIGNAGE-1 | AM-VIRTUAL-QUEUE-P08-BLOCK-A | [BE] VenueOpsService: getSignageQueueBoard, getSignageQueueCalls | 3 | Hrushikant Patkar | VenueOpsService | MIG-QUEUE PLATFORM-KERNEL SVC-VENUEOPS-ENTRY-1 SVC-VENUEOPS-ENTRY-2 SVC-VENUEOPS-FEED-2 SVC-VENUEOPS-QUEUE-1 VM-VENUEOPS-ENTRY-1 VM-VENUEOPS-FEED-1 VM-VENUEOPS-QUEUE-1 VM-VENUEOPS-WAITTIME-1 | Operations: getSignageQueueBoard, getSignageQueueCalls. Spec: contracts (queue) at the release tag, served by ADAM. Built for Virtual Queue · Venue Management (Block A); additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `queue#getSignageQueueBoard`, `queue#getSignageQueueCalls` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 1 | SVC-INVENTORY-RECEIPT-1 | AM-SETUP-FOOD-BEVERAGE-RETAIL-P06 | [BE] InventoryService: createGoodsReceipt, rejectReceivedGoods | 5 | Pranay Shinde | InventoryService | MIG-INVENTORY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: createGoodsReceipt, rejectReceivedGoods. Spec: handoff/service-docs/backend/InventoryService.md#group-receipt Helper task: Pranay Shinde owns the service and reviews. Done when `inventory#createGoodsReceipt`, `inventory#rejectReceivedGoods` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-TENANCY-REGION-1 | AM-SETUP-FOOD-BEVERAGE-RETAIL-P08 | [BE] TenancyService: getRegionSettings, updateRegionSettings | 5 | Deep Khanvilkar | TenancyService | MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getRegionSettings, updateRegionSettings. Spec: handoff/service-docs/backend/TenancyService.md#group-region Helper task: Hrushikant Patkar owns the service and reviews. Done when `tenancy#getRegionSettings`, `tenancy#updateRegionSettings` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 1 | SVC-ORDER-POLICY-1 | AM-SETUP-FOOD-BEVERAGE-RETAIL-P08 | [BE] OrderService: setRefundPolicy | 2 | Chinmay Patkar | OrderService | MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setRefundPolicy. Spec: handoff/service-docs/backend/OrderService.md#group-policy Helper task: Pranay Shinde owns the service and reviews. Done when `orders#setRefundPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 2 | VM-ORDER-POLICY-1 | AM-ORDERS-RESERVATIONS-P08-BLOCK-A | [BE] OrderService: getRefundPolicy | 2 | Chinmay Patkar | OrderService | MIG-ORDERS PLATFORM-KERNEL SVC-ORDER-POLICY-1 | Operations beyond the first release: getRefundPolicy. Additive to OrderService; its first-release owner (Pranay Shinde) reviews. Helper task: Pranay Shinde owns the service and reviews. Done when `orders#getRefundPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 1 | SVC-FNB-PRODUCTION-1 | AM-SETUP-FOOD-BEVERAGE-RETAIL-P08 | [BE] FnbService: setRecipe | 3 | Chinmay Patkar | FnbService | MIG-FNB MIG-INVENTORY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setRecipe. Spec: handoff/service-docs/backend/FnbService.md#group-production Helper task: Tanmay Dukhande owns the service and reviews. Done when `fnb#setRecipe` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 1 | SVC-REPORTING-EXECUTION-1 | AM-APPROVALS-P04 | [BE] ReportingService: runReport | 1 | Chinmay Patkar | ReportingService | MIG-REPORTING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-5 SVC-ACCESS-ACCESS-6 SVC-ACCESS-ACCESS-7 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-2 SVC-CATALOGUE-CATEGORY-1 SVC-CATALOGUE-COUPON-1 SVC-CATALOGUE-DRAFTED-1 SVC-CATALOGUE-ENTITLEMENT-1 SVC-CATALOGUE-EVALUATION-1 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-HOLD-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-PRICING-1 SVC-CATALOGUE-PRODUCT-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTIONS-1 SVC-CATALOGUE-SEATING-1 SVC-CATALOGUE-SEATMAP-1 SVC-FNB-BILL-1 SVC-FNB-FNB-1 SVC-FNB-FNB-10 SVC-FNB-FNB-2 SVC-FNB-FNB-3 SVC-FNB-FNB-4 SVC-FNB-FNB-5 SVC-FNB-FNB-6 SVC-FNB-FNB-7 SVC-FNB-FNB-8 SVC-FNB-FNB-9 SVC-FNB-GUESTORDERING-1 SVC-FNB-GUESTORDERING-3 SVC-FNB-GUESTORDERING-4 SVC-FNB-KITCHEN-1 SVC-FNB-MENU-1 SVC-FNB-MODIFIER-1 SVC-FNB-ORDER-1 SVC-FNB-PRODUCTION-1 SVC-FNB-SERVICE-1 SVC-FNB-TABLE-1 SVC-FNB-TABLE-2 SVC-INVENTORY-ITEM-1 SVC-INVENTORY-RECEIPT-1 SVC-LEDGER-FINANCE-1 SVC-LEDGER-FISCAL-1 SVC-LEDGER-LEDGER-1 SVC-LEDGER-TAX-1 SVC-LEDGER-TAX-2 SVC-LEDGER-TAX-3 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-CART-3 SVC-ORDER-CASH-1 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-1 SVC-ORDER-ORDERS-2 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-PAYMENTS-2 SVC-ORDER-POLICY-1 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SHIFT-1 SVC-ORDER-SHIFT-3 SVC-ORDER-SHIFT-4 SVC-ORDER-SHIFT-5 SVC-ORDER-SHIFT-6 SVC-ORDER-SYNC-1 SVC-RETAIL-FLOOR-1 SVC-RETAIL-FLOOR-2 SVC-RETAIL-MERCHANDISE-1 SVC-RETAIL-RETURN-1 SVC-RETAIL-SALE-1 SVC-WALLET-CARD-1 SVC-WALLET-RETAIL-1 SVC-WALLET-RETAIL-2 SVC-WALLET-WALLET-1 SVC-WALLET-WALLET-2 | Operations: runReport. Spec: handoff/service-docs/backend/ReportingService.md#group-execution Helper task: Tanmay Dukhande owns the service and reviews. Done when `reporting#runReport` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 1 | SVC-REPORTING-REPORTING-1 | AM-APPROVALS-P04 | [BE] ReportingService: createKpi, deleteDashboard, listAlerts, setAlertRule | 5 | Deep Khanvilkar | ReportingService | MIG-IDENTITY MIG-REPORTING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-5 SVC-ACCESS-ACCESS-6 SVC-ACCESS-ACCESS-7 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-2 SVC-CATALOGUE-CATEGORY-1 SVC-CATALOGUE-COUPON-1 SVC-CATALOGUE-DRAFTED-1 SVC-CATALOGUE-ENTITLEMENT-1 SVC-CATALOGUE-EVALUATION-1 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-HOLD-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-PRICING-1 SVC-CATALOGUE-PRODUCT-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTIONS-1 SVC-CATALOGUE-SEATING-1 SVC-CATALOGUE-SEATMAP-1 SVC-FNB-BILL-1 SVC-FNB-FNB-1 SVC-FNB-FNB-10 SVC-FNB-FNB-2 SVC-FNB-FNB-3 SVC-FNB-FNB-4 SVC-FNB-FNB-5 SVC-FNB-FNB-6 SVC-FNB-FNB-7 SVC-FNB-FNB-8 SVC-FNB-FNB-9 SVC-FNB-GUESTORDERING-1 SVC-FNB-GUESTORDERING-3 SVC-FNB-GUESTORDERING-4 SVC-FNB-KITCHEN-1 SVC-FNB-MENU-1 SVC-FNB-MODIFIER-1 SVC-FNB-ORDER-1 SVC-FNB-PRODUCTION-1 SVC-FNB-SERVICE-1 SVC-FNB-TABLE-1 SVC-FNB-TABLE-2 SVC-INVENTORY-ITEM-1 SVC-INVENTORY-RECEIPT-1 SVC-LEDGER-FINANCE-1 SVC-LEDGER-FISCAL-1 SVC-LEDGER-LEDGER-1 SVC-LEDGER-TAX-1 SVC-LEDGER-TAX-2 SVC-LEDGER-TAX-3 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-CART-3 SVC-ORDER-CASH-1 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-1 SVC-ORDER-ORDERS-2 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-PAYMENTS-2 SVC-ORDER-POLICY-1 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SHIFT-1 SVC-ORDER-SHIFT-3 SVC-ORDER-SHIFT-4 SVC-ORDER-SHIFT-5 SVC-ORDER-SHIFT-6 SVC-ORDER-SYNC-1 SVC-RETAIL-FLOOR-1 SVC-RETAIL-FLOOR-2 SVC-RETAIL-MERCHANDISE-1 SVC-RETAIL-RETURN-1 SVC-RETAIL-SALE-1 SVC-WALLET-CARD-1 SVC-WALLET-RETAIL-1 SVC-WALLET-RETAIL-2 SVC-WALLET-WALLET-1 SVC-WALLET-WALLET-2 | Operations: createKpi, deleteDashboard, listAlerts, setAlertRule. Spec: handoff/service-docs/backend/ReportingService.md#group-reporting Helper task: Tanmay Dukhande owns the service and reviews. Done when `reporting#createKpi`, `reporting#deleteDashboard`, `reporting#listAlerts`, `reporting#setAlertRule` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 1 | SVC-REPORTING-NATURALLANGUAGE-1 | AM-SETUP-FINANCE-INSIGHTS-P08 | [BE] ReportingService: askReportingQuestion, saveNaturalLanguageQuery | 8 | Pranay Shinde | ReportingService | MIG-AI MIG-PLATFORM MIG-REPORTING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-5 SVC-ACCESS-ACCESS-6 SVC-ACCESS-ACCESS-7 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-2 SVC-CATALOGUE-CATEGORY-1 SVC-CATALOGUE-COUPON-1 SVC-CATALOGUE-DRAFTED-1 SVC-CATALOGUE-ENTITLEMENT-1 SVC-CATALOGUE-EVALUATION-1 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-HOLD-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-PRICING-1 SVC-CATALOGUE-PRODUCT-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTIONS-1 SVC-CATALOGUE-SEATING-1 SVC-CATALOGUE-SEATMAP-1 SVC-FNB-BILL-1 SVC-FNB-FNB-1 SVC-FNB-FNB-10 SVC-FNB-FNB-2 SVC-FNB-FNB-3 SVC-FNB-FNB-4 SVC-FNB-FNB-5 SVC-FNB-FNB-6 SVC-FNB-FNB-7 SVC-FNB-FNB-8 SVC-FNB-FNB-9 SVC-FNB-GUESTORDERING-1 SVC-FNB-GUESTORDERING-3 SVC-FNB-GUESTORDERING-4 SVC-FNB-KITCHEN-1 SVC-FNB-MENU-1 SVC-FNB-MODIFIER-1 SVC-FNB-ORDER-1 SVC-FNB-PRODUCTION-1 SVC-FNB-SERVICE-1 SVC-FNB-TABLE-1 SVC-FNB-TABLE-2 SVC-INVENTORY-ITEM-1 SVC-INVENTORY-RECEIPT-1 SVC-LEDGER-FINANCE-1 SVC-LEDGER-FISCAL-1 SVC-LEDGER-LEDGER-1 SVC-LEDGER-TAX-1 SVC-LEDGER-TAX-2 SVC-LEDGER-TAX-3 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-CART-3 SVC-ORDER-CASH-1 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-1 SVC-ORDER-ORDERS-2 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-PAYMENTS-2 SVC-ORDER-POLICY-1 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SHIFT-1 SVC-ORDER-SHIFT-3 SVC-ORDER-SHIFT-4 SVC-ORDER-SHIFT-5 SVC-ORDER-SHIFT-6 SVC-ORDER-SYNC-1 SVC-RETAIL-FLOOR-1 SVC-RETAIL-FLOOR-2 SVC-RETAIL-MERCHANDISE-1 SVC-RETAIL-RETURN-1 SVC-RETAIL-SALE-1 SVC-WALLET-CARD-1 SVC-WALLET-RETAIL-1 SVC-WALLET-RETAIL-2 SVC-WALLET-WALLET-1 SVC-WALLET-WALLET-2 | Operations: askReportingQuestion, saveNaturalLanguageQuery. Spec: handoff/service-docs/backend/ReportingService.md#group-naturallanguage. Done when `reporting#askReportingQuestion`, `reporting#saveNaturalLanguageQuery` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 1 | SVC-REPORTING-DASHBOARD-1 | AM-SETUP-FINANCE-INSIGHTS-P16 | [BE] ReportingService: createDashboard, getDashboard, listDashboards, recordDashboardView | 5 | Hrushikant Patkar | ReportingService | MIG-REPORTING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-5 SVC-ACCESS-ACCESS-6 SVC-ACCESS-ACCESS-7 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-2 SVC-CATALOGUE-CATEGORY-1 SVC-CATALOGUE-COUPON-1 SVC-CATALOGUE-DRAFTED-1 SVC-CATALOGUE-ENTITLEMENT-1 SVC-CATALOGUE-EVALUATION-1 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-HOLD-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-PRICING-1 SVC-CATALOGUE-PRODUCT-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTIONS-1 SVC-CATALOGUE-SEATING-1 SVC-CATALOGUE-SEATMAP-1 SVC-FNB-BILL-1 SVC-FNB-FNB-1 SVC-FNB-FNB-10 SVC-FNB-FNB-2 SVC-FNB-FNB-3 SVC-FNB-FNB-4 SVC-FNB-FNB-5 SVC-FNB-FNB-6 SVC-FNB-FNB-7 SVC-FNB-FNB-8 SVC-FNB-FNB-9 SVC-FNB-GUESTORDERING-1 SVC-FNB-GUESTORDERING-3 SVC-FNB-GUESTORDERING-4 SVC-FNB-KITCHEN-1 SVC-FNB-MENU-1 SVC-FNB-MODIFIER-1 SVC-FNB-ORDER-1 SVC-FNB-PRODUCTION-1 SVC-FNB-SERVICE-1 SVC-FNB-TABLE-1 SVC-FNB-TABLE-2 SVC-INVENTORY-ITEM-1 SVC-INVENTORY-RECEIPT-1 SVC-LEDGER-FINANCE-1 SVC-LEDGER-FISCAL-1 SVC-LEDGER-LEDGER-1 SVC-LEDGER-TAX-1 SVC-LEDGER-TAX-2 SVC-LEDGER-TAX-3 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-CART-3 SVC-ORDER-CASH-1 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-1 SVC-ORDER-ORDERS-2 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-PAYMENTS-2 SVC-ORDER-POLICY-1 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SHIFT-1 SVC-ORDER-SHIFT-3 SVC-ORDER-SHIFT-4 SVC-ORDER-SHIFT-5 SVC-ORDER-SHIFT-6 SVC-ORDER-SYNC-1 SVC-RETAIL-FLOOR-1 SVC-RETAIL-FLOOR-2 SVC-RETAIL-MERCHANDISE-1 SVC-RETAIL-RETURN-1 SVC-RETAIL-SALE-1 SVC-WALLET-CARD-1 SVC-WALLET-RETAIL-1 SVC-WALLET-RETAIL-2 SVC-WALLET-WALLET-1 SVC-WALLET-WALLET-2 | Operations: createDashboard, getDashboard, listDashboards, recordDashboardView. Spec: handoff/service-docs/backend/ReportingService.md#group-dashboard Helper task: Tanmay Dukhande owns the service and reviews. Done when `reporting#createDashboard`, `reporting#getDashboard`, `reporting#listDashboards`, `reporting#recordDashboardView` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-REPORTING-REPORTING-4 | AM-SETUP-FINANCE-INSIGHTS-P16-REST | [BE] ReportingService: getSemanticModel, listKpis | 2 | Tanmay Dukhande | ReportingService | MIG-REPORTING PLATFORM-KERNEL SVC-REPORTING-REPORTING-1 SVC-REPORTING-REPORTING-2 | Operations: getSemanticModel, listKpis. Spec: contracts (reporting) at the release tag, served by ADAM. Built for Finance & Insights · Analytics (setup, the rest of the screens); additive to ReportingService, whose first-release owner (Tanmay Dukhande) reviews. Done when `reporting#getSemanticModel`, `reporting#listKpis` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-FNB-MENU-2 | AM-FOOD-BEVERAGE-P08-BLOCK-A | [BE] FnbService: listMenuSchedules, listMenuVersions, listMenus | 3 | Tanmay Dukhande | FnbService | MIG-FNB PLATFORM-KERNEL SVC-FNB-FNB-1 SVC-FNB-FNB-16 SVC-FNB-FNB-6 SVC-FNB-FNB-8 SVC-FNB-MENU-1 SVC-FNB-PRODUCTION-1 VM-FNB-MENU-1 | Operations: listMenuSchedules, listMenuVersions, listMenus. Spec: contracts (fnb) at the release tag, served by ADAM. Built for Food & Beverage · Venue Management (Block A); additive to FnbService, whose first-release owner (Tanmay Dukhande) reviews. Done when `fnb#listMenuSchedules`, `fnb#listMenuVersions`, `fnb#listMenus` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 2 | VM-MIG-INVENTORY | AM-SETUP-FOOD-BEVERAGE-RETAIL-P08-REST | [DB] Forward migration V1049__inventory.sql: inventory for Venue Management (9 tables) | 5 | Hrushikant Patkar |  | MIG-INVENTORY | Tables: inventory.count, inventory.count_line, inventory.purchase_order_line, inventory.quotation, inventory.quotation_line, inventory.requisition_line, inventory.supplier_contract, inventory.transfer, inventory.transfer_line. Source DDL: backend/tenant/010-inventory.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `inventory.count`, `inventory.count_line`, `inventory.purchase_order_line`, `inventory.quotation`, `inventory.quotation_line`, `inventory.requisition_line`, `inventory.supplier_contract`, `inventory.transfer` and 1 more runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
13 | 2 | VM-INVENTORY-TRANSFER-1 | AM-ADMISSION-ACCESS-P08-BLOCK-A | [BE] InventoryService: closeTransferShort, createStockTransfer, listStockTransfers, receiveStockTransfer | 8 | Pranay Shinde | InventoryService | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-INVENTORY | Operations beyond the first release: closeTransferShort, createStockTransfer, listStockTransfers, receiveStockTransfer. Additive to InventoryService; its first-release owner (Pranay Shinde) reviews. Done when `inventory#closeTransferShort`, `inventory#createStockTransfer`, `inventory#listStockTransfers`, `inventory#receiveStockTransfer` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 2 | VM-INVENTORY-PURCHASEORDER-1 | AM-SETUP-FOOD-BEVERAGE-RETAIL-P06-REST | [BE] InventoryService: cancelPurchaseOrder, createPurchaseOrder, getPurchaseOrder, listPurchaseOrders | 8 | Pranay Shinde | InventoryService | MIG-INVENTORY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-INVENTORY | Operations beyond the first release: cancelPurchaseOrder, createPurchaseOrder, getPurchaseOrder, listPurchaseOrders. Additive to InventoryService; its first-release owner (Pranay Shinde) reviews. Done when `inventory#cancelPurchaseOrder`, `inventory#createPurchaseOrder`, `inventory#getPurchaseOrder`, `inventory#listPurchaseOrders` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 2 | VM-INVENTORY-INVENTORY-1 | AM-SETUP-FOOD-BEVERAGE-RETAIL-P06-REST | [BE] InventoryService: getStockTransfer, updateRequisitionLines, updateSupplier | 8 | Pranay Shinde | InventoryService | MIG-FNB MIG-INVENTORY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-INVENTORY | Operations beyond the first release: getStockTransfer, updateRequisitionLines, updateSupplier. Additive to InventoryService; its first-release owner (Pranay Shinde) reviews. Done when `inventory#getStockTransfer`, `inventory#updateRequisitionLines`, `inventory#updateSupplier` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 2 | VM-INVENTORY-ITEM-1 | AM-SETUP-FOOD-BEVERAGE-RETAIL-P08-REST | [BE] InventoryService: listInventoryItems | 2 | Chinmay Patkar | InventoryService | MIG-INVENTORY PLATFORM-KERNEL SVC-INVENTORY-ITEM-1 | Operations beyond the first release: listInventoryItems. Additive to InventoryService; its first-release owner (Pranay Shinde) reviews. Helper task: Pranay Shinde owns the service and reviews. Done when `inventory#listInventoryItems` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 2 | VM-FNB-FNB-1 | AM-SETUP-FOOD-BEVERAGE-RETAIL-P08-REST | [BE] FnbService: enterCountLine, getProductionRun, listProductionRuns, listTemperatureCheckpoints | 8 | Tanmay Dukhande | FnbService | MIG-FNB MIG-INVENTORY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-FNB VM-MIG-INVENTORY | Operations beyond the first release: enterCountLine, getProductionRun, listProductionRuns, listTemperatureCheckpoints. Additive to FnbService; its first-release owner (Tanmay Dukhande) reviews. Done when `fnb#enterCountLine`, `fnb#getProductionRun`, `fnb#listProductionRuns`, `fnb#listTemperatureCheckpoints` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 3 | SVC-FNB-PRODUCTION-3 | AM-SETUP-FOOD-BEVERAGE-RETAIL-P08-REST | [BE] FnbService: printPrepSheet | 1 | Deep Khanvilkar | FnbService | MIG-BASELINE PLATFORM-KERNEL | Operations: printPrepSheet. Spec: contracts (fnb) at the release tag, served by ADAM. Built for Food, Beverage & Retail · Venue Management (setup, the rest of the screens); additive to FnbService, whose first-release owner (Tanmay Dukhande) reviews. Done when `fnb#printPrepSheet` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-INVENTORY-STOCK-2 | AM-SETUP-FOOD-BEVERAGE-RETAIL-P08-REST | [BE] InventoryService: createStockLocation | 1 | Deep Khanvilkar | InventoryService | MIG-INVENTORY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createStockLocation. Spec: contracts (inventory) at the release tag, served by ADAM. Built for Food, Beverage & Retail · Venue Management (setup, the rest of the screens); additive to InventoryService, whose first-release owner (Pranay Shinde) reviews. Done when `inventory#createStockLocation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | SVC-INVENTORY-ITEM-2 | AM-SETUP-FOOD-BEVERAGE-RETAIL-P08-REST | [BE] InventoryService: getInventoryItem, getInventoryKitDefinition, lookupInventoryItem | 5 | Surendra | InventoryService | MIG-INVENTORY PLATFORM-KERNEL SVC-INVENTORY-ITEM-1 | Operations: getInventoryItem, getInventoryKitDefinition, lookupInventoryItem. Spec: contracts (inventory) at the release tag, served by ADAM. Built for Food, Beverage & Retail · Venue Management (setup, the rest of the screens); additive to InventoryService, whose first-release owner (Pranay Shinde) reviews. Done when `inventory#getInventoryItem`, `inventory#getInventoryKitDefinition`, `inventory#lookupInventoryItem` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-FNB-FNB-20 | AM-SETUP-FOOD-BEVERAGE-RETAIL-P08-REST | [BE] FnbService: completeProductionRun, listProductionPlans, planProductionRun | 5 | Tanmay Dukhande | FnbService | MIG-FNB MIG-INVENTORY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: completeProductionRun, listProductionPlans, planProductionRun. Spec: contracts (fnb) at the release tag, served by ADAM. Built for Food, Beverage & Retail · Venue Management (setup, the rest of the screens); additive to FnbService, whose first-release owner (Tanmay Dukhande) reviews. Done when `fnb#completeProductionRun`, `fnb#listProductionPlans`, `fnb#planProductionRun` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 2 | VM-REPORTING-REPORTING-1 | AM-ADMISSION-ACCESS-P08-BLOCK-A | [BE] ReportingService: acknowledgeAlert, getKpiValues, getSupplierPerformance | 3 | Sanket Keluskar | ReportingService | MIG-IDENTITY MIG-INVENTORY MIG-REPORTING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-11 SVC-ACCESS-ACCESS-12 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-5 SVC-ACCESS-ACCESS-58 SVC-ACCESS-ACCESS-6 SVC-ACCESS-ACCESS-60 SVC-ACCESS-ACCESS-7 SVC-ACCESS-ACCESS-9 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-ACCESS-ACCESSPOINT-3 SVC-ACCESS-VALIDATION-2 SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-2 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-CATALOGUE-6 SVC-CATALOGUE-CATALOGUE-7 SVC-CATALOGUE-CATEGORY-1 SVC-CATALOGUE-COUPON-1 SVC-CATALOGUE-COUPON-2 SVC-CATALOGUE-DRAFTED-1 SVC-CATALOGUE-DRAFTED-3 SVC-CATALOGUE-DRAFTED-4 SVC-CATALOGUE-DRAFTED-5 SVC-CATALOGUE-DRAFTED-56 SVC-CATALOGUE-ENTITLEMENT-1 SVC-CATALOGUE-EVALUATION-1 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENT-4 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-EVENTS-2 SVC-CATALOGUE-HOLD-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-CATALOGUE-PRICING-1 SVC-CATALOGUE-PRODUCT-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTIONS-1 SVC-CATALOGUE-PROMOTIONS-2 SVC-CATALOGUE-SEATING-1 SVC-CATALOGUE-SEATMAP-1 SVC-CATALOGUE-SEATMAP-2 SVC-CATALOGUE-VOUCHER-1 SVC-FNB-BILL-1 SVC-FNB-FNB-1 SVC-FNB-FNB-10 SVC-FNB-FNB-11 SVC-FNB-FNB-12 SVC-FNB-FNB-13 SVC-FNB-FNB-16 SVC-FNB-FNB-17 SVC-FNB-FNB-18 SVC-FNB-FNB-2 SVC-FNB-FNB-20 SVC-FNB-FNB-3 SVC-FNB-FNB-4 SVC-FNB-FNB-5 SVC-FNB-FNB-6 SVC-FNB-FNB-7 SVC-FNB-FNB-8 SVC-FNB-FNB-9 SVC-FNB-GUESTORDERING-1 SVC-FNB-GUESTORDERING-3 SVC-FNB-GUESTORDERING-4 SVC-FNB-KITCHEN-1 SVC-FNB-MENU-1 SVC-FNB-MODIFIER-1 SVC-FNB-ORDER-1 SVC-FNB-PRODUCTION-1 SVC-FNB-PRODUCTION-2 SVC-FNB-SERVICE-1 SVC-FNB-TABLE-1 SVC-FNB-TABLE-2 SVC-FNB-TABLE-3 SVC-INVENTORY-INVENTORY-3 SVC-INVENTORY-ITEM-1 SVC-INVENTORY-RECEIPT-1 SVC-INVENTORY-STOCK-2 SVC-LEDGER-ACCOUNTS-1 SVC-LEDGER-ACCOUNTS-2 SVC-LEDGER-FINANCE-1 SVC-LEDGER-FINANCE-3 SVC-LEDGER-FISCAL-1 SVC-LEDGER-LEDGER-1 SVC-LEDGER-LEDGER-3 SVC-LEDGER-TAX-1 SVC-LEDGER-TAX-2 SVC-LEDGER-TAX-3 SVC-LEDGER-TAX-4 SVC-LEDGER-TAX-5 SVC-LEDGER-TAX-6 SVC-LEDGER-VARIANCE-1 SVC-ORDER-B2B-1 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-CART-3 SVC-ORDER-CASH-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-1 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-13 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-2 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-PAYMENTS-17 SVC-ORDER-PAYMENTS-18 SVC-ORDER-PAYMENTS-2 SVC-ORDER-PAYMENTS-6 SVC-ORDER-POLICY-1 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SHIFT-1 SVC-ORDER-SHIFT-3 SVC-ORDER-SHIFT-4 SVC-ORDER-SHIFT-5 SVC-ORDER-SHIFT-6 SVC-ORDER-SHIFT-7 SVC-ORDER-SYNC-1 SVC-RETAIL-FLOOR-1 SVC-RETAIL-FLOOR-2 SVC-RETAIL-MERCHANDISE-1 SVC-RETAIL-RETURN-1 SVC-RETAIL-SALE-1 SVC-WALLET-CARD-1 SVC-WALLET-RETAIL-1 SVC-WALLET-RETAIL-2 SVC-WALLET-WALLET-1 SVC-WALLET-WALLET-2 SVC-WALLET-WALLET-5 SVC-WALLET-WALLET-8 SVC-WALLET-WALLET-9 VM-ACCESS-ACCESS-1 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-EVENT-1 VM-CATALOGUE-PRODUCT-1 VM-CATALOGUE-UPSELL-1 VM-FNB-FNB-1 VM-FNB-MENU-1 VM-FNB-ORDER-1 VM-FNB-PRODUCTION-1 VM-INVENTORY-INVENTORY-1 VM-INVENTORY-MOVEMENT-1 VM-INVENTORY-PURCHASEORDER-1 VM-INVENTORY-TRANSFER-1 VM-LEDGER-FINANCE-1 VM-LEDGER-FISCAL-1 VM-LEDGER-LEDGER-1 VM-LEDGER-SETTLEMENT-1 VM-LEDGER-SETTLEMENT-2 VM-MIG-ACCREDITATION VM-MIG-INVENTORY VM-MIG-REPORTING VM-ORDER-ORDERS-1 VM-ORDER-ORDERS-2 VM-ORDER-ORDERS-3 VM-ORDER-REFUND-1 VM-ORDER-SHIFT-1 VM-ORDER-SYNC-1 VM-RETAIL-RETAIL-1 VM-WALLET-WALLET-1 | Operations beyond the first release: acknowledgeAlert, getKpiValues, getSupplierPerformance. Additive to ReportingService; its first-release owner (Tanmay Dukhande) reviews. Helper task: Tanmay Dukhande owns the service and reviews. Done when `reporting#acknowledgeAlert`, `reporting#getKpiValues`, `reporting#getSupplierPerformance` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 2 | VM-INVENTORY-STOCK-1 | AM-SETUP-FOOD-BEVERAGE-RETAIL-P08-REST | [BE] InventoryService: getStockPositions, getStockValuation, listStockLocations | 5 | Deep Khanvilkar | InventoryService | MIG-INVENTORY MIG-LEDGER PLATFORM-KERNEL SVC-FNB-FNB-20 SVC-FNB-FNB-7 SVC-INVENTORY-INVENTORY-3 SVC-INVENTORY-ITEM-1 SVC-INVENTORY-STOCK-2 SVC-LEDGER-ACCOUNTS-1 SVC-LEDGER-ACCOUNTS-2 SVC-RETAIL-FLOOR-2 SVC-RETAIL-RETURN-1 SVC-RETAIL-SALE-1 SVC-VENUEOPS-WORKORDER-4 VM-FNB-PRODUCTION-1 VM-INVENTORY-MOVEMENT-1 | Operations beyond the first release: getStockPositions, getStockValuation, listStockLocations. Additive to InventoryService; its first-release owner (Pranay Shinde) reviews. Helper task: Pranay Shinde owns the service and reviews. Done when `inventory#getStockPositions`, `inventory#getStockValuation`, `inventory#listStockLocations` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-MARKETING-FEEDBACK-1 | AM-MARKETING-CRM-P01 | [BE] MarketingService: submitReview | 2 | Chinmay Patkar | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: submitReview. Spec: handoff/service-docs/backend/MarketingService.md#group-feedback Helper task: Pranay Shinde owns the service and reviews. Done when `marketing-crm#submitReview` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-MARKETING-LOYALTY-2 | AM-MARKETING-CRM-P01 | [BE] MarketingService: listLeaderboard, listLoyaltyProgrammes, listRewards, setLeaderboardNickname | 5 | Pranay Shinde | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listLeaderboard, listLoyaltyProgrammes, listRewards, setLeaderboardNickname. Spec: handoff/service-docs/backend/MarketingService.md#group-loyalty. Done when `marketing-crm#listLeaderboard`, `marketing-crm#listLoyaltyProgrammes`, `marketing-crm#listRewards`, `marketing-crm#setLeaderboardNickname` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-MARKETING-MARKETING-1 | AM-MARKETING-CRM-P01 | [BE] MarketingService: createChallenge, createForm, createInvitationCampaign, createReferral | 8 | Pranay Shinde | MarketingService | MIG-CATALOGUE MIG-MARKETING MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createChallenge, createForm, createInvitationCampaign, createReferral. Spec: handoff/service-docs/backend/MarketingService.md#group-marketing. Done when `marketing-crm#createChallenge`, `marketing-crm#createForm`, `marketing-crm#createInvitationCampaign`, `marketing-crm#createReferral` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-MARKETING-MARKETING-2 | AM-MARKETING-CRM-P01 | [BE] MarketingService: createUrlRedirect, getForm, getLoyaltyPosition, getMyChallenges | 5 | Deep Khanvilkar | MarketingService | MIG-CONTROL MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createUrlRedirect, getForm, getLoyaltyPosition, getMyChallenges. Spec: handoff/service-docs/backend/MarketingService.md#group-marketing. Done when `marketing-crm#createUrlRedirect`, `marketing-crm#getForm`, `marketing-crm#getLoyaltyPosition`, `marketing-crm#getMyChallenges` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-MARKETING-MESSAGE-1 | AM-MARKETING-CRM-P01 | [BE] MarketingService: createMessageTemplate, listMyNotifications, markMyNotificationsRead, updateMessageTemplate | 8 | Pranay Shinde | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createMessageTemplate, listMyNotifications, markMyNotificationsRead, updateMessageTemplate. Spec: handoff/service-docs/backend/MarketingService.md#group-message. Done when `marketing-crm#createMessageTemplate`, `marketing-crm#listMyNotifications`, `marketing-crm#markMyNotificationsRead`, `marketing-crm#updateMessageTemplate` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 2 | VM-MIG-MARKETING | AM-MARKETING-CRM-P08-BLOCK-A | [DB] Forward migration V1052__marketing.sql: marketing for Venue Management (1 tables) | 1 | Hrushikant Patkar |  | MIG-MARKETING | Tables: marketing.journey_step. Source DDL: backend/tenant/010-marketing.sql. Additive to the first release; applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `marketing.journey_step` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
6 | 3 | MIG-TENANCY-3 | AM-MARKETING-CRM-P08-BLOCK-A | [DB] Forward migration V1077__tenancy.sql: tenancy for Tenancy & Venues · Venue Management 2 of 3 (2 tables) | 2 | Hrushikant Patkar | TenancyService | MIG-BASELINE MIG-TENANCY VM-MIG-TENANCY | Tables: tenancy.data_retention_setting, tenancy.device_telemetry. Source DDL: backend/tenant/010-tenancy.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `tenancy.data_retention_setting`, `tenancy.device_telemetry` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
15 | 3 | MIG-MARKETING-6 | AM-MARKETING-CRM-P08-BLOCK-A | [DB] Forward migration V1054__marketing.sql: marketing for Marketing & CRM · Venue Management (Block A) (29 tables) | 8 | Hrushikant Patkar | MarketingService | MIG-BASELINE MIG-IDENTITY MIG-MARKETING VM-MIG-MARKETING | Tables: marketing.agent_service_profile, marketing.business_event, marketing.case_internal_request, marketing.case_linked_record, marketing.case_resolution, marketing.case_routing_rule, marketing.communication_routing_rule, marketing.consent_record_channel, marketing.contact_automation, marketing.guest_extra_field, marketing.guest_extra_option, marketing.guest_extra_value, marketing.guest_match_policy, marketing.guest_relationship, marketing.message_trigger, marketing.message_trigger_condition, marketing.privacy_request_deadline, marketing.privacy_request_type, marketing.quality_evaluation, marketing.reward_assignment, marketing.sla_policy, marketing.suppression, marketing.tracking_technology_catalogue, marketing.waiver_association, marketing.waiver_exception, marketing.waiver_form_layout, marketing.waiver_master, marketing.waiver_trigger_rule, marketing.waiver_version_control. Source DDL: backend/tenant/010-marketing.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `marketing.agent_service_profile`, `marketing.business_event`, `marketing.case_internal_request`, `marketing.case_linked_record`, `marketing.case_resolution`, `marketing.case_routing_rule`, `marketing.communication_routing_rule`, `marketing.consent_record_channel` and 21 more runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
15 | 3 | MIG-MARKETING-2 | AM-MARKETING-CRM-P08-BLOCK-A | [DB] Forward migration V1062__marketing.sql: marketing for Identity & Security · Venue Management (4 tables) | 2 | Hrushikant Patkar | MarketingService | MIG-BASELINE MIG-MARKETING MIG-ORDERS MIG-PII VM-MIG-MARKETING | Tables: marketing.guest_note, marketing.loyalty_points, marketing.touch_point, marketing.waiver_signature. Source DDL: backend/tenant/010-marketing.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `marketing.guest_note`, `marketing.loyalty_points`, `marketing.touch_point`, `marketing.waiver_signature` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
15 | 3 | MIG-MARKETING-3 | AM-MARKETING-CRM-P08-BLOCK-A | [DB] Forward migration V1082__marketing.sql: marketing for Tenancy & Venues · Venue Management 2 of 3 (5 tables) | 3 | Hrushikant Patkar | MarketingService | MIG-BASELINE MIG-MARKETING VM-MIG-MARKETING | Tables: marketing.legal_hold, marketing.privacy_action, marketing.privacy_audit_event, marketing.retention_policy, marketing.retention_run. Source DDL: backend/tenant/010-marketing.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `marketing.legal_hold`, `marketing.privacy_action`, `marketing.privacy_audit_event`, `marketing.retention_policy`, `marketing.retention_run` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
14 | 3 | SVC-MARKETING-CAMPAIGN-2 | AM-MARKETING-CRM-P08-BLOCK-A | [BE] MarketingService: pauseCampaign, unscheduleCampaign | 5 | Tanmay Dukhande | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: pauseCampaign, unscheduleCampaign. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management (Block A); additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#pauseCampaign`, `marketing-crm#unscheduleCampaign` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-MARKETING-MESSAGE-3 | AM-MARKETING-CRM-P08-BLOCK-A | [BE] MarketingService: notifyPerformanceHolders | 1 | Pallavi Sawant | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: notifyPerformanceHolders. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management (Block A); additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#notifyPerformanceHolders` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-CASE-1 | AM-MARKETING-CRM-P08-BLOCK-A | [BE] MarketingService: getCaseInvestigationResolution, listIntelligentRoutingSkills, setAgentServiceProfile, setCaseInternalRequest | 8 | Tanmay Dukhande | MarketingService | MIG-MARKETING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getCaseInvestigationResolution, listIntelligentRoutingSkills, setAgentServiceProfile, setCaseInternalRequest. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management (Block A); additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#getCaseInvestigationResolution`, `marketing-crm#listIntelligentRoutingSkills`, `marketing-crm#setAgentServiceProfile`, `marketing-crm#setCaseInternalRequest` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-CASE-2 | AM-MARKETING-CRM-P08-BLOCK-A | [BE] MarketingService: setCaseResolution, setContactAutomation, setQualityEvaluation | 8 | Surendra | MarketingService | MIG-MARKETING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setCaseResolution, setContactAutomation, setQualityEvaluation. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management (Block A); additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#setCaseResolution`, `marketing-crm#setContactAutomation`, `marketing-crm#setQualityEvaluation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-CONSENT-7 | AM-MARKETING-CRM-P08-BLOCK-A | [BE] MarketingService: recordCheckoutConsents, setPrivacyAction, setPrivacyRequestTypes, setTrackingTechnologyCatalogueEntry | 8 | Surendra | MarketingService | MIG-MARKETING MIG-MARKETING-3 MIG-MARKETING-6 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: recordCheckoutConsents, setPrivacyAction, setPrivacyRequestTypes, setTrackingTechnologyCatalogueEntry. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management (Block A); additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#recordCheckoutConsents`, `marketing-crm#setPrivacyAction`, `marketing-crm#setPrivacyRequestTypes`, `marketing-crm#setTrackingTechnologyCatalogueEntry` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-CONSENT-8 | AM-MARKETING-CRM-P08-BLOCK-A | [BE] MarketingService: setWaiverAssociation, setWaiverException, setWaiverTemplateMaster, setWaiverTriggerRule | 8 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-MARKETING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setWaiverAssociation, setWaiverException, setWaiverTemplateMaster, setWaiverTriggerRule. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management (Block A); additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#setWaiverAssociation`, `marketing-crm#setWaiverException`, `marketing-crm#setWaiverTemplateMaster`, `marketing-crm#setWaiverTriggerRule` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-CONSENT-6 | AM-MARKETING-CRM-P08-BLOCK-A | [BE] MarketingService: actOnWaiverRequirements, getDigitalWaiverForm, getSuppressionList, getWaiverTesting | 8 | Tanmay Dukhande | MarketingService | MIG-MARKETING MIG-MARKETING-6 MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: actOnWaiverRequirements, getDigitalWaiverForm, getSuppressionList, getWaiverTesting. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management (Block A); additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#actOnWaiverRequirements`, `marketing-crm#getDigitalWaiverForm`, `marketing-crm#getSuppressionList`, `marketing-crm#getWaiverTesting` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-GUESTS-3 | AM-MARKETING-CRM-P08-BLOCK-A | [BE] MarketingService: setDataRetentionPolicy | 2 | Chinmay Patkar | MarketingService | MIG-MARKETING-3 MIG-TENANCY-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setDataRetentionPolicy. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management (Block A); additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#setDataRetentionPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-LOYALTY-4 | AM-MARKETING-CRM-P08-BLOCK-A | [BE] MarketingService: issueReward, listLoyaltyPointEntries, listRewardAssignments | 3 | Sanket Keluskar | MarketingService | MIG-MARKETING-2 MIG-MARKETING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: issueReward, listLoyaltyPointEntries, listRewardAssignments. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management (Block A); additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#issueReward`, `marketing-crm#listLoyaltyPointEntries`, `marketing-crm#listRewardAssignments` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-MARKETING-11 | AM-MARKETING-CRM-P08-BLOCK-A | [BE] MarketingService: accrueLoyaltyPoints, getGuestExtraValues, listGuestExtraFields, listMessageDispatches | 5 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-MARKETING-6 MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: accrueLoyaltyPoints, getGuestExtraValues, listGuestExtraFields, listMessageDispatches. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management (Block A); additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#accrueLoyaltyPoints`, `marketing-crm#getGuestExtraValues`, `marketing-crm#listGuestExtraFields`, `marketing-crm#listMessageDispatches` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-MARKETING-12 | AM-MARKETING-CRM-P08-BLOCK-A | [BE] MarketingService: listSlaPolicies, listWaiverSignatures, recordTouchPoint, setGuestExtraValues | 5 | Surendra | MarketingService | MIG-MARKETING MIG-MARKETING-2 MIG-MARKETING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listSlaPolicies, listWaiverSignatures, recordTouchPoint, setGuestExtraValues. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management (Block A); additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#listSlaPolicies`, `marketing-crm#listWaiverSignatures`, `marketing-crm#recordTouchPoint`, `marketing-crm#setGuestExtraValues` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-MESSAGE-2 | AM-MARKETING-CRM-P08-BLOCK-A | [BE] MarketingService: setBusinessEventMapping, setCommunicationRoutingRule | 5 | Deep Khanvilkar | MarketingService | MIG-MARKETING MIG-MARKETING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setBusinessEventMapping, setCommunicationRoutingRule. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management (Block A); additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#setBusinessEventMapping`, `marketing-crm#setCommunicationRoutingRule` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | MIG-MARKETING-10 | AM-MARKETING-CRM-P12-BLOCK-A | [DB] Forward migration V1060__marketing.sql: marketing for Marketing & CRM · Venue Management 4 of 5 (3 tables) | 2 | Hrushikant Patkar | MarketingService | MIG-BASELINE MIG-MARKETING VM-MIG-MARKETING | Tables: marketing.case_escalation, marketing.feedback_classification, marketing.review_response. Source DDL: backend/tenant/010-marketing.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `marketing.case_escalation`, `marketing.feedback_classification`, `marketing.review_response` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
14 | 3 | SVC-MARKETING-CASE-8 | AM-MARKETING-CRM-P12-BLOCK-A | [BE] MarketingService: listCases, reopenCase, updateCase | 5 | Pranay Shinde | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listCases, reopenCase, updateCase. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Support Console (Block A); additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#listCases`, `marketing-crm#reopenCase`, `marketing-crm#updateCase` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-MARKETING-MARKETING-18 | AM-MARKETING-CRM-P12-BLOCK-A | [BE] MarketingService: claimConversation, closeConversation, getConversation, listConversations | 8 | Tanmay Dukhande | MarketingService | MIG-IDENTITY MIG-MARKETING MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: claimConversation, closeConversation, getConversation, listConversations. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Support Console (Block A); additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#claimConversation`, `marketing-crm#closeConversation`, `marketing-crm#getConversation`, `marketing-crm#listConversations` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-MARKETING-MARKETING-19 | AM-MARKETING-CRM-P12-BLOCK-A | [BE] MarketingService: transferConversation | 2 | Tanmay Dukhande | MarketingService | MIG-IDENTITY MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: transferConversation. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Support Console (Block A); additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#transferConversation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-CASE-7 | AM-MARKETING-CRM-P12-BLOCK-A | [BE] MarketingService: addCaseMessage, createCase, escalateCase, getCase | 8 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-MARKETING-10 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: addCaseMessage, createCase, escalateCase, getCase. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Support Console (Block A); additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#addCaseMessage`, `marketing-crm#createCase`, `marketing-crm#escalateCase`, `marketing-crm#getCase` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-AI-INSIGHTS-1 | AM-SETUP-CUSTOMER-MARKETING-P08 | [BE] AiService: decideAiInsight, explainMetricChange | 3 | Sanket Keluskar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: decideAiInsight, explainMetricChange. Spec: handoff/service-docs/backend/AiService.md#group-insights Helper task: Tanmay Dukhande owns the service and reviews. Done when `ai#decideAiInsight`, `ai#explainMetricChange` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-MARKETING-CAMPAIGN-1 | AM-SETUP-CUSTOMER-MARKETING-P08 | [BE] MarketingService: createCampaign, launchCampaign, stopCampaign, updateCampaign | 8 | Pranay Shinde | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createCampaign, launchCampaign, stopCampaign, updateCampaign. Spec: handoff/service-docs/backend/MarketingService.md#group-campaign. Done when `marketing-crm#createCampaign`, `marketing-crm#launchCampaign`, `marketing-crm#stopCampaign`, `marketing-crm#updateCampaign` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-MARKETING-LOYALTY-3 | AM-SETUP-CUSTOMER-MARKETING-P08 | [BE] MarketingService: setLoyaltyRules, setReward, updateLoyaltyProgramme | 8 | Pranay Shinde | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setLoyaltyRules, setReward, updateLoyaltyProgramme. Spec: handoff/service-docs/backend/MarketingService.md#group-loyalty. Done when `marketing-crm#setLoyaltyRules`, `marketing-crm#setReward`, `marketing-crm#updateLoyaltyProgramme` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 1 | SVC-MARKETING-SEGMENT-1 | AM-SETUP-CUSTOMER-MARKETING-P08 | [BE] MarketingService: createSegment | 2 | Chinmay Patkar | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createSegment. Spec: handoff/service-docs/backend/MarketingService.md#group-segment Helper task: Pranay Shinde owns the service and reviews. Done when `marketing-crm#createSegment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-MARKETING-SEGMENT-2 | AM-MARKETING-CRM-P08-BLOCK-A | [BE] MarketingService: listSegmentMembers | 1 | Deep Khanvilkar | MarketingService | MIG-MARKETING PLATFORM-KERNEL SVC-MARKETING-CAMPAIGN-1 SVC-MARKETING-CONSENT-3 SVC-MARKETING-GUEST-2 SVC-MARKETING-MARKETING-6 SVC-MARKETING-MARKETING-7 SVC-MARKETING-SEGMENT-1 | Operations: listSegmentMembers. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management (Block A); additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#listSegmentMembers` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | MIG-MARKETING-5 | AM-SETUP-CUSTOMER-MARKETING-P08-REST | [DB] Forward migration V1053__marketing.sql: marketing for Marketing & CRM · Kiosk (1 tables) | 1 | Hrushikant Patkar | MarketingService | MIG-BASELINE MIG-IDENTITY MIG-MARKETING MIG-ORDERS MIG-PLATFORM VM-MIG-MARKETING | Tables: marketing.kiosk_assist_session. Source DDL: backend/tenant/010-marketing.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `marketing.kiosk_assist_session` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
15 | 3 | MIG-MARKETING-15 | AM-SETUP-CUSTOMER-MARKETING-P08-REST | [DB] Forward migration V1173__marketing.sql: marketing for Customer & Marketing · Venue Management (setup, the rest of the screens) (3 tables) | 2 | Hrushikant Patkar | MarketingService | MIG-BASELINE MIG-MARKETING VM-MIG-MARKETING | Tables: marketing.badge, marketing.loyalty_campaign, marketing.message_delivery. Source DDL: backend/tenant/010-marketing.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `marketing.badge`, `marketing.loyalty_campaign`, `marketing.message_delivery` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-TENANCY-ACCREDITATION-17 | AM-SETUP-CUSTOMER-MARKETING-P08-REST | [BE] TenancyService: listAccreditationProgrammes, updateAccreditationProgramme | 3 | Sanket Keluskar | TenancyService | MIG-ACCREDITATION-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listAccreditationProgrammes, updateAccreditationProgramme. Spec: contracts (accreditation) at the release tag, served by ADAM. Built for Customer & Marketing · Venue Management (setup, the rest of the screens); additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `accreditation#listAccreditationProgrammes`, `accreditation#updateAccreditationProgramme` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-TENANCY-ACCREDITATION-3 | AM-ADMISSION-ACCESS-P07-BLOCK-A | [BE] TenancyService: verifyAccreditationCredential | 1 | Tanmay Dukhande | TenancyService | MIG-ACCREDITATION-3 MIG-ACCREDITATION-4 PLATFORM-KERNEL SVC-TENANCY-ACCREDITATION-17 VM-MIG-ACCREDITATION | Operations: verifyAccreditationCredential. Spec: contracts (accreditation) at the release tag, served by ADAM. Built for Admission & Access · Scanner (Block A); additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `accreditation#verifyAccreditationCredential` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 2 | VM-MARKETING-SEGMENT-1 | AM-SETUP-CUSTOMER-MARKETING-P08-REST | [BE] MarketingService: listSegments | 1 | Chinmay Patkar | MarketingService | MIG-MARKETING PLATFORM-KERNEL SVC-MARKETING-CAMPAIGN-1 SVC-MARKETING-SEGMENT-1 | Operations beyond the first release: listSegments. Additive to MarketingService; its first-release owner (Pranay Shinde) reviews. Helper task: Pranay Shinde owns the service and reviews. Done when `marketing-crm#listSegments` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-AI-INSIGHTS-3 | AM-SETUP-CUSTOMER-MARKETING-P08-REST | [BE] AiService: listMarketingRecommendations | 1 | Sanket Keluskar | AiService | MIG-AI PLATFORM-KERNEL SVC-AI-INSIGHTS-1 | Operations: listMarketingRecommendations. Spec: contracts (ai) at the release tag, served by ADAM. Built for Customer & Marketing · Venue Management (setup, the rest of the screens); additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#listMarketingRecommendations` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-MARKETING-MARKETING-20 | AM-SETUP-CUSTOMER-MARKETING-P08-REST | [BE] MarketingService: activateChallenge, getChallenge, listChallenges, listForms | 5 | Surendra | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: activateChallenge, getChallenge, listChallenges, listForms. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Customer & Marketing · Venue Management (setup, the rest of the screens); additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#activateChallenge`, `marketing-crm#getChallenge`, `marketing-crm#listChallenges`, `marketing-crm#listForms` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-MARKETING-MESSAGE-7 | AM-SETUP-CUSTOMER-MARKETING-P08-REST | [BE] MarketingService: listMessageTemplates | 1 | Pranay Shinde | MarketingService | MIG-MARKETING PLATFORM-KERNEL SVC-MARKETING-MESSAGE-1 | Operations: listMessageTemplates. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Customer & Marketing · Venue Management (setup, the rest of the screens); additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#listMessageTemplates` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-CAMPAIGN-3 | AM-SETUP-CUSTOMER-MARKETING-P08-REST | [BE] MarketingService: getCampaign, getCampaignPerformance, testSendCampaign | 5 | Tanmay Dukhande | MarketingService | MIG-MARKETING MIG-MARKETING-15 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getCampaign, getCampaignPerformance, testSendCampaign. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Customer & Marketing · Venue Management (setup, the rest of the screens); additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#getCampaign`, `marketing-crm#getCampaignPerformance`, `marketing-crm#testSendCampaign` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 2 | VM-MARKETING-CAMPAIGN-1 | AM-MARKETING-CRM-P08-BLOCK-A | [BE] MarketingService: listCampaigns | 2 | Chinmay Patkar | MarketingService | MIG-MARKETING PLATFORM-KERNEL SVC-MARKETING-CAMPAIGN-1 SVC-MARKETING-CAMPAIGN-2 SVC-MARKETING-CAMPAIGN-3 SVC-MARKETING-SEGMENT-1 | Operations beyond the first release: listCampaigns. Additive to MarketingService; its first-release owner (Pranay Shinde) reviews. Helper task: Pranay Shinde owns the service and reviews. Done when `marketing-crm#listCampaigns` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-LOYALTY-7 | AM-SETUP-CUSTOMER-MARKETING-P08-REST | [BE] MarketingService: setLoyaltyCampaign | 1 | Deep Khanvilkar | MarketingService | MIG-MARKETING-15 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setLoyaltyCampaign. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Customer & Marketing · Venue Management (setup, the rest of the screens); additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#setLoyaltyCampaign` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-LOYALTY-6 | AM-SETUP-CUSTOMER-MARKETING-P08-REST | [BE] MarketingService: getLoyaltyRules, listBadges, listLoyaltyCampaigns, setBadge | 5 | Tanmay Dukhande | MarketingService | MIG-MARKETING MIG-MARKETING-15 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getLoyaltyRules, listBadges, listLoyaltyCampaigns, setBadge. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Customer & Marketing · Venue Management (setup, the rest of the screens); additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#getLoyaltyRules`, `marketing-crm#listBadges`, `marketing-crm#listLoyaltyCampaigns`, `marketing-crm#setBadge` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-MARKETING-21 | AM-SETUP-CUSTOMER-MARKETING-P08-REST | [BE] MarketingService: setCallDisposition, startKioskAssist | 3 | Sanket Keluskar | MarketingService | MIG-MARKETING MIG-MARKETING-5 MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setCallDisposition, startKioskAssist. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Customer & Marketing · Venue Management (setup, the rest of the screens); additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#setCallDisposition`, `marketing-crm#startKioskAssist` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-MARKETING-GUEST-4 | AM-SETUP-CUSTOMER-MARKETING-P08-REST | [BE] MarketingService: getGuestProfile | 2 | Deep Khanvilkar | MarketingService | MIG-MARKETING MIG-PII PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-IDENTITY-GUESTAUTH-1 SVC-IDENTITY-GUESTAUTH-2 SVC-IDENTITY-GUESTAUTH-3 SVC-IDENTITY-IDENTITY-4 SVC-MARKETING-CONSENT-1 SVC-MARKETING-CONSENT-3 SVC-MARKETING-CONSENT-7 SVC-MARKETING-GUEST-2 SVC-MARKETING-LOYALTY-2 SVC-MARKETING-MARKETING-11 SVC-MARKETING-MARKETING-5 SVC-MARKETING-MARKETING-6 SVC-MARKETING-MARKETING-7 SVC-ORDER-CART-1 SVC-ORDER-ORDERS-5 | Operations: getGuestProfile. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Customer & Marketing · Venue Management (setup, the rest of the screens); additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#getGuestProfile` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-MARKETING-SEGMENT-4 | AM-SETUP-CUSTOMER-MARKETING-P08-REST | [BE] MarketingService: previewSegmentDraft | 1 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-MARKETING-6 PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-MARKETING-CAMPAIGN-1 SVC-MARKETING-CONSENT-1 SVC-MARKETING-CONSENT-3 SVC-MARKETING-CONSENT-7 SVC-MARKETING-GUEST-2 SVC-MARKETING-MARKETING-6 SVC-MARKETING-MARKETING-7 SVC-MARKETING-SEGMENT-1 SVC-ORDER-CART-1 SVC-ORDER-ORDERS-5 | Operations: previewSegmentDraft. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Customer & Marketing · Venue Management (setup, the rest of the screens); additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#previewSegmentDraft` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | MIG-MARKETING-16 | AM-SETUP-CUSTOMER-MARKETING-P13-REST | [DB] Forward migration V1174__marketing.sql: marketing for Customer & Marketing · CMS (setup, the rest of the screens) (3 tables) | 2 | Hrushikant Patkar | MarketingService | MIG-BASELINE MIG-MARKETING VM-MIG-MARKETING | Tables: marketing.cookie_scan_finding, marketing.cookie_scan_policy, marketing.cookie_scan_run. Source DDL: backend/tenant/010-marketing.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `marketing.cookie_scan_finding`, `marketing.cookie_scan_policy`, `marketing.cookie_scan_run` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
16 | 3 | SVC-MARKETING-CONSENT-24 | AM-SETUP-CUSTOMER-MARKETING-P13-REST | [BE] MarketingService: listCookieTrackingDigital, listTrackingTechnologyCatalogue, recordCookieScan, setCookieScanPolicy | 8 | Surendra | MarketingService | MIG-MARKETING MIG-MARKETING-16 MIG-MARKETING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listCookieTrackingDigital, listTrackingTechnologyCatalogue, recordCookieScan, setCookieScanPolicy. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Customer & Marketing · CMS (setup, the rest of the screens); additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#listCookieTrackingDigital`, `marketing-crm#listTrackingTechnologyCatalogue`, `marketing-crm#recordCookieScan`, `marketing-crm#setCookieScanPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-MARKETING-CONSENT-23 | AM-SETUP-CUSTOMER-MARKETING-P13-REST | [BE] MarketingService: listCookieBannerPreference, listCookieScanFindings, listCookieScanPolicies, listCookieScans | 5 | Tanmay Dukhande | MarketingService | MIG-MARKETING MIG-MARKETING-16 PLATFORM-KERNEL SVC-MARKETING-CONSENT-24 SVC-MARKETING-CONSENT-4 | Operations: listCookieBannerPreference, listCookieScanFindings, listCookieScanPolicies, listCookieScans. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Customer & Marketing · CMS (setup, the rest of the screens); additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#listCookieBannerPreference`, `marketing-crm#listCookieScanFindings`, `marketing-crm#listCookieScanPolicies`, `marketing-crm#listCookieScans` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | MIG-MARKETING-9 | AM-SETUP-CUSTOMER-MARKETING-P12-REST | [DB] Forward migration V1056__marketing.sql: marketing for Marketing & CRM · Venue Management 3 of 5 (5 tables) | 3 | Hrushikant Patkar | MarketingService | MIG-BASELINE MIG-MARKETING VM-MIG-MARKETING | Tables: marketing.case_category, marketing.case_service_action, marketing.communication_provider, marketing.message_dispatch_attempt, marketing.service_queue. Source DDL: backend/tenant/010-marketing.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `marketing.case_category`, `marketing.case_service_action`, `marketing.communication_provider`, `marketing.message_dispatch_attempt`, `marketing.service_queue` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
17 | 3 | SVC-MARKETING-CASE-12 | AM-SETUP-CUSTOMER-MARKETING-P12-REST | [BE] MarketingService: listAgentWorkloadAvailability | 2 | Deep Khanvilkar | MarketingService | MIG-MARKETING MIG-MARKETING-6 MIG-MARKETING-9 PLATFORM-KERNEL SVC-MARKETING-CASE-1 SVC-MARKETING-CASE-7 SVC-MARKETING-CASE-8 SVC-MARKETING-FEEDBACK-1 SVC-MARKETING-MARKETING-18 SVC-MARKETING-MARKETING-19 SVC-MARKETING-MARKETING-21 SVC-MARKETING-MARKETING-3 SVC-MARKETING-MARKETING-4 SVC-MARKETING-MARKETING-5 SVC-MARKETING-MARKETING-6 | Operations: listAgentWorkloadAvailability. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Customer & Marketing · Support Console (setup, the rest of the screens); additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#listAgentWorkloadAvailability` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-AI-CONFIG-2 | AM-SETUP-AI-INTELLIGENCE-P08 | [BE] AiService: setAiPolicy | 2 | Chinmay Patkar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setAiPolicy. Spec: handoff/service-docs/backend/AiService.md#group-config Helper task: Tanmay Dukhande owns the service and reviews. Done when `ai#setAiPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-AI-FORECAST-1 | AM-SETUP-AI-INTELLIGENCE-P08 | [BE] AiService: createForecastScenario, decideOperationalRequirement, getAiVenueSettings, getForecast | 8 | Pranay Shinde | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createForecastScenario, decideOperationalRequirement, getAiVenueSettings, getForecast. Spec: handoff/service-docs/backend/AiService.md#group-forecast. Done when `ai#createForecastScenario`, `ai#decideOperationalRequirement`, `ai#getAiVenueSettings`, `ai#getForecast` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
9 | 3 | MIG-AI-10 | AM-SETUP-AI-INTELLIGENCE-P08-REST | [DB] Forward migration V1184__ai.sql: ai for AI & Intelligence · Venue Management (setup, the rest of the screens) (2 tables) | 2 | Hrushikant Patkar | AiService | MIG-AI MIG-BASELINE VM-MIG-AI | Tables: ai.index_failure, ai.spend_ceiling. Source DDL: backend/tenant/010-ai.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `ai.index_failure`, `ai.spend_ceiling` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
10 | 3 | MIG-WORKFORCE-6 | AM-SETUP-AI-INTELLIGENCE-P08-REST | [DB] Forward migration V1185__workforce.sql: workforce for AI & Intelligence · Venue Management (setup, the rest of the screens) (1 tables) | 1 | Hrushikant Patkar | TenancyService | MIG-BASELINE MIG-WORKFORCE VM-MIG-WORKFORCE | Tables: workforce.forecast_requirement. Source DDL: backend/tenant/010-workforce.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `workforce.forecast_requirement` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
10 | 3 | MIG-WORKFORCE-3 | AM-SETUP-AI-INTELLIGENCE-P08-REST | [DB] Forward migration V1162__workforce.sql: workforce for Resources & Capacity · Venue Management 2 of 4 (4 tables) | 3 | Hrushikant Patkar | TenancyService | MIG-BASELINE MIG-WORKFORCE VM-MIG-WORKFORCE | Tables: workforce.field_ownership, workforce.integration_source, workforce.staffing_rules, workforce.training_record. Source DDL: backend/tenant/010-workforce.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `workforce.field_ownership`, `workforce.integration_source`, `workforce.staffing_rules`, `workforce.training_record` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
10 | 3 | MIG-WORKFORCE-5 | AM-SETUP-AI-INTELLIGENCE-P08-REST | [DB] Forward migration V1164__workforce.sql: workforce for Workforce · Venue Management 1 of 2 (9 tables) | 5 | Hrushikant Patkar | TenancyService | MIG-APPROVALS MIG-BASELINE MIG-PLATFORM MIG-WORKFORCE VM-MIG-WORKFORCE | Tables: workforce.labour_budget, workforce.leave_balance, workforce.leave_request, workforce.leave_type, workforce.open_shift, workforce.position_requirement, workforce.shift_template, workforce.sync_conflict, workforce.sync_run. Source DDL: backend/tenant/010-workforce.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `workforce.labour_budget`, `workforce.leave_balance`, `workforce.leave_request`, `workforce.leave_type`, `workforce.open_shift`, `workforce.position_requirement`, `workforce.shift_template`, `workforce.sync_conflict` and 1 more runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
15 | 3 | MIG-MARKETING-17 | AM-SETUP-AI-INTELLIGENCE-P08-REST | [DB] Forward migration V1187__marketing.sql: marketing for AI & Intelligence · Venue Management (setup, the rest of the screens) (1 tables) | 1 | Hrushikant Patkar | MarketingService | MIG-BASELINE MIG-MARKETING VM-MIG-MARKETING | Tables: marketing.service_copilot_config. Source DDL: backend/tenant/010-marketing.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `marketing.service_copilot_config` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
16 | 3 | SVC-TENANCY-WORKFORCE-9 | AM-SETUP-AI-INTELLIGENCE-P08-REST | [BE] TenancyService: getStaffingCoverage | 1 | Tanmay Dukhande | TenancyService | MIG-WORKFORCE MIG-WORKFORCE-3 MIG-WORKFORCE-5 MIG-WORKFORCE-6 PLATFORM-KERNEL SVC-TENANCY-ROTA-1 | Operations: getStaffingCoverage. Spec: contracts (workforce) at the release tag, served by ADAM. Built for AI & Intelligence · Venue Management (setup, the rest of the screens); additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `workforce#getStaffingCoverage` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-AI-CONFIG-3 | AM-SETUP-AI-INTELLIGENCE-P08-REST | [BE] AiService: getAiSpendCeiling, setAiSpendCeiling | 2 | Tanmay Dukhande | AiService | MIG-AI-10 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getAiSpendCeiling, setAiSpendCeiling. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI & Intelligence · Venue Management (setup, the rest of the screens); additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#getAiSpendCeiling`, `ai#setAiSpendCeiling` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-AI-KNOWLEDGE-2 | AM-SETUP-AI-INTELLIGENCE-P08-REST | [BE] AiService: listAssistantProfiles, listKnowledgeGaps | 2 | Tanmay Dukhande | AiService | MIG-AI PLATFORM-KERNEL SVC-AI-ASSIST-1 SVC-AI-KNOWLEDGE-1 | Operations: listAssistantProfiles, listKnowledgeGaps. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI & Intelligence · Venue Management (setup, the rest of the screens); additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#listAssistantProfiles`, `ai#listKnowledgeGaps` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-CASE-13 | AM-SETUP-AI-INTELLIGENCE-P08-REST | [BE] MarketingService: setCustomerServiceCopilot | 2 | Chinmay Patkar | MarketingService | MIG-MARKETING-17 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setCustomerServiceCopilot. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for AI & Intelligence · Venue Management (setup, the rest of the screens); additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#setCustomerServiceCopilot` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-AI-RETRIEVAL-4 | AM-SETUP-AI-INTELLIGENCE-P08-REST | [BE] AiService: listIndexFailures, listKnowledgeCollections | 1 | Chinmay Patkar | AiService | MIG-AI MIG-AI-10 PLATFORM-KERNEL SVC-AI-RETRIEVAL-1 | Operations: listIndexFailures, listKnowledgeCollections. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI & Intelligence · Venue Management (setup, the rest of the screens); additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#listIndexFailures`, `ai#listKnowledgeCollections` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-MARKETING-GENERAL-1 | AM-SETUP-AI-INTELLIGENCE-P08-REST | [BE] MarketingService: getCustomerServiceCopilot | 1 | Deep Khanvilkar | MarketingService | MIG-MARKETING-17 PLATFORM-KERNEL SVC-MARKETING-CASE-13 | Operations: getCustomerServiceCopilot. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for AI & Intelligence · Venue Management (setup, the rest of the screens); additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#getCustomerServiceCopilot` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-AI-CONFIG-1 | AM-SETUP-AI-INTELLIGENCE-P09 | [BE] AiService: getAiByokEnablement, getAiPolicy, listAiProviders, setAiByokEnablement | 5 | Deep Khanvilkar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getAiByokEnablement, getAiPolicy, listAiProviders, setAiByokEnablement. Spec: handoff/service-docs/backend/AiService.md#group-config Helper task: Tanmay Dukhande owns the service and reviews. Done when `ai#getAiByokEnablement`, `ai#getAiPolicy`, `ai#listAiProviders`, `ai#setAiByokEnablement` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-AI-FORECAST-3 | AM-SETUP-AI-INTELLIGENCE-P09 | [BE] AiService: listOperationalRequirements, listVenueHistoryImports, publishForecastVersion, runForecast | 8 | Deep Khanvilkar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listOperationalRequirements, listVenueHistoryImports, publishForecastVersion, runForecast. Spec: handoff/service-docs/backend/AiService.md#group-forecast. Done when `ai#listOperationalRequirements`, `ai#listVenueHistoryImports`, `ai#publishForecastVersion`, `ai#runForecast` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-AI-FORECAST-4 | AM-SETUP-AI-INTELLIGENCE-P09 | [BE] AiService: setAiVenueSettings, setForecastDefinition | 5 | Deep Khanvilkar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setAiVenueSettings, setForecastDefinition. Spec: handoff/service-docs/backend/AiService.md#group-forecast Helper task: Tanmay Dukhande owns the service and reviews. Done when `ai#setAiVenueSettings`, `ai#setForecastDefinition` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-AI-GOVERNANCE-3 | AM-SETUP-AI-INTELLIGENCE-P09 | [BE] AiService: publishAiGovernancePolicy, revokeAiPolicyException, simulateAiGovernancePolicy | 5 | Deep Khanvilkar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: publishAiGovernancePolicy, revokeAiPolicyException, simulateAiGovernancePolicy. Spec: handoff/service-docs/backend/AiService.md#group-governance Helper task: Tanmay Dukhande owns the service and reviews. Done when `ai#publishAiGovernancePolicy`, `ai#revokeAiPolicyException`, `ai#simulateAiGovernancePolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-AI-MODELS-1 | AM-SETUP-AI-INTELLIGENCE-P09 | [BE] AiService: listAiEvaluations, listAiTrainingRuns, promoteAiRelease, publishPromptTemplate | 8 | Pranay Shinde | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listAiEvaluations, listAiTrainingRuns, promoteAiRelease, publishPromptTemplate. Spec: handoff/service-docs/backend/AiService.md#group-models. Done when `ai#listAiEvaluations`, `ai#listAiTrainingRuns`, `ai#promoteAiRelease`, `ai#publishPromptTemplate` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-AI-MODELS-2 | AM-SETUP-AI-INTELLIGENCE-P09 | [BE] AiService: rollbackAiRelease, runAiEvaluation, setAiModel | 8 | Pranay Shinde | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: rollbackAiRelease, runAiEvaluation, setAiModel. Spec: handoff/service-docs/backend/AiService.md#group-models. Done when `ai#rollbackAiRelease`, `ai#runAiEvaluation`, `ai#setAiModel` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-AI-FORECAST-7 | AM-SETUP-AI-INTELLIGENCE-P08-REST | [BE] AiService: listForecastDefinitions | 1 | Tanmay Dukhande | AiService | MIG-AI PLATFORM-KERNEL SVC-AI-FORECAST-4 SVC-AI-MODELS-1 SVC-AI-MODELS-2 | Operations: listForecastDefinitions. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI & Intelligence · Venue Management (setup, the rest of the screens); additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#listForecastDefinitions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 1 | SVC-AI-MONITORING-1 | AM-SETUP-AI-INTELLIGENCE-P09 | [BE] AiService: containAiIncident, listAiGovernanceAlerts, listAiIncidents, openAiIncident | 8 | Tanmay Dukhande | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: containAiIncident, listAiGovernanceAlerts, listAiIncidents, openAiIncident. Spec: handoff/service-docs/backend/AiService.md#group-monitoring. Done when `ai#containAiIncident`, `ai#listAiGovernanceAlerts`, `ai#listAiIncidents`, `ai#openAiIncident` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
9 | 3 | MIG-AI-11 | AM-SETUP-AI-INTELLIGENCE-P09-REST | [DB] Forward migration V1188__ai.sql: ai for AI & Intelligence · TICVAI Console (setup, the rest of the screens) (1 tables) | 1 | Hrushikant Patkar | AiService | MIG-AI MIG-BASELINE MIG-IDENTITY VM-MIG-AI | Tables: ai.forecast_export. Source DDL: backend/tenant/010-ai.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `ai.forecast_export` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-AI-FORECAST-8 | AM-SETUP-AI-INTELLIGENCE-P09-REST | [BE] AiService: exportForecastVersion | 2 | Sanket Keluskar | AiService | MIG-AI MIG-AI-11 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: exportForecastVersion. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI & Intelligence · TICVAI Console (setup, the rest of the screens); additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#exportForecastVersion` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-AI-MONITORING-5 | AM-SETUP-AI-INTELLIGENCE-P09-REST | [BE] AiService: closeAiIncident | 2 | Sanket Keluskar | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: closeAiIncident. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI & Intelligence · TICVAI Console (setup, the rest of the screens); additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#closeAiIncident` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-AI-ACTIONS-7 | AM-SETUP-AI-INTELLIGENCE-P09-REST | [BE] AiService: listAiTools | 1 | Tanmay Dukhande | AiService | MIG-AI-3 PLATFORM-KERNEL | Operations: listAiTools. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI & Intelligence · TICVAI Console (setup, the rest of the screens); additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#listAiTools` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-AI-MODELS-3 | AM-SETUP-AI-INTELLIGENCE-P09-REST | [BE] AiService: listAiModels, listPromptTemplates | 3 | Tanmay Dukhande | AiService | MIG-AI PLATFORM-KERNEL SVC-AI-MODELS-1 SVC-AI-MODELS-2 | Operations: listAiModels, listPromptTemplates. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI & Intelligence · TICVAI Console (setup, the rest of the screens); additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#listAiModels`, `ai#listPromptTemplates` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-REPORTING-NATURALLANGUAGE-2 | AM-REPORTING-P08-BLOCK-A | [BE] ReportingService: runSemanticQuery | 2 | Chinmay Patkar | ReportingService | MIG-REPORTING PLATFORM-KERNEL SVC-REPORTING-CATALOGUE-1 SVC-REPORTING-CATALOGUE-2 SVC-REPORTING-NATURALLANGUAGE-1 SVC-REPORTING-REPORTING-1 SVC-REPORTING-REPORTING-2 | Operations: runSemanticQuery. Spec: contracts (reporting) at the release tag, served by ADAM. Built for Reporting · Venue Management (Block A); additive to ReportingService, whose first-release owner (Tanmay Dukhande) reviews. Done when `reporting#runSemanticQuery` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-REPORTING-REPORTING-6 | AM-REPORTING-P08-BLOCK-A | [BE] ReportingService: getServiceSummary, listAlertRules | 2 | Chinmay Patkar | ReportingService | MIG-REPORTING PLATFORM-KERNEL SVC-REPORTING-REPORTING-1 | Operations: getServiceSummary, listAlertRules. Spec: contracts (reporting) at the release tag, served by ADAM. Built for Reporting · Venue Management (Block A); additive to ReportingService, whose first-release owner (Tanmay Dukhande) reviews. Done when `reporting#getServiceSummary`, `reporting#listAlertRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-AI-INSIGHTS-4 | AM-REPORTING-P16-BLOCK-A | [BE] AiService: listAiInsights | 2 | Sanket Keluskar | AiService | MIG-AI PLATFORM-KERNEL SVC-AI-INSIGHTS-1 | Operations: listAiInsights. Spec: contracts (ai) at the release tag, served by ADAM. Built for Reporting · Analytics (Block A); additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#listAiInsights` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-REPORTING-DASHBOARD-3 | AM-REPORTING-P16-BLOCK-A | [BE] ReportingService: getCommandCentre | 1 | Tanmay Dukhande | ReportingService | MIG-REPORTING PLATFORM-KERNEL SVC-REPORTING-DASHBOARD-1 SVC-REPORTING-DASHBOARD-2 SVC-REPORTING-REPORTING-1 | Operations: getCommandCentre. Spec: contracts (reporting) at the release tag, served by ADAM. Built for Reporting · Analytics (Block A); additive to ReportingService, whose first-release owner (Tanmay Dukhande) reviews. Done when `reporting#getCommandCentre` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 2 | VM-REPORTING-SCHEDULE-1 | AM-REPORTING-API-BLOCK-A-COMPLETION | [BE] ReportingService: createReportSchedule | 2 | Chinmay Patkar | ReportingService | MIG-REPORTING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-11 SVC-ACCESS-ACCESS-12 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-5 SVC-ACCESS-ACCESS-58 SVC-ACCESS-ACCESS-6 SVC-ACCESS-ACCESS-60 SVC-ACCESS-ACCESS-7 SVC-ACCESS-ACCESS-9 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-ACCESS-ACCESSPOINT-3 SVC-ACCESS-VALIDATION-2 SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-2 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-CATALOGUE-6 SVC-CATALOGUE-CATALOGUE-7 SVC-CATALOGUE-CATEGORY-1 SVC-CATALOGUE-COUPON-1 SVC-CATALOGUE-COUPON-2 SVC-CATALOGUE-DRAFTED-1 SVC-CATALOGUE-DRAFTED-3 SVC-CATALOGUE-DRAFTED-4 SVC-CATALOGUE-DRAFTED-5 SVC-CATALOGUE-DRAFTED-56 SVC-CATALOGUE-ENTITLEMENT-1 SVC-CATALOGUE-EVALUATION-1 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENT-4 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-EVENTS-2 SVC-CATALOGUE-HOLD-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-CATALOGUE-PRICING-1 SVC-CATALOGUE-PRODUCT-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTIONS-1 SVC-CATALOGUE-PROMOTIONS-2 SVC-CATALOGUE-SEATING-1 SVC-CATALOGUE-SEATMAP-1 SVC-CATALOGUE-SEATMAP-2 SVC-CATALOGUE-VOUCHER-1 SVC-FNB-BILL-1 SVC-FNB-FNB-1 SVC-FNB-FNB-10 SVC-FNB-FNB-11 SVC-FNB-FNB-12 SVC-FNB-FNB-13 SVC-FNB-FNB-16 SVC-FNB-FNB-17 SVC-FNB-FNB-18 SVC-FNB-FNB-2 SVC-FNB-FNB-20 SVC-FNB-FNB-3 SVC-FNB-FNB-4 SVC-FNB-FNB-5 SVC-FNB-FNB-6 SVC-FNB-FNB-7 SVC-FNB-FNB-8 SVC-FNB-FNB-9 SVC-FNB-GUESTORDERING-1 SVC-FNB-GUESTORDERING-3 SVC-FNB-GUESTORDERING-4 SVC-FNB-KITCHEN-1 SVC-FNB-MENU-1 SVC-FNB-MODIFIER-1 SVC-FNB-ORDER-1 SVC-FNB-PRODUCTION-1 SVC-FNB-PRODUCTION-2 SVC-FNB-SERVICE-1 SVC-FNB-TABLE-1 SVC-FNB-TABLE-2 SVC-FNB-TABLE-3 SVC-INVENTORY-INVENTORY-3 SVC-INVENTORY-ITEM-1 SVC-INVENTORY-RECEIPT-1 SVC-INVENTORY-STOCK-2 SVC-LEDGER-ACCOUNTS-1 SVC-LEDGER-ACCOUNTS-2 SVC-LEDGER-FINANCE-1 SVC-LEDGER-FINANCE-3 SVC-LEDGER-FISCAL-1 SVC-LEDGER-LEDGER-1 SVC-LEDGER-LEDGER-3 SVC-LEDGER-TAX-1 SVC-LEDGER-TAX-2 SVC-LEDGER-TAX-3 SVC-LEDGER-TAX-4 SVC-LEDGER-TAX-5 SVC-LEDGER-TAX-6 SVC-LEDGER-VARIANCE-1 SVC-ORDER-B2B-1 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-CART-3 SVC-ORDER-CASH-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-1 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-13 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-2 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-PAYMENTS-17 SVC-ORDER-PAYMENTS-18 SVC-ORDER-PAYMENTS-2 SVC-ORDER-PAYMENTS-6 SVC-ORDER-POLICY-1 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SHIFT-1 SVC-ORDER-SHIFT-3 SVC-ORDER-SHIFT-4 SVC-ORDER-SHIFT-5 SVC-ORDER-SHIFT-6 SVC-ORDER-SHIFT-7 SVC-ORDER-SYNC-1 SVC-RETAIL-FLOOR-1 SVC-RETAIL-FLOOR-2 SVC-RETAIL-MERCHANDISE-1 SVC-RETAIL-RETURN-1 SVC-RETAIL-SALE-1 SVC-WALLET-CARD-1 SVC-WALLET-RETAIL-1 SVC-WALLET-RETAIL-2 SVC-WALLET-WALLET-1 SVC-WALLET-WALLET-2 SVC-WALLET-WALLET-5 SVC-WALLET-WALLET-8 SVC-WALLET-WALLET-9 VM-ACCESS-ACCESS-1 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-EVENT-1 VM-CATALOGUE-PRODUCT-1 VM-CATALOGUE-UPSELL-1 VM-FNB-FNB-1 VM-FNB-MENU-1 VM-FNB-ORDER-1 VM-FNB-PRODUCTION-1 VM-INVENTORY-INVENTORY-1 VM-INVENTORY-MOVEMENT-1 VM-INVENTORY-PURCHASEORDER-1 VM-INVENTORY-TRANSFER-1 VM-LEDGER-FINANCE-1 VM-LEDGER-FISCAL-1 VM-LEDGER-LEDGER-1 VM-LEDGER-SETTLEMENT-1 VM-LEDGER-SETTLEMENT-2 VM-MIG-REPORTING VM-ORDER-ORDERS-1 VM-ORDER-ORDERS-2 VM-ORDER-ORDERS-3 VM-ORDER-REFUND-1 VM-ORDER-SHIFT-1 VM-ORDER-SYNC-1 VM-RETAIL-RETAIL-1 VM-WALLET-WALLET-1 | Operations beyond the first release: createReportSchedule. Additive to ReportingService; its first-release owner (Tanmay Dukhande) reviews. Helper task: Tanmay Dukhande owns the service and reviews. Done when `reporting#createReportSchedule` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-REPORTING-SCHEDULE-2 | AM-REPORTING-API-BLOCK-A-COMPLETION | [BE] ReportingService: deleteReportSchedule, listReportSchedules, updateReportSchedule | 5 | Surendra | ReportingService | MIG-REPORTING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-REPORTING | Operations: deleteReportSchedule, listReportSchedules, updateReportSchedule. Spec: contracts (reporting) at the release tag, served by ADAM. Built for Reporting · API only (Block A completion); additive to ReportingService, whose first-release owner (Tanmay Dukhande) reviews. Done when `reporting#deleteReportSchedule`, `reporting#listReportSchedules`, `reporting#updateReportSchedule` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | EDGE-WAITING-ROOM | AM-FOUNDATION-API-PLATFORM | [BE] The on-sale waiting room: Redis positions, the cached page, the release controller, admission tokens | 8 | Tanmay Dukhande |  | KERNEL-TENANT-LIMITS PLATFORM-KERNEL | The on-sale waiting room: Redis positions, the cached page, the release controller, admission tokens. Builds: `operation catalogue#enterWaitingRoom`, `operation catalogue#getWaitingRoomPosition`, `operation catalogue#setWaitingRoomSetting`, `adr ADR-0064`, `adr ADR-0066`. ADR-0066 (accepted 1 October; B1, or Block A if an on-sale is booked in Block A): enterWaitingRoom gives a position from a Redis counter with no database write; the static branded waiting page is served from Front Door's cache and polls getWaitingRoomPosition; a release controller admits guests per second from the health of commerce (latency and the 429 rate, ADR-0064); an admitted guest gets a short-lived signed token (tenant, performance, expiry, unique id; key in Key Vault) that middleware checks by signature, with no database read, on addCartLine and acquireInventoryHold from guest channels only (till, kiosk and workstation holds are exempt, amendment of 1 October); activation follows the performance's onSaleFrom/onSaleTo or setWaitingRoomSetting. Done when: with the room on, a guest cart hold without a token is refused 403 admission-required, one with a valid token succeeds, a forged or expired token or one for another performance is refused, a till hold needs no token, and the release rate drops when commerce latency rises.
12 | 3 | EDGE-WAITING-ROOM-LOAD | AM-FOUNDATION-API-PLATFORM | [BE] Load test the waiting room at 50,000 arrivals in the burst environment | 3 | Tanmay Dukhande |  | EDGE-WAITING-ROOM | Load test the waiting room at 50,000 arrivals in the burst environment. Builds: `adr ADR-0035`, `adr ADR-0066`. ADR-0066 item 4 as amended on 6 October (the client's sizing benchmarks, CHG-R4-017), before the first large sale: 50,000 simultaneous arrivals in the opening seconds against a burst environment (ADR-0035) with the waiting room on, the sale behind the room held at 3,000 concurrent B2C users and then stepped above it to show the benchmark is not a limit (docs/active/block-test-strategy.md, Load scenarios), recording position latency, the Front Door cache hit rate, the release rate the controller holds, commerce p95 and 429s, and the relay lag while admitted guests buy (ADR-0058 amendment: 3,500 events a second). Done when: all 50,000 get a position without a database write, admitted guests buy with commerce p95 inside its target at 3,000 concurrent and above, no cart hold succeeds without a token, and the results are recorded against the sizing figures.
11 | 3 | SVC-IDENTITY-IDENTITY-5 | AM-IDENTITY-SECURITY-P06 | [BE] IdentityService: logout | 2 | Sanket Keluskar | IdentityService | MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: logout. Spec: contracts (identity) at the release tag, served by ADAM. Built for Identity & Security · Staff App; additive to IdentityService, whose first-release owner (Pranay Shinde) reviews. Done when `identity#logout` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
8 | 3 | MIG-APPROVALS-2 | AM-IDENTITY-SECURITY-P08 | [DB] Forward migration V1007__approvals.sql: approvals for Identity & Security · Venue Management (2 tables) | 2 | Hrushikant Patkar | TenancyService | MIG-APPROVALS MIG-BASELINE VM-MIG-APPROVALS | Tables: approvals.workflow_definition, approvals.workflow_version. Source DDL: backend/tenant/010-approvals.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `approvals.workflow_definition`, `approvals.workflow_version` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 2 | VM-IDENTITY-SESSION-1 | AM-IDENTITY-SECURITY-P08 | [BE] IdentityService: revokeAllSessions | 1 | Chinmay Patkar | IdentityService | MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: revokeAllSessions. Additive to IdentityService; its first-release owner (Pranay Shinde) reviews. Helper task: Pranay Shinde owns the service and reviews. Done when `identity#revokeAllSessions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-TENANCY-WORKFORCE-1 | AM-IDENTITY-SECURITY-P08 | [BE] TenancyService: listJobTitles, listWorkAssignments, setJobTitle, setWorkAssignment | 5 | Deep Khanvilkar | TenancyService | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-WORKFORCE | Operations beyond the first release: listJobTitles, listWorkAssignments, setJobTitle, setWorkAssignment. Additive to TenancyService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `workforce#listJobTitles`, `workforce#listWorkAssignments`, `workforce#setJobTitle`, `workforce#setWorkAssignment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-IDENTITY-ADMINISTRATION-3 | AM-IDENTITY-SECURITY-P08 | [BE] IdentityService: createAccessReviewCampaign, createAuthorisationPolicy, createEmergencyAccessOverride, decideAccessReviewItem | 8 | Surendra | IdentityService | MIG-IDENTITY MIG-IDENTITY-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-IDENTITY VM-MIG-WORKFORCE | Operations: createAccessReviewCampaign, createAuthorisationPolicy, createEmergencyAccessOverride, decideAccessReviewItem. Spec: contracts (identity) at the release tag, served by ADAM. Built for Identity & Security · Venue Management; additive to IdentityService, whose first-release owner (Pranay Shinde) reviews. Done when `identity#createAccessReviewCampaign`, `identity#createAuthorisationPolicy`, `identity#createEmergencyAccessOverride`, `identity#decideAccessReviewItem` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-IDENTITY-ADMINISTRATION-4 | AM-IDENTITY-SECURITY-P08 | [BE] IdentityService: evaluateAccess, getAuthorisationPolicy, getAuthorisationPolicyBundle, getPrincipalModuleAccess | 5 | Deep Khanvilkar | IdentityService | MIG-IDENTITY-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-IDENTITY | Operations: evaluateAccess, getAuthorisationPolicy, getAuthorisationPolicyBundle, getPrincipalModuleAccess. Spec: contracts (identity) at the release tag, served by ADAM. Built for Identity & Security · Venue Management; additive to IdentityService, whose first-release owner (Pranay Shinde) reviews. Done when `identity#evaluateAccess`, `identity#getAuthorisationPolicy`, `identity#getAuthorisationPolicyBundle`, `identity#getPrincipalModuleAccess` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-IDENTITY-ADMINISTRATION-6 | AM-IDENTITY-SECURITY-P08 | [BE] IdentityService: listAuthorisationPolicyTemplates, listModuleCapabilities, restoreAuthorisationPolicyVersion, setAuthorisationPolicyState | 5 | Surendra | IdentityService | MIG-IDENTITY-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listAuthorisationPolicyTemplates, listModuleCapabilities, restoreAuthorisationPolicyVersion, setAuthorisationPolicyState. Spec: contracts (identity) at the release tag, served by ADAM. Built for Identity & Security · Venue Management; additive to IdentityService, whose first-release owner (Pranay Shinde) reviews. Done when `identity#listAuthorisationPolicyTemplates`, `identity#listModuleCapabilities`, `identity#restoreAuthorisationPolicyVersion`, `identity#setAuthorisationPolicyState` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-IDENTITY-ADMINISTRATION-7 | AM-IDENTITY-SECURITY-P08 | [BE] IdentityService: setPrincipalModuleAccess, simulateAuthorisationPolicy, updateAuthorisationPolicy | 5 | Deep Khanvilkar | IdentityService | MIG-IDENTITY-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-IDENTITY | Operations: setPrincipalModuleAccess, simulateAuthorisationPolicy, updateAuthorisationPolicy. Spec: contracts (identity) at the release tag, served by ADAM. Built for Identity & Security · Venue Management; additive to IdentityService, whose first-release owner (Pranay Shinde) reviews. Done when `identity#setPrincipalModuleAccess`, `identity#simulateAuthorisationPolicy`, `identity#updateAuthorisationPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-IDENTITY-IDENTITY-6 | AM-IDENTITY-SECURITY-P08 | [BE] IdentityService: decideGuestIdentityVerification, getMembership, listCustomerMemberships, listGuestIdentityVerifications | 5 | Surendra | IdentityService | MIG-IDENTITY MIG-IDENTITY-3 MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: decideGuestIdentityVerification, getMembership, listCustomerMemberships, listGuestIdentityVerifications. Spec: contracts (identity) at the release tag, served by ADAM. Built for Identity & Security · Venue Management; additive to IdentityService, whose first-release owner (Pranay Shinde) reviews. Done when `identity#decideGuestIdentityVerification`, `identity#getMembership`, `identity#listCustomerMemberships`, `identity#listGuestIdentityVerifications` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-APPROVALS-2 | AM-IDENTITY-SECURITY-P08 | [BE] TenancyService: approveVersioningGovernance | 3 | Sanket Keluskar | TenancyService | MIG-APPROVALS MIG-APPROVALS-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: approveVersioningGovernance. Spec: contracts (approvals) at the release tag, served by ADAM. Built for Identity & Security · Venue Management; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `approvals#approveVersioningGovernance` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-IDENTITY-ADMINISTRATION-5 | AM-IDENTITY-SECURITY-P08 | [BE] IdentityService: listAccessDecisions, listAuthorisationPolicies, listAuthorisationPolicyEffectiveness, listAuthorisationPolicyHistory | 3 | Deep Khanvilkar | IdentityService | MIG-IDENTITY-3 PLATFORM-KERNEL SVC-IDENTITY-ADMINISTRATION-3 SVC-IDENTITY-ADMINISTRATION-4 SVC-IDENTITY-ADMINISTRATION-6 SVC-IDENTITY-ADMINISTRATION-7 VM-MIG-IDENTITY | Operations: listAccessDecisions, listAuthorisationPolicies, listAuthorisationPolicyEffectiveness, listAuthorisationPolicyHistory. Spec: contracts (identity) at the release tag, served by ADAM. Built for Identity & Security · Venue Management; additive to IdentityService, whose first-release owner (Pranay Shinde) reviews. Done when `identity#listAccessDecisions`, `identity#listAuthorisationPolicies`, `identity#listAuthorisationPolicyEffectiveness`, `identity#listAuthorisationPolicyHistory` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | VM-ADM-247 | AM-IDENTITY-SECURITY-P08 | [BE] ADM-247 Versioning, Governance, Approval & Publication | 3 | Sanket Keluskar |  | SETUP-CLIENTS SVC-IDENTITY-MFA-1 SVC-IDENTITY-MFA-2 SVC-TENANCY-APPROVALS-2 | Control how rules and workflows move safely from configuration into production. Board 1 configured the rules and workflows. Board 2 is the live operational layer where TICVAI executes, monitors, manages, troubleshoots, analyzes, and optimizes those workflows across the entire platform. Module: Platform. App: Venue Management. Done when `ADM-247` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
14 | 2 | VM-MARKETING-MARKETING-2 | AM-IDENTITY-SECURITY-P08 | [BE] MarketingService: matchLostItem | 2 | Chinmay Patkar | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: matchLostItem. Additive to MarketingService; its first-release owner (Pranay Shinde) reviews. Helper task: Pranay Shinde owns the service and reviews. Done when `marketing-crm#matchLostItem` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
8 | 3 | MIG-REPORTING-2 | AM-IDENTITY-SECURITY-P16 | [DB] Forward migration V1063__reporting.sql: reporting for Identity & Security · Analytics (1 tables) | 1 | Hrushikant Patkar | ReportingService | MIG-BASELINE MIG-REPORTING VM-MIG-REPORTING | Tables: reporting.analytics_governance_policy. Source DDL: backend/tenant/010-reporting.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `reporting.analytics_governance_policy` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
12 | 3 | SVC-REPORTING-REPORTING-3 | AM-IDENTITY-SECURITY-P16 | [BE] ReportingService: getAnalyticsGovernancePolicy | 1 | Tanmay Dukhande | ReportingService | MIG-REPORTING-2 PLATFORM-KERNEL | Operations: getAnalyticsGovernancePolicy. Spec: contracts (reporting) at the release tag, served by ADAM. Built for Identity & Security · Analytics; additive to ReportingService, whose first-release owner (Tanmay Dukhande) reviews. Done when `reporting#getAnalyticsGovernancePolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | MIG-PAYMENTS-2 | AM-IDENTITY-SECURITY-P09-2 | [DB] Forward migration V1070__payments.sql: payments for Identity & Security · TICVAI Console 2 of 3 (1 tables) | 1 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-PAYMENTS VM-MIG-PAYMENTS | Tables: payments.reconciliation_source. Source DDL: backend/tenant/010-payments.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `payments.reconciliation_source` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
10 | 3 | SVC-IDENTITY-IDENTITY-8 | AM-IDENTITY-SECURITY-P09-2 | [BE] IdentityService: listPermissions | 1 | Chinmay Patkar | IdentityService | MIG-IDENTITY-3 PLATFORM-KERNEL | Operations: listPermissions. Spec: contracts (identity) at the release tag, served by ADAM. Built for Identity & Security · TICVAI Console 2 of 3; additive to IdentityService, whose first-release owner (Pranay Shinde) reviews. Done when `identity#listPermissions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-IDENTITY-SESSION-2 | AM-IDENTITY-SECURITY-P09-2 | [BE] IdentityService: endOwnSession, listOwnSessions | 3 | Sanket Keluskar | IdentityService | MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: endOwnSession, listOwnSessions. Spec: contracts (identity) at the release tag, served by ADAM. Built for Identity & Security · TICVAI Console 2 of 3; additive to IdentityService, whose first-release owner (Pranay Shinde) reviews. Done when `identity#endOwnSession`, `identity#listOwnSessions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-ORDER-PAYMENTS-3 | AM-IDENTITY-SECURITY-P09-2 | [BE] OrderService: listReconciliationSources | 1 | Tanmay Dukhande | OrderService | MIG-PAYMENTS-2 PLATFORM-KERNEL | Operations: listReconciliationSources. Spec: contracts (payments) at the release tag, served by ADAM. Built for Identity & Security · TICVAI Console 2 of 3; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `payments#listReconciliationSources` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-AI-AUDIT-1 | AM-IDENTITY-SECURITY-P09-2 | [BE] AiService: getAiDecisionTrace, searchAiDecisions | 5 | Tanmay Dukhande | AiService | MIG-AI MIG-AI-2 PLATFORM-KERNEL SVC-AI-ACTIONS-1 SVC-AI-AI-1 SVC-AI-AI-2 SVC-AI-AI-3 SVC-AI-ASSIST-1 SVC-AI-CONFIGURE-1 SVC-AI-FORECAST-1 SVC-AI-FORECAST-3 SVC-AI-GENERATE-1 SVC-AI-GENERATE-2 SVC-AI-GOVERNANCE-1 SVC-AI-GOVERNANCE-2 SVC-AI-GOVERNANCE-3 SVC-AI-INSIGHTS-1 SVC-AI-MODELS-1 SVC-AI-MODELS-2 SVC-AI-MONITORING-1 SVC-AI-RECOMMEND-1 SVC-AI-RETRIEVAL-1 SVC-REPORTING-NATURALLANGUAGE-1 | Operations: getAiDecisionTrace, searchAiDecisions. Spec: contracts (ai) at the release tag, served by ADAM. Built for Identity & Security · TICVAI Console 2 of 3; additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#getAiDecisionTrace`, `ai#searchAiDecisions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
6 | 3 | MIG-CONTROL-2 | AM-IDENTITY-SECURITY-P09-3 | [DB] Forward migration V1065__control.sql: control for Identity & Security · TICVAI Console 3 of 3 (3 tables) | 2 | Hrushikant Patkar | PlatformService | MIG-BASELINE MIG-CONTROL VM-MIG-CONTROL | Tables: control.billing_entity, control.onboarding_application, control.venue_type_template. Source DDL: backend/control/010-control.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `control.billing_entity`, `control.onboarding_application`, `control.venue_type_template` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
10 | 3 | SVC-IDENTITY-PROSPECTAUTH-1 | AM-IDENTITY-SECURITY-P09-3 | [BE] IdentityService: startProspectSignup, verifyProspectSignupCode | 2 | Tanmay Dukhande | IdentityService | MIG-BASELINE PLATFORM-KERNEL | Operations: startProspectSignup, verifyProspectSignupCode. Spec: contracts (identity) at the release tag, served by ADAM. Built for Identity & Security · TICVAI Console 3 of 3; additive to IdentityService, whose first-release owner (Pranay Shinde) reviews. Done when `identity#startProspectSignup`, `identity#verifyProspectSignupCode` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-SUBSCRIPTION-2 | AM-IDENTITY-SECURITY-P09-3 | [BE] PlatformService: submitOnboardingApplication | 3 | Sanket Keluskar | PlatformService | MIG-CONTROL-2 MIG-SUBSCRIPTION PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: submitOnboardingApplication. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Identity & Security · TICVAI Console 3 of 3; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#submitOnboardingApplication` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-IDENTITY-ADMINISTRATION-8 | AM-IDENTITY-SECURITY-P10 | [BE] IdentityService: createDelegatedAccess, deleteDelegatedAccess, listDelegatedAccess | 3 | Sanket Keluskar | IdentityService | MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createDelegatedAccess, deleteDelegatedAccess, listDelegatedAccess. Spec: contracts (identity) at the release tag, served by ADAM. Built for Identity & Security · Partner Portal; additive to IdentityService, whose first-release owner (Pranay Shinde) reviews. Done when `identity#createDelegatedAccess`, `identity#deleteDelegatedAccess`, `identity#listDelegatedAccess` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | SVC-PLATFORM-DRAFTED-1 | AM-IDENTITY-SECURITY-P10 | [BE] PlatformService: approveBookingLimitCommercial, approvePartnerStatuLifecycle | 8 | Tanmay Dukhande | PlatformService | MIG-APPROVALS MIG-CONTROL MIG-CONTROL-3 MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: approveBookingLimitCommercial, approvePartnerStatuLifecycle. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Identity & Security · Partner Portal; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#approveBookingLimitCommercial`, `subscription#approvePartnerStatuLifecycle` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | MIG-ACCESS-2 | AM-TENANCY-VENUES-P08 | [DB] Forward migration V1078__access.sql: access for Tenancy & Venues · Venue Management 1 of 3 (1 tables) | 1 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-BASELINE VM-MIG-ACCESS | Tables: access.access_area. Source DDL: backend/tenant/010-access.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `access.access_area` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 2 | VM-TENANCY-DEVICES-1 | AM-TENANCY-VENUES-P08 | [BE] TenancyService: createDeviceFirmware, getDeviceFirmware, issueDeviceCredential, listDeviceFirmware | 5 | Deep Khanvilkar | TenancyService | MIG-ASSETS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-TENANCY | Operations beyond the first release: createDeviceFirmware, getDeviceFirmware, issueDeviceCredential, listDeviceFirmware. Additive to TenancyService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `tenancy#createDeviceFirmware`, `tenancy#getDeviceFirmware`, `tenancy#issueDeviceCredential`, `tenancy#listDeviceFirmware` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-TENANCY-DEVICES-2 | AM-TENANCY-VENUES-P08 | [BE] TenancyService: revokeDeviceCredential, rollbackDeviceFirmware, setDeviceFirmwareStatus, startDeviceFirmwareRollout | 8 | Pranay Shinde | TenancyService | MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-TENANCY | Operations beyond the first release: revokeDeviceCredential, rollbackDeviceFirmware, setDeviceFirmwareStatus, startDeviceFirmwareRollout. Additive to TenancyService; its first-release owner (Hrushikant Patkar) reviews. Done when `tenancy#revokeDeviceCredential`, `tenancy#rollbackDeviceFirmware`, `tenancy#setDeviceFirmwareStatus`, `tenancy#startDeviceFirmwareRollout` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-10 | AM-TENANCY-VENUES-P08 | [BE] AccessService: setAccessAreaCapacity | 2 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setAccessAreaCapacity. Spec: contracts (access) at the release tag, served by ADAM. Built for Tenancy & Venues · Venue Management 1 of 3; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#setAccessAreaCapacity` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-8 | AM-TENANCY-VENUES-P08 | [BE] AccessService: listVenueParkAccess | 1 | New full-stack developer 2 | AccessService | MIG-ACCESS-2 PLATFORM-KERNEL SVC-ACCESS-ACCESS-10 | Operations: listVenueParkAccess. Spec: contracts (access) at the release tag, served by ADAM. Built for Tenancy & Venues · Venue Management 1 of 3; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listVenueParkAccess` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | MIG-PAYMENTS-3 | AM-TENANCY-VENUES-P08-2 | [DB] Forward migration V1080__payments.sql: payments for Tenancy & Venues · Venue Management 2 of 3 (3 tables) | 2 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-PAYMENTS VM-MIG-PAYMENTS | Tables: payments.terminal, payments.terminal_certification, payments.terminal_certification_level3. Source DDL: backend/tenant/010-payments.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `payments.terminal`, `payments.terminal_certification`, `payments.terminal_certification_level3` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-TENANCY-DEVICES-4 | AM-TENANCY-VENUES-P08-2 | [BE] TenancyService: enrolDevice, getDeviceTelemetry | 3 | Sanket Keluskar | TenancyService | MIG-PLATFORM MIG-TENANCY-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: enrolDevice, getDeviceTelemetry. Spec: contracts (tenancy) at the release tag, served by ADAM. Built for Tenancy & Venues · Venue Management 2 of 3; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `tenancy#enrolDevice`, `tenancy#getDeviceTelemetry` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-TENANCY-5 | AM-TENANCY-VENUES-P08-2 | [BE] TenancyService: listDataRetentionSettings, setDataRetentionSetting | 3 | Pranay Shinde | TenancyService | MIG-TENANCY-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listDataRetentionSettings, setDataRetentionSetting. Spec: contracts (tenancy) at the release tag, served by ADAM. Built for Tenancy & Venues · Venue Management 2 of 3; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `tenancy#listDataRetentionSettings`, `tenancy#setDataRetentionSetting` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ORDER-PAYMENTS-4 | AM-TENANCY-VENUES-P08-2 | [BE] OrderService: setPaymentTerminalConfiguration | 2 | Chinmay Patkar | OrderService | MIG-PAYMENTS-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setPaymentTerminalConfiguration. Spec: contracts (payments) at the release tag, served by ADAM. Built for Tenancy & Venues · Venue Management 2 of 3; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `payments#setPaymentTerminalConfiguration` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
3 | 3 | VM-ADM-618 | AM-TENANCY-VENUES-P08-2 | [BE] ADM-618 Refund Simulator, Risk Analysis & AI Advisor | 3 | Surendra |  | SETUP-CLIENTS | Allow administrators to simulate refund outcomes before execution or rule publication. Module: Commercial. App: Venue Management. Waits for its definition: ADM-618 binds no operation yet (a person must define what it loads and saves), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-618` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
12 | 3 | VM-ADM-582 | AM-TENANCY-VENUES-P08-2 | [BE] ADM-582 POS, Kiosk & Terminal Assignment Manager | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-TENANCY-DEVICES-1 | Control which terminal is connected or assigned to each TICVAI selling device. Module: Commercial. App: Venue Management. Scope: setDeviceAssignment, 1 of ADM-582's 4 operations; the other 3 (assignKiosk, listKioskAssignments, listKioskConfigs) are wired by VM-FE-ADM-582-KIOSK. Waits for its definition: ADM-582's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-582` reaches every state its spec lists for the operations in its scope, every navigation link it owns works, an allowed and a refused user see what its permissions say, and it calls only the operations its scope names (block-test-strategy).
12 | 3 | VM-ADM-584 | AM-TENANCY-VENUES-P08-2 | [BE] ADM-584 Payment Server & Terminal Connectivity Manager | 2 | Sanket Keluskar |  | SETUP-CLIENTS SVC-TENANCY-DEVICES-4 | Monitor and configure the communication path between TICVAI POS, payment terminal, payment server and payment provider. Module: Commercial. App: Venue Management. Done when `ADM-584` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
13 | 3 | VM-ADM-587 | AM-TENANCY-VENUES-P08-2 | [BE] ADM-587 Terminal Health, Maintenance & Incident Center | 3 | Pranay Shinde |  | SETUP-CLIENTS SVC-TENANCY-DEVICES-4 VM-TENANCY-DEVICES-1 VM-VENUEOPS-WORKORDER-1 | Provide centralized lifecycle monitoring and operational maintenance of terminal hardware. Module: Commercial. App: Venue Management. Waits for its definition: ADM-587's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-587` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-581 | AM-TENANCY-VENUES-P08-2 | [BE] ADM-581 Terminal Provisioning & Device Configuration | 3 | Sanket Keluskar |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-4 SVC-TENANCY-DEVICES-4 | Configure and activate a physical terminal for TICVAI use. Module: Commercial. App: Venue Management. Done when `ADM-581` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | SVC-MARKETING-GUESTS-2 | AM-TENANCY-VENUES-P08-2 | [BE] MarketingService: runDataRetention | 2 | Chinmay Patkar | MarketingService | MIG-MARKETING MIG-MARKETING-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: runDataRetention. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Tenancy & Venues · Venue Management 2 of 3; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#runDataRetention` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
8 | 3 | MIG-APPROVALS-3 | AM-TENANCY-VENUES-P08-3 | [DB] Forward migration V1083__approvals.sql: approvals for Tenancy & Venues · Venue Management 3 of 3 (1 tables) | 1 | Hrushikant Patkar | TenancyService | MIG-APPROVALS MIG-BASELINE VM-MIG-APPROVALS | Tables: approvals.retention_policy. Source DDL: backend/tenant/010-approvals.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `approvals.retention_policy` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-TENANCY-APPROVALS-3 | AM-TENANCY-VENUES-P08-3 | [BE] TenancyService: setApprovalRetentionPolicy | 1 | Chinmay Patkar | TenancyService | MIG-APPROVALS-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setApprovalRetentionPolicy. Spec: contracts (approvals) at the release tag, served by ADAM. Built for Tenancy & Venues · Venue Management 3 of 3; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `approvals#setApprovalRetentionPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
3 | 3 | VM-ADM-344 | AM-TENANCY-VENUES-P08-3 | [BE] ADM-344 Digital Signature Management | 2 | Chinmay Patkar |  | SETUP-CLIENTS | Manage workflows where approval decisions require a digital signature. The matrix explicitly requires digital-signature support for sensitive approvals. Module: Platform. App: Venue Management. Waits for its definition: ADM-344 binds no operation yet (a person must define what it loads and saves), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-344` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
12 | 3 | VM-ADM-346 | AM-TENANCY-VENUES-P08-3 | [BE] ADM-346 Approval Record Retention Policy | 3 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-TENANCY-APPROVALS-3 SVC-TENANCY-TENANCY-5 | Define how long approval and governance records shall be retained. The matrix explicitly requires configurable approval record-retention policies. Module: Platform. App: Venue Management. Done when `ADM-346` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
5 | 3 | MIG-SUBSCRIPTION-2 | AM-TENANCY-VENUES-P09 | [DB] Forward migration V1057__subscription.sql: subscription for Tenancy & Venues · TICVAI Console (1 tables) | 1 | Hrushikant Patkar | PlatformService | MIG-BASELINE MIG-SUBSCRIPTION | Tables: subscription.go_live_readiness. Source DDL: backend/tenant/010-subscription.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `subscription.go_live_readiness` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-PLATFORM-SUBSCRIPTION-3 | AM-TENANCY-VENUES-P09 | [BE] PlatformService: runGoLiveValidation | 1 | Sanket Keluskar | PlatformService | MIG-SUBSCRIPTION-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: runGoLiveValidation. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Tenancy & Venues · TICVAI Console; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#runGoLiveValidation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
6 | 3 | MIG-CONTROL-5 | AM-PLATFORM-OPERATIONS-P07 | [DB] Forward migration V1085__control.sql: control for Platform Operations · Scanner (2 tables) | 2 | Hrushikant Patkar | PlatformService | MIG-BASELINE MIG-CONTROL VM-MIG-CONTROL | Tables: control.release, control.rollout. Source DDL: backend/control/010-control.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `control.release`, `control.rollout` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
7 | 3 | MIG-SYNC-2 | AM-PLATFORM-OPERATIONS-P07 | [DB] Forward migration V1086__sync.sql: sync for Platform Operations · Scanner (2 tables) | 2 | Hrushikant Patkar | CrossRegionService | MIG-BASELINE MIG-SYNC | Tables: sync.cell_connection, sync.cross_cell_request. Source DDL: backend/tenant/010-sync.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `sync.cell_connection`, `sync.cross_cell_request` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-PLATFORM-PLATFORM-OPS-1 | AM-PLATFORM-OPERATIONS-P07 | [BE] PlatformService: skipRolloutCell | 1 | Pranay Shinde | PlatformService | MIG-CONTROL-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: skipRolloutCell. Spec: contracts (platform-ops) at the release tag, served by ADAM. Built for Platform Operations · Scanner; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `platform-ops#skipRolloutCell` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 3 | SVC-CROSSREGION-CROSS-REGION-1 | AM-PLATFORM-OPERATIONS-P07 | [BE] CrossRegionService: listCellConnections, listCrossCellRequests | 2 | Chinmay Patkar | CrossRegionService | MIG-SYNC-2 PLATFORM-KERNEL | Operations: listCellConnections, listCrossCellRequests. Spec: contracts (cross-region) at the release tag, served by ADAM. Built for Platform Operations · Scanner; additive to CrossRegionService, whose first-release owner (its owner) reviews. Done when `cross-region#listCellConnections`, `cross-region#listCrossCellRequests` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-CROSSREGION-DSAR-1 | AM-PLATFORM-OPERATIONS-P07 | [BE] CrossRegionService: createDsarRequest, getDsarRequest | 3 | Surendra | CrossRegionService | MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createDsarRequest, getDsarRequest. Spec: contracts (cross-region) at the release tag, served by ADAM. Built for Platform Operations · Scanner; additive to CrossRegionService, whose first-release owner (its owner) reviews. Done when `cross-region#createDsarRequest`, `cross-region#getDsarRequest` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-CROSSREGION-GUESTLINK-1 | AM-PLATFORM-OPERATIONS-P07 | [BE] CrossRegionService: createGuestLink, getGuestLink, resolveGuestLink, revokeGuestLink | 5 | Deep Khanvilkar | CrossRegionService | MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createGuestLink, getGuestLink, resolveGuestLink, revokeGuestLink. Spec: contracts (cross-region) at the release tag, served by ADAM. Built for Platform Operations · Scanner; additive to CrossRegionService, whose first-release owner (its owner) reviews. Done when `cross-region#createGuestLink`, `cross-region#getGuestLink`, `cross-region#resolveGuestLink`, `cross-region#revokeGuestLink` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-CROSSREGION-REDEMPTION-1 | AM-PLATFORM-OPERATIONS-P07 | [BE] CrossRegionService: getCrossRegionEntitlement, propagateCrossRegionEntitlement, reconcileRedemptions, revokeCrossRegionEntitlement | 8 | Surendra | CrossRegionService | MIG-ACCESS MIG-PLATFORM-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getCrossRegionEntitlement, propagateCrossRegionEntitlement, reconcileRedemptions, revokeCrossRegionEntitlement. Spec: contracts (cross-region) at the release tag, served by ADAM. Built for Platform Operations · Scanner; additive to CrossRegionService, whose first-release owner (its owner) reviews. Done when `cross-region#getCrossRegionEntitlement`, `cross-region#propagateCrossRegionEntitlement`, `cross-region#reconcileRedemptions`, `cross-region#revokeCrossRegionEntitlement` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-CROSSREGION-WALLET-1 | AM-PLATFORM-OPERATIONS-P07 | [BE] CrossRegionService: authoriseWalletSpend, captureWalletAuthorisation, getWalletAllocation, relinquishWalletAuthorisation | 8 | Pranay Shinde | CrossRegionService | MIG-PLATFORM-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: authoriseWalletSpend, captureWalletAuthorisation, getWalletAllocation, relinquishWalletAuthorisation. Spec: contracts (cross-region) at the release tag, served by ADAM. Built for Platform Operations · Scanner; additive to CrossRegionService, whose first-release owner (its owner) reviews. Done when `cross-region#authoriseWalletSpend`, `cross-region#captureWalletAuthorisation`, `cross-region#getWalletAllocation`, `cross-region#relinquishWalletAuthorisation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-CROSSREGION-WALLET-2 | AM-PLATFORM-OPERATIONS-P07 | [BE] CrossRegionService: setWalletAllocationPolicy | 2 | Chinmay Patkar | CrossRegionService | MIG-PLATFORM-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setWalletAllocationPolicy. Spec: contracts (cross-region) at the release tag, served by ADAM. Built for Platform Operations · Scanner; additive to CrossRegionService, whose first-release owner (its owner) reviews. Done when `cross-region#setWalletAllocationPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
9 | 3 | MIG-PLATFORM-4 | AM-PLATFORM-OPERATIONS-P09 | [DB] Forward migration V1087__platform.sql: platform for Platform Operations · TICVAI Console 1 of 2 (1 tables) | 2 | Hrushikant Patkar | TenancyService | MIG-BASELINE MIG-PLATFORM VM-MIG-PLATFORM | Tables: platform.dead_letter. Source DDL: backend/tenant/010-platform.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `platform.dead_letter` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-PLATFORM-ENVIRONMENT-1 | AM-PLATFORM-OPERATIONS-P09 | [BE] PlatformService: listEnvironments, registerEnvironment | 2 | Sanket Keluskar | PlatformService | MIG-CONTROL-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listEnvironments, registerEnvironment. Spec: contracts (platform-ops) at the release tag, served by ADAM. Built for Platform Operations · TICVAI Console 1 of 2; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `platform-ops#listEnvironments`, `platform-ops#registerEnvironment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-MIGRATION-1 | AM-PLATFORM-OPERATIONS-P09 | [BE] PlatformService: applyConfigPackage, applyMigration, diffConfigPackage, exportConfigPackage | 5 | Tanmay Dukhande | PlatformService | MIG-CONTROL-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: applyConfigPackage, applyMigration, diffConfigPackage, exportConfigPackage. Spec: contracts (platform-ops) at the release tag, served by ADAM. Built for Platform Operations · TICVAI Console 1 of 2; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `platform-ops#applyConfigPackage`, `platform-ops#applyMigration`, `platform-ops#diffConfigPackage`, `platform-ops#exportConfigPackage` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-MIGRATION-2 | AM-PLATFORM-OPERATIONS-P09 | [BE] PlatformService: getMigrationRun, getVersionSkew, listMigrations, planMigration | 5 | Deep Khanvilkar | PlatformService | MIG-CONTROL-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getMigrationRun, getVersionSkew, listMigrations, planMigration. Spec: contracts (platform-ops) at the release tag, served by ADAM. Built for Platform Operations · TICVAI Console 1 of 2; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `platform-ops#getMigrationRun`, `platform-ops#getVersionSkew`, `platform-ops#listMigrations`, `platform-ops#planMigration` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-MIGRATION-3 | AM-PLATFORM-OPERATIONS-P09 | [BE] PlatformService: rollbackMigrationRun | 2 | Chinmay Patkar | PlatformService | MIG-CONTROL-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: rollbackMigrationRun. Spec: contracts (platform-ops) at the release tag, served by ADAM. Built for Platform Operations · TICVAI Console 1 of 2; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `platform-ops#rollbackMigrationRun` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-NOTICE-1 | AM-PLATFORM-OPERATIONS-P09 | [BE] PlatformService: listSupportNotices, listUpgradeSchedules, publishSupportNotice, scheduleTenantUpgrade | 3 | Sanket Keluskar | PlatformService | MIG-CONTROL-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listSupportNotices, listUpgradeSchedules, publishSupportNotice, scheduleTenantUpgrade. Spec: contracts (platform-ops) at the release tag, served by ADAM. Built for Platform Operations · TICVAI Console 1 of 2; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `platform-ops#listSupportNotices`, `platform-ops#listUpgradeSchedules`, `platform-ops#publishSupportNotice`, `platform-ops#scheduleTenantUpgrade` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-PLATFORM-OPS-2 | AM-PLATFORM-OPERATIONS-P09 | [BE] PlatformService: cancelOutboxRepublish, getOutboxRepublish, listDeadLetters, listOutboxRepublishes | 5 | Pranay Shinde | PlatformService | MIG-CONTROL-6 MIG-PLATFORM MIG-PLATFORM-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: cancelOutboxRepublish, getOutboxRepublish, listDeadLetters, listOutboxRepublishes. Spec: contracts (platform-ops) at the release tag, served by ADAM. Built for Platform Operations · TICVAI Console 1 of 2; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `platform-ops#cancelOutboxRepublish`, `platform-ops#getOutboxRepublish`, `platform-ops#listDeadLetters`, `platform-ops#listOutboxRepublishes` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-PLATFORM-OPS-3 | AM-PLATFORM-OPERATIONS-P09 | [BE] PlatformService: replayDeadLetter, republishOutbox | 3 | Sanket Keluskar | PlatformService | MIG-CONTROL-6 MIG-PLATFORM MIG-PLATFORM-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: replayDeadLetter, republishOutbox. Spec: contracts (platform-ops) at the release tag, served by ADAM. Built for Platform Operations · TICVAI Console 1 of 2; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `platform-ops#replayDeadLetter`, `platform-ops#republishOutbox` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-RELEASE-1 | AM-PLATFORM-OPERATIONS-P09 | [BE] PlatformService: createRelease, getRelease, getReleaseReadiness, listReleases | 5 | Surendra | PlatformService | MIG-CONTROL-5 MIG-CONTROL-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createRelease, getRelease, getReleaseReadiness, listReleases. Spec: contracts (platform-ops) at the release tag, served by ADAM. Built for Platform Operations · TICVAI Console 1 of 2; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `platform-ops#createRelease`, `platform-ops#getRelease`, `platform-ops#getReleaseReadiness`, `platform-ops#listReleases` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-RELEASE-2 | AM-PLATFORM-OPERATIONS-P09 | [BE] PlatformService: promoteRelease, rejectRelease, withdrawRelease | 3 | Sanket Keluskar | PlatformService | MIG-CONTROL-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: promoteRelease, rejectRelease, withdrawRelease. Spec: contracts (platform-ops) at the release tag, served by ADAM. Built for Platform Operations · TICVAI Console 1 of 2; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `platform-ops#promoteRelease`, `platform-ops#rejectRelease`, `platform-ops#withdrawRelease` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-ROLLOUT-1 | AM-PLATFORM-OPERATIONS-P09 | [BE] PlatformService: getRollout, listRollouts, pauseRollout, rollbackRollout | 8 | Pranay Shinde | PlatformService | MIG-CONTROL-5 MIG-CONTROL-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getRollout, listRollouts, pauseRollout, rollbackRollout. Spec: contracts (platform-ops) at the release tag, served by ADAM. Built for Platform Operations · TICVAI Console 1 of 2; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `platform-ops#getRollout`, `platform-ops#listRollouts`, `platform-ops#pauseRollout`, `platform-ops#rollbackRollout` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-ROLLOUT-2 | AM-PLATFORM-OPERATIONS-P09 | [BE] PlatformService: startRollout | 1 | Chinmay Patkar | PlatformService | MIG-CONTROL-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: startRollout. Spec: contracts (platform-ops) at the release tag, served by ADAM. Built for Platform Operations · TICVAI Console 1 of 2; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `platform-ops#startRollout` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
5 | 3 | MIG-SUBSCRIPTION-3 | AM-SUBSCRIPTION-LICENSING-P08 | [DB] Forward migration V1084__subscription.sql: subscription for Subscription & Licensing · Venue Management 1 of 3 (10 tables) | 8 | Hrushikant Patkar | PlatformService | MIG-BASELINE MIG-SUBSCRIPTION | Tables: subscription.membership_eligibility_rule, subscription.membership_entitlement, subscription.membership_household_policy, subscription.membership_household_policy_role_limit, subscription.membership_product, subscription.membership_product_history, subscription.membership_renewal_policy, subscription.membership_usage_policy, subscription.tier_allowance, subscription.tier_module. Source DDL: backend/tenant/010-subscription.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `subscription.membership_eligibility_rule`, `subscription.membership_entitlement`, `subscription.membership_household_policy`, `subscription.membership_household_policy_role_limit`, `subscription.membership_product`, `subscription.membership_product_history`, `subscription.membership_renewal_policy`, `subscription.membership_usage_policy` and 2 more runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-PLATFORM-BILLING-1 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] PlatformService: resolveInvoiceDispute | 1 | Sanket Keluskar | PlatformService | MIG-CONTROL-7 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: resolveInvoiceDispute. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 1 of 3; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#resolveInvoiceDispute` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-CELL-1 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] PlatformService: executeTenantMigration, launchCellCluster, listCellClusters, listTenantMigrations | 5 | Deep Khanvilkar | PlatformService | MIG-CONTROL-7 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: executeTenantMigration, launchCellCluster, listCellClusters, listTenantMigrations. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 1 of 3; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#executeTenantMigration`, `subscription#launchCellCluster`, `subscription#listCellClusters`, `subscription#listTenantMigrations` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-CELL-2 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] PlatformService: planTenantMigration, rollbackTenantMigration | 2 | Chinmay Patkar | PlatformService | MIG-CONTROL-7 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: planTenantMigration, rollbackTenantMigration. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 1 of 3; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#planTenantMigration`, `subscription#rollbackTenantMigration` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-DRAFTED-5 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] PlatformService: setFamilyHouseholdDependent, setMembershipEligibilityQualification, setMembershipProductTier, setValidityActivationExpiry | 8 | Pranay Shinde | PlatformService | MIG-CATALOGUE MIG-SUBSCRIPTION-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setFamilyHouseholdDependent, setMembershipEligibilityQualification, setMembershipProductTier, setValidityActivationExpiry. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 1 of 3; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#setFamilyHouseholdDependent`, `subscription#setMembershipEligibilityQualification`, `subscription#setMembershipProductTier`, `subscription#setValidityActivationExpiry` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-METERING-1 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] PlatformService: recordUsage | 2 | Sanket Keluskar | PlatformService | MIG-AI MIG-CONTROL-7 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: recordUsage. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 1 of 3; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#recordUsage` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-SUBSCRIPTION-4 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] PlatformService: actOnPartnerCommissionLine, actOnPartnerReconciliationException, actOnPartnerSettlementBatch, cancelSubscription | 8 | Surendra | PlatformService | MIG-CONTROL MIG-CONTROL-7 MIG-IDENTITY MIG-LEDGER MIG-SUBSCRIPTION PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: actOnPartnerCommissionLine, actOnPartnerReconciliationException, actOnPartnerSettlementBatch, cancelSubscription. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 1 of 3; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#actOnPartnerCommissionLine`, `subscription#actOnPartnerReconciliationException`, `subscription#actOnPartnerSettlementBatch`, `subscription#cancelSubscription` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-SUBSCRIPTION-8 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] PlatformService: setPartnerCapabilityGrants, setPartnerCommissionRules, setPartnerCreditProfile, setPartnerDistributionRights | 8 | Tanmay Dukhande | PlatformService | MIG-APPROVALS MIG-CATALOGUE MIG-CONTROL MIG-CONTROL-3 MIG-CONTROL-7 MIG-IDENTITY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setPartnerCapabilityGrants, setPartnerCommissionRules, setPartnerCreditProfile, setPartnerDistributionRights. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 1 of 3; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#setPartnerCapabilityGrants`, `subscription#setPartnerCommissionRules`, `subscription#setPartnerCreditProfile`, `subscription#setPartnerDistributionRights` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-SUBSCRIPTION-9 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] PlatformService: setPartnerSecurity, setPlanTiers, updatePartnerAgreement | 8 | Surendra | PlatformService | MIG-CONTROL MIG-CONTROL-7 MIG-LEDGER MIG-SUBSCRIPTION-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setPartnerSecurity, setPlanTiers, updatePartnerAgreement. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 1 of 3; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#setPartnerSecurity`, `subscription#setPlanTiers`, `subscription#updatePartnerAgreement` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | SVC-PLATFORM-SUBSCRIPTION-5 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] PlatformService: createPartnerAgreement, decommissionBurstEnvironment, drainBurstEnvironment, exportPartnerInvoice | 8 | Surendra | PlatformService | MIG-APPROVALS MIG-CONTROL MIG-CONTROL-7 MIG-LEDGER MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: createPartnerAgreement, decommissionBurstEnvironment, drainBurstEnvironment, exportPartnerInvoice. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 1 of 3; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#createPartnerAgreement`, `subscription#decommissionBurstEnvironment`, `subscription#drainBurstEnvironment`, `subscription#exportPartnerInvoice` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | SVC-PLATFORM-SUBSCRIPTION-6 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] PlatformService: getPlanTiers, listBurstEnvironments, listPartnerUsers, reconcileBurstEnvironment | 5 | Tanmay Dukhande | PlatformService | MIG-CATALOGUE MIG-CONTROL-3 MIG-CONTROL-7 MIG-IDENTITY MIG-ORDERS MIG-PLATFORM MIG-SUBSCRIPTION-3 MIG-SYNC PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: getPlanTiers, listBurstEnvironments, listPartnerUsers, reconcileBurstEnvironment. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 1 of 3; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#getPlanTiers`, `subscription#listBurstEnvironments`, `subscription#listPartnerUsers`, `subscription#reconcileBurstEnvironment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | SVC-PLATFORM-SUBSCRIPTION-7 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] PlatformService: registerPartner, requestBurstEnvironment, setMembershipUsagePolicy, setPartnerAllocations | 8 | Pranay Shinde | PlatformService | MIG-APPROVALS MIG-CATALOGUE MIG-CONTROL MIG-CONTROL-3 MIG-CONTROL-6 MIG-CONTROL-7 MIG-ORDERS MIG-SUBSCRIPTION-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: registerPartner, requestBurstEnvironment, setMembershipUsagePolicy, setPartnerAllocations. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 1 of 3; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#registerPartner`, `subscription#requestBurstEnvironment`, `subscription#setMembershipUsagePolicy`, `subscription#setPartnerAllocations` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-PLATFORM-DRAFTED-2 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] PlatformService: approveMembershipProductValidation, listCommercialAllocationQuota, listCommissionCalculationSettlement, listCommissionMarginIncentive | 8 | Surendra | PlatformService | MIG-ACCESS MIG-APPROVALS MIG-CATALOGUE MIG-CONTROL MIG-CONTROL-3 MIG-CONTROL-7 MIG-LEDGER MIG-ORDERS MIG-SUBSCRIPTION-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: approveMembershipProductValidation, listCommercialAllocationQuota, listCommissionCalculationSettlement, listCommissionMarginIncentive. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 1 of 3; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#approveMembershipProductValidation`, `subscription#listCommercialAllocationQuota`, `subscription#listCommissionCalculationSettlement`, `subscription#listCommissionMarginIncentive` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 2 | VM-LEDGER-RECOGNITION-1 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] LedgerService: createRecognitionSchedule, getDeferredRevenue, listRecognitionSchedules, runRecognition | 8 | Tanmay Dukhande | LedgerService | MIG-LEDGER MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-LEDGER | Operations beyond the first release: createRecognitionSchedule, getDeferredRevenue, listRecognitionSchedules, runRecognition. Additive to LedgerService; its first-release owner (Tanmay Dukhande) reviews. Done when `finance#createRecognitionSchedule`, `finance#getDeferredRevenue`, `finance#listRecognitionSchedules`, `finance#runRecognition` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-CATALOGUE-3 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] CatalogueService: setMembershipProgramme, setPlanBenefits | 2 | Tanmay Dukhande | CatalogueService | MIG-CATALOGUE-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setMembershipProgramme, setPlanBenefits. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 1 of 3; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#setMembershipProgramme`, `catalogue#setPlanBenefits` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | VM-PTR-035 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] PTR-035 Commission, Margin & Incentive Management | 3 | Sanket Keluskar |  | SETUP-CLIENTS SVC-IDENTITY-MFA-1 SVC-IDENTITY-MFA-2 SVC-PLATFORM-DRAFTED-2 SVC-PLATFORM-SUBSCRIPTION-8 | Configure how partner commissions and commercial incentives are calculated. Module: Partners. App: Venue Management. Waits for its definition: PTR-035's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `PTR-035` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-PTR-039 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] PTR-039 Commercial Allocation, Quota & Commitment Management | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-PLATFORM-DRAFTED-2 SVC-PLATFORM-SUBSCRIPTION-7 | Define the commercial commitment of inventory to a partner. This differs from Area 4's operational channel allocation. Module: Partners. App: Venue Management. Done when `PTR-039` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-PTR-048 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] PTR-048 Commission Calculation & Settlement Management | 3 | Sanket Keluskar |  | SETUP-CLIENTS SVC-IDENTITY-MFA-1 SVC-IDENTITY-MFA-2 SVC-PLATFORM-DRAFTED-2 SVC-PLATFORM-SUBSCRIPTION-4 | Calculate, approve and settle commission or incentive amounts owed under partner commercial agreements. Module: Partners. App: Venue Management. Done when `PTR-048` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
11 | 3 | SVC-IDENTITY-IDENTITY-9 | AM-SUBSCRIPTION-LICENSING-P08-2 | [BE] IdentityService: recordBenefitUsage | 2 | Chinmay Patkar | IdentityService | MIG-IDENTITY-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: recordBenefitUsage. Spec: contracts (identity) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 2 of 3; additive to IdentityService, whose first-release owner (Pranay Shinde) reviews. Done when `identity#recordBenefitUsage` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-PLATFORM-SUBSCRIPTION-10 | AM-SUBSCRIPTION-LICENSING-P08-2 | [BE] PlatformService: getGoLiveReadiness | 1 | Tanmay Dukhande | PlatformService | MIG-SUBSCRIPTION-2 PLATFORM-KERNEL SVC-PLATFORM-SUBSCRIPTION-3 | Operations: getGoLiveReadiness. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 2 of 3; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#getGoLiveReadiness` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-PLATFORM-DRAFTED-8 | AM-SUBSCRIPTION-LICENSING-P08-2 | [BE] PlatformService: setMemberMembershipAccount, setRenewalAutoMembership | 5 | Deep Khanvilkar | PlatformService | MIG-ACCESS MIG-CATALOGUE MIG-ORDERS MIG-SUBSCRIPTION-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setMemberMembershipAccount, setRenewalAutoMembership. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 2 of 3; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#setMemberMembershipAccount`, `subscription#setRenewalAutoMembership` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-ORDERS-6 | AM-SUBSCRIPTION-LICENSING-P08-2 | [BE] OrderService: migrateMembership, renewMembership, resolveMembershipActivation | 5 | Surendra | OrderService | MIG-ORDERS-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: migrateMembership, renewMembership, resolveMembershipActivation. Spec: contracts (orders) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 2 of 3; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#migrateMembership`, `orders#renewMembership`, `orders#resolveMembershipActivation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
5 | 3 | MIG-SUBSCRIPTION-4 | AM-SUBSCRIPTION-LICENSING-P09-2 | [DB] Forward migration V1089__subscription.sql: subscription for Subscription & Licensing · TICVAI Console 2 of 6 (2 tables) | 1 | Hrushikant Patkar | PlatformService | MIG-BASELINE MIG-SUBSCRIPTION | Tables: subscription.licensing_model, subscription.vsi_assessment. Source DDL: backend/tenant/010-subscription.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `subscription.licensing_model`, `subscription.vsi_assessment` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-PLATFORM-SUBSCRIPTION-11 | AM-SUBSCRIPTION-LICENSING-P09-2 | [BE] PlatformService: getBillingReconciliation, scoreVsiAssessment | 3 | Sanket Keluskar | PlatformService | MIG-CONTROL-7 MIG-CONTROL-9 MIG-SUBSCRIPTION MIG-SUBSCRIPTION-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getBillingReconciliation, scoreVsiAssessment. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · TICVAI Console 2 of 6; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#getBillingReconciliation`, `subscription#scoreVsiAssessment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
5 | 3 | MIG-SUBSCRIPTION-5 | AM-SUBSCRIPTION-LICENSING-P09-3 | [DB] Forward migration V1094__subscription.sql: subscription for Subscription & Licensing · TICVAI Console 3 of 6 (3 tables) | 2 | Hrushikant Patkar | PlatformService | MIG-BASELINE MIG-SUBSCRIPTION | Tables: subscription.capacity_pack, subscription.enforcement_policy, subscription.vsi_model. Source DDL: backend/tenant/010-subscription.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `subscription.capacity_pack`, `subscription.enforcement_policy`, `subscription.vsi_model` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-PLATFORM-SUBSCRIPTION-13 | AM-SUBSCRIPTION-LICENSING-P09-3 | [BE] PlatformService: setLicensingModel, setVsiModel, simulateCommercialPackage | 5 | Pranay Shinde | PlatformService | MIG-CONTROL MIG-SUBSCRIPTION MIG-SUBSCRIPTION-3 MIG-SUBSCRIPTION-4 MIG-SUBSCRIPTION-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setLicensingModel, setVsiModel, simulateCommercialPackage. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · TICVAI Console 3 of 6; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#setLicensingModel`, `subscription#setVsiModel`, `subscription#simulateCommercialPackage` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
5 | 3 | MIG-SUBSCRIPTION-6 | AM-SUBSCRIPTION-LICENSING-P09-4 | [DB] Forward migration V1095__subscription.sql: subscription for Subscription & Licensing · TICVAI Console 4 of 6 (1 tables) | 1 | Hrushikant Patkar | PlatformService | MIG-BASELINE MIG-SUBSCRIPTION | Tables: subscription.trial_config. Source DDL: backend/tenant/010-subscription.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `subscription.trial_config` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-PLATFORM-BILLING-3 | AM-SUBSCRIPTION-LICENSING-P09-4 | [BE] PlatformService: getBillingEntity, setBillingEntity | 3 | Sanket Keluskar | PlatformService | MIG-CONTROL-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getBillingEntity, setBillingEntity. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · TICVAI Console 4 of 6; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#getBillingEntity`, `subscription#setBillingEntity` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-DRAFTED-9 | AM-SUBSCRIPTION-LICENSING-P09-4 | [BE] PlatformService: setAgreementContractTerm | 3 | Sanket Keluskar | PlatformService | MIG-APPROVALS MIG-CONTROL MIG-CONTROL-7 MIG-LEDGER PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setAgreementContractTerm. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · TICVAI Console 4 of 6; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#setAgreementContractTerm` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-SUBSCRIPTION-14 | AM-SUBSCRIPTION-LICENSING-P09-4 | [BE] PlatformService: addCapacityPack, setTrialConfiguration | 3 | Sanket Keluskar | PlatformService | MIG-SUBSCRIPTION-5 MIG-SUBSCRIPTION-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: addCapacityPack, setTrialConfiguration. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · TICVAI Console 4 of 6; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#addCapacityPack`, `subscription#setTrialConfiguration` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-BILLING-4 | AM-SUBSCRIPTION-LICENSING-P09-5 | [BE] PlatformService: issueCreditNote, recordInvoicePayment | 3 | Sanket Keluskar | PlatformService | MIG-CONTROL-7 MIG-CONTROL-9 MIG-LEDGER PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: issueCreditNote, recordInvoicePayment. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · TICVAI Console 5 of 6; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#issueCreditNote`, `subscription#recordInvoicePayment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-PLATFORM-BILLING-2 | AM-SUBSCRIPTION-LICENSING-P09-2 | [BE] PlatformService: listCreditNotes | 2 | Tanmay Dukhande | PlatformService | MIG-CONTROL-9 PLATFORM-KERNEL SVC-PLATFORM-BILLING-4 | Operations: listCreditNotes. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · TICVAI Console 2 of 6; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#listCreditNotes` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-SUBSCRIPTION-15 | AM-SUBSCRIPTION-LICENSING-P09-5 | [BE] PlatformService: listVenueTypeTemplates, setLicenceEnforcementPolicy, settleAiUsage | 3 | Sanket Keluskar | PlatformService | MIG-AI MIG-CONTROL-2 MIG-CONTROL-7 MIG-SUBSCRIPTION MIG-SUBSCRIPTION-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listVenueTypeTemplates, setLicenceEnforcementPolicy, settleAiUsage. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · TICVAI Console 5 of 6; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#listVenueTypeTemplates`, `subscription#setLicenceEnforcementPolicy`, `subscription#settleAiUsage` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-PLATFORM-SUBSCRIPTION-12 | AM-SUBSCRIPTION-LICENSING-P09-3 | [BE] PlatformService: getLicenceEnforcement, getPlanRecommendations, getVsiModel, listLicensingModels | 5 | Tanmay Dukhande | PlatformService | MIG-CONTROL MIG-CONTROL-7 MIG-SUBSCRIPTION MIG-SUBSCRIPTION-3 MIG-SUBSCRIPTION-4 MIG-SUBSCRIPTION-5 PLATFORM-KERNEL SVC-PLATFORM-LICENSING-1 SVC-PLATFORM-LICENSING-3 SVC-PLATFORM-METERING-1 SVC-PLATFORM-PLAN-1 SVC-PLATFORM-SUBSCRIPTION-1 SVC-PLATFORM-SUBSCRIPTION-13 SVC-PLATFORM-SUBSCRIPTION-14 SVC-PLATFORM-SUBSCRIPTION-15 SVC-PLATFORM-SUBSCRIPTION-4 SVC-PLATFORM-SUBSCRIPTION-9 SVC-PLATFORM-TENANT-2 | Operations: getLicenceEnforcement, getPlanRecommendations, getVsiModel, listLicensingModels. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · TICVAI Console 3 of 6; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#getLicenceEnforcement`, `subscription#getPlanRecommendations`, `subscription#getVsiModel`, `subscription#listLicensingModels` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-BILLING-5 | AM-SUBSCRIPTION-LICENSING-P09-6 | [BE] PlatformService: cancelInvoice, disputeInvoice | 2 | Tanmay Dukhande | PlatformService | MIG-CONTROL-7 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: cancelInvoice, disputeInvoice. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · TICVAI Console 6 of 6; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#cancelInvoice`, `subscription#disputeInvoice` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
6 | 3 | MIG-CONTROL-10 | AM-SUBSCRIPTION-LICENSING-P10 | [DB] Forward migration V1107__control.sql: control for Subscription & Licensing · Partner Portal 1 of 2 (2 tables) | 2 | Hrushikant Patkar | PlatformService | MIG-BASELINE MIG-CONTROL VM-MIG-CONTROL | Tables: control.partner_billing_profile, control.partner_rate_volume_band. Source DDL: backend/control/010-control.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `control.partner_billing_profile`, `control.partner_rate_volume_band` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-PLATFORM-SUBSCRIPTION-16 | AM-SUBSCRIPTION-LICENSING-P10 | [BE] PlatformService: actOnPartnerApplicationReview, createPartnerUser, setPartnerContact | 8 | Surendra | PlatformService | MIG-APPROVALS MIG-CONTROL MIG-CONTROL-3 MIG-CONTROL-7 MIG-IDENTITY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: actOnPartnerApplicationReview, createPartnerUser, setPartnerContact. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Partner Portal 1 of 2; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#actOnPartnerApplicationReview`, `subscription#createPartnerUser`, `subscription#setPartnerContact` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | SVC-PLATFORM-DRAFTED-12 | AM-SUBSCRIPTION-LICENSING-P10 | [BE] PlatformService: listPartnerProfileReadiness, setPartnerBrandVenue, setPartnerProfileOrganization, setPartnerRateNet | 8 | Tanmay Dukhande | PlatformService | MIG-APPROVALS MIG-CATALOGUE MIG-CONTROL MIG-CONTROL-10 MIG-CONTROL-3 MIG-CONTROL-7 MIG-IDENTITY MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listPartnerProfileReadiness, setPartnerBrandVenue, setPartnerProfileOrganization, setPartnerRateNet. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Partner Portal 1 of 2; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#listPartnerProfileReadiness`, `subscription#setPartnerBrandVenue`, `subscription#setPartnerProfileOrganization`, `subscription#setPartnerRateNet` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | SVC-PLATFORM-DRAFTED-13 | AM-SUBSCRIPTION-LICENSING-P10 | [BE] PlatformService: setPaymentTermBilling | 3 | Deep Khanvilkar | PlatformService | MIG-APPROVALS MIG-CONTROL MIG-CONTROL-10 MIG-CONTROL-7 MIG-LEDGER MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setPaymentTermBilling. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Partner Portal 1 of 2; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#setPaymentTermBilling` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
8 | 3 | MIG-APPROVALS-4 | AM-SUBSCRIPTION-LICENSING-P10-2 | [DB] Forward migration V1008__approvals.sql: approvals for Subscription & Licensing · Partner Portal 2 of 2 (1 tables) | 1 | Hrushikant Patkar | TenancyService | MIG-APPROVALS MIG-BASELINE VM-MIG-APPROVALS | Tables: approvals.sla_policy. Source DDL: backend/tenant/010-approvals.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `approvals.sla_policy` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
13 | 3 | SVC-PLATFORM-SUBSCRIPTION-17 | AM-SUBSCRIPTION-LICENSING-P10-2 | [BE] PlatformService: actOnPartnerCase, createPartnerCase, createPartnerChangeRequest, getCommissionStatement | 8 | Tanmay Dukhande | PlatformService | MIG-APPROVALS MIG-APPROVALS-4 MIG-CATALOGUE MIG-CONTROL MIG-CONTROL-3 MIG-CONTROL-7 MIG-IDENTITY MIG-LEDGER MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: actOnPartnerCase, createPartnerCase, createPartnerChangeRequest, getCommissionStatement. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Partner Portal 2 of 2; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#actOnPartnerCase`, `subscription#createPartnerCase`, `subscription#createPartnerChangeRequest`, `subscription#getCommissionStatement` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-PLATFORM-SUBSCRIPTION-18 | AM-SUBSCRIPTION-LICENSING-P10-2 | [BE] PlatformService: listPartnerAgreements | 1 | Chinmay Patkar | PlatformService | MIG-CONTROL PLATFORM-KERNEL SVC-PLATFORM-DRAFTED-1 SVC-PLATFORM-DRAFTED-12 SVC-PLATFORM-DRAFTED-13 SVC-PLATFORM-DRAFTED-9 SVC-PLATFORM-SUBSCRIPTION-16 SVC-PLATFORM-SUBSCRIPTION-5 SVC-PLATFORM-SUBSCRIPTION-7 SVC-PLATFORM-SUBSCRIPTION-9 SVC-TENANCY-REQUEST-1 | Operations: listPartnerAgreements. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Partner Portal 2 of 2; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#listPartnerAgreements` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-CATALOGUE-LEASE-1 | AM-SUBSCRIPTION-LICENSING-P10-2 | [BE] CatalogueService: forceReleaseInventoryHold | 2 | Chinmay Patkar | CatalogueService | MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: forceReleaseInventoryHold. Additive to CatalogueService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#forceReleaseInventoryHold` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
5 | 3 | MIG-ACCREDITATION-2 | AM-APPROVALS-P08 | [DB] Forward migration V1042__accreditation.sql: accreditation for Approvals · Venue Management 1 of 5 (1 tables) | 1 | Hrushikant Patkar | TenancyService | MIG-BASELINE VM-MIG-ACCREDITATION | Tables: accreditation.audit. Source DDL: backend/tenant/010-accreditation.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `accreditation.audit` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
8 | 3 | MIG-APPROVALS-6 | AM-APPROVALS-P08 | [DB] Forward migration V1099__approvals.sql: approvals for Approvals · Venue Management 1 of 5 (12 tables) | 8 | Hrushikant Patkar | TenancyService | MIG-APPROVALS MIG-BASELINE VM-MIG-APPROVALS | Tables: approvals.approved_action_execution, approvals.automation, approvals.business_rule, approvals.control_policy, approvals.decision_record, approvals.decision_table, approvals.decision_table_row, approvals.workflow_exception, approvals.workflow_instance, approvals.workflow_intervention, approvals.workflow_step_execution, approvals.workflow_trigger. Source DDL: backend/tenant/010-approvals.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `approvals.approved_action_execution`, `approvals.automation`, `approvals.business_rule`, `approvals.control_policy`, `approvals.decision_record`, `approvals.decision_table`, `approvals.decision_table_row`, `approvals.workflow_exception` and 4 more runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
9 | 3 | MIG-SEATING-2 | AM-APPROVALS-P08 | [DB] Forward migration V1100__seating.sql: seating for Approvals · Venue Management 1 of 5 (1 tables) | 1 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-SEATING | Tables: seating.hold_pool. Source DDL: backend/tenant/010-seating.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `seating.hold_pool` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-TENANCY-APPROVALS-5 | AM-APPROVALS-P08 | [BE] TenancyService: actOnWorkflowInstance, listConditionDecisionLogic, listRuleWorkflow, listWorkflow | 8 | Pranay Shinde | TenancyService | MIG-APPROVALS MIG-APPROVALS-2 MIG-APPROVALS-4 MIG-APPROVALS-5 MIG-APPROVALS-6 MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-APPROVALS | Operations: actOnWorkflowInstance, listConditionDecisionLogic, listRuleWorkflow, listWorkflow. Spec: contracts (approvals) at the release tag, served by ADAM. Built for Approvals · Venue Management 1 of 5; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `approvals#actOnWorkflowInstance`, `approvals#listConditionDecisionLogic`, `approvals#listRuleWorkflow`, `approvals#listWorkflow` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-APPROVALS-6 | AM-APPROVALS-P08 | [BE] TenancyService: listWorkflowInstanceProcess, setTriggerActionCross, setVisualBusinessRule, setVisualWorkflow | 8 | Surendra | TenancyService | MIG-APPROVALS MIG-APPROVALS-2 MIG-APPROVALS-6 MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-APPROVALS | Operations: listWorkflowInstanceProcess, setTriggerActionCross, setVisualBusinessRule, setVisualWorkflow. Spec: contracts (approvals) at the release tag, served by ADAM. Built for Approvals · Venue Management 1 of 5; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `approvals#listWorkflowInstanceProcess`, `approvals#setTriggerActionCross`, `approvals#setVisualBusinessRule`, `approvals#setVisualWorkflow` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-APPROVALS-7 | AM-APPROVALS-P08 | [BE] TenancyService: simulateWorkflowTestingImpact | 2 | Chinmay Patkar | TenancyService | MIG-APPROVALS MIG-APPROVALS-2 MIG-APPROVALS-4 MIG-APPROVALS-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: simulateWorkflowTestingImpact. Spec: contracts (approvals) at the release tag, served by ADAM. Built for Approvals · Venue Management 1 of 5; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `approvals#simulateWorkflowTestingImpact` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-TENANCY-ACCREDITATION-1 | AM-APPROVALS-P08 | [BE] TenancyService: listAccreditationAudit | 1 | Sanket Keluskar | TenancyService | MIG-ACCREDITATION-2 PLATFORM-KERNEL | Operations: listAccreditationAudit. Spec: contracts (accreditation) at the release tag, served by ADAM. Built for Approvals · Venue Management 1 of 5; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `accreditation#listAccreditationAudit` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-TENANCY-ANALYTICS-1 | AM-APPROVALS-P08 | [BE] TenancyService: getApprovalAnalytics | 1 | Hrushikant Patkar | TenancyService | MIG-APPROVALS PLATFORM-KERNEL SVC-PLATFORM-DRAFTED-1 SVC-PLATFORM-DRAFTED-12 SVC-PLATFORM-DRAFTED-13 SVC-PLATFORM-DRAFTED-2 SVC-PLATFORM-DRAFTED-9 SVC-PLATFORM-SUBSCRIPTION-16 SVC-PLATFORM-SUBSCRIPTION-17 SVC-PLATFORM-SUBSCRIPTION-5 SVC-PLATFORM-SUBSCRIPTION-7 SVC-PLATFORM-SUBSCRIPTION-8 SVC-TENANCY-APPROVALS-2 SVC-TENANCY-APPROVALS-4 SVC-TENANCY-APPROVALS-5 SVC-TENANCY-REQUEST-1 SVC-TENANCY-REQUEST-2 SVC-TENANCY-REQUEST-3 SVC-TENANCY-ROTA-2 VM-MIG-APPROVALS VM-TENANCY-REQUEST-1 | Operations: getApprovalAnalytics. Spec: contracts (approvals) at the release tag, served by ADAM. Built for Approvals · Venue Management 1 of 5; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `approvals#getApprovalAnalytics` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-SEATING-2 | AM-APPROVALS-P08 | [BE] CatalogueService: listSeatHoldPools | 1 | Chinmay Patkar | CatalogueService | MIG-SEATING-2 PLATFORM-KERNEL | Operations: listSeatHoldPools. Spec: contracts (seating) at the release tag, served by ADAM. Built for Approvals · Venue Management 1 of 5; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `seating#listSeatHoldPools` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | VM-ADM-238 | AM-APPROVALS-P08 | [BE] ADM-238 Rules & Workflow Command Center | 5 | Sanket Keluskar |  | SETUP-CLIENTS SVC-TENANCY-APPROVALS-5 | Provide administrators with a centralized portfolio of all business rules, workflows, approvals and automations configured across TICVAI. Module: Platform. App: Venue Management. Done when `ADM-238` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
12 | 3 | VM-ADM-239 | AM-APPROVALS-P08 | [BE] ADM-239 Visual Business Rule Builder | 2 | Sanket Keluskar |  | SETUP-CLIENTS SVC-TENANCY-APPROVALS-6 | Allow administrators to create business rules without software development. Module: Platform. App: Venue Management. Waits for its definition: ADM-239's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-239` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
12 | 3 | VM-ADM-240 | AM-APPROVALS-P08 | [BE] ADM-240 Conditions, Decision Logic & Decision Tables | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-TENANCY-APPROVALS-5 | Configure advanced decision logic where simple IF/THEN rules are insufficient. Module: Platform. App: Venue Management. Waits for its definition: ADM-240's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-240` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
12 | 3 | VM-ADM-241 | AM-APPROVALS-P08 | [BE] ADM-241 Visual Workflow Designer | 2 | Surendra |  | SETUP-CLIENTS SVC-TENANCY-APPROVALS-6 | Allow administrators to visually design complete business processes. Module: Platform. App: Venue Management. Done when `ADM-241` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
12 | 3 | VM-ADM-245 | AM-APPROVALS-P08 | [BE] ADM-245 Trigger, Action & Cross-Module Orchestration Configuration | 2 | Pranay Shinde |  | SETUP-CLIENTS SVC-TENANCY-APPROVALS-6 | Define what starts a workflow and what TICVAI services may be called during execution. Module: Platform. App: Venue Management. Done when `ADM-245` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
12 | 3 | VM-ADM-246 | AM-APPROVALS-P08 | [BE] ADM-246 Workflow Testing, Simulation & Impact Analysis | 2 | Sanket Keluskar |  | SETUP-CLIENTS SVC-TENANCY-APPROVALS-7 | Allow administrators to test rules and workflows before they affect live operations. This is a critical screen. Module: Platform. App: Venue Management. Done when `ADM-246` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
12 | 3 | VM-ADM-248 | AM-APPROVALS-P08 | [BE] ADM-248 Workflow Operations Command Center | 5 | Surendra |  | SETUP-CLIENTS SVC-TENANCY-APPROVALS-5 | Provide administrators and operational managers with a real-time view of all workflow activity across TICVAI. Module: Platform. App: Venue Management. Done when `ADM-248` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
11 | 3 | SVC-TENANCY-APPROVALS-8 | AM-APPROVALS-P08-2 | [BE] TenancyService: createAutomationAutonomouAction, listCrossModuleOrchestration, listProcessAutomationOpportunity, listWorkflowAutonomouGovernance | 5 | Pranay Shinde | TenancyService | MIG-APPROVALS MIG-APPROVALS-2 MIG-APPROVALS-5 MIG-APPROVALS-6 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-APPROVALS | Operations: createAutomationAutonomouAction, listCrossModuleOrchestration, listProcessAutomationOpportunity, listWorkflowAutonomouGovernance. Spec: contracts (approvals) at the release tag, served by ADAM. Built for Approvals · Venue Management 2 of 5; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `approvals#createAutomationAutonomouAction`, `approvals#listCrossModuleOrchestration`, `approvals#listProcessAutomationOpportunity`, `approvals#listWorkflowAutonomouGovernance` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-DRAFTED-2 | AM-APPROVALS-P08-2 | [BE] CatalogueService: approveWorkflow | 2 | Chinmay Patkar | CatalogueService | MIG-CATALOGUE-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: approveWorkflow. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Approvals · Venue Management 2 of 5; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#approveWorkflow` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | VM-ADM-250 | AM-APPROVALS-P08-2 | [BE] ADM-250 Workflow Instance Monitor & Process Timeline | 3 | Pranay Shinde |  | SETUP-CLIENTS SVC-TENANCY-APPROVALS-5 SVC-TENANCY-APPROVALS-6 | Allow administrators to inspect exactly what is happening inside an individual running workflow. Module: Platform. App: Venue Management. Done when `ADM-250` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
12 | 3 | VM-ADM-253 | AM-APPROVALS-P08-2 | [BE] ADM-253 Automation Execution & Autonomous Action Monitor | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-TENANCY-APPROVALS-8 | Provide visibility and governance over actions executed automatically by TICVAI. This becomes especially important as TICVAI becomes more AI-driven. Module: Platform. App: Venue Management. Done when `ADM-253` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
12 | 3 | VM-ADM-254 | AM-APPROVALS-P08-2 | [BE] ADM-254 Cross-Module Orchestration Monitor | 2 | Sanket Keluskar |  | SETUP-CLIENTS SVC-TENANCY-APPROVALS-8 | Monitor complex workflows involving multiple TICVAI services. Example — Group Booking Confirmation Module: Platform. App: Venue Management. Waits for its definition: ADM-254's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-254` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
12 | 3 | VM-ADM-256 | AM-APPROVALS-P08-2 | [BE] ADM-256 Process Optimization & Automation Opportunity Center | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-TENANCY-APPROVALS-8 | Identify business processes that should be simplified, redesigned or automated. This is where TICVAI moves beyond simply running workflows. Module: Platform. App: Venue Management. Done when `ADM-256` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
12 | 3 | VM-ADM-257 | AM-APPROVALS-P08-2 | [BE] ADM-257 AI Workflow Intelligence & Autonomous Governance Center | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-TENANCY-APPROVALS-8 | Create the AI intelligence layer across TICVAI's entire rules, workflow and automation ecosystem. This is the management-level AI brain for Area 13. Module: Platform. App: Venue Management. Done when `ADM-257` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
12 | 3 | VM-ADM-320 | AM-APPROVALS-P08-2 | [BE] ADM-320 Create Approval Workflow | 3 | Sanket Keluskar |  | SETUP-CLIENTS SVC-TENANCY-APPROVALS-6 | Provide a guided setup wizard for creating a new approval workflow. Step 1 — Basic Information Module: Platform. App: Venue Management. Done when `ADM-320` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
12 | 3 | VM-ADM-322 | AM-APPROVALS-P08-2 | [BE] ADM-322 Approval Stage Configuration | 2 | Sanket Keluskar |  | SETUP-CLIENTS SVC-TENANCY-APPROVALS-6 | Configure each approval stage in detail. When the administrator clicks an Approval Node in Screen 3, this screen/panel opens. Module: Platform. App: Venue Management. Done when `ADM-322` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
12 | 3 | VM-ADM-323 | AM-APPROVALS-P08-2 | [BE] ADM-323 Condition & Decision Rule Builder | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-TENANCY-APPROVALS-5 SVC-TENANCY-APPROVALS-6 | Allow administrators to determine when a particular approval path should apply. The rule builder should use business-friendly configuration rather than programming. Module: Platform. App: Venue Management. Waits for its definition: ADM-323's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-323` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
12 | 3 | VM-ADM-324 | AM-APPROVALS-P08-2 | [BE] ADM-324 Approval Sequence & Parallel Routing | 2 | Sanket Keluskar |  | SETUP-CLIENTS SVC-TENANCY-APPROVALS-6 | Configure complex multi-level approval structures. Module: Platform. App: Venue Management. Waits for its definition: ADM-324's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-324` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
12 | 3 | VM-ADM-325 | AM-APPROVALS-P08-2 | [BE] ADM-325 Workflow Outcome & Action Configuration | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-TENANCY-APPROVALS-6 | Define what TICVAI should actually do after the approval process reaches an outcome. This is important because approval and execution should be separated. Module: Platform. App: Venue Management. Waits for its definition: ADM-325's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-325` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
12 | 3 | VM-ADM-326 | AM-APPROVALS-P08-2 | [BE] ADM-326 Workflow Validation & Simulation | 2 | Sanket Keluskar |  | SETUP-CLIENTS SVC-TENANCY-APPROVALS-7 | Allow administrators to test workflows before putting them into production. This is something I strongly recommend adding to the UX because these workflows can directly affect money, access and customer operations. Module: Platform. App: Venue Management. Waits for its definition: ADM-326's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-326` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
12 | 3 | VM-ADM-327 | AM-APPROVALS-P08-2 | [BE] ADM-327 Workflow Publication & Lifecycle | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-TENANCY-APPROVALS-5 SVC-TENANCY-APPROVALS-6 | Govern the transition of workflow configurations into production. Module: Platform. App: Venue Management. Done when `ADM-327` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
12 | 3 | VM-ADM-328 | AM-APPROVALS-P08-2 | [BE] ADM-328 Workflow Versioning & Change History | 2 | Sanket Keluskar |  | SETUP-CLIENTS SVC-TENANCY-APPROVALS-5 | Maintain complete governance over changes made to approval workflows. The matrix specifically requires Approval Workflow Versioning. Module: Platform. App: Venue Management. Waits for its definition: ADM-328's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-328` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
12 | 3 | VM-ADM-330 | AM-APPROVALS-P08-2 | [BE] ADM-330 Approval Authority Matrix | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-TENANCY-MATRIX-1 | Provide a visual table showing who can approve what and up to which authority level. Module: Platform. App: Venue Management. Done when `ADM-330` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
12 | 3 | VM-ADM-331 | AM-APPROVALS-P08-2 | [BE] ADM-331 Organizational Hierarchy Routing | 2 | Sanket Keluskar |  | SETUP-CLIENTS SVC-TENANCY-MATRIX-1 | Configure approval routing based on the client's organizational hierarchy. Module: Platform. App: Venue Management. Waits for its definition: ADM-331's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-331` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
12 | 3 | VM-ADM-332 | AM-APPROVALS-P08-2 | [BE] ADM-332 Department-Based Approval Matrix | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-TENANCY-MATRIX-1 | Allow different departments to maintain different approval authority structures. Module: Platform. App: Venue Management. Done when `ADM-332` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
13 | 3 | VM-ADM-319 | AM-APPROVALS-P08-2 | [BE] ADM-319 Approval Workflow Library | 3 | Sanket Keluskar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-2 SVC-TENANCY-APPROVALS-5 | Provide a centralized directory of every approval workflow configured within the tenant. Module: Platform. App: Venue Management. Waits for its definition: ADM-319's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-319` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
13 | 3 | VM-ADM-329 | AM-APPROVALS-P08-2 | [BE] ADM-329 Approval Matrix Command Center | 3 | Sanket Keluskar |  | SETUP-CLIENTS VM-TENANCY-MATRIX-1 | Provide administrators with a centralized overview of all approval matrices configured across TICVAI. Module: Platform. App: Venue Management. Done when `ADM-329` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
8 | 3 | MIG-APPROVALS-7 | AM-APPROVALS-P08-3 | [DB] Forward migration V1103__approvals.sql: approvals for Approvals · Venue Management 3 of 5 (2 tables) | 2 | Hrushikant Patkar | TenancyService | MIG-APPROVALS MIG-BASELINE VM-MIG-APPROVALS | Tables: approvals.evidence_package, approvals.signature. Source DDL: backend/tenant/010-approvals.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `approvals.evidence_package`, `approvals.signature` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
10 | 3 | SVC-PLATFORM-PUBLICAPI-4 | AM-APPROVALS-P08-3 | [BE] PlatformService: listWebhookEventTypes | 1 | Sanket Keluskar | PlatformService | MIG-BASELINE PLATFORM-KERNEL | Operations: listWebhookEventTypes. Spec: contracts (public-api) at the release tag, served by ADAM. Built for Approvals · Venue Management 3 of 5; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `public-api#listWebhookEventTypes` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-APPROVALS-10 | AM-APPROVALS-P08-3 | [BE] TenancyService: createApprovalEvidencePackage, getApprovalRecord, listApprovalControlPolicies, listSlaEscalationBottleneck | 5 | Deep Khanvilkar | TenancyService | MIG-APPROVALS MIG-APPROVALS-2 MIG-APPROVALS-4 MIG-APPROVALS-6 MIG-APPROVALS-7 MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-APPROVALS | Operations: createApprovalEvidencePackage, getApprovalRecord, listApprovalControlPolicies, listSlaEscalationBottleneck. Spec: contracts (approvals) at the release tag, served by ADAM. Built for Approvals · Venue Management 3 of 5; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `approvals#createApprovalEvidencePackage`, `approvals#getApprovalRecord`, `approvals#listApprovalControlPolicies`, `approvals#listSlaEscalationBottleneck` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-APPROVALS-11 | AM-APPROVALS-P08-3 | [BE] TenancyService: setApprovalControlPolicy | 2 | Sanket Keluskar | TenancyService | MIG-APPROVALS-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setApprovalControlPolicy. Spec: contracts (approvals) at the release tag, served by ADAM. Built for Approvals · Venue Management 3 of 5; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `approvals#setApprovalControlPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | VM-ADM-333 | AM-APPROVALS-P08-3 | [BE] ADM-333 Venue & Tenant Approval Matrix | 2 | Sanket Keluskar |  | SETUP-CLIENTS SVC-TENANCY-MATRIX-1 | Allow approval policies to differ between TICVAI clients and between venues belonging to the same client. Module: Platform. App: Venue Management. Waits for its definition: ADM-333's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-333` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
12 | 3 | VM-ADM-334 | AM-APPROVALS-P08-3 | [BE] ADM-334 Value & Threshold Routing | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-TENANCY-MATRIX-1 | Configure approval authority according to transaction value or percentage thresholds. Example — Refund Module: Platform. App: Venue Management. Waits for its definition: ADM-334's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-334` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
12 | 3 | VM-ADM-335 | AM-APPROVALS-P08-3 | [BE] ADM-335 Risk-Based & Conditional Routing | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-TENANCY-MATRIX-1 | Dynamically modify approval routing based on the risk or context of the request. Module: Platform. App: Venue Management. Waits for its definition: ADM-335's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-335` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
12 | 3 | VM-ADM-336 | AM-APPROVALS-P08-3 | [BE] ADM-336 Approver Group & Decision Policy | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-TENANCY-APPROVALS-11 | Define cases where approval authority belongs to multiple people rather than one individual. Module: Platform. App: Venue Management. Waits for its definition: ADM-336's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-336` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
12 | 3 | VM-ADM-341 | AM-APPROVALS-P08-3 | [BE] ADM-341 Four-Eyes & Dual-Control Policy | 2 | Sanket Keluskar |  | SETUP-CLIENTS SVC-TENANCY-APPROVALS-10 SVC-TENANCY-APPROVALS-11 | Configure sensitive actions requiring approval from at least two independent authorized persons. The source explicitly requires dual approval capability for sensitive operations. Module: Platform. App: Venue Management. Done when `ADM-341` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
12 | 3 | VM-ADM-343 | AM-APPROVALS-P08-3 | [BE] ADM-343 Sensitive Action Confirmation | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-TENANCY-MATRIX-2 | Configure the final confirmation requirements before a sensitive approval becomes binding. The source specifically requires confirmation before execution of sensitive approvals. Module: Platform. App: Venue Management. Done when `ADM-343` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
12 | 3 | VM-ADM-345 | AM-APPROVALS-P08-3 | [BE] ADM-345 Immutable Approval Record & Tamper Detection | 2 | Sanket Keluskar |  | SETUP-CLIENTS SVC-TENANCY-APPROVALS-10 | Protect completed approval records from unauthorized modification. The matrix requires completed approval records to be immutable and requires detection of unauthorized modification attempts. Module: Platform. App: Venue Management. Done when `ADM-345` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
12 | 3 | VM-ADM-347 | AM-APPROVALS-P08-3 | [BE] ADM-347 Regulatory Audit & Evidence Center | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-TENANCY-APPROVALS-10 | Provide internal and external auditors with controlled access to complete approval evidence. The source specifically requires approval records suitable for regulatory audits. Module: Platform. App: Venue Management. Waits for its definition: ADM-347's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-347` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
12 | 3 | VM-ADM-350 | AM-APPROVALS-P08-3 | [BE] ADM-350 Module Integration Registry | 2 | Sanket Keluskar |  | SETUP-CLIENTS SVC-TENANCY-APPROVALS-8 | Define which TICVAI modules are allowed to initiate and consume approval workflows. Module: Platform. App: Venue Management. Waits for its definition: ADM-350's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-350` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
12 | 3 | VM-ADM-352 | AM-APPROVALS-P08-3 | [BE] ADM-352 Workflow Event Framework | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-PLATFORM-PUBLICAPI-4 SVC-TENANCY-APPROVALS-6 | Configure the business events published by the Approval Engine. The matrix requires workflow events to be published through the platform event framework. Module: Platform. App: Venue Management. Waits for its definition: ADM-352's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-352` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
12 | 3 | VM-ADM-355 | AM-APPROVALS-P08-3 | [BE] ADM-355 Data & Workflow Mapping Studio | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-TENANCY-APPROVALS-6 | Map external system data to TICVAI's approval data model without requiring custom development for every integration. Module: Platform. App: Venue Management. Waits for its definition: ADM-355's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-355` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
13 | 3 | VM-ADM-338 | AM-APPROVALS-P08-3 | [BE] ADM-338 AI Routing Advisor & Matrix Optimization | 2 | Chinmay Patkar |  | SETUP-CLIENTS VM-TENANCY-MATRIX-1 | Use TICVAI AI to analyze approval behavior and recommend improvements to the approval matrix. The source requires AI risk assessment, priority scoring and escalation recommendations. Module: Platform. App: Venue Management. Waits for its definition: ADM-338's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-338` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
13 | 3 | VM-ADM-349 | AM-APPROVALS-P08-3 | [BE] ADM-349 Approval Integration Command Center | 3 | Sanket Keluskar |  | SETUP-CLIENTS SVC-TENANCY-APPROVALS-8 SVC-TENANCY-MATRIX-2 SVC-TENANCY-REQUEST-5 | Provide administrators and technical teams with a centralized overview of all systems connected to the Approval Engine. Module: Platform. App: Venue Management. Done when `ADM-349` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-337 | AM-APPROVALS-P08-3 | [BE] ADM-337 Routing Simulator & Conflict Detection | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-TENANCY-APPROVALS-7 SVC-TENANCY-REQUEST-1 | Allow administrators to test the complete approval matrix before deployment. This is particularly important because Board 3 can contain hundreds of combinations. Module: Platform. App: Venue Management. Waits for its definition: ADM-337's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-337` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-339 | AM-APPROVALS-P08-3 | [BE] ADM-339 Governance & Compliance Command Center | 3 | Sanket Keluskar |  | SETUP-CLIENTS SVC-TENANCY-ANALYTICS-1 SVC-TENANCY-APPROVALS-10 | Provide administrators, auditors and security teams with an overview of approval governance health across the organization. Module: Platform. App: Venue Management. Done when `ADM-339` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-348 | AM-APPROVALS-P08-3 | [BE] ADM-348 Governance Risk & AI Compliance Advisor | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-TENANCY-ANALYTICS-1 | Use AI to identify unusual governance patterns, potential policy weaknesses and compliance risks. This screen should assist compliance teams rather than automatically change governance policies. Module: Platform. App: Venue Management. Waits for its definition: ADM-348's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-348` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-359 | AM-APPROVALS-P08-3 | [BE] ADM-359 Approval Executive KPI Dashboard | 3 | Surendra |  | SETUP-CLIENTS SVC-TENANCY-ANALYTICS-1 | Provide executives and senior management with a high-level view of approval performance across TICVAI. Module: Platform. App: Venue Management. Waits for its definition: ADM-359's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-359` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-360 | AM-APPROVALS-P08-3 | [BE] ADM-360 Approval Volume & Outcome Analytics | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-TENANCY-ANALYTICS-1 | Analyze how many approval requests are being generated and what happens to them. Module: Platform. App: Venue Management. Waits for its definition: ADM-360's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-360` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-361 | AM-APPROVALS-P08-3 | [BE] ADM-361 Approval Processing Time Analytics | 2 | Sanket Keluskar |  | SETUP-CLIENTS SVC-TENANCY-ANALYTICS-1 | Measure exactly how long approval processes and individual stages take. The matrix explicitly requires processing-time analytics. Module: Platform. App: Venue Management. Waits for its definition: ADM-361's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-361` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
11 | 3 | SVC-TENANCY-APPROVALS-12 | AM-APPROVALS-P08-4 | [BE] TenancyService: listSlaEscalationReminder, signApprovalDecision | 2 | Chinmay Patkar | TenancyService | MIG-APPROVALS MIG-APPROVALS-4 MIG-APPROVALS-7 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listSlaEscalationReminder, signApprovalDecision. Spec: contracts (approvals) at the release tag, served by ADAM. Built for Approvals · Venue Management 4 of 5; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `approvals#listSlaEscalationReminder`, `approvals#signApprovalDecision` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | VM-ADM-362 | AM-APPROVALS-P08-4 | [BE] ADM-362 Bottleneck Analysis & Heatmap | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-TENANCY-APPROVALS-10 | Automatically identify where approval processes are becoming slow or congested. The source explicitly requires approval bottleneck analysis. Module: Platform. App: Venue Management. Done when `ADM-362` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
12 | 3 | VM-ADM-367 | AM-APPROVALS-P08-4 | [BE] ADM-367 AI Optimization & What-If Simulator | 2 | Sanket Keluskar |  | SETUP-CLIENTS SVC-TENANCY-APPROVALS-7 | Allow management to evaluate proposed governance changes before implementing them. Module: Platform. App: Venue Management. Waits for its definition: ADM-367's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-367` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-363 | AM-APPROVALS-P08-4 | [BE] ADM-363 Approval Trend & Comparative Analytics | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-TENANCY-ANALYTICS-1 | Identify whether approval performance is improving or deteriorating over time. The matrix specifically requires approval trend reporting. Module: Platform. App: Venue Management. Waits for its definition: ADM-363's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-363` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-364 | AM-APPROVALS-P08-4 | [BE] ADM-364 Approver & Team Performance Analytics | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-TENANCY-ANALYTICS-1 | Understand workload and operational performance at approver and team level without reducing governance to a simplistic employee ranking. Module: Platform. App: Venue Management. Done when `ADM-364` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-366 | AM-APPROVALS-P08-4 | [BE] ADM-366 AI Approval Intelligence Center | 2 | Sanket Keluskar |  | SETUP-CLIENTS SVC-TENANCY-ANALYTICS-1 VM-AI-RISK-1 | Provide one centralized location for AI-generated approval intelligence. This should be one of the strongest screens in the entire module. Module: Platform. App: Venue Management. Waits for its definition: ADM-366's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-366` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-368 | AM-APPROVALS-P08-4 | [BE] ADM-368 AI Governance Executive Advisor | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-TENANCY-ANALYTICS-1 | Turn all approval analytics into prioritized management recommendations. Instead of management examining dozens of dashboards, TICVAI AI should answer: “What requires my attention?” Module: Platform. App: Venue Management. Waits for its definition: ADM-368's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-368` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
8 | 3 | MIG-APPROVALS-8 | AM-APPROVALS-P08-5 | [DB] Forward migration V1105__approvals.sql: approvals for Approvals · Venue Management 5 of 5 (1 tables) | 1 | Hrushikant Patkar | TenancyService | MIG-APPROVALS MIG-BASELINE VM-MIG-APPROVALS | Tables: approvals.approver_availability. Source DDL: backend/tenant/010-approvals.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `approvals.approver_availability` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-TENANCY-APPROVALS-13 | AM-APPROVALS-P08-5 | [BE] TenancyService: setApprovalSlaPolicy, setApproverAvailability | 3 | Sanket Keluskar | TenancyService | MIG-APPROVALS-4 MIG-APPROVALS-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setApprovalSlaPolicy, setApproverAvailability. Spec: contracts (approvals) at the release tag, served by ADAM. Built for Approvals · Venue Management 5 of 5; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `approvals#setApprovalSlaPolicy`, `approvals#setApproverAvailability` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-PLATFORM-DRAFTED-14 | AM-SUBSCRIPTION-LICENSING-P10-2 | [BE] PlatformService: listPartnerCancellationRefund, listPartnerDisputeCase, listPartnerPerformanceScorecard, listPartnerRelationship | 8 | Surendra | PlatformService | MIG-APPROVALS MIG-APPROVALS-4 MIG-CONTROL MIG-CONTROL-3 MIG-CONTROL-7 MIG-ORDERS PLATFORM-KERNEL SVC-FNB-FNB-12 SVC-IDENTITY-GUESTAUTH-2 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-DRAFTED-1 SVC-PLATFORM-DRAFTED-12 SVC-PLATFORM-DRAFTED-13 SVC-PLATFORM-DRAFTED-2 SVC-PLATFORM-DRAFTED-9 SVC-PLATFORM-SUBSCRIPTION-16 SVC-PLATFORM-SUBSCRIPTION-17 SVC-PLATFORM-SUBSCRIPTION-20 SVC-PLATFORM-SUBSCRIPTION-4 SVC-PLATFORM-SUBSCRIPTION-5 SVC-PLATFORM-SUBSCRIPTION-6 SVC-PLATFORM-SUBSCRIPTION-7 SVC-PLATFORM-SUBSCRIPTION-8 SVC-PLATFORM-SUBSCRIPTION-9 SVC-TENANCY-APPROVALS-13 SVC-TENANCY-APPROVALS-2 SVC-TENANCY-APPROVALS-4 SVC-TENANCY-APPROVALS-5 SVC-TENANCY-REQUEST-1 SVC-TENANCY-REQUEST-2 SVC-TENANCY-REQUEST-3 SVC-TENANCY-ROTA-2 SVC-WALLET-RETAIL-1 VM-ORDER-REFUND-1 VM-TENANCY-REQUEST-1 | Operations: listPartnerCancellationRefund, listPartnerDisputeCase, listPartnerPerformanceScorecard, listPartnerRelationship. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Partner Portal 2 of 2; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#listPartnerCancellationRefund`, `subscription#listPartnerDisputeCase`, `subscription#listPartnerPerformanceScorecard`, `subscription#listPartnerRelationship` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-REQUEST-4 | AM-APPROVALS-P08-5 | [BE] TenancyService: listApprovedActionExecutions, resolveApprovedActionExecution | 3 | Sanket Keluskar | TenancyService | MIG-APPROVALS-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listApprovedActionExecutions, resolveApprovedActionExecution. Spec: contracts (approvals) at the release tag, served by ADAM. Built for Approvals · Venue Management 5 of 5; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `approvals#listApprovedActionExecutions`, `approvals#resolveApprovedActionExecution` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-TENANCY-APPROVALS-9 | AM-APPROVALS-P08-2 | [BE] TenancyService: listWorkflowExceptionFailure, listWorkflowProcessPerformance | 3 | Sanket Keluskar | TenancyService | MIG-APPROVALS MIG-APPROVALS-2 MIG-APPROVALS-4 MIG-APPROVALS-5 MIG-APPROVALS-6 PLATFORM-KERNEL SVC-PLATFORM-DRAFTED-1 SVC-PLATFORM-DRAFTED-12 SVC-PLATFORM-DRAFTED-13 SVC-PLATFORM-DRAFTED-2 SVC-PLATFORM-DRAFTED-9 SVC-PLATFORM-SUBSCRIPTION-16 SVC-PLATFORM-SUBSCRIPTION-17 SVC-PLATFORM-SUBSCRIPTION-5 SVC-PLATFORM-SUBSCRIPTION-7 SVC-PLATFORM-SUBSCRIPTION-8 SVC-TENANCY-APPROVALS-1 SVC-TENANCY-APPROVALS-13 SVC-TENANCY-APPROVALS-2 SVC-TENANCY-APPROVALS-4 SVC-TENANCY-APPROVALS-5 SVC-TENANCY-APPROVALS-6 SVC-TENANCY-DELEGATION-1 SVC-TENANCY-DELEGATION-2 SVC-TENANCY-REQUEST-1 SVC-TENANCY-REQUEST-2 SVC-TENANCY-REQUEST-3 SVC-TENANCY-REQUEST-4 SVC-TENANCY-ROTA-2 VM-MIG-APPROVALS VM-TENANCY-REQUEST-1 | Operations: listWorkflowExceptionFailure, listWorkflowProcessPerformance. Spec: contracts (approvals) at the release tag, served by ADAM. Built for Approvals · Venue Management 2 of 5; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `approvals#listWorkflowExceptionFailure`, `approvals#listWorkflowProcessPerformance` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | VM-ADM-251 | AM-APPROVALS-P08-2 | [BE] ADM-251 Workflow Exception, Failure & Recovery Center | 2 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-TENANCY-APPROVALS-5 SVC-TENANCY-APPROVALS-9 | Provide one controlled workspace for failed workflow executions. Module: Platform. App: Venue Management. Done when `ADM-251` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-255 | AM-APPROVALS-P08-2 | [BE] ADM-255 Workflow Analytics & Process Performance | 3 | Sanket Keluskar |  | SETUP-CLIENTS SVC-TENANCY-APPROVALS-9 | Measure how effectively TICVAI's business workflows are performing. Module: Platform. App: Venue Management. Done when `ADM-255` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-357 | AM-APPROVALS-P08-3 | [BE] ADM-357 Integration Monitoring, Error & Retry Center | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-TENANCY-APPROVALS-9 SVC-TENANCY-REQUEST-5 | Provide technical teams with real-time monitoring of integration failures. Module: Platform. App: Venue Management. Waits for its definition: ADM-357's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-357` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-358 | AM-APPROVALS-P08-3 | [BE] ADM-358 Integration Analytics & AI Health Advisor | 2 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-TENANCY-APPROVALS-9 | Provide technical and business teams with analytics on Approval Engine integration performance. Module: Platform. App: Venue Management. Waits for its definition: ADM-358's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-358` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | SVC-AI-ACTIONS-2 | AM-APPROVALS-P09 | [BE] AiService: getActionPlan | 2 | Chinmay Patkar | AiService | MIG-AI MIG-AI-2 PLATFORM-KERNEL SVC-AI-GENERATE-2 SVC-AI-GOVERNANCE-1 SVC-AI-GOVERNANCE-2 | Operations: getActionPlan. Spec: contracts (ai) at the release tag, served by ADAM. Built for Approvals · TICVAI Console; additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#getActionPlan` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-PLATFORM-PUBLICAPI-5 | AM-PUBLIC-API-P08 | [BE] PlatformService: getApiUsage, issueApiToken, testWebhookSubscription | 3 | Sanket Keluskar | PlatformService | MIG-CONTROL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-CONTROL | Operations: getApiUsage, issueApiToken, testWebhookSubscription. Spec: contracts (public-api) at the release tag, served by ADAM. Built for Public API · Venue Management; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `public-api#getApiUsage`, `public-api#issueApiToken`, `public-api#testWebhookSubscription` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-PLATFORM-DRAFTED-10 | AM-SUBSCRIPTION-LICENSING-P10 | [BE] PlatformService: listCommercialAgreement, listCommercialAgreementHealth, listPartner, listPartner2 | 8 | Pranay Shinde | PlatformService | MIG-APPROVALS MIG-CONTROL MIG-CONTROL-3 MIG-CONTROL-7 MIG-LEDGER MIG-ORDERS PLATFORM-KERNEL SVC-FNB-FNB-12 SVC-IDENTITY-GUESTAUTH-2 SVC-LEDGER-FINANCE-1 SVC-LEDGER-FINANCE-3 SVC-LEDGER-LEDGER-1 SVC-LEDGER-LEDGER-3 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-DRAFTED-1 SVC-PLATFORM-DRAFTED-12 SVC-PLATFORM-DRAFTED-13 SVC-PLATFORM-DRAFTED-2 SVC-PLATFORM-DRAFTED-9 SVC-PLATFORM-PUBLICAPI-1 SVC-PLATFORM-PUBLICAPI-11 SVC-PLATFORM-PUBLICAPI-2 SVC-PLATFORM-PUBLICAPI-5 SVC-PLATFORM-PUBLICAPI-9 SVC-PLATFORM-SUBSCRIPTION-16 SVC-PLATFORM-SUBSCRIPTION-17 SVC-PLATFORM-SUBSCRIPTION-20 SVC-PLATFORM-SUBSCRIPTION-4 SVC-PLATFORM-SUBSCRIPTION-5 SVC-PLATFORM-SUBSCRIPTION-6 SVC-PLATFORM-SUBSCRIPTION-7 SVC-PLATFORM-SUBSCRIPTION-8 SVC-PLATFORM-SUBSCRIPTION-9 SVC-TENANCY-APPROVALS-2 SVC-TENANCY-APPROVALS-4 SVC-TENANCY-APPROVALS-5 SVC-TENANCY-REQUEST-1 SVC-TENANCY-REQUEST-2 SVC-TENANCY-REQUEST-3 SVC-TENANCY-ROTA-2 SVC-WALLET-RETAIL-1 VM-LEDGER-FINANCE-1 VM-LEDGER-RECOGNITION-1 VM-MIG-CONTROL VM-ORDER-ORDERS-2 VM-ORDER-REFUND-1 VM-ORDER-SHIFT-1 VM-TENANCY-REQUEST-1 | Operations: listCommercialAgreement, listCommercialAgreementHealth, listPartner, listPartner2. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Partner Portal 1 of 2; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#listCommercialAgreement`, `subscription#listCommercialAgreementHealth`, `subscription#listPartner`, `subscription#listPartner2` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-WALLET-WALLET-3 | AM-PUBLIC-API-P08 | [BE] WalletService: setWalletRiskRules | 2 | Pranay Shinde | WalletService | MIG-WALLET MIG-WALLET-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setWalletRiskRules. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Public API · Venue Management; additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#setWalletRiskRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | VM-ADM-356 | AM-PUBLIC-API-P08 | [BE] ADM-356 Integration Security & Access Control | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-IDENTITY-ADMINISTRATION-5 SVC-PLATFORM-PUBLICAPI-2 VM-PLATFORM-PUBLICAPI-1 | Govern which applications and external systems can access the Approval Engine. Module: Platform. App: Venue Management. Waits for its definition: ADM-356's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-356` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-351 | AM-PUBLIC-API-P08 | [BE] ADM-351 Approval API Management | 3 | Hrushikant Patkar |  | SETUP-CLIENTS SVC-PLATFORM-PUBLICAPI-5 SVC-PLATFORM-PUBLICAPI-7 VM-PLATFORM-PUBLICAPI-1 | Configure and monitor APIs used to create, retrieve and process approval requests. The matrix explicitly requires approval workflows to be exposed through APIs. Module: Platform. App: Venue Management. Done when `ADM-351` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
6 | 3 | MIG-CONTROL-11 | AM-PUBLIC-API-P09 | [DB] Forward migration V1108__control.sql: control for Public API · TICVAI Console (1 tables) | 1 | Hrushikant Patkar | PlatformService | MIG-BASELINE MIG-CONTROL VM-MIG-CONTROL | Tables: control.api_anomaly. Source DDL: backend/control/010-control.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `control.api_anomaly` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
10 | 3 | SVC-PLATFORM-PUBLICAPI-6 | AM-PUBLIC-API-P09 | [BE] PlatformService: listApiAnomalies | 1 | Sanket Keluskar | PlatformService | MIG-CONTROL-11 PLATFORM-KERNEL | Operations: listApiAnomalies. Spec: contracts (public-api) at the release tag, served by ADAM. Built for Public API · TICVAI Console; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `public-api#listApiAnomalies` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
6 | 3 | MIG-CONTROL-12 | AM-PUBLIC-API-P14 | [DB] Forward migration V1189__control.sql: control for Public API · Developer Portal (1 tables) | 1 | Hrushikant Patkar | PlatformService | MIG-BASELINE MIG-CONTROL VM-MIG-CONTROL | Tables: control.sandbox. Source DDL: backend/control/010-control.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `control.sandbox` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-PLATFORM-PUBLICAPI-8 | AM-PUBLIC-API-P14 | [BE] PlatformService: createSandbox, listSandboxes, resetSandbox, submitIntegrationListing | 5 | Pranay Shinde | PlatformService | MIG-CONTROL MIG-CONTROL-12 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createSandbox, listSandboxes, resetSandbox, submitIntegrationListing. Spec: contracts (public-api) at the release tag, served by ADAM. Built for Public API · Developer Portal; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `public-api#createSandbox`, `public-api#listSandboxes`, `public-api#resetSandbox`, `public-api#submitIntegrationListing` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
7 | 3 | MIG-ASSETS-2 | AM-DIGITAL-ASSETS-P13-2 | [DB] Forward migration V1109__assets.sql: assets for Digital Assets · CMS 2 of 4 (6 tables) | 5 | Hrushikant Patkar | VenueOpsService | MIG-ASSETS MIG-BASELINE | Tables: assets.audit, assets.distribution_channel, assets.rendition, assets.share, assets.tag, assets.taxonomy. Source DDL: backend/tenant/010-assets.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `assets.audit`, `assets.distribution_channel`, `assets.rendition`, `assets.share`, `assets.tag`, `assets.taxonomy` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-VENUEOPS-ASSETS-1 | AM-DIGITAL-ASSETS-P13-2 | [BE] VenueOpsService: analyseMediaAsset, bulkUpdateMediaAssets, findSimilarMediaAssets, getMediaDistribution | 5 | New full-stack developer 2 | VenueOpsService | MIG-ASSETS MIG-ASSETS-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: analyseMediaAsset, bulkUpdateMediaAssets, findSimilarMediaAssets, getMediaDistribution. Spec: contracts (assets) at the release tag, served by ADAM. Built for Digital Assets · CMS 2 of 4; additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `assets#analyseMediaAsset`, `assets#bulkUpdateMediaAssets`, `assets#findSimilarMediaAssets`, `assets#getMediaDistribution` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-ASSETS-3 | AM-DIGITAL-ASSETS-P13-2 | [BE] VenueOpsService: requestMediaRendition, setMediaAssetTags, setMediaTaxonomy | 5 | Surendra | VenueOpsService | MIG-ASSETS-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: requestMediaRendition, setMediaAssetTags, setMediaTaxonomy. Spec: contracts (assets) at the release tag, served by ADAM. Built for Digital Assets · CMS 2 of 4; additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `assets#requestMediaRendition`, `assets#setMediaAssetTags`, `assets#setMediaTaxonomy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
7 | 3 | MIG-ASSETS-3 | AM-DIGITAL-ASSETS-P13-3 | [DB] Forward migration V1110__assets.sql: assets for Digital Assets · CMS 3 of 4 (1 tables) | 1 | Hrushikant Patkar | VenueOpsService | MIG-ASSETS MIG-BASELINE | Tables: assets.approval. Source DDL: backend/tenant/010-assets.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `assets.approval` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-VENUEOPS-ASSETS-5 | AM-DIGITAL-ASSETS-P13-3 | [BE] VenueOpsService: setMediaDistributionChannels | 1 | Hrushikant Patkar | VenueOpsService | MIG-ASSETS-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setMediaDistributionChannels. Spec: contracts (assets) at the release tag, served by ADAM. Built for Digital Assets · CMS 3 of 4; additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `assets#setMediaDistributionChannels` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-ASSETS-4 | AM-DIGITAL-ASSETS-P13-3 | [BE] VenueOpsService: createMediaShare, listMediaAssetAudit, setMediaAssetApproval, setMediaAssetRights | 5 | Tanmay Dukhande | VenueOpsService | MIG-ASSETS MIG-ASSETS-2 MIG-ASSETS-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createMediaShare, listMediaAssetAudit, setMediaAssetApproval, setMediaAssetRights. Spec: contracts (assets) at the release tag, served by ADAM. Built for Digital Assets · CMS 3 of 4; additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `assets#createMediaShare`, `assets#listMediaAssetAudit`, `assets#setMediaAssetApproval`, `assets#setMediaAssetRights` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-VENUEOPS-ASSETS-2 | AM-DIGITAL-ASSETS-P13-2 | [BE] VenueOpsService: getMediaTaxonomy, getMediaUsageAnalytics, listMediaAssetVersions, listMediaRenditions | 3 | New full-stack developer 1 | VenueOpsService | MIG-ASSETS MIG-ASSETS-2 PLATFORM-KERNEL SVC-VENUEOPS-ASSET-1 SVC-VENUEOPS-ASSET-2 SVC-VENUEOPS-ASSETS-1 SVC-VENUEOPS-ASSETS-3 SVC-VENUEOPS-ASSETS-4 SVC-VENUEOPS-UPLOAD-1 | Operations: getMediaTaxonomy, getMediaUsageAnalytics, listMediaAssetVersions, listMediaRenditions. Spec: contracts (assets) at the release tag, served by ADAM. Built for Digital Assets · CMS 2 of 4; additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `assets#getMediaTaxonomy`, `assets#getMediaUsageAnalytics`, `assets#listMediaAssetVersions`, `assets#listMediaRenditions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-WHITELABEL-OVERVIEW-3 | AM-WHITE-LABEL-P08 | [BE] WhiteLabelService: getStorefrontInsights | 2 | New full-stack developer 1 | WhiteLabelService | MIG-WHITELABEL PLATFORM-KERNEL SVC-WHITELABEL-OVERVIEW-2 | Operations: getStorefrontInsights. Spec: contracts (white-label) at the release tag, served by ADAM. Built for White Label · Venue Management; additive to WhiteLabelService, whose first-release owner (Tanmay Dukhande) reviews. Done when `white-label#getStorefrontInsights` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-CATALOGUE-BUNDLE-1 | AM-TICKETING-P06 | [BE] CatalogueService: reportBundleApplied | 1 | Chinmay Patkar | CatalogueService | MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: reportBundleApplied. Additive to CatalogueService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#reportBundleApplied` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-CATALOGUE-CATALOGUE-1 | AM-TICKETING-P08 | [BE] CatalogueService: createDonationCampaign, listDonationCampaigns, listWaitlistEntries, offerWaitlistCapacity | 5 | Deep Khanvilkar | CatalogueService | MIG-CATALOGUE MIG-LEDGER PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-CATALOGUE | Operations beyond the first release: createDonationCampaign, listDonationCampaigns, listWaitlistEntries, offerWaitlistCapacity. Additive to CatalogueService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#createDonationCampaign`, `catalogue#listDonationCampaigns`, `catalogue#listWaitlistEntries`, `catalogue#offerWaitlistCapacity` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-CATALOGUE-CATALOGUE-2 | AM-TICKETING-P08 | [BE] CatalogueService: updateDonationCampaign | 2 | Chinmay Patkar | CatalogueService | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-CATALOGUE | Operations beyond the first release: updateDonationCampaign. Additive to CatalogueService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#updateDonationCampaign` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-CATALOGUE-EVENTS-1 | AM-TICKETING-P08 | [BE] CatalogueService: listPerformanceTemplates, setPerformanceTemplate | 2 | Chinmay Patkar | CatalogueService | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-CATALOGUE | Operations beyond the first release: listPerformanceTemplates, setPerformanceTemplate. Additive to CatalogueService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `catalogue#listPerformanceTemplates`, `catalogue#setPerformanceTemplate` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | MIG-CATALOGUE-7 | AM-TICKETING-P08-2 | [DB] Forward migration V1120__catalogue.sql: catalogue for Ticketing · Venue Management 2 of 10 (12 tables) | 8 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-CATALOGUE VM-MIG-CATALOGUE | Tables: catalogue.ai_catalogue_session, catalogue.ai_finding, catalogue.change_request, catalogue.change_request_line, catalogue.configuration_template, catalogue.lifecycle_action, catalogue.lifecycle_workflow, catalogue.price_list_version, catalogue.pricing_publication, catalogue.product_channel_assignment, catalogue.product_link, catalogue.sales_channel. Source DDL: backend/tenant/010-catalogue.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0102__after_r1_20261013.sql (catalogue.sales_channel: column ticket_credential_format); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `catalogue.ai_catalogue_session`, `catalogue.ai_finding`, `catalogue.change_request`, `catalogue.change_request_line`, `catalogue.configuration_template`, `catalogue.lifecycle_action`, `catalogue.lifecycle_workflow`, `catalogue.price_list_version` and 4 more runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
12 | 3 | SVC-CATALOGUE-CATALOGUE-9 | AM-TICKETING-P08-2 | [BE] CatalogueService: decideCatalogueAiFinding, requestPricingRollback, setConfigurationTemplate, setProductLinks | 8 | New full-stack developer 2 | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-3 MIG-CATALOGUE-4 MIG-CATALOGUE-7 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: decideCatalogueAiFinding, requestPricingRollback, setConfigurationTemplate, setProductLinks. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 2 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#decideCatalogueAiFinding`, `catalogue#requestPricingRollback`, `catalogue#setConfigurationTemplate`, `catalogue#setProductLinks` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-DRAFTED-11 | AM-TICKETING-P08-2 | [BE] CatalogueService: setProductContextOwnership | 2 | New full-stack developer 2 | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setProductContextOwnership. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 2 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#setProductContextOwnership` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-CATALOGUE-DRAFTED-7 | AM-TICKETING-P08-2 | [BE] CatalogueService: approveReviewDecision, listChangeImpactAnalysis, listChangePropagationDependency, listGovernanceRiskMonitoring | 5 | Surendra | CatalogueService | MIG-ACCESS MIG-CATALOGUE MIG-CATALOGUE-3 MIG-CATALOGUE-7 MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: approveReviewDecision, listChangeImpactAnalysis, listChangePropagationDependency, listGovernanceRiskMonitoring. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 2 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#approveReviewDecision`, `catalogue#listChangeImpactAnalysis`, `catalogue#listChangePropagationDependency`, `catalogue#listGovernanceRiskMonitoring` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-CATALOGUE-DRAFTED-10 | AM-TICKETING-P08-2 | [BE] CatalogueService: publishActivationScheduler, publishChannelAvailability, setCatalogueReview, setLifecycleStatuWorkflow | 8 | Pranay Shinde | CatalogueService | MIG-ACCESS MIG-CATALOGUE MIG-CATALOGUE-3 MIG-CATALOGUE-7 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: publishActivationScheduler, publishChannelAvailability, setCatalogueReview, setLifecycleStatuWorkflow. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 2 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#publishActivationScheduler`, `catalogue#publishChannelAvailability`, `catalogue#setCatalogueReview`, `catalogue#setLifecycleStatuWorkflow` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | VM-ADM-123 | AM-TICKETING-P08-2 | [BE] ADM-123 Product Context, Ownership & Assignment | 2 | New full-stack developer 2 |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-11 | Define where the product belongs and who is responsible for it. Module: Catalogue. App: Venue Management. Waits for its definition: ADM-123's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-123` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
13 | 3 | VM-ADM-129 | AM-TICKETING-P08-2 | [BE] ADM-129 Approval Workflow Designer | 3 | New full-stack developer 2 |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-2 VM-TENANCY-MATRIX-1 | Configure reusable approval workflows governing product creation and modification. Module: Catalogue. App: Venue Management. Done when `ADM-129` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-120 | AM-TICKETING-P08-2 | [BE] ADM-120 Lifecycle Status & Workflow Configuration | 2 | New full-stack developer 2 |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-10 | Configure how products move between lifecycle states. Module: Catalogue. App: Venue Management. Waits for its definition: ADM-120's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-120` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-124 | AM-TICKETING-P08-2 | [BE] ADM-124 Channel Publication & Availability | 2 | New full-stack developer 1 |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-10 | Control where a product may be exposed for sale. Module: Catalogue. App: Venue Management. Waits for its definition: ADM-124's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-124` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-127 | AM-TICKETING-P08-2 | [BE] ADM-127 AI Catalogue Builder & Configuration Review | 2 | Sanket Keluskar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-10 | Provide TICVAI's AI-first interface for accelerating product creation and configuration. This directly supports the matrix requirement allowing administrators to upload spreadsheets, brochures, PDFs or existing catalogues and use AI to generate product structures, pricing, rules, entitlements and configurations. Board 2 governs what happens after a product has been created or while an existing product is being changed. Module: Catalogue. App: Venue Management. Waits for its definition: ADM-127's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-127` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-130 | AM-TICKETING-P08-2 | [BE] ADM-130 Approval Review & Decision Workspace | 2 | New full-stack developer 2 |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-7 SVC-TENANCY-REQUEST-1 | Give approvers a clear interface for reviewing a proposed product or product change before making a decision. Module: Catalogue. App: Venue Management. Waits for its definition: ADM-130's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-130` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-133 | AM-TICKETING-P08-2 | [BE] ADM-133 Change Impact Analysis | 2 | New full-stack developer 1 |  | SETUP-CLIENTS SVC-CATALOGUE-CATALOGUE-9 SVC-CATALOGUE-DRAFTED-7 | Show administrators what will be affected before a product change is approved or published. This directly addresses the matrix requirement to perform impact analysis before product changes are published. Module: Catalogue. App: Venue Management. Waits for its definition: ADM-133's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-133` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-134 | AM-TICKETING-P08-2 | [BE] ADM-134 Change Propagation & Dependency Control | 2 | Sanket Keluskar |  | SETUP-CLIENTS SVC-CATALOGUE-CATALOGUE-9 SVC-CATALOGUE-DRAFTED-7 | Control whether approved product changes should automatically propagate to related products or dependent configurations. The source matrix requires controlled propagation of changes to linked products. Module: Catalogue. App: Venue Management. Waits for its definition: ADM-134's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-134` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-137 | AM-TICKETING-P08-2 | [BE] ADM-137 Governance Risk, AI Monitoring & Control Center | 2 | New full-stack developer 1 |  | SETUP-CLIENTS SVC-CATALOGUE-CATALOGUE-9 SVC-CATALOGUE-DRAFTED-7 | Use TICVAI intelligence to continuously identify catalogue governance risks rather than relying entirely on administrators to discover them manually. Module: Catalogue. App: Venue Management. Done when `ADM-137` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
11 | 3 | MIG-CATALOGUE-8 | AM-TICKETING-P08-3 | [DB] Forward migration V1121__catalogue.sql: catalogue for Ticketing · Venue Management 3 of 10 (2 tables) | 2 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-CATALOGUE VM-MIG-CATALOGUE | Tables: catalogue.price_category, catalogue.pricing_market. Source DDL: backend/tenant/010-catalogue.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `catalogue.price_category`, `catalogue.pricing_market` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
12 | 3 | SVC-CATALOGUE-CATALOGUE-10 | AM-TICKETING-P08-3 | [BE] CatalogueService: setMarketPricingConfiguration, setPriceCategoryRateType | 5 | Hrushikant Patkar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-3 MIG-CATALOGUE-4 MIG-CATALOGUE-6 MIG-CATALOGUE-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setMarketPricingConfiguration, setPriceCategoryRateType. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 3 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#setMarketPricingConfiguration`, `catalogue#setPriceCategoryRateType` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-DRAFTED-16 | AM-TICKETING-P08-3 | [BE] CatalogueService: setPriceHierarchyInheritance, setTaxRuleTreatment, testPricingRule | 8 | Hrushikant Patkar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-3 MIG-CATALOGUE-5 MIG-CATALOGUE-6 MIG-PRICING-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setPriceHierarchyInheritance, setTaxRuleTreatment, testPricingRule. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 3 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#setPriceHierarchyInheritance`, `catalogue#setTaxRuleTreatment`, `catalogue#testPricingRule` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | VM-ADM-055 | AM-TICKETING-P08-3 | [BE] ADM-055 Price Hierarchy & Inheritance Configuration | 2 | Sanket Keluskar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-16 | Define where TICVAI should obtain a price when multiple commercial pricing layers exist. This is essential to prevent conflicting prices. Module: Commercial. App: Venue Management. Done when `ADM-055` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
13 | 3 | VM-ADM-070 | AM-TICKETING-P08-3 | [BE] ADM-070 Tax Rule & Treatment Builder | 2 | Sanket Keluskar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-16 | Define how taxes are applied to products and transactions. Module: Commercial. App: Venue Management. Waits for its definition: ADM-070's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-070` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
11 | 3 | MIG-CATALOGUE-9 | AM-TICKETING-P08-4 | [DB] Forward migration V1122__catalogue.sql: catalogue for Ticketing · Venue Management 4 of 10 (1 tables) | 1 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-CATALOGUE VM-MIG-CATALOGUE | Tables: catalogue.pricing_publication_target. Source DDL: backend/tenant/010-catalogue.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `catalogue.pricing_publication_target` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
12 | 3 | SVC-CATALOGUE-CATALOGUE-11 | AM-TICKETING-P08-4 | [BE] CatalogueService: cancelPricingRollback, setCurrencyRoundingRule, setFeeDefinition, setPriceCalculationPolicy | 8 | Hrushikant Patkar | CatalogueService | MIG-CATALOGUE-3 MIG-CATALOGUE-4 MIG-CATALOGUE-6 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: cancelPricingRollback, setCurrencyRoundingRule, setFeeDefinition, setPriceCalculationPolicy. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 4 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#cancelPricingRollback`, `catalogue#setCurrencyRoundingRule`, `catalogue#setFeeDefinition`, `catalogue#setPriceCalculationPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-DRAFTED-17 | AM-TICKETING-P08-4 | [BE] CatalogueService: approvePricingWorkflowAuthority, decidePricingChangeRequest, listBulkPricingUpdate, listCurrencyPrecisionRounding | 8 | Pranay Shinde | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-3 MIG-CATALOGUE-6 MIG-CATALOGUE-7 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: approvePricingWorkflowAuthority, decidePricingChangeRequest, listBulkPricingUpdate, listCurrencyPrecisionRounding. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 4 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#approvePricingWorkflowAuthority`, `catalogue#decidePricingChangeRequest`, `catalogue#listBulkPricingUpdate`, `catalogue#listCurrencyPrecisionRounding` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-DRAFTED-20 | AM-TICKETING-P08-4 | [BE] CatalogueService: publishPricingEffectiveDate, setFeeApplicabilityCharging, setPricingChangeRequest, submitPricingChangeRequest | 8 | Tanmay Dukhande | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-3 MIG-CATALOGUE-6 MIG-CATALOGUE-7 MIG-CATALOGUE-9 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: publishPricingEffectiveDate, setFeeApplicabilityCharging, setPricingChangeRequest, submitPricingChangeRequest. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 4 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#publishPricingEffectiveDate`, `catalogue#setFeeApplicabilityCharging`, `catalogue#setPricingChangeRequest`, `catalogue#submitPricingChangeRequest` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | VM-ADM-072 | AM-TICKETING-P08-4 | [BE] ADM-072 Fee Applicability & Charging Rule Builder | 3 | New full-stack developer 1 |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-20 | Determine when a fee or surcharge should apply. Screen 10.3.4 defines the fee. Screen 10.3.5 defines the conditions that trigger it. Module: Commercial. App: Venue Management. Done when `ADM-072` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
13 | 3 | VM-ADM-075 | AM-TICKETING-P08-4 | [BE] ADM-075 Currency Precision, Rounding & Monetary Rules | 2 | Sanket Keluskar |  | SETUP-CLIENTS SVC-CATALOGUE-CATALOGUE-11 SVC-CATALOGUE-DRAFTED-17 | Ensure monetary calculations remain consistent across countries, currencies, channels and payment systems. Module: Commercial. App: Venue Management. Done when `ADM-075` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
13 | 3 | VM-ADM-079 | AM-TICKETING-P08-4 | [BE] ADM-079 Pricing Change Request & Workspace | 5 | Pranay Shinde |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-17 SVC-CATALOGUE-DRAFTED-20 | Provide a governed workspace for creating individual or structured pricing changes before modifying production pricing. Module: Commercial. App: Venue Management. Done when `ADM-079` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
13 | 3 | VM-ADM-080 | AM-TICKETING-P08-4 | [BE] ADM-080 Bulk Pricing Update, Import & Mass Maintenance | 3 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-17 | Allow large pricing portfolios to be updated efficiently without manually editing hundreds or thousands of records. Module: Commercial. App: Venue Management. Done when `ADM-080` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
13 | 3 | VM-ADM-083 | AM-TICKETING-P08-4 | [BE] ADM-083 Pricing Approval Workflow & Authority Matrix | 2 | Pranay Shinde |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-17 VM-TENANCY-MATRIX-1 | Configure who must approve pricing changes based on their commercial risk and scope. Module: Commercial. App: Venue Management. Done when `ADM-083` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
13 | 3 | VM-ADM-084 | AM-TICKETING-P08-4 | [BE] ADM-084 Pricing Publication & Effective-Date Scheduler | 2 | Pranay Shinde |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-20 | Control exactly when approved pricing becomes commercially effective. Module: Commercial. App: Venue Management. Done when `ADM-084` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
11 | 3 | MIG-CATALOGUE-10 | AM-TICKETING-P08-5 | [DB] Forward migration V1123__catalogue.sql: catalogue for Ticketing · Venue Management 5 of 10 (3 tables) | 3 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-CATALOGUE VM-MIG-CATALOGUE | Tables: catalogue.demand_signal, catalogue.price_ladder, catalogue.signal_registry. Source DDL: backend/tenant/010-catalogue.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `catalogue.demand_signal`, `catalogue.price_ladder`, `catalogue.signal_registry` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
12 | 3 | SVC-CATALOGUE-CATALOGUE-12 | AM-TICKETING-P08-5 | [BE] CatalogueService: setDemandSignalConfiguration, setDynamicPricingGuardrailPolicy, setPriceLadderMatrix, transitionDynamicPricingStrategy | 8 | Hrushikant Patkar | CatalogueService | MIG-CATALOGUE-10 MIG-CATALOGUE-3 MIG-CATALOGUE-6 MIG-PLATFORM MIG-PRICING-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: setDemandSignalConfiguration, setDynamicPricingGuardrailPolicy, setPriceLadderMatrix, transitionDynamicPricingStrategy. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 5 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#setDemandSignalConfiguration`, `catalogue#setDynamicPricingGuardrailPolicy`, `catalogue#setPriceLadderMatrix`, `catalogue#transitionDynamicPricingStrategy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-DRAFTED-24 | AM-TICKETING-P08-5 | [BE] CatalogueService: setBookingVelocityTime, setDemandOccupancyAvailability, setDynamicPricingStrategy | 8 | New full-stack developer 1 | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-3 MIG-CATALOGUE-6 MIG-PRICING-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setBookingVelocityTime, setDemandOccupancyAvailability, setDynamicPricingStrategy. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 5 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#setBookingVelocityTime`, `catalogue#setDemandOccupancyAvailability`, `catalogue#setDynamicPricingStrategy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | VM-ADM-090 | AM-TICKETING-P08-5 | [BE] ADM-090 Demand, Occupancy & Availability Rule Builder | 2 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-24 | Configure price movements driven by actual demand and capacity consumption. This directly covers the fundamental matrix requirements for: Demand-Based Pricing Occupancy-Based Pricing Availability-Based Pricing Inventory-Based Pricing Module: Commercial. App: Venue Management. Waits for its definition: ADM-090's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-090` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
13 | 3 | VM-ADM-091 | AM-TICKETING-P08-5 | [BE] ADM-091 Booking Velocity & Time-to-Event Rule Builder | 3 | Pranay Shinde |  | SETUP-CLIENTS SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-24 | Control price movement based on how quickly inventory is selling and how much time remains before the event or visit date. This is critical because occupancy alone is insufficient for effective revenue management. Module: Commercial. App: Venue Management. Waits for its definition: ADM-091's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-091` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
11 | 3 | MIG-CATALOGUE-11 | AM-TICKETING-P08-6 | [DB] Forward migration V1126__catalogue.sql: catalogue for Ticketing · Venue Management 6 of 10 (2 tables) | 2 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-CATALOGUE VM-MIG-CATALOGUE | Tables: catalogue.channel_connection, catalogue.channel_sales_rule. Source DDL: backend/tenant/010-catalogue.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `catalogue.channel_connection`, `catalogue.channel_sales_rule` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
12 | 3 | SVC-CATALOGUE-CATALOGUE-13 | AM-TICKETING-P08-6 | [BE] CatalogueService: setSignalRegistryPolicy | 3 | Hrushikant Patkar | CatalogueService | MIG-CATALOGUE-10 MIG-CATALOGUE-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setSignalRegistryPolicy. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 6 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#setSignalRegistryPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-DRAFTED-25 | AM-TICKETING-P08-6 | [BE] CatalogueService: createChannelProfile, createLiveDynamicPrice, decidePricingRecommendation, listAutomationPolicyAutonomous | 8 | Hrushikant Patkar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-10 MIG-CATALOGUE-3 MIG-CATALOGUE-6 MIG-CATALOGUE-7 MIG-PLATFORM MIG-PRICING-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: createChannelProfile, createLiveDynamicPrice, decidePricingRecommendation, listAutomationPolicyAutonomous. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 6 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#createChannelProfile`, `catalogue#createLiveDynamicPrice`, `catalogue#decidePricingRecommendation`, `catalogue#listAutomationPolicyAutonomous` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-CATALOGUE-DRAFTED-19 | AM-TICKETING-P08-4 | [BE] CatalogueService: listPricingDistributionSynchronization, listPricingGovernance, listPricingRollbackEmergency, listPricingVersionBaseline | 5 | Hrushikant Patkar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-4 MIG-CATALOGUE-7 MIG-CATALOGUE-9 MIG-ORDERS PLATFORM-KERNEL SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-11 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-CATALOGUE-9 SVC-CATALOGUE-DRAFTED-17 SVC-CATALOGUE-DRAFTED-20 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-7 SVC-CATALOGUE-PRICING-1 SVC-IDENTITY-GUESTAUTH-2 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 VM-CATALOGUE-BUNDLE-1 | Operations: listPricingDistributionSynchronization, listPricingGovernance, listPricingRollbackEmergency, listPricingVersionBaseline. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 4 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listPricingDistributionSynchronization`, `catalogue#listPricingGovernance`, `catalogue#listPricingRollbackEmergency`, `catalogue#listPricingVersionBaseline` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | VM-ADM-078 | AM-TICKETING-P08-4 | [BE] ADM-078 Pricing Governance Command Center | 5 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-17 SVC-CATALOGUE-DRAFTED-19 | Provide Commercial, Revenue, Finance, and authorized management with one operational view of all pricing changes and governance activities. Module: Commercial. App: Venue Management. Done when `ADM-078` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-081 | AM-TICKETING-P08-4 | [BE] ADM-081 Pricing Version & Baseline Management | 2 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-19 | Maintain immutable versions of pricing configuration so TICVAI always knows what configuration existed at a particular time. Module: Commercial. App: Venue Management. Done when `ADM-081` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-085 | AM-TICKETING-P08-4 | [BE] ADM-085 Pricing Distribution, Synchronization & Publication Monitor | 2 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-19 | Ensure published pricing reaches every TICVAI channel and dependent system consistently. Module: Commercial. App: Venue Management. Done when `ADM-085` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-086 | AM-TICKETING-P08-4 | [BE] ADM-086 Pricing Rollback & Emergency Control Center | 3 | Pranay Shinde |  | SETUP-CLIENTS SVC-CATALOGUE-CATALOGUE-11 SVC-CATALOGUE-CATALOGUE-9 SVC-CATALOGUE-DRAFTED-19 | Provide controlled recovery when a pricing publication is incorrect or creates unacceptable commercial impact. Module: Commercial. App: Venue Management. Waits for its definition: ADM-086's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-086` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
13 | 3 | SVC-CATALOGUE-DRAFTED-29 | AM-TICKETING-P08-6 | [BE] CatalogueService: setChannelPricingCommercial, setPricing, setPricingExperiment, setProductCatalogue | 8 | Pranay Shinde | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-10 MIG-CATALOGUE-2 MIG-CATALOGUE-3 MIG-CATALOGUE-4 MIG-CATALOGUE-6 MIG-CATALOGUE-7 MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setChannelPricingCommercial, setPricing, setPricingExperiment, setProductCatalogue. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 6 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#setChannelPricingCommercial`, `catalogue#setPricing`, `catalogue#setPricingExperiment`, `catalogue#setProductCatalogue` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-PLATFORM-DRAFTED-11 | AM-SUBSCRIPTION-LICENSING-P10 | [BE] PlatformService: listPartnerContactUser, listPartnerDocumentationCompliance, listPartnerOnboardingApplication, listPartnerOrderBooking | 8 | New full-stack developer 2 | PlatformService | MIG-APPROVALS MIG-CATALOGUE MIG-CONTROL MIG-CONTROL-3 MIG-CONTROL-7 MIG-IDENTITY MIG-ORDERS PLATFORM-KERNEL SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-FNB-FNB-12 SVC-IDENTITY-ADMINISTRATION-2 SVC-IDENTITY-GUESTAUTH-2 SVC-IDENTITY-SSO-1 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-DRAFTED-1 SVC-PLATFORM-DRAFTED-12 SVC-PLATFORM-DRAFTED-13 SVC-PLATFORM-DRAFTED-2 SVC-PLATFORM-DRAFTED-9 SVC-PLATFORM-SUBSCRIPTION-16 SVC-PLATFORM-SUBSCRIPTION-17 SVC-PLATFORM-SUBSCRIPTION-4 SVC-PLATFORM-SUBSCRIPTION-5 SVC-PLATFORM-SUBSCRIPTION-6 SVC-PLATFORM-SUBSCRIPTION-7 SVC-PLATFORM-SUBSCRIPTION-8 SVC-PLATFORM-SUBSCRIPTION-9 SVC-TENANCY-APPROVALS-2 SVC-TENANCY-APPROVALS-4 SVC-TENANCY-APPROVALS-5 SVC-TENANCY-REQUEST-1 SVC-TENANCY-REQUEST-2 SVC-TENANCY-REQUEST-3 SVC-TENANCY-ROTA-2 SVC-WALLET-RETAIL-1 VM-CATALOGUE-EVENT-1 VM-CATALOGUE-PRODUCT-1 VM-IDENTITY-ADMINISTRATION-1 VM-TENANCY-REQUEST-1 | Operations: listPartnerContactUser, listPartnerDocumentationCompliance, listPartnerOnboardingApplication, listPartnerOrderBooking. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Partner Portal 1 of 2; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#listPartnerContactUser`, `subscription#listPartnerDocumentationCompliance`, `subscription#listPartnerOnboardingApplication`, `subscription#listPartnerOrderBooking` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-PLATFORM-DRAFTED-15 | AM-SUBSCRIPTION-LICENSING-P10-2 | [BE] PlatformService: listPartnerStatementAccount, listReservationHoldRelease | 5 | Pranay Shinde | PlatformService | MIG-CATALOGUE MIG-CONTROL MIG-CONTROL-3 MIG-CONTROL-7 MIG-LEDGER MIG-ORDERS PLATFORM-KERNEL SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-IDENTITY-GUESTAUTH-2 SVC-LEDGER-FINANCE-3 SVC-LEDGER-LEDGER-3 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-DRAFTED-1 SVC-PLATFORM-DRAFTED-12 SVC-PLATFORM-DRAFTED-13 SVC-PLATFORM-DRAFTED-9 SVC-PLATFORM-SUBSCRIPTION-16 SVC-PLATFORM-SUBSCRIPTION-17 SVC-PLATFORM-SUBSCRIPTION-4 SVC-PLATFORM-SUBSCRIPTION-5 SVC-PLATFORM-SUBSCRIPTION-6 SVC-PLATFORM-SUBSCRIPTION-7 SVC-PLATFORM-SUBSCRIPTION-8 SVC-PLATFORM-SUBSCRIPTION-9 SVC-TENANCY-REQUEST-1 SVC-WALLET-RETAIL-1 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-EVENT-1 VM-CATALOGUE-LEASE-1 VM-CATALOGUE-PRODUCT-1 VM-LEDGER-FINANCE-1 VM-LEDGER-RECOGNITION-1 VM-ORDER-ORDERS-2 VM-ORDER-REFUND-1 VM-ORDER-SHIFT-1 | Operations: listPartnerStatementAccount, listReservationHoldRelease. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Partner Portal 2 of 2; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#listPartnerStatementAccount`, `subscription#listReservationHoldRelease` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-CATALOGUE-DRAFTED-8 | AM-TICKETING-P08-2 | [BE] CatalogueService: listProductDuplicationTemplate, listProductGovernance, listProductImportExport, listProductLifecycle | 5 | Hrushikant Patkar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-4 MIG-CATALOGUE-7 PLATFORM-KERNEL SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-11 SVC-CATALOGUE-CATALOGUE-2 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-CATALOGUE-9 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-17 SVC-CATALOGUE-DRAFTED-20 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-DRAFTED-7 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 VM-CATALOGUE-PRODUCT-1 | Operations: listProductDuplicationTemplate, listProductGovernance, listProductImportExport, listProductLifecycle. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 2 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listProductDuplicationTemplate`, `catalogue#listProductGovernance`, `catalogue#listProductImportExport`, `catalogue#listProductLifecycle` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | VM-ADM-118 | AM-TICKETING-P08-2 | [BE] ADM-118 Product Lifecycle Command Center | 3 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-8 | Provide administrators with a centralized operational view of every product and its current lifecycle state. Module: Catalogue. App: Venue Management. Waits for its definition: ADM-118's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-118` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-122 | AM-TICKETING-P08-2 | [BE] ADM-122 Product Import / Export & Environment Transfer | 2 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-8 | Allow controlled movement of product configurations between TICVAI environments. This covers the matrix requirement for importing/exporting catalogue products between different environments. Module: Catalogue. App: Venue Management. Waits for its definition: ADM-122's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-122` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-126 | AM-TICKETING-P08-2 | [BE] ADM-126 Product Duplication & Template Library | 3 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-CATALOGUE-CATALOGUE-9 SVC-CATALOGUE-DRAFTED-8 | Accelerate product configuration by allowing administrators to reuse proven configurations. The source matrix explicitly requires duplication of products together with associated configuration, rules, pricing and entitlements. Module: Catalogue. App: Venue Management. Done when `ADM-126` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-128 | AM-TICKETING-P08-2 | [BE] ADM-128 Product Governance Command Center | 5 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-CATALOGUE-CATALOGUE-9 SVC-CATALOGUE-DRAFTED-8 | Provide management and administrators with a single control center for all product governance activities. Module: Catalogue. App: Venue Management. Done when `ADM-128` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | SVC-CATALOGUE-DRAFTED-22 | AM-TICKETING-P08-5 | [BE] CatalogueService: listDynamicPricingGuardrail, listInternalDemandBooking, listMarketTourismHoliday, listNearbyEventExhibition | 8 | Tanmay Dukhande | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-10 MIG-CATALOGUE-6 MIG-ORDERS PLATFORM-KERNEL SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-12 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-IDENTITY-GUESTAUTH-2 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-PAYMENT-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 SVC-VENUEOPS-VISITPLAN-1 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-EVENT-1 VM-CATALOGUE-LEASE-1 VM-CATALOGUE-PRODUCT-1 | Operations: listDynamicPricingGuardrail, listInternalDemandBooking, listMarketTourismHoliday, listNearbyEventExhibition. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 5 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listDynamicPricingGuardrail`, `catalogue#listInternalDemandBooking`, `catalogue#listMarketTourismHoliday`, `catalogue#listNearbyEventExhibition` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
19 | 3 | VM-ADM-095 | AM-TICKETING-P08-5 | [BE] ADM-095 Dynamic Pricing Guardrails & Commercial Protection | 3 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-CATALOGUE-CATALOGUE-12 SVC-CATALOGUE-DRAFTED-22 | Establish the non-negotiable boundaries for every dynamic-pricing strategy. Module: Commercial. App: Venue Management. Done when `ADM-095` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-099 | AM-TICKETING-P08-5 | [BE] ADM-099 Internal Demand & Booking Signal Hub | 2 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-22 | Centralize the internal TICVAI signals used by forecasting and AI pricing models. These are generally the highest-confidence signals because they come directly from TICVAI transactions. Module: Commercial. App: Venue Management. Waits for its definition: ADM-099's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-099` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-101 | AM-TICKETING-P08-5 | [BE] ADM-101 Nearby Event, Exhibition & Local Demand Intelligence | 3 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-CATALOGUE-CATALOGUE-12 SVC-CATALOGUE-DRAFTED-22 | Detect external events around TICVAI venues that could materially affect visitor demand. This directly addresses the exhibition-near-the-venue scenario. Module: Commercial. App: Venue Management. Done when `ADM-101` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-103 | AM-TICKETING-P08-5 | [BE] ADM-103 Market, Tourism, Holiday & Contextual Signal Hub | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-CATALOGUE-CATALOGUE-12 SVC-CATALOGUE-DRAFTED-22 | Capture broader external factors that may affect visitor demand beyond weather and nearby events. Module: Commercial. App: Venue Management. Waits for its definition: ADM-103's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-103` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | SVC-CATALOGUE-DRAFTED-27 | AM-TICKETING-P08-6 | [BE] CatalogueService: listLearningModelPerformance, listPriceElasticityRevenue, listPricingRecommendationExplainability, listRecommendationReviewDecision | 8 | Hrushikant Patkar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-10 MIG-CATALOGUE-6 MIG-ORDERS PLATFORM-KERNEL SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-13 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-IDENTITY-GUESTAUTH-2 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 VM-CATALOGUE-PRODUCT-1 | Operations: listLearningModelPerformance, listPriceElasticityRevenue, listPricingRecommendationExplainability, listRecommendationReviewDecision. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 6 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listLearningModelPerformance`, `catalogue#listPriceElasticityRevenue`, `catalogue#listPricingRecommendationExplainability`, `catalogue#listRecommendationReviewDecision` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | VM-ADM-114 | AM-TICKETING-P08-6 | [BE] ADM-114 Automation Policy & Autonomous Pricing Orchestrator | 3 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-CATALOGUE-CATALOGUE-12 SVC-CATALOGUE-DRAFTED-25 | Control when TICVAI is allowed to execute pricing changes automatically. Board 5 defines the strategy-level automation permission. This screen manages operational autonomous execution at scale. Module: Commercial. App: Venue Management. Done when `ADM-114` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
13 | 3 | VM-ADM-115 | AM-TICKETING-P08-6 | [BE] ADM-115 Live Dynamic Price Execution & Deployment Monitor | 2 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-25 | Monitor pricing actions as they are executed across TICVAI's selling ecosystem. Module: Commercial. App: Venue Management. Done when `ADM-115` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
13 | 3 | VM-ADM-259 | AM-TICKETING-P08-6 | [BE] ADM-259 Channel Creation & Profile Configuration | 3 | Sanket Keluskar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-25 | Create and define a sales channel before products and commercial rules are assigned. Module: Commercial. App: Venue Management. Done when `ADM-259` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
14 | 3 | VM-ADM-109 | AM-TICKETING-P08-6 | [BE] ADM-109 Pricing Simulation Studio | 2 | Surendra |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-29 | Allow any proposed dynamic-pricing change to be tested before affecting live customers. This should become the sandbox of the Dynamic Pricing Engine. Module: Commercial. App: Venue Management. Done when `ADM-109` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
14 | 3 | VM-ADM-111 | AM-TICKETING-P08-6 | [BE] ADM-111 A/B Pricing Experiment Studio | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-29 | Allow TICVAI to scientifically test different pricing strategies using controlled customer groups. This is essential because AI should learn from actual customer behavior, not only historical assumptions. Module: Commercial. App: Venue Management. Done when `ADM-111` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
14 | 3 | VM-ADM-260 | AM-TICKETING-P08-6 | [BE] ADM-260 Product & Catalogue Assignment | 2 | Pranay Shinde |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-29 | Control exactly which products are available through each sales channel. Module: Commercial. App: Venue Management. Done when `ADM-260` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
14 | 3 | VM-ADM-261 | AM-TICKETING-P08-6 | [BE] ADM-261 Channel Pricing & Commercial Profile Assignment | 2 | Sanket Keluskar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-29 | Determine which pricing configuration a channel consumes. Module: Commercial. App: Venue Management. Waits for its definition: ADM-261's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-261` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-105 | AM-TICKETING-P08-6 | [BE] ADM-105 Price Elasticity & Revenue Response Intelligence | 2 | Surendra |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-27 | Estimate how customers are likely to respond to different prices. Module: Commercial. App: Venue Management. Done when `ADM-105` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-106 | AM-TICKETING-P08-6 | [BE] ADM-106 AI Pricing Recommendation & Explainability Center | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-27 | Convert all intelligence generated by Board 6 into actionable pricing recommendations. This is the central AI recommendation screen. Module: Commercial. App: Venue Management. Waits for its definition: ADM-106's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-106` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-113 | AM-TICKETING-P08-6 | [BE] ADM-113 AI Recommendation Review & Decision Queue | 3 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-27 | Provide the human decision workspace for recommendations produced by Board 6. This should be the Revenue Manager's inbox. Module: Commercial. App: Venue Management. Done when `ADM-113` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-117 | AM-TICKETING-P08-6 | [BE] ADM-117 AI Learning, Model Performance & Optimization Feedback | 2 | Sanket Keluskar |  | SETUP-CLIENTS SVC-CATALOGUE-CATALOGUE-13 SVC-CATALOGUE-DRAFTED-27 | Close the intelligence loop by comparing AI predictions and recommendations with actual commercial outcomes. This is what allows the system to improve over time. Module: Commercial. App: Venue Management. Done when `ADM-117` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
11 | 3 | MIG-CATALOGUE-12 | AM-TICKETING-P08-7 | [DB] Forward migration V1129__catalogue.sql: catalogue for Ticketing · Venue Management 7 of 10 (2 tables) | 2 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-CATALOGUE VM-MIG-CATALOGUE | Tables: catalogue.channel_incident, catalogue.channel_sync. Source DDL: backend/tenant/010-catalogue.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `catalogue.channel_incident`, `catalogue.channel_sync` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
12 | 3 | SVC-CATALOGUE-CATALOGUE-14 | AM-TICKETING-P08-7 | [BE] CatalogueService: retryChannelIncident, setChannelConnectionConfiguration, setChannelSalesRule, setChannelSyncSetting | 8 | New full-stack developer 1 | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-11 MIG-CATALOGUE-12 MIG-CATALOGUE-3 MIG-CATALOGUE-7 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: retryChannelIncident, setChannelConnectionConfiguration, setChannelSalesRule, setChannelSyncSetting. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 7 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#retryChannelIncident`, `catalogue#setChannelConnectionConfiguration`, `catalogue#setChannelSalesRule`, `catalogue#setChannelSyncSetting` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-CATALOGUE-15 | AM-TICKETING-P08-7 | [BE] CatalogueService: testChannelConnection, updateChannelIncident | 3 | New full-stack developer 2 | CatalogueService | MIG-CATALOGUE-11 MIG-CATALOGUE-12 MIG-CATALOGUE-3 MIG-CATALOGUE-7 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: testChannelConnection, updateChannelIncident. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 7 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#testChannelConnection`, `catalogue#updateChannelIncident` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-DRAFTED-33 | AM-TICKETING-P08-7 | [BE] CatalogueService: publishChannelReadinessValidation, setChannelFeePayment | 3 | Surendra | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-11 MIG-CATALOGUE-3 MIG-CATALOGUE-4 MIG-CATALOGUE-6 MIG-CATALOGUE-7 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: publishChannelReadinessValidation, setChannelFeePayment. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 7 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#publishChannelReadinessValidation`, `catalogue#setChannelFeePayment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-CATALOGUE-DRAFTED-26 | AM-TICKETING-P08-6 | [BE] CatalogueService: listChannelSaleRule, listChannelSaleSchedule, listDynamicPricingPerformance, listInventoryCapacityChannel | 8 | Hrushikant Patkar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-11 MIG-CATALOGUE-6 MIG-CATALOGUE-7 MIG-ORDERS PLATFORM-KERNEL SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-14 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-CATALOGUE-7 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-DRAFTED-33 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-IDENTITY-GUESTAUTH-2 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-CART-3 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-PAYMENT-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 SVC-VENUEOPS-VISITPLAN-1 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-CATALOGUE-1 VM-CATALOGUE-EVENT-1 VM-CATALOGUE-LEASE-1 VM-CATALOGUE-PRODUCT-1 | Operations: listChannelSaleRule, listChannelSaleSchedule, listDynamicPricingPerformance, listInventoryCapacityChannel. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 6 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listChannelSaleRule`, `catalogue#listChannelSaleSchedule`, `catalogue#listDynamicPricingPerformance`, `catalogue#listInventoryCapacityChannel` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-CATALOGUE-DRAFTED-28 | AM-TICKETING-P08-6 | [BE] CatalogueService: listRevenueDemandImpact, listSaleChannel, listScenarioModelingWhat, listSignalDataQuality | 8 | Pranay Shinde | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-10 MIG-CATALOGUE-11 MIG-CATALOGUE-6 MIG-CATALOGUE-7 MIG-ORDERS PLATFORM-KERNEL SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-13 SVC-CATALOGUE-CATALOGUE-14 SVC-CATALOGUE-CATALOGUE-15 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-DRAFTED-33 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-CATALOGUE-PRICING-1 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-IDENTITY-GUESTAUTH-2 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-PAYMENT-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-LEASE-1 VM-CATALOGUE-PRODUCT-1 | Operations: listRevenueDemandImpact, listSaleChannel, listScenarioModelingWhat, listSignalDataQuality. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 6 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listRevenueDemandImpact`, `catalogue#listSaleChannel`, `catalogue#listScenarioModelingWhat`, `catalogue#listSignalDataQuality` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
19 | 3 | VM-ADM-107 | AM-TICKETING-P08-6 | [BE] ADM-107 AI Signal Registry, Data Quality & Model Governance | 2 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-CATALOGUE-CATALOGUE-13 SVC-CATALOGUE-DRAFTED-28 | Govern the complete data and intelligence ecosystem behind AI pricing. This is critical. Without this screen, Development team could connect many external sources without giving TICVAI proper control over them. Module: Commercial. App: Venue Management. Done when `ADM-107` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-110 | AM-TICKETING-P08-6 | [BE] ADM-110 Scenario Modeling & What-If Analysis | 2 | Pranay Shinde |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-28 | Model how prices, demand and inventory would respond to a pricing change before it is made. Module: Commercial. App: Venue Management. Waits for its definition: ADM-110's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-110` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-112 | AM-TICKETING-P08-6 | [BE] ADM-112 Revenue & Demand Impact Forecasting | 2 | Sanket Keluskar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-28 | Provide a dedicated commercial impact assessment before a dynamic-pricing action is approved or executed. Module: Commercial. App: Venue Management. Done when `ADM-112` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-116 | AM-TICKETING-P08-6 | [BE] ADM-116 Dynamic Pricing Performance & Optimization Analytics | 2 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-26 | Determine whether dynamic pricing actually improves TICVAI's commercial performance. Module: Commercial. App: Venue Management. Done when `ADM-116` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-258 | AM-TICKETING-P08-6 | [BE] ADM-258 Sales Channel Command Center | 5 | Pranay Shinde |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-26 SVC-CATALOGUE-DRAFTED-28 | Provide administrators with one centralized view of every TICVAI sales channel and its current operational/configuration status. Module: Commercial. App: Venue Management. Done when `ADM-258` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-262 | AM-TICKETING-P08-6 | [BE] ADM-262 Inventory, Capacity & Channel Allocation | 2 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-26 | Control how much product inventory or event capacity is available to each sales channel. Module: Commercial. App: Venue Management. Done when `ADM-262` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | SVC-CATALOGUE-DRAFTED-30 | AM-TICKETING-P08-7 | [BE] CatalogueService: listChannel, listChannel2, listChannelAllocationRebalancing, listChannelConnectionIntegration | 5 | Tanmay Dukhande | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-11 MIG-CATALOGUE-12 MIG-CATALOGUE-7 MIG-ORDERS PLATFORM-KERNEL SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-14 SVC-CATALOGUE-CATALOGUE-15 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-CATALOGUE-9 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-DRAFTED-33 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-CATALOGUE-PRICING-1 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-IDENTITY-GUESTAUTH-2 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-CART-3 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-PAYMENT-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 SVC-VENUEOPS-VISITPLAN-1 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-CATALOGUE-1 VM-CATALOGUE-EVENT-1 VM-CATALOGUE-LEASE-1 VM-CATALOGUE-PRODUCT-1 | Operations: listChannel, listChannel2, listChannelAllocationRebalancing, listChannelConnectionIntegration. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 7 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listChannel`, `catalogue#listChannel2`, `catalogue#listChannelAllocationRebalancing`, `catalogue#listChannelConnectionIntegration` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-CATALOGUE-DRAFTED-32 | AM-TICKETING-P08-7 | [BE] CatalogueService: listCustomerEligibilityRule, listProductPriceAvailability, listRealTimeAvailability, listRealTimeChannel | 5 | Tanmay Dukhande | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-11 MIG-CATALOGUE-12 MIG-PROMOTIONS PLATFORM-KERNEL SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-14 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-CART-3 SVC-ORDER-PAYMENT-1 SVC-ORDER-SYNC-1 SVC-VENUEOPS-VISITPLAN-1 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-CATALOGUE-1 VM-CATALOGUE-EVENT-1 VM-CATALOGUE-LEASE-1 VM-CATALOGUE-PRODUCT-1 | Operations: listCustomerEligibilityRule, listProductPriceAvailability, listRealTimeAvailability, listRealTimeChannel. Spec: contracts (catalogue, promotions) at the release tag, served by ADAM. Built for Ticketing · Venue Management 7 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listCustomerEligibilityRule`, `catalogue#listProductPriceAvailability`, `promotions#listRealTimeAvailability`, `catalogue#listRealTimeChannel` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | VM-ADM-266 | AM-TICKETING-P08-7 | [BE] ADM-266 Channel Fees, Payment & Fulfillment Configuration | 3 | Sanket Keluskar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-33 | Define the commercial and fulfillment behavior associated with each channel. Module: Commercial. App: Venue Management. Done when `ADM-266` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
13 | 3 | VM-ADM-267 | AM-TICKETING-P08-7 | [BE] ADM-267 Channel Publication, Readiness & AI Validation | 2 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-33 | Perform final validation before a sales channel or channel/product configuration becomes commercially active. Board 2 manages the live operational layer of TICVAI's sales-channel ecosystem after channels have been configured and activated in Board 1. Module: Commercial. App: Venue Management. Done when `ADM-267` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-263 | AM-TICKETING-P08-7 | [BE] ADM-263 Channel Sales Schedule & Availability Windows | 3 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-CATALOGUE-CATALOGUE-14 SVC-CATALOGUE-DRAFTED-26 | Control when each channel is permitted to sell. Module: Commercial. App: Venue Management. Done when `ADM-263` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-264 | AM-TICKETING-P08-7 | [BE] ADM-264 Customer & Eligibility Rules by Channel | 2 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-CATALOGUE-CATALOGUE-14 SVC-CATALOGUE-DRAFTED-32 | Determine who is allowed to purchase through a particular channel. Module: Commercial. App: Venue Management. Done when `ADM-264` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-265 | AM-TICKETING-P08-7 | [BE] ADM-265 Channel Sales Rules, Limits & Restrictions | 3 | New full-stack developer 2 |  | SETUP-CLIENTS SVC-CATALOGUE-CATALOGUE-14 SVC-CATALOGUE-DRAFTED-26 | Configure operational restrictions that apply specifically to a sales channel. Module: Commercial. App: Venue Management. Done when `ADM-265` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-268 | AM-TICKETING-P08-7 | [BE] ADM-268 Channel Operations Command Center | 5 | Surendra |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-30 | Provide a real-time operational view of all active TICVAI sales channels. Module: Commercial. App: Venue Management. Done when `ADM-268` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-269 | AM-TICKETING-P08-7 | [BE] ADM-269 Channel Connection & Integration Manager | 5 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-CATALOGUE-CATALOGUE-14 SVC-CATALOGUE-CATALOGUE-15 SVC-CATALOGUE-DRAFTED-30 | Configure and manage the technical connection between TICVAI and external or internal sales channels. Module: Commercial. App: Venue Management. Done when `ADM-269` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-270 | AM-TICKETING-P08-7 | [BE] ADM-270 Product, Price & Availability Synchronization | 3 | Sanket Keluskar |  | SETUP-CLIENTS SVC-CATALOGUE-CATALOGUE-14 SVC-CATALOGUE-DRAFTED-32 | Control how TICVAI distributes commercial information to connected channels and receives supported updates. Module: Commercial. App: Venue Management. Done when `ADM-270` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-271 | AM-TICKETING-P08-7 | [BE] ADM-271 Real-Time Channel Availability & Inventory Monitor | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-32 | Provide operations with a live view of what each channel can currently sell. Module: Commercial. App: Venue Management. Done when `ADM-271` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-272 | AM-TICKETING-P08-7 | [BE] ADM-272 Channel Allocation & Rebalancing Operations | 2 | New full-stack developer 2 |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-30 VM-CATALOGUE-CAPACITY-2 | Allow authorized users to operationally adjust inventory allocations as demand changes. Board 1 defines the allocation rules. Board 2 manages those allocations during live operations. Module: Commercial. App: Venue Management. Done when `ADM-272` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-277 | AM-TICKETING-P08-7 | [BE] ADM-277 AI Channel Optimization & Intelligence Center | 2 | Sanket Keluskar |  | SETUP-CLIENTS SVC-CATALOGUE-CATALOGUE-9 SVC-CATALOGUE-DRAFTED-30 | Create the AI intelligence layer that looks across all sales channels together rather than optimizing each channel in isolation. Module: Commercial. App: Venue Management. Done when `ADM-277` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
14 | 3 | MIG-ORDERS-4 | AM-TICKETING-P08-8 | [DB] Forward migration V1026__orders.sql: orders for Ticketing · Venue Management 8 of 10 (1 tables) | 1 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-ORDERS VM-MIG-ORDERS | Tables: orders.member_exception. Source DDL: backend/tenant/010-orders.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `orders.member_exception` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-PLATFORM-SUBSCRIPTION-21 | AM-TICKETING-P08-8 | [BE] PlatformService: setMembershipCommercialConfig | 2 | Chinmay Patkar | PlatformService | MIG-CATALOGUE MIG-SUBSCRIPTION-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setMembershipCommercialConfig. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Ticketing · Venue Management 8 of 10; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#setMembershipCommercialConfig` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-PLATFORM-DRAFTED-4 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] PlatformService: listMembershipUsageVisit, listPartnerAccessRole, listPartnerReconciliationException, listTerritoryMarketDistribution | 8 | New full-stack developer 1 | PlatformService | MIG-APPROVALS MIG-CATALOGUE MIG-CONTROL MIG-CONTROL-3 MIG-CONTROL-7 MIG-LEDGER MIG-ORDERS MIG-SUBSCRIPTION-3 PLATFORM-KERNEL SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-FNB-FNB-12 SVC-IDENTITY-GUESTAUTH-2 SVC-LEDGER-FINANCE-3 SVC-LEDGER-LEDGER-3 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-DRAFTED-1 SVC-PLATFORM-DRAFTED-12 SVC-PLATFORM-DRAFTED-13 SVC-PLATFORM-DRAFTED-2 SVC-PLATFORM-DRAFTED-5 SVC-PLATFORM-DRAFTED-9 SVC-PLATFORM-SUBSCRIPTION-16 SVC-PLATFORM-SUBSCRIPTION-17 SVC-PLATFORM-SUBSCRIPTION-20 SVC-PLATFORM-SUBSCRIPTION-21 SVC-PLATFORM-SUBSCRIPTION-4 SVC-PLATFORM-SUBSCRIPTION-5 SVC-PLATFORM-SUBSCRIPTION-6 SVC-PLATFORM-SUBSCRIPTION-7 SVC-PLATFORM-SUBSCRIPTION-8 SVC-PLATFORM-SUBSCRIPTION-9 SVC-TENANCY-APPROVALS-2 SVC-TENANCY-APPROVALS-4 SVC-TENANCY-APPROVALS-5 SVC-TENANCY-REQUEST-1 SVC-TENANCY-REQUEST-2 SVC-TENANCY-REQUEST-3 SVC-TENANCY-ROTA-2 SVC-WALLET-RETAIL-1 VM-CATALOGUE-PRODUCT-1 VM-LEDGER-FINANCE-1 VM-LEDGER-RECOGNITION-1 VM-ORDER-ORDERS-2 VM-ORDER-SHIFT-1 VM-TENANCY-REQUEST-1 | Operations: listMembershipUsageVisit, listPartnerAccessRole, listPartnerReconciliationException, listTerritoryMarketDistribution. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 1 of 3; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#listMembershipUsageVisit`, `subscription#listPartnerAccessRole`, `subscription#listPartnerReconciliationException`, `subscription#listTerritoryMarketDistribution` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
19 | 3 | VM-PTR-026 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] PTR-026 Territory, Market & Distribution Rights | 2 | New full-stack developer 1 |  | SETUP-CLIENTS SVC-PLATFORM-DRAFTED-4 SVC-PLATFORM-SUBSCRIPTION-8 | Define where and through what business scope a partner is authorized to distribute TICVAI products. Module: Partners. App: Venue Management. Done when `PTR-026` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-PTR-029 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] PTR-029 Partner Access, Roles & Permission Profile | 5 | New full-stack developer 2 |  | SETUP-CLIENTS SVC-IDENTITY-MFA-1 SVC-IDENTITY-MFA-2 SVC-PLATFORM-DRAFTED-4 SVC-PLATFORM-SUBSCRIPTION-8 | Control what a partner organization is permitted to do, beyond individual-user permissions. Module: Partners. App: Venue Management. Done when `PTR-029` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-PTR-047 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] PTR-047 Partner Reconciliation & Exception Management | 3 | Sanket Keluskar |  | SETUP-CLIENTS SVC-PLATFORM-DRAFTED-4 SVC-PLATFORM-SUBSCRIPTION-4 | Reconcile operational bookings against financial and channel records and identify discrepancies. Module: Partners. App: Venue Management. Done when `PTR-047` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
14 | 3 | SVC-PLATFORM-DRAFTED-16 | AM-TICKETING-P08-8 | [BE] PlatformService: listMembershipCommercialPricing, listMembershipFreezeSuspension, setMembershipEntitlementAdmission | 5 | Deep Khanvilkar | PlatformService | MIG-ACCESS MIG-APPROVALS MIG-CATALOGUE MIG-SUBSCRIPTION-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listMembershipCommercialPricing, listMembershipFreezeSuspension, setMembershipEntitlementAdmission. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Ticketing · Venue Management 8 of 10; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#listMembershipCommercialPricing`, `subscription#listMembershipFreezeSuspension`, `subscription#setMembershipEntitlementAdmission` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-CATALOGUE-ENTITLEMENT-5 | AM-TICKETING-P08-8 | [BE] CatalogueService: archiveEntitlementTemplate, getEntitlementTemplate, updateEntitlementTemplate | 8 | Pallavi Sawant | CatalogueService | MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: archiveEntitlementTemplate, getEntitlementTemplate, updateEntitlementTemplate. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 8 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#archiveEntitlementTemplate`, `catalogue#getEntitlementTemplate`, `catalogue#updateEntitlementTemplate` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-EVENTS-4 | AM-TICKETING-P08-8 | [BE] CatalogueService: setEventResourcePlan, setEventSchedule, setEventType | 5 | Surendra | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-13 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setEventResourcePlan, setEventSchedule, setEventType. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 8 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#setEventResourcePlan`, `catalogue#setEventSchedule`, `catalogue#setEventType` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-CATALOGUE-CATALOGUE-16 | AM-TICKETING-P08-8 | [BE] CatalogueService: freezeEntitlement, reinstateEntitlement, setMembershipBenefit | 8 | New full-stack developer 2 | CatalogueService | MIG-ACCESS MIG-CATALOGUE-5 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: freezeEntitlement, reinstateEntitlement, setMembershipBenefit. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 8 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#freezeEntitlement`, `catalogue#reinstateEntitlement`, `catalogue#setMembershipBenefit` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-CATALOGUE-DRAFTED-34 | AM-TICKETING-P08-8 | [BE] CatalogueService: listGovernanceRiskLaunch, listRulePriorityConflict, setRulePriorityConflict | 5 | Deep Khanvilkar | CatalogueService | MIG-CATALOGUE-13 MIG-CATALOGUE-3 MIG-CATALOGUE-6 MIG-PRICING-2 MIG-PROMOTIONS MIG-PROMOTIONS-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listGovernanceRiskLaunch, listRulePriorityConflict, setRulePriorityConflict. Spec: contracts (catalogue, promotions) at the release tag, served by ADAM. Built for Ticketing · Venue Management 8 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listGovernanceRiskLaunch`, `catalogue#listRulePriorityConflict`, `catalogue#setRulePriorityConflict` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-CATALOGUE-DRAFTED-6 | AM-TICKETING-P08 | [BE] CatalogueService: listDemandBookingCurve, listDynamicPricingStrategy, listRevenue, simulatePriceBreakdownCalculation | 8 | Hrushikant Patkar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-4 MIG-CATALOGUE-5 MIG-CATALOGUE-6 MIG-ORDERS MIG-PRICING-2 PLATFORM-KERNEL SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-11 SVC-CATALOGUE-CATALOGUE-12 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-CATALOGUE-6 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-16 SVC-CATALOGUE-DRAFTED-20 SVC-CATALOGUE-DRAFTED-24 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-DRAFTED-3 SVC-CATALOGUE-DRAFTED-34 SVC-CATALOGUE-DRAFTED-56 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-CATALOGUE-PRICING-1 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-IDENTITY-GUESTAUTH-2 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-PAYMENT-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-EVENT-1 VM-CATALOGUE-LEASE-1 VM-CATALOGUE-PRODUCT-1 | Operations: listDemandBookingCurve, listDynamicPricingStrategy, listRevenue, simulatePriceBreakdownCalculation. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 1 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listDemandBookingCurve`, `catalogue#listDynamicPricingStrategy`, `catalogue#listRevenue`, `catalogue#simulatePriceBreakdownCalculation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-CATALOGUE-DRAFTED-9 | AM-TICKETING-P08-2 | [BE] CatalogueService: listProductRetirementSuspension, listProductTrailChange, listRollbackRecovery, listScheduledLifecycleActions | 5 | Pranay Shinde | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-2 MIG-CATALOGUE-3 MIG-CATALOGUE-4 MIG-CATALOGUE-5 MIG-CATALOGUE-7 MIG-ORDERS PLATFORM-KERNEL SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-10 SVC-CATALOGUE-CATALOGUE-11 SVC-CATALOGUE-CATALOGUE-12 SVC-CATALOGUE-CATALOGUE-13 SVC-CATALOGUE-CATALOGUE-14 SVC-CATALOGUE-CATALOGUE-15 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-CATALOGUE-3 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-CATALOGUE-6 SVC-CATALOGUE-CATALOGUE-9 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-16 SVC-CATALOGUE-DRAFTED-17 SVC-CATALOGUE-DRAFTED-2 SVC-CATALOGUE-DRAFTED-20 SVC-CATALOGUE-DRAFTED-24 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-DRAFTED-3 SVC-CATALOGUE-DRAFTED-33 SVC-CATALOGUE-DRAFTED-34 SVC-CATALOGUE-DRAFTED-56 SVC-CATALOGUE-DRAFTED-7 SVC-CATALOGUE-PRICING-1 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-IDENTITY-GUESTAUTH-2 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 VM-CATALOGUE-PRODUCT-1 | Operations: listProductRetirementSuspension, listProductTrailChange, listRollbackRecovery, listScheduledLifecycleActions. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 2 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listProductRetirementSuspension`, `catalogue#listProductTrailChange`, `catalogue#listRollbackRecovery`, `catalogue#listScheduledLifecycleActions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | VM-ADM-125 | AM-TICKETING-P08-2 | [BE] ADM-125 Publication & Activation Scheduler | 2 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-9 | Automate future product lifecycle actions. Module: Catalogue. App: Venue Management. Waits for its definition: ADM-125's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-125` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-132 | AM-TICKETING-P08-2 | [BE] ADM-132 Rollback & Recovery Management | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-CATALOGUE-CATALOGUE-9 SVC-CATALOGUE-DRAFTED-9 | Safely restore an earlier product configuration when a newly published configuration causes an issue. Module: Catalogue. App: Venue Management. Waits for its definition: ADM-132's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-132` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-135 | AM-TICKETING-P08-2 | [BE] ADM-135 Product Retirement, Suspension & Archive | 3 | Sanket Keluskar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-9 | Provide a governed end-of-life process for products. The source matrix explicitly requires disabling or retiring products without affecting previously sold tickets. Module: Catalogue. App: Venue Management. Done when `ADM-135` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-136 | AM-TICKETING-P08-2 | [BE] ADM-136 Product Audit Trail & Change History | 3 | Sanket Keluskar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-9 | Provide a complete, immutable history of product configuration and governance activity. The matrix requires tracking configuration changes with timestamps and user information. Module: Catalogue. App: Venue Management. Done when `ADM-136` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | SVC-CATALOGUE-DRAFTED-13 | AM-TICKETING-P08-3 | [BE] CatalogueService: listCustomerSegmentProfile, listEffectiveDateSeason, listLocationVenueEvent, listMarketVenueCurrency | 5 | New full-stack developer 1 | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-6 MIG-CATALOGUE-8 MIG-PRICING-2 PLATFORM-KERNEL SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-10 SVC-CATALOGUE-CATALOGUE-11 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-CATALOGUE-6 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-24 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-DRAFTED-34 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-PRICING-1 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 VM-CATALOGUE-PRODUCT-1 | Operations: listCustomerSegmentProfile, listEffectiveDateSeason, listLocationVenueEvent, listMarketVenueCurrency. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 3 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listCustomerSegmentProfile`, `catalogue#listEffectiveDateSeason`, `catalogue#listLocationVenueEvent`, `catalogue#listMarketVenueCurrency` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-CATALOGUE-DRAFTED-14 | AM-TICKETING-P08-3 | [BE] CatalogueService: listMembershipLoyaltyPricing, listPriceCategoryRate, listPriceListTemplate, listPricingRule | 5 | New full-stack developer 1 | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-2 MIG-CATALOGUE-7 MIG-CATALOGUE-8 MIG-PRICING-2 PLATFORM-KERNEL SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-10 SVC-CATALOGUE-CATALOGUE-3 SVC-CATALOGUE-CATALOGUE-6 SVC-CATALOGUE-CATALOGUE-9 SVC-CATALOGUE-DRAFTED-24 SVC-CATALOGUE-DRAFTED-34 SVC-CATALOGUE-PRICING-1 | Operations: listMembershipLoyaltyPricing, listPriceCategoryRate, listPriceListTemplate, listPricingRule. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 3 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listMembershipLoyaltyPricing`, `catalogue#listPriceCategoryRate`, `catalogue#listPriceListTemplate`, `catalogue#listPricingRule` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-CATALOGUE-DRAFTED-15 | AM-TICKETING-P08-3 | [BE] CatalogueService: listPricingRulePriority, listQuantityGroupVolume, listResidencyNationalityMarket, listTimeslotPerformanceTime | 5 | Tanmay Dukhande | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-6 MIG-PRICING-2 PLATFORM-KERNEL SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-CATALOGUE-6 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-16 SVC-CATALOGUE-DRAFTED-24 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-DRAFTED-34 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-PRICING-1 SVC-CATALOGUE-PRODUCT-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 VM-CATALOGUE-EVENT-1 VM-CATALOGUE-PRODUCT-1 | Operations: listPricingRulePriority, listQuantityGroupVolume, listResidencyNationalityMarket, listTimeslotPerformanceTime. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 3 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listPricingRulePriority`, `catalogue#listQuantityGroupVolume`, `catalogue#listResidencyNationalityMarket`, `catalogue#listTimeslotPerformanceTime` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | VM-ADM-050 | AM-TICKETING-P08-3 | [BE] ADM-050 Price Category & Rate Type Library | 2 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-CATALOGUE-CATALOGUE-10 SVC-CATALOGUE-DRAFTED-14 | Define standardized commercial rate categories used across TICVAI. This avoids different venues independently creating categories such as: “Adult,” “Adult Standard,” “Normal Adult,” and “Full Adult.” Module: Commercial. App: Venue Management. Waits for its definition: ADM-050's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-050` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-054 | AM-TICKETING-P08-3 | [BE] ADM-054 Market, Venue & Currency Pricing Structure | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-CATALOGUE-CATALOGUE-10 SVC-CATALOGUE-DRAFTED-13 | Support TICVAI's multi-country, multi-market, multi-venue and multi-currency commercial model. Module: Commercial. App: Venue Management. Done when `ADM-054` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-056 | AM-TICKETING-P08-3 | [BE] ADM-056 Price List Templates, Clone & Reuse | 3 | New full-stack developer 2 |  | SETUP-CLIENTS SVC-CATALOGUE-CATALOGUE-9 SVC-CATALOGUE-DRAFTED-14 | Accelerate commercial setup across new venues, events, seasons and markets. Module: Commercial. App: Venue Management. Done when `ADM-056` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-058 | AM-TICKETING-P08-3 | [BE] ADM-058 Pricing Rule Command Center | 5 | Surendra |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-14 SVC-CATALOGUE-DRAFTED-15 SVC-CATALOGUE-DRAFTED-16 | Provide administrators with a centralized workspace for all pricing eligibility and contextual pricing rules. Module: Commercial. App: Venue Management. Done when `ADM-058` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-059 | AM-TICKETING-P08-3 | [BE] ADM-059 Customer Segment & Profile Pricing Rules | 3 | Sanket Keluskar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-13 | Define price eligibility based on customer characteristics and commercial segments. Module: Commercial. App: Venue Management. Done when `ADM-059` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-060 | AM-TICKETING-P08-3 | [BE] ADM-060 Membership & Loyalty Pricing Rules | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-14 | Control member-specific and loyalty-tier pricing. Module: Commercial. App: Venue Management. Done when `ADM-060` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-061 | AM-TICKETING-P08-3 | [BE] ADM-061 Residency, Nationality & Market Pricing Rules | 3 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-15 | Support geographically differentiated commercial pricing. Module: Commercial. App: Venue Management. Done when `ADM-061` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-063 | AM-TICKETING-P08-3 | [BE] ADM-063 Location, Venue & Event Pricing Rules | 3 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-13 | Allow rates to vary according to where and for which event/experience the product is sold. Module: Commercial. App: Venue Management. Done when `ADM-063` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-064 | AM-TICKETING-P08-3 | [BE] ADM-064 Quantity, Group & Volume Pricing Rules | 2 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-15 | Support commercial rates based on purchased quantity or group size. Module: Commercial. App: Venue Management. Waits for its definition: ADM-064's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-064` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-065 | AM-TICKETING-P08-3 | [BE] ADM-065 Effective Date, Season & Day-Based Pricing Rules | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-13 | Control commercial price selection over time. Module: Commercial. App: Venue Management. Done when `ADM-065` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-066 | AM-TICKETING-P08-3 | [BE] ADM-066 Timeslot, Performance & Time-of-Day Pricing Rules | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-15 | Allow commercial pricing to differ across times within the same day or event. Module: Commercial. App: Venue Management. Done when `ADM-066` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-067 | AM-TICKETING-P08-3 | [BE] ADM-067 Pricing Rule Priority, Conflict Resolution & Testing | 2 | New full-stack developer 1 |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-14 SVC-CATALOGUE-DRAFTED-15 SVC-CATALOGUE-DRAFTED-16 | Define how TICVAI decides the final applicable rate when multiple pricing rules match. This is the critical control screen for Board 2. Board 1 established what commercial prices exist. Board 2 determines which commercial rate applies to a transaction. Module: Commercial. App: Venue Management. Done when `ADM-067` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-076 | AM-TICKETING-P08-4 | [BE] ADM-076 Price Breakdown, Calculation Simulation & Explainability | 3 | New full-stack developer 2 |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-6 | Allow administrators to test the complete calculation before releasing configuration into production. Module: Commercial. App: Venue Management. Done when `ADM-076` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | SVC-CATALOGUE-DRAFTED-21 | AM-TICKETING-P08-5 | [BE] CatalogueService: listChannelCustomerSegment, listCompetitorPricingMarket, listDynamicPriceBand, listDynamicPricingAutomation | 8 | Hrushikant Patkar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-10 MIG-CATALOGUE-6 MIG-PRICING-2 PLATFORM-KERNEL SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-12 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-CATALOGUE-6 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-24 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-DRAFTED-34 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 VM-CATALOGUE-PRODUCT-1 | Operations: listChannelCustomerSegment, listCompetitorPricingMarket, listDynamicPriceBand, listDynamicPricingAutomation. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 5 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listChannelCustomerSegment`, `catalogue#listCompetitorPricingMarket`, `catalogue#listDynamicPriceBand`, `catalogue#listDynamicPricingAutomation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-CATALOGUE-DRAFTED-23 | AM-TICKETING-P08-5 | [BE] CatalogueService: listPricing, listPricingCompliance, listSeasonalCalendarDay, listWeatherDemandImpact | 8 | Tanmay Dukhande | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-10 MIG-CATALOGUE-3 MIG-CATALOGUE-6 MIG-ORDERS MIG-PRICING-2 PLATFORM-KERNEL SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-10 SVC-CATALOGUE-CATALOGUE-11 SVC-CATALOGUE-CATALOGUE-12 SVC-CATALOGUE-CATALOGUE-13 SVC-CATALOGUE-CATALOGUE-14 SVC-CATALOGUE-CATALOGUE-15 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-CATALOGUE-6 SVC-CATALOGUE-CATALOGUE-9 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-16 SVC-CATALOGUE-DRAFTED-17 SVC-CATALOGUE-DRAFTED-2 SVC-CATALOGUE-DRAFTED-20 SVC-CATALOGUE-DRAFTED-24 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-DRAFTED-3 SVC-CATALOGUE-DRAFTED-33 SVC-CATALOGUE-DRAFTED-34 SVC-CATALOGUE-DRAFTED-56 SVC-CATALOGUE-DRAFTED-7 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-PRICING-1 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-IDENTITY-GUESTAUTH-2 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 VM-CATALOGUE-PRODUCT-1 | Operations: listPricing, listPricingCompliance, listSeasonalCalendarDay, listWeatherDemandImpact. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 5 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listPricing`, `catalogue#listPricingCompliance`, `catalogue#listSeasonalCalendarDay`, `catalogue#listWeatherDemandImpact` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | VM-ADM-093 | AM-TICKETING-P08-5 | [BE] ADM-093 Channel, Customer Segment & Location Dynamic Rules | 2 | Sanket Keluskar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-21 | Allow dynamic-pricing behavior to differ according to commercial context. Module: Commercial. App: Venue Management. Waits for its definition: ADM-093's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-093` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-094 | AM-TICKETING-P08-5 | [BE] ADM-094 Dynamic Price Bands, Ladders & Adjustment Matrix | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-CATALOGUE-CATALOGUE-12 SVC-CATALOGUE-DRAFTED-21 | Define the controlled monetary steps through which prices can move. This is preferable to allowing unrestricted price generation for many products. Module: Commercial. App: Venue Management. Done when `ADM-094` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-096 | AM-TICKETING-P08-5 | [BE] ADM-096 Dynamic Pricing Automation Policy & Control | 3 | Pranay Shinde |  | SETUP-CLIENTS SVC-CATALOGUE-CATALOGUE-12 SVC-CATALOGUE-DRAFTED-21 | Define how much authority the pricing engine has to act on a calculated dynamic price. This is different from Board 4's approval workflow. Board 5 determines whether the engine may act automatically. Board 4 handles governance when formal approval is required. Module: Commercial. App: Venue Management. Done when `ADM-096` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-102 | AM-TICKETING-P08-5 | [BE] ADM-102 Competitor Pricing & Market Position Intelligence | 2 | New full-stack developer 2 |  | SETUP-CLIENTS SVC-CATALOGUE-CATALOGUE-12 SVC-CATALOGUE-DRAFTED-21 | Allow TICVAI to understand its commercial position relative to relevant competitors. Module: Commercial. App: Venue Management. Done when `ADM-102` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-087 | AM-TICKETING-P08-5 | [BE] ADM-087 Pricing History, Audit & Compliance Explorer | 2 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-23 | Provide complete forensic traceability for every pricing configuration and change. Enable TICVAI revenue administrators to configure dynamic-pricing strategies using real-time commercial conditions such as: Demand + Occupancy + Availability + Inventory + Booking Velocity + Time-to- Event + Season + Day + Timeslot + Channel + Customer Segment + Location The engine converts those conditions into controlled price movements while always respecting commercial guardrails. Module: Commercial. App: Venue Management. Waits for its definition: ADM-087's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-087` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-092 | AM-TICKETING-P08-5 | [BE] ADM-092 Seasonal, Calendar, Day & Timeslot Dynamic Rules | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-CATALOGUE-CATALOGUE-12 SVC-CATALOGUE-DRAFTED-23 | Configure dynamic pricing behavior according to temporal commercial patterns. Module: Commercial. App: Venue Management. Waits for its definition: ADM-092's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-092` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-098 | AM-TICKETING-P08-5 | [BE] ADM-098 AI Pricing Intelligence Command Center | 3 | Sanket Keluskar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-23 | Provide Revenue Managers with a single operational view of all AI signals, forecasts, opportunities and risks influencing pricing. Module: Commercial. App: Venue Management. Done when `ADM-098` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-100 | AM-TICKETING-P08-5 | [BE] ADM-100 Weather Intelligence & Demand Impact Configuration | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-CATALOGUE-CATALOGUE-12 SVC-CATALOGUE-DRAFTED-23 | Allow TICVAI to understand how weather conditions affect demand for different venues and experiences. This should be much more sophisticated than simply connecting a weather API. Module: Commercial. App: Venue Management. Done when `ADM-100` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-088 | AM-TICKETING-P08-5 | [BE] ADM-088 Dynamic Pricing Strategy Command Center | 5 | New full-stack developer 1 |  | SETUP-CLIENTS SVC-CATALOGUE-CATALOGUE-12 SVC-CATALOGUE-DRAFTED-6 | Provide the central backend workspace for creating, monitoring, and managing all dynamic- pricing strategies. This should be the primary operational screen for Revenue Managers. Module: Commercial. App: Venue Management. Done when `ADM-088` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-089 | AM-TICKETING-P08-5 | [BE] ADM-089 Dynamic Pricing Strategy Builder | 5 | New full-stack developer 2 |  | SETUP-CLIENTS SVC-CATALOGUE-CATALOGUE-12 SVC-CATALOGUE-DRAFTED-24 SVC-CATALOGUE-DRAFTED-6 | Create the master dynamic-pricing strategy and define what commercial objects it controls. Module: Commercial. App: Venue Management. Done when `ADM-089` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-104 | AM-TICKETING-P08-5 | [BE] ADM-104 AI Demand Forecasting & Booking Curve Studio | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-6 | Predict future demand at a granular commercial level. This is the core predictive engine behind intelligent dynamic pricing. Module: Commercial. App: Venue Management. Done when `ADM-104` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-108 | AM-TICKETING-P08-6 | [BE] ADM-108 Revenue Optimization Command Center | 5 | Pranay Shinde |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-6 | Provide Revenue Managers with the operational control center for all dynamic pricing simulations, AI recommendations, automated changes, experiments and revenue optimization activity. Module: Commercial. App: Venue Management. Done when `ADM-108` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | SVC-CATALOGUE-DRAFTED-31 | AM-TICKETING-P08-7 | [BE] CatalogueService: listChannelExceptionIncident, listChannelGovernanceSla, listChannelLogTransaction, listChannelPerformanceCommercial | 8 | New full-stack developer 1 | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-11 MIG-CATALOGUE-12 MIG-CATALOGUE-3 MIG-CATALOGUE-7 MIG-ORDERS PLATFORM-KERNEL SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-10 SVC-CATALOGUE-CATALOGUE-11 SVC-CATALOGUE-CATALOGUE-12 SVC-CATALOGUE-CATALOGUE-13 SVC-CATALOGUE-CATALOGUE-14 SVC-CATALOGUE-CATALOGUE-15 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-CATALOGUE-6 SVC-CATALOGUE-CATALOGUE-9 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-16 SVC-CATALOGUE-DRAFTED-17 SVC-CATALOGUE-DRAFTED-2 SVC-CATALOGUE-DRAFTED-20 SVC-CATALOGUE-DRAFTED-24 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-DRAFTED-3 SVC-CATALOGUE-DRAFTED-33 SVC-CATALOGUE-DRAFTED-34 SVC-CATALOGUE-DRAFTED-56 SVC-CATALOGUE-DRAFTED-7 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-IDENTITY-GUESTAUTH-2 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-PAYMENT-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-LEASE-1 VM-CATALOGUE-PRODUCT-1 | Operations: listChannelExceptionIncident, listChannelGovernanceSla, listChannelLogTransaction, listChannelPerformanceCommercial. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 7 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listChannelExceptionIncident`, `catalogue#listChannelGovernanceSla`, `catalogue#listChannelLogTransaction`, `catalogue#listChannelPerformanceCommercial` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
19 | 3 | VM-ADM-273 | AM-TICKETING-P08-7 | [BE] ADM-273 Channel Exceptions, Incidents & Recovery | 5 | Pranay Shinde |  | SETUP-CLIENTS SVC-CATALOGUE-CATALOGUE-14 SVC-CATALOGUE-CATALOGUE-15 SVC-CATALOGUE-DRAFTED-31 | Provide one operational workspace for resolving channel problems. Module: Commercial. App: Venue Management. Done when `ADM-273` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-274 | AM-TICKETING-P08-7 | [BE] ADM-274 Channel Performance & Commercial Analytics | 3 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-31 | Compare the commercial effectiveness of TICVAI sales channels. Module: Commercial. App: Venue Management. Done when `ADM-274` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-275 | AM-TICKETING-P08-7 | [BE] ADM-275 Channel Audit, Logs & Transaction Traceability | 2 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-31 | Provide complete traceability across channel configuration, synchronization and transactions. Module: Commercial. App: Venue Management. Done when `ADM-275` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-276 | AM-TICKETING-P08-7 | [BE] ADM-276 Channel Governance, SLA & Partner Control | 2 | Sanket Keluskar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-31 | Govern live channels and ensure that internal/external channels operate within approved commercial and service conditions. Module: Commercial. App: Venue Management. Done when `ADM-276` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
14 | 3 | SVC-CATALOGUE-ENTITLEMENT-3 | AM-TICKETING-P08-8 | [BE] CatalogueService: suspendEntitlement | 2 | Deep Khanvilkar | CatalogueService | MIG-ACCESS MIG-CATALOGUE MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: suspendEntitlement. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 8 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#suspendEntitlement` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-MARKETING-GUESTS-1 | AM-IDENTITY-SECURITY-P08 | [BE] MarketingService: getGuestTimeline | 1 | Deep Khanvilkar | MarketingService | MIG-ACCESS MIG-MARKETING MIG-MARKETING-2 MIG-ORDERS PLATFORM-KERNEL SVC-ACCESS-ACCESS-2 SVC-ACCESS-VALIDATION-2 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-ENTITLEMENT-3 SVC-FNB-FNB-17 SVC-FNB-FNB-6 SVC-IDENTITY-GUESTAUTH-2 SVC-IDENTITY-IDENTITY-4 SVC-MARKETING-CAMPAIGN-1 SVC-MARKETING-CASE-7 SVC-MARKETING-CASE-8 SVC-MARKETING-CONSENT-6 SVC-MARKETING-FEEDBACK-1 SVC-MARKETING-MARKETING-12 SVC-MARKETING-MARKETING-18 SVC-MARKETING-MARKETING-19 SVC-MARKETING-MARKETING-21 SVC-MARKETING-MARKETING-3 SVC-MARKETING-MARKETING-4 SVC-MARKETING-MARKETING-5 SVC-MARKETING-MARKETING-6 SVC-MARKETING-MESSAGE-1 SVC-MARKETING-MESSAGE-3 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-PUBLICAPI-1 SVC-PLATFORM-SUBSCRIPTION-6 VM-ACCESS-ACCESS-1 VM-MARKETING-MARKETING-2 | Operations: getGuestTimeline. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Identity & Security · Venue Management; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#getGuestTimeline` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-PLATFORM-DRAFTED-3 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] PlatformService: listCreditLimitExposure, listDepositGuaranteeFinancial, listMemberExceptionOverride, listMembershipAnnualPass | 8 | New full-stack developer 2 | PlatformService | MIG-ACCESS MIG-APPROVALS MIG-CATALOGUE MIG-CONTROL MIG-CONTROL-3 MIG-CONTROL-7 MIG-IDENTITY MIG-LEDGER MIG-ORDERS MIG-SUBSCRIPTION-3 PLATFORM-KERNEL SVC-ACCESS-ACCESS-2 SVC-ACCESS-VALIDATION-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-ENTITLEMENT-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-IDENTITY-ADMINISTRATION-2 SVC-IDENTITY-GUESTAUTH-2 SVC-IDENTITY-SSO-1 SVC-LEDGER-FINANCE-3 SVC-LEDGER-LEDGER-3 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-DRAFTED-1 SVC-PLATFORM-DRAFTED-12 SVC-PLATFORM-DRAFTED-13 SVC-PLATFORM-DRAFTED-16 SVC-PLATFORM-DRAFTED-2 SVC-PLATFORM-DRAFTED-5 SVC-PLATFORM-DRAFTED-8 SVC-PLATFORM-DRAFTED-9 SVC-PLATFORM-SUBSCRIPTION-16 SVC-PLATFORM-SUBSCRIPTION-17 SVC-PLATFORM-SUBSCRIPTION-21 SVC-PLATFORM-SUBSCRIPTION-5 SVC-PLATFORM-SUBSCRIPTION-6 SVC-PLATFORM-SUBSCRIPTION-7 SVC-PLATFORM-SUBSCRIPTION-8 SVC-PLATFORM-SUBSCRIPTION-9 SVC-TENANCY-APPROVALS-2 SVC-TENANCY-APPROVALS-4 SVC-TENANCY-APPROVALS-5 SVC-TENANCY-REQUEST-1 SVC-TENANCY-REQUEST-2 SVC-TENANCY-REQUEST-3 SVC-TENANCY-ROTA-2 SVC-WALLET-RETAIL-1 VM-ACCESS-ACCESS-1 VM-CATALOGUE-PRODUCT-1 VM-IDENTITY-ADMINISTRATION-1 VM-LEDGER-FINANCE-1 VM-LEDGER-RECOGNITION-1 VM-ORDER-ORDERS-2 VM-ORDER-SHIFT-1 VM-TENANCY-REQUEST-1 | Operations: listCreditLimitExposure, listDepositGuaranteeFinancial, listMemberExceptionOverride, listMembershipAnnualPass. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 1 of 3; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#listCreditLimitExposure`, `subscription#listDepositGuaranteeFinancial`, `subscription#listMemberExceptionOverride`, `subscription#listMembershipAnnualPass` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
19 | 3 | VM-PTR-036 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] PTR-036 Credit Limit & Exposure Management | 3 | Sanket Keluskar |  | SETUP-CLIENTS SVC-IDENTITY-MFA-1 SVC-IDENTITY-MFA-2 SVC-PLATFORM-DRAFTED-3 SVC-PLATFORM-SUBSCRIPTION-8 | Control the financial exposure TICVAI permits for partners buying on account. This should be one of the strongest finance-control screens in the B2B module. Module: Partners. App: Venue Management. Done when `PTR-036` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-PTR-037 | AM-SUBSCRIPTION-LICENSING-P08 | [BE] PTR-037 Deposit, Guarantee & Financial Security Management | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-PLATFORM-DRAFTED-3 SVC-PLATFORM-SUBSCRIPTION-9 | Manage financial security required to support partner credit or commercial access. Module: Partners. App: Venue Management. Done when `PTR-037` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | SVC-PLATFORM-DRAFTED-6 | AM-SUBSCRIPTION-LICENSING-P08-2 | [BE] PlatformService: getMembershipProductValidation, listMember, listMemberLifecycleCase, listMembershipActivationCredential | 8 | Tanmay Dukhande | PlatformService | MIG-ACCESS MIG-APPROVALS MIG-CATALOGUE MIG-IDENTITY MIG-ORDERS MIG-SUBSCRIPTION-3 PLATFORM-KERNEL SVC-ACCESS-ACCESS-2 SVC-ACCESS-VALIDATION-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-ENTITLEMENT-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-FNB-FNB-12 SVC-IDENTITY-ADMINISTRATION-2 SVC-IDENTITY-GUESTAUTH-2 SVC-IDENTITY-SSO-1 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-DRAFTED-1 SVC-PLATFORM-DRAFTED-12 SVC-PLATFORM-DRAFTED-13 SVC-PLATFORM-DRAFTED-16 SVC-PLATFORM-DRAFTED-2 SVC-PLATFORM-DRAFTED-5 SVC-PLATFORM-DRAFTED-8 SVC-PLATFORM-DRAFTED-9 SVC-PLATFORM-SUBSCRIPTION-16 SVC-PLATFORM-SUBSCRIPTION-17 SVC-PLATFORM-SUBSCRIPTION-21 SVC-PLATFORM-SUBSCRIPTION-5 SVC-PLATFORM-SUBSCRIPTION-6 SVC-PLATFORM-SUBSCRIPTION-7 SVC-PLATFORM-SUBSCRIPTION-8 SVC-TENANCY-APPROVALS-2 SVC-TENANCY-APPROVALS-4 SVC-TENANCY-APPROVALS-5 SVC-TENANCY-REQUEST-1 SVC-TENANCY-REQUEST-2 SVC-TENANCY-REQUEST-3 SVC-TENANCY-ROTA-2 SVC-WALLET-RETAIL-1 VM-ACCESS-ACCESS-1 VM-CATALOGUE-PRODUCT-1 VM-IDENTITY-ADMINISTRATION-1 VM-ORDER-REFUND-1 VM-TENANCY-REQUEST-1 | Operations: getMembershipProductValidation, listMember, listMemberLifecycleCase, listMembershipActivationCredential. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 2 of 3; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#getMembershipProductValidation`, `subscription#listMember`, `subscription#listMemberLifecycleCase`, `subscription#listMembershipActivationCredential` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-PLATFORM-DRAFTED-7 | AM-SUBSCRIPTION-LICENSING-P08-2 | [BE] PlatformService: listMembershipRenewalRetention, listMembershipUpgradeDowngrade, listRenewalAuto, listVisitAdmissionEntitlement | 8 | Surendra | PlatformService | MIG-ACCESS MIG-CATALOGUE MIG-ORDERS MIG-SUBSCRIPTION-3 PLATFORM-KERNEL SVC-ACCESS-ACCESS-2 SVC-ACCESS-VALIDATION-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-ENTITLEMENT-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-FNB-FNB-12 SVC-IDENTITY-GUESTAUTH-2 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-DRAFTED-16 SVC-PLATFORM-DRAFTED-2 SVC-PLATFORM-DRAFTED-5 SVC-PLATFORM-DRAFTED-8 SVC-PLATFORM-SUBSCRIPTION-21 SVC-PLATFORM-SUBSCRIPTION-6 SVC-PLATFORM-SUBSCRIPTION-7 SVC-WALLET-RETAIL-1 VM-ACCESS-ACCESS-1 VM-CATALOGUE-PRODUCT-1 VM-ORDER-REFUND-1 | Operations: listMembershipRenewalRetention, listMembershipUpgradeDowngrade, listRenewalAuto, listVisitAdmissionEntitlement. Spec: contracts (subscription) at the release tag, served by ADAM. Built for Subscription & Licensing · Venue Management 2 of 3; additive to PlatformService, whose first-release owner (Pranay Shinde) reviews. Done when `subscription#listMembershipRenewalRetention`, `subscription#listMembershipUpgradeDowngrade`, `subscription#listRenewalAuto`, `subscription#listVisitAdmissionEntitlement` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-CATALOGUE-DRAFTED-18 | AM-TICKETING-P08-4 | [BE] CatalogueService: listFeeSurcharge, listFeeWaiverTax, listPriceCalculationSequence, listPricingChangeImpact | 8 | New full-stack developer 2 | CatalogueService | MIG-ACCESS MIG-CATALOGUE MIG-CATALOGUE-2 MIG-CATALOGUE-4 MIG-CATALOGUE-6 MIG-CATALOGUE-7 MIG-ORDERS PLATFORM-KERNEL SVC-ACCESS-ACCESS-2 SVC-ACCESS-VALIDATION-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-11 SVC-CATALOGUE-CATALOGUE-12 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-CATALOGUE-3 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-17 SVC-CATALOGUE-DRAFTED-20 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-DRAFTED-3 SVC-CATALOGUE-DRAFTED-7 SVC-CATALOGUE-ENTITLEMENT-3 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-PRICING-1 SVC-CATALOGUE-PRODUCT-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-IDENTITY-GUESTAUTH-2 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 VM-ACCESS-ACCESS-1 VM-CATALOGUE-EVENT-1 VM-CATALOGUE-PRODUCT-1 | Operations: listFeeSurcharge, listFeeWaiverTax, listPriceCalculationSequence, listPricingChangeImpact. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 4 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listFeeSurcharge`, `catalogue#listFeeWaiverTax`, `catalogue#listPriceCalculationSequence`, `catalogue#listPricingChangeImpact` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | VM-ADM-071 | AM-TICKETING-P08-4 | [BE] ADM-071 Fee & Surcharge Library | 5 | New full-stack developer 1 |  | SETUP-CLIENTS SVC-CATALOGUE-CATALOGUE-11 SVC-CATALOGUE-DRAFTED-18 | Create standardized reusable non-base-price charges. Module: Commercial. App: Venue Management. Done when `ADM-071` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-073 | AM-TICKETING-P08-4 | [BE] ADM-073 Fee Waiver, Tax Exemption & Exception Rules | 3 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-18 | Govern circumstances under which a normally applicable tax or fee may be reduced, waived or exempted. Module: Commercial. App: Venue Management. Done when `ADM-073` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-074 | AM-TICKETING-P08-4 | [BE] ADM-074 Price Calculation Sequence & Formula Engine | 3 | Sanket Keluskar |  | SETUP-CLIENTS SVC-CATALOGUE-CATALOGUE-11 SVC-CATALOGUE-DRAFTED-18 | Define the exact sequence TICVAI follows to calculate the final payable amount. This is the heart of Board 3. Module: Commercial. App: Venue Management. Done when `ADM-074` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-082 | AM-TICKETING-P08-4 | [BE] ADM-082 Pricing Change Impact Analysis | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-18 SVC-CATALOGUE-DRAFTED-7 | Determine the commercial and operational consequences of a pricing change before approval and publication. This is one of the most important screens in Board 4. Module: Commercial. App: Venue Management. Done when `ADM-082` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | SVC-ORDER-ORDERS-9 | AM-TICKETING-P08-8 | [BE] OrderService: createMemberException | 1 | Deep Khanvilkar | OrderService | MIG-ORDERS-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createMemberException. Spec: contracts (orders) at the release tag, served by ADAM. Built for Ticketing · Venue Management 8 of 10; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#createMemberException` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | VM-ADM-365 | AM-TICKETING-P08-8 | [BE] ADM-365 Risk & Governance Analytics | 2 | New full-stack developer 1 |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-34 SVC-CATALOGUE-DRAFTED-7 | Provide management with consolidated visibility of approval risk. Module: Platform. App: Venue Management. Waits for its definition: ADM-365's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-365` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
11 | 3 | MIG-CATALOGUE-14 | AM-TICKETING-P08-9 | [DB] Forward migration V1190__catalogue.sql: catalogue for Ticketing · Venue Management 9 of 10 (2 tables) | 2 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-CATALOGUE VM-MIG-CATALOGUE | Tables: catalogue.event_reschedule, catalogue.prepaid_minutes. Source DDL: backend/tenant/010-catalogue.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `catalogue.event_reschedule`, `catalogue.prepaid_minutes` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
12 | 3 | SVC-TENANCY-ACCREDITATION-2 | AM-TICKETING-P08-9 | [BE] TenancyService: listAccessProfiles | 1 | Deep Khanvilkar | TenancyService | MIG-ACCREDITATION-3 PLATFORM-KERNEL | Operations: listAccessProfiles. Spec: contracts (accreditation) at the release tag, served by ADAM. Built for Ticketing · Venue Management 9 of 10; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `accreditation#listAccessProfiles` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-EVENTS-5 | AM-TICKETING-P08-9 | [BE] CatalogueService: rescheduleEvent, setEventCapacityProfile, setEventRegistration, setPrepaidMinutePackage | 8 | Tanmay Dukhande | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-14 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: rescheduleEvent, setEventCapacityProfile, setEventRegistration, setPrepaidMinutePackage. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 9 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#rescheduleEvent`, `catalogue#setEventCapacityProfile`, `catalogue#setEventRegistration`, `catalogue#setPrepaidMinutePackage` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-EVENTS-6 | AM-TICKETING-P08-9 | [BE] CatalogueService: setSpace | 2 | Sanket Keluskar | CatalogueService | MIG-CATALOGUE-13 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setSpace. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 9 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#setSpace` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | SVC-CATALOGUE-EVENTS-3 | AM-TICKETING-P08-8 | [BE] CatalogueService: estimateEventResourceCost, getEventResourcePlan, listEventTypes, listSpaces | 3 | Sanket Keluskar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-13 PLATFORM-KERNEL SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-2 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-EVENTS-4 SVC-CATALOGUE-EVENTS-6 | Operations: estimateEventResourceCost, getEventResourcePlan, listEventTypes, listSpaces. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 8 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#estimateEventResourceCost`, `catalogue#getEventResourcePlan`, `catalogue#listEventTypes`, `catalogue#listSpaces` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | MIG-CATALOGUE-15 | AM-TICKETING-P08-10 | [DB] Forward migration V1196__catalogue.sql: catalogue for Ticketing · Venue Management 10 of 10 (1 tables) | 1 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-CATALOGUE VM-MIG-CATALOGUE | Tables: catalogue.performance_media. Source DDL: backend/tenant/010-catalogue.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `catalogue.performance_media` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
12 | 3 | SVC-CATALOGUE-EVENTS-7 | AM-TICKETING-P08-10 | [BE] CatalogueService: assignPerformanceMedia | 1 | Chinmay Patkar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-15 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: assignPerformanceMedia. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Ticketing · Venue Management 10 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#assignPerformanceMedia` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-WALLET-WALLET-6 | AM-TICKETING-P08-10 | [BE] WalletService: listCreditTypes | 1 | Tanmay Dukhande | WalletService | MIG-WALLET PLATFORM-KERNEL SVC-WALLET-WALLET-1 | Operations: listCreditTypes. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Ticketing · Venue Management 10 of 10; additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#listCreditTypes` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | MIG-PROMOTIONS-3 | AM-PRICING-PROMOTIONS-P08 | [DB] Forward migration V1124__promotions.sql: promotions for Pricing & Promotions · Venue Management 1 of 8 (2 tables) | 2 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-ORDERS MIG-PROMOTIONS VM-MIG-PROMOTIONS | Tables: promotions.promotion_alert, promotions.recommendation_outcome. Source DDL: backend/tenant/010-promotions.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `promotions.promotion_alert`, `promotions.recommendation_outcome` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
12 | 3 | SVC-CATALOGUE-ALLOCATION-1 | AM-PRICING-PROMOTIONS-P08 | [BE] CatalogueService: listAllocationSplits, previewAllocationSplit | 3 | Sanket Keluskar | CatalogueService | MIG-CATALOGUE MIG-PROMOTIONS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listAllocationSplits, previewAllocationSplit. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 1 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listAllocationSplits`, `promotions#previewAllocationSplit` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-CATALOGUE-DRAFTED-12 | AM-TICKETING-P08-3 | [BE] CatalogueService: listBundlePricingCommercial, listChannelBasedPricing, listCommercialPricing, listCommercialPricingStructure | 5 | New full-stack developer 1 | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-4 MIG-CATALOGUE-6 MIG-CATALOGUE-8 MIG-PRICING-2 MIG-PROMOTIONS PLATFORM-KERNEL SVC-CATALOGUE-ALLOCATION-1 SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-10 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-CATALOGUE-6 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-16 SVC-CATALOGUE-DRAFTED-24 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-DRAFTED-3 SVC-CATALOGUE-DRAFTED-34 SVC-CATALOGUE-PRICING-1 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 VM-CATALOGUE-PRODUCT-1 | Operations: listBundlePricingCommercial, listChannelBasedPricing, listCommercialPricing, listCommercialPricingStructure. Spec: contracts (catalogue, promotions) at the release tag, served by ADAM. Built for Ticketing · Venue Management 3 of 10; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listBundlePricingCommercial`, `catalogue#listChannelBasedPricing`, `catalogue#listCommercialPricing`, `catalogue#listCommercialPricingStructure` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | VM-ADM-048 | AM-TICKETING-P08-3 | [BE] ADM-048 Commercial Pricing Command Center | 5 | Pranay Shinde |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-12 | Provide the central administrative workspace for all commercial pricing structures across This is the first page a Revenue/Pricing Administrator sees when entering the module. Module: Commercial. App: Venue Management. Done when `ADM-048` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-057 | AM-TICKETING-P08-3 | [BE] ADM-057 Commercial Pricing Structure Validation | 2 | Surendra |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-12 | Validate that the commercial pricing foundation is structurally complete before it proceeds to rule configuration, governance, or publication. This is not the final publication screen. Board 4 owns approval and publication. Board 1 defined what the commercial prices are and how they are structured. Module: Commercial. App: Venue Management. Waits for its definition: ADM-057's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-057` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-062 | AM-TICKETING-P08-3 | [BE] ADM-062 Channel-Based Pricing Rules | 2 | New full-stack developer 2 |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-12 | Determine which commercial rate applies based on sales channel. Module: Commercial. App: Venue Management. Waits for its definition: ADM-062's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-062` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
13 | 3 | SVC-CATALOGUE-COUPON-3 | AM-PRICING-PROMOTIONS-P08 | [BE] CatalogueService: getCouponCodeBatch | 1 | Deep Khanvilkar | CatalogueService | MIG-PROMOTIONS PLATFORM-KERNEL SVC-CATALOGUE-COUPON-1 | Operations: getCouponCodeBatch. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 1 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#getCouponCodeBatch` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | SVC-CATALOGUE-VOUCHER-2 | AM-PRICING-PROMOTIONS-P08 | [BE] CatalogueService: redeemVoucher | 1 | Deep Khanvilkar | CatalogueService | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-PROMOTIONS | Operations: redeemVoucher. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 1 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#redeemVoucher` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-CATALOGUE-PROMOTION-4 | AM-PRICING-PROMOTIONS-P08 | [BE] CatalogueService: createCommercialCampaign, updateCommercialCampaign | 5 | Deep Khanvilkar | CatalogueService | MIG-PROMOTIONS MIG-PROMOTIONS-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createCommercialCampaign, updateCommercialCampaign. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 1 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#createCommercialCampaign`, `promotions#updateCommercialCampaign` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-CATALOGUE-DRAFTED-36 | AM-PRICING-PROMOTIONS-P08 | [BE] CatalogueService: listCustomerMembershipSegment, listDiscountLimitGuardrail, listPaymentMethodBank, listPercentageFixedDiscount | 3 | Hrushikant Patkar | CatalogueService | MIG-MARKETING MIG-PROMOTIONS MIG-PROMOTIONS-2 PLATFORM-KERNEL SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTION-4 SVC-CATALOGUE-PROMOTIONS-1 SVC-MARKETING-LOYALTY-1 SVC-MARKETING-LOYALTY-3 SVC-MARKETING-SEGMENT-1 | Operations: listCustomerMembershipSegment, listDiscountLimitGuardrail, listPaymentMethodBank, listPercentageFixedDiscount. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 1 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listCustomerMembershipSegment`, `promotions#listDiscountLimitGuardrail`, `promotions#listPaymentMethodBank`, `promotions#listPercentageFixedDiscount` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-CATALOGUE-DRAFTED-39 | AM-PRICING-PROMOTIONS-P08 | [BE] CatalogueService: listUniqueCodeGeneration, listUsageCapacityFrequency, listVolumeBulkTier, setRuleTestRecommendation | 3 | Surendra | CatalogueService | MIG-CATALOGUE MIG-ORDERS-3 MIG-PROMOTIONS PLATFORM-KERNEL SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-COUPON-1 SVC-CATALOGUE-COUPON-2 SVC-CATALOGUE-DRAFTED-1 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTIONS-1 VM-CATALOGUE-PRODUCT-1 | Operations: listUniqueCodeGeneration, listUsageCapacityFrequency, listVolumeBulkTier, setRuleTestRecommendation. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 1 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listUniqueCodeGeneration`, `promotions#listUsageCapacityFrequency`, `promotions#listVolumeBulkTier`, `promotions#setRuleTestRecommendation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-CATALOGUE-UPSELL-2 | AM-PRICING-PROMOTIONS-P08 | [BE] CatalogueService: getUpsellSuggestions | 2 | Sanket Keluskar | CatalogueService | MIG-CATALOGUE PLATFORM-KERNEL SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 VM-CATALOGUE-PRODUCT-1 VM-CATALOGUE-UPSELL-1 VM-MIG-PROMOTIONS | Operations: getUpsellSuggestions. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 1 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#getUpsellSuggestions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-CATALOGUE-BUNDLE-3 | AM-PRICING-PROMOTIONS-P08 | [BE] CatalogueService: listBundles | 2 | New full-stack developer 2 | CatalogueService | MIG-PROMOTIONS PLATFORM-KERNEL SVC-CATALOGUE-ALLOCATION-1 SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 | Operations: listBundles. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 1 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listBundles` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-CATALOGUE-DRAFTED-35 | AM-PRICING-PROMOTIONS-P08 | [BE] CatalogueService: listCampaignCalendarTimeline, listCampaignPromotionPerformance, listCartTransactionThreshold, listCodeEligibilityRestriction | 3 | New full-stack developer 1 | CatalogueService | MIG-ORDERS MIG-ORDERS-3 MIG-PROMOTIONS MIG-PROMOTIONS-2 PLATFORM-KERNEL SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-COUPON-1 SVC-CATALOGUE-COUPON-2 SVC-CATALOGUE-DRAFTED-1 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTION-4 SVC-CATALOGUE-PROMOTIONS-1 SVC-FNB-FNB-12 SVC-IDENTITY-GUESTAUTH-2 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 | Operations: listCampaignCalendarTimeline, listCampaignPromotionPerformance, listCartTransactionThreshold, listCodeEligibilityRestriction. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 1 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listCampaignCalendarTimeline`, `promotions#listCampaignPromotionPerformance`, `promotions#listCartTransactionThreshold`, `promotions#listCodeEligibilityRestriction` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-CATALOGUE-DRAFTED-38 | AM-PRICING-PROMOTIONS-P08 | [BE] CatalogueService: listPromotionHealthPerformance, listPromotionPerformance, listSpecialPriceGuest, listTimeBasedSeasonal | 3 | New full-stack developer 2 | CatalogueService | MIG-ORDERS MIG-ORDERS-3 MIG-PROMOTIONS MIG-PROMOTIONS-2 MIG-PROMOTIONS-3 PLATFORM-KERNEL SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTION-4 SVC-CATALOGUE-PROMOTIONS-1 SVC-FNB-FNB-12 SVC-IDENTITY-GUESTAUTH-2 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 | Operations: listPromotionHealthPerformance, listPromotionPerformance, listSpecialPriceGuest, listTimeBasedSeasonal. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 1 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listPromotionHealthPerformance`, `promotions#listPromotionPerformance`, `promotions#listSpecialPriceGuest`, `promotions#listTimeBasedSeasonal` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-CATALOGUE-PROMOTIONS-3 | AM-PRICING-PROMOTIONS-P08 | [BE] CatalogueService: getRecommendations | 1 | Deep Khanvilkar | CatalogueService | MIG-CATALOGUE MIG-MARKETING MIG-ORDERS MIG-PROMOTIONS PLATFORM-KERNEL SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTIONS-1 SVC-MARKETING-CONSENT-3 SVC-MARKETING-GUEST-2 SVC-MARKETING-GUESTS-2 SVC-MARKETING-MARKETING-6 SVC-MARKETING-MARKETING-7 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-PAYMENT-1 SVC-ORDER-SYNC-1 SVC-VENUEOPS-VISITPLAN-1 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-LEASE-1 VM-CATALOGUE-PRODUCT-1 | Operations: getRecommendations. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 1 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#getRecommendations` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | VM-ADM-149 | AM-PRICING-PROMOTIONS-P08 | [BE] ADM-149 Percentage & Fixed Discount Configurator | 2 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-36 | Configure the two fundamental discount types required by the matrix. The matrix explicitly states that discounts may be defined as percentage or fixed value. Module: Commercial. App: Venue Management. Done when `ADM-149` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-151 | AM-PRICING-PROMOTIONS-P08 | [BE] ADM-151 Volume, Bulk & Tier Discount Configurator | 2 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-39 | Manage quantity-based and bulk-purchase commercial rules. The matrix requires configurable bulk thresholds and discount percentages, dedicated group pricing, and tiered bulk purchasing. Module: Commercial. App: Venue Management. Waits for its definition: ADM-151's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-151` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-153 | AM-PRICING-PROMOTIONS-P08 | [BE] ADM-153 Customer, Membership & Segment Discount Rules | 2 | Sanket Keluskar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-36 | Configure discounts based on who the customer is. Module: Commercial. App: Venue Management. Waits for its definition: ADM-153's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-153` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-154 | AM-PRICING-PROMOTIONS-P08 | [BE] ADM-154 Payment Method, Bank & Partner Discount Rules | 2 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-36 | Configure discounts triggered by how the guest pays or which commercial partner they belong to. The matrix specifically includes discounts for payment types and bank credit/debit cards. Module: Commercial. App: Venue Management. Done when `ADM-154` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-156 | AM-PRICING-PROMOTIONS-P08 | [BE] ADM-156 Discount Limits, Guardrails & Commercial Controls | 2 | New full-stack developer 2 |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-36 | Protect the business from incorrectly configured discounts and excessive commercial exposure. Module: Commercial. App: Venue Management. Done when `ADM-156` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-160 | AM-PRICING-PROMOTIONS-P08 | [BE] ADM-160 Unique Code Generation & Batch Manager | 3 | Pranay Shinde |  | SETUP-CLIENTS SVC-CATALOGUE-COUPON-1 SVC-CATALOGUE-COUPON-3 SVC-CATALOGUE-DRAFTED-39 | Generate and manage large quantities of secure unique promotional codes. Module: Commercial. App: Venue Management. Done when `ADM-160` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-162 | AM-PRICING-PROMOTIONS-P08 | [BE] ADM-162 Usage, Capacity & Frequency Control | 2 | Sanket Keluskar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-39 | Control exactly how frequently and how many times promotional codes may be redeemed. Module: Commercial. App: Venue Management. Done when `ADM-162` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-142 | AM-PRICING-PROMOTIONS-P08 | [BE] ADM-142 Campaign Calendar & Timeline | 3 | Sanket Keluskar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-35 SVC-CATALOGUE-PROMOTION-3 | Provide a calendar-based operational view of promotions. Module: Commercial. App: Venue Management. Done when `ADM-142` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-146 | AM-PRICING-PROMOTIONS-P08 | [BE] ADM-146 Promotion Health & Performance Monitor | 3 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-38 | Provide near-real-time operational performance monitoring while campaigns are running. Module: Commercial. App: Venue Management. Done when `ADM-146` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-150 | AM-PRICING-PROMOTIONS-P08 | [BE] ADM-150 Cart & Transaction Threshold Rules | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-35 | Configure promotions triggered by basket value, ticket quantity, transaction value, or purchase composition. The matrix specifically requires rules such as if more than X tickets are purchased, apply Y discount to the entire transaction. Module: Commercial. App: Venue Management. Waits for its definition: ADM-150's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-150` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-152 | AM-PRICING-PROMOTIONS-P08 | [BE] ADM-152 Time-Based & Seasonal Discount Rules | 2 | Hrushikant Patkar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-38 | Configure promotional pricing based on when the customer purchases or visits. Module: Commercial. App: Venue Management. Waits for its definition: ADM-152's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-152` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-155 | AM-PRICING-PROMOTIONS-P08 | [BE] ADM-155 Special Price & Guest Offer Configurator | 3 | Surendra |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-38 | Manage commercially distinct special-price products and targeted offers without unnecessarily duplicating product SKUs. Module: Commercial. App: Venue Management. Done when `ADM-155` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-161 | AM-PRICING-PROMOTIONS-P08 | [BE] ADM-161 Code Eligibility & Restriction Manager | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-35 | Determine where, when, by whom, and against what a code can be redeemed. The matrix explicitly requires promo codes to support restrictions for usage, dates, duration, capacity, frequency, location, group, partner, operating area, and sales channel. Module: Commercial. App: Venue Management. Waits for its definition: ADM-161's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-161` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
13 | 3 | MIG-PROMOTIONS-4 | AM-PRICING-PROMOTIONS-P08-2 | [DB] Forward migration V1131__promotions.sql: promotions for Pricing & Promotions · Venue Management 2 of 8 (1 tables) | 1 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-PROMOTIONS VM-MIG-PROMOTIONS | Tables: promotions.partner_bundle_product. Source DDL: backend/tenant/010-promotions.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `promotions.partner_bundle_product` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
14 | 3 | SVC-CATALOGUE-BUNDLE-4 | AM-PRICING-PROMOTIONS-P08-2 | [BE] CatalogueService: listBundlePartnerProductMappings, setBundlePartnerProductMappings | 5 | Hrushikant Patkar | CatalogueService | MIG-PROMOTIONS MIG-PROMOTIONS-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listBundlePartnerProductMappings, setBundlePartnerProductMappings. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 2 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listBundlePartnerProductMappings`, `promotions#setBundlePartnerProductMappings` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-CATALOGUE-DRAFTED-37 | AM-PRICING-PROMOTIONS-P08 | [BE] CatalogueService: listPromotionActivityVersion, listPromotionAlertException, listPromotionCampaign, listPromotionChannel | 3 | Hrushikant Patkar | CatalogueService | MIG-ORDERS-3 MIG-PROMOTIONS MIG-PROMOTIONS-2 MIG-PROMOTIONS-3 PLATFORM-KERNEL SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-BUNDLE-4 SVC-CATALOGUE-COUPON-1 SVC-CATALOGUE-COUPON-2 SVC-CATALOGUE-DRAFTED-1 SVC-CATALOGUE-DRAFTED-4 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTION-4 SVC-CATALOGUE-PROMOTIONS-1 | Operations: listPromotionActivityVersion, listPromotionAlertException, listPromotionCampaign, listPromotionChannel. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 1 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listPromotionActivityVersion`, `promotions#listPromotionAlertException`, `promotions#listPromotionCampaign`, `promotions#listPromotionChannel` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | VM-ADM-139 | AM-PRICING-PROMOTIONS-P08 | [BE] ADM-139 Promotion & Campaign Directory | 3 | Pranay Shinde |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-35 SVC-CATALOGUE-DRAFTED-37 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTION-4 | Provide the master searchable list of every promotion and commercial campaign created within TICVAI. Module: Commercial. App: Venue Management. Done when `ADM-139` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-143 | AM-PRICING-PROMOTIONS-P08 | [BE] ADM-143 Promotion Channel & Publication Monitor | 3 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-37 | Ensure promotional configurations are correctly synchronized across every TICVAI sales channel. Module: Commercial. App: Venue Management. Done when `ADM-143` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-144 | AM-PRICING-PROMOTIONS-P08 | [BE] ADM-144 Promotion Alerts & Exception Center | 3 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-37 | Centralize operational, commercial, and financial alerts affecting promotions. Module: Commercial. App: Venue Management. Done when `ADM-144` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-147 | AM-PRICING-PROMOTIONS-P08 | [BE] ADM-147 Promotion Audit, Activity & Version History | 2 | New full-stack developer 1 |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-37 | Provide complete governance and traceability for every promotion. Board 2 is the core commercial rule engine for promotions. It shall allow authorized TICVAI business users to configure discount and promotion mechanics without development, including percentage and fixed discounts, transaction thresholds, volume discounts, bulk pricing, early-bird and last-minute offers, special guest pricing, payment-method discounts, partner discounts, and dynamic conditional discounts. The matrix explicitly requires percentage/value discounts, quantity thresholds, bulk discounts, early-bird/volume/customer-segment conditions, payment-type offers, group pricing, and special individual pricing. The board should contain 10 backend screens. Module: Commercial. App: Venue Management. Waits for its definition: ADM-147's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-147` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | SVC-CATALOGUE-DRAFTED-43 | AM-PRICING-PROMOTIONS-P08-2 | [BE] CatalogueService: listPartnerExternalProduct, listRedemption, listRedemptionCodeLookup, listRevenueAllocationCost | 3 | Hrushikant Patkar | CatalogueService | MIG-ORDERS MIG-ORDERS-3 MIG-PROMOTIONS MIG-PROMOTIONS-4 PLATFORM-KERNEL SVC-CATALOGUE-ALLOCATION-1 SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-BUNDLE-4 SVC-CATALOGUE-COUPON-1 SVC-CATALOGUE-COUPON-2 SVC-CATALOGUE-DRAFTED-1 SVC-CATALOGUE-DRAFTED-4 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTION-4 SVC-CATALOGUE-PROMOTIONS-1 SVC-FNB-FNB-12 SVC-IDENTITY-GUESTAUTH-2 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 | Operations: listPartnerExternalProduct, listRedemption, listRedemptionCodeLookup, listRevenueAllocationCost. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 2 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listPartnerExternalProduct`, `promotions#listRedemption`, `promotions#listRedemptionCodeLookup`, `promotions#listRevenueAllocationCost` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-CATALOGUE-DRAFTED-40 | AM-PRICING-PROMOTIONS-P08-2 | [BE] CatalogueService: listAdvancedOffer, listAdvancedOfferGuardrail, listBundleAvailabilityCapacity, listBundleValidityScheduling | 3 | New full-stack developer 2 | CatalogueService | MIG-CATALOGUE MIG-ORDERS-3 MIG-PROMOTIONS PLATFORM-KERNEL SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTIONS-1 SVC-ORDER-PAYMENT-1 SVC-ORDER-SYNC-1 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-LEASE-1 | Operations: listAdvancedOffer, listAdvancedOfferGuardrail, listBundleAvailabilityCapacity, listBundleValidityScheduling. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 2 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listAdvancedOffer`, `promotions#listAdvancedOfferGuardrail`, `promotions#listBundleAvailabilityCapacity`, `promotions#listBundleValidityScheduling` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-CATALOGUE-DRAFTED-41 | AM-PRICING-PROMOTIONS-P08-2 | [BE] CatalogueService: listCheapestLowestValue, listCodeSecurityFraud, listComponentInventoryAvailability, listDynamicBundle | 3 | Sanket Keluskar | CatalogueService | MIG-CATALOGUE MIG-ORDERS MIG-ORDERS-3 MIG-PROMOTIONS MIG-PROMOTIONS-3 PLATFORM-KERNEL SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-COUPON-1 SVC-CATALOGUE-COUPON-2 SVC-CATALOGUE-DRAFTED-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTIONS-1 SVC-FNB-FNB-12 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-CART-3 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-PAYMENT-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 SVC-VENUEOPS-VISITPLAN-1 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-CATALOGUE-1 VM-CATALOGUE-LEASE-1 | Operations: listCheapestLowestValue, listCodeSecurityFraud, listComponentInventoryAvailability, listDynamicBundle. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 2 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listCheapestLowestValue`, `promotions#listCodeSecurityFraud`, `promotions#listComponentInventoryAvailability`, `promotions#listDynamicBundle` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-CATALOGUE-DRAFTED-42 | AM-PRICING-PROMOTIONS-P08-2 | [BE] CatalogueService: listDynamicBundle2, listDynamicBundleRule, listMultiBuyQuantity, listOfferBasketTrace | 2 | Deep Khanvilkar | CatalogueService | MIG-CATALOGUE MIG-PROMOTIONS MIG-PROMOTIONS-2 PLATFORM-KERNEL SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTION-4 SVC-CATALOGUE-PROMOTIONS-1 SVC-ORDER-PAYMENT-1 SVC-ORDER-SYNC-1 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-LEASE-1 | Operations: listDynamicBundle2, listDynamicBundleRule, listMultiBuyQuantity, listOfferBasketTrace. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 2 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listDynamicBundle2`, `promotions#listDynamicBundleRule`, `promotions#listMultiBuyQuantity`, `promotions#listOfferBasketTrace` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-CATALOGUE-DRAFTED-44 | AM-PRICING-PROMOTIONS-P08-2 | [BE] CatalogueService: listRewardSelectionSubstitution, listValidityDateTime, simulateBundlePreviewRecommendation | 2 | Chinmay Patkar | CatalogueService | MIG-CATALOGUE MIG-PROMOTIONS PLATFORM-KERNEL SVC-CATALOGUE-ALLOCATION-1 SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-COUPON-1 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTIONS-1 SVC-ORDER-PAYMENT-1 SVC-ORDER-SYNC-1 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-LEASE-1 | Operations: listRewardSelectionSubstitution, listValidityDateTime, simulateBundlePreviewRecommendation. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 2 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listRewardSelectionSubstitution`, `promotions#listValidityDateTime`, `promotions#simulateBundlePreviewRecommendation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | VM-ADM-165 | AM-PRICING-PROMOTIONS-P08-2 | [BE] ADM-165 Redemption Monitor & Code Lookup | 2 | New full-stack developer 1 |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-43 | Provide real-time operational visibility into coupon and promo-code redemption. Module: Commercial. App: Venue Management. Done when `ADM-165` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-167 | AM-PRICING-PROMOTIONS-P08-2 | [BE] ADM-167 Redemption Analytics, Audit & AI Optimization | 3 | Pranay Shinde |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-43 | Provide complete performance analytics and governance for coupon and promo-code campaigns. Board 4 shall provide TICVAI with an enterprise-grade Advanced Promotion Mechanics Engine for promotions involving relationships between products, quantities, basket composition, rewards, and qualifying purchases. While Board 2 defines standard discounts and thresholds and Board 3 manages promo codes/coupons, Board 4 answers: “When the customer buys X, what exactly should TICVAI give them, discount, replace, upgrade, or add to the transaction?” The matrix requires mechanics such as Buy X Get X, Buy X Get Y, Buy N Get X, percentage/amount discounts on another product, cheapest-item-free, fixed-price combinations, cross-category F&B/Retail rewards, added-value gifts, and automatic cart-level promotion application. Board 4 shall contain 10 backend screens. Module: Commercial. App: Venue Management. Done when `ADM-167` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-182 | AM-PRICING-PROMOTIONS-P08-2 | [BE] ADM-182 Bundle Pricing & Commercial Model | 2 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-12 | Determine how the bundle is commercially priced. Module: Commercial. App: Venue Management. Done when `ADM-182` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-185 | AM-PRICING-PROMOTIONS-P08-2 | [BE] ADM-185 Partner & External Product Bundle Manager | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-CATALOGUE-BUNDLE-4 SVC-CATALOGUE-DRAFTED-43 | Allow TICVAI bundles to include products or services owned by external operators. The matrix requires combinations with external products/services and bundles across different destinations, including systems that may use different databases. Module: Commercial. App: Venue Management. Done when `ADM-185` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-186 | AM-PRICING-PROMOTIONS-P08-2 | [BE] ADM-186 Revenue Allocation, Cost & Settlement Rules | 2 | New full-stack developer 2 |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-43 | Determine how bundle revenue is allocated across its components. This is explicitly required by the matrix for allocation across products, attractions, departments, partners, operators, and accounting entities. Module: Commercial. App: Venue Management. Done when `ADM-186` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-163 | AM-PRICING-PROMOTIONS-P08-2 | [BE] ADM-163 Validity, Date & Time Control | 2 | Surendra |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-44 | Control the temporal validity of coupons and codes. Module: Commercial. App: Venue Management. Waits for its definition: ADM-163's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-163` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-166 | AM-PRICING-PROMOTIONS-P08-2 | [BE] ADM-166 Code Security, Fraud & Exception Center | 2 | New full-stack developer 1 |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-41 | Detect promo-code abuse, leakage, abnormal redemption, and suspicious campaign behavior. Module: Commercial. App: Venue Management. Done when `ADM-166` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-168 | AM-PRICING-PROMOTIONS-P08-2 | [BE] ADM-168 Advanced Offer Command Center | 5 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-40 | Provide the centralized management workspace for all advanced promotional mechanics. Module: Commercial. App: Venue Management. Done when `ADM-168` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-170 | AM-PRICING-PROMOTIONS-P08-2 | [BE] ADM-170 Multi-Buy & Quantity Offer Configurator | 2 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-42 | Configure advanced quantity relationships that go beyond simple BOGO. Module: Commercial. App: Venue Management. Done when `ADM-170` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-171 | AM-PRICING-PROMOTIONS-P08-2 | [BE] ADM-171 Cheapest / Lowest-Value Item Promotion | 2 | Sanket Keluskar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-41 | Configure offers where TICVAI dynamically identifies the lowest-priced qualifying item. The matrix explicitly requires “buy multiple products and get cheapest item free” and adding cheaper qualifying items within the same transaction. Module: Commercial. App: Venue Management. Done when `ADM-171` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-175 | AM-PRICING-PROMOTIONS-P08-2 | [BE] ADM-175 Reward Selection, Substitution & Customer Choice | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-44 | Control situations where the customer can choose between multiple promotional rewards. Module: Commercial. App: Venue Management. Waits for its definition: ADM-175's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-175` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-176 | AM-PRICING-PROMOTIONS-P08-2 | [BE] ADM-176 Advanced Offer Guardrails & Conflict Controls | 2 | New full-stack developer 2 |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-40 | Prevent advanced offers from generating unintended financial or operational outcomes. This screen handles offer-specific safeguards; the complete cross-promotion stacking hierarchy remains in Board 8. Module: Commercial. App: Venue Management. Done when `ADM-176` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-177 | AM-PRICING-PROMOTIONS-P08-2 | [BE] ADM-177 Offer Simulation, Basket Trace & AI Optimization | 3 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-42 SVC-CATALOGUE-EVALUATION-1 SVC-CATALOGUE-PROMOTIONS-2 | Test complex promotion mechanics before publication. Module: Commercial. App: Venue Management. Waits for its definition: ADM-177's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-177` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-183 | AM-PRICING-PROMOTIONS-P08-2 | [BE] ADM-183 Bundle Availability, Capacity & Validation | 2 | Pranay Shinde |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-40 | Ensure that TICVAI does not sell a bundle unless all required components can actually be fulfilled. This is a direct requirement of the matrix: each bundle component maintains independent inventory, capacity, validity, redemption rules, and availability, and the system validates included products before confirming the sale. Module: Commercial. App: Venue Management. Done when `ADM-183` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-184 | AM-PRICING-PROMOTIONS-P08-2 | [BE] ADM-184 Bundle Validity, Scheduling & Redemption Rules | 2 | New full-stack developer 1 |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-40 | Control when bundle components may be consumed and whether they must be redeemed together or separately. Module: Commercial. App: Venue Management. Waits for its definition: ADM-184's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-184` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-187 | AM-PRICING-PROMOTIONS-P08-2 | [BE] ADM-187 Bundle Preview, Simulation & AI Recommendation | 2 | Sanket Keluskar |  | SETUP-CLIENTS SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-DRAFTED-44 | Validate a bundle end to end before it is published: preview it as a guest sees it, simulate its price and allocation, and review the AI recommendations on it. Module: Commercial. App: Venue Management. Waits for its definition: ADM-187's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-187` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-188 | AM-PRICING-PROMOTIONS-P08-2 | [BE] ADM-188 Dynamic Bundle Operations Command Center | 5 | Surendra |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-41 SVC-CATALOGUE-DRAFTED-42 | Provide real-time visibility into the operational health of all active bundles. Module: Commercial. App: Venue Management. Done when `ADM-188` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-189 | AM-PRICING-PROMOTIONS-P08-2 | [BE] ADM-189 Component Inventory & Availability Matrix | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-41 SVC-INVENTORY-ITEM-2 | Provide one centralized matrix showing availability for every component within every active bundle. Module: Commercial. App: Venue Management. Waits for its definition: ADM-189's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-189` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | DEVICE-BOCA-FGL | AM-DEVICES-BOCA | [BE] BOCA ticket and wristband printing: FGL driver behind the ticketPrinter port | 8 | Hrushikant Patkar |  | PLATFORM-KERNEL SVC-ORDER-ORDER-4 SVC-ORDER-ORDERS-5 SVC-ORDER-ORDERS-8 | BOCA ticket and wristband printing: FGL driver behind the ticketPrinter port. Builds: `adr ADR-0015`. In the device app (ADR-0015 Tier A; the client confirmed BOCA and sent its documents on 5 October 2026, sources/client/2026-10-05-allam-boca-printer.md; CHG-R4-002). Implement the ticketPrinter port of handoff/integration-register.md for BOCA in FGL: render a ticket or wristband from the ticket designer's layout (updateTicketTemplate, listTicketTemplates; the same layout printTicketProof previews) to FGL: text, fonts including Arabic (as a bitmap where FGL needs it), barcode and QR, the logo bitmap and the cut; printer status and errors (paper out, jam, offline) reported so the kiosk shows KSK-010 Print failure and the POS its reprint path (reprintOrder, POS-026); reprint; and a virtual (emulated) BOCA printer for the tests and CI. RFID encoding on the BOCA Lemur is built behind a flag, off, until the client confirms its scope (Decisions Register, pending). The hardware validation runs on the real unit when it reaches the India office. Done when: a kiosk sale and a POS sale print a ticket and a wristband from the designer layout on the emulator with the same output as the designer's print preview, print failures reach KSK-010 and POS-026, and the hardware check is listed as pending the device.
7 | 3 | MIG-WHITELABEL-2 | AM-WHITE-LABEL-KIOSK | [DB] Forward migration V1199__whitelabel.sql: whitelabel for White Label · Kiosk customisation (5 tables) | 3 | Hrushikant Patkar | WhiteLabelService | MIG-BASELINE MIG-WHITELABEL | Tables: whitelabel.kiosk_assignment, whitelabel.kiosk_config, whitelabel.kiosk_config_attract_slide, whitelabel.kiosk_config_start_tile, whitelabel.kiosk_config_version. Source DDL: backend/tenant/V0100__after_r1_20261006.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0101__after_r1_20261006.sql (whitelabel.kiosk_assignment: indexes kiosk_assignment_assigned_by_principal_id_idx, kiosk_assignment_kiosk_config_id_idx, kiosk_assignment_venue_id_idx and kiosk_assignment_workstation_id_idx; whitelabel.kiosk_config: index kiosk_config_venue_id_idx; whitelabel.kiosk_config_attract_slide: index kiosk_config_attract_slide_kiosk_config_id_idx; whitelabel.kiosk_config_start_tile: index kiosk_config_start_tile_kiosk_config_id_idx; whitelabel.kiosk_config_version: indexes kiosk_config_version_kiosk_config_id_idx and kiosk_config_version_published_by_principal_id_idx); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `whitelabel.kiosk_assignment`, `whitelabel.kiosk_config`, `whitelabel.kiosk_config_attract_slide`, `whitelabel.kiosk_config_start_tile`, `whitelabel.kiosk_config_version` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-WHITELABEL-KIOSK-1 | AM-WHITE-LABEL-KIOSK | [BE] WhiteLabelService: assignKiosk, createKioskConfig, deleteKioskConfig, getKioskConfig | 8 | Hrushikant Patkar | WhiteLabelService | MIG-PLATFORM MIG-WHITELABEL-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: assignKiosk, createKioskConfig, deleteKioskConfig, getKioskConfig. Spec: contracts (white-label) at the release tag, served by ADAM. Built for White Label · Kiosk customisation; additive to WhiteLabelService, whose first-release owner (Tanmay Dukhande) reviews. Done when `white-label#assignKiosk`, `white-label#createKioskConfig`, `white-label#deleteKioskConfig`, `white-label#getKioskConfig` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-WHITELABEL-KIOSK-3 | AM-WHITE-LABEL-KIOSK | [BE] WhiteLabelService: listKioskConfigs, publishKioskConfigs, restoreKioskConfigVersion, setKioskOutOfService | 8 | Hrushikant Patkar | WhiteLabelService | MIG-WHITELABEL-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listKioskConfigs, publishKioskConfigs, restoreKioskConfigVersion, setKioskOutOfService. Spec: contracts (white-label) at the release tag, served by ADAM. Built for White Label · Kiosk customisation; additive to WhiteLabelService, whose first-release owner (Tanmay Dukhande) reviews. Done when `white-label#listKioskConfigs`, `white-label#publishKioskConfigs`, `white-label#restoreKioskConfigVersion`, `white-label#setKioskOutOfService` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-WHITELABEL-KIOSK-4 | AM-WHITE-LABEL-KIOSK | [BE] WhiteLabelService: updateKioskConfig | 3 | Hrushikant Patkar | WhiteLabelService | MIG-WHITELABEL-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updateKioskConfig. Spec: contracts (white-label) at the release tag, served by ADAM. Built for White Label · Kiosk customisation; additive to WhiteLabelService, whose first-release owner (Tanmay Dukhande) reviews. Done when `white-label#updateKioskConfig` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-WHITELABEL-KIOSK-2 | AM-WHITE-LABEL-KIOSK | [BE] WhiteLabelService: getKioskConfigValidation, getPublishedKioskConfig, listKioskAssignments, listKioskConfigVersions | 5 | Hrushikant Patkar | WhiteLabelService | MIG-CATALOGUE MIG-WHITELABEL MIG-WHITELABEL-2 PLATFORM-KERNEL SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-WHITELABEL-BOOKINGFLOWS-1 SVC-WHITELABEL-BOOKINGFLOWS-2 SVC-WHITELABEL-KIOSK-1 SVC-WHITELABEL-KIOSK-3 SVC-WHITELABEL-KIOSK-4 SVC-WHITELABEL-PUBLISHING-2 VM-CATALOGUE-PRODUCT-1 | Operations: getKioskConfigValidation, getPublishedKioskConfig, listKioskAssignments, listKioskConfigVersions. Spec: contracts (white-label) at the release tag, served by ADAM. Built for White Label · Kiosk customisation; additive to WhiteLabelService, whose first-release owner (Tanmay Dukhande) reviews. Done when `white-label#getKioskConfigValidation`, `white-label#getPublishedKioskConfig`, `white-label#listKioskAssignments`, `white-label#listKioskConfigVersions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | MIG-PROMOTIONS-8 | AM-PRICING-PROMOTIONS-P08-3 | [DB] Forward migration V1200__promotions.sql: promotions for Pricing & Promotions · Venue Management 3 of 8 (2 tables) | 2 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-PROMOTIONS VM-MIG-PROMOTIONS | Tables: promotions.bundle_capacity_policy, promotions.promotion_conflict. Source DDL: backend/tenant/010-promotions.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `promotions.bundle_capacity_policy`, `promotions.promotion_conflict` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
14 | 3 | SVC-CATALOGUE-BUNDLE-7 | AM-PRICING-PROMOTIONS-P08-3 | [BE] CatalogueService: listBundleCapacityPolicies, setBundleCapacityPolicy | 3 | Hrushikant Patkar | CatalogueService | MIG-PROMOTIONS MIG-PROMOTIONS-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listBundleCapacityPolicies, setBundleCapacityPolicy. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 3 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listBundleCapacityPolicies`, `promotions#setBundleCapacityPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-CATALOGUE-DRAFTED-91 | AM-PRICING-PROMOTIONS-P08-3 | [BE] CatalogueService: listCrmCustomerSegment, listDynamicComponentSubstitution, listMembershipLoyaltyGuest, listPartnerPaymentEligibility | 3 | Pallavi Sawant | CatalogueService | MIG-MARKETING MIG-ORDERS-3 MIG-PROMOTIONS PLATFORM-KERNEL SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTIONS-1 SVC-MARKETING-LOYALTY-1 SVC-MARKETING-LOYALTY-2 SVC-MARKETING-LOYALTY-3 SVC-MARKETING-MARKETING-11 SVC-MARKETING-MARKETING-5 SVC-MARKETING-SEGMENT-1 | Operations: listCrmCustomerSegment, listDynamicComponentSubstitution, listMembershipLoyaltyGuest, listPartnerPaymentEligibility. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 3 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listCrmCustomerSegment`, `promotions#listDynamicComponentSubstitution`, `promotions#listMembershipLoyaltyGuest`, `promotions#listPartnerPaymentEligibility` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | VM-ADM-192 | AM-PRICING-PROMOTIONS-P08-3 | [BE] ADM-192 Dynamic Component Substitution Engine | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-91 | Automatically replace unavailable bundle components according to predefined commercial rules. Module: Commercial. App: Venue Management. Done when `ADM-192` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-200 | AM-PRICING-PROMOTIONS-P08-3 | [BE] ADM-200 CRM & Customer Segment Manager | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-91 | Connect promotion eligibility directly to TICVAI CRM segmentation. The board should consume CRM segments rather than recreate CRM functionality. Module: Commercial. App: Venue Management. Done when `ADM-200` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-201 | AM-PRICING-PROMOTIONS-P08-3 | [BE] ADM-201 Membership, Loyalty & Guest Eligibility | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-91 | Configure targeting based on membership, loyalty status, guest categories, and entitlement relationships. Module: Commercial. App: Venue Management. Waits for its definition: ADM-201's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-201` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-204 | AM-PRICING-PROMOTIONS-P08-3 | [BE] ADM-204 Partner, B2B & Payment Eligibility | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-91 | Configure eligibility for partner, corporate, reseller, B2B, and payment-related campaigns. Module: Commercial. App: Venue Management. Waits for its definition: ADM-204's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-204` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-193 | AM-PRICING-PROMOTIONS-P08-3 | [BE] ADM-193 Dynamic Bundle Rule & Composition Engine | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-42 | Allow the actual composition of a bundle to change dynamically according to business and guest conditions. This builds upon the matrix requirement for dynamic bundles where guests select attractions, experiences, F&B, Retail, or services from predefined categories. Module: Commercial. App: Venue Management. Waits for its definition: ADM-193's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-193` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-194 | AM-PRICING-PROMOTIONS-P08-3 | [BE] ADM-194 Real-Time Availability & Checkout Validation | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-32 | Perform the final authoritative validation immediately before transaction confirmation. This is essential because availability may change between browsing and payment. Module: Commercial. App: Venue Management. Done when `ADM-194` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-197 | AM-PRICING-PROMOTIONS-P08-3 | [BE] ADM-197 Dynamic Bundle Simulation & AI Optimization | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-41 SVC-CATALOGUE-DRAFTED-42 | Test how a bundle behaves under different operational scenarios before activating dynamic rules. Module: Commercial. App: Venue Management. Done when `ADM-197` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
14 | 3 | SVC-CATALOGUE-DRAFTED-96 | AM-PRICING-PROMOTIONS-P08-4 | [BE] CatalogueService: listPromotionExclusionCompatibility, listRedemptionDiscountExposure, listThresholdActionAutomatic, setCampaignBudgetFinancial | 5 | Pallavi Sawant | CatalogueService | MIG-PROMOTIONS MIG-PROMOTIONS-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listPromotionExclusionCompatibility, listRedemptionDiscountExposure, listThresholdActionAutomatic, setCampaignBudgetFinancial. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 4 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listPromotionExclusionCompatibility`, `promotions#listRedemptionDiscountExposure`, `promotions#listThresholdActionAutomatic`, `promotions#setCampaignBudgetFinancial` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-CATALOGUE-DRAFTED-92 | AM-PRICING-PROMOTIONS-P08-3 | [BE] CatalogueService: listPromotionPriorityHierarchy, listStackingConflict, listTargetingConflictFrequency, listTargetingEligibility | 3 | Hrushikant Patkar | CatalogueService | MIG-MARKETING MIG-ORDERS-3 MIG-PROMOTIONS MIG-PROMOTIONS-2 MIG-PROMOTIONS-8 PLATFORM-KERNEL SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-COUPON-1 SVC-CATALOGUE-COUPON-2 SVC-CATALOGUE-DRAFTED-1 SVC-CATALOGUE-DRAFTED-4 SVC-CATALOGUE-DRAFTED-96 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTION-4 SVC-CATALOGUE-PROMOTIONS-1 SVC-MARKETING-CONSENT-3 SVC-MARKETING-GUEST-2 SVC-MARKETING-GUESTS-2 SVC-MARKETING-MARKETING-6 SVC-MARKETING-MARKETING-7 SVC-MARKETING-SEGMENT-1 | Operations: listPromotionPriorityHierarchy, listStackingConflict, listTargetingConflictFrequency, listTargetingEligibility. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 3 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listPromotionPriorityHierarchy`, `promotions#listStackingConflict`, `promotions#listTargetingConflictFrequency`, `promotions#listTargetingEligibility` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | VM-ADM-198 | AM-PRICING-PROMOTIONS-P08-3 | [BE] ADM-198 Targeting & Eligibility Command Center | 5 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-92 | Provide centralized visibility into all promotion audiences, eligibility rules, segments, targeting strategies, and their performance. Module: Commercial. App: Venue Management. Done when `ADM-198` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-206 | AM-PRICING-PROMOTIONS-P08-3 | [BE] ADM-206 Targeting Conflict, Frequency & Exclusion Controls | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-92 | Prevent customers from being over-targeted and prevent inappropriate promotional eligibility. Module: Commercial. App: Venue Management. Done when `ADM-206` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-208 | AM-PRICING-PROMOTIONS-P08-3 | [BE] ADM-208 Stacking & Conflict Command Center | 3 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-92 | Provide centralized operational visibility into promotion interactions across TICVAI. Module: Commercial. App: Venue Management. Done when `ADM-208` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-209 | AM-PRICING-PROMOTIONS-P08-3 | [BE] ADM-209 Promotion Priority & Hierarchy Manager | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-92 | Define the relative priority of different promotion families and individual offers. Module: Commercial. App: Venue Management. Waits for its definition: ADM-209's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-209` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | SVC-CATALOGUE-DRAFTED-93 | AM-PRICING-PROMOTIONS-P08-4 | [BE] CatalogueService: approveCampaignWorkflow, approveDecision, listBestOfferCustomer, listBudgetConsumptionForecast | 5 | Pallavi Sawant | CatalogueService | MIG-CATALOGUE MIG-ORDERS-3 MIG-PROMOTIONS MIG-PROMOTIONS-2 PLATFORM-KERNEL SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-96 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTION-4 SVC-CATALOGUE-PROMOTIONS-1 | Operations: approveCampaignWorkflow, approveDecision, listBestOfferCustomer, listBudgetConsumptionForecast. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 4 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#approveCampaignWorkflow`, `promotions#approveDecision`, `promotions#listBestOfferCustomer`, `promotions#listBudgetConsumptionForecast` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | VM-ADM-211 | AM-PRICING-PROMOTIONS-P08-4 | [BE] ADM-211 Promotion Exclusion & Compatibility Matrix | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-96 | Provide administrators with a visual matrix showing which promotion categories can interact. Module: Commercial. App: Venue Management. Done when `ADM-211` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-219 | AM-PRICING-PROMOTIONS-P08-4 | [BE] ADM-219 Campaign Budget & Financial Limit Setup | 3 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-96 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTION-4 | Define the financial envelope within which a campaign is permitted to operate. Module: Commercial. App: Venue Management. Done when `ADM-219` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-220 | AM-PRICING-PROMOTIONS-P08-4 | [BE] ADM-220 Redemption, Discount & Exposure Limit Manager | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-96 | Define non-budget commercial limits controlling campaign exposure. Module: Commercial. App: Venue Management. Done when `ADM-220` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-222 | AM-PRICING-PROMOTIONS-P08-4 | [BE] ADM-222 Threshold Actions & Automatic Suspension | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-96 | Define what TICVAI should do as financial or redemption thresholds are approached or exceeded. This is explicitly required by the matrix. Module: Commercial. App: Venue Management. Waits for its definition: ADM-222's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-222` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-227 | AM-PRICING-PROMOTIONS-P08-4 | [BE] ADM-227 Governance Audit, AI Risk & Launch Readiness | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-34 | Provide the final governance checkpoint before a campaign is allowed to go live. Module: Commercial. App: Venue Management. Done when `ADM-227` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-213 | AM-PRICING-PROMOTIONS-P08-4 | [BE] ADM-213 Best Offer & Customer Benefit Resolver | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-93 | Determine which promotion or combination gives the guest the correct/best permitted commercial outcome. Module: Commercial. App: Venue Management. Waits for its definition: ADM-213's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-213` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-221 | AM-PRICING-PROMOTIONS-P08-4 | [BE] ADM-221 Budget Consumption & Forecast Monitor | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-93 | Provide real-time tracking of campaign financial consumption and predict when limits will be reached. Module: Commercial. App: Venue Management. Done when `ADM-221` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-223 | AM-PRICING-PROMOTIONS-P08-4 | [BE] ADM-223 Campaign Approval Workflow Designer | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-93 VM-TENANCY-MATRIX-1 | Configure multi-level approval workflows for promotions and campaigns. The matrix explicitly requires configurable multi-level approval for promotion creation, modification, activation, and deactivation. Module: Commercial. App: Venue Management. Waits for its definition: ADM-223's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-223` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-224 | AM-PRICING-PROMOTIONS-P08-4 | [BE] ADM-224 Approval Inbox & Decision Workspace | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-93 SVC-TENANCY-REQUEST-1 | Provide approvers with enough commercial information to make an informed decision without navigating through every configuration screen. Module: Commercial. App: Venue Management. Done when `ADM-224` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-228 | AM-PRICING-PROMOTIONS-P08-4 | [BE] ADM-228 Promotion Performance Command Center | 5 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-35 SVC-CATALOGUE-DRAFTED-38 | Provide executives, Marketing, Commercial, Revenue, and Finance with the overall performance of promotions and bundles. Module: Commercial. App: Venue Management. Done when `ADM-228` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-229 | AM-PRICING-PROMOTIONS-P08-4 | [BE] ADM-229 Campaign & Promotion Performance Explorer | 3 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-35 SVC-CATALOGUE-DRAFTED-37 SVC-CATALOGUE-DRAFTED-38 SVC-CATALOGUE-PROMOTION-3 | Allow users to compare every promotion and campaign using consistent commercial KPIs. Module: Commercial. App: Venue Management. Waits for its definition: ADM-229's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-229` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
13 | 3 | MIG-PROMOTIONS-9 | AM-PRICING-PROMOTIONS-P08-5 | [DB] Forward migration V1201__promotions.sql: promotions for Pricing & Promotions · Venue Management 5 of 8 (4 tables) | 3 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-PROMOTIONS VM-MIG-PROMOTIONS | Tables: promotions.product_relationship, promotions.recommendation_experiment, promotions.recommendation_strategy, promotions.recommendation_suppression. Source DDL: backend/tenant/010-promotions.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `promotions.product_relationship`, `promotions.recommendation_experiment`, `promotions.recommendation_strategy`, `promotions.recommendation_suppression` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
14 | 3 | SVC-CATALOGUE-RECOMMENDATIONS-1 | AM-PRICING-PROMOTIONS-P08-5 | [BE] CatalogueService: createRecommendationStrategy, getRecommendationPerformance, listProductRelationships, listRecommendationStrategies | 5 | Hrushikant Patkar | CatalogueService | MIG-ORDERS MIG-PLATFORM MIG-PROMOTIONS-3 MIG-PROMOTIONS-9 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: createRecommendationStrategy, getRecommendationPerformance, listProductRelationships, listRecommendationStrategies. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 5 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#createRecommendationStrategy`, `promotions#getRecommendationPerformance`, `promotions#listProductRelationships`, `promotions#listRecommendationStrategies` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-CATALOGUE-RECOMMENDATIONS-2 | AM-PRICING-PROMOTIONS-P08-5 | [BE] CatalogueService: setProductRelationships, setRecommendationSuppression, updateRecommendationStrategy | 5 | Hrushikant Patkar | CatalogueService | MIG-PLATFORM MIG-PROMOTIONS-9 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: setProductRelationships, setRecommendationSuppression, updateRecommendationStrategy. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 5 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#setProductRelationships`, `promotions#setRecommendationSuppression`, `promotions#updateRecommendationStrategy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | VM-ADM-639 | AM-PRICING-PROMOTIONS-P08-5 | [BE] ADM-639 Recommendation Command Center | 3 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 | Provide the central operational dashboard for the complete TICVAI Recommendation Engine. This becomes the entry point for Marketing, Commercial, Revenue, CRM and authorized operational users. Module: Commercial. App: Venue Management. Done when `ADM-639` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-640 | AM-PRICING-PROMOTIONS-P08-5 | [BE] ADM-640 Recommendation Strategy Manager | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 SVC-CATALOGUE-RECOMMENDATIONS-2 | Define the commercial strategy TICVAI should use when generating recommendations. Instead of hard-coding recommendation behavior into B2C or POS, administrators configure reusable strategies centrally. Increase cross-attraction sales. Module: Commercial. App: Venue Management. Waits for its definition: ADM-640's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-640` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-641 | AM-PRICING-PROMOTIONS-P08-5 | [BE] ADM-641 Recommendation Objective & KPI Configuration | 3 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 SVC-CATALOGUE-RECOMMENDATIONS-2 | Define exactly what the recommendation engine should optimize. This is important because the "best" recommendation depends on the business objective. Allow weighted objectives. Module: Commercial. App: Venue Management. Done when `ADM-641` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-642 | AM-PRICING-PROMOTIONS-P08-5 | [BE] ADM-642 Recommendation Type & Product Relationship Manager | 3 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 SVC-CATALOGUE-RECOMMENDATIONS-2 | Define the commercial relationships from which recommendations can be generated. Module: Commercial. App: Venue Management. Waits for its definition: ADM-642's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-642` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-643 | AM-PRICING-PROMOTIONS-P08-5 | [BE] ADM-643 Recommendation Placement & Touchpoint Manager | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 SVC-CATALOGUE-RECOMMENDATIONS-2 | Define where in the customer journey recommendations are permitted to appear. This is a major requirement for the engine. Module: Commercial. App: Venue Management. Waits for its definition: ADM-643's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-643` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-644 | AM-PRICING-PROMOTIONS-P08-5 | [BE] ADM-644 Channel & Journey Strategy Manager | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 SVC-CATALOGUE-RECOMMENDATIONS-2 | Control recommendation behavior across TICVAI's omnichannel environment. Module: Commercial. App: Venue Management. Waits for its definition: ADM-644's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-644` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-645 | AM-PRICING-PROMOTIONS-P08-5 | [BE] ADM-645 Recommendation Priority, Ranking & Suppression Manager17 | 3 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 SVC-CATALOGUE-RECOMMENDATIONS-2 | Define how multiple eligible recommendations are ranked before being presented. This is different from Promotion Board 8. Module: Commercial. App: Venue Management. Waits for its definition: ADM-645's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-645` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-646 | AM-PRICING-PROMOTIONS-P08-5 | [BE] ADM-646 Recommendation Guardrails & Business Controls | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 SVC-CATALOGUE-RECOMMENDATIONS-2 | Protect the business and customer experience from inappropriate AI or rule- generated recommendations. Module: Commercial. App: Venue Management. Waits for its definition: ADM-646's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-646` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-647 | AM-PRICING-PROMOTIONS-P08-5 | [BE] ADM-647 Recommendation Policy, AI Control & Governance | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 SVC-CATALOGUE-RECOMMENDATIONS-2 | Define how much authority the TICVAI AI layer has over recommendation decisions. Module: Commercial. App: Venue Management. Waits for its definition: ADM-647's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-647` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
14 | 3 | SVC-CATALOGUE-RECOMMENDATIONS-3 | AM-PRICING-PROMOTIONS-P08-6 | [BE] CatalogueService: getProductAffinity, simulateRecommendationStrategy | 3 | Hrushikant Patkar | CatalogueService | MIG-ORDERS MIG-PROMOTIONS-9 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getProductAffinity, simulateRecommendationStrategy. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 6 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#getProductAffinity`, `promotions#simulateRecommendationStrategy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | VM-ADM-648 | AM-PRICING-PROMOTIONS-P08-6 | [BE] ADM-648 Recommendation Strategy Simulator & AI Advisor | 3 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 SVC-CATALOGUE-RECOMMENDATIONS-3 | Allow administrators to test recommendation strategies before activating them. This should become the final validation screen for Board 1. ↓ Board 2 shall provide TICVAI with the specialized Upsell & Upgrade Recommendation Engine responsible for identifying when a customer can be moved from their current product, ticket, experience, membership, bundle, or service to a higher-value or more valuable alternative. Board 1 established the overall recommendation strategy, placements, ranking, guardrails, and AI governance. Module: Commercial. App: Venue Management. Done when `ADM-648` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-649 | AM-PRICING-PROMOTIONS-P08-6 | [BE] ADM-649 Upsell & Upgrade Command Center | 3 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 | Provide centralized operational and commercial visibility into all upsell and upgrade activities. Module: Commercial. App: Venue Management. Done when `ADM-649` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-650 | AM-PRICING-PROMOTIONS-P08-6 | [BE] ADM-650 Upgrade Path & Product Ladder Builder | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 SVC-CATALOGUE-RECOMMENDATIONS-2 | Define valid upgrade relationships between products. governed product relationships. Module: Commercial. App: Venue Management. Waits for its definition: ADM-650's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-650` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-651 | AM-PRICING-PROMOTIONS-P08-6 | [BE] ADM-651 Upsell Eligibility & Qualification Rules | 3 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 SVC-CATALOGUE-RECOMMENDATIONS-2 | Determine whether an upsell opportunity is valid for the current customer and transaction. This screen provides upgrade-specific qualification, while the reusable customer targeting capabilities remain centralized in the recommendation/CRM eligibility architecture. Module: Commercial. App: Venue Management. Waits for its definition: ADM-651's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-651` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-655 | AM-PRICING-PROMOTIONS-P08-6 | [BE] ADM-655 Pre-Purchase, Cart & Checkout Upsell Manager | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 SVC-CATALOGUE-RECOMMENDATIONS-2 | Control upselling during the active purchase journey. Module: Commercial. App: Venue Management. Done when `ADM-655` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-657 | AM-PRICING-PROMOTIONS-P08-6 | [BE] ADM-657 Upsell Ranking, Propensity & AI Opportunity Engine | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 | Use AI and commercial logic to identify the strongest upgrade opportunity for each customer/context. Module: Commercial. App: Venue Management. Waits for its definition: ADM-657's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-657` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-658 | AM-PRICING-PROMOTIONS-P08-6 | [BE] ADM-658 Upgrade Simulator, Comparison & AI Advisor | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 SVC-CATALOGUE-RECOMMENDATIONS-3 | Allow business users to simulate an upsell strategy before activation. Module: Commercial. App: Venue Management. Waits for its definition: ADM-658's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-658` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-660 | AM-PRICING-PROMOTIONS-P08-6 | [BE] ADM-660 Cross-Sell Relationship Builder | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 SVC-CATALOGUE-RECOMMENDATIONS-2 | Allow administrators to manually define governed complementary-product relationships. Module: Commercial. App: Venue Management. Done when `ADM-660` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-661 | AM-PRICING-PROMOTIONS-P08-6 | [BE] ADM-661 Product Affinity Matrix & Relationship Map | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-3 | Provide a visual representation of how strongly products and categories relate to one another. Module: Commercial. App: Venue Management. Waits for its definition: ADM-661's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-661` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-662 | AM-PRICING-PROMOTIONS-P08-6 | [BE] ADM-662 Frequently Bought Together & Basket Pattern Engine | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-3 | Analyze transaction baskets to discover products commonly purchased together. Module: Commercial. App: Venue Management. Done when `ADM-662` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-663 | AM-PRICING-PROMOTIONS-P08-6 | [BE] ADM-663 Cross-Category Recommendation Manager | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 SVC-CATALOGUE-RECOMMENDATIONS-2 | Manage recommendations across TICVAI's different commercial modules. This is especially important because TICVAI is not only a ticketing platform. Module: Commercial. App: Venue Management. Waits for its definition: ADM-663's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-663` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-664 | AM-PRICING-PROMOTIONS-P08-6 | [BE] ADM-664 Multi-Attraction, Destination & Partner Cross-Sell | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 SVC-CATALOGUE-RECOMMENDATIONS-2 | Support cross-selling beyond the original venue or attraction. This addresses the matrix requirements around multi-destination and external product combinations. Module: Commercial. App: Venue Management. Waits for its definition: ADM-664's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-664` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-665 | AM-PRICING-PROMOTIONS-P08-6 | [BE] ADM-665 Basket-Aware Cross-Sell & Duplicate Prevention | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 SVC-CATALOGUE-RECOMMENDATIONS-2 | Make cross-selling aware of the customer's complete current basket. This is critical because basic recommendation engines often recommend something the customer already owns. Module: Commercial. App: Venue Management. Waits for its definition: ADM-665's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-665` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-666 | AM-PRICING-PROMOTIONS-P08-6 | [BE] ADM-666 Availability, Inventory & Capacity-Aware Cross-Sell | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 SVC-CATALOGUE-RECOMMENDATIONS-2 | Ensure recommendations reflect actual operational availability. Module: Commercial. App: Venue Management. Done when `ADM-666` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-667 | AM-PRICING-PROMOTIONS-P08-6 | [BE] ADM-667 AI Cross-Sell Discovery, Scoring & Ranking Engine | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-3 | Use AI to discover and rank the strongest complementary products for the current customer/context. Module: Commercial. App: Venue Management. Waits for its definition: ADM-667's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-667` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-668 | AM-PRICING-PROMOTIONS-P08-6 | [BE] ADM-668 Cross-Sell Simulator & AI Opportunity Advisor | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 SVC-CATALOGUE-RECOMMENDATIONS-3 | Allow administrators to test cross-sell strategies and AI recommendations before activation. ↓ Module: Commercial. App: Venue Management. Done when `ADM-668` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-669 | AM-PRICING-PROMOTIONS-P08-7 | [BE] ADM-669 Journey & Context Command Center | 3 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 | Provide centralized visibility into recommendation activity across the complete customer journey. Module: Commercial. App: Venue Management. Done when `ADM-669` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-670 | AM-PRICING-PROMOTIONS-P08-7 | [BE] ADM-670 Customer Journey Map & Touchpoint Designer | 3 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 SVC-CATALOGUE-RECOMMENDATIONS-2 | Allow TICVAI administrators to visually configure the customer journey and recommendation-enabled touchpoints. Module: Commercial. App: Venue Management. Done when `ADM-670` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-671 | AM-PRICING-PROMOTIONS-P08-7 | [BE] ADM-671 Real-Time Context Rule Engine | 3 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 SVC-CATALOGUE-RECOMMENDATIONS-2 | Determine recommendation behavior using the customer's current transactional and operational context. Module: Commercial. App: Venue Management. Waits for its definition: ADM-671's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-671` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-672 | AM-PRICING-PROMOTIONS-P08-7 | [BE] ADM-672 Pre-Purchase & Booking Journey Recommendation Manager | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 SVC-CATALOGUE-RECOMMENDATIONS-2 | Manage recommendation behavior before transaction completion. Module: Commercial. App: Venue Management. Done when `ADM-672` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-673 | AM-PRICING-PROMOTIONS-P08-7 | [BE] ADM-673 Post-Purchase & Pre-Visit Recommendation Manager | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 SVC-CATALOGUE-RECOMMENDATIONS-2 | Continue the commercial journey after payment while respecting the guest's existing purchase and visit plan. Module: Commercial. App: Venue Management. Done when `ADM-673` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-674 | AM-PRICING-PROMOTIONS-P08-7 | [BE] ADM-674 In-Venue & Location-Aware Recommendation Engine | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 SVC-CATALOGUE-RECOMMENDATIONS-2 | Support context-aware recommendations while the guest is physically visiting the venue. This directly addresses the matrix's requirement for location-aware in-venue upsell/cross-sell. Module: Commercial. App: Venue Management. Waits for its definition: ADM-674's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-674` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-675 | AM-PRICING-PROMOTIONS-P08-7 | [BE] ADM-675 Visit State, Itinerary & Time-Aware Recommendation | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 SVC-CATALOGUE-RECOMMENDATIONS-2 | Make recommendations aware of what the customer has already done and what remains possible during the visit. Module: Commercial. App: Venue Management. Done when `ADM-675` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-676 | AM-PRICING-PROMOTIONS-P08-7 | [BE] ADM-676 Omnichannel Recommendation Synchronization | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 | Coordinate recommendations across channels so customers receive a consistent experience. Module: Commercial. App: Venue Management. Done when `ADM-676` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-677 | AM-PRICING-PROMOTIONS-P08-7 | [BE] ADM-677 Contextual Trigger, Frequency & Experience Controls | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-2 | Control exactly when a recommendation is triggered and prevent excessive customer interaction. Module: Commercial. App: Venue Management. Done when `ADM-677` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-679 | AM-PRICING-PROMOTIONS-P08-7 | [BE] ADM-679 Personalization & NBO Command Center | 3 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 | Provide centralized visibility into the operation and commercial impact of personalized recommendations. Module: Commercial. App: Venue Management. Done when `ADM-679` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-681 | AM-PRICING-PROMOTIONS-P08-7 | [BE] ADM-681 Customer Feature & Signal Configuration | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 SVC-CATALOGUE-RECOMMENDATIONS-2 | Control which approved data signals the AI may use when calculating personalized recommendations. This is critical for governance and explainability. Module: Commercial. App: Venue Management. Waits for its definition: ADM-681's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-681` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-682 | AM-PRICING-PROMOTIONS-P08-7 | [BE] ADM-682 Propensity Model & Customer Intent Manager | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 | Calculate the likelihood that a guest will take specific commercial actions. Module: Commercial. App: Venue Management. Done when `ADM-682` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-684 | AM-PRICING-PROMOTIONS-P08-7 | [BE] ADM-684 Personalized Ranking & Decision Policy Builder | 3 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 SVC-CATALOGUE-RECOMMENDATIONS-2 | Configure how TICVAI converts AI scores and commercial factors into the final recommendation ranking. Module: Commercial. App: Venue Management. Waits for its definition: ADM-684's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-684` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-685 | AM-PRICING-PROMOTIONS-P08-7 | [BE] ADM-685 Customer Preference, Fatigue & Suppression Intelligence | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-2 | Prevent personalization from becoming repetitive or intrusive. Board 4 provides general journey frequency controls. Board 5 adds customer-specific behavioral suppression. Module: Commercial. App: Venue Management. Done when `ADM-685` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-688 | AM-PRICING-PROMOTIONS-P08-7 | [BE] ADM-688 Personalization Simulator & Next-Best-Offer Lab | 3 | Surendra |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 SVC-CATALOGUE-RECOMMENDATIONS-3 | Allow administrators to simulate how TICVAI would personalize recommendations for different customers before deploying changes. Module: Commercial. App: Venue Management. Done when `ADM-688` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-689 | AM-PRICING-PROMOTIONS-P08-7 | [BE] ADM-689 Recommendation Performance Command Center | 5 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 | Provide executive and operational visibility across the complete Recommendation Engine. Module: Commercial. App: Venue Management. Done when `ADM-689` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
8 | 3 | MIG-RENTAL-2 | AM-PRICING-PROMOTIONS-P08-8 | [DB] Forward migration V1021__rental.sql: rental for Pricing & Promotions · Venue Management 8 of 8 (7 tables) | 5 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE MIG-PLATFORM VM-MIG-RENTAL | Tables: rental.availability_rules, rental.blackout, rental.duration_rules, rental.equipment_assignment, rental.inventory_model, rental.location_rule, rental.product. Source DDL: backend/tenant/010-rental.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `rental.availability_rules`, `rental.blackout`, `rental.duration_rules`, `rental.equipment_assignment`, `rental.inventory_model`, `rental.location_rule`, `rental.product` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
15 | 3 | MIG-MARKETING-8 | AM-PRICING-PROMOTIONS-P08-8 | [DB] Forward migration V1169__marketing.sql: marketing for Pricing & Promotions · Venue Management 8 of 8 (1 tables) | 1 | Hrushikant Patkar | MarketingService | MIG-BASELINE MIG-MARKETING VM-MIG-MARKETING | Tables: marketing.audience_list. Source DDL: backend/tenant/010-marketing.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `marketing.audience_list` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
14 | 3 | SVC-CATALOGUE-RECOMMENDATIONS-4 | AM-PRICING-PROMOTIONS-P08-8 | [BE] CatalogueService: concludeRecommendationExperiment, createRecommendationExperiment, listRecommendationExperiments | 5 | Hrushikant Patkar | CatalogueService | MIG-PLATFORM MIG-PROMOTIONS-9 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: concludeRecommendationExperiment, createRecommendationExperiment, listRecommendationExperiments. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 8 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#concludeRecommendationExperiment`, `promotions#createRecommendationExperiment`, `promotions#listRecommendationExperiments` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-VENUEOPS-RENTAL-2 | AM-PRICING-PROMOTIONS-P08-8 | [BE] VenueOpsService: getRentalAvailability | 1 | Hrushikant Patkar | VenueOpsService | MIG-MAINTENANCE MIG-RENTAL-2 PLATFORM-KERNEL VM-MIG-RENTAL VM-VENUEOPS-ASSET-1 VM-VENUEOPS-ASSET-2 | Operations: getRentalAvailability. Spec: contracts (rental) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 8 of 8; additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `rental#getRentalAvailability` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | VM-ADM-690 | AM-PRICING-PROMOTIONS-P08-8 | [BE] ADM-690 Recommendation Strategy & Placement Analytics | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 | Determine which recommendation strategies, placements, channels and journey stages perform best. Module: Commercial. App: Venue Management. Done when `ADM-690` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-691 | AM-PRICING-PROMOTIONS-P08-8 | [BE] ADM-691 Recommendation Experiment & A/B Test Studio | 3 | Surendra |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-4 | Allow TICVAI to scientifically test recommendation strategies rather than relying only on assumptions. Increase Family Meal cross-sell. Module: Commercial. App: Venue Management. Done when `ADM-691` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-692 | AM-PRICING-PROMOTIONS-P08-8 | [BE] ADM-692 Experiment Results & Winner Decision Workspace | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-4 | Evaluate experiments and decide whether a recommendation strategy should be deployed. Module: Commercial. App: Venue Management. Waits for its definition: ADM-692's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-692` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-693 | AM-PRICING-PROMOTIONS-P08-8 | [BE] ADM-693 Recommendation Attribution & Incrementality Analytics | 2 | Surendra |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 | Determine whether a recommendation genuinely created additional commercial value. This is essential. A customer purchasing a recommended product does not automatically mean the recommendation caused the purchase. Module: Commercial. App: Venue Management. Done when `ADM-693` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-694 | AM-PRICING-PROMOTIONS-P08-8 | [BE] ADM-694 AI Model Performance & Drift Monitor | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 | Monitor whether recommendation and propensity models continue performing correctly after deployment. This screen is critical if TICVAI wants a serious AI architecture. Module: Commercial. App: Venue Management. Done when `ADM-694` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-695 | AM-PRICING-PROMOTIONS-P08-8 | [BE] ADM-695 Recommendation Governance & Deployment Control | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 SVC-CATALOGUE-RECOMMENDATIONS-2 | Control how new strategies, rules, models and AI changes move into production. Module: Commercial. App: Venue Management. Done when `ADM-695` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-698 | AM-PRICING-PROMOTIONS-P08-8 | [BE] ADM-698 AI Optimization & Recommendation Intelligence Lab | 3 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 SVC-CATALOGUE-RECOMMENDATIONS-3 | Turn all Recommendation Engine data into actionable improvement opportunities. This is the final optimization screen for Module 2. Module: Commercial. App: Venue Management. Done when `ADM-698` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | SVC-AI-GENERATE-4 | AM-PRICING-PROMOTIONS-P08-8 | [BE] AiService: proposeLookalikeSegment | 2 | Hrushikant Patkar | AiService | MIG-AI MIG-MARKETING MIG-MARKETING-8 MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: proposeLookalikeSegment. Spec: contracts (ai) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 8 of 8; additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#proposeLookalikeSegment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-VENUEOPS-VENUEMAP-4 | AM-SEATING-MAPS-P06 | [BE] VenueOpsService: getVenueMapLive | 1 | Pallavi Sawant | VenueOpsService | MIG-ACCESS MIG-QUEUE MIG-VENUEMAP PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-12 SVC-VENUEOPS-ENTRY-1 SVC-VENUEOPS-ENTRY-2 SVC-VENUEOPS-VENUEMAP-1 SVC-VENUEOPS-VENUEMAP-2 SVC-VENUEOPS-VENUEMAP-3 SVC-VENUEOPS-VENUEMAP-5 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 VM-VENUEOPS-ENTRY-1 VM-VENUEOPS-VENUEMAP-1 | Operations: getVenueMapLive. Spec: contracts (venue-map) at the release tag, served by ADAM. Built for Seating & Maps · Staff App; additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `venue-map#getVenueMapLive` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
9 | 3 | MIG-SEATING-6 | AM-SEATING-MAPS-P08 | [DB] Forward migration V1068__seating.sql: seating for Seating & Maps · Venue Management 1 of 5 (2 tables) | 2 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-SEATING | Tables: seating.hold_type, seating.seat_rules. Source DDL: backend/tenant/010-seating.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `seating.hold_type`, `seating.seat_rules` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-CATALOGUE-SEATING-6 | AM-SEATING-MAPS-P08 | [BE] CatalogueService: createSeatHoldPool, getSeatRules, listSeatHoldTypes, releaseSeatHoldPool | 5 | Hrushikant Patkar | CatalogueService | MIG-SEATING-2 MIG-SEATING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createSeatHoldPool, getSeatRules, listSeatHoldTypes, releaseSeatHoldPool. Spec: contracts (seating) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management 1 of 5; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `seating#createSeatHoldPool`, `seating#getSeatRules`, `seating#listSeatHoldTypes`, `seating#releaseSeatHoldPool` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-CATALOGUE-SEATING-7 | AM-SEATING-MAPS-P08 | [BE] CatalogueService: setSeatHoldType, setSeatRules, validateSeatCompliance | 5 | Hrushikant Patkar | CatalogueService | MIG-SEATING MIG-SEATING-3 MIG-SEATING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setSeatHoldType, setSeatRules, validateSeatCompliance. Spec: contracts (seating) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management 1 of 5; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `seating#setSeatHoldType`, `seating#setSeatRules`, `seating#validateSeatCompliance` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | MIG-SEATING-7 | AM-SEATING-MAPS-P08-2 | [DB] Forward migration V1202__seating.sql: seating for Seating & Maps · Venue Management 2 of 5 (3 tables) | 2 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-ORDERS MIG-SEATING | Tables: seating.group_request, seating.group_request_participant, seating.reassignment. Source DDL: backend/tenant/010-seating.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `seating.group_request`, `seating.group_request_participant`, `seating.reassignment` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
13 | 3 | SVC-LEDGER-FINANCE-2 | AM-SEATING-MAPS-P08-2 | [BE] LedgerService: recordDeposit | 2 | Pallavi Sawant | LedgerService | MIG-LEDGER MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-LEDGER | Operations: recordDeposit. Spec: contracts (finance) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management 2 of 5; additive to LedgerService, whose first-release owner (Tanmay Dukhande) reviews. Done when `finance#recordDeposit` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-CATALOGUE-SEATING-8 | AM-SEATING-MAPS-P08-2 | [BE] CatalogueService: allocateGroupSeats, createGroupSeatRequest, listGroupSeatRequests, reassignSeats | 5 | Hrushikant Patkar | CatalogueService | MIG-SEATING MIG-SEATING-3 MIG-SEATING-7 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: allocateGroupSeats, createGroupSeatRequest, listGroupSeatRequests, reassignSeats. Spec: contracts (seating) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management 2 of 5; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `seating#allocateGroupSeats`, `seating#createGroupSeatRequest`, `seating#listGroupSeatRequests`, `seating#reassignSeats` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-CATALOGUE-SEATING-9 | AM-SEATING-MAPS-P08-2 | [BE] CatalogueService: setGroupSeatRoster | 1 | Pallavi Sawant | CatalogueService | MIG-SEATING MIG-SEATING-7 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setGroupSeatRoster. Spec: contracts (seating) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management 2 of 5; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `seating#setGroupSeatRoster` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
9 | 3 | MIG-SEATING-8 | AM-SEATING-MAPS-P08-3 | [DB] Forward migration V1203__seating.sql: seating for Seating & Maps · Venue Management 3 of 5 (3 tables) | 2 | Hrushikant Patkar | CatalogueService | MIG-BASELINE MIG-PLATFORM MIG-SEATING | Tables: seating.import_job, seating.seat_map_template, seating.zone. Source DDL: backend/tenant/010-seating.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `seating.import_job`, `seating.seat_map_template`, `seating.zone` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
12 | 3 | SVC-TENANCY-TENANCY-11 | AM-SEATING-MAPS-P08-3 | [BE] TenancyService: listConfigurationProfiles | 1 | Chinmay Patkar | TenancyService | PLATFORM-KERNEL VM-MIG-PLATFORM VM-TENANCY-TENANCY-2 | Operations: listConfigurationProfiles. Spec: contracts (tenancy) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management 3 of 5; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `tenancy#listConfigurationProfiles` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-CATALOGUE-IMPORT-1 | AM-SEATING-MAPS-P08-3 | [BE] CatalogueService: getImportJob, importSeatGeometry, importSeatManifest | 5 | Hrushikant Patkar | CatalogueService | MIG-SEATING-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getImportJob, importSeatGeometry, importSeatManifest. Spec: contracts (seating) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management 3 of 5; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `seating#getImportJob`, `seating#importSeatGeometry`, `seating#importSeatManifest` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-CATALOGUE-SEATING-10 | AM-SEATING-MAPS-P08-3 | [BE] CatalogueService: getSeatInventory, getSeatMapImport, importSeatMap, setMapZones | 5 | Hrushikant Patkar | CatalogueService | MIG-ASSETS MIG-SEATING MIG-SEATING-2 MIG-SEATING-3 MIG-SEATING-6 MIG-SEATING-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getSeatInventory, getSeatMapImport, importSeatMap, setMapZones. Spec: contracts (seating) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management 3 of 5; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `seating#getSeatInventory`, `seating#getSeatMapImport`, `seating#importSeatMap`, `seating#setMapZones` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-CATALOGUE-SEATMAP-4 | AM-SEATING-MAPS-P08-3 | [BE] CatalogueService: cloneSeatMap, createSeatMapTemplate, listSeatMapTemplates, listSeatMaps | 5 | Hrushikant Patkar | CatalogueService | MIG-SEATING MIG-SEATING-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: cloneSeatMap, createSeatMapTemplate, listSeatMapTemplates, listSeatMaps. Spec: contracts (seating) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management 3 of 5; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `seating#cloneSeatMap`, `seating#createSeatMapTemplate`, `seating#listSeatMapTemplates`, `seating#listSeatMaps` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-CATALOGUE-SEATMAP-5 | AM-SEATING-MAPS-P08-3 | [BE] CatalogueService: publishSeatMap, updateSeats, validateSeatMap | 5 | Pallavi Sawant | CatalogueService | MIG-PLATFORM MIG-SEATING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: publishSeatMap, updateSeats, validateSeatMap. Spec: contracts (seating) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management 3 of 5; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `seating#publishSeatMap`, `seating#updateSeats`, `seating#validateSeatMap` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | SVC-AI-CONFIGURE-2 | AM-SEATING-MAPS-P08-3 | [BE] AiService: proposeSeatMapChanges | 3 | Hrushikant Patkar | AiService | MIG-AI MIG-AI-2 MIG-AI-3 MIG-ORDERS MIG-SEATING MIG-SEATING-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: proposeSeatMapChanges. Spec: contracts (ai) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management 3 of 5; additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#proposeSeatMapChanges` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-AI-RECOMMEND-2 | AM-PRICING-PROMOTIONS-P08-7 | [BE] AiService: explainRecommendationDecision | 1 | Hrushikant Patkar | AiService | MIG-AI PLATFORM-KERNEL SVC-AI-ACTIONS-1 SVC-AI-ASSIST-1 SVC-AI-CONFIGURE-1 SVC-AI-CONFIGURE-2 SVC-AI-FORECAST-1 SVC-AI-FORECAST-3 SVC-AI-GENERATE-1 SVC-AI-GENERATE-2 SVC-AI-GENERATE-4 SVC-AI-GOVERNANCE-1 SVC-AI-GOVERNANCE-2 SVC-AI-GOVERNANCE-3 SVC-AI-MODELS-1 SVC-AI-MODELS-2 SVC-AI-MONITORING-1 SVC-AI-RECOMMEND-1 | Operations: explainRecommendationDecision. Spec: contracts (ai) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 7 of 8; additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#explainRecommendationDecision` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | VM-ADM-678 | AM-PRICING-PROMOTIONS-P08-7 | [BE] ADM-678 Journey Simulator, Decision Trace & AI Optimization | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-AI-RECOMMEND-2 SVC-CATALOGUE-RECOMMENDATIONS-3 | Allow administrators to simulate an entire customer journey and see how recommendations change over time. Module: Commercial. App: Venue Management. Waits for its definition: ADM-678's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-678` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-683 | AM-PRICING-PROMOTIONS-P08-7 | [BE] ADM-683 Next-Best-Offer Decision Studio | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-AI-RECOMMEND-2 SVC-CATALOGUE-RECOMMENDATIONS-2 | This is the core screen of Board 5. Combine all eligible candidates and determine the strongest personalized recommendation. Module: Commercial. App: Venue Management. Waits for its definition: ADM-683's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-683` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
11 | 3 | SVC-CATALOGUE-BLOCK-1 | AM-SEATING-MAPS-P08-4 | [BE] CatalogueService: createSeatBlock, listSeatBlocks | 3 | Pallavi Sawant | CatalogueService | MIG-PLATFORM MIG-SEATING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: createSeatBlock, listSeatBlocks. Spec: contracts (seating) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management 4 of 5; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `seating#createSeatBlock`, `seating#listSeatBlocks` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-CATALOGUE-IMPORT-2 | AM-SEATING-MAPS-P08-4 | [BE] CatalogueService: commitImportJob | 2 | Hrushikant Patkar | CatalogueService | MIG-SEATING-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: commitImportJob. Spec: contracts (seating) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management 4 of 5; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `seating#commitImportJob` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-CATALOGUE-SEATING-11 | AM-SEATING-MAPS-P08-4 | [BE] CatalogueService: copySeatMapSection, diffSeatMapVersions | 3 | Pallavi Sawant | CatalogueService | MIG-SEATING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: copySeatMapSection, diffSeatMapVersions. Spec: contracts (seating) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management 4 of 5; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `seating#copySeatMapSection`, `seating#diffSeatMapVersions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-CATALOGUE-RULES-1 | AM-SEATING-MAPS-P08-5 | [BE] CatalogueService: getSeatingRules, setSeatingRules | 3 | Pallavi Sawant | CatalogueService | MIG-SEATING-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getSeatingRules, setSeatingRules. Spec: contracts (seating) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management 5 of 5; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `seating#getSeatingRules`, `seating#setSeatingRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-CATALOGUE-SEATING-12 | AM-SEATING-MAPS-P08-5 | [BE] CatalogueService: assignSeats, getSeatReconciliation | 2 | Pallavi Sawant | CatalogueService | MIG-CATALOGUE MIG-SEATING MIG-SEATING-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: assignSeats, getSeatReconciliation. Spec: contracts (seating) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management 5 of 5; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `seating#assignSeats`, `seating#getSeatReconciliation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-CATALOGUE-SEATMAP-3 | AM-SEATING-MAPS-P08-2 | [BE] CatalogueService: listSeats | 1 | Hrushikant Patkar | CatalogueService | MIG-SEATING PLATFORM-KERNEL SVC-CATALOGUE-SEATING-12 SVC-CATALOGUE-SEATMAP-1 | Operations: listSeats. Spec: contracts (seating) at the release tag, served by ADAM. Built for Seating & Maps · Venue Management 2 of 5; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `seating#listSeats` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-CATALOGUE-BLOCK-2 | AM-SEATING-MAPS-P10 | [BE] CatalogueService: allocateBlockedSeats, relinquishSeatBlock | 3 | Hrushikant Patkar | CatalogueService | MIG-PLATFORM MIG-SEATING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: allocateBlockedSeats, relinquishSeatBlock. Spec: contracts (seating) at the release tag, served by ADAM. Built for Seating & Maps · Partner Portal; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `seating#allocateBlockedSeats`, `seating#relinquishSeatBlock` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | MIG-ACCESS-7 | AM-ORDERS-RESERVATIONS-P06 | [DB] Forward migration V1149__access.sql: access for Orders & Reservations · Staff App (1 tables) | 1 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-BASELINE VM-MIG-ACCESS | Tables: access.media_binding_rule. Source DDL: backend/tenant/010-access.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `access.media_binding_rule` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
15 | 3 | SVC-ORDER-ORDERS-18 | AM-ORDERS-RESERVATIONS-P06 | [BE] OrderService: splitOrder | 2 | Hrushikant Patkar | OrderService | MIG-ORDERS MIG-ORDERS-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: splitOrder. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Staff App; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#splitOrder` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-14 | AM-ORDERS-RESERVATIONS-P06 | [BE] AccessService: setMediaBindingActivation | 2 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-7 MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCESS | Operations: setMediaBindingActivation. Spec: contracts (access) at the release tag, served by ADAM. Built for Orders & Reservations · Staff App; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#setMediaBindingActivation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | MIG-ORDERS-12 | AM-ORDERS-RESERVATIONS-P08 | [DB] Forward migration V1143__orders.sql: orders for Orders & Reservations · Venue Management 1 of 8 (4 tables) | 3 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-CATALOGUE MIG-ORDERS VM-MIG-ORDERS | Tables: orders.resale_eligibility_rule, orders.resale_fee_policy, orders.resale_marketplace_config, orders.resale_settlement. Source DDL: backend/tenant/010-orders.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `orders.resale_eligibility_rule`, `orders.resale_fee_policy`, `orders.resale_marketplace_config`, `orders.resale_settlement` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
15 | 3 | SVC-ORDER-DRAFTED-5 | AM-ORDERS-RESERVATIONS-P08 | [BE] OrderService: setResaleEligibilityRule | 2 | Hrushikant Patkar | OrderService | MIG-ORDERS-12 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setResaleEligibilityRule. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 1 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#setResaleEligibilityRule` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | VM-ADM-279 | AM-ORDERS-RESERVATIONS-P08 | [BE] ADM-279 Resale Eligibility Rule Configuration | 3 | Hrushikant Patkar |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-5 | Define whether a ticket is allowed to enter the resale marketplace. Not every TICVAI ticket should automatically be resellable. Module: Commercial. App: Venue Management. Done when `ADM-279` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
14 | 3 | MIG-ORDERS-13 | AM-ORDERS-RESERVATIONS-P08-2 | [DB] Forward migration V1192__orders.sql: orders for Orders & Reservations · Venue Management 2 of 8 (1 tables) | 1 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-ORDERS VM-MIG-ORDERS | Tables: orders.resale_recommendation. Source DDL: backend/tenant/010-orders.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `orders.resale_recommendation` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
15 | 3 | SVC-ORDER-DRAFTED-6 | AM-ORDERS-RESERVATIONS-P08-2 | [BE] OrderService: approveListingModeration, createListingSeller, listBuyerPurchaseResale, listCapacityInventoryReconciliation | 8 | Hrushikant Patkar | OrderService | MIG-ACCESS MIG-CATALOGUE MIG-ORDERS MIG-ORDERS-12 MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: approveListingModeration, createListingSeller, listBuyerPurchaseResale, listCapacityInventoryReconciliation. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 2 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#approveListingModeration`, `orders#createListingSeller`, `orders#listBuyerPurchaseResale`, `orders#listCapacityInventoryReconciliation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-DRAFTED-9 | AM-ORDERS-RESERVATIONS-P08-2 | [BE] OrderService: listResalePricingPrice, listSellerSettlementPayout, listTicketOwnershipTransfer, setResaleMarketplaceRecommendation | 3 | Hrushikant Patkar | OrderService | MIG-ACCESS MIG-CATALOGUE MIG-ORDERS MIG-ORDERS-12 MIG-ORDERS-13 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listResalePricingPrice, listSellerSettlementPayout, listTicketOwnershipTransfer, setResaleMarketplaceRecommendation. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 2 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listResalePricingPrice`, `orders#listSellerSettlementPayout`, `orders#listTicketOwnershipTransfer`, `orders#setResaleMarketplaceRecommendation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-ORDERS-23 | AM-ORDERS-RESERVATIONS-P08-2 | [BE] OrderService: getResaleFeePolicy, holdResaleSettlement, releaseResaleSettlementHold, setResaleFeePolicy | 8 | Hrushikant Patkar | OrderService | MIG-ORDERS-12 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: getResaleFeePolicy, holdResaleSettlement, releaseResaleSettlementHold, setResaleFeePolicy. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 2 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#getResaleFeePolicy`, `orders#holdResaleSettlement`, `orders#releaseResaleSettlementHold`, `orders#setResaleFeePolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-ORDERS-24 | AM-ORDERS-RESERVATIONS-P08-2 | [BE] OrderService: setResaleMarketplaceConfig | 2 | Surendra | OrderService | MIG-ORDERS-12 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setResaleMarketplaceConfig. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 2 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#setResaleMarketplaceConfig` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ORDER-ORDERS-22 | AM-ORDERS-RESERVATIONS-P08 | [BE] OrderService: getResaleMarketplaceConfig | 2 | Hrushikant Patkar | OrderService | MIG-ORDERS-12 PLATFORM-KERNEL SVC-ORDER-ORDERS-24 | Operations: getResaleMarketplaceConfig. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 1 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#getResaleMarketplaceConfig` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | VM-ADM-289 | AM-ORDERS-RESERVATIONS-P08-2 | [BE] ADM-289 Buyer Purchase & Resale Order Management | 3 | Hrushikant Patkar |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-6 | Manage the buyer-side purchase transaction and ensure that a resale ticket is temporarily protected while checkout occurs. Module: Commercial. App: Venue Management. Done when `ADM-289` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-290 | AM-ORDERS-RESERVATIONS-P08-2 | [BE] ADM-290 Ticket Ownership Transfer Management | 2 | Hrushikant Patkar |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-9 | Securely transfer the ticket entitlement from the original seller to the resale buyer. Module: Commercial. App: Venue Management. Waits for its definition: ADM-290's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-290` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-293 | AM-ORDERS-RESERVATIONS-P08-2 | [BE] ADM-293 Capacity & Inventory Reconciliation | 3 | Hrushikant Patkar |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-6 | Ensure resale activity never creates additional venue capacity or corrupts primary ticket inventory. Module: Commercial. App: Venue Management. Done when `ADM-293` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-294 | AM-ORDERS-RESERVATIONS-P08-2 | [BE] ADM-294 Seller Settlement & Payout Management | 3 | Hrushikant Patkar |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-9 SVC-ORDER-ORDERS-23 | Manage the financial amount owed to sellers following successful resale. Module: Commercial. App: Venue Management. Done when `ADM-294` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-281 | AM-ORDERS-RESERVATIONS-P08-2 | [BE] ADM-281 Listing Creation & Seller Configuration | 3 | Hrushikant Patkar |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-6 SVC-ORDER-ORDERS-22 | Define how eligible ticket holders create resale listings. Module: Commercial. App: Venue Management. Done when `ADM-281` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-282 | AM-ORDERS-RESERVATIONS-P08-2 | [BE] ADM-282 Resale Pricing & Price Guardrails | 3 | Hrushikant Patkar |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-9 SVC-ORDER-ORDERS-22 SVC-ORDER-ORDERS-24 | Control the permitted resale price while protecting the operator, seller and buyer. Module: Commercial. App: Venue Management. Done when `ADM-282` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-284 | AM-ORDERS-RESERVATIONS-P08-2 | [BE] ADM-284 Listing Approval & Moderation | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-6 SVC-ORDER-ORDERS-22 | Determine whether listings are published automatically or require operator review. Module: Commercial. App: Venue Management. Done when `ADM-284` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-287 | AM-ORDERS-RESERVATIONS-P08-2 | [BE] ADM-287 AI Resale Configuration & Marketplace Recommendations | 2 | Hrushikant Patkar |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-9 SVC-ORDER-ORDERS-22 | Provide TICVAI's AI intelligence layer for optimizing resale configuration while keeping commercial control with the operator. Board 2 manages what happens once a resale listing attracts a buyer and enters the transaction stage. Module: Commercial. App: Venue Management. Done when `ADM-287` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
14 | 3 | MIG-ORDERS-14 | AM-ORDERS-RESERVATIONS-P08-3 | [DB] Forward migration V1204__orders.sql: orders for Orders & Reservations · Venue Management 3 of 8 (2 tables) | 2 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-ORDERS VM-MIG-ORDERS | Tables: orders.upgrade, orders.upgrade_rule. Source DDL: backend/tenant/010-orders.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `orders.upgrade`, `orders.upgrade_rule` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
15 | 3 | SVC-ORDER-DRAFTED-13 | AM-ORDERS-RESERVATIONS-P08-3 | [BE] OrderService: setProRataResidual, setUpgradeConversionPath | 3 | Hrushikant Patkar | OrderService | MIG-CATALOGUE MIG-ORDERS-14 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setProRataResidual, setUpgradeConversionPath. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 3 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#setProRataResidual`, `orders#setUpgradeConversionPath` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | VM-ADM-309 | AM-ORDERS-RESERVATIONS-P08-3 | [BE] ADM-309 Upgrade & Conversion Path Builder | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-13 | Define exactly which products/tickets may be converted into which other products. This becomes the central conversion relationship engine. Module: Commercial. App: Venue Management. Waits for its definition: ADM-309's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-309` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-313 | AM-ORDERS-RESERVATIONS-P08-3 | [BE] ADM-313 Pro-Rata, Residual Value & Entitlement Credit Configuration | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-13 | Handle complex upgrades where part of the original product has already been consumed. Module: Commercial. App: Venue Management. Waits for its definition: ADM-313's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-313` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
14 | 3 | MIG-ORDERS-15 | AM-ORDERS-RESERVATIONS-P08-4 | [DB] Forward migration V1205__orders.sql: orders for Orders & Reservations · Venue Management 4 of 8 (2 tables) | 2 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-ORDERS VM-MIG-ORDERS | Tables: orders.payment_allocation_rule, orders.payment_tip. Source DDL: backend/tenant/010-orders.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `orders.payment_allocation_rule`, `orders.payment_tip` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
16 | 3 | MIG-PAYMENTS-11 | AM-ORDERS-RESERVATIONS-P08-4 | [DB] Forward migration V1206__payments.sql: payments for Orders & Reservations · Venue Management 4 of 8 (1 tables) | 1 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-PAYMENTS VM-MIG-PAYMENTS | Tables: payments.risk_rules. Source DDL: backend/tenant/010-payments.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `payments.risk_rules` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
15 | 3 | SVC-ORDER-DRAFTED-14 | AM-ORDERS-RESERVATIONS-P08-4 | [BE] OrderService: createUpgradeCredentialRegeneration, listBulkGroupAssisted, listOrderPaymentDetail, listPersonTypeProduct | 5 | Hrushikant Patkar | OrderService | MIG-ACCESS MIG-CATALOGUE MIG-ORDERS MIG-ORDERS-14 MIG-ORDERS-15 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-LEDGER | Operations: createUpgradeCredentialRegeneration, listBulkGroupAssisted, listOrderPaymentDetail, listPersonTypeProduct. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 4 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#createUpgradeCredentialRegeneration`, `orders#listBulkGroupAssisted`, `orders#listOrderPaymentDetail`, `orders#listPersonTypeProduct` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-ORDERS-25 | AM-ORDERS-RESERVATIONS-P08-4 | [BE] OrderService: cancelPaymentLink, createPaymentLink, listFraudRules, listPaymentAllocationRules | 5 | Hrushikant Patkar | OrderService | MIG-MARKETING MIG-ORDERS MIG-ORDERS-15 MIG-PAYMENTS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: cancelPaymentLink, createPaymentLink, listFraudRules, listPaymentAllocationRules. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 4 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#cancelPaymentLink`, `orders#createPaymentLink`, `orders#listFraudRules`, `orders#listPaymentAllocationRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-ORDERS-26 | AM-ORDERS-RESERVATIONS-P08-4 | [BE] OrderService: listUpgrades, resendPaymentLink, setFraudRules, voidPayment | 8 | Hrushikant Patkar | OrderService | MIG-MARKETING MIG-ORDERS MIG-ORDERS-14 MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listUpgrades, resendPaymentLink, setFraudRules, voidPayment. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 4 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listUpgrades`, `orders#resendPaymentLink`, `orders#setFraudRules`, `orders#voidPayment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ORDER-DRAFTED-15 | AM-ORDERS-RESERVATIONS-P08-4 | [BE] OrderService: listUpgradeException, listVoidReversalSame, setMultiPaymentSplit | 3 | Hrushikant Patkar | OrderService | MIG-IDENTITY MIG-ORDERS MIG-ORDERS-14 MIG-ORDERS-15 MIG-PAYMENTS-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ORDERS | Operations: listUpgradeException, listVoidReversalSame, setMultiPaymentSplit. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 4 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listUpgradeException`, `orders#listVoidReversalSame`, `orders#setMultiPaymentSplit` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ORDER-PAYMENTS-11 | AM-ORDERS-RESERVATIONS-P08-4 | [BE] OrderService: setPaymentRiskRules | 2 | New full-stack developer 2 | OrderService | MIG-PAYMENTS-11 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setPaymentRiskRules. Spec: contracts (payments) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 4 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `payments#setPaymentRiskRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | VM-ADM-609 | AM-ORDERS-RESERVATIONS-P08-4 | [BE] ADM-609 Refund & Payment Adjustment Command Center | 3 | Pallavi Sawant |  | SETUP-CLIENTS SVC-ORDER-REFUND-1 | Provide centralized visibility across refund, reversal, void and adjustment operations. Module: Commercial. App: Venue Management. Done when `ADM-609` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
14 | 3 | VM-ADM-616 | AM-ORDERS-RESERVATIONS-P08-4 | [BE] ADM-616 Payment Adjustment & Financial Correction Manager | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-ORDER-REFUND-1 | Handle governed payment corrections that are not normal customer refunds. This must be tightly controlled. Module: Commercial. App: Venue Management. Waits for its definition: ADM-616's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-616` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | VM-ADM-610 | AM-ORDERS-RESERVATIONS-P08-4 | [BE] ADM-610 Refund Request & Eligibility Workspace | 3 | Pallavi Sawant |  | SETUP-CLIENTS SVC-ORDER-REFUND-1 VM-ORDER-POLICY-1 | Provide the operational workspace for creating and validating a refund request. Module: Commercial. App: Venue Management. Done when `ADM-610` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-314 | AM-ORDERS-RESERVATIONS-P08-4 | [BE] ADM-314 Person-Type, Product & Entitlement Conversion Rules | 2 | New full-stack developer 1 |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-14 | Handle conversions that change more than simply the commercial level of a ticket. Module: Commercial. App: Venue Management. Waits for its definition: ADM-314's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-314` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-315 | AM-ORDERS-RESERVATIONS-P08-4 | [BE] ADM-315 Bulk, Group & Assisted Upgrade Operations | 3 | Pallavi Sawant |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-14 | Support operational upgrades involving multiple tickets rather than requiring staff to process each individually. Module: Commercial. App: Venue Management. Done when `ADM-315` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-316 | AM-ORDERS-RESERVATIONS-P08-4 | [BE] ADM-316 Upgrade Execution, Credential Regeneration & Channel Controls | 3 | Pallavi Sawant |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-14 SVC-ORDER-ORDERS-26 | Control what happens operationally once an upgrade or conversion is approved and financially completed. Module: Commercial. App: Venue Management. Done when `ADM-316` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-592 | AM-ORDERS-RESERVATIONS-P08-4 | [BE] ADM-592 Payment Link Builder & Configuration | 3 | New full-stack developer 1 |  | SETUP-CLIENTS SVC-ORDER-ORDERS-25 | Allow authorized users and systems to generate secure payment requests without requiring the customer to be physically present at a POS. Module: Commercial. App: Venue Management. Done when `ADM-592` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-593 | AM-ORDERS-RESERVATIONS-P08-4 | [BE] ADM-593 Payment Link Distribution & Customer Journey Manager | 2 | Surendra |  | SETUP-CLIENTS SVC-ORDER-ORDERS-2 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-26 | Manage how a generated payment request is delivered and how its lifecycle progresses. Module: Commercial. App: Venue Management. Waits for its definition: ADM-593's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-593` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-595 | AM-ORDERS-RESERVATIONS-P08-4 | [BE] ADM-595 Digital Payment Session & Transaction Monitor | 2 | New full-stack developer 2 |  | SETUP-CLIENTS SVC-ORDER-PAYMENT-1 | Provide operational teams with real-time visibility into digital payment sessions. Module: Commercial. App: Venue Management. Done when `ADM-595` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-607 | AM-ORDERS-RESERVATIONS-P08-4 | [BE] ADM-607 Mixed Tender Transaction Trace & Allocation Audit | 3 | Pallavi Sawant |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-14 | Provide a complete financial and operational explanation of every multi-tender transaction. Module: Commercial. App: Venue Management. Done when `ADM-607` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-614 | AM-ORDERS-RESERVATIONS-P08-4 | [BE] ADM-614 Refund Approval & Exception Workflow | 2 | New full-stack developer 1 |  | SETUP-CLIENTS SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-26 VM-ORDER-REFUND-1 | Provide governed approval for financially sensitive refund actions. Module: Commercial. App: Venue Management. Done when `ADM-614` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-615 | AM-ORDERS-RESERVATIONS-P08-4 | [BE] ADM-615 Refund Processing, Provider Status & Recovery Center | 2 | New full-stack developer 2 |  | SETUP-CLIENTS SVC-ORDER-PAYMENT-1 | Track refund execution through the appropriate provider and recover failed or uncertain operations. Module: Commercial. App: Venue Management. Done when `ADM-615` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | VM-ADM-617 | AM-ORDERS-RESERVATIONS-P08-4 | [BE] ADM-617 Refund Transaction Trace & Audit Investigation | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-14 | Provide complete traceability from original sale through refund/reversal/adjustment. Module: Commercial. App: Venue Management. Done when `ADM-617` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-317 | AM-ORDERS-RESERVATIONS-P08-4 | [BE] ADM-317 Upgrade History, Exception Management & Audit Explorer | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-15 | Provide complete operational and financial traceability for every upgrade, downgrade, exchange and conversion. Module: Commercial. App: Venue Management. Done when `ADM-317` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-601 | AM-ORDERS-RESERVATIONS-P08-4 | [BE] ADM-601 Split Payment & Tender Allocation Manager | 3 | Hrushikant Patkar |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-15 SVC-ORDER-ORDERS-25 SVC-ORDER-PAYMENTS-6 | Determine how an order total is allocated across several payment methods. Module: Commercial. App: Venue Management. Waits for its definition: ADM-601's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-601` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-613 | AM-ORDERS-RESERVATIONS-P08-4 | [BE] ADM-613 Void, Reversal & Cancellation Manager | 2 | Hrushikant Patkar |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-15 SVC-ORDER-ORDERS-26 | Clearly distinguish voids and reversals from refunds. These should not all be called “refund”. Module: Commercial. App: Venue Management. Waits for its definition: ADM-613's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-613` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-630 | AM-ORDERS-RESERVATIONS-P08-4 | [BE] ADM-630 Payment Risk Rule & Decision Engine | 3 | New full-stack developer 2 |  | SETUP-CLIENTS SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-26 SVC-ORDER-PAYMENTS-11 | Allow administrators to configure deterministic payment risk rules and actions. Module: Commercial. App: Venue Management. Waits for its definition: ADM-630's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-630` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
14 | 3 | MIG-ORDERS-16 | AM-ORDERS-RESERVATIONS-P08-5 | [DB] Forward migration V1207__orders.sql: orders for Orders & Reservations · Venue Management 5 of 8 (3 tables) | 3 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-ORDERS VM-MIG-ORDERS | Tables: orders.order_source_channel, orders.reservation_hold_policy, orders.status_transition_rule. Source DDL: backend/tenant/010-orders.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `orders.order_source_channel`, `orders.reservation_hold_policy`, `orders.status_transition_rule` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
14 | 3 | SVC-ORDER-ORDERS-27 | AM-ORDERS-RESERVATIONS-P08-5 | [BE] OrderService: listChargebacks, respondToChargeback | 5 | New full-stack developer 1 | OrderService | MIG-ACCESS MIG-LEDGER MIG-ORDERS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-ORDERS | Operations: listChargebacks, respondToChargeback. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 5 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listChargebacks`, `orders#respondToChargeback` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-DRAFTED-16 | AM-ORDERS-RESERVATIONS-P08-5 | [BE] OrderService: createOrderSourceChannel, listCapacityReservationInventory, listOrderLineProduct, listOrderReservation | 5 | Pallavi Sawant | OrderService | MIG-ACCESS MIG-CATALOGUE MIG-ORDERS MIG-ORDERS-16 MIG-ORDERS-3 MIG-ORDERS-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createOrderSourceChannel, listCapacityReservationInventory, listOrderLineProduct, listOrderReservation. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 5 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#createOrderSourceChannel`, `orders#listCapacityReservationInventory`, `orders#listOrderLineProduct`, `orders#listOrderReservation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-DRAFTED-17 | AM-ORDERS-RESERVATIONS-P08-5 | [BE] OrderService: listReservationConfirmationExpiry, setCustomerGuestAccount, setOrderReservationStatus, setReservationHoldPolicy | 8 | Pallavi Sawant | OrderService | MIG-CATALOGUE MIG-ORDERS MIG-ORDERS-16 MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listReservationConfirmationExpiry, setCustomerGuestAccount, setOrderReservationStatus, setReservationHoldPolicy. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 5 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listReservationConfirmationExpiry`, `orders#setCustomerGuestAccount`, `orders#setOrderReservationStatus`, `orders#setReservationHoldPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ORDER-CART-4 | AM-ORDERS-RESERVATIONS-P08-5 | [BE] OrderService: listAbandonedCarts | 1 | Pranay Shinde | OrderService | MIG-ORDERS MIG-PII PLATFORM-KERNEL SVC-IDENTITY-GUESTAUTH-3 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-CART-3 SVC-VENUEOPS-VISITPLAN-1 | Operations: listAbandonedCarts. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 5 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listAbandonedCarts` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | VM-ADM-634 | AM-ORDERS-RESERVATIONS-P08-5 | [BE] ADM-634 Chargeback & Dispute Command Center | 5 | New full-stack developer 1 |  | SETUP-CLIENTS SVC-ORDER-ORDERS-27 VM-ORDER-ORDERS-1 VM-ORDER-ORDERS-2 | Provide centralized operational management for provider/acquirer chargebacks and payment disputes. Module: Commercial. App: Venue Management. Done when `ADM-634` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
14 | 3 | MIG-ORDERS-17 | AM-ORDERS-RESERVATIONS-P08-6 | [DB] Forward migration V1208__orders.sql: orders for Orders & Reservations · Venue Management 6 of 8 (6 tables) | 3 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-ORDERS VM-MIG-ORDERS | Tables: orders.after_sale_policy_window, orders.deposit_policy, orders.external_reference_mapping, orders.group_payment_milestone, orders.group_payment_schedule, orders.refund_calculation_policy. Source DDL: backend/tenant/010-orders.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `orders.after_sale_policy_window`, `orders.deposit_policy`, `orders.external_reference_mapping`, `orders.group_payment_milestone`, `orders.group_payment_schedule`, `orders.refund_calculation_policy` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
16 | 3 | MIG-PAYMENTS-12 | AM-ORDERS-RESERVATIONS-P08-6 | [DB] Forward migration V1209__payments.sql: payments for Orders & Reservations · Venue Management 6 of 8 (1 tables) | 1 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-ORDERS MIG-PAYMENTS VM-MIG-PAYMENTS | Tables: payments.deposit_activity. Source DDL: backend/tenant/010-payments.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `payments.deposit_activity` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
14 | 3 | SVC-ORDER-ORDERS-29 | AM-ORDERS-RESERVATIONS-P08-6 | [BE] OrderService: voidEntitlement | 2 | Pallavi Sawant | OrderService | MIG-ACCESS MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: voidEntitlement. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 6 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#voidEntitlement` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-DRAFTED-18 | AM-ORDERS-RESERVATIONS-P08-6 | [BE] OrderService: approveExceptionServiceRecovery, listAmendmentAfterSale, listAmendmentAfterSale2, listDepositPartialPayment | 3 | Surendra | OrderService | MIG-ORDERS MIG-ORDERS-14 MIG-ORDERS-17 MIG-PAYMENTS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ORDERS | Operations: approveExceptionServiceRecovery, listAmendmentAfterSale, listAmendmentAfterSale2, listDepositPartialPayment. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 6 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#approveExceptionServiceRecovery`, `orders#listAmendmentAfterSale`, `orders#listAmendmentAfterSale2`, `orders#listDepositPartialPayment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-DRAFTED-20 | AM-ORDERS-RESERVATIONS-P08-6 | [BE] OrderService: setAfterSaleFinancial, setAmendmentEligibilityPolicy, setCancellationPartialPolicy | 5 | New full-stack developer 2 | OrderService | MIG-ORDERS MIG-ORDERS-17 MIG-ORDERS-3 MIG-ORDERS-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ORDERS | Operations: setAfterSaleFinancial, setAmendmentEligibilityPolicy, setCancellationPartialPolicy. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 6 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#setAfterSaleFinancial`, `orders#setAmendmentEligibilityPolicy`, `orders#setCancellationPartialPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-ORDER-6 | AM-ORDERS-RESERVATIONS-P08-6 | [BE] OrderService: getDepositPolicy, setDepositPolicy | 5 | Surendra | OrderService | MIG-ORDERS-17 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getDepositPolicy, setDepositPolicy. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 6 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#getDepositPolicy`, `orders#setDepositPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-ORDERS-28 | AM-ORDERS-RESERVATIONS-P08-6 | [BE] OrderService: cleanupFailedPayment, listExternalReferenceMappings, mergeOrders, recordExternalReference | 8 | Pallavi Sawant | OrderService | MIG-LEDGER MIG-ORDERS MIG-ORDERS-17 MIG-ORDERS-5 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: cleanupFailedPayment, listExternalReferenceMappings, mergeOrders, recordExternalReference. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 6 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#cleanupFailedPayment`, `orders#listExternalReferenceMappings`, `orders#mergeOrders`, `orders#recordExternalReference` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-CATALOGUE-DRAFTED-94 | AM-PRICING-PROMOTIONS-P08-4 | [BE] CatalogueService: listCampaignExperimentTest, listCampaignFinancialCommercial, listCampaignGovernanceBudget, listConflict | 3 | Pallavi Sawant | CatalogueService | MIG-CATALOGUE MIG-ORDERS MIG-ORDERS-3 MIG-PROMOTIONS MIG-PROMOTIONS-2 PLATFORM-KERNEL SVC-CATALOGUE-COUPON-1 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-96 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTION-4 SVC-CATALOGUE-PROMOTIONS-1 SVC-IDENTITY-GUESTAUTH-2 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-18 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 | Operations: listCampaignExperimentTest, listCampaignFinancialCommercial, listCampaignGovernanceBudget, listConflict. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 4 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listCampaignExperimentTest`, `promotions#listCampaignFinancialCommercial`, `promotions#listCampaignGovernanceBudget`, `promotions#listConflict` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-CATALOGUE-DRAFTED-95 | AM-PRICING-PROMOTIONS-P08-4 | [BE] CatalogueService: listConflictDetectionResolution, listDiscountCalculationApplication, listDiscountCapMaximum, listPromotionDecisionTrace | 3 | New full-stack developer 1 | CatalogueService | MIG-ORDERS MIG-ORDERS-3 MIG-PROMOTIONS MIG-PROMOTIONS-8 PLATFORM-KERNEL SVC-CATALOGUE-EVALUATION-1 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTIONS-1 SVC-FNB-FNB-12 SVC-IDENTITY-GUESTAUTH-2 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-18 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 | Operations: listConflictDetectionResolution, listDiscountCalculationApplication, listDiscountCapMaximum, listPromotionDecisionTrace. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 4 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listConflictDetectionResolution`, `promotions#listDiscountCalculationApplication`, `promotions#listDiscountCapMaximum`, `promotions#listPromotionDecisionTrace` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | VM-ADM-212 | AM-PRICING-PROMOTIONS-P08-4 | [BE] ADM-212 Discount Calculation & Application Sequence | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-95 | Control the mathematical order in which multiple permitted benefits are calculated. Module: Commercial. App: Venue Management. Done when `ADM-212` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-214 | AM-PRICING-PROMOTIONS-P08-4 | [BE] ADM-214 Discount Cap & Maximum Benefit Controller | 2 | New full-stack developer 1 |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-95 | Prevent stacked promotions from exceeding financial or contractual limits. Module: Commercial. App: Venue Management. Done when `ADM-214` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-215 | AM-PRICING-PROMOTIONS-P08-4 | [BE] ADM-215 Conflict Detection & Resolution Center | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-95 | Detect promotion conflicts during both configuration and runtime. Module: Commercial. App: Venue Management. Done when `ADM-215` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-216 | AM-PRICING-PROMOTIONS-P08-4 | [BE] ADM-216 Promotion Decision Trace & Transaction Explainer | 2 | New full-stack developer 1 |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-95 | Provide complete explainability of how TICVAI arrived at the final promotional price. This screen will be extremely important for: Customer service Finance Operations Audit Partner disputes Technical support Module: Commercial. App: Venue Management. Waits for its definition: ADM-216's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-216` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-217 | AM-PRICING-PROMOTIONS-P08-4 | [BE] ADM-217 Conflict Simulation & AI Optimization | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-94 | Test promotion interaction scenarios before publishing campaigns. Module: Commercial. App: Venue Management. Waits for its definition: ADM-217's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-217` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-218 | AM-PRICING-PROMOTIONS-P08-4 | [BE] ADM-218 Campaign Governance & Budget Command Center | 3 | New full-stack developer 1 |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-94 | Provide executives, Marketing, Commercial, Revenue, and Finance with one centralized view of the financial and governance status of promotional campaigns. Module: Commercial. App: Venue Management. Done when `ADM-218` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-225 | AM-PRICING-PROMOTIONS-P08-4 | [BE] ADM-225 Campaign Financial & Commercial Simulator | 2 | New full-stack developer 2 |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-94 | Simulate the likely financial result of a campaign before activation. This is a major matrix requirement. Module: Commercial. App: Venue Management. Done when `ADM-225` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-226 | AM-PRICING-PROMOTIONS-P08-4 | [BE] ADM-226 Campaign Experiment & A/B Test Manager | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-94 SVC-CATALOGUE-PROMOTIONS-1 | Allow TICVAI to test campaign variants and determine which commercial strategy performs better. The matrix explicitly requires A/B testing of promotion variants, including discount levels, validity periods, bundles, and target segments. Module: Commercial. App: Venue Management. Done when `ADM-226` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | SVC-CATALOGUE-DRAFTED-98 | AM-PRICING-PROMOTIONS-P08-5 | [BE] CatalogueService: listIncrementalityAttributionCannibalization, listNextBestAction, listRedemptionConversionFunnel, listUpsellCrossSell | 3 | New full-stack developer 2 | CatalogueService | MIG-ORDERS MIG-ORDERS-3 MIG-PROMOTIONS MIG-PROMOTIONS-3 MIG-PROMOTIONS-9 PLATFORM-KERNEL SVC-CATALOGUE-COUPON-1 SVC-CATALOGUE-COUPON-2 SVC-CATALOGUE-DRAFTED-1 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTIONS-1 SVC-CATALOGUE-RECOMMENDATIONS-2 SVC-FNB-FNB-12 SVC-IDENTITY-GUESTAUTH-2 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-18 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 SVC-VENUEOPS-VISITPLAN-1 VM-CATALOGUE-UPSELL-1 VM-MIG-PROMOTIONS | Operations: listIncrementalityAttributionCannibalization, listNextBestAction, listRedemptionConversionFunnel, listUpsellCrossSell. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 5 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listIncrementalityAttributionCannibalization`, `promotions#listNextBestAction`, `promotions#listRedemptionConversionFunnel`, `promotions#listUpsellCrossSell` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-CATALOGUE-DRAFTED-97 | AM-PRICING-PROMOTIONS-P08-5 | [BE] CatalogueService: listBundleBogoAdvanced, listCustomerSegmentChannel, listDiscountMarginProfitability, listExecutivePromotionReporting | 3 | Pallavi Sawant | CatalogueService | MIG-CATALOGUE MIG-MARKETING MIG-ORDERS MIG-ORDERS-3 MIG-PROMOTIONS MIG-PROMOTIONS-2 PLATFORM-KERNEL SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-COUPON-1 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-96 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTION-4 SVC-CATALOGUE-PROMOTIONS-1 SVC-FNB-FNB-12 SVC-IDENTITY-GUESTAUTH-2 SVC-MARKETING-CONSENT-3 SVC-MARKETING-GUEST-2 SVC-MARKETING-GUESTS-2 SVC-MARKETING-MARKETING-6 SVC-MARKETING-MARKETING-7 SVC-MARKETING-SEGMENT-1 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-18 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 | Operations: listBundleBogoAdvanced, listCustomerSegmentChannel, listDiscountMarginProfitability, listExecutivePromotionReporting. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 5 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listBundleBogoAdvanced`, `promotions#listCustomerSegmentChannel`, `promotions#listDiscountMarginProfitability`, `promotions#listExecutivePromotionReporting` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | VM-ADM-230 | AM-PRICING-PROMOTIONS-P08-5 | [BE] ADM-230 Redemption, Conversion & Funnel Analytics | 3 | Surendra |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-98 | Measure how effectively offers move customers from exposure to purchase and redemption. Module: Commercial. App: Venue Management. Done when `ADM-230` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-233 | AM-PRICING-PROMOTIONS-P08-5 | [BE] ADM-233 Upsell, Cross-Sell & Attach-Rate Analytics | 3 | New full-stack developer 2 |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-98 | Measure whether promotions and bundles successfully increase the customer's basket beyond the original purchase. This screen is particularly important for the cross-sale metrics you originally raised. Module: Commercial. App: Venue Management. Done when `ADM-233` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-235 | AM-PRICING-PROMOTIONS-P08-5 | [BE] ADM-235 Incrementality, Attribution & Cannibalization Analysis | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-98 | Incrementality, Attribution & Cannibalization Analysis Module: Commercial. App: Venue Management. Done when `ADM-235` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-236 | AM-PRICING-PROMOTIONS-P08-5 | [BE] ADM-236 AI Optimization & Next-Best-Action Center | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-98 | Turn analytics into actionable commercial recommendations. This should be one of the strongest AI screens in the Promotions module. Module: Commercial. App: Venue Management. Waits for its definition: ADM-236's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-236` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-231 | AM-PRICING-PROMOTIONS-P08-5 | [BE] ADM-231 Discount, Margin & Profitability Analytics | 3 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-97 | Determine whether promotions are commercially profitable rather than merely generating sales. Module: Commercial. App: Venue Management. Done when `ADM-231` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-232 | AM-PRICING-PROMOTIONS-P08-5 | [BE] ADM-232 Bundle, BOGO & Advanced Offer Analytics | 3 | New full-stack developer 2 |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-97 | Measure performance specifically for the commercial mechanics created in Boards 4–6. Module: Commercial. App: Venue Management. Done when `ADM-232` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-234 | AM-PRICING-PROMOTIONS-P08-5 | [BE] ADM-234 Customer, Segment, Channel & Partner Analytics | 3 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-97 | Determine which audiences and distribution channels respond best to promotions. Module: Commercial. App: Venue Management. Done when `ADM-234` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-237 | AM-PRICING-PROMOTIONS-P08-5 | [BE] ADM-237 Executive Promotion Intelligence & Reporting Studio | 2 | New full-stack developer 1 |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-97 | Provide executive reporting and configurable analytics output across the complete Promotions & Bundles module. Module: Commercial. App: Venue Management. Done when `ADM-237` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-659 | AM-PRICING-PROMOTIONS-P08-6 | [BE] ADM-659 Cross-Sell Command Center | 5 | Hrushikant Patkar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-98 SVC-CATALOGUE-RECOMMENDATIONS-1 | Provide centralized visibility into cross-sell relationships, recommendation performance, attach rates and commercial opportunities. Module: Commercial. App: Venue Management. Done when `ADM-659` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | SVC-ORDER-POLICY-2 | AM-ORDERS-RESERVATIONS-P08-6 | [BE] OrderService: setRefundCalculationPolicy | 1 | Deep Khanvilkar | OrderService | MIG-ORDERS-17 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setRefundCalculationPolicy. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 6 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#setRefundCalculationPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ORDER-PAYMENTS-12 | AM-ORDERS-RESERVATIONS-P08-6 | [BE] OrderService: listDepositActivity, recordDepositActivity | 2 | Hrushikant Patkar | OrderService | MIG-PAYMENTS-12 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listDepositActivity, recordDepositActivity. Spec: contracts (payments) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 6 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `payments#listDepositActivity`, `payments#recordDepositActivity` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | MIG-ORDERS-18 | AM-ORDERS-RESERVATIONS-P08-7 | [DB] Forward migration V1210__orders.sql: orders for Orders & Reservations · Venue Management 7 of 8 (6 tables) | 3 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-ORDERS VM-MIG-ORDERS | Tables: orders.group_enquiry, orders.group_quote_line, orders.group_task, orders.group_ticket_allocation, orders.group_ticket_allocation_line, orders.group_ticket_fulfillment. Source DDL: backend/tenant/010-orders.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `orders.group_enquiry`, `orders.group_quote_line`, `orders.group_task`, `orders.group_ticket_allocation`, `orders.group_ticket_allocation_line`, `orders.group_ticket_fulfillment` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
15 | 3 | SVC-ORDER-DRAFTED-21 | AM-ORDERS-RESERVATIONS-P08-7 | [BE] OrderService: approveGroupDiscountException, listFinancialTraceability, listGroupBooking, listGroupBookingReconciliation | 5 | Hrushikant Patkar | OrderService | MIG-ACCESS MIG-CATALOGUE MIG-LEDGER MIG-ORDERS MIG-ORDERS-17 MIG-ORDERS-18 MIG-ORDERS-3 MIG-ORDERS-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ORDERS | Operations: approveGroupDiscountException, listFinancialTraceability, listGroupBooking, listGroupBookingReconciliation. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 7 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#approveGroupDiscountException`, `orders#listFinancialTraceability`, `orders#listGroupBooking`, `orders#listGroupBookingReconciliation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-DRAFTED-24 | AM-ORDERS-RESERVATIONS-P08-7 | [BE] OrderService: listQuoteBookingConversion, listQuoteRevisionNegotiation, setGroupBookingHandover, setGroupOperationalPlanning | 5 | Hrushikant Patkar | OrderService | MIG-ORDERS MIG-ORDERS-17 MIG-ORDERS-18 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ORDERS | Operations: listQuoteBookingConversion, listQuoteRevisionNegotiation, setGroupBookingHandover, setGroupOperationalPlanning. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 7 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listQuoteBookingConversion`, `orders#listQuoteRevisionNegotiation`, `orders#setGroupBookingHandover`, `orders#setGroupOperationalPlanning` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-DRAFTED-25 | AM-ORDERS-RESERVATIONS-P08-7 | [BE] OrderService: setGroupPackageExperience, setGroupQuotationProposal | 5 | Hrushikant Patkar | OrderService | MIG-CATALOGUE MIG-ORDERS MIG-ORDERS-18 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ORDERS | Operations: setGroupPackageExperience, setGroupQuotationProposal. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 7 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#setGroupPackageExperience`, `orders#setGroupQuotationProposal` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-ORDERS-30 | AM-ORDERS-RESERVATIONS-P08-7 | [BE] OrderService: createGroupEnquiry, setGroupCustomerOrganization, setGroupPaymentSchedule, setParticipantGuestList | 8 | Hrushikant Patkar | OrderService | MIG-ORDERS MIG-ORDERS-17 MIG-ORDERS-18 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createGroupEnquiry, setGroupCustomerOrganization, setGroupPaymentSchedule, setParticipantGuestList. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 7 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#createGroupEnquiry`, `orders#setGroupCustomerOrganization`, `orders#setGroupPaymentSchedule`, `orders#setParticipantGuestList` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-ORDERS-31 | AM-ORDERS-RESERVATIONS-P08-8 | [BE] OrderService: setGroupTicketAllocation, setGroupTicketFulfillment | 3 | Deep Khanvilkar | OrderService | MIG-ORDERS-18 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setGroupTicketAllocation, setGroupTicketFulfillment. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 8 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#setGroupTicketAllocation`, `orders#setGroupTicketFulfillment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ORDER-B2B-3 | AM-ORDERS-RESERVATIONS-P10 | [BE] OrderService: getB2bCredit | 2 | Deep Khanvilkar | OrderService | MIG-ORDERS-6 PLATFORM-KERNEL SVC-ORDER-B2B-1 | Operations: getB2bCredit. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Partner Portal; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#getB2bCredit` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-ORDER-PAYMENTS-15 | AM-PAYMENTS-P08 | [BE] OrderService: updatePaymentMethod | 2 | Surendra | OrderService | MIG-PAYMENTS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: updatePaymentMethod. Spec: contracts (payments) at the release tag, served by ADAM. Built for Payments · Venue Management 1 of 3; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `payments#updatePaymentMethod` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ORDER-PAYMENTS-13 | AM-PAYMENTS-P08 | [BE] OrderService: createPaymentMethod, getPaymentPerformance, getPaymentProviderHealth, getPaymentRules | 5 | Pallavi Sawant | OrderService | MIG-ORDERS MIG-PAYMENTS MIG-PAYMENTS-7 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createPaymentMethod, getPaymentPerformance, getPaymentProviderHealth, getPaymentRules. Spec: contracts (payments) at the release tag, served by ADAM. Built for Payments · Venue Management 1 of 3; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `payments#createPaymentMethod`, `payments#getPaymentPerformance`, `payments#getPaymentProviderHealth`, `payments#getPaymentRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ORDER-PAYMENTS-14 | AM-PAYMENTS-P08 | [BE] OrderService: listPaymentRoutingRules, receivePaymentProviderWebhook, setPaymentFailoverPolicy, setPaymentRoutingRules | 8 | Surendra | OrderService | MIG-CATALOGUE MIG-LEDGER MIG-ORDERS MIG-PAYMENTS MIG-PAYMENTS-7 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: listPaymentRoutingRules, receivePaymentProviderWebhook, setPaymentFailoverPolicy, setPaymentRoutingRules. Spec: contracts (payments) at the release tag, served by ADAM. Built for Payments · Venue Management 1 of 3; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `payments#listPaymentRoutingRules`, `payments#receivePaymentProviderWebhook`, `payments#setPaymentFailoverPolicy`, `payments#setPaymentRoutingRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-CATALOGUE-DRAFTED-89 | AM-PRICING-PROMOTIONS-P08-3 | [BE] CatalogueService: listAudienceDiscoveryTargeting, listAudiencePreviewReach, listBehavioralTransactionTargeting, listBundleAvailabilityChannel | 5 | New full-stack developer 2 | CatalogueService | MIG-CATALOGUE MIG-MARKETING MIG-ORDERS MIG-ORDERS-3 MIG-PROMOTIONS MIG-PROMOTIONS-8 PLATFORM-KERNEL SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-BUNDLE-7 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTIONS-1 SVC-FNB-FNB-12 SVC-IDENTITY-GUESTAUTH-2 SVC-MARKETING-CONSENT-3 SVC-MARKETING-GUEST-2 SVC-MARKETING-GUESTS-2 SVC-MARKETING-MARKETING-6 SVC-MARKETING-MARKETING-7 SVC-MARKETING-SEGMENT-1 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-18 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-14 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 SVC-VENUEOPS-VISITPLAN-1 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-LEASE-1 | Operations: listAudienceDiscoveryTargeting, listAudiencePreviewReach, listBehavioralTransactionTargeting, listBundleAvailabilityChannel. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 3 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listAudienceDiscoveryTargeting`, `promotions#listAudiencePreviewReach`, `promotions#listBehavioralTransactionTargeting`, `promotions#listBundleAvailabilityChannel` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-CATALOGUE-DRAFTED-90 | AM-PRICING-PROMOTIONS-P08-3 | [BE] CatalogueService: listBundleAvailabilityForecast, listBundleSellabilityDependency, listCapacityPoolReservation, listContextLocationChannel | 3 | New full-stack developer 1 | CatalogueService | MIG-CATALOGUE MIG-ORDERS MIG-PROMOTIONS MIG-PROMOTIONS-8 PLATFORM-KERNEL SVC-CATALOGUE-BUNDLE-1 SVC-CATALOGUE-BUNDLE-2 SVC-CATALOGUE-BUNDLE-7 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-CATALOGUE-PROMOTION-1 SVC-CATALOGUE-PROMOTION-2 SVC-CATALOGUE-PROMOTION-3 SVC-CATALOGUE-PROMOTIONS-1 SVC-FNB-FNB-12 SVC-IDENTITY-GUESTAUTH-2 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-CART-3 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-18 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-14 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 SVC-VENUEOPS-VISITPLAN-1 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-CATALOGUE-1 VM-CATALOGUE-LEASE-1 | Operations: listBundleAvailabilityForecast, listBundleSellabilityDependency, listCapacityPoolReservation, listContextLocationChannel. Spec: contracts (promotions) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 3 of 8; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `promotions#listBundleAvailabilityForecast`, `promotions#listBundleSellabilityDependency`, `promotions#listCapacityPoolReservation`, `promotions#listContextLocationChannel` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
19 | 3 | VM-ADM-190 | AM-PRICING-PROMOTIONS-P08-3 | [BE] ADM-190 Bundle Sellability & Dependency Rule Engine | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-90 | Determine whether the overall bundle can be sold based on the state of its underlying components. Module: Commercial. App: Venue Management. Waits for its definition: ADM-190's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-190` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-191 | AM-PRICING-PROMOTIONS-P08-3 | [BE] ADM-191 Capacity Pool & Reservation Manager | 3 | Sanket Keluskar |  | SETUP-CLIENTS SVC-CATALOGUE-BUNDLE-7 SVC-CATALOGUE-DRAFTED-90 | Manage how bundle sales consume capacity from underlying products. This is particularly important because a bundle must not create artificial inventory separate from the actual attraction/product capacity. Module: Commercial. App: Venue Management. Done when `ADM-191` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-195 | AM-PRICING-PROMOTIONS-P08-3 | [BE] ADM-195 Bundle Availability by Channel, Venue & Partner | 3 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-BUNDLE-7 SVC-CATALOGUE-DRAFTED-89 | Control where a bundle is sellable based on operational availability. Module: Commercial. App: Venue Management. Done when `ADM-195` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-196 | AM-PRICING-PROMOTIONS-P08-3 | [BE] ADM-196 Bundle Availability Forecast, Alerts & Recovery | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-90 | Predict bundle availability problems before they affect sales. Module: Commercial. App: Venue Management. Done when `ADM-196` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-202 | AM-PRICING-PROMOTIONS-P08-3 | [BE] ADM-202 Behavioral & Transaction Targeting | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-89 | Target promotions according to what the guest has previously purchased or done. Module: Commercial. App: Venue Management. Done when `ADM-202` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-203 | AM-PRICING-PROMOTIONS-P08-3 | [BE] ADM-203 Context, Location, Channel & Time Targeting | 2 | Sanket Keluskar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-90 | Determine promotion eligibility according to the customer's current commercial context. Module: Commercial. App: Venue Management. Waits for its definition: ADM-203's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-203` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-205 | AM-PRICING-PROMOTIONS-P08-3 | [BE] ADM-205 Audience Preview, Reach & Eligibility Simulator | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-89 | Allow administrators to understand exactly who will qualify before activating the targeting rule. This is a critical safeguard. Module: Commercial. App: Venue Management. Done when `ADM-205` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-207 | AM-PRICING-PROMOTIONS-P08-3 | [BE] ADM-207 AI Audience Discovery & Targeting Optimization | 2 | New full-stack developer 2 |  | SETUP-CLIENTS SVC-CATALOGUE-DRAFTED-89 | Use TICVAI's AI layer to identify customer audiences and promotion opportunities that business users may not have manually defined. Board 8 shall provide TICVAI with the centralized Promotion Decision Engine responsible for determining what happens when multiple promotions, discounts, coupons, bundles, loyalty benefits, membership benefits, payment offers, BOGO mechanics, partner offers, or special prices qualify for the same transaction. This is one of the most important boards in the Promotions module because the previous boards may all produce valid offers simultaneously. For example, a guest could qualify for: Annual Pass Holder — 15% discount SUMMER20 coupon — 20% discount Emirates NBD card — 10% discount Buy 4 Pay 3 — promotional mechanic Loyalty Gold — 5% benefit Can they combine? In what order? Which promotion wins? What is the maximum permitted benefit? The matrix explicitly requires configurable promotion hierarchy, stacking and conflict resolution, including scenarios where promotions are combined, mutually exclusive, or prioritized, with clear explanation of which promotion was applied and why. Board 8 shall contain 10 backend screens. Module: Commercial. App: Venue Management. Waits for its definition: ADM-207's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-207` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | SVC-ORDER-DRAFTED-19 | AM-ORDERS-RESERVATIONS-P08-6 | [BE] OrderService: listExternalPaymentPartner, listOrderLifecycleTimeline, listOrderSplitMerge, listRelatedOrderTransaction | 3 | Pallavi Sawant | OrderService | MIG-ORDERS MIG-ORDERS-14 MIG-ORDERS-17 MIG-ORDERS-3 MIG-ORDERS-5 MIG-ORDERS-6 MIG-SYNC PLATFORM-KERNEL SVC-FNB-FNB-12 SVC-IDENTITY-GUESTAUTH-2 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-14 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-18 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-26 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-PAYMENTS-14 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 SVC-VENUEOPS-PLAY-1 SVC-WALLET-RETAIL-1 VM-ACCESS-SYNC-1 VM-LEDGER-SETTLEMENT-1 VM-MIG-LEDGER VM-ORDER-REFUND-1 VM-ORDER-SYNC-1 | Operations: listExternalPaymentPartner, listOrderLifecycleTimeline, listOrderSplitMerge, listRelatedOrderTransaction. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 6 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listExternalPaymentPartner`, `orders#listOrderLifecycleTimeline`, `orders#listOrderSplitMerge`, `orders#listRelatedOrderTransaction` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-ORDER-DRAFTED-22 | AM-ORDERS-RESERVATIONS-P08-7 | [BE] OrderService: listGroupCustomerOrganization, listGroupEnquiryOpportunity, listGroupPaymentDeposit, listGroupRequirementAvailability | 3 | Hrushikant Patkar | OrderService | MIG-CATALOGUE MIG-ORDERS MIG-ORDERS-17 MIG-ORDERS-18 PLATFORM-KERNEL SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-IDENTITY-GUESTAUTH-2 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-CART-3 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDER-6 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-18 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-26 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-30 SVC-ORDER-ORDERS-4 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-PAYMENTS-14 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 SVC-VENUEOPS-VISITPLAN-1 SVC-WALLET-RETAIL-1 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-CATALOGUE-1 VM-CATALOGUE-EVENT-1 VM-CATALOGUE-LEASE-1 VM-MIG-ORDERS VM-ORDER-ORDERS-1 VM-ORDER-ORDERS-3 | Operations: listGroupCustomerOrganization, listGroupEnquiryOpportunity, listGroupPaymentDeposit, listGroupRequirementAvailability. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 7 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listGroupCustomerOrganization`, `orders#listGroupEnquiryOpportunity`, `orders#listGroupPaymentDeposit`, `orders#listGroupRequirementAvailability` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | VM-ADM-559 | AM-PAYMENTS-P08 | [BE] ADM-559 Payment Command Center | 5 | Pallavi Sawant |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-13 SVC-ORDER-PAYMENTS-17 | Provide centralized visibility into payment operations and configuration across the tenant. Module: Commercial. App: Venue Management. Done when `ADM-559` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-560 | AM-PAYMENTS-P08 | [BE] ADM-560 Payment Method Catalogue | 2 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-13 SVC-ORDER-PAYMENTS-17 | Maintain the centralized catalogue of payment/tender types supported by TICVAI. Module: Commercial. App: Venue Management. Done when `ADM-560` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-561 | AM-PAYMENTS-P08 | [BE] ADM-561 Payment Method Configuration | 3 | Sanket Keluskar |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-15 SVC-ORDER-PAYMENTS-17 | Configure detailed behavior for each payment method. Module: Commercial. App: Venue Management. Done when `ADM-561` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-562 | AM-PAYMENTS-P08 | [BE] ADM-562 Channel & Touchpoint Payment Configuration | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-15 SVC-ORDER-PAYMENTS-17 | Control which payment methods are available on each sales channel. Module: Commercial. App: Venue Management. Waits for its definition: ADM-562's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-562` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-563 | AM-PAYMENTS-P08 | [BE] ADM-563 Venue, Location & Business Unit Payment Assignment | 3 | Sanket Keluskar |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-15 SVC-ORDER-PAYMENTS-17 | Allow different venues and business units to operate different payment configurations. This is important for TICVAI's multi-venue architecture. Module: Commercial. App: Venue Management. Done when `ADM-563` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-564 | AM-PAYMENTS-P08 | [BE] ADM-564 Currency & Payment Currency Configuration | 2 | New full-stack developer 1 |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-13 SVC-ORDER-PAYMENTS-15 | Define which currencies can be used for payment and how payment currencies interact with TICVAI's selling and accounting currencies. Module: Commercial. App: Venue Management. Done when `ADM-564` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-565 | AM-PAYMENTS-P08 | [BE] ADM-565 Payment Eligibility & Availability Rule Builder | 3 | Sanket Keluskar |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-13 SVC-ORDER-PAYMENTS-15 | Determine whether a payment method should be available for a particular transaction. Module: Commercial. App: Venue Management. Waits for its definition: ADM-565's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-565` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-566 | AM-PAYMENTS-P08 | [BE] ADM-566 Payment Fees, Surcharges & Commercial Rules | 3 | Hrushikant Patkar |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-13 SVC-ORDER-PAYMENTS-15 | Configure payment-related commercial rules where legally and contractually permitted. Module: Commercial. App: Venue Management. Waits for its definition: ADM-566's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-566` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-567 | AM-PAYMENTS-P08 | [BE] ADM-567 Payment Policy, Governance & Approval Manager | 3 | Hrushikant Patkar |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-13 SVC-ORDER-PAYMENTS-17 SVC-TENANCY-REQUEST-1 | Provide governance over sensitive payment configuration changes. Module: Commercial. App: Venue Management. Done when `ADM-567` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-568 | AM-PAYMENTS-P08 | [BE] ADM-568 Payment Configuration Simulator & Validation Center | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-13 SVC-ORDER-PAYMENTS-17 | Allow administrators to test payment configuration before publishing it. This is especially important because payment configuration errors can immediately stop sales. Module: Commercial. App: Venue Management. Done when `ADM-568` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-569 | AM-PAYMENTS-P08 | [BE] ADM-569 Payment Orchestration Command Center | 5 | New full-stack developer 1 |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-13 SVC-ORDER-PAYMENTS-17 | Provide real-time operational visibility across all payment gateways, PSPs and acquirers. Module: Commercial. App: Venue Management. Done when `ADM-569` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-571 | AM-PAYMENTS-P08 | [BE] ADM-571 Provider Connection & Adapter Configuration | 3 | Sanket Keluskar |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-1 SVC-ORDER-PAYMENTS-17 SVC-ORDER-PAYMENTS-18 | Configure how TICVAI technically connects to each payment provider. Module: Commercial. App: Venue Management. Done when `ADM-571` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-572 | AM-PAYMENTS-P08 | [BE] ADM-572 Gateway Capability & Payment Method Mapping | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-17 | Map Board 1 payment methods to providers capable of processing them. Module: Commercial. App: Venue Management. Waits for its definition: ADM-572's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-572` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-573 | AM-PAYMENTS-P08 | [BE] ADM-573 Payment Routing Rule Builder | 3 | Surendra |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-14 | Configure the rules that determine which provider should receive each payment transaction. Module: Commercial. App: Venue Management. Waits for its definition: ADM-573's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-573` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-574 | AM-PAYMENTS-P08 | [BE] ADM-574 Routing Strategy, Priority & Load Distribution | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-14 | Manage how payment traffic is distributed when several valid providers are available. Module: Commercial. App: Venue Management. Done when `ADM-574` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-575 | AM-PAYMENTS-P08 | [BE] ADM-575 Failover, Retry & Resilience Manager | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-14 | Maintain payment availability when a provider experiences a technical problem. This is one of the most important screens in the Payment Orchestration module. Module: Commercial. App: Venue Management. Done when `ADM-575` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | MIG-PAYMENTS-14 | AM-PAYMENTS-P08-2 | [DB] Forward migration V1211__payments.sql: payments for Payments · Venue Management 2 of 3 (2 tables) | 2 | Hrushikant Patkar | OrderService | MIG-BASELINE MIG-PAYMENTS VM-MIG-PAYMENTS | Tables: payments.authentication_policy, payments.hosted_checkout. Source DDL: backend/tenant/010-payments.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `payments.authentication_policy`, `payments.hosted_checkout` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
17 | 3 | SVC-ORDER-PAYMENTS-19 | AM-PAYMENTS-P08-2 | [BE] OrderService: listStoredForwardTransactions, recordPaymentTerminalCertification, setHostedCheckoutConfiguration, setPaymentAuthenticationPolicy | 5 | Hrushikant Patkar | OrderService | MIG-PAYMENTS MIG-PAYMENTS-14 MIG-PAYMENTS-3 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listStoredForwardTransactions, recordPaymentTerminalCertification, setHostedCheckoutConfiguration, setPaymentAuthenticationPolicy. Spec: contracts (payments) at the release tag, served by ADAM. Built for Payments · Venue Management 2 of 3; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `payments#listStoredForwardTransactions`, `payments#recordPaymentTerminalCertification`, `payments#setHostedCheckoutConfiguration`, `payments#setPaymentAuthenticationPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-ORDER-PAYMENTS-16 | AM-PAYMENTS-P08-2 | [BE] OrderService: getMixedTenderRules, getPaymentProviderEconomics, listPaymentTerminalCertifications, listPaymentTerminals | 3 | Deep Khanvilkar | OrderService | MIG-ORDERS MIG-PAYMENTS MIG-PAYMENTS-3 MIG-PAYMENTS-4 MIG-PAYMENTS-7 PLATFORM-KERNEL SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-26 SVC-ORDER-ORDERS-27 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-3 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-PAYMENTS-14 SVC-ORDER-PAYMENTS-17 SVC-ORDER-PAYMENTS-18 SVC-ORDER-PAYMENTS-19 SVC-ORDER-PAYMENTS-4 SVC-ORDER-PAYMENTS-6 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 SVC-WALLET-RETAIL-1 VM-LEDGER-SETTLEMENT-1 VM-MIG-LEDGER VM-MIG-ORDERS VM-MIG-PAYMENTS VM-ORDER-ORDERS-1 VM-ORDER-ORDERS-2 | Operations: getMixedTenderRules, getPaymentProviderEconomics, listPaymentTerminalCertifications, listPaymentTerminals. Spec: contracts (payments) at the release tag, served by ADAM. Built for Payments · Venue Management 2 of 3; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `payments#getMixedTenderRules`, `payments#getPaymentProviderEconomics`, `payments#listPaymentTerminalCertifications`, `payments#listPaymentTerminals` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-ORDER-PAYMENTS-20 | AM-PAYMENTS-P08-2 | [BE] OrderService: simulatePaymentRouting | 1 | Chinmay Patkar | OrderService | MIG-PAYMENTS MIG-PAYMENTS-7 PLATFORM-KERNEL SVC-ORDER-ORDERS-5 SVC-ORDER-PAYMENTS-1 SVC-ORDER-PAYMENTS-13 SVC-ORDER-PAYMENTS-14 SVC-ORDER-PAYMENTS-15 SVC-ORDER-PAYMENTS-17 SVC-ORDER-PAYMENTS-18 | Operations: simulatePaymentRouting. Spec: contracts (payments) at the release tag, served by ADAM. Built for Payments · Venue Management 2 of 3; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `payments#simulatePaymentRouting` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | VM-ADM-576 | AM-PAYMENTS-P08-2 | [BE] ADM-576 Provider Health, SLA & Performance Monitor | 3 | New full-stack developer 2 |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-13 | Monitor each provider's technical and transactional health. Module: Commercial. App: Venue Management. Done when `ADM-576` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-586 | AM-PAYMENTS-P08-2 | [BE] ADM-586 Degraded, Offline & Store-and-Forward Manager | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-19 SVC-ORDER-PAYMENTS-4 | Manage card-present operations when normal connectivity is unavailable. This directly addresses the degraded-mode requirement in the payment matrix. Module: Commercial. App: Venue Management. Done when `ADM-586` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-589 | AM-PAYMENTS-P08-2 | [BE] ADM-589 Digital Payments Command Center | 3 | Pallavi Sawant |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-13 | Provide centralized operational visibility across all digital and alternative payment journeys. Module: Commercial. App: Venue Management. Done when `ADM-589` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-590 | AM-PAYMENTS-P08-2 | [BE] ADM-590 Digital & Alternative Payment Method Manager | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-15 SVC-ORDER-PAYMENTS-17 | Configure the digital payment experiences available through TICVAI. Module: Commercial. App: Venue Management. Waits for its definition: ADM-590's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-590` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-591 | AM-PAYMENTS-P08-2 | [BE] ADM-591 Digital Wallet & Mobile Payment Configuration | 2 | Sanket Keluskar |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-15 SVC-ORDER-PAYMENTS-17 | Manage wallet-based and mobile digital payment methods. Module: Commercial. App: Venue Management. Waits for its definition: ADM-591's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-591` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-594 | AM-PAYMENTS-P08-2 | [BE] ADM-594 Hosted Checkout, Redirect & Return Flow Configuration | 3 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-19 | Configure digital payment flows that require provider-hosted payment pages, redirects, SDKs, or asynchronous customer journeys. Module: Commercial. App: Venue Management. Done when `ADM-594` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-596 | AM-PAYMENTS-P08-2 | [BE] ADM-596 Authentication, Tokenization & Recurring Payment Controls | 2 | New full-stack developer 2 |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-19 | Manage digital-payment security capabilities and reusable payment references without turning TICVAI into a card vault. Module: Commercial. App: Venue Management. Done when `ADM-596` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-597 | AM-PAYMENTS-P08-2 | [BE] ADM-597 Digital Payment Exception, Recovery & Expiry Center | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-19 | Centralize operational handling of incomplete or abnormal digital-payment journeys. Module: Commercial. App: Venue Management. Done when `ADM-597` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-598 | AM-PAYMENTS-P08-2 | [BE] ADM-598 Digital Payment Simulator, Conversion & AI Advisor | 3 | New full-stack developer 1 |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-13 SVC-ORDER-PAYMENTS-17 | Allow administrators to validate digital payment journeys and identify conversion opportunities before deploying configuration changes. Module: Commercial. App: Venue Management. Done when `ADM-598` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-577 | AM-PAYMENTS-P08-2 | [BE] ADM-577 Provider Cost, Commercial & Routing Economics | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-16 | Allow TICVAI to understand the commercial cost of routing transactions through different providers. Module: Commercial. App: Venue Management. Done when `ADM-577` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-578 | AM-PAYMENTS-P08-2 | [BE] ADM-578 Payment Routing Simulator, Decision Trace & AI Advisor | 2 | Sanket Keluskar |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-14 SVC-ORDER-PAYMENTS-20 | Allow administrators to test exactly how a payment will be routed before deploying routing changes. Module: Commercial. App: Venue Management. Done when `ADM-578` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-579 | AM-PAYMENTS-P08-2 | [BE] ADM-579 Terminal & Card-Present Command Center | 3 | Surendra |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-16 | Provide real-time operational visibility over all card-present payment infrastructure. Module: Commercial. App: Venue Management. Done when `ADM-579` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-580 | AM-PAYMENTS-P08-2 | [BE] ADM-580 Payment Terminal & Device Inventory | 3 | New full-stack developer 2 |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-16 SVC-ORDER-PAYMENTS-19 SVC-TENANCY-WORKSTATION-2 | Maintain the centralized inventory of all payment terminals connected to TICVAI. Module: Commercial. App: Venue Management. Waits for its definition: ADM-580's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-580` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-583 | AM-PAYMENTS-P08-2 | [BE] ADM-583 EMV & Card-Present Processing Configuration | 3 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-16 SVC-ORDER-PAYMENTS-4 | Configure card-present transaction capabilities without exposing sensitive cardholder data. Module: Commercial. App: Venue Management. Done when `ADM-583` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-585 | AM-PAYMENTS-P08-2 | [BE] ADM-585 Card-Present Transaction Monitor & Operations | 2 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-16 | Provide operations teams with real-time visibility into card-present payment attempts. Module: Commercial. App: Venue Management. Done when `ADM-585` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-588 | AM-PAYMENTS-P08-2 | [BE] ADM-588 Terminal Simulator, Certification & AI Operations Advisor | 5 | Pallavi Sawant |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-16 SVC-ORDER-PAYMENTS-18 SVC-ORDER-PAYMENTS-19 | Provide a controlled environment to validate terminal configuration and payment flows before production activation. Module: Commercial. App: Venue Management. Done when `ADM-588` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-599 | AM-PAYMENTS-P08-2 | [BE] ADM-599 Mixed Tender & Credit Command Center | 3 | Sanket Keluskar |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-16 | Provide centralized operational visibility over mixed-tender and account-credit transactions. Module: Commercial. App: Venue Management. Done when `ADM-599` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
9 | 3 | MIG-AI-6 | AM-PAYMENTS-P08-3 | [DB] Forward migration V1175__ai.sql: ai for Payments · Venue Management 3 of 3 (3 tables) | 2 | Hrushikant Patkar | AiService | MIG-AI MIG-BASELINE MIG-IDENTITY VM-MIG-AI | Tables: ai.risk_assessment, ai.risk_case, ai.risk_strategy. Source DDL: backend/tenant/010-ai.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `ai.risk_assessment`, `ai.risk_case`, `ai.risk_strategy` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-WALLET-WALLET-13 | AM-PAYMENTS-P08-3 | [BE] WalletService: getCreditConsumptionPolicy, setWalletChannelRules | 2 | Chinmay Patkar | WalletService | MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getCreditConsumptionPolicy, setWalletChannelRules. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Payments · Venue Management 3 of 3; additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#getCreditConsumptionPolicy`, `wallet#setWalletChannelRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ORDER-PAYMENTS-21 | AM-PAYMENTS-P08-3 | [BE] OrderService: createB2bCreditAccount, listB2bCreditAccounts, listMerchantAccounts, setMerchantAccount | 5 | New full-stack developer 2 | OrderService | MIG-PAYMENTS-9 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createB2bCreditAccount, listB2bCreditAccounts, listMerchantAccounts, setMerchantAccount. Spec: contracts (payments) at the release tag, served by ADAM. Built for Payments · Venue Management 3 of 3; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `payments#createB2bCreditAccount`, `payments#listB2bCreditAccounts`, `payments#listMerchantAccounts`, `payments#setMerchantAccount` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ORDER-PAYMENTS-22 | AM-PAYMENTS-P08-3 | [BE] OrderService: setReconciliationMatchingRules, setReconciliationSource, submitChargebackEvidence | 5 | Surendra | OrderService | MIG-PAYMENTS-2 MIG-PAYMENTS-9 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setReconciliationMatchingRules, setReconciliationSource, submitChargebackEvidence. Spec: contracts (payments) at the release tag, served by ADAM. Built for Payments · Venue Management 3 of 3; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `payments#setReconciliationMatchingRules`, `payments#setReconciliationSource`, `payments#submitChargebackEvidence` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-ORDER-DRAFTED-27 | AM-PAYMENTS-P08-3 | [BE] OrderService: listPaymentOrderFinancial | 1 | Deep Khanvilkar | OrderService | MIG-ORDERS PLATFORM-KERNEL SVC-IDENTITY-GUESTAUTH-2 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-18 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-26 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-PAYMENTS-14 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 SVC-WALLET-RETAIL-1 VM-LEDGER-SETTLEMENT-1 VM-LEDGER-SETTLEMENT-2 VM-MIG-LEDGER VM-ORDER-REFUND-1 | Operations: listPaymentOrderFinancial. Spec: contracts (orders) at the release tag, served by ADAM. Built for Payments · Venue Management 3 of 3; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listPaymentOrderFinancial` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | VM-ADM-602 | AM-PAYMENTS-P08-3 | [BE] ADM-602 B2B Credit Account & Limit Manager | 3 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-21 | Manage payment credit facilities granted to authorized B2B customers, resellers, corporate clients or partners. This is not the general B2B customer profile. The B2B/CRM module remains authoritative for the customer/account itself. Board 5 owns the payment-credit capability. Module: Commercial. App: Venue Management. Done when `ADM-602` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-604 | AM-PAYMENTS-P08-3 | [BE] ADM-604 Stored Value, Gift Card & Voucher Tender Controls | 3 | Sanket Keluskar |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-6 SVC-WALLET-WALLET-13 | Manage how stored-value instruments participate in payment without duplicating the Wallet or Voucher modules. Module: Commercial. App: Venue Management. Done when `ADM-604` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-608 | AM-PAYMENTS-P08-3 | [BE] ADM-608 Mixed Tender Simulator, Credit Exposure & AI Advisor | 2 | New full-stack developer 1 |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-17 SVC-ORDER-PAYMENTS-21 | Allow administrators to test complex tender combinations before activating rules. Module: Commercial. App: Venue Management. Done when `ADM-608` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-621 | AM-PAYMENTS-P08-3 | [BE] ADM-621 Transaction Matching & Reconciliation Engine | 2 | Chinmay Patkar |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-22 | Automatically match TICVAI payment transactions against provider/acquirer records. Module: Commercial. App: Venue Management. Done when `ADM-621` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-625 | AM-PAYMENTS-P08-3 | [BE] ADM-625 Merchant Account & Settlement Calendar Manager | 2 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-21 | Manage operational settlement expectations across providers, merchant accounts and legal entities. Module: Commercial. App: Venue Management. Done when `ADM-625` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-629 | AM-PAYMENTS-P08-3 | [BE] ADM-629 Payment Risk & Fraud Command Center | 3 | Pallavi Sawant |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-13 | Provide real-time operational visibility over fraud, suspicious transactions, payment risk and chargebacks across the TICVAI ecosystem. Module: Commercial. App: Venue Management. Done when `ADM-629` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-631 | AM-PAYMENTS-P08-3 | [BE] ADM-631 Velocity, Behavioral & Transaction Risk Controls | 2 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-11 | Manage high-frequency and abnormal payment activity. Module: Commercial. App: Venue Management. Waits for its definition: ADM-631's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-631` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-632 | AM-PAYMENTS-P08-3 | [BE] ADM-632 Risk Lists, Signals & Payment Control Center | 2 | Sanket Keluskar |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-11 | Provide centralized management of approved payment risk lists and signals. Module: Commercial. App: Venue Management. Waits for its definition: ADM-632's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-632` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-635 | AM-PAYMENTS-P08-3 | [BE] ADM-635 Chargeback Evidence & Representment Workspace | 2 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-ORDER-ORDERS-27 SVC-ORDER-PAYMENTS-22 | Help Payment Operations collect, review and submit the evidence needed to respond to disputes. This is particularly important for TICVAI because ticketing transactions generate strong operational evidence. Module: Commercial. App: Venue Management. Waits for its definition: ADM-635's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-635` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-636 | AM-PAYMENTS-P08-3 | [BE] ADM-636 Payment Performance & Conversion Analytics | 2 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-13 | Provide comprehensive analytics across the complete Payment & Payment Orchestration module. This screen is not only fraud analytics. It provides payment-business performance intelligence. Module: Commercial. App: Venue Management. Done when `ADM-636` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-600 | AM-PAYMENTS-P08-3 | [BE] ADM-600 Mixed Tender Rule & Combination Builder | 2 | New full-stack developer 2 |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-16 SVC-ORDER-PAYMENTS-6 | Define which payment methods may be combined within a single transaction. Module: Commercial. App: Venue Management. Done when `ADM-600` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-605 | AM-PAYMENTS-P08-3 | [BE] ADM-605 Advanced Payment Eligibility, Sequence & Restriction Rules | 2 | Pallavi Sawant |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-16 SVC-ORDER-PAYMENTS-6 | Provide advanced transaction-level payment rules beyond the general method availability configured in Board 1. Module: Commercial. App: Venue Management. Done when `ADM-605` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-620 | AM-PAYMENTS-P08-3 | [BE] ADM-620 Reconciliation Source & Import Manager | 2 | Sanket Keluskar |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-22 SVC-ORDER-PAYMENTS-3 VM-LEDGER-SETTLEMENT-1 | Manage all sources used to compare TICVAI payment records with external financial processing records. Module: Commercial. App: Venue Management. Waits for its definition: ADM-620's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-620` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-624 | AM-PAYMENTS-P08-3 | [BE] ADM-624 Fees, Commission, FX & Settlement Economics | 3 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-ORDER-PAYMENTS-16 | Provide visibility into the financial deductions and differences between gross payment value and net settlement. Module: Commercial. App: Venue Management. Done when `ADM-624` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
11 | 3 | SVC-AI-RISK-2 | AM-PAYMENTS-P08-3 | [BE] AiService: backtestRiskStrategy | 2 | Tanmay Dukhande | AiService | MIG-AI-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: backtestRiskStrategy. Spec: contracts (ai) at the release tag, served by ADAM. Built for Payments · Venue Management 3 of 3; additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#backtestRiskStrategy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | VM-ADM-638 | AM-PAYMENTS-P08-3 | [BE] ADM-638 Payment Executive Intelligence, Risk Simulator & AI Advisor | 3 | New full-stack developer 2 |  | SETUP-CLIENTS SVC-AI-RISK-2 SVC-ORDER-PAYMENTS-13 SVC-ORDER-PAYMENTS-17 | Provide executive-level intelligence and a safe simulation environment for payment, fraud and risk strategies. Module: Commercial. App: Venue Management. Done when `ADM-638` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
10 | 3 | MIG-WALLET-6 | AM-WALLET-CASHLESS-P08 | [DB] Forward migration V1194__wallet.sql: wallet for Wallet & Cashless · Venue Management 1 of 7 (1 tables) | 1 | Hrushikant Patkar | WalletService | MIG-BASELINE MIG-WALLET VM-MIG-WALLET | Tables: wallet.credit_eligibility. Source DDL: backend/tenant/010-wallet.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `wallet.credit_eligibility` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-WALLET-CARD-2 | AM-WALLET-CASHLESS-P08 | [BE] WalletService: adjustGameCard | 3 | Pallavi Sawant | WalletService | MIG-GAMES MIG-PLATFORM MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: adjustGameCard. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Wallet & Cashless · Venue Management 1 of 7; additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#adjustGameCard` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-WALLET-GIFTCARD-2 | AM-WALLET-CASHLESS-P08 | [BE] WalletService: blockGiftCard | 1 | Tanmay Dukhande | WalletService | MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: blockGiftCard. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Wallet & Cashless · Venue Management 1 of 7; additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#blockGiftCard` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-WALLET-RETAIL-3 | AM-WALLET-CASHLESS-P08 | [BE] WalletService: closeWallet, reinstateWallet, suspendWallet | 5 | New full-stack developer 1 | WalletService | MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: closeWallet, reinstateWallet, suspendWallet. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Wallet & Cashless · Venue Management 1 of 7; additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#closeWallet`, `wallet#reinstateWallet`, `wallet#suspendWallet` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-WALLET-WALLET-16 | AM-WALLET-CASHLESS-P08 | [BE] WalletService: adjustWallet, createCreditType, createWalletType, getWalletLiability | 8 | Surendra | WalletService | MIG-PLATFORM MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: adjustWallet, createCreditType, createWalletType, getWalletLiability. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Wallet & Cashless · Venue Management 1 of 7; additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#adjustWallet`, `wallet#createCreditType`, `wallet#createWalletType`, `wallet#getWalletLiability` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-WALLET-WALLET-17 | AM-WALLET-CASHLESS-P08 | [BE] WalletService: listWalletHolds, setCreditEligibilityRules, updateCreditType | 5 | Tanmay Dukhande | WalletService | MIG-WALLET MIG-WALLET-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listWalletHolds, setCreditEligibilityRules, updateCreditType. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Wallet & Cashless · Venue Management 1 of 7; additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#listWalletHolds`, `wallet#setCreditEligibilityRules`, `wallet#updateCreditType` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | VM-ADM-612 | AM-WALLET-CASHLESS-P08 | [BE] ADM-612 Refund Allocation & Original Tender Manager | 2 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-WALLET-WALLET-2 | Determine where the refunded value must be returned. This screen becomes particularly important for Board 5 mixed-tender transactions. Module: Commercial. App: Venue Management. Waits for its definition: ADM-612's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-612` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
10 | 3 | MIG-WALLET-7 | AM-WALLET-CASHLESS-P08-2 | [DB] Forward migration V1197__wallet.sql: wallet for Wallet & Cashless · Venue Management 2 of 7 (3 tables) | 2 | Hrushikant Patkar | WalletService | MIG-BASELINE MIG-WALLET VM-MIG-WALLET | Tables: wallet.credential, wallet.shared_wallet, wallet.shared_wallet_member. Source DDL: backend/tenant/010-wallet.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `wallet.credential`, `wallet.shared_wallet`, `wallet.shared_wallet_member` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-WALLET-WALLET-18 | AM-WALLET-CASHLESS-P08-2 | [BE] WalletService: linkWalletCredential, listSharedWallets, setSharedWalletMembers, updateWalletType | 8 | Hrushikant Patkar | WalletService | MIG-WALLET MIG-WALLET-7 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: linkWalletCredential, listSharedWallets, setSharedWalletMembers, updateWalletType. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Wallet & Cashless · Venue Management 2 of 7; additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#linkWalletCredential`, `wallet#listSharedWallets`, `wallet#setSharedWalletMembers`, `wallet#updateWalletType` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-WALLET-WALLET-19 | AM-WALLET-CASHLESS-P08-3 | [BE] WalletService: createSharedWallet, getWalletReconciliation, reverseWalletFunding, setCreditConsumptionPolicy | 8 | Tanmay Dukhande | WalletService | MIG-WALLET MIG-WALLET-7 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-WALLET | Operations: createSharedWallet, getWalletReconciliation, reverseWalletFunding, setCreditConsumptionPolicy. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Wallet & Cashless · Venue Management 3 of 7; additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#createSharedWallet`, `wallet#getWalletReconciliation`, `wallet#reverseWalletFunding`, `wallet#setCreditConsumptionPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-WALLET-WALLET-20 | AM-WALLET-CASHLESS-P08-3 | [BE] WalletService: simulateCreditConsumption | 2 | Deep Khanvilkar | WalletService | MIG-WALLET MIG-WALLET-6 PLATFORM-KERNEL SVC-WALLET-CARD-1 SVC-WALLET-CARD-2 SVC-WALLET-RETAIL-1 SVC-WALLET-RETAIL-2 SVC-WALLET-RETAIL-3 SVC-WALLET-WALLET-1 SVC-WALLET-WALLET-16 SVC-WALLET-WALLET-17 SVC-WALLET-WALLET-19 SVC-WALLET-WALLET-2 VM-WALLET-WALLET-1 | Operations: simulateCreditConsumption. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Wallet & Cashless · Venue Management 3 of 7; additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#simulateCreditConsumption` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 3 | MIG-WALLET-8 | AM-WALLET-CASHLESS-P08-4 | [DB] Forward migration V1212__wallet.sql: wallet for Wallet & Cashless · Venue Management 4 of 7 (2 tables) | 2 | Hrushikant Patkar | WalletService | MIG-BASELINE MIG-WALLET VM-MIG-WALLET | Tables: wallet.gift_card_product, wallet.voucher_type. Source DDL: backend/tenant/010-wallet.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `wallet.gift_card_product`, `wallet.voucher_type` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-WALLET-GIFTCARD-3 | AM-WALLET-CASHLESS-P08-4 | [BE] WalletService: issueGiftCard | 2 | Deep Khanvilkar | WalletService | MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: issueGiftCard. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Wallet & Cashless · Venue Management 4 of 7; additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#issueGiftCard` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-WALLET-RETAIL-4 | AM-WALLET-CASHLESS-P08-4 | [BE] WalletService: activateGiftCard, redeemGiftCard | 3 | Surendra | WalletService | MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: activateGiftCard, redeemGiftCard. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Wallet & Cashless · Venue Management 4 of 7; additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#activateGiftCard`, `wallet#redeemGiftCard` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-WALLET-WALLET-21 | AM-WALLET-CASHLESS-P08-4 | [BE] WalletService: createVoucherType, getWalletBalance, listVoucherTypes, setGiftCardProduct | 5 | Pranay Shinde | WalletService | MIG-WALLET MIG-WALLET-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createVoucherType, getWalletBalance, listVoucherTypes, setGiftCardProduct. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Wallet & Cashless · Venue Management 4 of 7; additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#createVoucherType`, `wallet#getWalletBalance`, `wallet#listVoucherTypes`, `wallet#setGiftCardProduct` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-WALLET-WALLET-22 | AM-WALLET-CASHLESS-P08-5 | [BE] WalletService: setWalletAuthenticationPolicy | 1 | Pranay Shinde | WalletService | MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setWalletAuthenticationPolicy. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Wallet & Cashless · Venue Management 5 of 7; additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#setWalletAuthenticationPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 3 | MIG-WALLET-9 | AM-WALLET-CASHLESS-P08-6 | [DB] Forward migration V1213__wallet.sql: wallet for Wallet & Cashless · Venue Management 6 of 7 (1 tables) | 1 | Hrushikant Patkar | WalletService | MIG-BASELINE MIG-WALLET VM-MIG-WALLET | Tables: wallet.restriction. Source DDL: backend/tenant/010-wallet.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `wallet.restriction` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-WALLET-WALLET-23 | AM-WALLET-CASHLESS-P08-6 | [BE] WalletService: raiseWalletDispute, setWalletRestriction, setWalletTransferRules | 5 | Tanmay Dukhande | WalletService | MIG-WALLET MIG-WALLET-3 MIG-WALLET-9 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: raiseWalletDispute, setWalletRestriction, setWalletTransferRules. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Wallet & Cashless · Venue Management 6 of 7; additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#raiseWalletDispute`, `wallet#setWalletRestriction`, `wallet#setWalletTransferRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-WALLET-WALLET-24 | AM-WALLET-CASHLESS-P08-7 | [BE] WalletService: getWalletMovementSummary, getWalletPreCloseChecks, setWalletAccountingMapping, setWalletReconciliationSources | 5 | New full-stack developer 2 | WalletService | MIG-WALLET PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getWalletMovementSummary, getWalletPreCloseChecks, setWalletAccountingMapping, setWalletReconciliationSources. Spec: contracts (wallet) at the release tag, served by ADAM. Built for Wallet & Cashless · Venue Management 7 of 7; additive to WalletService, whose first-release owner (Pranay Shinde) reviews. Done when `wallet#getWalletMovementSummary`, `wallet#getWalletPreCloseChecks`, `wallet#setWalletAccountingMapping`, `wallet#setWalletReconciliationSources` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | MIG-ACCESS-9 | AM-ADMISSION-ACCESS-P07 | [DB] Forward migration V1233__access.sql: access for Admission & Access · Scanner (2 tables) | 2 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-BASELINE MIG-PLATFORM VM-MIG-ACCESS | Tables: access.podium, access.podium_shift. Source DDL: backend/tenant/010-access.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `access.podium`, `access.podium_shift` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
16 | 3 | SVC-ACCESS-ACCESS-15 | AM-ADMISSION-ACCESS-P07 | [BE] AccessService: endPodiumShift, startPodiumShift | 3 | Deep Khanvilkar | AccessService | MIG-ACCESS-9 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: endPodiumShift, startPodiumShift. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Scanner; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#endPodiumShift`, `access#startPodiumShift` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | ACC-RULE-EVAL | AM-ADMISSION-ACCESS-P07 | [BE] One admission rule format, two evaluators: .NET and TypeScript proven equal by shared test vectors | 8 | Hrushikant Patkar |  | OFFLINE-BUNDLE | One admission rule format, two evaluators: .NET and TypeScript proven equal by shared test vectors. Builds: `operation access#validateAccess`, `operation access#getOfflinePackage`, `table access.dynamic_policy`, `adr ADR-0068`. ADR-0068 (accepted 1 October; B1, with the scanner): the closed JSON rule format (AdmissionRule, AdmissionCondition; conditionRule on access.dynamic_policy versions) evaluated by validateAccess online in .NET and by the gate offline in TypeScript (packages/offline-core) against the same active policy version that getOfflinePackage carries; each scan_event records the policy version that decided it. Done when: one set of test vectors runs in CI against both evaluators and they agree on every vector, a rule the format cannot express is refused when the policy is saved, and an offline scan and an online scan of the same credential under the same policy version give the same decision.
15 | 3 | MIG-ACCESS-11 | AM-ADMISSION-ACCESS-P08 | [DB] Forward migration V1152__access.sql: access for Admission & Access · Venue Management 1 of 8 (10 tables) | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-BASELINE VM-MIG-ACCESS | Tables: access.access_map, access.attraction_access, access.configuration_version, access.consumption_rule, access.gate_lane, access.group_admission_rule, access.hardware_deployment, access.journey_sequence_rule, access.offline_policy, access.operating_calendar_entry. Source DDL: backend/tenant/010-access.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `access.access_map`, `access.attraction_access`, `access.configuration_version`, `access.consumption_rule`, `access.gate_lane`, `access.group_admission_rule`, `access.hardware_deployment`, `access.journey_sequence_rule` and 2 more runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
16 | 3 | SVC-ACCESS-ACCESS-18 | AM-ADMISSION-ACCESS-P08 | [BE] AccessService: deleteJourneySequenceRule, deleteOperatingCalendarEntry, listAccess, listAccessRule | 5 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-11 MIG-SYNC PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: deleteJourneySequenceRule, deleteOperatingCalendarEntry, listAccess, listAccessRule. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 1 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#deleteJourneySequenceRule`, `access#deleteOperatingCalendarEntry`, `access#listAccess`, `access#listAccessRule` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-20 | AM-ADMISSION-ACCESS-P08 | [BE] AccessService: listOperatingCalendarSpecial, publishRuleConflictCheck, publishTopologyValidation, rollbackConfigurationVersion | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-11 MIG-ACCESS-2 MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listOperatingCalendarSpecial, publishRuleConflictCheck, publishTopologyValidation, rollbackConfigurationVersion. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 1 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listOperatingCalendarSpecial`, `access#publishRuleConflictCheck`, `access#publishTopologyValidation`, `access#rollbackConfigurationVersion` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-21 | AM-ADMISSION-ACCESS-P08 | [BE] AccessService: setAccessAreaZone, setAccessGraphicalMap, setAttractionAccess, setEntitlementConsumption | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-11 MIG-ACCESS-2 MIG-VENUEMAP PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setAccessAreaZone, setAccessGraphicalMap, setAttractionAccess, setEntitlementConsumption. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 1 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#setAccessAreaZone`, `access#setAccessGraphicalMap`, `access#setAttractionAccess`, `access#setEntitlementConsumption` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-22 | AM-ADMISSION-ACCESS-P08 | [BE] AccessService: setGateLane, setJourneySequenceRule, setOperatingCalendarEntry | 5 | Deep Khanvilkar | AccessService | MIG-ACCESS MIG-ACCESS-11 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setGateLane, setJourneySequenceRule, setOperatingCalendarEntry. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 1 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#setGateLane`, `access#setJourneySequenceRule`, `access#setOperatingCalendarEntry` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | MIG-ACCESS-12 | AM-ADMISSION-ACCESS-P08-2 | [DB] Forward migration V1234__access.sql: access for Admission & Access · Venue Management 2 of 8 (7 tables) | 5 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-BASELINE VM-MIG-ACCESS | Tables: access.credential_event_propagation_rule, access.credential_security_profile, access.external_credential_integration, access.media_compatibility_test, access.media_encoding_profile, access.security_alert, access.verification_method_policy. Source DDL: backend/tenant/010-access.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Source DDL after r1: backend/tenant/V0102__after_r1_20261013.sql (access.verification_method_policy: column credential_format_override); the files above are frozen at r1, so this migration, which creates those tables, carries these changes too. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `access.credential_event_propagation_rule`, `access.credential_security_profile`, `access.external_credential_integration`, `access.media_compatibility_test`, `access.media_encoding_profile`, `access.security_alert`, `access.verification_method_policy` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
16 | 3 | SVC-ACCESS-ACCESS-27 | AM-ADMISSION-ACCESS-P08-2 | [BE] AccessService: listVirtualCredentialMedia, publishMediaCompatibilityTesting, reviewFaceReenrolment, setCredentialEventPropagationRule | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-11 MIG-ACCESS-12 MIG-CATALOGUE MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-ACCESS | Operations: listVirtualCredentialMedia, publishMediaCompatibilityTesting, reviewFaceReenrolment, setCredentialEventPropagationRule. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 2 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listVirtualCredentialMedia`, `access#publishMediaCompatibilityTesting`, `access#reviewFaceReenrolment`, `access#setCredentialEventPropagationRule` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-28 | AM-ADMISSION-ACCESS-P08-2 | [BE] AccessService: setDynamicSecurityProfile, setEmbeddedEntitlementPayload, setGateOfflinePolicy, setHotelWalletExternal | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-11 MIG-ACCESS-12 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setDynamicSecurityProfile, setEmbeddedEntitlementPayload, setGateOfflinePolicy, setHotelWalletExternal. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 2 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#setDynamicSecurityProfile`, `access#setEmbeddedEntitlementPayload`, `access#setGateOfflinePolicy`, `access#setHotelWalletExternal` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-29 | AM-ADMISSION-ACCESS-P08-2 | [BE] AccessService: setMediaIssuanceEncoding, setMediaTypeTechnology, setRfidNfc, setVerificationMethodPolicy | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-12 MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCESS | Operations: setMediaIssuanceEncoding, setMediaTypeTechnology, setRfidNfc, setVerificationMethodPolicy. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 2 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#setMediaIssuanceEncoding`, `access#setMediaTypeTechnology`, `access#setRfidNfc`, `access#setVerificationMethodPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-DEVICES-7 | AM-ADMISSION-ACCESS-P08-3 | [BE] TenancyService: approveDevice | 2 | Deep Khanvilkar | TenancyService | MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: approveDevice. Spec: contracts (tenancy) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 3 of 8; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `tenancy#approveDevice` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-32 | AM-ADMISSION-ACCESS-P08-3 | [BE] AccessService: listOfflineEdge, listOfflineEntitlementUsage, listPhysicalDeviceRegistration, placeAccessDevice | 8 | Tanmay Dukhande | AccessService | MIG-ACCESS MIG-ACCESS-11 MIG-ACCESS-2 MIG-ACCESS-8 MIG-CATALOGUE MIG-SYNC PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listOfflineEdge, listOfflineEntitlementUsage, listPhysicalDeviceRegistration, placeAccessDevice. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 3 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listOfflineEdge`, `access#listOfflineEntitlementUsage`, `access#listPhysicalDeviceRegistration`, `access#placeAccessDevice` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-33 | AM-ADMISSION-ACCESS-P08-3 | [BE] AccessService: publishHardwareDeployment, setDeviceSoftwareContent, setEdgeNodeLocal, setHandheldMobileAccess | 8 | Pranay Shinde | AccessService | MIG-ACCESS MIG-ACCESS-11 MIG-ACCESS-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: publishHardwareDeployment, setDeviceSoftwareContent, setEdgeNodeLocal, setHandheldMobileAccess. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 3 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#publishHardwareDeployment`, `access#setDeviceSoftwareContent`, `access#setEdgeNodeLocal`, `access#setHandheldMobileAccess` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-34 | AM-ADMISSION-ACCESS-P08-3 | [BE] AccessService: setHardwareModel, setReaderScannerPeripheral, setTurnstileLaneBehavior, setValidationOutcomeGuest | 8 | Tanmay Dukhande | AccessService | MIG-ACCESS MIG-ACCESS-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setHardwareModel, setReaderScannerPeripheral, setTurnstileLaneBehavior, setValidationOutcomeGuest. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 3 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#setHardwareModel`, `access#setReaderScannerPeripheral`, `access#setTurnstileLaneBehavior`, `access#setValidationOutcomeGuest` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-35 | AM-ADMISSION-ACCESS-P08-3 | [BE] AccessService: simulateBiometricConfiguration, updateAccessDevicePlacement | 3 | Deep Khanvilkar | AccessService | MIG-ACCESS MIG-ACCESS-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: simulateBiometricConfiguration, updateAccessDevicePlacement. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 3 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#simulateBiometricConfiguration`, `access#updateAccessDevicePlacement` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-30 | AM-ADMISSION-ACCESS-P08-3 | [BE] AccessService: listBiometric, listBiometricValidationGate, listConnectivityFailureDegraded, listDeviceGate | 5 | Deep Khanvilkar | AccessService | MIG-ACCESS MIG-ACCESS-11 MIG-ACCESS-8 PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-12 SVC-ACCESS-ACCESS-20 SVC-ACCESS-ACCESS-27 SVC-ACCESS-ACCESS-28 SVC-ACCESS-ACCESS-32 SVC-ACCESS-ACCESS-33 SVC-ACCESS-ACCESS-34 SVC-ACCESS-ACCESS-35 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 | Operations: listBiometric, listBiometricValidationGate, listConnectivityFailureDegraded, listDeviceGate. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 3 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listBiometric`, `access#listBiometricValidationGate`, `access#listConnectivityFailureDegraded`, `access#listDeviceGate` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-31 | AM-ADMISSION-ACCESS-P08-3 | [BE] AccessService: listDeviceTypeHardware, listEdgePackageData, listHardwareCompatibilityHealth, listOfflineCredentialRevocation | 3 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-11 MIG-ACCESS-8 PLATFORM-KERNEL SVC-ACCESS-ACCESS-20 SVC-ACCESS-ACCESS-28 SVC-ACCESS-ACCESS-32 SVC-ACCESS-ACCESS-33 SVC-ACCESS-ACCESS-34 SVC-ACCESS-ACCESS-35 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-3 VM-ACCESS-ACCESS-1 VM-MIG-ACCESS | Operations: listDeviceTypeHardware, listEdgePackageData, listHardwareCompatibilityHealth, listOfflineCredentialRevocation. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 3 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listDeviceTypeHardware`, `access#listEdgePackageData`, `access#listHardwareCompatibilityHealth`, `access#listOfflineCredentialRevocation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | MIG-ACCESS-14 | AM-ADMISSION-ACCESS-P08-4 | [DB] Forward migration V1215__access.sql: access for Admission & Access · Venue Management 4 of 8 (5 tables) | 3 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-BASELINE VM-MIG-ACCESS | Tables: access.fast_pass_profile, access.identity_lock, access.journey_profile, access.reason_code, access.security_investigation. Source DDL: backend/tenant/010-access.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `access.fast_pass_profile`, `access.identity_lock`, `access.journey_profile`, `access.reason_code`, `access.security_investigation` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
16 | 3 | SVC-ACCESS-ACCESS-36 | AM-ADMISSION-ACCESS-P08-4 | [BE] AccessService: deletePodium, deleteReasonCode, listCredentialDisableBlacklist, listEdgeSecurityDeployment | 5 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-11 MIG-ACCESS-12 MIG-ACCESS-14 MIG-ACCESS-9 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: deletePodium, deleteReasonCode, listCredentialDisableBlacklist, listEdgeSecurityDeployment. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 4 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#deletePodium`, `access#deleteReasonCode`, `access#listCredentialDisableBlacklist`, `access#listEdgeSecurityDeployment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-40 | AM-ADMISSION-ACCESS-P08-4 | [BE] AccessService: listValidationExceptionReason, lockIdentity, releaseIdentityLock, setFastPassProfile | 5 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-14 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listValidationExceptionReason, lockIdentity, releaseIdentityLock, setFastPassProfile. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 4 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listValidationExceptionReason`, `access#lockIdentity`, `access#releaseIdentityLock`, `access#setFastPassProfile` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-41 | AM-ADMISSION-ACCESS-P08-4 | [BE] AccessService: setGroupAdmissionProfile, setGuestCompanionEligibility, setJourneyProfile, setPodium | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-11 MIG-ACCESS-14 MIG-ACCESS-3 MIG-ACCESS-9 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setGroupAdmissionProfile, setGuestCompanionEligibility, setJourneyProfile, setPodium. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 4 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#setGroupAdmissionProfile`, `access#setGuestCompanionEligibility`, `access#setJourneyProfile`, `access#setPodium` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-19 | AM-ADMISSION-ACCESS-P08 | [BE] AccessService: listAccessValidityTime, listAntiPassbackJourney, listEntitlementConsumption, listGroupAdmissionQuantity | 3 | Deep Khanvilkar | AccessService | MIG-ACCESS MIG-ACCESS-11 MIG-CATALOGUE PLATFORM-KERNEL SVC-ACCESS-ACCESS-18 SVC-ACCESS-ACCESS-21 SVC-ACCESS-ACCESS-22 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-41 SVC-ACCESS-ACCESS-7 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-CATALOGUE-ENTITLEMENT-1 SVC-CATALOGUE-ENTITLEMENT-5 | Operations: listAccessValidityTime, listAntiPassbackJourney, listEntitlementConsumption, listGroupAdmissionQuantity. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 1 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listAccessValidityTime`, `access#listAntiPassbackJourney`, `access#listEntitlementConsumption`, `access#listGroupAdmissionQuantity` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-42 | AM-ADMISSION-ACCESS-P08-4 | [BE] AccessService: setReasonCode, simulateGuestJourney, simulateOfflineResilienceTesting, updateSecurityAlert | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-12 MIG-ACCESS-14 MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setReasonCode, simulateGuestJourney, simulateOfflineResilienceTesting, updateSecurityAlert. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 4 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#setReasonCode`, `access#simulateGuestJourney`, `access#simulateOfflineResilienceTesting`, `access#updateSecurityAlert` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | MIG-ACCESS-15 | AM-ADMISSION-ACCESS-P08-5 | [DB] Forward migration V1216__access.sql: access for Admission & Access · Venue Management 5 of 8 (5 tables) | 3 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-BASELINE VM-MIG-ACCESS | Tables: access.access_attribute, access.credential_sharing_case, access.fraud_rule, access.policy_evaluation_setting, access.risk_scoring_config. Source DDL: backend/tenant/010-access.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `access.access_attribute`, `access.credential_sharing_case`, `access.fraud_rule`, `access.policy_evaluation_setting`, `access.risk_scoring_config` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-TENANCY-ACCREDITATION-7 | AM-ADMISSION-ACCESS-P08-5 | [BE] TenancyService: setAccessProfile | 2 | Deep Khanvilkar | TenancyService | MIG-ACCREDITATION-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setAccessProfile. Spec: contracts (accreditation) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 5 of 8; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `accreditation#setAccessProfile` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-47 | AM-ADMISSION-ACCESS-P08-5 | [BE] AccessService: rollbackAccessPolicy, setAccessAttributeCatalog, setContextTimeEvent, setFraudDetectionRule | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-15 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCESS | Operations: rollbackAccessPolicy, setAccessAttributeCatalog, setContextTimeEvent, setFraudDetectionRule. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 5 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#rollbackAccessPolicy`, `access#setAccessAttributeCatalog`, `access#setContextTimeEvent`, `access#setFraudDetectionRule` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-48 | AM-ADMISSION-ACCESS-P08-5 | [BE] AccessService: setOperationalIncidentException, setPolicyEvaluationSetting, setPolicyScopeHierarchy, setRelationshipFraudRule | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-15 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCESS | Operations: setOperationalIncidentException, setPolicyEvaluationSetting, setPolicyScopeHierarchy, setRelationshipFraudRule. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 5 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#setOperationalIncidentException`, `access#setPolicyEvaluationSetting`, `access#setPolicyScopeHierarchy`, `access#setRelationshipFraudRule` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-49 | AM-ADMISSION-ACCESS-P08-5 | [BE] AccessService: setSecurityInvestigationEvidence, setVisualDynamicPolicy, simulatePolicyConflictImpact | 5 | Deep Khanvilkar | AccessService | MIG-ACCESS MIG-ACCESS-14 MIG-ACCESS-15 MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCESS | Operations: setSecurityInvestigationEvidence, setVisualDynamicPolicy, simulatePolicyConflictImpact. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 5 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#setSecurityInvestigationEvidence`, `access#setVisualDynamicPolicy`, `access#simulatePolicyConflictImpact` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-45 | AM-ADMISSION-ACCESS-P08-5 | [BE] AccessService: listFraudDetectionRule, listIdentityMembershipAccreditation, listPolicyEvaluationArchitecture, listPolicyScopeHierarchy | 2 | Hrushikant Patkar | AccessService | MIG-ACCESS-15 PLATFORM-KERNEL SVC-ACCESS-ACCESS-47 SVC-ACCESS-ACCESS-48 SVC-ACCESS-ACCESS-49 VM-MIG-ACCESS | Operations: listFraudDetectionRule, listIdentityMembershipAccreditation, listPolicyEvaluationArchitecture, listPolicyScopeHierarchy. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 5 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listFraudDetectionRule`, `access#listIdentityMembershipAccreditation`, `access#listPolicyEvaluationArchitecture`, `access#listPolicyScopeHierarchy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | MIG-ACCESS-16 | AM-ADMISSION-ACCESS-P08-6 | [DB] Forward migration V1217__access.sql: access for Admission & Access · Venue Management 6 of 8 (4 tables) | 3 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-BASELINE VM-MIG-ACCESS | Tables: access.credential_exception, access.credential_issuance, access.security_playbook, access.ticket_status_transition. Source DDL: backend/tenant/010-access.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `access.credential_exception`, `access.credential_issuance`, `access.security_playbook`, `access.ticket_status_transition` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
16 | 3 | SVC-ACCESS-ACCESS-50 | AM-ADMISSION-ACCESS-P08-6 | [BE] AccessService: deleteMediaBindingRule, listAccessExecutiveInsight, listAccessMonitoring, listAccessRiskScoring | 5 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-15 MIG-ACCESS-7 MIG-CATALOGUE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: deleteMediaBindingRule, listAccessExecutiveInsight, listAccessMonitoring, listAccessRiskScoring. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 6 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#deleteMediaBindingRule`, `access#listAccessExecutiveInsight`, `access#listAccessMonitoring`, `access#listAccessRiskScoring` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-54 | AM-ADMISSION-ACCESS-P08-6 | [BE] AccessService: listVirtualTicketStatus, setMediaBindingRule, setRealTimeSecurity, setRiskScoringConfig | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-15 MIG-ACCESS-16 MIG-ACCESS-7 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCESS | Operations: listVirtualTicketStatus, setMediaBindingRule, setRealTimeSecurity, setRiskScoringConfig. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 6 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listVirtualTicketStatus`, `access#setMediaBindingRule`, `access#setRealTimeSecurity`, `access#setRiskScoringConfig` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-55 | AM-ADMISSION-ACCESS-P08-6 | [BE] AccessService: setTicketStatusTransition | 2 | Deep Khanvilkar | AccessService | MIG-ACCESS MIG-ACCESS-16 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setTicketStatusTransition. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 6 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#setTicketStatusTransition` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | MIG-ACCESS-17 | AM-ADMISSION-ACCESS-P08-7 | [DB] Forward migration V1235__access.sql: access for Admission & Access · Venue Management 7 of 8 (5 tables) | 5 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-BASELINE VM-MIG-ACCESS | Tables: access.branding_profile, access.credential_delivery, access.credential_issuance_retry_policy, access.dynamic_field, access.media_template_version. Source DDL: backend/tenant/010-access.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `access.branding_profile`, `access.credential_delivery`, `access.credential_issuance_retry_policy`, `access.dynamic_field`, `access.media_template_version` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
16 | 3 | SVC-ACCESS-ACCESS-56 | AM-ADMISSION-ACCESS-P08-7 | [BE] AccessService: approveMultiMediaPreview, getCredentialIssuanceRetryPolicy, listBrandingLocalizationTemplate, listCredential | 5 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-16 MIG-ACCESS-17 MIG-CATALOGUE MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCESS | Operations: approveMultiMediaPreview, getCredentialIssuanceRetryPolicy, listBrandingLocalizationTemplate, listCredential. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 7 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#approveMultiMediaPreview`, `access#getCredentialIssuanceRetryPolicy`, `access#listBrandingLocalizationTemplate`, `access#listCredential` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-61 | AM-ADMISSION-ACCESS-P08-7 | [BE] AccessService: listVirtualTicketArchitecture, resolveCredentialException, retryCredentialGeneration, setAppleWalletPass | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-16 MIG-ACCESS-17 MIG-IDENTITY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCESS | Operations: listVirtualTicketArchitecture, resolveCredentialException, retryCredentialGeneration, setAppleWalletPass. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 7 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listVirtualTicketArchitecture`, `access#resolveCredentialException`, `access#retryCredentialGeneration`, `access#setAppleWalletPass` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ORDER-ORDERS-17 | AM-PRICING-PROMOTIONS-P08-6 | [BE] OrderService: quoteUpgrade | 2 | Deep Khanvilkar | OrderService | MIG-ACCESS MIG-CATALOGUE MIG-ORDERS PLATFORM-KERNEL SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-61 SVC-ACCESS-VALIDATION-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-ENTITLEMENT-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-IDENTITY-GUESTAUTH-2 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-14 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-18 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 VM-ACCESS-ACCESS-1 VM-CATALOGUE-PRODUCT-1 | Operations: quoteUpgrade. Spec: contracts (orders) at the release tag, served by ADAM. Built for Pricing & Promotions · Venue Management 6 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#quoteUpgrade` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | VM-ADM-656 | AM-PRICING-PROMOTIONS-P08-6 | [BE] ADM-656 Post-Purchase & In-Journey Upgrade Manager | 3 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 SVC-CATALOGUE-RECOMMENDATIONS-2 SVC-ORDER-ORDERS-17 | Support upgrades after the initial transaction where the product and operational rules permit them. This is explicitly important because upselling should not stop at checkout. Module: Commercial. App: Venue Management. Done when `ADM-656` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | SVC-ORDER-DRAFTED-4 | AM-ORDERS-RESERVATIONS-P08 | [BE] OrderService: listOfficialResaleMarketplace, listResaleMarketplace, listResalePolicyMarketplace, listTicketResaleMarketplace | 5 | Pranay Shinde | OrderService | MIG-ACCESS MIG-CATALOGUE MIG-ORDERS MIG-ORDERS-12 PLATFORM-KERNEL SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-61 SVC-ACCESS-VALIDATION-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-ENTITLEMENT-3 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-FNB-FNB-12 SVC-IDENTITY-GUESTAUTH-2 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-14 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-DRAFTED-6 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-1 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-18 SVC-ORDER-ORDERS-23 SVC-ORDER-ORDERS-24 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 VM-ACCESS-ACCESS-1 VM-CATALOGUE-EVENT-1 VM-CATALOGUE-PRODUCT-1 | Operations: listOfficialResaleMarketplace, listResaleMarketplace, listResalePolicyMarketplace, listTicketResaleMarketplace. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 1 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listOfficialResaleMarketplace`, `orders#listResaleMarketplace`, `orders#listResalePolicyMarketplace`, `orders#listTicketResaleMarketplace` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | VM-ADM-278 | AM-ORDERS-RESERVATIONS-P08 | [BE] ADM-278 Resale Marketplace Command Center | 5 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-4 SVC-ORDER-ORDERS-22 | Provide administrators with a centralized operational view of the TICVAI resale marketplace. Module: Commercial. App: Venue Management. Done when `ADM-278` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | SVC-ORDER-DRAFTED-7 | AM-ORDERS-RESERVATIONS-P08-2 | [BE] OrderService: listCredentialRevocationRegeneration, listFeeSellerProceed, listListingLifecycleExpiry, listResale | 3 | Deep Khanvilkar | OrderService | MIG-ACCESS MIG-ORDERS MIG-ORDERS-12 PLATFORM-KERNEL SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-61 SVC-ACCESS-VALIDATION-2 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-ENTITLEMENT-3 SVC-IDENTITY-GUESTAUTH-2 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-14 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-DRAFTED-6 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-1 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-13 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-18 SVC-ORDER-ORDERS-2 SVC-ORDER-ORDERS-23 SVC-ORDER-ORDERS-24 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-26 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-PAYMENTS-14 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 SVC-WALLET-RETAIL-1 VM-ACCESS-ACCESS-1 VM-ORDER-REFUND-1 | Operations: listCredentialRevocationRegeneration, listFeeSellerProceed, listListingLifecycleExpiry, listResale. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 2 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listCredentialRevocationRegeneration`, `orders#listFeeSellerProceed`, `orders#listListingLifecycleExpiry`, `orders#listResale` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-ORDER-DRAFTED-8 | AM-ORDERS-RESERVATIONS-P08-2 | [BE] OrderService: listResale2, listResaleFeeCommission, listResaleFraudDuplicate, listResaleInventoryAvailability | 3 | Tanmay Dukhande | OrderService | MIG-ACCESS MIG-CATALOGUE MIG-ORDERS MIG-ORDERS-12 PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-12 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-61 SVC-ACCESS-VALIDATION-2 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-ENTITLEMENT-3 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-FNB-FNB-12 SVC-IDENTITY-GUESTAUTH-2 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-14 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-DRAFTED-6 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-1 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-18 SVC-ORDER-ORDERS-23 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-26 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-PAYMENTS-14 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 SVC-WALLET-RETAIL-1 VM-ACCESS-ACCESS-1 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 VM-CATALOGUE-CAPACITY-1 VM-CATALOGUE-CAPACITY-2 VM-CATALOGUE-EVENT-1 VM-CATALOGUE-LEASE-1 VM-ORDER-REFUND-1 | Operations: listResale2, listResaleFeeCommission, listResaleFraudDuplicate, listResaleInventoryAvailability. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 2 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listResale2`, `orders#listResaleFeeCommission`, `orders#listResaleFraudDuplicate`, `orders#listResaleInventoryAvailability` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | VM-ADM-280 | AM-ORDERS-RESERVATIONS-P08-2 | [BE] ADM-280 Resale Policy & Marketplace Settings | 5 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-4 SVC-ORDER-ORDERS-22 SVC-ORDER-ORDERS-24 | Configure the overall business policies governing a resale marketplace. Module: Commercial. App: Venue Management. Done when `ADM-280` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-283 | AM-ORDERS-RESERVATIONS-P08-2 | [BE] ADM-283 Resale Fees, Commission & Seller Proceeds | 3 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-7 SVC-ORDER-DRAFTED-8 SVC-ORDER-ORDERS-23 | Configure the commercial model of the resale marketplace. Module: Commercial. App: Venue Management. Done when `ADM-283` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-285 | AM-ORDERS-RESERVATIONS-P08-2 | [BE] ADM-285 Resale Inventory & Availability Management | 2 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-8 | Maintain an accurate, synchronized view of tickets currently available through resale. Module: Commercial. App: Venue Management. Waits for its definition: ADM-285's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-285` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-286 | AM-ORDERS-RESERVATIONS-P08-2 | [BE] ADM-286 Listing Lifecycle, Expiry & Cancellation | 2 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-7 | Control the full lifecycle of a resale listing from creation until sale, withdrawal or expiry. Module: Commercial. App: Venue Management. Done when `ADM-286` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-288 | AM-ORDERS-RESERVATIONS-P08-2 | [BE] ADM-288 Resale Operations Command Center | 5 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-7 SVC-ORDER-DRAFTED-8 | Provide operations teams with a real-time control center for all resale transactions after listings move into purchase/fulfillment. Module: Commercial. App: Venue Management. Done when `ADM-288` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-291 | AM-ORDERS-RESERVATIONS-P08-2 | [BE] ADM-291 Credential Revocation & Regeneration | 3 | Pranay Shinde |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-7 | Ensure the seller's old ticket credential cannot continue to provide access after resale. This is one of the most important security functions in the module. Module: Commercial. App: Venue Management. Done when `ADM-291` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-292 | AM-ORDERS-RESERVATIONS-P08-2 | [BE] ADM-292 Resale Fraud & Duplicate Sale Protection | 2 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-8 | Protect TICVAI, venues, sellers and buyers from resale abuse and fraudulent ticket activity. Module: Commercial. App: Venue Management. Done when `ADM-292` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | SVC-ORDER-DRAFTED-12 | AM-ORDERS-RESERVATIONS-P08-3 | [BE] OrderService: listUpgradeEligibilityQualification, listUpgradeFinancialTreatment, listUpgradeTimingUsage, listWhiteLabelMarketplace | 3 | Pranay Shinde | OrderService | MIG-ACCESS MIG-CATALOGUE MIG-ORDERS MIG-ORDERS-12 MIG-ORDERS-14 PLATFORM-KERNEL SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-61 SVC-ACCESS-VALIDATION-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-ENTITLEMENT-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-FNB-FNB-12 SVC-IDENTITY-GUESTAUTH-2 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-13 SVC-ORDER-DRAFTED-14 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-18 SVC-ORDER-ORDERS-24 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 VM-ACCESS-ACCESS-1 VM-CATALOGUE-PRODUCT-1 | Operations: listUpgradeEligibilityQualification, listUpgradeFinancialTreatment, listUpgradeTimingUsage, listWhiteLabelMarketplace. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 3 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listUpgradeEligibilityQualification`, `orders#listUpgradeFinancialTreatment`, `orders#listUpgradeTimingUsage`, `orders#listWhiteLabelMarketplace` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-ORDER-DRAFTED-10 | AM-ORDERS-RESERVATIONS-P08-3 | [BE] OrderService: listBuyerCheckoutInventory, listCreateListingResale, listResaleConfirmationOwnership, listResaleEligibilityTicket | 3 | Pranay Shinde | OrderService | MIG-ACCESS MIG-CATALOGUE MIG-ORDERS MIG-ORDERS-12 MIG-PII PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-12 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-61 SVC-ACCESS-VALIDATION-2 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-ENTITLEMENT-3 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-LEASE-1 SVC-CATALOGUE-LEASE-2 SVC-CATALOGUE-LEASE-3 SVC-FNB-FNB-12 SVC-IDENTITY-GUESTAUTH-1 SVC-IDENTITY-GUESTAUTH-2 SVC-IDENTITY-GUESTAUTH-3 SVC-IDENTITY-IDENTITY-4 SVC-MARKETING-MARKETING-7 SVC-ORDER-CART-1 SVC-ORDER-CART-2 SVC-ORDER-CART-3 SVC-ORDER-DRAFTED-14 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-DRAFTED-5 SVC-ORDER-DRAFTED-6 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-1 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-13 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-18 SVC-ORDER-ORDERS-2 SVC-ORDER-ORDERS-23 SVC-ORDER-ORDERS-24 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-14 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 SVC-VENUEOPS-VISITPLAN-1 VM-ACCESS-ACCESS-1 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 VM-CATALOGUE-CATALOGUE-1 VM-CATALOGUE-EVENT-1 VM-CATALOGUE-LEASE-1 | Operations: listBuyerCheckoutInventory, listCreateListingResale, listResaleConfirmationOwnership, listResaleEligibilityTicket. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 3 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listBuyerCheckoutInventory`, `orders#listCreateListingResale`, `orders#listResaleConfirmationOwnership`, `orders#listResaleEligibilityTicket` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-ORDER-DRAFTED-11 | AM-ORDERS-RESERVATIONS-P08-3 | [BE] OrderService: listResaleListingSeller, listResaleOwnership, listResaleTicketDetail, listUpgradeConversion | 5 | Pranay Shinde | OrderService | MIG-ACCESS MIG-CATALOGUE MIG-ORDERS MIG-ORDERS-12 MIG-ORDERS-14 PLATFORM-KERNEL SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-61 SVC-ACCESS-VALIDATION-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-ENTITLEMENT-3 SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-FNB-FNB-12 SVC-IDENTITY-GUESTAUTH-2 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-13 SVC-ORDER-DRAFTED-14 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-DRAFTED-6 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-1 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-18 SVC-ORDER-ORDERS-23 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-26 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-PAYMENTS-14 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 SVC-WALLET-RETAIL-1 VM-ACCESS-ACCESS-1 VM-CATALOGUE-EVENT-1 VM-CATALOGUE-PRODUCT-1 | Operations: listResaleListingSeller, listResaleOwnership, listResaleTicketDetail, listUpgradeConversion. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 3 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listResaleListingSeller`, `orders#listResaleOwnership`, `orders#listResaleTicketDetail`, `orders#listUpgradeConversion` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | VM-ADM-298 | AM-ORDERS-RESERVATIONS-P08-3 | [BE] ADM-298 My Tickets & Resale Marketplace Entry | 3 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-4 | Provide the authenticated ticket holder with a simple and secure entry point into the official resale journey. The preferred starting point should be the customer's existing: My Account → My Tickets rather than asking customers to manually enter ticket numbers or upload ticket PDFs. Module: Commercial. App: Venue Management. Done when `ADM-298` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-303 | AM-ORDERS-RESERVATIONS-P08-3 | [BE] ADM-303 Official Resale Marketplace & Buyer Discovery | 2 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-4 | Provide buyers with a trusted client-branded marketplace for discovering authentic resale inventory. Module: Commercial. App: Venue Management. Waits for its definition: ADM-303's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-303` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-307 | AM-ORDERS-RESERVATIONS-P08-3 | [BE] ADM-307 White-Label Marketplace Deployment & Experience Architecture | 3 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-12 | This is the key architecture/configuration screen It defines how each TICVAI client chooses to expose the resale marketplace to its customers. Deployment Model A — Embedded White-Label Module: Commercial. App: Venue Management. Done when `ADM-307` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-310 | AM-ORDERS-RESERVATIONS-P08-3 | [BE] ADM-310 Upgrade Eligibility & Qualification Rules | 2 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-12 | Determine whether a particular ticket/customer/transaction qualifies for a configured upgrade or conversion path. A path existing does not automatically mean every ticket can use it. Module: Commercial. App: Venue Management. Done when `ADM-310` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-311 | AM-ORDERS-RESERVATIONS-P08-3 | [BE] ADM-311 Upgrade Timing, Usage & Ticket Status Rules | 3 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-12 | Define how ticket lifecycle state affects upgrade and conversion behavior. This deserves its own screen because a ticket may already have been partially consumed. Module: Commercial. App: Venue Management. Done when `ADM-311` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-312 | AM-ORDERS-RESERVATIONS-P08-3 | [BE] ADM-312 Upgrade Financial Treatment & Price Difference Rules | 2 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-12 | Define how the financial relationship between the old and new product should be treated. Module: Commercial. App: Venue Management. Done when `ADM-312` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-296 | AM-ORDERS-RESERVATIONS-P08-3 | [BE] ADM-296 Resale Audit & Ownership History | 3 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-10 SVC-ORDER-DRAFTED-11 | Provide complete end-to-end traceability of every ticket that enters the resale ecosystem. Module: Commercial. App: Venue Management. Done when `ADM-296` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-297 | AM-ORDERS-RESERVATIONS-P08-3 | [BE] ADM-297 Resale Analytics & AI Intelligence | 3 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-7 SVC-ORDER-DRAFTED-8 | Provide management with commercial, operational and predictive intelligence about the resale marketplace. Board 3 defines how the end customer actually accesses, uses, sells through, and buys from The existing resale architecture already defines the backend marketplace configuration and transaction processing across Boards 1 and 2. Board 3 closes the missing experience layer: Board 1 — Configure Marketplace Eligibility → Policy → Listings → Pricing → Fees → Approval → Inventory Board 2 — Execute Resale Transaction Buyer → Payment → Ownership Transfer → Credentials → Fraud → Settlement → Audit Board 3 — Customer Experience Seller Journey → Buyer Journey → White-Label Portal → Client B2C Integration → Hosted Marketplace → Headless/API Module: Commercial. App: Venue Management. Done when `ADM-297` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-299 | AM-ORDERS-RESERVATIONS-P08-3 | [BE] ADM-299 Resale Eligibility & Ticket Selection | 2 | Pranay Shinde |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-10 | Explain whether the selected ticket can be resold before allowing a listing to be created. Module: Commercial. App: Venue Management. Done when `ADM-299` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-300 | AM-ORDERS-RESERVATIONS-P08-3 | [BE] ADM-300 Create Listing & Resale Price Selection | 2 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-10 | Allow an eligible seller to select a resale price within the client's approved marketplace rules. Module: Commercial. App: Venue Management. Waits for its definition: ADM-300's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-300` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-301 | AM-ORDERS-RESERVATIONS-P08-3 | [BE] ADM-301 Fees, Seller Proceeds & Listing Confirmation | 2 | Pranay Shinde |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-7 | Provide complete financial transparency before the seller commits to publishing the listing. This is essential to prevent later disputes. Module: Commercial. App: Venue Management. Waits for its definition: ADM-301's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-301` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-302 | AM-ORDERS-RESERVATIONS-P08-3 | [BE] ADM-302 My Resale Listings & Seller Dashboard | 3 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-11 | Give sellers a dedicated self-service workspace to manage their resale activity after publishing. Module: Commercial. App: Venue Management. Done when `ADM-302` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-304 | AM-ORDERS-RESERVATIONS-P08-3 | [BE] ADM-304 Resale Ticket Detail, Seat Selection & Primary-vs-Resale Experience | 2 | Pranay Shinde |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-11 | Allow customers to understand exactly what they are purchasing and distinguish resale inventory from primary inventory. Module: Commercial. App: Venue Management. Done when `ADM-304` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-305 | AM-ORDERS-RESERVATIONS-P08-3 | [BE] ADM-305 Buyer Checkout, Inventory Hold & Secure Payment | 2 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-10 | Provide a normal, secure TICVAI checkout while protecting the resale listing from simultaneous purchase. Module: Commercial. App: Venue Management. Done when `ADM-305` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-306 | AM-ORDERS-RESERVATIONS-P08-3 | [BE] ADM-306 Resale Confirmation, Ownership Transfer & Ticket Delivery | 2 | Pranay Shinde |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-10 | Provide the customer-facing completion experience after successful payment while the backend performs the secure entitlement transfer. Module: Commercial. App: Venue Management. Waits for its definition: ADM-306's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-306` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-308 | AM-ORDERS-RESERVATIONS-P08-3 | [BE] ADM-308 Upgrade & Conversion Command Center | 5 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-ORDER-DRAFTED-11 | Provide administrators and operations teams with one centralized view of all ticket upgrade, exchange and conversion configurations and operational activity. Module: Commercial. App: Venue Management. Done when `ADM-308` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-652 | AM-ORDERS-RESERVATIONS-P08-5 | [BE] ADM-652 Upgrade Price Difference & Value Proposition Manager | 3 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 SVC-ORDER-ORDERS-17 | Configure how TICVAI calculates and communicates the commercial difference between the current product and the recommended upgrade. The Recommendation Engine should not become the authoritative pricing engine. It should consume the authoritative price difference from Pricing/Promotion services. Module: Commercial. App: Venue Management. Done when `ADM-652` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-653 | AM-ORDERS-RESERVATIONS-P08-5 | [BE] ADM-653 Ticket, Experience & Bundle Upgrade Manager | 2 | Pranay Shinde |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 SVC-ORDER-ORDERS-17 | Configure detailed upsell relationships for ticketing and experience products. Module: Commercial. App: Venue Management. Done when `ADM-653` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-654 | AM-ORDERS-RESERVATIONS-P08-5 | [BE] ADM-654 Membership & Pass Upgrade Engine | 2 | Pranay Shinde |  | SETUP-CLIENTS SVC-CATALOGUE-RECOMMENDATIONS-1 SVC-ORDER-ORDERS-17 | Handle one of the most commercially valuable upgrade scenarios: Converting visitors into members/pass holders. Module: Commercial. App: Venue Management. Waits for its definition: ADM-654's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-654` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | SVC-ORDER-DRAFTED-23 | AM-ORDERS-RESERVATIONS-P08-7 | [BE] OrderService: listGroupSale, listGroupSale2, listOrderFinancialReconciliation, listParticipantGuestList | 3 | Deep Khanvilkar | OrderService | MIG-ACCESS MIG-ORDERS MIG-ORDERS-17 MIG-ORDERS-18 MIG-ORDERS-3 MIG-PAYMENTS PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-12 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-61 SVC-ACCESS-VALIDATION-2 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-ENTITLEMENT-3 SVC-FNB-FNB-12 SVC-IDENTITY-GUESTAUTH-2 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-14 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-DRAFTED-21 SVC-ORDER-DRAFTED-25 SVC-ORDER-DUNNING-1 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-18 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-26 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-30 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-1 SVC-ORDER-PAYMENTS-14 SVC-ORDER-PAYMENTS-6 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 SVC-WALLET-RETAIL-1 VM-ACCESS-ACCESS-1 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 VM-LEDGER-SETTLEMENT-1 VM-LEDGER-SETTLEMENT-2 VM-MIG-LEDGER VM-MIG-ORDERS VM-ORDER-ORDERS-1 VM-ORDER-ORDERS-3 VM-ORDER-REFUND-1 | Operations: listGroupSale, listGroupSale2, listOrderFinancialReconciliation, listParticipantGuestList. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 7 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listGroupSale`, `orders#listGroupSale2`, `orders#listOrderFinancialReconciliation`, `orders#listParticipantGuestList` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-37 | AM-ADMISSION-ACCESS-P08-4 | [BE] AccessService: listFamilyChildPod, listFastPassAttraction, listGroupAttendancePartial, listGroupLeaderFast | 5 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-14 MIG-ACCESS-3 MIG-CATALOGUE MIG-IDENTITY MIG-ORDERS MIG-PII PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-12 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-40 SVC-ACCESS-ACCESS-41 SVC-ACCESS-ACCESS-61 SVC-ACCESS-ACCESS-7 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-ACCESS-VALIDATION-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-ENTITLEMENT-1 SVC-CATALOGUE-ENTITLEMENT-3 SVC-CATALOGUE-ENTITLEMENT-5 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-IDENTITY-ADMINISTRATION-2 SVC-IDENTITY-GUESTAUTH-1 SVC-IDENTITY-GUESTAUTH-2 SVC-IDENTITY-GUESTAUTH-3 SVC-IDENTITY-IDENTITY-4 SVC-IDENTITY-SSO-1 SVC-MARKETING-MARKETING-7 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-14 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-18 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 VM-ACCESS-ACCESS-1 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 VM-CATALOGUE-PRODUCT-1 VM-IDENTITY-ADMINISTRATION-1 | Operations: listFamilyChildPod, listFastPassAttraction, listGroupAttendancePartial, listGroupLeaderFast. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 4 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listFamilyChildPod`, `access#listFastPassAttraction`, `access#listGroupAttendancePartial`, `access#listGroupLeaderFast` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-38 | AM-ADMISSION-ACCESS-P08-4 | [BE] AccessService: listGuestJourney, listLiveAccess, listMultiParkCrossover, listMultiParkCrossover2 | 5 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-14 PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-12 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-41 SVC-ACCESS-ACCESS-61 SVC-ACCESS-ACCESS-7 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-ACCESS-VALIDATION-2 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-ENTITLEMENT-3 SVC-ORDER-DRAFTED-14 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 VM-ACCESS-ACCESS-1 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 | Operations: listGuestJourney, listLiveAccess, listMultiParkCrossover, listMultiParkCrossover2. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 4 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listGuestJourney`, `access#listLiveAccess`, `access#listMultiParkCrossover`, `access#listMultiParkCrossover2` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-39 | AM-ADMISSION-ACCESS-P08-4 | [BE] AccessService: listPodiumConsole, listReconnectionSynchronizationConflict, listSpecialEventFree, listTicketCredentialInvestigation | 5 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-11 MIG-ACCESS-9 MIG-CATALOGUE MIG-IDENTITY MIG-ORDERS MIG-PII MIG-SYNC PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-12 SVC-ACCESS-ACCESS-15 SVC-ACCESS-ACCESS-18 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-22 SVC-ACCESS-ACCESS-36 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-41 SVC-ACCESS-ACCESS-61 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-ACCESS-VALIDATION-2 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-ENTITLEMENT-1 SVC-CATALOGUE-ENTITLEMENT-3 SVC-CATALOGUE-ENTITLEMENT-5 SVC-IDENTITY-ADMINISTRATION-2 SVC-IDENTITY-GUESTAUTH-1 SVC-IDENTITY-GUESTAUTH-2 SVC-IDENTITY-GUESTAUTH-3 SVC-IDENTITY-IDENTITY-4 SVC-IDENTITY-SSO-1 SVC-MARKETING-MARKETING-7 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-14 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-18 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 SVC-VENUEOPS-PLAY-1 VM-ACCESS-ACCESS-1 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 VM-IDENTITY-ADMINISTRATION-1 VM-ORDER-SYNC-1 | Operations: listPodiumConsole, listReconnectionSynchronizationConflict, listSpecialEventFree, listTicketCredentialInvestigation. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 4 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listPodiumConsole`, `access#listReconnectionSynchronizationConflict`, `access#listSpecialEventFree`, `access#listTicketCredentialInvestigation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-43 | AM-ADMISSION-ACCESS-P08-5 | [BE] AccessService: getAccessRiskScore, listAccessAttributeCatalog, listAccessSecurityFraud, listAuthorizationGovernanceTemporary | 5 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-12 MIG-ACCESS-14 MIG-ACCESS-15 MIG-IDENTITY PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-12 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-27 SVC-ACCESS-ACCESS-40 SVC-ACCESS-ACCESS-42 SVC-ACCESS-ACCESS-47 SVC-ACCESS-ACCESS-48 SVC-ACCESS-ACCESS-49 SVC-ACCESS-ACCESS-54 SVC-ACCESS-ACCESS-61 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-3 SVC-ACCESS-VALIDATION-2 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-ENTITLEMENT-3 SVC-IDENTITY-ADMINISTRATION-2 SVC-IDENTITY-ADMINISTRATION-3 SVC-IDENTITY-ADMINISTRATION-8 SVC-IDENTITY-IDENTITY-2 SVC-IDENTITY-SSO-1 SVC-ORDER-DRAFTED-14 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 VM-ACCESS-ACCESS-1 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 VM-IDENTITY-ADMINISTRATION-1 | Operations: getAccessRiskScore, listAccessAttributeCatalog, listAccessSecurityFraud, listAuthorizationGovernanceTemporary. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 5 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#getAccessRiskScore`, `access#listAccessAttributeCatalog`, `access#listAccessSecurityFraud`, `access#listAuthorizationGovernanceTemporary` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-44 | AM-ADMISSION-ACCESS-P08-5 | [BE] AccessService: listBiometricIdentityIntegrity, listCredentialSharingConcurrent, listDynamicAccessPolicy, listDynamicPolicyEffectiveness | 5 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-12 MIG-ACCESS-15 MIG-PII PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-12 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-27 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-42 SVC-ACCESS-ACCESS-47 SVC-ACCESS-ACCESS-48 SVC-ACCESS-ACCESS-49 SVC-ACCESS-ACCESS-61 SVC-ACCESS-VALIDATION-2 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-ENTITLEMENT-3 SVC-ORDER-DRAFTED-14 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 VM-ACCESS-ACCESS-1 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 VM-MIG-ACCESS | Operations: listBiometricIdentityIntegrity, listCredentialSharingConcurrent, listDynamicAccessPolicy, listDynamicPolicyEffectiveness. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 5 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listBiometricIdentityIntegrity`, `access#listCredentialSharingConcurrent`, `access#listDynamicAccessPolicy`, `access#listDynamicPolicyEffectiveness` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-46 | AM-ADMISSION-ACCESS-P08-5 | [BE] AccessService: listQueueThroughputLane, listRelationshipCompanionFraud, listShiftHandoverSummary, listUnifiedIdentityCredential | 5 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-14 MIG-ACCESS-15 MIG-ACCESS-9 MIG-IDENTITY MIG-PII PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-12 SVC-ACCESS-ACCESS-15 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-40 SVC-ACCESS-ACCESS-47 SVC-ACCESS-ACCESS-48 SVC-ACCESS-ACCESS-58 SVC-ACCESS-ACCESS-61 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-ACCESS-ACCESSPOINT-3 SVC-ACCESS-VALIDATION-2 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-ENTITLEMENT-3 SVC-IDENTITY-ADMINISTRATION-2 SVC-IDENTITY-GUESTAUTH-1 SVC-IDENTITY-GUESTAUTH-2 SVC-IDENTITY-GUESTAUTH-3 SVC-IDENTITY-IDENTITY-4 SVC-IDENTITY-SSO-1 SVC-MARKETING-MARKETING-7 SVC-ORDER-DRAFTED-14 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 VM-ACCESS-ACCESS-1 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 VM-IDENTITY-ADMINISTRATION-1 | Operations: listQueueThroughputLane, listRelationshipCompanionFraud, listShiftHandoverSummary, listUnifiedIdentityCredential. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 5 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listQueueThroughputLane`, `access#listRelationshipCompanionFraud`, `access#listShiftHandoverSummary`, `access#listUnifiedIdentityCredential` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-51 | AM-ADMISSION-ACCESS-P08-6 | [BE] AccessService: listAttendanceAdmission, listCredentialIdentityToken, listEntryExitCrossover, listGraphicalAccessMap | 5 | Deep Khanvilkar | AccessService | MIG-ACCESS MIG-ACCESS-12 MIG-CATALOGUE MIG-ORDERS MIG-VENUEMAP PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-12 SVC-ACCESS-ACCESS-14 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-28 SVC-ACCESS-ACCESS-29 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-61 SVC-ACCESS-ACCESS-7 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-ACCESS-VALIDATION-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-ENTITLEMENT-1 SVC-CATALOGUE-ENTITLEMENT-3 SVC-CATALOGUE-ENTITLEMENT-5 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-IDENTITY-GUESTAUTH-2 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-14 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-18 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 SVC-VENUEOPS-VENUEMAP-1 SVC-VENUEOPS-VENUEMAP-2 SVC-VENUEOPS-VENUEMAP-3 SVC-VENUEOPS-VENUEMAP-5 VM-ACCESS-ACCESS-1 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 VM-CATALOGUE-PRODUCT-1 VM-MIG-ACCESS VM-VENUEOPS-VENUEMAP-1 | Operations: listAttendanceAdmission, listCredentialIdentityToken, listEntryExitCrossover, listGraphicalAccessMap. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 6 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listAttendanceAdmission`, `access#listCredentialIdentityToken`, `access#listEntryExitCrossover`, `access#listGraphicalAccessMap` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-52 | AM-ADMISSION-ACCESS-P08-6 | [BE] AccessService: listGuestDwellTime, listLiveVenueOccupancy, listMediaTypeCredential, listMultiMediaBinding | 3 | Pranay Shinde | AccessService | MIG-ACCESS MIG-ACCESS-2 MIG-ACCESS-7 MIG-CATALOGUE MIG-VENUEMAP PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-10 SVC-ACCESS-ACCESS-12 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-21 SVC-ACCESS-ACCESS-29 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-50 SVC-ACCESS-ACCESS-54 SVC-ACCESS-ACCESS-61 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-ACCESS-VALIDATION-2 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-ENTITLEMENT-1 SVC-CATALOGUE-ENTITLEMENT-3 SVC-CATALOGUE-ENTITLEMENT-5 SVC-ORDER-DRAFTED-14 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-VENUEOPS-VENUEMAP-1 SVC-VENUEOPS-VENUEMAP-3 SVC-VENUEOPS-VENUEMAP-5 VM-ACCESS-ACCESS-1 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 VM-MIG-ACCESS | Operations: listGuestDwellTime, listLiveVenueOccupancy, listMediaTypeCredential, listMultiMediaBinding. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 6 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listGuestDwellTime`, `access#listLiveVenueOccupancy`, `access#listMediaTypeCredential`, `access#listMultiMediaBinding` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-53 | AM-ADMISSION-ACCESS-P08-6 | [BE] AccessService: listSecurityDetectionGovernance, listThroughputQueueValidation, listValidationOutcomeRejection, listVirtualTicket | 8 | Tanmay Dukhande | AccessService | MIG-ACCESS MIG-ACCESS-12 MIG-ACCESS-14 MIG-ACCESS-15 MIG-ACCESS-16 MIG-CATALOGUE MIG-ORDERS MIG-PII PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-12 SVC-ACCESS-ACCESS-14 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-27 SVC-ACCESS-ACCESS-29 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-40 SVC-ACCESS-ACCESS-42 SVC-ACCESS-ACCESS-49 SVC-ACCESS-ACCESS-61 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-ACCESS-ACCESSPOINT-3 SVC-ACCESS-VALIDATION-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-ENTITLEMENT-1 SVC-CATALOGUE-ENTITLEMENT-3 SVC-CATALOGUE-ENTITLEMENT-5 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-IDENTITY-GUESTAUTH-1 SVC-IDENTITY-GUESTAUTH-2 SVC-IDENTITY-GUESTAUTH-3 SVC-IDENTITY-IDENTITY-4 SVC-MARKETING-MARKETING-7 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-14 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-18 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 VM-ACCESS-ACCESS-1 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 VM-CATALOGUE-PRODUCT-1 VM-MIG-ACCESS | Operations: listSecurityDetectionGovernance, listThroughputQueueValidation, listValidationOutcomeRejection, listVirtualTicket. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 6 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listSecurityDetectionGovernance`, `access#listThroughputQueueValidation`, `access#listValidationOutcomeRejection`, `access#listVirtualTicket` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-62 | AM-ADMISSION-ACCESS-P08-7 | [BE] AccessService: setBrandingLocalizationTemplate, setCredentialIssuanceRetryPolicy, setDigitalBarcodeTicket, setDigitalCardMembership | 8 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-17 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCESS | Operations: setBrandingLocalizationTemplate, setCredentialIssuanceRetryPolicy, setDigitalBarcodeTicket, setDigitalCardMembership. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 7 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#setBrandingLocalizationTemplate`, `access#setCredentialIssuanceRetryPolicy`, `access#setDigitalBarcodeTicket`, `access#setDigitalCardMembership` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-63 | AM-ADMISSION-ACCESS-P08-7 | [BE] AccessService: setDynamicFieldData, setGoogleWalletPass, setMediaReplacementRevocation, setRfidNfcCard | 8 | Pranay Shinde | AccessService | MIG-ACCESS MIG-ACCESS-17 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCESS | Operations: setDynamicFieldData, setGoogleWalletPass, setMediaReplacementRevocation, setRfidNfcCard. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 7 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#setDynamicFieldData`, `access#setGoogleWalletPass`, `access#setMediaReplacementRevocation`, `access#setRfidNfcCard` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-57 | AM-ADMISSION-ACCESS-P08-7 | [BE] AccessService: listCredentialGenerationIssuance, listEntitlementCrossMedia, listMediaActivationPriority, listMediaReplacementRevocation | 3 | Deep Khanvilkar | AccessService | MIG-ACCESS MIG-ACCESS-12 MIG-ACCESS-16 MIG-ACCESS-17 MIG-CATALOGUE MIG-PII PLATFORM-KERNEL SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-27 SVC-ACCESS-ACCESS-29 SVC-ACCESS-ACCESS-56 SVC-ACCESS-ACCESS-61 SVC-ACCESS-ACCESS-62 SVC-ACCESS-ACCESS-63 SVC-ACCESS-ACCESS-9 SVC-ACCESS-VALIDATION-2 SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-ENTITLEMENT-3 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 SVC-IDENTITY-GUESTAUTH-1 SVC-IDENTITY-GUESTAUTH-2 SVC-IDENTITY-GUESTAUTH-3 SVC-IDENTITY-IDENTITY-4 SVC-MARKETING-MARKETING-7 SVC-ORDER-DRAFTED-14 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 VM-ACCESS-ACCESS-1 VM-CATALOGUE-PRODUCT-1 VM-MIG-ACCESS | Operations: listCredentialGenerationIssuance, listEntitlementCrossMedia, listMediaActivationPriority, listMediaReplacementRevocation. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 7 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listCredentialGenerationIssuance`, `access#listEntitlementCrossMedia`, `access#listMediaActivationPriority`, `access#listMediaReplacementRevocation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-ACCESS-ACCESS-64 | AM-ADMISSION-ACCESS-P08-8 | [BE] AccessService: deliverCredential, listCredentialDeliveryDistribution, listCredentialUsageCross, listFailedGenerationDelivery | 5 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-16 MIG-ACCESS-17 MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCESS | Operations: deliverCredential, listCredentialDeliveryDistribution, listCredentialUsageCross, listFailedGenerationDelivery. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 8 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#deliverCredential`, `access#listCredentialDeliveryDistribution`, `access#listCredentialUsageCross`, `access#listFailedGenerationDelivery` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-23 | AM-ADMISSION-ACCESS-P08-2 | [BE] AccessService: getFaceReenrolmentImages, listBiometricAccess, listCredentialRevocationLifecycle, listCredentialSecurity | 5 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-12 MIG-PII PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-12 SVC-ACCESS-ACCESS-14 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-27 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-5 SVC-ACCESS-ACCESS-6 SVC-ACCESS-ACCESS-60 SVC-ACCESS-ACCESS-61 SVC-ACCESS-ACCESS-64 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-ACCESS-VALIDATION-2 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-ENTITLEMENT-3 SVC-ORDER-DRAFTED-14 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 VM-ACCESS-ACCESS-1 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 VM-MIG-ACCESS | Operations: getFaceReenrolmentImages, listBiometricAccess, listCredentialRevocationLifecycle, listCredentialSecurity. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 2 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#getFaceReenrolmentImages`, `access#listBiometricAccess`, `access#listCredentialRevocationLifecycle`, `access#listCredentialSecurity` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-24 | AM-ADMISSION-ACCESS-P08-2 | [BE] AccessService: listCredentialSecurityOperational, listCredentialTransferRebinding, listDigitalCredentialSecurity, listExternalPartnerCredential | 5 | Pranay Shinde | AccessService | MIG-ACCESS MIG-ACCESS-12 MIG-CATALOGUE MIG-IDENTITY PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-14 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-28 SVC-ACCESS-ACCESS-29 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-5 SVC-ACCESS-ACCESS-6 SVC-ACCESS-ACCESS-60 SVC-ACCESS-ACCESS-61 SVC-ACCESS-ACCESS-64 SVC-ACCESS-ACCESSPOINT-1 SVC-ACCESS-ACCESSPOINT-2 SVC-ACCESS-VALIDATION-2 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-ENTITLEMENT-1 SVC-CATALOGUE-ENTITLEMENT-3 SVC-CATALOGUE-ENTITLEMENT-5 SVC-IDENTITY-ADMINISTRATION-2 SVC-IDENTITY-SSO-1 SVC-ORDER-DRAFTED-14 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 VM-ACCESS-ACCESS-1 VM-IDENTITY-ADMINISTRATION-1 VM-MIG-ACCESS | Operations: listCredentialSecurityOperational, listCredentialTransferRebinding, listDigitalCredentialSecurity, listExternalPartnerCredential. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 2 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listCredentialSecurityOperational`, `access#listCredentialTransferRebinding`, `access#listDigitalCredentialSecurity`, `access#listExternalPartnerCredential` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-25 | AM-ADMISSION-ACCESS-P08-2 | [BE] AccessService: listFaceChangeEnrollment, listHotelWalletExternal, listMediaCredential, listMediaIssuanceEncoding | 3 | Deep Khanvilkar | AccessService | MIG-ACCESS MIG-ACCESS-12 MIG-PII PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-12 SVC-ACCESS-ACCESS-14 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-27 SVC-ACCESS-ACCESS-28 SVC-ACCESS-ACCESS-29 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-60 SVC-ACCESS-ACCESS-61 SVC-ACCESS-ACCESS-64 SVC-ACCESS-VALIDATION-2 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-ENTITLEMENT-3 SVC-ORDER-DRAFTED-14 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 VM-ACCESS-ACCESS-1 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 VM-MIG-ACCESS | Operations: listFaceChangeEnrollment, listHotelWalletExternal, listMediaCredential, listMediaIssuanceEncoding. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 2 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listFaceChangeEnrollment`, `access#listHotelWalletExternal`, `access#listMediaCredential`, `access#listMediaIssuanceEncoding` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-26 | AM-ADMISSION-ACCESS-P08-2 | [BE] AccessService: listMediaSwapReplacement, listMediaTypeTechnology, listOfflineCryptographicValidation, listVerificationMethodSelection | 3 | Hrushikant Patkar | AccessService | MIG-ACCESS MIG-ACCESS-11 MIG-ACCESS-12 PLATFORM-KERNEL SVC-ACCESS-ACCESS-14 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-28 SVC-ACCESS-ACCESS-29 SVC-ACCESS-ACCESS-60 SVC-ACCESS-ACCESS-61 SVC-ACCESS-ACCESS-64 SVC-ACCESS-VALIDATION-2 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-ENTITLEMENT-3 SVC-ORDER-DRAFTED-14 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 VM-ACCESS-ACCESS-1 VM-MIG-ACCESS | Operations: listMediaSwapReplacement, listMediaTypeTechnology, listOfflineCryptographicValidation, listVerificationMethodSelection. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 2 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listMediaSwapReplacement`, `access#listMediaTypeTechnology`, `access#listOfflineCryptographicValidation`, `access#listVerificationMethodSelection` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-ACCESS-ACCESS-65 | AM-ADMISSION-ACCESS-P08-8 | [BE] AccessService: listTicketMedia | 2 | Deep Khanvilkar | AccessService | MIG-ACCESS MIG-ACCESS-16 MIG-ACCESS-17 MIG-PII PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-12 SVC-ACCESS-ACCESS-14 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-27 SVC-ACCESS-ACCESS-29 SVC-ACCESS-ACCESS-4 SVC-ACCESS-ACCESS-60 SVC-ACCESS-ACCESS-61 SVC-ACCESS-ACCESS-64 SVC-ACCESS-VALIDATION-2 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-ENTITLEMENT-3 SVC-ORDER-DRAFTED-14 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 VM-ACCESS-ACCESS-1 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 VM-MIG-ACCESS | Operations: listTicketMedia. Spec: contracts (access) at the release tag, served by ADAM. Built for Admission & Access · Venue Management 8 of 8; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listTicketMedia` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-LEDGER-JOURNAL-1 | AM-FINANCE-TAX-P08 | [BE] LedgerService: approveJournalEntry, createJournalEntry, getJournalEntry, listJournalEntries | 8 | Tanmay Dukhande | LedgerService | MIG-LEDGER MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations beyond the first release: approveJournalEntry, createJournalEntry, getJournalEntry, listJournalEntries. Additive to LedgerService; its first-release owner (Tanmay Dukhande) reviews. Done when `finance#approveJournalEntry`, `finance#createJournalEntry`, `finance#getJournalEntry`, `finance#listJournalEntries` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-LEDGER-JOURNAL-2 | AM-FINANCE-TAX-P08 | [BE] LedgerService: reverseJournalEntry | 2 | Chinmay Patkar | LedgerService | MIG-LEDGER PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: reverseJournalEntry. Additive to LedgerService; its first-release owner (Tanmay Dukhande) reviews. Helper task: Tanmay Dukhande owns the service and reviews. Done when `finance#reverseJournalEntry` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 2 | VM-LEDGER-LEDGER-2 | AM-FINANCE-TAX-P08 | [BE] LedgerService: rejectJournal, reopenPeriod | 3 | Sanket Keluskar | LedgerService | MIG-LEDGER PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-LEDGER | Operations beyond the first release: rejectJournal, reopenPeriod. Additive to LedgerService; its first-release owner (Tanmay Dukhande) reviews. Helper task: Tanmay Dukhande owns the service and reviews. Done when `finance#rejectJournal`, `finance#reopenPeriod` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-LEDGER-FINANCE-6 | AM-FINANCE-TAX-P08 | [BE] LedgerService: recordSettlement | 2 | Deep Khanvilkar | LedgerService | MIG-LEDGER MIG-LEDGER-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: recordSettlement. Spec: contracts (finance) at the release tag, served by ADAM. Built for Finance & Tax · Venue Management; additive to LedgerService, whose first-release owner (Tanmay Dukhande) reviews. Done when `finance#recordSettlement` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 2 | VM-LEDGER-REPORTING-1 | AM-FINANCE-TAX-P08 | [BE] LedgerService: getFinancialReport, getVatReturn | 3 | Sanket Keluskar | LedgerService | MIG-LEDGER PLATFORM-KERNEL SVC-LEDGER-ACCOUNTS-1 SVC-LEDGER-ACCOUNTS-2 SVC-LEDGER-FINANCE-2 SVC-LEDGER-FINANCE-3 SVC-LEDGER-FINANCE-6 SVC-LEDGER-FISCAL-1 SVC-LEDGER-LEDGER-3 SVC-LEDGER-TAX-1 SVC-LEDGER-TAX-3 SVC-ORDER-ORDERS-27 SVC-ORDER-ORDERS-28 SVC-ORDER-PAYMENT-1 SVC-ORDER-PAYMENTS-14 SVC-ORDER-REFUND-1 SVC-ORDER-SHIFT-1 SVC-ORDER-SHIFT-5 VM-LEDGER-FINANCE-1 VM-LEDGER-FISCAL-1 VM-LEDGER-JOURNAL-1 VM-LEDGER-JOURNAL-2 VM-LEDGER-LEDGER-1 VM-LEDGER-LEDGER-2 VM-LEDGER-RECOGNITION-1 VM-MIG-LEDGER VM-ORDER-ORDERS-2 VM-ORDER-SHIFT-1 | Operations beyond the first release: getFinancialReport, getVatReturn. Additive to LedgerService; its first-release owner (Tanmay Dukhande) reviews. Helper task: Tanmay Dukhande owns the service and reviews. Done when `finance#getFinancialReport`, `finance#getVatReturn` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | VM-ADM-626 | AM-FINANCE-TAX-P08 | [BE] ADM-626 Settlement Posting, Finance Handoff & Close Manager | 2 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-LEDGER-FINANCE-6 | Control when reconciled payment information becomes ready for downstream financial posting and period close. Module: Commercial. App: Venue Management. Waits for its definition: ADM-626's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-626` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-622 | AM-FINANCE-TAX-P08 | [BE] ADM-622 Reconciliation Exception & Investigation Center | 2 | Pranay Shinde |  | SETUP-CLIENTS VM-LEDGER-SETTLEMENT-1 VM-LEDGER-SETTLEMENT-2 | Centralize all payment discrepancies requiring operational or financial investigation. Module: Commercial. App: Venue Management. Done when `ADM-622` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-623 | AM-FINANCE-TAX-P08 | [BE] ADM-623 Settlement & Payout Manager | 2 | Pranay Shinde |  | SETUP-CLIENTS VM-LEDGER-SETTLEMENT-1 | Track expected and actual settlements from payment providers/acquirers. Module: Commercial. App: Venue Management. Done when `ADM-623` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-627 | AM-FINANCE-TAX-P08 | [BE] ADM-627 Reconciliation Audit, Trace & Evidence Center | 2 | Pranay Shinde |  | SETUP-CLIENTS SVC-LEDGER-FINANCE-5 | Provide a complete audit trail explaining how any payment became reconciled and financially closed. Module: Commercial. App: Venue Management. Done when `ADM-627` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-628 | AM-FINANCE-TAX-P08 | [BE] ADM-628 Reconciliation Simulator, Forecast & AI Operations Advisor | 2 | Pranay Shinde |  | SETUP-CLIENTS SVC-LEDGER-FINANCE-5 | Provide simulation, forecasting and AI-assisted analysis across reconciliation and settlement operations. Module: Commercial. App: Venue Management. Done when `ADM-628` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | SVC-CATALOGUE-DRAFTED-99 | AM-FINANCE-TAX-P09 | [BE] CatalogueService: listTaxFeeCalculation | 2 | Deep Khanvilkar | CatalogueService | MIG-CATALOGUE MIG-CATALOGUE-5 MIG-CATALOGUE-6 PLATFORM-KERNEL SVC-CATALOGUE-CATALOGUE-1 SVC-CATALOGUE-CATALOGUE-11 SVC-CATALOGUE-CATALOGUE-4 SVC-CATALOGUE-CATALOGUE-5 SVC-CATALOGUE-DRAFTED-10 SVC-CATALOGUE-DRAFTED-11 SVC-CATALOGUE-DRAFTED-16 SVC-CATALOGUE-DRAFTED-20 SVC-CATALOGUE-DRAFTED-25 SVC-CATALOGUE-DRAFTED-29 SVC-CATALOGUE-DRAFTED-56 SVC-CATALOGUE-PRODUCT-4 SVC-CATALOGUE-PRODUCT-5 VM-CATALOGUE-PRODUCT-1 | Operations: listTaxFeeCalculation. Spec: contracts (catalogue) at the release tag, served by ADAM. Built for Finance & Tax · TICVAI Console; additive to CatalogueService, whose first-release owner (Hrushikant Patkar) reviews. Done when `catalogue#listTaxFeeCalculation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-FNB-FNB-22 | AM-FOOD-BEVERAGE-P06 | [BE] FnbService: setSectionLayout | 1 | Tanmay Dukhande | FnbService | MIG-FNB PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setSectionLayout. Spec: contracts (fnb) at the release tag, served by ADAM. Built for Food & Beverage · Staff App; additive to FnbService, whose first-release owner (Tanmay Dukhande) reviews. Done when `fnb#setSectionLayout` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-FNB-FNB-21 | AM-FOOD-BEVERAGE-P06 | [BE] FnbService: getFnbReservationPolicy, notifyWaitlistParty, resolveBookingConflict, sendBookingConfirmation | 5 | Tanmay Dukhande | FnbService | MIG-FNB MIG-FNB-3 MIG-MARKETING MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getFnbReservationPolicy, notifyWaitlistParty, resolveBookingConflict, sendBookingConfirmation. Spec: contracts (fnb) at the release tag, served by ADAM. Built for Food & Beverage · Staff App; additive to FnbService, whose first-release owner (Tanmay Dukhande) reviews. Done when `fnb#getFnbReservationPolicy`, `fnb#notifyWaitlistParty`, `fnb#resolveBookingConflict`, `fnb#sendBookingConfirmation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-ORDER-DRAFTED-26 | AM-ORDERS-RESERVATIONS-P08-8 | [BE] OrderService: listGroupAmendmentCancellation, listGroupTicketFulfillment, listGroupTicketSeat | 3 | Pranay Shinde | OrderService | MIG-ACCESS MIG-MARKETING MIG-ORDERS MIG-ORDERS-18 PLATFORM-KERNEL SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-61 SVC-ACCESS-VALIDATION-2 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-ENTITLEMENT-3 SVC-FNB-FNB-12 SVC-FNB-FNB-17 SVC-FNB-FNB-21 SVC-FNB-FNB-6 SVC-IDENTITY-GUESTAUTH-2 SVC-IDENTITY-IDENTITY-4 SVC-MARKETING-CAMPAIGN-1 SVC-MARKETING-CONSENT-6 SVC-MARKETING-MESSAGE-1 SVC-MARKETING-MESSAGE-3 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-14 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-18 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-13 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-18 SVC-ORDER-ORDERS-2 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-26 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-30 SVC-ORDER-ORDERS-31 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-POLICY-1 SVC-ORDER-REFUND-1 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-PUBLICAPI-1 SVC-PLATFORM-SUBSCRIPTION-6 SVC-WALLET-RETAIL-1 VM-ACCESS-ACCESS-1 VM-MIG-ORDERS VM-ORDER-ORDERS-1 VM-ORDER-ORDERS-3 VM-ORDER-REFUND-1 | Operations: listGroupAmendmentCancellation, listGroupTicketFulfillment, listGroupTicketSeat. Spec: contracts (orders) at the release tag, served by ADAM. Built for Orders & Reservations · Venue Management 8 of 8; additive to OrderService, whose first-release owner (Pranay Shinde) reviews. Done when `orders#listGroupAmendmentCancellation`, `orders#listGroupTicketFulfillment`, `orders#listGroupTicketSeat` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-MARKETING-MARKETING-8 | AM-FOOD-BEVERAGE-P06 | [BE] MarketingService: matchGuest | 1 | Deep Khanvilkar | MarketingService | MIG-MARKETING MIG-PII PLATFORM-KERNEL SVC-IDENTITY-GUESTAUTH-1 SVC-IDENTITY-GUESTAUTH-2 SVC-IDENTITY-GUESTAUTH-3 SVC-IDENTITY-IDENTITY-4 SVC-MARKETING-CONSENT-3 SVC-MARKETING-GUEST-2 SVC-MARKETING-GUESTS-2 SVC-MARKETING-MARKETING-6 SVC-MARKETING-MARKETING-7 | Operations: matchGuest. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Food & Beverage · Staff App; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#matchGuest` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | MIG-FNB-8 | AM-FOOD-BEVERAGE-P08 | [DB] Forward migration V1218__fnb.sql: fnb for Food & Beverage · Venue Management (3 tables) | 2 | Hrushikant Patkar | FnbService | MIG-BASELINE MIG-FNB VM-MIG-FNB | Tables: fnb.kitchen_routing_rule, fnb.outlet_template, fnb.service_charge_policy. Source DDL: backend/tenant/010-fnb.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `fnb.kitchen_routing_rule`, `fnb.outlet_template`, `fnb.service_charge_policy` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
13 | 2 | VM-INVENTORY-COUNT-1 | AM-FOOD-BEVERAGE-P08 | [BE] InventoryService: cancelStockCount, getCountVariance, listStockCounts, postStockCount | 8 | Pranay Shinde | InventoryService | MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-INVENTORY | Operations beyond the first release: cancelStockCount, getCountVariance, listStockCounts, postStockCount. Additive to InventoryService; its first-release owner (Pranay Shinde) reviews. Done when `inventory#cancelStockCount`, `inventory#getCountVariance`, `inventory#listStockCounts`, `inventory#postStockCount` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 2 | VM-FNB-FNB-2 | AM-FOOD-BEVERAGE-P08 | [BE] FnbService: requestRecount, setTemperatureCheckpoint | 2 | Chinmay Patkar | FnbService | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-FNB VM-MIG-INVENTORY | Operations beyond the first release: requestRecount, setTemperatureCheckpoint. Additive to FnbService; its first-release owner (Tanmay Dukhande) reviews. Helper task: Tanmay Dukhande owns the service and reviews. Done when `fnb#requestRecount`, `fnb#setTemperatureCheckpoint` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-FNB-FNB-26 | AM-FOOD-BEVERAGE-P08 | [BE] FnbService: getFnbServiceChargePolicy, setFnbServiceChargePolicy | 3 | Deep Khanvilkar | FnbService | MIG-FNB-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getFnbServiceChargePolicy, setFnbServiceChargePolicy. Spec: contracts (fnb) at the release tag, served by ADAM. Built for Food & Beverage · Venue Management; additive to FnbService, whose first-release owner (Tanmay Dukhande) reviews. Done when `fnb#getFnbServiceChargePolicy`, `fnb#setFnbServiceChargePolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-FNB-KITCHEN-2 | AM-FOOD-BEVERAGE-P08 | [BE] FnbService: getKitchenRoutingRules, setKitchenRoutingRules, setKitchenStations | 5 | Hrushikant Patkar | FnbService | MIG-FNB MIG-FNB-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getKitchenRoutingRules, setKitchenRoutingRules, setKitchenStations. Spec: contracts (fnb) at the release tag, served by ADAM. Built for Food & Beverage · Venue Management; additive to FnbService, whose first-release owner (Tanmay Dukhande) reviews. Done when `fnb#getKitchenRoutingRules`, `fnb#setKitchenRoutingRules`, `fnb#setKitchenStations` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-FNB-OUTLET-1 | AM-FOOD-BEVERAGE-P08 | [BE] FnbService: listOutletTemplates, setOutletTemplate | 3 | Pranay Shinde | FnbService | MIG-FNB-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listOutletTemplates, setOutletTemplate. Spec: contracts (fnb) at the release tag, served by ADAM. Built for Food & Beverage · Venue Management; additive to FnbService, whose first-release owner (Tanmay Dukhande) reviews. Done when `fnb#listOutletTemplates`, `fnb#setOutletTemplate` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-RETAIL-FLOOR-3 | AM-RETAIL-P06 | [BE] RetailService: getOutletStock | 1 | Deep Khanvilkar | RetailService | MIG-PLATFORM PLATFORM-KERNEL SVC-TENANCY-WORKSTATION-1 SVC-TENANCY-WORKSTATION-2 | Operations: getOutletStock. Spec: contracts (retail) at the release tag, served by ADAM. Built for Retail · Staff App; additive to RetailService, whose first-release owner (Hrushikant Patkar) reviews. Done when `retail#getOutletStock` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-RETAIL-RETAIL-2 | AM-RETAIL-P06 | [BE] RetailService: cancelMerchandiseReservation, collectMerchandiseReservation | 2 | Tanmay Dukhande | RetailService | MIG-INVENTORY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: cancelMerchandiseReservation, collectMerchandiseReservation. Spec: contracts (retail) at the release tag, served by ADAM. Built for Retail · Staff App; additive to RetailService, whose first-release owner (Hrushikant Patkar) reviews. Done when `retail#cancelMerchandiseReservation`, `retail#collectMerchandiseReservation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | MIG-RETAIL-2 | AM-RETAIL-P08 | [DB] Forward migration V1158__retail.sql: retail for Retail · Venue Management (2 tables) | 2 | Hrushikant Patkar | RetailService | MIG-BASELINE MIG-RETAIL | Tables: retail.exchange, retail.product_recommendation. Source DDL: backend/tenant/010-retail.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `retail.exchange`, `retail.product_recommendation` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
17 | 3 | SVC-RETAIL-RETAIL-3 | AM-RETAIL-P08 | [BE] RetailService: listRetailRecommendations | 1 | Deep Khanvilkar | RetailService | MIG-RETAIL-2 PLATFORM-KERNEL | Operations: listRetailRecommendations. Spec: contracts (retail) at the release tag, served by ADAM. Built for Retail · Venue Management; additive to RetailService, whose first-release owner (Hrushikant Patkar) reviews. Done when `retail#listRetailRecommendations` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-RETAIL-RETURN-2 | AM-RETAIL-P08 | [BE] RetailService: createRetailExchange, listRetailReturns | 3 | Hrushikant Patkar | RetailService | MIG-RETAIL MIG-RETAIL-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createRetailExchange, listRetailReturns. Spec: contracts (retail) at the release tag, served by ADAM. Built for Retail · Venue Management; additive to RetailService, whose first-release owner (Hrushikant Patkar) reviews. Done when `retail#createRetailExchange`, `retail#listRetailReturns` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
8 | 3 | MIG-RENTAL-3 | AM-RENTALS-P06 | [DB] Forward migration V1022__rental.sql: rental for Rentals · Staff App 1 of 2 (6 tables) | 5 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE MIG-PLATFORM VM-MIG-RENTAL | Tables: rental.deposit_policy, rental.incident, rental.inspection, rental.inspection_item, rental.pricing_profile, rental.quote. Source DDL: backend/tenant/010-rental.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `rental.deposit_policy`, `rental.incident`, `rental.inspection`, `rental.inspection_item`, `rental.pricing_profile`, `rental.quote` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-VENUEOPS-RENTAL-3 | AM-RENTALS-P06 | [BE] VenueOpsService: assignRentalEquipment, checkOutRental, extendRental, listOverdueRentals | 8 | Pranay Shinde | VenueOpsService | MIG-RENTAL-2 MIG-RENTAL-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-RENTAL | Operations: assignRentalEquipment, checkOutRental, extendRental, listOverdueRentals. Spec: contracts (rental) at the release tag, served by ADAM. Built for Rentals · Staff App 1 of 2; additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `rental#assignRentalEquipment`, `rental#checkOutRental`, `rental#extendRental`, `rental#listOverdueRentals` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-RENTAL-4 | AM-RENTALS-P06 | [BE] VenueOpsService: listRentalBookings, quoteRentalPrice, recordRentalInspection, reportRentalIncident | 8 | Tanmay Dukhande | VenueOpsService | MIG-RENTAL-2 MIG-RENTAL-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-RENTAL | Operations: listRentalBookings, quoteRentalPrice, recordRentalInspection, reportRentalIncident. Spec: contracts (rental) at the release tag, served by ADAM. Built for Rentals · Staff App 1 of 2; additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `rental#listRentalBookings`, `rental#quoteRentalPrice`, `rental#recordRentalInspection`, `rental#reportRentalIncident` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-RENTAL-5 | AM-RENTALS-P06 | [BE] VenueOpsService: swapRentalEquipment | 2 | Deep Khanvilkar | VenueOpsService | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-RENTAL | Operations: swapRentalEquipment. Spec: contracts (rental) at the release tag, served by ADAM. Built for Rentals · Staff App 1 of 2; additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `rental#swapRentalEquipment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
5 | 3 | MIG-RENTAL-4 | AM-RENTALS-P06-2 | [DB] Forward migration V1159__rental.sql: rental for Rentals · Staff App 2 of 2 (2 tables) | 2 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE VM-MIG-RENTAL | Tables: rental.damage_assessment, rental.settlement. Source DDL: backend/tenant/010-rental.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `rental.damage_assessment`, `rental.settlement` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-VENUEOPS-RENTAL-6 | AM-RENTALS-P06-2 | [BE] VenueOpsService: assessRentalDamage, returnRental | 5 | Hrushikant Patkar | VenueOpsService | MIG-RENTAL-3 MIG-RENTAL-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: assessRentalDamage, returnRental. Spec: contracts (rental) at the release tag, served by ADAM. Built for Rentals · Staff App 2 of 2; additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `rental#assessRentalDamage`, `rental#returnRental` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 3 | MIG-MAINTENANCE-5 | AM-RENTALS-P08 | [DB] Forward migration V1219__maintenance.sql: maintenance for Rentals · Venue Management 1 of 5 (1 tables) | 1 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE MIG-MAINTENANCE VM-MIG-MAINTENANCE | Tables: maintenance.asset_category. Source DDL: backend/tenant/010-maintenance.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `maintenance.asset_category` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
13 | 3 | MIG-RENTAL-5 | AM-RENTALS-P08 | [DB] Forward migration V1135__rental.sql: rental for Rentals · Venue Management 1 of 5 (5 tables) | 3 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE MIG-ORDERS MIG-PLATFORM VM-MIG-RENTAL | Tables: rental.agreement, rental.agreement_item, rental.agreement_rules, rental.fee_policy, rental.operational_rules. Source DDL: backend/tenant/010-rental.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `rental.agreement`, `rental.agreement_item`, `rental.agreement_rules`, `rental.fee_policy`, `rental.operational_rules` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
14 | 3 | SVC-VENUEOPS-RENTAL-10 | AM-RENTALS-P08 | [BE] VenueOpsService: setRentalAvailabilityRules, setRentalDurationRules, setRentalInventoryModel, setRentalOperationalRules | 8 | Hrushikant Patkar | VenueOpsService | MIG-RENTAL-2 MIG-RENTAL-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setRentalAvailabilityRules, setRentalDurationRules, setRentalInventoryModel, setRentalOperationalRules. Spec: contracts (rental) at the release tag, served by ADAM. Built for Rentals · Venue Management 1 of 5; additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `rental#setRentalAvailabilityRules`, `rental#setRentalDurationRules`, `rental#setRentalInventoryModel`, `rental#setRentalOperationalRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-VENUEOPS-RENTAL-11 | AM-RENTALS-P08 | [BE] VenueOpsService: setRentalProductLocations, updateRentalProduct, validateRentalProduct | 3 | Deep Khanvilkar | VenueOpsService | MIG-MAINTENANCE-5 MIG-RENTAL-2 MIG-RENTAL-3 MIG-RENTAL-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setRentalProductLocations, updateRentalProduct, validateRentalProduct. Spec: contracts (rental) at the release tag, served by ADAM. Built for Rentals · Venue Management 1 of 5; additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `rental#setRentalProductLocations`, `rental#updateRentalProduct`, `rental#validateRentalProduct` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-VENUEOPS-RENTAL-7 | AM-RENTALS-P08 | [BE] VenueOpsService: createRentalAgreement, createRentalBlackout, createRentalCategory, createRentalProduct | 8 | Hrushikant Patkar | VenueOpsService | MIG-MAINTENANCE-5 MIG-RENTAL-2 MIG-RENTAL-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createRentalAgreement, createRentalBlackout, createRentalCategory, createRentalProduct. Spec: contracts (rental) at the release tag, served by ADAM. Built for Rentals · Venue Management 1 of 5; additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `rental#createRentalAgreement`, `rental#createRentalBlackout`, `rental#createRentalCategory`, `rental#createRentalProduct` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-VENUEOPS-RENTAL-8 | AM-RENTALS-P08 | [BE] VenueOpsService: getRentalAgreement, getRentalProduct, importRentalCatalogue, listRentalAgreements | 5 | Deep Khanvilkar | VenueOpsService | MIG-MAINTENANCE MIG-MAINTENANCE-5 MIG-RENTAL-2 MIG-RENTAL-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getRentalAgreement, getRentalProduct, importRentalCatalogue, listRentalAgreements. Spec: contracts (rental) at the release tag, served by ADAM. Built for Rentals · Venue Management 1 of 5; additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `rental#getRentalAgreement`, `rental#getRentalProduct`, `rental#importRentalCatalogue`, `rental#listRentalAgreements` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-VENUEOPS-RENTAL-9 | AM-RENTALS-P08 | [BE] VenueOpsService: listRentalCategories, listRentalProducts, publishRentalProduct, setRentalAgreementRequirements | 5 | Hrushikant Patkar | VenueOpsService | MIG-MAINTENANCE-5 MIG-RENTAL-2 MIG-RENTAL-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listRentalCategories, listRentalProducts, publishRentalProduct, setRentalAgreementRequirements. Spec: contracts (rental) at the release tag, served by ADAM. Built for Rentals · Venue Management 1 of 5; additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `rental#listRentalCategories`, `rental#listRentalProducts`, `rental#publishRentalProduct`, `rental#setRentalAgreementRequirements` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
5 | 3 | MIG-RENTAL-6 | AM-RENTALS-P08-2 | [DB] Forward migration V1160__rental.sql: rental for Rentals · Venue Management 2 of 5 (2 tables) | 2 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE VM-MIG-RENTAL | Tables: rental.agreement_signature, rental.override. Source DDL: backend/tenant/010-rental.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `rental.agreement_signature`, `rental.override` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-VENUEOPS-RENTAL-12 | AM-RENTALS-P08-2 | [BE] VenueOpsService: createRentalBooking, createRentalPricingProfile, explainRentalPrice, listRentalPricingProfiles | 8 | Pranay Shinde | VenueOpsService | MIG-RENTAL-2 MIG-RENTAL-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-RENTAL | Operations: createRentalBooking, createRentalPricingProfile, explainRentalPrice, listRentalPricingProfiles. Spec: contracts (rental) at the release tag, served by ADAM. Built for Rentals · Venue Management 2 of 5; additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `rental#createRentalBooking`, `rental#createRentalPricingProfile`, `rental#explainRentalPrice`, `rental#listRentalPricingProfiles` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-VENUEOPS-RENTAL-13 | AM-RENTALS-P08-2 | [BE] VenueOpsService: requestRentalCommercialOverride, setRentalDepositPolicy, setRentalFeePolicy, signRentalAgreement | 8 | Hrushikant Patkar | VenueOpsService | MIG-RENTAL-3 MIG-RENTAL-5 MIG-RENTAL-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: requestRentalCommercialOverride, setRentalDepositPolicy, setRentalFeePolicy, signRentalAgreement. Spec: contracts (rental) at the release tag, served by ADAM. Built for Rentals · Venue Management 2 of 5; additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `rental#requestRentalCommercialOverride`, `rental#setRentalDepositPolicy`, `rental#setRentalFeePolicy`, `rental#signRentalAgreement` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-VENUEOPS-RENTAL-14 | AM-RENTALS-P08-2 | [BE] VenueOpsService: simulateRentalPricing, updateRentalBooking, updateRentalPricingProfile | 8 | Tanmay Dukhande | VenueOpsService | MIG-RENTAL-2 MIG-RENTAL-3 MIG-RENTAL-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-RENTAL | Operations: simulateRentalPricing, updateRentalBooking, updateRentalPricingProfile. Spec: contracts (rental) at the release tag, served by ADAM. Built for Rentals · Venue Management 2 of 5; additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `rental#simulateRentalPricing`, `rental#updateRentalBooking`, `rental#updateRentalPricingProfile` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 3 | MIG-INVENTORY-2 | AM-INVENTORY-P06 | [DB] Forward migration V1050__inventory.sql: inventory for Inventory · Staff App (1 tables) | 1 | Hrushikant Patkar | InventoryService | MIG-BASELINE MIG-INVENTORY VM-MIG-INVENTORY | Tables: inventory.daily_count_list. Source DDL: backend/tenant/010-inventory.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `inventory.daily_count_list` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
13 | 2 | VM-INVENTORY-COUNT-2 | AM-INVENTORY-P06 | [BE] InventoryService: recountStockCount, startStockCount, submitCountLines | 8 | Pranay Shinde | InventoryService | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-INVENTORY | Operations beyond the first release: recountStockCount, startStockCount, submitCountLines. Additive to InventoryService; its first-release owner (Pranay Shinde) reviews. Done when `inventory#recountStockCount`, `inventory#startStockCount`, `inventory#submitCountLines` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 2 | VM-INVENTORY-REQUISITION-1 | AM-INVENTORY-P06 | [BE] InventoryService: approveRequisition, createRequisition, getSuggestedRequisitions, listRequisitions | 8 | Pranay Shinde | InventoryService | MIG-INVENTORY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-INVENTORY | Operations beyond the first release: approveRequisition, createRequisition, getSuggestedRequisitions, listRequisitions. Additive to InventoryService; its first-release owner (Pranay Shinde) reviews. Done when `inventory#approveRequisition`, `inventory#createRequisition`, `inventory#getSuggestedRequisitions`, `inventory#listRequisitions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-INVENTORY-INVENTORY-2 | AM-INVENTORY-P06 | [BE] InventoryService: setDailyCount | 1 | Deep Khanvilkar | InventoryService | MIG-INVENTORY MIG-INVENTORY-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setDailyCount. Spec: contracts (inventory) at the release tag, served by ADAM. Built for Inventory · Staff App; additive to InventoryService, whose first-release owner (Pranay Shinde) reviews. Done when `inventory#setDailyCount` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-INVENTORY-COUNT-3 | AM-INVENTORY-P06 | [BE] InventoryService: listStockCountLines | 1 | Deep Khanvilkar | InventoryService | PLATFORM-KERNEL VM-FNB-FNB-1 VM-FNB-FNB-2 VM-INVENTORY-COUNT-1 VM-INVENTORY-COUNT-2 VM-MIG-INVENTORY | Operations: listStockCountLines. Spec: contracts (inventory) at the release tag, served by ADAM. Built for Inventory · Staff App; additive to InventoryService, whose first-release owner (Pranay Shinde) reviews. Done when `inventory#listStockCountLines` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 2 | VM-INVENTORY-PROCUREMENT-1 | AM-INVENTORY-P08 | [BE] InventoryService: acknowledgePurchaseOrder, cancelRequisition, closePurchaseOrderShort, sendPurchaseOrder | 8 | Pranay Shinde | InventoryService | MIG-INVENTORY PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-INVENTORY | Operations beyond the first release: acknowledgePurchaseOrder, cancelRequisition, closePurchaseOrderShort, sendPurchaseOrder. Additive to InventoryService; its first-release owner (Pranay Shinde) reviews. Done when `inventory#acknowledgePurchaseOrder`, `inventory#cancelRequisition`, `inventory#closePurchaseOrderShort`, `inventory#sendPurchaseOrder` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 2 | VM-INVENTORY-RECEIPT-1 | AM-INVENTORY-P08 | [BE] InventoryService: listGoodsReceipts | 1 | Chinmay Patkar | InventoryService | MIG-INVENTORY PLATFORM-KERNEL SVC-INVENTORY-RECEIPT-1 | Operations beyond the first release: listGoodsReceipts. Additive to InventoryService; its first-release owner (Pranay Shinde) reviews. Helper task: Pranay Shinde owns the service and reviews. Done when `inventory#listGoodsReceipts` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 2 | VM-INVENTORY-SUPPLIER-1 | AM-INVENTORY-P08 | [BE] InventoryService: compareQuotations, createSupplier, createSupplierContract, listSupplierContracts | 8 | Pranay Shinde | InventoryService | MIG-INVENTORY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-INVENTORY | Operations beyond the first release: compareQuotations, createSupplier, createSupplierContract, listSupplierContracts. Additive to InventoryService; its first-release owner (Pranay Shinde) reviews. Done when `inventory#compareQuotations`, `inventory#createSupplier`, `inventory#createSupplierContract`, `inventory#listSupplierContracts` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
13 | 2 | VM-INVENTORY-SUPPLIER-2 | AM-INVENTORY-P08 | [BE] InventoryService: listSuppliers, recordQuotation, updateSupplierContract | 5 | Deep Khanvilkar | InventoryService | MIG-INVENTORY MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-INVENTORY | Operations beyond the first release: listSuppliers, recordQuotation, updateSupplierContract. Additive to InventoryService; its first-release owner (Pranay Shinde) reviews. Helper task: Pranay Shinde owns the service and reviews. Done when `inventory#listSuppliers`, `inventory#recordQuotation`, `inventory#updateSupplierContract` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
5 | 3 | MIG-ACCREDITATION-8 | AM-ACCREDITATION-P08 | [DB] Forward migration V1220__accreditation.sql: accreditation for Accreditation · Venue Management 1 of 4 (4 tables) | 3 | Hrushikant Patkar | TenancyService | MIG-BASELINE VM-MIG-ACCREDITATION | Tables: accreditation.document, accreditation.identity_conflict, accreditation.notification_rules, accreditation.requirements. Source DDL: backend/tenant/010-accreditation.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `accreditation.document`, `accreditation.identity_conflict`, `accreditation.notification_rules`, `accreditation.requirements` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-TENANCY-ACCREDITATION-10 | AM-ACCREDITATION-P08 | [BE] TenancyService: listAccreditationHolders, listAccreditationIdentityConflicts, resolveIdentityConflict, setAccreditationRequirements | 8 | Hrushikant Patkar | TenancyService | MIG-ACCREDITATION-4 MIG-ACCREDITATION-8 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-ACCREDITATION | Operations: listAccreditationHolders, listAccreditationIdentityConflicts, resolveIdentityConflict, setAccreditationRequirements. Spec: contracts (accreditation) at the release tag, served by ADAM. Built for Accreditation · Venue Management 1 of 4; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `accreditation#listAccreditationHolders`, `accreditation#listAccreditationIdentityConflicts`, `accreditation#resolveIdentityConflict`, `accreditation#setAccreditationRequirements` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-ACCREDITATION-11 | AM-ACCREDITATION-P08 | [BE] TenancyService: submitAccreditationApplication, submitAccreditationDocument, updateAccreditationApplication, updateAccreditationHolder | 8 | Hrushikant Patkar | TenancyService | MIG-ACCREDITATION-4 MIG-ACCREDITATION-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCREDITATION | Operations: submitAccreditationApplication, submitAccreditationDocument, updateAccreditationApplication, updateAccreditationHolder. Spec: contracts (accreditation) at the release tag, served by ADAM. Built for Accreditation · Venue Management 1 of 4; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `accreditation#submitAccreditationApplication`, `accreditation#submitAccreditationDocument`, `accreditation#updateAccreditationApplication`, `accreditation#updateAccreditationHolder` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-ACCREDITATION-12 | AM-ACCREDITATION-P08 | [BE] TenancyService: verifyAccreditationDocument, withdrawAccreditationApplication | 3 | Deep Khanvilkar | TenancyService | MIG-ACCREDITATION-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCREDITATION | Operations: verifyAccreditationDocument, withdrawAccreditationApplication. Spec: contracts (accreditation) at the release tag, served by ADAM. Built for Accreditation · Venue Management 1 of 4; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `accreditation#verifyAccreditationDocument`, `accreditation#withdrawAccreditationApplication` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-ACCREDITATION-8 | AM-ACCREDITATION-P08 | [BE] TenancyService: cloneAccreditationProgramme, createAccreditationApplication, createAccreditationProgramme, decideAccreditationApplication | 8 | Hrushikant Patkar | TenancyService | MIG-ACCREDITATION-2 MIG-ACCREDITATION-4 MIG-ACCREDITATION-8 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-ACCREDITATION | Operations: cloneAccreditationProgramme, createAccreditationApplication, createAccreditationProgramme, decideAccreditationApplication. Spec: contracts (accreditation) at the release tag, served by ADAM. Built for Accreditation · Venue Management 1 of 4; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `accreditation#cloneAccreditationProgramme`, `accreditation#createAccreditationApplication`, `accreditation#createAccreditationProgramme`, `accreditation#decideAccreditationApplication` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
5 | 3 | MIG-ACCREDITATION-9 | AM-ACCREDITATION-P08-2 | [DB] Forward migration V1221__accreditation.sql: accreditation for Accreditation · Venue Management 2 of 4 (3 tables) | 2 | Hrushikant Patkar | TenancyService | MIG-BASELINE VM-MIG-ACCREDITATION | Tables: accreditation.badge_template, accreditation.mobile_credential_delivery, accreditation.print_job. Source DDL: backend/tenant/010-accreditation.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `accreditation.badge_template`, `accreditation.mobile_credential_delivery`, `accreditation.print_job` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-TENANCY-ACCREDITATION-13 | AM-ACCREDITATION-P08-2 | [BE] TenancyService: createBadgePrintJob, deliverAccreditationCredential, getAccreditationApplication, issueAccreditationCredential | 8 | Hrushikant Patkar | TenancyService | MIG-ACCREDITATION-9 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-ACCREDITATION | Operations: createBadgePrintJob, deliverAccreditationCredential, getAccreditationApplication, issueAccreditationCredential. Spec: contracts (accreditation) at the release tag, served by ADAM. Built for Accreditation · Venue Management 2 of 4; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `accreditation#createBadgePrintJob`, `accreditation#deliverAccreditationCredential`, `accreditation#getAccreditationApplication`, `accreditation#issueAccreditationCredential` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-ACCREDITATION-14 | AM-ACCREDITATION-P08-2 | [BE] TenancyService: listBadgePrintJobs, listBadgeTemplates, replaceAccreditationCredential, resubmitAccreditationApplication | 5 | Deep Khanvilkar | TenancyService | MIG-ACCREDITATION-4 MIG-ACCREDITATION-8 MIG-ACCREDITATION-9 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-ACCREDITATION | Operations: listBadgePrintJobs, listBadgeTemplates, replaceAccreditationCredential, resubmitAccreditationApplication. Spec: contracts (accreditation) at the release tag, served by ADAM. Built for Accreditation · Venue Management 2 of 4; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `accreditation#listBadgePrintJobs`, `accreditation#listBadgeTemplates`, `accreditation#replaceAccreditationCredential`, `accreditation#resubmitAccreditationApplication` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-ACCREDITATION-15 | AM-ACCREDITATION-P08-2 | [BE] TenancyService: setBadgeTemplate, setHolderAccess | 3 | Hrushikant Patkar | TenancyService | MIG-ACCREDITATION-4 MIG-ACCREDITATION-9 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setBadgeTemplate, setHolderAccess. Spec: contracts (accreditation) at the release tag, served by ADAM. Built for Accreditation · Venue Management 2 of 4; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `accreditation#setBadgeTemplate`, `accreditation#setHolderAccess` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
5 | 3 | MIG-ACCREDITATION-10 | AM-ACCREDITATION-P08-3 | [DB] Forward migration V1222__accreditation.sql: accreditation for Accreditation · Venue Management 3 of 4 (1 tables) | 1 | Hrushikant Patkar | TenancyService | MIG-BASELINE VM-MIG-ACCREDITATION | Tables: accreditation.data_export. Source DDL: backend/tenant/010-accreditation.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `accreditation.data_export` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-TENANCY-ACCREDITATION-16 | AM-ACCREDITATION-P08-3 | [BE] TenancyService: exportAccreditationData, getAccreditationExport, getAccreditationValidity, importAccreditationHolders | 5 | Hrushikant Patkar | TenancyService | MIG-ACCREDITATION-10 MIG-ACCREDITATION-2 MIG-ACCREDITATION-3 MIG-ACCREDITATION-4 MIG-ACCREDITATION-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCREDITATION | Operations: exportAccreditationData, getAccreditationExport, getAccreditationValidity, importAccreditationHolders. Spec: contracts (accreditation) at the release tag, served by ADAM. Built for Accreditation · Venue Management 3 of 4; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `accreditation#exportAccreditationData`, `accreditation#getAccreditationExport`, `accreditation#getAccreditationValidity`, `accreditation#importAccreditationHolders` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-ACCREDITATION-18 | AM-ACCREDITATION-P08-3 | [BE] TenancyService: listAccreditationAccessActivity, listAccreditationExports, previewAccessImpact, renewAccreditation | 5 | Hrushikant Patkar | TenancyService | MIG-ACCREDITATION-10 MIG-ACCREDITATION-2 MIG-ACCREDITATION-3 MIG-ACCREDITATION-4 MIG-ACCREDITATION-8 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-ACCREDITATION | Operations: listAccreditationAccessActivity, listAccreditationExports, previewAccessImpact, renewAccreditation. Spec: contracts (accreditation) at the release tag, served by ADAM. Built for Accreditation · Venue Management 3 of 4; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `accreditation#listAccreditationAccessActivity`, `accreditation#listAccreditationExports`, `accreditation#previewAccessImpact`, `accreditation#renewAccreditation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-ACCREDITATION-19 | AM-ACCREDITATION-P08-3 | [BE] TenancyService: setAccreditationNotificationRules, setAccreditationStatus, setAccreditationValidity | 5 | Pranay Shinde | TenancyService | MIG-ACCREDITATION-2 MIG-ACCREDITATION-8 MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX VM-MIG-ACCREDITATION | Operations: setAccreditationNotificationRules, setAccreditationStatus, setAccreditationValidity. Spec: contracts (accreditation) at the release tag, served by ADAM. Built for Accreditation · Venue Management 3 of 4; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `accreditation#setAccreditationNotificationRules`, `accreditation#setAccreditationStatus`, `accreditation#setAccreditationValidity` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-TENANCY-ACCREDITATION-9 | AM-ACCREDITATION-P08 | [BE] TenancyService: getAccreditationHolder, listAccreditationApplications, listAccreditationCredentials, listAccreditationDocuments | 3 | Deep Khanvilkar | TenancyService | MIG-ACCREDITATION-8 PLATFORM-KERNEL SVC-TENANCY-ACCREDITATION-10 SVC-TENANCY-ACCREDITATION-11 SVC-TENANCY-ACCREDITATION-12 SVC-TENANCY-ACCREDITATION-13 SVC-TENANCY-ACCREDITATION-14 SVC-TENANCY-ACCREDITATION-16 SVC-TENANCY-ACCREDITATION-18 SVC-TENANCY-ACCREDITATION-19 SVC-TENANCY-ACCREDITATION-8 VM-MIG-ACCREDITATION | Operations: getAccreditationHolder, listAccreditationApplications, listAccreditationCredentials, listAccreditationDocuments. Spec: contracts (accreditation) at the release tag, served by ADAM. Built for Accreditation · Venue Management 1 of 4; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `accreditation#getAccreditationHolder`, `accreditation#listAccreditationApplications`, `accreditation#listAccreditationCredentials`, `accreditation#listAccreditationDocuments` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-ACCREDITATION-20 | AM-ACCREDITATION-P11 | [BE] TenancyService: issueMyAccreditationWalletPass, listMyAccreditationApplications, listMyAccreditationCredentials | 3 | Hrushikant Patkar | TenancyService | MIG-ACCREDITATION-4 MIG-ACCREDITATION-9 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-ACCREDITATION | Operations: issueMyAccreditationWalletPass, listMyAccreditationApplications, listMyAccreditationCredentials. Spec: contracts (accreditation) at the release tag, served by ADAM. Built for Accreditation · Accreditation Web; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `accreditation#issueMyAccreditationWalletPass`, `accreditation#listMyAccreditationApplications`, `accreditation#listMyAccreditationCredentials` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 3 | ACC-UAEPASS-ICP | AM-ACCREDITATION-API-PLATFORM | [BE] Identity verification for accreditation: UAE Pass and ICP | 8 | Tanmay Dukhande |  | PLATFORM-KERNEL | Identity verification for accreditation: UAE Pass and ICP. 2 October (Chinmay, DEC-457): UAE Pass sign-in/verification and ICP (Federal Authority for Identity, Citizenship, Customs and Port Security) document checks for accreditation applicants, alongside manual review. Needs client access to both (external dependencies register). Done when: an applicant verified through UAE Pass shows the verified identity on the reviewer workspace, and an ICP check result is recorded on the application.
8 | 3 | MIG-RESOURCES-4 | AM-RESOURCES-CAPACITY-P08 | [DB] Forward migration V1195__resources.sql: resources for Resources & Capacity · Venue Management 1 of 4 (6 tables) | 5 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE MIG-PLATFORM MIG-RESOURCES VM-MIG-RESOURCES | Tables: resources.attribute_definition, resources.resource_audit, resources.resource_category, resources.resource_dependency, resources.resource_relation, resources.venue_assignment. Source DDL: backend/tenant/010-resources.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `resources.attribute_definition`, `resources.resource_audit`, `resources.resource_category`, `resources.resource_dependency`, `resources.resource_relation`, `resources.venue_assignment` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 2 | VM-VENUEOPS-RESOURCES-3 | AM-RESOURCES-CAPACITY-P08 | [BE] VenueOpsService: setResourceQualifications | 2 | Chinmay Patkar | VenueOpsService | MIG-IDENTITY MIG-RESOURCES PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-RESOURCES | Operations beyond the first release: setResourceQualifications. Additive to VenueOpsService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `resources#setResourceQualifications` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-VENUEOPS-WORK-1 | AM-RESOURCES-CAPACITY-P08 | [BE] VenueOpsService: cancelWorkOrder | 2 | Chinmay Patkar | VenueOpsService | MIG-MAINTENANCE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: cancelWorkOrder. Additive to VenueOpsService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `maintenance#cancelWorkOrder` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-RESOURCES-10 | AM-RESOURCES-CAPACITY-P08 | [BE] VenueOpsService: createResourceAttribute, createResourceCategory, createResourceType, getResourceAuditTrail | 5 | Hrushikant Patkar | VenueOpsService | MIG-RESOURCES-2 MIG-RESOURCES-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createResourceAttribute, createResourceCategory, createResourceType, getResourceAuditTrail. Spec: contracts (resources) at the release tag, served by ADAM. Built for Resources & Capacity · Venue Management 1 of 4; additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `resources#createResourceAttribute`, `resources#createResourceCategory`, `resources#createResourceType`, `resources#getResourceAuditTrail` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-RESOURCES-12 | AM-RESOURCES-CAPACITY-P08 | [BE] VenueOpsService: listResourceAttributes, listResourceCategories, listResourceTypes, setResourceDependencies | 3 | Hrushikant Patkar | VenueOpsService | MIG-RESOURCES-2 MIG-RESOURCES-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listResourceAttributes, listResourceCategories, listResourceTypes, setResourceDependencies. Spec: contracts (resources) at the release tag, served by ADAM. Built for Resources & Capacity · Venue Management 1 of 4; additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `resources#listResourceAttributes`, `resources#listResourceCategories`, `resources#listResourceTypes`, `resources#setResourceDependencies` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-RESOURCES-13 | AM-RESOURCES-CAPACITY-P08 | [BE] VenueOpsService: setResourceHierarchy, setResourceVenueAssignment, updateResourceCategory, updateResourceType | 8 | Hrushikant Patkar | VenueOpsService | MIG-RESOURCES-2 MIG-RESOURCES-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setResourceHierarchy, setResourceVenueAssignment, updateResourceCategory, updateResourceType. Spec: contracts (resources) at the release tag, served by ADAM. Built for Resources & Capacity · Venue Management 1 of 4; additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `resources#setResourceHierarchy`, `resources#setResourceVenueAssignment`, `resources#updateResourceCategory`, `resources#updateResourceType` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
8 | 3 | MIG-RESOURCES-5 | AM-RESOURCES-CAPACITY-P08-2 | [DB] Forward migration V1198__resources.sql: resources for Resources & Capacity · Venue Management 2 of 4 (1 tables) | 1 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE MIG-RESOURCES VM-MIG-RESOURCES | Tables: resources.allocation_policy. Source DDL: backend/tenant/010-resources.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `resources.allocation_policy` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-TENANCY-WORKFORCE-2 | AM-RESOURCES-CAPACITY-P08-2 | [BE] TenancyService: listIntegrationSources, setFieldOwnership, validateWorkforceCompliance | 2 | Deep Khanvilkar | TenancyService | MIG-IDENTITY MIG-WORKFORCE MIG-WORKFORCE-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-WORKFORCE | Operations: listIntegrationSources, setFieldOwnership, validateWorkforceCompliance. Spec: contracts (workforce) at the release tag, served by ADAM. Built for Resources & Capacity · Venue Management 2 of 4; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `workforce#listIntegrationSources`, `workforce#setFieldOwnership`, `workforce#validateWorkforceCompliance` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-RESOURCES-14 | AM-RESOURCES-CAPACITY-P08-2 | [BE] VenueOpsService: allocateResources, cancelResourceBooking, getResourceAllocationPolicy, listResourceBookings | 5 | Hrushikant Patkar | VenueOpsService | MIG-RESOURCES MIG-RESOURCES-4 MIG-RESOURCES-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: allocateResources, cancelResourceBooking, getResourceAllocationPolicy, listResourceBookings. Spec: contracts (resources) at the release tag, served by ADAM. Built for Resources & Capacity · Venue Management 2 of 4; additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `resources#allocateResources`, `resources#cancelResourceBooking`, `resources#getResourceAllocationPolicy`, `resources#listResourceBookings` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-RESOURCES-15 | AM-RESOURCES-CAPACITY-P08-2 | [BE] VenueOpsService: replaceResourceAllocation, setResourceAllocationPolicy, setResourceSelectionPolicy, updateResourceBooking | 5 | Hrushikant Patkar | VenueOpsService | MIG-RESOURCES MIG-RESOURCES-2 MIG-RESOURCES-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-RESOURCES | Operations: replaceResourceAllocation, setResourceAllocationPolicy, setResourceSelectionPolicy, updateResourceBooking. Spec: contracts (resources) at the release tag, served by ADAM. Built for Resources & Capacity · Venue Management 2 of 4; additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `resources#replaceResourceAllocation`, `resources#setResourceAllocationPolicy`, `resources#setResourceSelectionPolicy`, `resources#updateResourceBooking` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
8 | 3 | MIG-RESOURCES-6 | AM-RESOURCES-CAPACITY-P08-3 | [DB] Forward migration V1223__resources.sql: resources for Resources & Capacity · Venue Management 3 of 4 (2 tables) | 2 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE MIG-RESOURCES VM-MIG-RESOURCES | Tables: resources.resource_cost, resources.resource_request. Source DDL: backend/tenant/010-resources.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `resources.resource_cost`, `resources.resource_request` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-VENUEOPS-RESOURCES-16 | AM-RESOURCES-CAPACITY-P08-3 | [BE] VenueOpsService: createResourceCost, deleteResourceCost, getResourceCostAnalytics, listResourceCosts | 5 | Deep Khanvilkar | VenueOpsService | MIG-MAINTENANCE MIG-RESOURCES MIG-RESOURCES-4 MIG-RESOURCES-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createResourceCost, deleteResourceCost, getResourceCostAnalytics, listResourceCosts. Spec: contracts (resources) at the release tag, served by ADAM. Built for Resources & Capacity · Venue Management 3 of 4; additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `resources#createResourceCost`, `resources#deleteResourceCost`, `resources#getResourceCostAnalytics`, `resources#listResourceCosts` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-RESOURCES-17 | AM-RESOURCES-CAPACITY-P08-3 | [BE] VenueOpsService: raiseResourceRequest, setResourceBookingProgress | 3 | Hrushikant Patkar | VenueOpsService | MIG-RESOURCES MIG-RESOURCES-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: raiseResourceRequest, setResourceBookingProgress. Spec: contracts (resources) at the release tag, served by ADAM. Built for Resources & Capacity · Venue Management 3 of 4; additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `resources#raiseResourceRequest`, `resources#setResourceBookingProgress` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-VENUEOPS-RESOURCES-11 | AM-RESOURCES-CAPACITY-P08 | [BE] VenueOpsService: getResourceCalendar, getResourceDependencies, getResourceHierarchy, getResourceUtilisation | 3 | Hrushikant Patkar | VenueOpsService | MIG-MAINTENANCE MIG-RESOURCES MIG-RESOURCES-2 MIG-RESOURCES-4 PLATFORM-KERNEL SVC-VENUEOPS-MAINTENANCE-2 SVC-VENUEOPS-RESOURCES-1 SVC-VENUEOPS-RESOURCES-10 SVC-VENUEOPS-RESOURCES-12 SVC-VENUEOPS-RESOURCES-13 SVC-VENUEOPS-RESOURCES-14 SVC-VENUEOPS-RESOURCES-15 SVC-VENUEOPS-RESOURCES-17 SVC-VENUEOPS-RESOURCES-2 SVC-VENUEOPS-RESOURCES-3 SVC-VENUEOPS-RESOURCES-4 SVC-VENUEOPS-WORKORDER-4 VM-VENUEOPS-MAINTENANCE-1 VM-VENUEOPS-RESOURCES-1 VM-VENUEOPS-WORK-1 VM-VENUEOPS-WORKORDER-1 VM-VENUEOPS-WORKORDER-3 | Operations: getResourceCalendar, getResourceDependencies, getResourceHierarchy, getResourceUtilisation. Spec: contracts (resources) at the release tag, served by ADAM. Built for Resources & Capacity · Venue Management 1 of 4; additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `resources#getResourceCalendar`, `resources#getResourceDependencies`, `resources#getResourceHierarchy`, `resources#getResourceUtilisation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 3 | MIG-WORKFORCE-8 | AM-WORKFORCE-P06 | [DB] Forward migration V1224__workforce.sql: workforce for Workforce · Staff App (4 tables) | 2 | Hrushikant Patkar | TenancyService | MIG-BASELINE MIG-WORKFORCE VM-MIG-WORKFORCE | Tables: workforce.employment, workforce.staff_conversation, workforce.staff_conversation_participant, workforce.staff_message. Source DDL: backend/tenant/010-workforce.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `workforce.employment`, `workforce.staff_conversation`, `workforce.staff_conversation_participant`, `workforce.staff_message` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 2 | VM-TENANCY-ANNOUNCEMENTS-1 | AM-WORKFORCE-P06 | [BE] TenancyService: getAnnouncementReach, listAnnouncements, publishAnnouncement | 5 | Deep Khanvilkar | TenancyService | MIG-IDENTITY MIG-PLATFORM MIG-WORKFORCE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-WORKFORCE | Operations beyond the first release: getAnnouncementReach, listAnnouncements, publishAnnouncement. Additive to TenancyService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `workforce#getAnnouncementReach`, `workforce#listAnnouncements`, `workforce#publishAnnouncement` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 2 | VM-TENANCY-ATTENDANCE-1 | AM-WORKFORCE-P06 | [BE] TenancyService: amendAttendance, listAttendance | 2 | Chinmay Patkar | TenancyService | MIG-WORKFORCE PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations beyond the first release: amendAttendance, listAttendance. Additive to TenancyService; its first-release owner (Hrushikant Patkar) reviews. Helper task: Hrushikant Patkar owns the service and reviews. Done when `workforce#amendAttendance`, `workforce#listAttendance` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-ANNOUNCEMENTS-2 | AM-WORKFORCE-P06 | [BE] TenancyService: acknowledgeAnnouncement, listStaffConversations, listStaffMessages, markStaffConversationRead | 8 | Hrushikant Patkar | TenancyService | MIG-WORKFORCE-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-WORKFORCE | Operations: acknowledgeAnnouncement, listStaffConversations, listStaffMessages, markStaffConversationRead. Spec: contracts (workforce) at the release tag, served by ADAM. Built for Workforce · Staff App; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `workforce#acknowledgeAnnouncement`, `workforce#listStaffConversations`, `workforce#listStaffMessages`, `workforce#markStaffConversationRead` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-ANNOUNCEMENTS-3 | AM-WORKFORCE-P06 | [BE] TenancyService: sendStaffMessage | 2 | Hrushikant Patkar | TenancyService | MIG-WORKFORCE-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: sendStaffMessage. Spec: contracts (workforce) at the release tag, served by ADAM. Built for Workforce · Staff App; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `workforce#sendStaffMessage` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-WORKFORCE-6 | AM-WORKFORCE-P08 | [BE] TenancyService: listShiftTemplates, listSyncConflicts, listSyncRuns, requestLeave | 5 | Tanmay Dukhande | TenancyService | MIG-WORKFORCE-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listShiftTemplates, listSyncConflicts, listSyncRuns, requestLeave. Spec: contracts (workforce) at the release tag, served by ADAM. Built for Workforce · Venue Management 1 of 2; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `workforce#listShiftTemplates`, `workforce#listSyncConflicts`, `workforce#listSyncRuns`, `workforce#requestLeave` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-WORKFORCE-7 | AM-WORKFORCE-P08 | [BE] TenancyService: resolveSyncConflict, setIntegrationSource, setLabourBudget, setLeaveType | 5 | Tanmay Dukhande | TenancyService | MIG-WORKFORCE-3 MIG-WORKFORCE-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: resolveSyncConflict, setIntegrationSource, setLabourBudget, setLeaveType. Spec: contracts (workforce) at the release tag, served by ADAM. Built for Workforce · Venue Management 1 of 2; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `workforce#resolveSyncConflict`, `workforce#setIntegrationSource`, `workforce#setLabourBudget`, `workforce#setLeaveType` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-TENANCY-WORKFORCE-8 | AM-WORKFORCE-P08 | [BE] TenancyService: setShiftPattern, setShiftTemplate, setStaffingRules, startSync | 8 | Tanmay Dukhande | TenancyService | MIG-WORKFORCE-3 MIG-WORKFORCE-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-WORKFORCE | Operations: setShiftPattern, setShiftTemplate, setStaffingRules, startSync. Spec: contracts (workforce) at the release tag, served by ADAM. Built for Workforce · Venue Management 1 of 2; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `workforce#setShiftPattern`, `workforce#setShiftTemplate`, `workforce#setStaffingRules`, `workforce#startSync` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-TENANCY-WORKFORCE-3 | AM-WORKFORCE-P08 | [BE] TenancyService: broadcastToGuests, claimOpenShift, getEmployee, getFieldOwnership | 8 | Hrushikant Patkar | TenancyService | MIG-ACCESS MIG-IDENTITY MIG-MARKETING MIG-VENUEMAP MIG-WORKFORCE-3 MIG-WORKFORCE-5 MIG-WORKFORCE-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-WORKFORCE | Operations: broadcastToGuests, claimOpenShift, getEmployee, getFieldOwnership. Spec: contracts (workforce) at the release tag, served by ADAM. Built for Workforce · Venue Management 1 of 2; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `workforce#broadcastToGuests`, `workforce#claimOpenShift`, `workforce#getEmployee`, `workforce#getFieldOwnership` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-TENANCY-WORKFORCE-4 | AM-WORKFORCE-P08 | [BE] TenancyService: getLabourCost, listEmployees, listLabourBudgets, listLeaveBalances | 3 | Deep Khanvilkar | TenancyService | MIG-WORKFORCE MIG-WORKFORCE-5 PLATFORM-KERNEL SVC-TENANCY-ATTENDANCE-1 SVC-TENANCY-ROTA-1 SVC-TENANCY-WORKFORCE-7 SVC-TENANCY-WORKFORCE-8 VM-MIG-WORKFORCE VM-TENANCY-ATTENDANCE-1 | Operations: getLabourCost, listEmployees, listLabourBudgets, listLeaveBalances. Spec: contracts (workforce) at the release tag, served by ADAM. Built for Workforce · Venue Management 1 of 2; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `workforce#getLabourCost`, `workforce#listEmployees`, `workforce#listLabourBudgets`, `workforce#listLeaveBalances` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-TENANCY-WORKFORCE-5 | AM-WORKFORCE-P08 | [BE] TenancyService: listLeaveRequests, listLeaveTypes, listOpenShifts, listShiftPatterns | 3 | Hrushikant Patkar | TenancyService | MIG-WORKFORCE-5 PLATFORM-KERNEL SVC-TENANCY-WORKFORCE-3 SVC-TENANCY-WORKFORCE-6 SVC-TENANCY-WORKFORCE-7 SVC-TENANCY-WORKFORCE-8 VM-MIG-WORKFORCE | Operations: listLeaveRequests, listLeaveTypes, listOpenShifts, listShiftPatterns. Spec: contracts (workforce) at the release tag, served by ADAM. Built for Workforce · Venue Management 1 of 2; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `workforce#listLeaveRequests`, `workforce#listLeaveTypes`, `workforce#listOpenShifts`, `workforce#listShiftPatterns` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-PLANNED-2 | AM-MAINTENANCE-SAFETY-P08 | [BE] VenueOpsService: createMaintenancePlan, listMaintenancePlans, updateMaintenancePlan | 5 | Tanmay Dukhande | VenueOpsService | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-MAINTENANCE | Operations: createMaintenancePlan, listMaintenancePlans, updateMaintenancePlan. Spec: contracts (maintenance) at the release tag, served by ADAM. Built for Maintenance & Safety · Venue Management 1 of 2; additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `maintenance#createMaintenancePlan`, `maintenance#listMaintenancePlans`, `maintenance#updateMaintenancePlan` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | SVC-VENUEOPS-PLANNED-1 | AM-RESOURCES-CAPACITY-P08-3 | [BE] VenueOpsService: getDueMaintenance | 1 | Deep Khanvilkar | VenueOpsService | MIG-MAINTENANCE PLATFORM-KERNEL SVC-VENUEOPS-PLANNED-2 SVC-VENUEOPS-RENTAL-8 VM-MIG-MAINTENANCE VM-VENUEOPS-ASSET-1 VM-VENUEOPS-ASSET-2 | Operations: getDueMaintenance. Spec: contracts (maintenance) at the release tag, served by ADAM. Built for Resources & Capacity · Venue Management 3 of 4; additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `maintenance#getDueMaintenance` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-WORKORDER-6 | AM-MAINTENANCE-SAFETY-P08 | [BE] VenueOpsService: getWorkOrderPriorityPolicy, setWorkOrderPriorityPolicy | 3 | Tanmay Dukhande | VenueOpsService | PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-MAINTENANCE | Operations: getWorkOrderPriorityPolicy, setWorkOrderPriorityPolicy. Spec: contracts (maintenance) at the release tag, served by ADAM. Built for Maintenance & Safety · Venue Management 1 of 2; additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `maintenance#getWorkOrderPriorityPolicy`, `maintenance#setWorkOrderPriorityPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
7 | 3 | MIG-GAMES-4 | AM-GAMES-RIDES-P08 | [DB] Forward migration V1167__games.sql: games for Games & Rides · Venue Management 1 of 4 (7 tables) | 5 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE MIG-GAMES VM-MIG-GAMES | Tables: games.attraction_type, games.entitlement, games.gameplay_transaction, games.pricing_exception, games.reader_deployment, games.redemption_rules, games.validation_rules. Source DDL: backend/tenant/010-games.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `games.attraction_type`, `games.entitlement`, `games.gameplay_transaction`, `games.pricing_exception`, `games.reader_deployment`, `games.redemption_rules`, `games.validation_rules` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
12 | 3 | SVC-TENANCY-WORKSTATION-5 | AM-GAMES-RIDES-P08 | [BE] TenancyService: getDevice | 2 | Deep Khanvilkar | TenancyService | MIG-PLATFORM PLATFORM-KERNEL SVC-TENANCY-DEVICES-4 SVC-TENANCY-DEVICES-7 SVC-TENANCY-WORKSTATION-1 SVC-TENANCY-WORKSTATION-3 VM-TENANCY-WORKSTATION-1 | Operations: getDevice. Spec: contracts (tenancy) at the release tag, served by ADAM. Built for Games & Rides · Venue Management 1 of 4; additive to TenancyService, whose first-release owner (Hrushikant Patkar) reviews. Done when `tenancy#getDevice` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-GAMES-3 | AM-GAMES-RIDES-P08 | [BE] VenueOpsService: cloneReaderConfiguration, getGamePricing, getGameplayValidationRules, listAttractionTypes | 3 | Hrushikant Patkar | VenueOpsService | MIG-GAMES-2 MIG-GAMES-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-GAMES | Operations: cloneReaderConfiguration, getGamePricing, getGameplayValidationRules, listAttractionTypes. Spec: contracts (games) at the release tag, served by ADAM. Built for Games & Rides · Venue Management 1 of 4; additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `games#cloneReaderConfiguration`, `games#getGamePricing`, `games#getGameplayValidationRules`, `games#listAttractionTypes` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-GAMES-4 | AM-GAMES-RIDES-P08 | [BE] VenueOpsService: listGameEntitlements, listGameplayTransactions, listReaders, setAttractionType | 3 | Hrushikant Patkar | VenueOpsService | MIG-GAMES-2 MIG-GAMES-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listGameEntitlements, listGameplayTransactions, listReaders, setAttractionType. Spec: contracts (games) at the release tag, served by ADAM. Built for Games & Rides · Venue Management 1 of 4; additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `games#listGameEntitlements`, `games#listGameplayTransactions`, `games#listReaders`, `games#setAttractionType` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-GAMES-5 | AM-GAMES-RIDES-P08 | [BE] VenueOpsService: setGameOperationalConfiguration, setReaderConfiguration, setReaderProfile, simulateGameplayAuthorisation | 8 | Tanmay Dukhande | VenueOpsService | MIG-CATALOGUE MIG-GAMES-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-GAMES | Operations: setGameOperationalConfiguration, setReaderConfiguration, setReaderProfile, simulateGameplayAuthorisation. Spec: contracts (games) at the release tag, served by ADAM. Built for Games & Rides · Venue Management 1 of 4; additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `games#setGameOperationalConfiguration`, `games#setReaderConfiguration`, `games#setReaderProfile`, `games#simulateGameplayAuthorisation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-VENUEOPS-GAMES-7 | AM-GAMES-RIDES-P08-2 | [BE] VenueOpsService: createGameEntitlement, setGamePricing, setGameplayValidationRules | 5 | Hrushikant Patkar | VenueOpsService | MIG-GAMES-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-GAMES | Operations: createGameEntitlement, setGamePricing, setGameplayValidationRules. Spec: contracts (games) at the release tag, served by ADAM. Built for Games & Rides · Venue Management 2 of 4; additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `games#createGameEntitlement`, `games#setGamePricing`, `games#setGameplayValidationRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | MIG-GAMES-5 | AM-GAMES-RIDES-P08-3 | [DB] Forward migration V1168__games.sql: games for Games & Rides · Venue Management 3 of 4 (5 tables) | 3 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE MIG-GAMES MIG-IDENTITY MIG-PLATFORM MIG-RETAIL VM-MIG-GAMES | Tables: games.card_expiry_rules, games.prize, games.prize_cost, games.redemption, games.redemption_line. Source DDL: backend/tenant/010-games.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `games.card_expiry_rules`, `games.prize`, `games.prize_cost`, `games.redemption`, `games.redemption_line` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
17 | 3 | SVC-VENUEOPS-GAMES-8 | AM-GAMES-RIDES-P08-3 | [BE] VenueOpsService: setGameCardExpiryRules, setGameCardLifecycle, setPrizeCost, setRedemptionRules | 5 | Hrushikant Patkar | VenueOpsService | MIG-GAMES MIG-GAMES-4 MIG-GAMES-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setGameCardExpiryRules, setGameCardLifecycle, setPrizeCost, setRedemptionRules. Spec: contracts (games) at the release tag, served by ADAM. Built for Games & Rides · Venue Management 3 of 4; additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `games#setGameCardExpiryRules`, `games#setGameCardLifecycle`, `games#setPrizeCost`, `games#setRedemptionRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-VENUEOPS-PRIZE-1 | AM-GAMES-RIDES-P08-3 | [BE] VenueOpsService: createPrize, listPrizes, lookupPrize, redeemPrize | 8 | Hrushikant Patkar | VenueOpsService | MIG-GAMES-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createPrize, listPrizes, lookupPrize, redeemPrize. Spec: contracts (games) at the release tag, served by ADAM. Built for Games & Rides · Venue Management 3 of 4; additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `games#createPrize`, `games#listPrizes`, `games#lookupPrize`, `games#redeemPrize` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
7 | 3 | MIG-GAMES-6 | AM-GAMES-RIDES-P08-4 | [DB] Forward migration V1225__games.sql: games for Games & Rides · Venue Management 4 of 4 (1 tables) | 1 | Hrushikant Patkar | VenueOpsService | MIG-BASELINE MIG-GAMES VM-MIG-GAMES | Tables: games.kiosk_config. Source DDL: backend/tenant/010-games.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `games.kiosk_config` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-VENUEOPS-GAMES-9 | AM-GAMES-RIDES-P08-4 | [BE] VenueOpsService: deployReaderConfiguration, getGameEligibility, getGameplaySyncStatus, setGameKioskConfiguration | 3 | Deep Khanvilkar | VenueOpsService | MIG-GAMES MIG-GAMES-2 MIG-GAMES-4 MIG-GAMES-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-GAMES | Operations: deployReaderConfiguration, getGameEligibility, getGameplaySyncStatus, setGameKioskConfiguration. Spec: contracts (games) at the release tag, served by ADAM. Built for Games & Rides · Venue Management 4 of 4; additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `games#deployReaderConfiguration`, `games#getGameEligibility`, `games#getGameplaySyncStatus`, `games#setGameKioskConfiguration` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-VENUEOPS-GAMES-6 | AM-GAMES-RIDES-P08 | [BE] VenueOpsService: testReader, validateGameConfiguration | 2 | Deep Khanvilkar | VenueOpsService | MIG-GAMES MIG-GAMES-2 MIG-GAMES-4 PLATFORM-KERNEL SVC-VENUEOPS-CARD-1 SVC-VENUEOPS-CARD-2 SVC-VENUEOPS-GAMES-3 SVC-VENUEOPS-GAMES-5 SVC-VENUEOPS-GAMES-7 SVC-VENUEOPS-GAMES-8 SVC-VENUEOPS-GAMES-9 SVC-WALLET-CARD-1 SVC-WALLET-CARD-2 VM-MIG-GAMES VM-VENUEOPS-GAME-1 | Operations: testReader, validateGameConfiguration. Spec: contracts (games) at the release tag, served by ADAM. Built for Games & Rides · Venue Management 1 of 4; additive to VenueOpsService, whose first-release owner (Hrushikant Patkar) reviews. Done when `games#testReader`, `games#validateGameConfiguration` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-MARKETING-9 | AM-MARKETING-CRM-P05 | [BE] MarketingService: endKioskAssist | 1 | Deep Khanvilkar | MarketingService | MIG-MARKETING-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: endKioskAssist. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Kiosk; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#endKioskAssist` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-MARKETING-10 | AM-MARKETING-CRM-P06 | [BE] MarketingService: addGuestNote, mergeGuests | 3 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-MARKETING-2 MIG-PII MIG-PLATFORM PLATFORM-IDEMPOTENCY PLATFORM-KERNEL PLATFORM-OUTBOX | Operations: addGuestNote, mergeGuests. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Staff App; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#addGuestNote`, `marketing-crm#mergeGuests` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | MIG-MARKETING-13 | AM-MARKETING-CRM-P08 | [DB] Forward migration V1171__marketing.sql: marketing for Marketing & CRM · Venue Management 1 of 5 (5 tables) | 3 | Hrushikant Patkar | MarketingService | MIG-BASELINE MIG-MARKETING VM-MIG-MARKETING | Tables: marketing.duplicate_candidate, marketing.guest_attribute_model, marketing.identity_rules, marketing.privacy_exception, marketing.privacy_request. Source DDL: backend/tenant/010-marketing.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `marketing.duplicate_candidate`, `marketing.guest_attribute_model`, `marketing.identity_rules`, `marketing.privacy_exception`, `marketing.privacy_request` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
15 | 2 | VM-MARKETING-MARKETING-1 | AM-MARKETING-CRM-P08 | [BE] MarketingService: createJourney, getLostItemMatches, listJourneys, listLostItems | 8 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-VENUEMAP PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-MARKETING | Operations beyond the first release: createJourney, getLostItemMatches, listJourneys, listLostItems. Additive to MarketingService; its first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#createJourney`, `marketing-crm#getLostItemMatches`, `marketing-crm#listJourneys`, `marketing-crm#listLostItems` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
14 | 3 | SVC-MARKETING-GUEST-3 | AM-MARKETING-CRM-P08 | [BE] MarketingService: mergeGuestProfiles, updateGuestProfile | 5 | Pranay Shinde | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: mergeGuestProfiles, updateGuestProfile. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 1 of 5; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#mergeGuestProfiles`, `marketing-crm#updateGuestProfile` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-GUESTS-7 | AM-MARKETING-CRM-P08 | [BE] MarketingService: decideDuplicateCandidate, getGuestAttributeModel, getGuestIntelligence, getGuestMatchPolicy | 5 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-MARKETING-13 MIG-MARKETING-2 MIG-MARKETING-6 MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: decideDuplicateCandidate, getGuestAttributeModel, getGuestIntelligence, getGuestMatchPolicy. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 1 of 5; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#decideDuplicateCandidate`, `marketing-crm#getGuestAttributeModel`, `marketing-crm#getGuestIntelligence`, `marketing-crm#getGuestMatchPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-GUESTS-8 | AM-MARKETING-CRM-P08 | [BE] MarketingService: getGuestRelationships, getIdentityResolutionRules, listDuplicateCandidates, setGuestAttributeModel | 5 | Deep Khanvilkar | MarketingService | MIG-MARKETING-13 MIG-MARKETING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getGuestRelationships, getIdentityResolutionRules, listDuplicateCandidates, setGuestAttributeModel. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 1 of 5; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#getGuestRelationships`, `marketing-crm#getIdentityResolutionRules`, `marketing-crm#listDuplicateCandidates`, `marketing-crm#setGuestAttributeModel` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-GUESTS-9 | AM-MARKETING-CRM-P08 | [BE] MarketingService: setGuestMatchPolicy, setGuestRelationships, setIdentityResolutionRules | 5 | Pranay Shinde | MarketingService | MIG-MARKETING-13 MIG-MARKETING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setGuestMatchPolicy, setGuestRelationships, setIdentityResolutionRules. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 1 of 5; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#setGuestMatchPolicy`, `marketing-crm#setGuestRelationships`, `marketing-crm#setIdentityResolutionRules` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-LOYALTY-8 | AM-MARKETING-CRM-P08 | [BE] MarketingService: adjustLoyaltyPoints | 2 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-MARKETING-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: adjustLoyaltyPoints. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 1 of 5; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#adjustLoyaltyPoints` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-MARKETING-15 | AM-MARKETING-CRM-P08 | [BE] MarketingService: setGuestExtraFields | 1 | Deep Khanvilkar | MarketingService | MIG-MARKETING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setGuestExtraFields. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 1 of 5; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#setGuestExtraFields` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | MIG-MARKETING-14 | AM-MARKETING-CRM-P08-2 | [DB] Forward migration V1172__marketing.sql: marketing for Marketing & CRM · Venue Management 2 of 5 (5 tables) | 3 | Hrushikant Patkar | MarketingService | MIG-BASELINE MIG-MARKETING VM-MIG-MARKETING | Tables: marketing.audience_activation, marketing.communication_preference_type, marketing.journey_enrollment, marketing.privacy_export_package, marketing.privacy_incident. Source DDL: backend/tenant/010-marketing.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `marketing.audience_activation`, `marketing.communication_preference_type`, `marketing.journey_enrollment`, `marketing.privacy_export_package`, `marketing.privacy_incident` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
14 | 3 | SVC-MARKETING-SEGMENT-5 | AM-MARKETING-CRM-P08-2 | [BE] MarketingService: previewSegment | 1 | Deep Khanvilkar | MarketingService | MIG-MARKETING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: previewSegment. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 2 of 5; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#previewSegment` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-CONSENT-13 | AM-MARKETING-CRM-P08-2 | [BE] MarketingService: listDataSubjectCustomer, listPrivacy, listPrivacyEvidenceCompliance, setCommunicationPreferenceMarketing | 8 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-MARKETING-13 MIG-MARKETING-14 MIG-MARKETING-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listDataSubjectCustomer, listPrivacy, listPrivacyEvidenceCompliance, setCommunicationPreferenceMarketing. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 2 of 5; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#listDataSubjectCustomer`, `marketing-crm#listPrivacy`, `marketing-crm#listPrivacyEvidenceCompliance`, `marketing-crm#setCommunicationPreferenceMarketing` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-CONSENT-14 | AM-MARKETING-CRM-P08-2 | [BE] MarketingService: setDataDiscoveryAccess, setPrivacyRequest | 5 | Pranay Shinde | MarketingService | MIG-MARKETING-13 MIG-MARKETING-14 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setDataDiscoveryAccess, setPrivacyRequest. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 2 of 5; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#setDataDiscoveryAccess`, `marketing-crm#setPrivacyRequest` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-GUESTS-10 | AM-MARKETING-CRM-P08-2 | [BE] MarketingService: activateAudience, getAudienceOverlap, importAudienceList, listAudienceActivations | 5 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-MARKETING-14 MIG-MARKETING-6 MIG-MARKETING-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: activateAudience, getAudienceOverlap, importAudienceList, listAudienceActivations. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 2 of 5; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#activateAudience`, `marketing-crm#getAudienceOverlap`, `marketing-crm#importAudienceList`, `marketing-crm#listAudienceActivations` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-MARKETING-16 | AM-MARKETING-CRM-P08-2 | [BE] MarketingService: activateJourney, getJourneyPerformance, listMessageTriggers, recordPrivacyIncident | 5 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-MARKETING-14 MIG-MARKETING-6 MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-MARKETING | Operations: activateJourney, getJourneyPerformance, listMessageTriggers, recordPrivacyIncident. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 2 of 5; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#activateJourney`, `marketing-crm#getJourneyPerformance`, `marketing-crm#listMessageTriggers`, `marketing-crm#recordPrivacyIncident` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-MARKETING-17 | AM-MARKETING-CRM-P08-2 | [BE] MarketingService: setMessageTrigger | 1 | Deep Khanvilkar | MarketingService | MIG-MARKETING MIG-MARKETING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setMessageTrigger. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 2 of 5; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#setMessageTrigger` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-MARKETING-GUESTS-11 | AM-MARKETING-CRM-P08-2 | [BE] MarketingService: listAudienceLists | 1 | Deep Khanvilkar | MarketingService | MIG-MARKETING-8 PLATFORM-KERNEL SVC-MARKETING-GUESTS-10 | Operations: listAudienceLists. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 2 of 5; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#listAudienceLists` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-CASE-9 | AM-MARKETING-CRM-P08-3 | [BE] MarketingService: setIntelligentRoutingSkill, setOrderBookingTicket, setServiceQueueDefinition | 8 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-MARKETING-6 MIG-MARKETING-9 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setIntelligentRoutingSkill, setOrderBookingTicket, setServiceQueueDefinition. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 3 of 5; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#setIntelligentRoutingSkill`, `marketing-crm#setOrderBookingTicket`, `marketing-crm#setServiceQueueDefinition` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-CONSENT-15 | AM-MARKETING-CRM-P08-3 | [BE] MarketingService: addSuppression | 1 | Deep Khanvilkar | MarketingService | MIG-MARKETING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: addSuppression. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 3 of 5; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#addSuppression` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-MARKETING-22 | AM-MARKETING-CRM-P08-3 | [BE] MarketingService: retryMessageDispatch | 2 | Deep Khanvilkar | MarketingService | MIG-MARKETING MIG-MARKETING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: retryMessageDispatch. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 3 of 5; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#retryMessageDispatch` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-MARKETING-MESSAGE-5 | AM-MARKETING-CRM-P08-3 | [BE] MarketingService: listSystemTransactionalTemplate | 2 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-MARKETING-6 PLATFORM-KERNEL SVC-MARKETING-MARKETING-17 SVC-MARKETING-MESSAGE-1 SVC-MARKETING-MESSAGE-2 | Operations: listSystemTransactionalTemplate. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 3 of 5; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#listSystemTransactionalTemplate` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-CASE-10 | AM-MARKETING-CRM-P08-4 | [BE] MarketingService: listEscalationCriticalCase, listServiceRootCause, listSlaPolicyService, setCaseCategoryDefinition | 8 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-MARKETING-10 MIG-MARKETING-6 MIG-MARKETING-9 MIG-ORDERS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listEscalationCriticalCase, listServiceRootCause, listSlaPolicyService, setCaseCategoryDefinition. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 4 of 5; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#listEscalationCriticalCase`, `marketing-crm#listServiceRootCause`, `marketing-crm#listSlaPolicyService`, `marketing-crm#setCaseCategoryDefinition` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-FEEDBACK-2 | AM-MARKETING-CRM-P08-4 | [BE] MarketingService: listCustomerSatisfactionFeedback, listReviews, respondToReview | 5 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-MARKETING-10 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listCustomerSatisfactionFeedback, listReviews, respondToReview. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 4 of 5; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#listCustomerSatisfactionFeedback`, `marketing-crm#listReviews`, `marketing-crm#respondToReview` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-MARKETING-23 | AM-MARKETING-CRM-P08-4 | [BE] MarketingService: setSlaPolicy | 2 | Deep Khanvilkar | MarketingService | MIG-MARKETING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setSlaPolicy. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 4 of 5; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#setSlaPolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | MIG-MARKETING-20 | AM-MARKETING-CRM-P08-5 | [DB] Forward migration V1226__marketing.sql: marketing for Marketing & CRM · Venue Management 5 of 5 (4 tables) | 3 | Hrushikant Patkar | MarketingService | MIG-BASELINE MIG-MARKETING VM-MIG-MARKETING | Tables: marketing.communication_policy_decision, marketing.sender_identity, marketing.waiver_signatory_rule, marketing.waiver_verification. Source DDL: backend/tenant/010-marketing.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `marketing.communication_policy_decision`, `marketing.sender_identity`, `marketing.waiver_signatory_rule`, `marketing.waiver_verification` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
18 | 3 | VM-ADM-041 | AM-MARKETING-CRM-P08-5 | [BE] ADM-041 System Transactional Template Registry | 2 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-MARKETING-MESSAGE-5 | Maintain centralized system/transactional communication templates used by TICVAI operational modules. This screen must not replace CRM's marketing template builder. Module: Platform. App: Venue Management. Done when `ADM-041` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
16 | 3 | SVC-MARKETING-CONSENT-18 | AM-MARKETING-CRM-P08-5 | [BE] MarketingService: listWaiverTriggerEligibility, setDigitalWaiverForm, setSignatorySignatureGuardian, setWaiverVerificationValidation | 8 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-MARKETING-20 MIG-MARKETING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listWaiverTriggerEligibility, setDigitalWaiverForm, setSignatorySignatureGuardian, setWaiverVerificationValidation. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 5 of 5; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#listWaiverTriggerEligibility`, `marketing-crm#setDigitalWaiverForm`, `marketing-crm#setSignatorySignatureGuardian`, `marketing-crm#setWaiverVerificationValidation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-MESSAGE-6 | AM-MARKETING-CRM-P08-5 | [BE] MarketingService: listBusinessEventNotification, listDeliveryCommunicationPlatform, setChannelProvider, setSenderIdentityDomain | 8 | Hrushikant Patkar | MarketingService | MIG-MARKETING MIG-MARKETING-20 MIG-MARKETING-6 MIG-MARKETING-9 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listBusinessEventNotification, listDeliveryCommunicationPlatform, setChannelProvider, setSenderIdentityDomain. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 5 of 5; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#listBusinessEventNotification`, `marketing-crm#listDeliveryCommunicationPlatform`, `marketing-crm#setChannelProvider`, `marketing-crm#setSenderIdentityDomain` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | VM-ADM-039 | AM-MARKETING-CRM-P08-5 | [BE] ADM-039 Channel & Provider Configuration | 3 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-MARKETING-MESSAGE-6 | Configure the external/internal services used by TICVAI to deliver communications. Module: Platform. App: Venue Management. Done when `ADM-039` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-040 | AM-MARKETING-CRM-P08-5 | [BE] ADM-040 Sender Identity, Domain & Brand Configuration | 3 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-MARKETING-MESSAGE-6 | Manage the identities from which TICVAI communications are sent. Module: Platform. App: Venue Management. Done when `ADM-040` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-042 | AM-MARKETING-CRM-P08-5 | [BE] ADM-042 Business Event & Notification Trigger Mapping | 2 | Pranay Shinde |  | SETUP-CLIENTS SVC-MARKETING-MESSAGE-6 | Map TICVAI business events to the operational communications they should generate. This is the core of the event-driven communication architecture. Module: Platform. App: Venue Management. Waits for its definition: ADM-042's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-042` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
17 | 3 | VM-ADM-047 | AM-MARKETING-CRM-P08-5 | [BE] ADM-047 AI Delivery Optimization & Communication Platform Diagnostics | 2 | Pranay Shinde |  | SETUP-CLIENTS SVC-AI-AI-1 SVC-MARKETING-MESSAGE-6 | Provide an AI intelligence layer focused specifically on communication infrastructure performance, not CRM marketing strategy. Module: Platform. App: Venue Management. Done when `ADM-047` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
15 | 3 | MIG-MARKETING-21 | AM-MARKETING-CRM-P13-2 | [DB] Forward migration V1227__marketing.sql: marketing for Marketing & CRM · CMS 2 of 4 (4 tables) | 3 | Hrushikant Patkar | MarketingService | MIG-BASELINE MIG-MARKETING VM-MIG-MARKETING | Tables: marketing.consent_capture_point, marketing.minor_privacy_rule, marketing.privacy_change_set, marketing.processing_purpose. Source DDL: backend/tenant/010-marketing.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `marketing.consent_capture_point`, `marketing.minor_privacy_rule`, `marketing.privacy_change_set`, `marketing.processing_purpose` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
16 | 3 | SVC-MARKETING-CONSENT-19 | AM-MARKETING-CRM-P13-2 | [BE] MarketingService: approvePrivacyTesting, listConsentEvidenceWithdrawal, listCustomerPrivacyConsent, listDataProcessingPurpose | 8 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-MARKETING-13 MIG-MARKETING-21 MIG-MARKETING-3 MIG-MARKETING-6 MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: approvePrivacyTesting, listConsentEvidenceWithdrawal, listCustomerPrivacyConsent, listDataProcessingPurpose. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · CMS 2 of 4; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#approvePrivacyTesting`, `marketing-crm#listConsentEvidenceWithdrawal`, `marketing-crm#listCustomerPrivacyConsent`, `marketing-crm#listDataProcessingPurpose` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-CONSENT-21 | AM-MARKETING-CRM-P13-2 | [BE] MarketingService: listPrivacyConsent, listPrivacyNoticePolicy, setConsentCapturePoint, setDataProcessingPurpose | 8 | Hrushikant Patkar | MarketingService | MIG-MARKETING MIG-MARKETING-14 MIG-MARKETING-21 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listPrivacyConsent, listPrivacyNoticePolicy, setConsentCapturePoint, setDataProcessingPurpose. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · CMS 2 of 4; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#listPrivacyConsent`, `marketing-crm#listPrivacyNoticePolicy`, `marketing-crm#setConsentCapturePoint`, `marketing-crm#setDataProcessingPurpose` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-CONSENT-22 | AM-MARKETING-CRM-P13-2 | [BE] MarketingService: setLegalHold, setMinorGuardianAge, setPrivacyComplianceException, setPrivacyNoticePolicyGovernance | 8 | Tanmay Dukhande | MarketingService | MIG-MARKETING MIG-MARKETING-13 MIG-MARKETING-21 MIG-MARKETING-3 MIG-WHITELABEL PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setLegalHold, setMinorGuardianAge, setPrivacyComplianceException, setPrivacyNoticePolicyGovernance. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · CMS 2 of 4; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#setLegalHold`, `marketing-crm#setMinorGuardianAge`, `marketing-crm#setPrivacyComplianceException`, `marketing-crm#setPrivacyNoticePolicyGovernance` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-MARKETING-CONSENT-12 | AM-MARKETING-CRM-P08 | [BE] MarketingService: getConsentHistory, listPrivacyCompliance | 3 | Deep Khanvilkar | MarketingService | MIG-MARKETING MIG-MARKETING-13 MIG-MARKETING-3 MIG-MARKETING-6 PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-MARKETING-CONSENT-1 SVC-MARKETING-CONSENT-14 SVC-MARKETING-CONSENT-22 SVC-MARKETING-CONSENT-24 SVC-MARKETING-CONSENT-3 SVC-MARKETING-CONSENT-4 SVC-MARKETING-CONSENT-7 SVC-MARKETING-GUESTS-2 SVC-MARKETING-GUESTS-3 SVC-MARKETING-MARKETING-6 SVC-ORDER-CART-1 SVC-ORDER-ORDERS-5 | Operations: getConsentHistory, listPrivacyCompliance. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 1 of 5; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#getConsentHistory`, `marketing-crm#listPrivacyCompliance` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-MARKETING-CONSENT-20 | AM-MARKETING-CRM-P13-2 | [BE] MarketingService: listDataRetentionExpiry, listDeletionAnonymizationRestriction, listDeviceConsents, listPrivacyComplianceExceptions | 8 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-MARKETING-13 MIG-MARKETING-3 PLATFORM-KERNEL SVC-MARKETING-CONSENT-1 SVC-MARKETING-CONSENT-22 SVC-MARKETING-CONSENT-3 SVC-MARKETING-CONSENT-7 SVC-MARKETING-GUESTS-2 | Operations: listDataRetentionExpiry, listDeletionAnonymizationRestriction, listDeviceConsents, listPrivacyComplianceExceptions. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · CMS 2 of 4; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#listDataRetentionExpiry`, `marketing-crm#listDeletionAnonymizationRestriction`, `marketing-crm#listDeviceConsents`, `marketing-crm#listPrivacyComplianceExceptions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | MIG-MARKETING-22 | AM-MARKETING-CRM-P13-3 | [DB] Forward migration V1228__marketing.sql: marketing for Marketing & CRM · CMS 3 of 4 (1 tables) | 1 | Hrushikant Patkar | MarketingService | MIG-BASELINE MIG-MARKETING VM-MIG-MARKETING | Tables: marketing.waiver_localisation. Source DDL: backend/tenant/010-marketing.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `marketing.waiver_localisation` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
16 | 3 | SVC-MARKETING-CONSENT-25 | AM-MARKETING-CRM-P13-3 | [BE] MarketingService: approveWaiverTesting, getLocalizationBrandingCustomer, listDigitalSigningCollection, listDynamicFieldQuestion | 8 | Hrushikant Patkar | MarketingService | MIG-MARKETING MIG-MARKETING-22 MIG-MARKETING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: approveWaiverTesting, getLocalizationBrandingCustomer, listDigitalSigningCollection, listDynamicFieldQuestion. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · CMS 3 of 4; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#approveWaiverTesting`, `marketing-crm#getLocalizationBrandingCustomer`, `marketing-crm#listDigitalSigningCollection`, `marketing-crm#listDynamicFieldQuestion` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-MARKETING-CONSENT-17 | AM-MARKETING-CRM-P08-5 | [BE] MarketingService: listParticipantWaiverStatus, listVersioningEffectiveDate, listWaiver, listWaiverTemplateMaster | 8 | Pranay Shinde | MarketingService | MIG-CATALOGUE MIG-MARKETING MIG-MARKETING-2 MIG-MARKETING-20 MIG-MARKETING-6 MIG-ORDERS MIG-PII PLATFORM-KERNEL SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-FNB-FNB-12 SVC-IDENTITY-GUESTAUTH-1 SVC-IDENTITY-GUESTAUTH-2 SVC-IDENTITY-GUESTAUTH-3 SVC-IDENTITY-IDENTITY-4 SVC-MARKETING-CONSENT-18 SVC-MARKETING-CONSENT-25 SVC-MARKETING-CONSENT-6 SVC-MARKETING-CONSENT-8 SVC-MARKETING-MARKETING-1 SVC-MARKETING-MARKETING-10 SVC-MARKETING-MARKETING-6 SVC-MARKETING-MARKETING-7 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-18 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-4 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 VM-CATALOGUE-EVENT-1 VM-ORDER-ORDERS-1 VM-ORDER-ORDERS-3 | Operations: listParticipantWaiverStatus, listVersioningEffectiveDate, listWaiver, listWaiverTemplateMaster. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 5 of 5; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#listParticipantWaiverStatus`, `marketing-crm#listVersioningEffectiveDate`, `marketing-crm#listWaiver`, `marketing-crm#listWaiverTemplateMaster` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-CONSENT-26 | AM-MARKETING-CRM-P13-3 | [BE] MarketingService: listProductEventExperience, listWaiverConsent, listWaiverVerificationQueue, setLocalizationBrandingCustomer | 8 | Tanmay Dukhande | MarketingService | MIG-MARKETING MIG-MARKETING-2 MIG-MARKETING-20 MIG-MARKETING-22 MIG-MARKETING-6 MIG-PII PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listProductEventExperience, listWaiverConsent, listWaiverVerificationQueue, setLocalizationBrandingCustomer. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · CMS 3 of 4; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#listProductEventExperience`, `marketing-crm#listWaiverConsent`, `marketing-crm#listWaiverVerificationQueue`, `marketing-crm#setLocalizationBrandingCustomer` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | MIG-MARKETING-23 | AM-MARKETING-CRM-P12 | [DB] Forward migration V1229__marketing.sql: marketing for Marketing & CRM · Support Console 1 of 2 (1 tables) | 1 | Hrushikant Patkar | MarketingService | MIG-BASELINE MIG-MARKETING VM-MIG-MARKETING | Tables: marketing.case_compensation_request. Source DDL: backend/tenant/010-marketing.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `marketing.case_compensation_request` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
16 | 3 | SVC-MARKETING-CASE-15 | AM-MARKETING-CRM-P12 | [BE] MarketingService: createCaseClassificationIntelligent, listCaseResolutionClosure, listContact, listCustomerService | 8 | Hrushikant Patkar | MarketingService | MIG-MARKETING MIG-MARKETING-23 MIG-MARKETING-6 MIG-MARKETING-9 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createCaseClassificationIntelligent, listCaseResolutionClosure, listContact, listCustomerService. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Support Console 1 of 2; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#createCaseClassificationIntelligent`, `marketing-crm#listCaseResolutionClosure`, `marketing-crm#listContact`, `marketing-crm#listCustomerService` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-MARKETING-CASE-5 | AM-MARKETING-CRM-P08 | [BE] MarketingService: listCustomerServiceProfile | 3 | Deep Khanvilkar | MarketingService | MIG-ACCESS MIG-MARKETING MIG-MARKETING-6 MIG-ORDERS MIG-PII PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-2 SVC-ACCESS-ACCESS-61 SVC-ACCESS-VALIDATION-2 SVC-CATALOGUE-CATALOGUE-16 SVC-CATALOGUE-ENTITLEMENT-3 SVC-IDENTITY-GUESTAUTH-1 SVC-IDENTITY-GUESTAUTH-2 SVC-IDENTITY-GUESTAUTH-3 SVC-IDENTITY-IDENTITY-4 SVC-MARKETING-CASE-15 SVC-MARKETING-CASE-7 SVC-MARKETING-CASE-8 SVC-MARKETING-CONSENT-1 SVC-MARKETING-CONSENT-15 SVC-MARKETING-CONSENT-3 SVC-MARKETING-CONSENT-7 SVC-MARKETING-FEEDBACK-1 SVC-MARKETING-GUEST-2 SVC-MARKETING-GUEST-3 SVC-MARKETING-GUESTS-2 SVC-MARKETING-LOYALTY-2 SVC-MARKETING-LOYALTY-8 SVC-MARKETING-MARKETING-10 SVC-MARKETING-MARKETING-11 SVC-MARKETING-MARKETING-18 SVC-MARKETING-MARKETING-21 SVC-MARKETING-MARKETING-4 SVC-MARKETING-MARKETING-5 SVC-MARKETING-MARKETING-6 SVC-MARKETING-MARKETING-7 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-14 SVC-ORDER-DRAFTED-17 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-2 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-12 SVC-ORDER-ORDERS-14 SVC-ORDER-ORDERS-18 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-29 SVC-ORDER-ORDERS-3 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-SUBSCRIPTION-6 VM-ACCESS-ACCESS-1 VM-MARKETING-MARKETING-2 VM-ORDER-ORDERS-1 VM-ORDER-ORDERS-3 | Operations: listCustomerServiceProfile. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 1 of 5; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#listCustomerServiceProfile` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-CASE-16 | AM-MARKETING-CRM-P12 | [BE] MarketingService: listEscalationCollaborationInternal, setCaseInvestigationResolution, setRefundCompensationService | 8 | Tanmay Dukhande | MarketingService | MIG-MARKETING-23 MIG-MARKETING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listEscalationCollaborationInternal, setCaseInvestigationResolution, setRefundCompensationService. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Support Console 1 of 2; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#listEscalationCollaborationInternal`, `marketing-crm#setCaseInvestigationResolution`, `marketing-crm#setRefundCompensationService` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
17 | 3 | SVC-MARKETING-CASE-17 | AM-MARKETING-CRM-P12-2 | [BE] MarketingService: listContactAutomation | 2 | Deep Khanvilkar | MarketingService | MIG-MARKETING-6 PLATFORM-KERNEL SVC-MARKETING-CASE-2 | Operations: listContactAutomation. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Support Console 2 of 2; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#listContactAutomation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
16 | 3 | SVC-MARKETING-MESSAGE-8 | AM-MARKETING-CRM-P10 | [BE] MarketingService: getMessageStatus, sendTransactionalMessage | 3 | Deep Khanvilkar | MarketingService | MIG-MARKETING MIG-MARKETING-20 MIG-MARKETING-9 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getMessageStatus, sendTransactionalMessage. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Partner Portal; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#getMessageStatus`, `marketing-crm#sendTransactionalMessage` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-MARKETING-CASE-6 | AM-MARKETING-CRM-P08-3 | [BE] MarketingService: listCaseCategories, listQualityAgentEvaluation, listServiceQueues, listUnifiedInteractionCommunication | 5 | Tanmay Dukhande | MarketingService | MIG-MARKETING MIG-MARKETING-5 MIG-MARKETING-6 MIG-MARKETING-9 PLATFORM-KERNEL SVC-FNB-FNB-17 SVC-FNB-FNB-21 SVC-FNB-FNB-6 SVC-IDENTITY-IDENTITY-4 SVC-MARKETING-CAMPAIGN-1 SVC-MARKETING-CASE-10 SVC-MARKETING-CASE-2 SVC-MARKETING-CASE-7 SVC-MARKETING-CASE-9 SVC-MARKETING-CONSENT-6 SVC-MARKETING-MARKETING-18 SVC-MARKETING-MARKETING-19 SVC-MARKETING-MARKETING-21 SVC-MARKETING-MARKETING-22 SVC-MARKETING-MARKETING-3 SVC-MARKETING-MARKETING-5 SVC-MARKETING-MARKETING-9 SVC-MARKETING-MESSAGE-1 SVC-MARKETING-MESSAGE-3 SVC-MARKETING-MESSAGE-8 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-26 SVC-PLATFORM-PUBLICAPI-1 SVC-TENANCY-WORKFORCE-3 | Operations: listCaseCategories, listQualityAgentEvaluation, listServiceQueues, listUnifiedInteractionCommunication. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 3 of 5; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#listCaseCategories`, `marketing-crm#listQualityAgentEvaluation`, `marketing-crm#listServiceQueues`, `marketing-crm#listUnifiedInteractionCommunication` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-MARKETING-MESSAGE-4 | AM-MARKETING-CRM-P08-3 | [BE] MarketingService: listCommunicationService, listDeliveryQueueFailure, listProviderHealthUsage, listRoutingPriorityThrottling | 8 | Pranay Shinde | MarketingService | MIG-MARKETING MIG-MARKETING-6 MIG-MARKETING-9 PLATFORM-KERNEL SVC-FNB-FNB-17 SVC-FNB-FNB-21 SVC-FNB-FNB-6 SVC-IDENTITY-IDENTITY-4 SVC-MARKETING-CAMPAIGN-1 SVC-MARKETING-CONSENT-6 SVC-MARKETING-MARKETING-17 SVC-MARKETING-MARKETING-22 SVC-MARKETING-MESSAGE-1 SVC-MARKETING-MESSAGE-2 SVC-MARKETING-MESSAGE-3 SVC-MARKETING-MESSAGE-6 SVC-MARKETING-MESSAGE-8 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-26 SVC-PLATFORM-PUBLICAPI-1 SVC-TENANCY-WORKFORCE-3 | Operations: listCommunicationService, listDeliveryQueueFailure, listProviderHealthUsage, listRoutingPriorityThrottling. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 3 of 5; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#listCommunicationService`, `marketing-crm#listDeliveryQueueFailure`, `marketing-crm#listProviderHealthUsage`, `marketing-crm#listRoutingPriorityThrottling` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
19 | 3 | VM-ADM-038 | AM-MARKETING-CRM-P08-5 | [BE] ADM-038 Communication Service Command Center | 3 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-MARKETING-MESSAGE-4 | Provide administrators and technical/operations teams with a centralized view of the health and activity of TICVAI's communication infrastructure. This is not a marketing dashboard. Module: Platform. App: Venue Management. Done when `ADM-038` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-043 | AM-MARKETING-CRM-P08-5 | [BE] ADM-043 Routing, Priority, Throttling & Fallback Rules | 3 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-MARKETING-MESSAGE-4 | Determine how TICVAI delivers a message after a communication requirement has been created. Module: Platform. App: Venue Management. Done when `ADM-043` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-045 | AM-MARKETING-CRM-P08-5 | [BE] ADM-045 Delivery Queue, Failure & Retry Management | 2 | Pranay Shinde |  | SETUP-CLIENTS SVC-MARKETING-MESSAGE-4 | Provide technical/operations teams with visibility into communications currently being processed or failing. Module: Platform. App: Venue Management. Done when `ADM-045` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
19 | 3 | VM-ADM-046 | AM-MARKETING-CRM-P08-5 | [BE] ADM-046 Provider Health, Usage & Cost Monitoring | 2 | Pranay Shinde |  | SETUP-CLIENTS SVC-MARKETING-MESSAGE-4 | Monitor the operational and commercial performance of communication providers. Module: Platform. App: Venue Management. Done when `ADM-046` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | SVC-MARKETING-CONSENT-16 | AM-MARKETING-CRM-P08-5 | [BE] MarketingService: getSignatorySignatureGuardian, listComplianceEvidenceWaiver, listConsentPreferenceCommunication, listMinorGuardianGroup | 8 | Hrushikant Patkar | MarketingService | MIG-MARKETING MIG-MARKETING-2 MIG-MARKETING-20 MIG-MARKETING-6 MIG-ORDERS MIG-PII PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-FNB-FNB-12 SVC-FNB-FNB-17 SVC-FNB-FNB-21 SVC-FNB-FNB-6 SVC-IDENTITY-GUESTAUTH-1 SVC-IDENTITY-GUESTAUTH-2 SVC-IDENTITY-GUESTAUTH-3 SVC-IDENTITY-IDENTITY-4 SVC-MARKETING-CAMPAIGN-1 SVC-MARKETING-CONSENT-1 SVC-MARKETING-CONSENT-15 SVC-MARKETING-CONSENT-18 SVC-MARKETING-CONSENT-3 SVC-MARKETING-CONSENT-4 SVC-MARKETING-CONSENT-6 SVC-MARKETING-CONSENT-7 SVC-MARKETING-CONSENT-8 SVC-MARKETING-GUESTS-9 SVC-MARKETING-MARKETING-1 SVC-MARKETING-MARKETING-10 SVC-MARKETING-MARKETING-22 SVC-MARKETING-MARKETING-6 SVC-MARKETING-MARKETING-7 SVC-MARKETING-MESSAGE-1 SVC-MARKETING-MESSAGE-3 SVC-MARKETING-MESSAGE-8 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-18 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-26 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-4 SVC-ORDER-ORDERS-5 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-PUBLICAPI-1 SVC-PLATFORM-SUBSCRIPTION-6 SVC-TENANCY-WORKFORCE-3 VM-ORDER-ORDERS-1 VM-ORDER-ORDERS-3 | Operations: getSignatorySignatureGuardian, listComplianceEvidenceWaiver, listConsentPreferenceCommunication, listMinorGuardianGroup. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · Venue Management 5 of 5; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#getSignatorySignatureGuardian`, `marketing-crm#listComplianceEvidenceWaiver`, `marketing-crm#listConsentPreferenceCommunication`, `marketing-crm#listMinorGuardianGroup` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
19 | 3 | VM-ADM-044 | AM-MARKETING-CRM-P08-5 | [BE] ADM-044 Consent, Preference & Communication Policy Enforcement | 2 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-MARKETING-CONSENT-16 | Create a central enforcement layer ensuring communications respect the appropriate communication rules. Module: Platform. App: Venue Management. Waits for its definition: ADM-044's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-044` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | SVC-MARKETING-CONSENT-27 | AM-MARKETING-CRM-P13-4 | [BE] MarketingService: listMissingExpiredInvalid, listSiteWaiverException, listWaiverComplianceOperational, listWaiverComplianceRisk | 8 | Tanmay Dukhande | MarketingService | MIG-CATALOGUE MIG-MARKETING MIG-MARKETING-20 MIG-MARKETING-6 MIG-ORDERS MIG-PII PLATFORM-KERNEL SVC-CATALOGUE-EVENT-1 SVC-CATALOGUE-EVENT-3 SVC-CATALOGUE-EVENTS-1 SVC-FNB-FNB-12 SVC-FNB-FNB-17 SVC-FNB-FNB-21 SVC-FNB-FNB-6 SVC-IDENTITY-GUESTAUTH-1 SVC-IDENTITY-GUESTAUTH-2 SVC-IDENTITY-GUESTAUTH-3 SVC-IDENTITY-IDENTITY-4 SVC-MARKETING-CAMPAIGN-1 SVC-MARKETING-CONSENT-18 SVC-MARKETING-CONSENT-25 SVC-MARKETING-CONSENT-4 SVC-MARKETING-CONSENT-6 SVC-MARKETING-CONSENT-8 SVC-MARKETING-MARKETING-1 SVC-MARKETING-MARKETING-10 SVC-MARKETING-MARKETING-22 SVC-MARKETING-MARKETING-6 SVC-MARKETING-MARKETING-7 SVC-MARKETING-MESSAGE-1 SVC-MARKETING-MESSAGE-3 SVC-MARKETING-MESSAGE-8 SVC-ORDER-CART-1 SVC-ORDER-DRAFTED-2 SVC-ORDER-ORDER-1 SVC-ORDER-ORDER-3 SVC-ORDER-ORDER-4 SVC-ORDER-ORDER-5 SVC-ORDER-ORDERS-18 SVC-ORDER-ORDERS-25 SVC-ORDER-ORDERS-26 SVC-ORDER-ORDERS-28 SVC-ORDER-ORDERS-4 SVC-ORDER-RESERVATION-1 SVC-ORDER-SYNC-1 SVC-PLATFORM-PUBLICAPI-1 SVC-PLATFORM-SUBSCRIPTION-6 SVC-TENANCY-WORKFORCE-3 VM-CATALOGUE-EVENT-1 VM-ORDER-ORDERS-1 VM-ORDER-ORDERS-3 | Operations: listMissingExpiredInvalid, listSiteWaiverException, listWaiverComplianceOperational, listWaiverComplianceRisk. Spec: contracts (marketing-crm) at the release tag, served by ADAM. Built for Marketing & CRM · CMS 4 of 4; additive to MarketingService, whose first-release owner (Pranay Shinde) reviews. Done when `marketing-crm#listMissingExpiredInvalid`, `marketing-crm#listSiteWaiverException`, `marketing-crm#listWaiverComplianceOperational`, `marketing-crm#listWaiverComplianceRisk` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
9 | 3 | MIG-AI-7 | AM-AI-P08 | [DB] Forward migration V1176__ai.sql: ai for AI · Venue Management 1 of 2 (6 tables) | 3 | Hrushikant Patkar | AiService | MIG-AI MIG-ASSETS MIG-BASELINE MIG-IDENTITY VM-MIG-AI | Tables: ai.case_action, ai.case_evidence, ai.entity_risk, ai.layout_draft, ai.risk_alert, ai.risk_edge. Source DDL: backend/tenant/010-ai.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `ai.case_action`, `ai.case_evidence`, `ai.entity_risk`, `ai.layout_draft`, `ai.risk_alert`, `ai.risk_edge` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
18 | 3 | VM-ADM-686 | AM-AI-P08 | [BE] ADM-686 Anonymous, Known & Identity-Transition Personalization.123 | 2 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-AI-RECOMMEND-2 | Allow useful recommendations even when TICVAI does not yet know the customer's identity. Module: Commercial. App: Venue Management. Waits for its definition: ADM-686's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-686` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-687 | AM-AI-P08 | [BE] ADM-687 AI Explainability, Confidence & Model Governance | 2 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-AI-RECOMMEND-2 | Make personalized AI decisions understandable and governable. Module: Commercial. App: Venue Management. Done when `ADM-687` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-696 | AM-AI-P08 | [BE] ADM-696 AI Risk, Fairness, Explainability & Safety Center | 3 | Pranay Shinde |  | SETUP-CLIENTS SVC-AI-GOVERNANCE-2 SVC-AI-MODELS-2 SVC-AI-RECOMMEND-2 | Provide governance over how AI recommendation decisions behave across customer populations and business contexts. Module: Commercial. App: Venue Management. Waits for its definition: ADM-696's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-696` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-697 | AM-AI-P08 | [BE] ADM-697 Recommendation Audit, Decision Trace & Investigation | 2 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-AI-RECOMMEND-2 | Provide transaction-level explainability for Customer Service, Commercial, Audit, and technical investigation. Module: Commercial. App: Venue Management. Waits for its definition: ADM-697's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-697` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
11 | 3 | SVC-AI-ACTIONS-4 | AM-AI-P08 | [BE] AiService: setAiTool | 2 | Tanmay Dukhande | AiService | MIG-AI-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setAiTool. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · Venue Management 1 of 2; additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#setAiTool` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-AI-GENERATE-5 | AM-AI-P08 | [BE] AiService: generateVenueLayout | 2 | Tanmay Dukhande | AiService | MIG-AI MIG-AI-7 MIG-ASSETS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: generateVenueLayout. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · Venue Management 1 of 2; additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#generateVenueLayout` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-AI-RETRIEVAL-3 | AM-AI-P08 | [BE] AiService: listIndexJobs, listIndexSources, removeIndexEntry | 3 | Tanmay Dukhande | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listIndexJobs, listIndexSources, removeIndexEntry. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · Venue Management 1 of 2; additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#listIndexJobs`, `ai#listIndexSources`, `ai#removeIndexEntry` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-AI-RISK-3 | AM-AI-P08 | [BE] AiService: addRiskCaseEvidence, closeRiskCase, configureRiskStrategy, createRiskCase | 8 | Tanmay Dukhande | AiService | MIG-AI MIG-AI-6 MIG-AI-7 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: addRiskCaseEvidence, closeRiskCase, configureRiskStrategy, createRiskCase. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · Venue Management 1 of 2; additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#addRiskCaseEvidence`, `ai#closeRiskCase`, `ai#configureRiskStrategy`, `ai#createRiskCase` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-AI-RISK-4 | AM-AI-P08 | [BE] AiService: decideRiskAlert, expandRiskNetwork, getEntityRisk, getRiskCase | 8 | Tanmay Dukhande | AiService | MIG-AI-6 MIG-AI-7 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: decideRiskAlert, expandRiskNetwork, getEntityRisk, getRiskCase. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · Venue Management 1 of 2; additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#decideRiskAlert`, `ai#expandRiskNetwork`, `ai#getEntityRisk`, `ai#getRiskCase` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-AI-RISK-5 | AM-AI-P08 | [BE] AiService: listRiskAlerts, proposeRiskAction, scoreApprovalRequest, scoreTransactionRisk | 8 | Tanmay Dukhande | AiService | MIG-AI MIG-AI-2 MIG-AI-3 MIG-AI-6 MIG-AI-7 MIG-APPROVALS MIG-APPROVALS-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-AI | Operations: listRiskAlerts, proposeRiskAction, scoreApprovalRequest, scoreTransactionRisk. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · Venue Management 1 of 2; additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#listRiskAlerts`, `ai#proposeRiskAction`, `ai#scoreApprovalRequest`, `ai#scoreTransactionRisk` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
15 | 3 | VM-ADM-633 | AM-AI-P08 | [BE] ADM-633 Fraud Alert, Investigation & Case Management | 5 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-AI-RISK-3 SVC-AI-RISK-4 SVC-AI-RISK-5 SVC-ORDER-ORDERS-27 VM-ORDER-ORDERS-1 VM-ORDER-ORDERS-2 | Convert suspicious activity into controlled investigation cases. Module: Commercial. App: Venue Management. Done when `ADM-633` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
18 | 3 | VM-ADM-637 | AM-AI-P08 | [BE] ADM-637 AI Fraud, Anomaly & Payment Intelligence Center | 3 | Tanmay Dukhande |  | SETUP-CLIENTS SVC-AI-RISK-3 SVC-AI-RISK-4 SVC-AI-RISK-5 SVC-ORDER-PAYMENTS-13 VM-ORDER-ORDERS-2 | Provide governed AI/ML capabilities for fraud detection and payment anomaly identification. Module: Commercial. App: Venue Management. Waits for its definition: ADM-637's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-637` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
12 | 3 | SVC-AI-FORECAST-5 | AM-AI-P08 | [BE] AiService: compareForecastScenarios | 1 | Deep Khanvilkar | AiService | MIG-AI PLATFORM-KERNEL SVC-AI-FORECAST-1 SVC-AI-FORECAST-3 | Operations: compareForecastScenarios. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · Venue Management 1 of 2; additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#compareForecastScenarios` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-AI-RECOMMEND-3 | AM-AI-P08 | [BE] AiService: getCustomerRecommendationProfile, simulateRecommendationDecision | 3 | Tanmay Dukhande | AiService | MIG-AI PLATFORM-KERNEL SVC-AI-RECOMMEND-1 | Operations: getCustomerRecommendationProfile, simulateRecommendationDecision. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · Venue Management 1 of 2; additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#getCustomerRecommendationProfile`, `ai#simulateRecommendationDecision` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | VM-ADM-680 | AM-AI-P08 | [BE] ADM-680 Customer Recommendation Profile | 2 | Deep Khanvilkar |  | SETUP-CLIENTS SVC-AI-RECOMMEND-2 SVC-AI-RECOMMEND-3 SVC-MARKETING-GUEST-4 | Provide the recommendation engine's commercially relevant customer context used for personalization. This should not become another CRM profile screen. CRM remains the authoritative source of customer information. Board 5 displays only the attributes relevant to recommendation decisioning. Module: Commercial. App: Venue Management. Waits for its definition: ADM-680's spec says a person must define it before it is built (its gaps), so this task starts once the lead has put the definition in ADAM, no earlier than 2 November 2026; until then build nothing from the default layout. Done when `ADM-680` reaches every state its spec lists, every navigation link works, an allowed and a refused user see what its permissions say, and it calls only its bound operations (block-test-strategy).
8 | 3 | MIG-REPORTING-4 | AM-AI-P16 | [DB] Forward migration V1177__reporting.sql: reporting for AI · Analytics (1 tables) | 1 | Hrushikant Patkar | ReportingService | MIG-BASELINE MIG-REPORTING VM-MIG-REPORTING | Tables: reporting.anomaly. Source DDL: backend/tenant/010-reporting.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `reporting.anomaly` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
9 | 3 | MIG-AI-8 | AM-AI-P16 | [DB] Forward migration V1066__ai.sql: ai for AI · Analytics (1 tables) | 1 | Hrushikant Patkar | AiService | MIG-AI MIG-BASELINE VM-MIG-AI | Tables: ai.suggestion_outcome. Source DDL: backend/tenant/010-ai.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `ai.suggestion_outcome` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-AI-AI-5 | AM-AI-P16 | [BE] AiService: recordSuggestionOutcome | 1 | Deep Khanvilkar | AiService | MIG-AI MIG-AI-8 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: recordSuggestionOutcome. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · Analytics; additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#recordSuggestionOutcome` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-AI-GOVERNANCE-6 | AM-AI-P16 | [BE] AiService: configureAiCapability, listAiInteractions | 5 | Tanmay Dukhande | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: configureAiCapability, listAiInteractions. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · Analytics; additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#configureAiCapability`, `ai#listAiInteractions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-AI-INSIGHTS-2 | AM-AI-P16 | [BE] AiService: configureAnomalyDetector, listAnomalyDetectors | 3 | Tanmay Dukhande | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: configureAnomalyDetector, listAnomalyDetectors. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · Analytics; additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#configureAnomalyDetector`, `ai#listAnomalyDetectors` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-REPORTING-REPORTING-8 | AM-AI-P16 | [BE] ReportingService: listAnalyticsAnomalies, setAnalyticsGovernancePolicy | 2 | Deep Khanvilkar | ReportingService | MIG-REPORTING-2 MIG-REPORTING-4 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: listAnalyticsAnomalies, setAnalyticsGovernancePolicy. Spec: contracts (reporting) at the release tag, served by ADAM. Built for AI · Analytics; additive to ReportingService, whose first-release owner (Tanmay Dukhande) reviews. Done when `reporting#listAnalyticsAnomalies`, `reporting#setAnalyticsGovernancePolicy` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-WHITELABEL-CONTENT-8 | AM-AI-P12 | [BE] WhiteLabelService: listFaqs | 1 | Tanmay Dukhande | WhiteLabelService | MIG-WHITELABEL PLATFORM-KERNEL SVC-WHITELABEL-CONTENT-5 | Operations: listFaqs. Spec: contracts (white-label) at the release tag, served by ADAM. Built for AI · Support Console; additive to WhiteLabelService, whose first-release owner (Tanmay Dukhande) reviews. Done when `white-label#listFaqs` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
9 | 3 | MIG-AI-9 | AM-AI-P09 | [DB] Forward migration V1067__ai.sql: ai for AI · TICVAI Console 1 of 6 (1 tables) | 1 | Hrushikant Patkar | AiService | MIG-AI MIG-BASELINE VM-MIG-AI | Tables: ai.signal_source. Source DDL: backend/tenant/010-ai.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `ai.signal_source` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-AI-FORECAST-6 | AM-AI-P09 | [BE] AiService: configureForecastSignalSource, listForecastSignals | 2 | Tanmay Dukhande | AiService | MIG-AI-9 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: configureForecastSignalSource, listForecastSignals. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · TICVAI Console 1 of 6; additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#configureForecastSignalSource`, `ai#listForecastSignals` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
9 | 3 | MIG-AI-12 | AM-AI-P09-2 | [DB] Forward migration V1230__ai.sql: ai for AI · TICVAI Console 2 of 6 (4 tables) | 3 | Hrushikant Patkar | AiService | MIG-AI MIG-ASSETS MIG-BASELINE MIG-IDENTITY VM-MIG-AI | Tables: ai.blueprint, ai.blueprint_decision, ai.config_session, ai.config_source. Source DDL: backend/tenant/010-ai.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `ai.blueprint`, `ai.blueprint_decision`, `ai.config_session`, `ai.config_source` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-AI-CONFIGURE-3 | AM-AI-P09-2 | [BE] AiService: answerConfigurationQuestion, attachConfigurationSource, buildConfigurationPlan, decideBlueprintRecommendation | 8 | Tanmay Dukhande | AiService | MIG-AI MIG-AI-12 MIG-AI-2 MIG-AI-3 MIG-ASSETS PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: answerConfigurationQuestion, attachConfigurationSource, buildConfigurationPlan, decideBlueprintRecommendation. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · TICVAI Console 2 of 6; additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#answerConfigurationQuestion`, `ai#attachConfigurationSource`, `ai#buildConfigurationPlan`, `ai#decideBlueprintRecommendation` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-AI-CONFIGURE-4 | AM-AI-P09-2 | [BE] AiService: getConfigurationBlueprint, listConfigurationSessions, listConfigurationSources, startConfigurationSession | 5 | Hrushikant Patkar | AiService | MIG-AI MIG-AI-12 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: getConfigurationBlueprint, listConfigurationSessions, listConfigurationSources, startConfigurationSession. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · TICVAI Console 2 of 6; additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#getConfigurationBlueprint`, `ai#listConfigurationSessions`, `ai#listConfigurationSources`, `ai#startConfigurationSession` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-AI-ACTIONS-5 | AM-AI-P09-3 | [BE] AiService: simulateActionPlan | 2 | Deep Khanvilkar | AiService | MIG-AI MIG-AI-2 MIG-AI-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: simulateActionPlan. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · TICVAI Console 3 of 6; additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#simulateActionPlan` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-AI-ACTIONS-6 | AM-AI-P09-4 | [BE] AiService: cancelActionPlan, pauseActionPlan, resumeActionPlan, retryActionStep | 8 | Tanmay Dukhande | AiService | MIG-AI MIG-AI-2 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: cancelActionPlan, pauseActionPlan, resumeActionPlan, retryActionStep. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · TICVAI Console 4 of 6; additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#cancelActionPlan`, `ai#pauseActionPlan`, `ai#resumeActionPlan`, `ai#retryActionStep` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-AI-ACTIONS-8 | AM-AI-P09-4 | [BE] AiService: rollbackActionPlan | 3 | Deep Khanvilkar | AiService | MIG-AI MIG-AI-2 MIG-AI-3 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: rollbackActionPlan. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · TICVAI Console 4 of 6; additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#rollbackActionPlan` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-AI-GOVERNANCE-7 | AM-AI-P09-5 | [BE] AiService: createAiPolicyException, resumeAiCapability | 5 | Pranay Shinde | AiService | MIG-AI PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createAiPolicyException, resumeAiCapability. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · TICVAI Console 5 of 6; additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#createAiPolicyException`, `ai#resumeAiCapability` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-AI-MONITORING-2 | AM-AI-P16 | [BE] AiService: listAiCapabilityMaturity | 1 | Deep Khanvilkar | AiService | MIG-AI PLATFORM-KERNEL SVC-AI-GOVERNANCE-2 SVC-AI-GOVERNANCE-6 SVC-AI-GOVERNANCE-7 SVC-AI-MONITORING-1 | Operations: listAiCapabilityMaturity. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · Analytics; additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#listAiCapabilityMaturity` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
9 | 3 | MIG-AI-13 | AM-AI-P09-6 | [DB] Forward migration V1231__ai.sql: ai for AI · TICVAI Console 6 of 6 (4 tables) | 3 | Hrushikant Patkar | AiService | MIG-AI MIG-BASELINE MIG-IDENTITY VM-MIG-AI | Tables: ai.control, ai.control_test, ai.evidence_package, ai.risk_register. Source DDL: backend/tenant/010-ai.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `ai.control`, `ai.control_test`, `ai.evidence_package`, `ai.risk_register` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-AI-AUDIT-3 | AM-AI-P09-6 | [BE] AiService: exportAiEvidencePackage, replayAiDecision | 2 | Tanmay Dukhande | AiService | MIG-AI MIG-AI-13 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: exportAiEvidencePackage, replayAiDecision. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · TICVAI Console 6 of 6; additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#exportAiEvidencePackage`, `ai#replayAiDecision` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-AI-MONITORING-3 | AM-AI-P09-6 | [BE] AiService: decideAiGovernanceAlert, listAiCapabilityHealth, listAiControls, listAiRiskRegister | 5 | Tanmay Dukhande | AiService | MIG-AI MIG-AI-13 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: decideAiGovernanceAlert, listAiCapabilityHealth, listAiControls, listAiRiskRegister. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · TICVAI Console 6 of 6; additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#decideAiGovernanceAlert`, `ai#listAiCapabilityHealth`, `ai#listAiControls`, `ai#listAiRiskRegister` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-AI-MONITORING-4 | AM-AI-P09-6 | [BE] AiService: runAiControlTest, setAiRiskRegisterEntry | 3 | Tanmay Dukhande | AiService | MIG-AI MIG-AI-13 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: runAiControlTest, setAiRiskRegisterEntry. Spec: contracts (ai) at the release tag, served by ADAM. Built for AI · TICVAI Console 6 of 6; additive to AiService, whose first-release owner (Tanmay Dukhande) reviews. Done when `ai#runAiControlTest`, `ai#setAiRiskRegisterEntry` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 3 | AI-BE-SHARED-BASELINE-THEN-LEARN-1 | AM-AI-ENGINE-SHARED-BASELINE-THEN-LEARN | [BE] AI back end: Shared: the baseline-then-learn layer (part 1) | 8 | Tanmay Dukhande | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Shared: the baseline-then-learn layer (built once, used by every data-driven capability) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Duplicate of SVC-AI-FORECAST-2 and SVC-AI-FORECAST-3 (Block A), which build importVenueHistory, getVenueHistoryImport and listVenueHistoryImports: do not build it again; close this ticket as merged when those two close (Chinmay, 4 October, CHG-AIPH-002). It stays in the plan with its points, dates and owner because dropping its 72 points changes the plan's average task size, which sets every developer's pace, and moves 17 Block A tasks by more than a working day. Done when SVC-AI-FORECAST-2 and SVC-AI-FORECAST-3 are done and this ticket is closed as merged into them, with no code of its own.
10 | 3 | AI-BE-SHARED-BASELINE-THEN-LEARN-2 | AM-AI-ENGINE-SHARED-BASELINE-THEN-LEARN | [BE] AI back end: Shared: the baseline-then-learn layer (part 2) | 8 | Pranay Shinde | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Shared: the baseline-then-learn layer (built once, used by every data-driven capability) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Duplicate of SVC-AI-FORECAST-2 and SVC-AI-FORECAST-3 (Block A), which build importVenueHistory, getVenueHistoryImport and listVenueHistoryImports: do not build it again; close this ticket as merged when those two close (Chinmay, 4 October, CHG-AIPH-002). It stays in the plan with its points, dates and owner because dropping its 72 points changes the plan's average task size, which sets every developer's pace, and moves 17 Block A tasks by more than a working day. Done when SVC-AI-FORECAST-2 and SVC-AI-FORECAST-3 are done and this ticket is closed as merged into them, with no code of its own.
10 | 3 | AI-BE-SHARED-BASELINE-THEN-LEARN-3 | AM-AI-ENGINE-SHARED-BASELINE-THEN-LEARN | [BE] AI back end: Shared: the baseline-then-learn layer (part 3) | 8 | Tanmay Dukhande | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Shared: the baseline-then-learn layer (built once, used by every data-driven capability) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Duplicate of SVC-AI-FORECAST-2 and SVC-AI-FORECAST-3 (Block A), which build importVenueHistory, getVenueHistoryImport and listVenueHistoryImports: do not build it again; close this ticket as merged when those two close (Chinmay, 4 October, CHG-AIPH-002). It stays in the plan with its points, dates and owner because dropping its 72 points changes the plan's average task size, which sets every developer's pace, and moves 17 Block A tasks by more than a working day. Done when SVC-AI-FORECAST-2 and SVC-AI-FORECAST-3 are done and this ticket is closed as merged into them, with no code of its own.
10 | 3 | AI-BE-SHARED-BASELINE-THEN-LEARN-4 | AM-AI-ENGINE-SHARED-BASELINE-THEN-LEARN | [BE] AI back end: Shared: the baseline-then-learn layer (part 4) | 8 | Tanmay Dukhande | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Shared: the baseline-then-learn layer (built once, used by every data-driven capability) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Duplicate of SVC-AI-FORECAST-2 and SVC-AI-FORECAST-3 (Block A), which build importVenueHistory, getVenueHistoryImport and listVenueHistoryImports: do not build it again; close this ticket as merged when those two close (Chinmay, 4 October, CHG-AIPH-002). It stays in the plan with its points, dates and owner because dropping its 72 points changes the plan's average task size, which sets every developer's pace, and moves 17 Block A tasks by more than a working day. Done when SVC-AI-FORECAST-2 and SVC-AI-FORECAST-3 are done and this ticket is closed as merged into them, with no code of its own.
10 | 3 | AI-BE-SHARED-BASELINE-THEN-LEARN-5 | AM-AI-ENGINE-SHARED-BASELINE-THEN-LEARN | [BE] AI back end: Shared: the baseline-then-learn layer (part 5) | 8 | Pranay Shinde | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Shared: the baseline-then-learn layer (built once, used by every data-driven capability) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Duplicate of SVC-AI-FORECAST-2 and SVC-AI-FORECAST-3 (Block A), which build importVenueHistory, getVenueHistoryImport and listVenueHistoryImports: do not build it again; close this ticket as merged when those two close (Chinmay, 4 October, CHG-AIPH-002). It stays in the plan with its points, dates and owner because dropping its 72 points changes the plan's average task size, which sets every developer's pace, and moves 17 Block A tasks by more than a working day. Done when SVC-AI-FORECAST-2 and SVC-AI-FORECAST-3 are done and this ticket is closed as merged into them, with no code of its own.
10 | 3 | AI-BE-SHARED-BASELINE-THEN-LEARN-6 | AM-AI-ENGINE-SHARED-BASELINE-THEN-LEARN | [BE] AI back end: Shared: the baseline-then-learn layer (part 6) | 8 | Tanmay Dukhande | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Shared: the baseline-then-learn layer (built once, used by every data-driven capability) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Duplicate of SVC-AI-FORECAST-2 and SVC-AI-FORECAST-3 (Block A), which build importVenueHistory, getVenueHistoryImport and listVenueHistoryImports: do not build it again; close this ticket as merged when those two close (Chinmay, 4 October, CHG-AIPH-002). It stays in the plan with its points, dates and owner because dropping its 72 points changes the plan's average task size, which sets every developer's pace, and moves 17 Block A tasks by more than a working day. Done when SVC-AI-FORECAST-2 and SVC-AI-FORECAST-3 are done and this ticket is closed as merged into them, with no code of its own.
10 | 3 | AI-BE-SHARED-BASELINE-THEN-LEARN-7 | AM-AI-ENGINE-SHARED-BASELINE-THEN-LEARN | [BE] AI back end: Shared: the baseline-then-learn layer (part 7) | 8 | Pranay Shinde | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Shared: the baseline-then-learn layer (built once, used by every data-driven capability) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Duplicate of SVC-AI-FORECAST-2 and SVC-AI-FORECAST-3 (Block A), which build importVenueHistory, getVenueHistoryImport and listVenueHistoryImports: do not build it again; close this ticket as merged when those two close (Chinmay, 4 October, CHG-AIPH-002). It stays in the plan with its points, dates and owner because dropping its 72 points changes the plan's average task size, which sets every developer's pace, and moves 17 Block A tasks by more than a working day. Done when SVC-AI-FORECAST-2 and SVC-AI-FORECAST-3 are done and this ticket is closed as merged into them, with no code of its own.
10 | 3 | AI-BE-SHARED-BASELINE-THEN-LEARN-8 | AM-AI-ENGINE-SHARED-BASELINE-THEN-LEARN | [BE] AI back end: Shared: the baseline-then-learn layer (part 8) | 8 | Tanmay Dukhande | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Shared: the baseline-then-learn layer (built once, used by every data-driven capability) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Duplicate of SVC-AI-FORECAST-2 and SVC-AI-FORECAST-3 (Block A), which build importVenueHistory, getVenueHistoryImport and listVenueHistoryImports: do not build it again; close this ticket as merged when those two close (Chinmay, 4 October, CHG-AIPH-002). It stays in the plan with its points, dates and owner because dropping its 72 points changes the plan's average task size, which sets every developer's pace, and moves 17 Block A tasks by more than a working day. Done when SVC-AI-FORECAST-2 and SVC-AI-FORECAST-3 are done and this ticket is closed as merged into them, with no code of its own.
10 | 3 | AI-BE-SHARED-BASELINE-THEN-LEARN-9 | AM-AI-ENGINE-SHARED-BASELINE-THEN-LEARN | [BE] AI back end: Shared: the baseline-then-learn layer (part 9) | 8 | Pranay Shinde | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Shared: the baseline-then-learn layer (built once, used by every data-driven capability) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Duplicate of SVC-AI-FORECAST-2 and SVC-AI-FORECAST-3 (Block A), which build importVenueHistory, getVenueHistoryImport and listVenueHistoryImports: do not build it again; close this ticket as merged when those two close (Chinmay, 4 October, CHG-AIPH-002). It stays in the plan with its points, dates and owner because dropping its 72 points changes the plan's average task size, which sets every developer's pace, and moves 17 Block A tasks by more than a working day. Done when SVC-AI-FORECAST-2 and SVC-AI-FORECAST-3 are done and this ticket is closed as merged into them, with no code of its own.
10 | 3 | AI-BE-CONFIGURATION-ASSISTANT-1 | AM-AI-ENGINE-CONFIGURATION-ASSISTANT | [BE] AI back end: Configuration assistant (part 1) | 8 | Tanmay Dukhande | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Configuration assistant (discovery, blueprint, build plan, change and rollback) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Done when the work in the description above is built, tested and reviewed by a peer in the same stack (block-test-strategy).
10 | 3 | AI-BE-CONFIGURATION-ASSISTANT-10 | AM-AI-ENGINE-CONFIGURATION-ASSISTANT | [BE] AI back end: Configuration assistant (part 10) | 8 | Pranay Shinde | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Configuration assistant (discovery, blueprint, build plan, change and rollback) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Done when the work in the description above is built, tested and reviewed by a peer in the same stack (block-test-strategy).
10 | 3 | AI-BE-CONFIGURATION-ASSISTANT-11 | AM-AI-ENGINE-CONFIGURATION-ASSISTANT | [BE] AI back end: Configuration assistant (part 11) | 8 | Tanmay Dukhande | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Configuration assistant (discovery, blueprint, build plan, change and rollback) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Done when the work in the description above is built, tested and reviewed by a peer in the same stack (block-test-strategy).
10 | 3 | AI-BE-CONFIGURATION-ASSISTANT-12 | AM-AI-ENGINE-CONFIGURATION-ASSISTANT | [BE] AI back end: Configuration assistant (part 12) | 8 | Tanmay Dukhande | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Configuration assistant (discovery, blueprint, build plan, change and rollback) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Done when the work in the description above is built, tested and reviewed by a peer in the same stack (block-test-strategy).
10 | 3 | AI-BE-CONFIGURATION-ASSISTANT-2 | AM-AI-ENGINE-CONFIGURATION-ASSISTANT | [BE] AI back end: Configuration assistant (part 2) | 8 | Pranay Shinde | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Configuration assistant (discovery, blueprint, build plan, change and rollback) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Done when the work in the description above is built, tested and reviewed by a peer in the same stack (block-test-strategy).
10 | 3 | AI-BE-CONFIGURATION-ASSISTANT-3 | AM-AI-ENGINE-CONFIGURATION-ASSISTANT | [BE] AI back end: Configuration assistant (part 3) | 8 | Tanmay Dukhande | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Configuration assistant (discovery, blueprint, build plan, change and rollback) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Done when the work in the description above is built, tested and reviewed by a peer in the same stack (block-test-strategy).
10 | 3 | AI-BE-CONFIGURATION-ASSISTANT-4 | AM-AI-ENGINE-CONFIGURATION-ASSISTANT | [BE] AI back end: Configuration assistant (part 4) | 8 | Pranay Shinde | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Configuration assistant (discovery, blueprint, build plan, change and rollback) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Done when the work in the description above is built, tested and reviewed by a peer in the same stack (block-test-strategy).
10 | 3 | AI-BE-CONFIGURATION-ASSISTANT-5 | AM-AI-ENGINE-CONFIGURATION-ASSISTANT | [BE] AI back end: Configuration assistant (part 5) | 8 | Tanmay Dukhande | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Configuration assistant (discovery, blueprint, build plan, change and rollback) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Done when the work in the description above is built, tested and reviewed by a peer in the same stack (block-test-strategy).
10 | 3 | AI-BE-CONFIGURATION-ASSISTANT-6 | AM-AI-ENGINE-CONFIGURATION-ASSISTANT | [BE] AI back end: Configuration assistant (part 6) | 8 | Pranay Shinde | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Configuration assistant (discovery, blueprint, build plan, change and rollback) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Done when the work in the description above is built, tested and reviewed by a peer in the same stack (block-test-strategy).
10 | 3 | AI-BE-CONFIGURATION-ASSISTANT-7 | AM-AI-ENGINE-CONFIGURATION-ASSISTANT | [BE] AI back end: Configuration assistant (part 7) | 8 | Tanmay Dukhande | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Configuration assistant (discovery, blueprint, build plan, change and rollback) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Done when the work in the description above is built, tested and reviewed by a peer in the same stack (block-test-strategy).
10 | 3 | AI-BE-CONFIGURATION-ASSISTANT-8 | AM-AI-ENGINE-CONFIGURATION-ASSISTANT | [BE] AI back end: Configuration assistant (part 8) | 8 | Pranay Shinde | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Configuration assistant (discovery, blueprint, build plan, change and rollback) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Done when the work in the description above is built, tested and reviewed by a peer in the same stack (block-test-strategy).
10 | 3 | AI-BE-CONFIGURATION-ASSISTANT-9 | AM-AI-ENGINE-CONFIGURATION-ASSISTANT | [BE] AI back end: Configuration assistant (part 9) | 8 | Tanmay Dukhande | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Configuration assistant (discovery, blueprint, build plan, change and rollback) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Done when the work in the description above is built, tested and reviewed by a peer in the same stack (block-test-strategy).
10 | 3 | AI-BE-ANALYTICS-ASSISTANT-1 | AM-AI-ENGINE-ANALYTICS-ASSISTANT | [BE] AI back end: Analytics assistant and metric explanation (part 1) | 8 | Tanmay Dukhande | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Analytics assistant and metric explanation (Ask TICVAI, explainMetricChange, insights) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Done when the work in the description above is built, tested and reviewed by a peer in the same stack (block-test-strategy).
10 | 3 | AI-BE-ANALYTICS-ASSISTANT-2 | AM-AI-ENGINE-ANALYTICS-ASSISTANT | [BE] AI back end: Analytics assistant and metric explanation (part 2) | 8 | Tanmay Dukhande | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Analytics assistant and metric explanation (Ask TICVAI, explainMetricChange, insights) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Done when the work in the description above is built, tested and reviewed by a peer in the same stack (block-test-strategy).
10 | 3 | AI-BE-ANALYTICS-ASSISTANT-3 | AM-AI-ENGINE-ANALYTICS-ASSISTANT | [BE] AI back end: Analytics assistant and metric explanation (part 3) | 8 | Tanmay Dukhande | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Analytics assistant and metric explanation (Ask TICVAI, explainMetricChange, insights) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Done when the work in the description above is built, tested and reviewed by a peer in the same stack (block-test-strategy).
10 | 3 | AI-BE-ANALYTICS-ASSISTANT-4 | AM-AI-ENGINE-ANALYTICS-ASSISTANT | [BE] AI back end: Analytics assistant and metric explanation (part 4) | 8 | Tanmay Dukhande | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Analytics assistant and metric explanation (Ask TICVAI, explainMetricChange, insights) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Done when the work in the description above is built, tested and reviewed by a peer in the same stack (block-test-strategy).
10 | 3 | AI-BE-ANALYTICS-ASSISTANT-5 | AM-AI-ENGINE-ANALYTICS-ASSISTANT | [BE] AI back end: Analytics assistant and metric explanation (part 5) | 8 | Tanmay Dukhande | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Analytics assistant and metric explanation (Ask TICVAI, explainMetricChange, insights) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Done when the work in the description above is built, tested and reviewed by a peer in the same stack (block-test-strategy).
10 | 3 | AI-BE-ANALYTICS-ASSISTANT-6 | AM-AI-ENGINE-ANALYTICS-ASSISTANT | [BE] AI back end: Analytics assistant and metric explanation (part 6) | 8 | Hrushikant Patkar | AiService | PLATFORM-KERNEL | The back-end work the AI review names for Analytics assistant and metric explanation (Ask TICVAI, explainMetricChange, insights) beyond the AI engineers' own (validate-only tool operations, semantic-spec compile, historical import). Additive to AiService and the owning services; their owners review. Done when the work in the description above is built, tested and reviewed by a peer in the same stack (block-test-strategy).
8 | 3 | MIG-REPORTING-5 | AM-REPORTING-P08 | [DB] Forward migration V1178__reporting.sql: reporting for Reporting · Venue Management 1 of 2 (1 tables) | 1 | Hrushikant Patkar | ReportingService | MIG-BASELINE MIG-IDENTITY MIG-REPORTING VM-MIG-REPORTING | Tables: reporting.export. Source DDL: backend/tenant/010-reporting.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `reporting.export` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
10 | 3 | SVC-ACCESS-ACCESS-69 | AM-REPORTING-P08 | [BE] AccessService: listAccessReportScheduled | 1 | Deep Khanvilkar | AccessService | MIG-BASELINE PLATFORM-KERNEL | Operations: listAccessReportScheduled. Spec: contracts (access) at the release tag, served by ADAM. Built for Reporting · Venue Management 1 of 2; additive to AccessService, whose first-release owner (Hrushikant Patkar) reviews. Done when `access#listAccessReportScheduled` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-REPORTING-EXPORT-1 | AM-REPORTING-P08 | [BE] ReportingService: exportReportResult | 1 | Deep Khanvilkar | ReportingService | MIG-REPORTING-5 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: exportReportResult. Spec: contracts (reporting) at the release tag, served by ADAM. Built for Reporting · Venue Management 1 of 2; additive to ReportingService, whose first-release owner (Tanmay Dukhande) reviews. Done when `reporting#exportReportResult` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
8 | 3 | MIG-REPORTING-6 | AM-REPORTING-P08-2 | [DB] Forward migration V1179__reporting.sql: reporting for Reporting · Venue Management 2 of 2 (2 tables) | 2 | Hrushikant Patkar | ReportingService | MIG-BASELINE MIG-REPORTING VM-MIG-REPORTING | Tables: reporting.pipeline, reporting.site_normalisation_basis. Source DDL: backend/tenant/010-reporting.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `reporting.pipeline`, `reporting.site_normalisation_basis` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
13 | 3 | SVC-INVENTORY-INVENTORY-5 | AM-REPORTING-P16 | [BE] InventoryService: listExpiringBatches | 2 | Deep Khanvilkar | InventoryService | MIG-INVENTORY PLATFORM-KERNEL SVC-INVENTORY-ITEM-1 | Operations: listExpiringBatches. Spec: contracts (inventory) at the release tag, served by ADAM. Built for Reporting · Analytics 1 of 4; additive to InventoryService, whose first-release owner (Pranay Shinde) reviews. Done when `inventory#listExpiringBatches` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
10 | 3 | SVC-REPORTING-CATALOGUE-3 | AM-REPORTING-P16-2 | [BE] ReportingService: listReportFields | 1 | Tanmay Dukhande | ReportingService | MIG-BASELINE PLATFORM-KERNEL | Operations: listReportFields. Spec: contracts (reporting) at the release tag, served by ADAM. Built for Reporting · Analytics 2 of 4; additive to ReportingService, whose first-release owner (Tanmay Dukhande) reviews. Done when `reporting#listReportFields` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-REPORTING-EXECUTION-2 | AM-REPORTING-P16-2 | [BE] ReportingService: cancelReportExecution, getReportExecution | 2 | Deep Khanvilkar | ReportingService | MIG-REPORTING PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: cancelReportExecution, getReportExecution. Spec: contracts (reporting) at the release tag, served by ADAM. Built for Reporting · Analytics 2 of 4; additive to ReportingService, whose first-release owner (Tanmay Dukhande) reviews. Done when `reporting#cancelReportExecution`, `reporting#getReportExecution` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 2 | VM-REPORTING-EXECUTION-1 | AM-REPORTING-P08 | [BE] ReportingService: listReportExecutions | 1 | Chinmay Patkar | ReportingService | MIG-REPORTING PLATFORM-KERNEL SVC-REPORTING-EXECUTION-1 SVC-REPORTING-EXECUTION-2 | Operations beyond the first release: listReportExecutions. Additive to ReportingService; its first-release owner (Tanmay Dukhande) reviews. Helper task: Tanmay Dukhande owns the service and reviews. Done when `reporting#listReportExecutions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-REPORTING-REPORTING-11 | AM-REPORTING-P16-2 | [BE] ReportingService: listSeededReports, listSiteNormalisationBases, setKpiTargets | 3 | Deep Khanvilkar | ReportingService | MIG-REPORTING MIG-REPORTING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL VM-MIG-REPORTING | Operations: listSeededReports, listSiteNormalisationBases, setKpiTargets. Spec: contracts (reporting) at the release tag, served by ADAM. Built for Reporting · Analytics 2 of 4; additive to ReportingService, whose first-release owner (Tanmay Dukhande) reviews. Done when `reporting#listSeededReports`, `reporting#listSiteNormalisationBases`, `reporting#setKpiTargets` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
8 | 3 | MIG-REPORTING-7 | AM-REPORTING-P16-3 | [DB] Forward migration V1232__reporting.sql: reporting for Reporting · Analytics 3 of 4 (2 tables) | 2 | Hrushikant Patkar | ReportingService | MIG-BASELINE MIG-REPORTING VM-MIG-REPORTING | Tables: reporting.delivery, reporting.subscription. Source DDL: backend/tenant/010-reporting.sql and the matching rows of 900-foreign-keys, 910-indexes and 920-row-level-security. A forward migration after the r1 baseline (frozen, check-migration-freeze); applied forward by SqlMigrationRunner, and a second run applies nothing. Write this migration yourself, in our repository: the package's numbered SQL files (backend/tenant and backend/control: 000-930 and the V01nn after-r1 files) are the reference you copy from, never run as they are. Copying functions or tables out of them, such as the helpers at the top of 920 and 930, is expected; 'Do not hand-edit' is about the package's own files. Done when the migration for `reporting.delivery`, `reporting.subscription` runs forward on an empty database and on the previous release's schema, every table matches its spec in ADAM (columns, keys, indexes, row-level security), and a peer has reviewed it.
11 | 3 | SVC-REPORTING-REPORTING-12 | AM-REPORTING-P16-3 | [BE] ReportingService: createReportSubscription, getAnalyticsUsage, listReportDeliveries, listReportSubscriptions | 3 | Deep Khanvilkar | ReportingService | MIG-REPORTING MIG-REPORTING-7 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: createReportSubscription, getAnalyticsUsage, listReportDeliveries, listReportSubscriptions. Spec: contracts (reporting) at the release tag, served by ADAM. Built for Reporting · Analytics 3 of 4; additive to ReportingService, whose first-release owner (Tanmay Dukhande) reviews. Done when `reporting#createReportSubscription`, `reporting#getAnalyticsUsage`, `reporting#listReportDeliveries`, `reporting#listReportSubscriptions` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
12 | 3 | SVC-REPORTING-EXPORT-2 | AM-REPORTING-P16-3 | [BE] ReportingService: getReportExport | 1 | Deep Khanvilkar | ReportingService | MIG-REPORTING-5 PLATFORM-KERNEL SVC-REPORTING-EXPORT-1 | Operations: getReportExport. Spec: contracts (reporting) at the release tag, served by ADAM. Built for Reporting · Analytics 3 of 4; additive to ReportingService, whose first-release owner (Tanmay Dukhande) reviews. Done when `reporting#getReportExport` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-REPORTING-EXECUTION-3 | AM-REPORTING-P16-3 | [BE] ReportingService: getReportResult | 1 | Deep Khanvilkar | ReportingService | MIG-REPORTING PLATFORM-KERNEL SVC-REPORTING-EXECUTION-1 SVC-REPORTING-EXECUTION-2 | Operations: getReportResult. Spec: contracts (reporting) at the release tag, served by ADAM. Built for Reporting · Analytics 3 of 4; additive to ReportingService, whose first-release owner (Tanmay Dukhande) reviews. Done when `reporting#getReportResult` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
11 | 3 | SVC-REPORTING-REPORTING-13 | AM-REPORTING-P16-4 | [BE] ReportingService: setSiteNormalisationBasis | 1 | Deep Khanvilkar | ReportingService | MIG-REPORTING-6 PLATFORM-IDEMPOTENCY PLATFORM-KERNEL | Operations: setSiteNormalisationBasis. Spec: contracts (reporting) at the release tag, served by ADAM. Built for Reporting · Analytics 4 of 4; additive to ReportingService, whose first-release owner (Tanmay Dukhande) reviews. Done when `reporting#setSiteNormalisationBasis` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
18 | 3 | SVC-REPORTING-REPORTING-10 | AM-REPORTING-P08-2 | [BE] ReportingService: getAnalyticsBenchmark, listAnalyticsPipelines | 2 | Deep Khanvilkar | ReportingService | MIG-ACCESS MIG-REPORTING MIG-REPORTING-6 PLATFORM-KERNEL SVC-ACCESS-ACCESS-1 SVC-ACCESS-ACCESS-12 SVC-REPORTING-REPORTING-1 SVC-REPORTING-REPORTING-11 SVC-REPORTING-REPORTING-13 SVC-REPORTING-REPORTING-2 VM-ACCESS-SYNC-1 VM-ACCESS-VALIDATION-1 VM-MIG-REPORTING | Operations: getAnalyticsBenchmark, listAnalyticsPipelines. Spec: contracts (reporting) at the release tag, served by ADAM. Built for Reporting · Venue Management 2 of 2; additive to ReportingService, whose first-release owner (Tanmay Dukhande) reviews. Done when `reporting#getAnalyticsBenchmark`, `reporting#listAnalyticsPipelines` pass their contract tests against the contract in ADAM, including every documented error response; each reads and writes only the tables its spec lists, under row-level security; unit tests cover its rules; and a peer in the same stack has reviewed and tested it.
1 | 3 | TEST-SAME-NUMBERS | AM-REPORTING-API-PLATFORM | [BE] Same numbers test: till, back-office and Analytics reports agree | 3 | Deep Khanvilkar |  |  | Same numbers test: till, back-office and Analytics reports agree. Builds: `screen POS-008`. 2 October (Chinmay, DEC-559, prevention of CHG-FIN-006): an automated comparison of the same measure (takings, gross sales, net revenue, refunds) for the same period and scope on the till report (POS-008), the back-office report and the Analytics (P16) dashboard; fails when they differ. Done when: the test runs in CI against the seeded demo tenant.

## Migrations
Order | Task | Migration file | Database | Schema | Tables | Columns | References (created earlier or deferred) | Assignee | Points | Owning service
0 | MIG-BASELINE | V0001__baseline.sql | both | (baseline) | 0 | 0 |  | Hrushikant Patkar | 3
1 | MIG-CONTROL | V0002__control.sql | control | control | 19 | 301 |  | Hrushikant Patkar | 8 | PlatformService
2 | MIG-KERNEL | V0003__kernel.sql | tenant | kernel | 1 | 3 |  | Hrushikant Patkar | 1 | TenancyService
3 | MIG-TENANCY | V0004__tenancy.sql | tenant | tenancy | 1 | 12 |  | Hrushikant Patkar | 1 | TenancyService
4 | MIG-SUBSCRIPTION | V0005__subscription.sql | tenant | subscription | 5 | 52 | platform | Hrushikant Patkar | 3 | PlatformService
5 | MIG-TRANSPORT | V0006__transport.sql | tenant | transport | 12 | 109 | assets | Hrushikant Patkar | 8 | VenueOpsService
6 | MIG-PII | V0007__pii.sql | tenant | pii | 5 | 54 | access, marketing | Hrushikant Patkar | 3 | IdentityService
7 | MIG-GAMES | V0008__games.sql | tenant | games | 2 | 17 | pii, platform | Hrushikant Patkar | 2 | VenueOpsService
8 | MIG-IDENTITY | V0009__identity.sql | tenant | identity | 18 | 157 | pii, platform | Hrushikant Patkar | 8 | IdentityService
9 | MIG-APPROVALS | V0010__approvals.sql | tenant | approvals | 6 | 108 | identity | Hrushikant Patkar | 5 | TenancyService
10 | MIG-REPORTING | V0011__reporting.sql | tenant | reporting | 15 | 160 | identity, platform | Hrushikant Patkar | 8 | ReportingService
11 | MIG-SYNC | V0012__sync.sql | tenant | sync | 1 | 11 | identity, platform | Hrushikant Patkar | 1 | CrossRegionService
12 | MIG-ASSETS | V0013__assets.sql | tenant | assets | 7 | 74 | identity, platform | Hrushikant Patkar | 5 | VenueOpsService
13 | MIG-AI | V0014__ai.sql | tenant | ai | 49 | 714 | assets, identity, pii, platform | Hrushikant Patkar | 8 | AiService
14 | MIG-RESOURCES | V0015__resources.sql | tenant | resources | 7 | 89 | identity, orders, pii, platform | Hrushikant Patkar | 5 | VenueOpsService
15 | MIG-WHITELABEL | V0016__whitelabel.sql | tenant | whitelabel | 29 | 271 | identity, platform, promotions | Hrushikant Patkar | 8 | WhiteLabelService
16 | MIG-PLATFORM | V0017__platform.sql | tenant | platform | 17 | 205 | access, approvals, identity, inventory, ledger | Hrushikant Patkar | 8 | TenancyService
17 | MIG-WORKFORCE | V0018__workforce.sql | tenant | workforce | 3 | 39 | access, identity, platform | Hrushikant Patkar | 2 | TenancyService
18 | MIG-SEATING | V0019__seating.sql | tenant | seating | 11 | 89 | assets, catalogue, identity, pii, platform | Hrushikant Patkar | 5 | CatalogueService
19 | MIG-MAINTENANCE | V0020__maintenance.sql | tenant | maintenance | 6 | 148 | access, identity, inventory, platform | Hrushikant Patkar | 5 | VenueOpsService
20 | MIG-WALLET | V0021__wallet.sql | tenant | wallet | 22 | 204 | identity, orders, pii, platform | Hrushikant Patkar | 8 | WalletService
21 | MIG-CATALOGUE | V0022__catalogue.sql | tenant | catalogue | 23 | 325 | access, identity, ledger, pii, platform, seating | Hrushikant Patkar | 8 | CatalogueService
22 | MIG-LEDGER | V0023__ledger.sql | tenant | ledger | 18 | 271 | catalogue, identity, orders, platform | Hrushikant Patkar | 8 | LedgerService
23 | MIG-INVENTORY | V0024__inventory.sql | tenant | inventory | 12 | 172 | identity, ledger, platform | Hrushikant Patkar | 8 | InventoryService
24 | MIG-PROMOTIONS | V0025__promotions.sql | tenant | promotions | 16 | 182 | ledger, orders, pii, platform | Hrushikant Patkar | 8 | CatalogueService
25 | MIG-ORDERS | V0026__orders.sql | tenant | orders | 39 | 476 | access, catalogue, identity, ledger, pii, platform, promotions | Hrushikant Patkar | 8 | OrderService
26 | MIG-ACCESS | V0027__access.sql | tenant | access | 19 | 325 | catalogue, identity, orders, pii, platform | Hrushikant Patkar | 8 | AccessService
27 | MIG-MARKETING | V0028__marketing.sql | tenant | marketing | 55 | 672 | ai, catalogue, identity, ledger, orders, pii, platform | Hrushikant Patkar | 8 | MarketingService
28 | MIG-FNB | V0029__fnb.sql | tenant | fnb | 41 | 397 | access, catalogue, identity, inventory, orders, pii, platform, seating | Hrushikant Patkar | 8 | FnbService
29 | MIG-PAYMENTS | V0030__payments.sql | tenant | payments | 12 | 141 | marketing, orders, pii | Hrushikant Patkar | 8 | OrderService
30 | MIG-QUEUE | V0031__queue.sql | tenant | queue | 4 | 77 | access, catalogue, maintenance, pii, platform | Hrushikant Patkar | 3 | VenueOpsService
31 | MIG-RETAIL | V0032__retail.sql | tenant | retail | 10 | 110 | access, catalogue, fnb, identity, inventory, orders, pii, platform | Hrushikant Patkar | 5 | RetailService
32 | MIG-VENUEMAP | V0033__venuemap.sql | tenant | venuemap | 8 | 118 | access, assets, catalogue, marketing, orders, platform, promotions, resources | Hrushikant Patkar | 5 | VenueOpsService
33 | MIG-FOREIGN-KEYS | V0034__cross_schema_foreign_keys.sql | tenant | (cross-schema) | 0 | 0 |  | Hrushikant Patkar | 2

## Tables
Migration | Table | Database | Columns | Row-level security | Partitioned by month | Operations reading | Operations writing | Foreign keys to | Why it is in the release | Owning service | Source DDL
MIG-CONTROL | control.api_client | control | 14 | none |  | 5 | 4 | control.integration_listing | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.api_licence | control | 9 | none |  | 2 | 1 | control.tenant | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.api_version | control | 9 | none |  | 2 | 1 |  | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.cell_tenant | control | 10 | none |  | 0 | 0 |  | referenced by control.outbox_relay | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.content_block | control | 12 | scope_path |  | 6 | 3 |  | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.developer_account | control | 8 | none |  | 3 | 2 |  | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.developer_member | control | 7 | none |  | 1 | 1 |  | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.integration_listing | control | 12 | none |  | 3 | 1 |  | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.licence_add_on | control | 7 | none |  | 4 | 1 |  | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.licence_add_on_limit | control | 6 | none |  | 0 | 1 | control.licence_add_on | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.outbox_relay | control | 6 | none |  | 0 | 0 | control.cell_tenant | kernel machinery: the relay lease per tenant database (ADR-0058; PLATFORM-OUTBOX) | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.partner | control | 28 | scope_path |  | 0 | 0 |  | referenced by control.partner_agreement | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.partner_agreement | control | 53 | scope_path |  | 0 | 1 | control.partner | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.partner_application | control | 31 | scope_path |  | 0 | 1 |  | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.partner_change_request | control | 28 | scope_path |  | 0 | 1 |  | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.production_access_request | control | 14 | none |  | 1 | 1 | control.api_client, control.integration_listing | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.seo_metadata | control | 15 | scope_path |  | 2 | 1 |  | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.tenant | control | 23 | none |  | 9 | 5 |  | used by the first release | PlatformService | backend/control/010-control.sql
MIG-CONTROL | control.url_redirect | control | 9 | scope_path |  | 1 | 1 |  | used by the first release | PlatformService | backend/control/010-control.sql
MIG-KERNEL | kernel.inbox | tenant | 3 | tenant root (one tenant per database; no tenant_id by design) | yes | 0 | 0 |  | kernel machinery: the inbox per tenant database (ADR-0058; PLATFORM-OUTBOX, MIG-PARTITIONS) | TenancyService | backend/tenant/010-kernel.sql
MIG-TENANCY | tenancy.device_assignment | tenant | 12 | scope_path |  | 2 | 1 |  | used by the first release | TenancyService | backend/tenant/010-tenancy.sql
MIG-SUBSCRIPTION | subscription.contract | tenant | 12 | tenant root (one tenant per database; no tenant_id by design) |  | 5 | 2 | platform.tenant, subscription.plan | used by the first release | PlatformService | backend/tenant/010-subscription.sql
MIG-SUBSCRIPTION | subscription.module_listing | tenant | 15 | tenant root (one tenant per database; no tenant_id by design) |  | 2 | 1 |  | used by the first release | PlatformService | backend/tenant/010-subscription.sql
MIG-SUBSCRIPTION | subscription.plan | tenant | 16 | tenant root (one tenant per database; no tenant_id by design) |  | 6 | 2 |  | used by the first release | PlatformService | backend/tenant/010-subscription.sql
MIG-SUBSCRIPTION | subscription.plan_limit | tenant | 6 | tenant root (one tenant per database; no tenant_id by design) |  | 2 | 2 | subscription.plan | used by the first release | PlatformService | backend/tenant/010-subscription.sql
MIG-SUBSCRIPTION | subscription.plan_module | tenant | 3 | tenant root (one tenant per database; no tenant_id by design) |  | 2 | 2 | subscription.plan | used by the first release | PlatformService | backend/tenant/010-subscription.sql
MIG-TRANSPORT | transport.departure | tenant | 10 | tenant root (one tenant per database; no tenant_id by design) |  | 5 | 2 |  | used by the first release | VenueOpsService | backend/tenant/010-transport.sql
MIG-TRANSPORT | transport.fare_matrix_cell | tenant | 5 | tenant root (one tenant per database; no tenant_id by design) |  | 7 | 1 | transport.fare_table | used by the first release | VenueOpsService | backend/tenant/010-transport.sql
MIG-TRANSPORT | transport.fare_passenger_type | tenant | 11 | tenant root (one tenant per database; no tenant_id by design) |  | 6 | 1 | transport.fare_table | used by the first release | VenueOpsService | backend/tenant/010-transport.sql
MIG-TRANSPORT | transport.fare_table | tenant | 7 | tenant root (one tenant per database; no tenant_id by design) |  | 8 | 2 |  | used by the first release | VenueOpsService | backend/tenant/010-transport.sql
MIG-TRANSPORT | transport.favourite_route | tenant | 9 | venue_id |  | 3 | 2 |  | used by the first release | VenueOpsService | backend/tenant/010-transport.sql
MIG-TRANSPORT | transport.network_import | tenant | 10 | venue_id |  | 2 | 1 | assets.media_asset | used by the first release | VenueOpsService | backend/tenant/010-transport.sql
MIG-TRANSPORT | transport.pass_type | tenant | 14 | venue_id |  | 4 | 2 |  | used by the first release | VenueOpsService | backend/tenant/010-transport.sql
MIG-TRANSPORT | transport.route | tenant | 12 | venue_id |  | 12 | 4 |  | used by the first release | VenueOpsService | backend/tenant/010-transport.sql
MIG-TRANSPORT | transport.route_stop | tenant | 7 | through its owner |  | 11 | 3 | transport.route | used by the first release | VenueOpsService | backend/tenant/010-transport.sql
MIG-TRANSPORT | transport.station | tenant | 8 | venue_id |  | 13 | 3 |  | used by the first release | VenueOpsService | backend/tenant/010-transport.sql
MIG-TRANSPORT | transport.timetable | tenant | 12 | tenant root (one tenant per database; no tenant_id by design) |  | 7 | 4 |  | used by the first release | VenueOpsService | backend/tenant/010-transport.sql
MIG-TRANSPORT | transport.timetable_run | tenant | 4 | tenant root (one tenant per database; no tenant_id by design) |  | 3 | 2 | transport.timetable | used by the first release | VenueOpsService | backend/tenant/010-transport.sql
MIG-PII | pii.consent_identifier | tenant | 6 | scope_path |  | 0 | 1 |  | used by the first release | IdentityService | backend/tenant/010-pii.sql
MIG-PII | pii.subject | tenant | 13 | tenant root (one tenant per database; no tenant_id by design) |  | 20 | 7 |  | used by the first release | IdentityService | backend/tenant/010-pii.sql
MIG-PII | pii.subject_biometric | tenant | 15 | through its owner |  | 4 | 3 | access.entitlement, marketing.consent_purpose, pii.subject | used by the first release | IdentityService | backend/tenant/010-pii.sql
MIG-PII | pii.subject_contact | tenant | 10 | subject |  | 6 | 2 | pii.subject | used by the first release | IdentityService | backend/tenant/010-pii.sql
MIG-PII | pii.subject_document | tenant | 10 | subject |  | 0 | 2 | pii.subject | used by the first release | IdentityService | backend/tenant/010-pii.sql
MIG-GAMES | games.card | tenant | 15 | venue_id |  | 3 | 2 | pii.subject, platform.scope | used by the first release | VenueOpsService | backend/tenant/010-games.sql
MIG-GAMES | games.credit_ledger | tenant | 2 | through its owner |  | 1 | 0 | games.card | used by the first release | VenueOpsService | backend/tenant/010-games.sql
MIG-IDENTITY | identity.capability_template | tenant | 9 | scope_path |  | 2 | 1 |  | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.delegated_access | tenant | 21 | scope_path |  | 14 | 2 | identity.principal, identity.role, pii.subject, platform.scope | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.guest_credential | tenant | 6 | subject |  | 1 | 2 |  | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.guest_identity_verification | tenant | 13 | subject |  | 2 | 1 |  | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.guest_verification_policy | tenant | 14 | scope_path |  | 2 | 1 |  | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.mfa_challenge | tenant | 2 | tenant root (one tenant per database; no tenant_id by design) |  | 1 | 2 | identity.principal | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.mfa_method | tenant | 9 | tenant root (one tenant per database; no tenant_id by design) |  | 11 | 3 | identity.principal | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.mfa_recovery_code | tenant | 2 | tenant root (one tenant per database; no tenant_id by design) |  | 2 | 2 | identity.principal | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.otp_challenge | tenant | 2 | subject |  | 2 | 2 | pii.subject | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.password_policy | tenant | 13 | scope_path |  | 3 | 1 |  | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.platform_staff_grant | tenant | 9 | scope_path |  | 2 | 1 |  | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.principal | tenant | 9 | tenant root (one tenant per database; no tenant_id by design) |  | 24 | 1 | identity.role, platform.scope | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.principal_credential | tenant | 2 | tenant root (one tenant per database; no tenant_id by design) |  | 3 | 1 | identity.principal | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.refresh_token | tenant | 10 | tenant root (one tenant per database; no tenant_id by design) |  | 1 | 2 |  | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.role | tenant | 9 | tenant root (one tenant per database; no tenant_id by design) |  | 8 | 2 |  | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.role_permission | tenant | 6 | tenant root (one tenant per database; no tenant_id by design) |  | 3 | 2 | identity.role | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.segregation_rule | tenant | 9 | scope_path |  | 3 | 1 |  | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-IDENTITY | identity.session | tenant | 12 | venue_id |  | 5 | 6 | identity.principal | used by the first release | IdentityService | backend/tenant/010-identity.sql
MIG-APPROVALS | approvals.decision | tenant | 13 | through its owner |  | 3 | 1 | approvals.request, identity.principal | used by the first release | TenancyService | backend/tenant/010-approvals.sql
MIG-APPROVALS | approvals.delegation | tenant | 13 | scope_path |  | 4 | 2 | identity.principal | used by the first release | TenancyService | backend/tenant/010-approvals.sql
MIG-APPROVALS | approvals.external_provider | tenant | 16 | scope_path |  | 2 | 1 |  | used by the first release | TenancyService | backend/tenant/010-approvals.sql
MIG-APPROVALS | approvals.matrix | tenant | 6 | scope_path |  | 6 | 2 |  | used by the first release | TenancyService | backend/tenant/010-approvals.sql
MIG-APPROVALS | approvals.request | tenant | 30 | scope_path |  | 3 | 2 | identity.principal | used by the first release | TenancyService | backend/tenant/010-approvals.sql
MIG-APPROVALS | approvals.rule | tenant | 30 | through its owner |  | 7 | 2 | approvals.matrix | used by the first release | TenancyService | backend/tenant/010-approvals.sql
MIG-REPORTING | reporting.alert | tenant | 18 | scope_path |  | 1 | 0 |  | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.alert_rule | tenant | 13 | scope_path |  | 2 | 1 |  | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.dashboard | tenant | 10 | venue_id |  | 6 | 3 | identity.principal, platform.scope | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.dashboard_tile | tenant | 8 | tenant root (one tenant per database; no tenant_id by design) |  | 5 | 2 | reporting.dashboard, reporting.report_definition | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.dashboard_view | tenant | 5 | venue_id |  | 0 | 1 | identity.principal, reporting.dashboard | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.execution | tenant | 15 | through its owner |  | 1 | 1 | identity.principal, reporting.report_definition, reporting.schedule | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.kpi_definition | tenant | 12 | scope_path |  | 2 | 1 |  | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.natural_language_query | tenant | 9 | scope_path |  | 1 | 2 |  | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.report_column | tenant | 14 | through its owner |  | 6 | 4 | reporting.report_definition | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.report_definition | tenant | 16 | scope_path |  | 8 | 4 | identity.principal | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.report_definition_version | tenant | 7 | scope_path |  | 1 | 2 |  | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.report_filter | tenant | 7 | through its owner |  | 6 | 4 | reporting.report_definition | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.report_parameter | tenant | 7 | through its owner |  | 6 | 3 | reporting.report_definition | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.schedule | tenant | 15 | through its owner |  | 0 | 0 | identity.principal, reporting.report_definition | referenced by reporting.execution | ReportingService | backend/tenant/010-reporting.sql
MIG-REPORTING | reporting.semantic_model | tenant | 4 | scope_path |  | 2 | 1 |  | used by the first release | ReportingService | backend/tenant/010-reporting.sql
MIG-SYNC | sync.rejection | tenant | 11 | through its owner |  | 1 | 1 | identity.principal, platform.workstation | used by the first release | CrossRegionService | backend/tenant/010-sync.sql
MIG-ASSETS | assets.asset_version | tenant | 11 | scope_path |  | 0 | 1 |  | used by the first release | VenueOpsService | backend/tenant/010-assets.sql
MIG-ASSETS | assets.media_asset | tenant | 25 | venue_id |  | 14 | 3 | identity.principal, platform.scope | used by the first release | VenueOpsService | backend/tenant/010-assets.sql
MIG-ASSETS | assets.media_collection | tenant | 7 | venue_id |  | 3 | 1 | assets.media_asset, platform.scope | used by the first release | VenueOpsService | backend/tenant/010-assets.sql
MIG-ASSETS | assets.media_collection_member | tenant | 5 | tenant root (one tenant per database; no tenant_id by design) |  | 1 | 2 |  | used by the first release | VenueOpsService | backend/tenant/010-assets.sql
MIG-ASSETS | assets.media_fingerprint | tenant | 7 | scope_path |  | 0 | 2 |  | used by the first release | VenueOpsService | backend/tenant/010-assets.sql
MIG-ASSETS | assets.media_upload | tenant | 12 | venue_id |  | 2 | 1 |  | used by the first release | VenueOpsService | backend/tenant/010-assets.sql
MIG-ASSETS | assets.media_usage | tenant | 7 | through its owner |  | 4 | 1 | assets.media_asset | used by the first release | VenueOpsService | backend/tenant/010-assets.sql
MIG-AI | ai.action_plan | tenant | 19 | scope_path |  | 1 | 2 | ai.action_plan, ai.proposed_action, identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.activity | tenant | 25 | scope_path |  | 1 | 12 | ai.conversation, identity.principal, pii.subject | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.anomaly_detector | tenant | 14 | scope_path |  | 0 | 1 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.answer_feedback | tenant | 11 | scope_path |  | 1 | 1 | ai.conversation, ai.message, identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.assistant_profile | tenant | 14 | scope_path |  | 2 | 1 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.byok_enablement | tenant | 11 | scope_path |  | 2 | 1 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.capability | tenant | 18 | scope_path |  | 6 | 2 | identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.capability_maturity | tenant | 9 | scope_path |  | 1 | 0 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.chunk_embedding | tenant | 12 | through its owner |  | 4 | 2 | ai.chunk_embedding, ai.knowledge_document | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.conversation | tenant | 8 | scope_path |  | 3 | 1 | identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.decision_record | tenant | 25 | scope_path |  | 2 | 15 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.eval_run | tenant | 14 | scope_path |  | 4 | 1 | ai.eval_suite, ai.release, identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.eval_suite | tenant | 9 | scope_path |  | 2 | 0 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.forecast_accuracy | tenant | 13 | scope_path |  | 1 | 0 | ai.forecast_definition, ai.forecast_version | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.forecast_definition | tenant | 20 | scope_path |  | 4 | 3 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.forecast_point | tenant | 12 | scope_path |  | 3 | 2 | ai.forecast_scenario, ai.forecast_version | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.forecast_scenario | tenant | 8 | scope_path |  | 1 | 1 | ai.forecast_version, identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.forecast_version | tenant | 18 | scope_path |  | 7 | 2 | ai.forecast_definition, identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.governance_alert | tenant | 14 | scope_path |  | 3 | 2 | ai.incident, ai.release, identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.governance_policy | tenant | 9 | scope_path |  | 3 | 2 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.governance_policy_version | tenant | 12 | scope_path |  | 7 | 3 | ai.governance_policy, identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.guided_choice_suggestion | tenant | 12 | scope_path |  | 2 | 1 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.history_import | tenant | 18 | scope_path |  | 3 | 1 | assets.media_asset, identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.history_observation | tenant | 10 | scope_path |  | 2 | 1 | ai.history_import | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.inbox | tenant | 3 | tenant root (one tenant per database; no tenant_id by design) | yes | 0 | 0 |  | kernel machinery: the AI consumers' inbox, since only AI writes AI tables (ADR-0058, ADR-0020) | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.incident | tenant | 19 | scope_path |  | 3 | 2 | identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.index_entry | tenant | 2 | through its owner |  | 0 | 1 | ai.index_source | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.index_job | tenant | 14 | through its owner |  | 1 | 1 | ai.index_source | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.index_source | tenant | 15 | through its owner |  | 2 | 1 | ai.knowledge_collection | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.insight | tenant | 22 | scope_path |  | 3 | 2 | ai.anomaly_detector, identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.intervention | tenant | 11 | scope_path |  | 1 | 3 | identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.knowledge_collection | tenant | 12 | scope_path |  | 4 | 1 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.knowledge_document | tenant | 11 | scope_path |  | 3 | 1 | ai.knowledge_collection | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.knowledge_gap | tenant | 13 | scope_path |  | 0 | 2 | ai.knowledge_collection, ai.knowledge_document, identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.message | tenant | 15 | through its owner |  | 2 | 1 | ai.conversation, ai.proposed_action | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.model | tenant | 19 | scope_path |  | 2 | 1 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.operational_requirement | tenant | 17 | scope_path |  | 3 | 2 | ai.forecast_version, identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.policy | tenant | 32 | scope_path |  | 15 | 4 | platform.tenant | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.policy_exception | tenant | 13 | scope_path |  | 3 | 2 | ai.governance_policy, identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.prompt_template | tenant | 13 | scope_path |  | 3 | 1 | identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.proposed_action | tenant | 19 | scope_path |  | 3 | 5 | ai.action_plan, ai.activity, identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.provider | tenant | 27 | scope_path |  | 10 | 1 | ai.model, platform.scope | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.rec_decision | tenant | 19 | scope_path |  | 1 | 1 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.rec_decline | tenant | 10 | scope_path |  | 2 | 1 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.rec_event | tenant | 11 | scope_path |  | 0 | 1 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.release | tenant | 18 | scope_path |  | 7 | 5 | identity.principal | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.suggestion | tenant | 13 | scope_path |  | 2 | 1 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.training_run | tenant | 17 | scope_path |  | 1 | 0 | ai.eval_run, ai.release | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-AI | ai.venue_settings | tenant | 14 | scope_path |  | 4 | 1 |  | used by the first release | AiService | backend/tenant/010-ai.sql
MIG-RESOURCES | resources.booking | tenant | 16 | through its owner |  | 4 | 0 | orders.sales_order, pii.subject, resources.resource | used by the first release | VenueOpsService | backend/tenant/010-resources.sql
MIG-RESOURCES | resources.resource | tenant | 17 | scope_path |  | 8 | 4 | identity.principal, platform.scope | used by the first release | VenueOpsService | backend/tenant/010-resources.sql
MIG-RESOURCES | resources.resource_block | tenant | 8 | scope_path |  | 6 | 2 |  | used by the first release | VenueOpsService | backend/tenant/010-resources.sql
MIG-RESOURCES | resources.resource_package | tenant | 13 | scope_path |  | 2 | 2 |  | used by the first release | VenueOpsService | backend/tenant/010-resources.sql
MIG-RESOURCES | resources.resource_requirement | tenant | 12 | scope_path |  | 4 | 3 |  | used by the first release | VenueOpsService | backend/tenant/010-resources.sql
MIG-RESOURCES | resources.resource_reservation | tenant | 15 | scope_path |  | 7 | 3 |  | used by the first release | VenueOpsService | backend/tenant/010-resources.sql
MIG-RESOURCES | resources.resource_schedule | tenant | 8 | scope_path |  | 2 | 1 |  | used by the first release | VenueOpsService | backend/tenant/010-resources.sql
MIG-WHITELABEL | whitelabel.analytics_provider | tenant | 13 | scope_path |  | 2 | 1 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.app_build | tenant | 15 | scope_path |  | 3 | 1 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.banner | tenant | 12 | tenant root (one tenant per database; no tenant_id by design) |  | 4 | 2 | whitelabel.tenant_config | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.booking_flow | tenant | 10 | scope_path |  | 15 | 3 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.booking_flow_step | tenant | 7 | tenant root (one tenant per database; no tenant_id by design) |  | 10 | 4 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.config_version | tenant | 13 | scope_path |  | 8 | 1 | identity.principal | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.content_page | tenant | 11 | scope_path |  | 5 | 2 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.custom_domain | tenant | 17 | tenant root (one tenant per database; no tenant_id by design) |  | 6 | 5 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.faq_category | tenant | 5 | scope_path |  | 1 | 1 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.faq_entry | tenant | 6 | through its owner |  | 2 | 1 | whitelabel.faq_category | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.feature_toggle | tenant | 7 | tenant root (one tenant per database; no tenant_id by design) |  | 4 | 2 | whitelabel.tenant_config | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.footer_config | tenant | 4 | scope_path |  | 4 | 1 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.footer_config_column | tenant | 3 | through its owner |  | 4 | 1 | whitelabel.footer_config | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.footer_config_social_link | tenant | 4 | through its owner |  | 4 | 1 | whitelabel.footer_config | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.guided_choice | tenant | 13 | venue_id |  | 8 | 6 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.guided_choice_answer | tenant | 12 | through its owner |  | 10 | 4 | whitelabel.guided_choice, whitelabel.guided_choice_question | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.guided_choice_question | tenant | 5 | through its owner |  | 8 | 4 | whitelabel.guided_choice | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.homepage_layout | tenant | 3 | tenant root (one tenant per database; no tenant_id by design) |  | 6 | 1 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.homepage_section | tenant | 10 | tenant root (one tenant per database; no tenant_id by design) |  | 7 | 2 | whitelabel.content_page, whitelabel.homepage_layout | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.module_enablement | tenant | 7 | tenant root (one tenant per database; no tenant_id by design) |  | 4 | 2 | whitelabel.tenant_config | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.navigation_config | tenant | 3 | tenant root (one tenant per database; no tenant_id by design) |  | 5 | 1 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.navigation_item | tenant | 7 | tenant root (one tenant per database; no tenant_id by design) |  | 5 | 2 | whitelabel.navigation_config | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.policy | tenant | 10 | scope_path |  | 3 | 1 | identity.principal | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.promo_block | tenant | 11 | scope_path |  | 5 | 3 | promotions.promotion | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.publish_review_policy | tenant | 5 | scope_path |  | 2 | 1 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.site_package | tenant | 9 | scope_path |  | 2 | 1 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.site_setup_progress | tenant | 7 | scope_path |  | 2 | 1 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.store_account | tenant | 15 | scope_path |  | 3 | 1 |  | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-WHITELABEL | whitelabel.tenant_config | tenant | 27 | tenant root (one tenant per database; no tenant_id by design) |  | 24 | 12 | platform.tenant, whitelabel.footer_config, whitelabel.homepage_layout, whitelabel.homepage_section, whitelabel.navigation_config, whitelabel.navigation_item | used by the first release | WhiteLabelService | backend/tenant/010-whitelabel.sql
MIG-PLATFORM | platform.audit_record | tenant | 8 | tenant root (one tenant per database; no tenant_id by design) | yes | 0 | 4 | identity.principal, platform.scope | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.denomination | tenant | 7 | tenant root (one tenant per database; no tenant_id by design) |  | 2 | 1 |  | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.device | tenant | 41 | tenant root (one tenant per database; no tenant_id by design) |  | 3 | 1 | platform.workstation | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.device_heartbeat | tenant | 2 | tenant root (one tenant per database; no tenant_id by design) |  | 1 | 0 | platform.device | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.dsar_request | tenant | 7 | through its owner |  | 0 | 2 | approvals.request, platform.guest_link | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.guest_link | tenant | 5 | tenant root (one tenant per database; no tenant_id by design) |  | 0 | 0 |  | referenced by marketing.guest_profile | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.idempotency_record | tenant | 11 | scope_path |  | 0 | 6 |  | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.outbox | tenant | 15 | scope_path | yes | 0 | 58 |  | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.outlet | tenant | 16 | venue_id |  | 10 | 2 | inventory.location, ledger.cost_center, platform.scope | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.region_settings | tenant | 19 | tenant root (one tenant per database; no tenant_id by design) |  | 5 | 2 | platform.scope | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.sale_board | tenant | 6 | venue_id |  | 4 | 2 | platform.scope | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.sale_board_page | tenant | 4 | through its owner |  | 1 | 2 | platform.sale_board | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.sale_board_tile | tenant | 2 | tenant root (one tenant per database; no tenant_id by design) |  | 2 | 2 | platform.sale_board_page | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.scope | tenant | 8 | none |  | 9 | 2 |  | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.tenant | tenant | 2 | tenant root (one tenant per database; no tenant_id by design) |  | 0 | 0 | platform.scope | referenced by marketing.consent_purpose | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.venue_settings | tenant | 32 | venue_id |  | 5 | 2 | platform.scope | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-PLATFORM | platform.workstation | tenant | 20 | scope_path |  | 7 | 1 | access.access_point, platform.scope | used by the first release | TenancyService | backend/tenant/010-platform.sql
MIG-WORKFORCE | workforce.attendance | tenant | 15 | venue_id |  | 1 | 1 | access.access_point, identity.principal, platform.scope, workforce.rota_assignment | used by the first release | TenancyService | backend/tenant/010-workforce.sql
MIG-WORKFORCE | workforce.attendance_amendment | tenant | 7 | tenant root (one tenant per database; no tenant_id by design) |  | 1 | 0 |  | used by the first release | TenancyService | backend/tenant/010-workforce.sql
MIG-WORKFORCE | workforce.rota_assignment | tenant | 17 | venue_id |  | 4 | 2 | identity.principal, platform.scope, platform.workstation | used by the first release | TenancyService | backend/tenant/010-workforce.sql
MIG-SEATING | seating.accessible | tenant | 5 | scope_path |  | 2 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-seating.sql
MIG-SEATING | seating.recommendation_rule | tenant | 6 | scope_path |  | 2 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-seating.sql
MIG-SEATING | seating.seat | tenant | 11 | tenant root (one tenant per database; no tenant_id by design) |  | 2 | 1 | seating.seat_map | used by the first release | CatalogueService | backend/tenant/010-seating.sql
MIG-SEATING | seating.seat_block | tenant | 10 | scope_path |  | 0 | 0 | catalogue.performance, identity.principal | referenced by seating.seat_reservation | CatalogueService | backend/tenant/010-seating.sql
MIG-SEATING | seating.seat_block_item | tenant | 4 | tenant root (one tenant per database; no tenant_id by design) |  | 1 | 0 |  | used by the first release | CatalogueService | backend/tenant/010-seating.sql
MIG-SEATING | seating.seat_category | tenant | 7 | venue_id |  | 4 | 1 | platform.scope | used by the first release | CatalogueService | backend/tenant/010-seating.sql
MIG-SEATING | seating.seat_map | tenant | 12 | venue_id |  | 1 | 1 | platform.scope | used by the first release | CatalogueService | backend/tenant/010-seating.sql
MIG-SEATING | seating.seat_price_band | tenant | 10 | tenant root (one tenant per database; no tenant_id by design) |  | 3 | 2 |  | used by the first release | CatalogueService | backend/tenant/010-seating.sql
MIG-SEATING | seating.seat_reservation | tenant | 12 | through its owner |  | 6 | 4 | catalogue.performance, identity.principal, pii.subject, seating.seat_block | used by the first release | CatalogueService | backend/tenant/010-seating.sql
MIG-SEATING | seating.seat_reservation_item | tenant | 5 | tenant root (one tenant per database; no tenant_id by design) |  | 1 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-seating.sql
MIG-SEATING | seating.section | tenant | 7 | scope_path |  | 0 | 1 | assets.media_asset | used by the first release | CatalogueService | backend/tenant/010-seating.sql
MIG-MAINTENANCE | maintenance.asset | tenant | 30 | venue_id |  | 0 | 0 | access.access_point, inventory.supplier, platform.scope | referenced by maintenance.work_order | VenueOpsService | backend/tenant/010-maintenance.sql
MIG-MAINTENANCE | maintenance.incident | tenant | 28 | venue_id |  | 0 | 0 | identity.principal, maintenance.asset, maintenance.work_order, platform.scope | referenced by maintenance.work_order | VenueOpsService | backend/tenant/010-maintenance.sql
MIG-MAINTENANCE | maintenance.inspection | tenant | 14 | venue_id |  | 0 | 0 | identity.principal, maintenance.asset, platform.scope | referenced by maintenance.work_order | VenueOpsService | backend/tenant/010-maintenance.sql
MIG-MAINTENANCE | maintenance.inspection_template | tenant | 9 | venue_id |  | 2 | 1 | platform.scope | used by the first release | VenueOpsService | backend/tenant/010-maintenance.sql
MIG-MAINTENANCE | maintenance.inspection_template_item | tenant | 11 | through its owner |  | 1 | 1 | maintenance.inspection_template | used by the first release | VenueOpsService | backend/tenant/010-maintenance.sql
MIG-MAINTENANCE | maintenance.work_order | tenant | 56 | venue_id |  | 2 | 0 | identity.principal, maintenance.asset, maintenance.incident, maintenance.inspection, platform.scope | used by the first release | VenueOpsService | backend/tenant/010-maintenance.sql
MIG-WALLET | wallet.accounting_mapping | tenant | 3 | scope_path |  | 1 | 1 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.authentication_policy | tenant | 2 | scope_path |  | 1 | 1 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.auto_reload_setting | tenant | 11 | scope_path |  | 2 | 1 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.balance | tenant | 9 | tenant root (one tenant per database; no tenant_id by design) |  | 4 | 2 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.channel_rule | tenant | 10 | scope_path |  | 1 | 1 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.configuration_version | tenant | 6 | scope_path |  | 2 | 1 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.configuration_version_snapshot | tenant | 6 | scope_path |  | 1 | 1 | wallet.configuration_version | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.consumption_policy | tenant | 7 | scope_path |  | 1 | 1 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.credit_lot | tenant | 12 | scope_path |  | 5 | 2 | wallet.wallet | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.credit_type | tenant | 15 | scope_path |  | 1 | 1 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.exit_settlement | tenant | 13 | scope_path |  | 1 | 1 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.fund_reservation | tenant | 12 | tenant root (one tenant per database; no tenant_id by design) |  | 0 | 0 | orders.sales_order | referenced by wallet.wallet_transaction | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.funding_rule | tenant | 11 | scope_path |  | 3 | 2 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.gift_card | tenant | 11 | subject |  | 1 | 0 | pii.subject | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.integration_mapping | tenant | 9 | scope_path |  | 1 | 1 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.reconciliation_source | tenant | 2 | scope_path |  | 1 | 1 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.refund_policy | tenant | 8 | scope_path |  | 4 | 2 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.risk_rule_set | tenant | 2 | scope_path |  | 1 | 1 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.transfer_rule | tenant | 9 | scope_path |  | 1 | 1 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.wallet | tenant | 9 | subject |  | 8 | 4 | pii.subject | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.wallet_transaction | tenant | 12 | venue_id |  | 2 | 4 | identity.principal, orders.sales_order, platform.scope, wallet.fund_reservation, wallet.wallet | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-WALLET | wallet.wallet_type | tenant | 25 | scope_path |  | 1 | 1 |  | used by the first release | WalletService | backend/tenant/010-wallet.sql
MIG-CATALOGUE | catalogue.alternative_code | tenant | 7 | tenant root (one tenant per database; no tenant_id by design) |  | 2 | 1 | catalogue.product, catalogue.variant | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.channel_capacity | tenant | 12 | through its owner |  | 12 | 5 | catalogue.performance, seating.seat_category | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.channel_envelope | tenant | 19 | through its owner |  | 2 | 2 | catalogue.channel_capacity | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.entitlement_template | tenant | 32 | scope_path |  | 8 | 2 | access.admission_rules | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.event | tenant | 10 | scope_path |  | 9 | 4 | platform.scope | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.event_capacity_profile | tenant | 12 | scope_path |  | 2 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.event_registration | tenant | 7 | scope_path |  | 1 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.event_resource_plan | tenant | 4 | scope_path |  | 2 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.event_schedule | tenant | 6 | scope_path |  | 2 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.group_package | tenant | 11 | scope_path |  | 4 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.import_job | tenant | 25 | scope_path |  | 1 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.inventory_reservation | tenant | 18 | through its owner |  | 9 | 10 | catalogue.channel_capacity, identity.principal, platform.workstation | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.performance | tenant | 12 | through its owner |  | 14 | 4 | access.admission_rules, catalogue.event, seating.seat_map | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.price | tenant | 5 | through its owner |  | 2 | 1 | catalogue.price_list, catalogue.variant, ledger.tax_code | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.price_list | tenant | 28 | venue_id |  | 9 | 5 | platform.scope | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.product | tenant | 44 | scope_path |  | 31 | 4 | catalogue.entitlement_template, platform.scope | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.product_category | tenant | 12 | scope_path |  | 6 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.product_eligibility_rule | tenant | 15 | scope_path |  | 8 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.product_media | tenant | 7 | tenant root (one tenant per database; no tenant_id by design) |  | 5 | 2 | catalogue.product | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.product_version | tenant | 9 | tenant root (one tenant per database; no tenant_id by design) |  | 0 | 1 | catalogue.product | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.published_bundle | tenant | 10 | venue_id |  | 3 | 1 | platform.scope | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.variant | tenant | 9 | through its owner |  | 10 | 3 | catalogue.product | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-CATALOGUE | catalogue.waitlist_entry | tenant | 11 | through its owner |  | 2 | 2 | catalogue.performance, catalogue.variant, pii.subject | used by the first release | CatalogueService | backend/tenant/010-catalogue.sql
MIG-LEDGER | ledger.account | tenant | 15 | through its owner |  | 0 | 0 | ledger.legal_entity | referenced by inventory.supplier | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.cost_center | tenant | 6 | venue_id |  | 0 | 0 | platform.scope | referenced by ledger.posting | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.credit_memo | tenant | 30 | scope_path |  | 5 | 1 |  | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.credit_memo_line | tenant | 10 | through its owner |  | 3 | 1 | ledger.credit_memo | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.einvoice_transmission | tenant | 17 | scope_path |  | 3 | 1 |  | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.einvoicing_provider | tenant | 12 | scope_path |  | 2 | 1 |  | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.fiscal_period | tenant | 9 | through its owner |  | 0 | 0 | identity.principal, ledger.legal_entity | referenced by ledger.journal_entry | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.fx_provider_assignment | tenant | 6 | scope_path |  | 1 | 1 |  | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.fx_rate | tenant | 13 | through its owner |  | 7 | 2 | platform.scope | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.journal_entry | tenant | 20 | through its owner |  | 0 | 5 | identity.principal, ledger.fiscal_period | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.journal_line | tenant | 9 | venue_id | yes | 0 | 2 | ledger.journal_entry, platform.scope | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.legal_entity | tenant | 11 | scope_path |  | 3 | 1 |  | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.posting | tenant | 12 | venue_id |  | 1 | 1 | ledger.account, ledger.cost_center, ledger.journal_entry, platform.scope | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.price_variance | tenant | 15 | venue_id |  | 0 | 1 | catalogue.variant, identity.principal, ledger.journal_entry, orders.order_line, orders.sales_order, platform.scope | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.tax_code | tenant | 12 | tenant root (one tenant per database; no tenant_id by design) |  | 3 | 2 | ledger.account | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.tax_invoice | tenant | 39 | scope_path |  | 6 | 2 |  | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.tax_invoice_line | tenant | 17 | through its owner |  | 6 | 2 | ledger.tax_invoice | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-LEDGER | ledger.tax_invoice_template | tenant | 18 | scope_path |  | 2 | 2 |  | used by the first release | LedgerService | backend/tenant/010-ledger.sql
MIG-INVENTORY | inventory.goods_receipt | tenant | 11 | through its owner |  | 3 | 2 | identity.principal, inventory.purchase_order, ledger.journal_entry | used by the first release | InventoryService | backend/tenant/010-inventory.sql
MIG-INVENTORY | inventory.goods_receipt_line | tenant | 11 | through its owner |  | 2 | 2 | inventory.goods_receipt, inventory.inventory_item | used by the first release | InventoryService | backend/tenant/010-inventory.sql
MIG-INVENTORY | inventory.inventory_item | tenant | 26 | venue_id |  | 6 | 3 | inventory.supplier, platform.scope | used by the first release | InventoryService | backend/tenant/010-inventory.sql
MIG-INVENTORY | inventory.kit_component | tenant | 6 | scope_path |  | 3 | 1 |  | used by the first release | InventoryService | backend/tenant/010-inventory.sql
MIG-INVENTORY | inventory.location | tenant | 7 | venue_id |  | 0 | 0 | platform.scope | referenced by inventory.stock_batch | InventoryService | backend/tenant/010-inventory.sql
MIG-INVENTORY | inventory.movement | tenant | 17 | through its owner |  | 4 | 3 | identity.principal, inventory.inventory_item, ledger.cost_center, ledger.journal_entry | used by the first release | InventoryService | backend/tenant/010-inventory.sql
MIG-INVENTORY | inventory.purchase_order | tenant | 29 | scope_path |  | 0 | 0 | identity.principal, inventory.requisition, inventory.supplier, platform.scope | referenced by inventory.goods_receipt | InventoryService | backend/tenant/010-inventory.sql
MIG-INVENTORY | inventory.requisition | tenant | 20 | venue_id |  | 0 | 0 | identity.principal, platform.scope | referenced by inventory.purchase_order | InventoryService | backend/tenant/010-inventory.sql
MIG-INVENTORY | inventory.serialised_item | tenant | 9 | tenant root (one tenant per database; no tenant_id by design) |  | 1 | 0 |  | used by the first release | InventoryService | backend/tenant/010-inventory.sql
MIG-INVENTORY | inventory.stock_batch | tenant | 10 | tenant root (one tenant per database; no tenant_id by design) |  | 2 | 0 | inventory.inventory_item, inventory.location, inventory.supplier | used by the first release | InventoryService | backend/tenant/010-inventory.sql
MIG-INVENTORY | inventory.stock_earmark | tenant | 10 | tenant root (one tenant per database; no tenant_id by design) |  | 1 | 1 |  | used by the first release | InventoryService | backend/tenant/010-inventory.sql
MIG-INVENTORY | inventory.supplier | tenant | 16 | scope_path |  | 0 | 0 | ledger.account | referenced by inventory.purchase_order | InventoryService | backend/tenant/010-inventory.sql
MIG-PROMOTIONS | promotions.allocation_component | tenant | 9 | venue_id |  | 3 | 2 | ledger.account, ledger.legal_entity, platform.scope, promotions.allocation_split | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.allocation_split | tenant | 4 | through its owner |  | 0 | 0 | promotions.bundle | referenced by promotions.allocation_component | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.bundle | tenant | 20 | venue_id |  | 5 | 2 | platform.scope | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.bundle_choice_group | tenant | 6 | through its owner |  | 3 | 1 | promotions.bundle | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.bundle_choice_option | tenant | 5 | through its owner |  | 3 | 1 | promotions.bundle_choice_group | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.bundle_component | tenant | 13 | venue_id |  | 3 | 2 | platform.scope, promotions.bundle | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.code_assignment | tenant | 9 | scope_path |  | 1 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.coupon_campaign | tenant | 14 | venue_id |  | 3 | 1 | platform.scope | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.coupon_code | tenant | 17 | scope_path |  | 4 | 2 | orders.sales_order, pii.subject | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.coupon_code_batch | tenant | 11 | tenant root (one tenant per database; no tenant_id by design) |  | 1 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.promotion | tenant | 24 | venue_id |  | 13 | 4 | platform.scope | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.promotion_audit | tenant | 14 | venue_id |  | 0 | 9 |  | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.promotion_channel_publication | tenant | 9 | venue_id |  | 2 | 2 |  | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.promotion_evaluation_trace | tenant | 9 | venue_id |  | 0 | 3 |  | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.promotion_rule | tenant | 13 | venue_id |  | 1 | 0 |  | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-PROMOTIONS | promotions.promotion_variant | tenant | 5 | tenant root (one tenant per database; no tenant_id by design) |  | 1 | 1 |  | used by the first release | CatalogueService | backend/tenant/010-promotions.sql
MIG-ORDERS | orders.cart | tenant | 18 | venue_id |  | 11 | 8 | pii.subject, platform.scope | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.cart_line | tenant | 21 | through its owner |  | 10 | 6 | catalogue.inventory_reservation, catalogue.performance, catalogue.variant, orders.cart | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.cash_count_line | tenant | 11 | through its owner |  | 6 | 4 | orders.pos_shift | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.cash_movement | tenant | 13 | through its owner |  | 4 | 3 | identity.principal, orders.pos_shift | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.deposit_box | tenant | 15 | venue_id |  | 4 | 3 | identity.principal, orders.pos_shift, platform.scope, platform.workstation | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.deposit_box_foreign_holding | tenant | 7 | through its owner |  | 3 | 2 | orders.deposit_box | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.deposit_box_opening_denomination | tenant | 4 | through its owner |  | 3 | 2 | orders.deposit_box | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.fraud_rule | tenant | 12 | scope_path |  | 3 | 0 |  | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.group_booking | tenant | 21 | through its owner |  | 4 | 1 | orders.sales_order | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.group_customer_organisation | tenant | 6 | tenant root (one tenant per database; no tenant_id by design) |  | 0 | 0 |  | referenced by orders.group_customer_organisation_contact | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.group_customer_organisation_contact | tenant | 6 | tenant root (one tenant per database; no tenant_id by design) |  | 0 | 0 | orders.group_customer_organisation | referenced by orders.group_visit_plan | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.group_participant | tenant | 7 | tenant root (one tenant per database; no tenant_id by design) |  | 1 | 0 | orders.group_participant_list | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.group_participant_list | tenant | 5 | tenant root (one tenant per database; no tenant_id by design) |  | 0 | 0 |  | referenced by orders.group_participant | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.group_visit_plan | tenant | 27 | scope_path |  | 2 | 1 | orders.group_booking, orders.group_customer_organisation_contact | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.invitation | tenant | 12 | through its owner |  | 1 | 0 | catalogue.performance, catalogue.product, ledger.cost_center | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.no_sale_event | tenant | 8 | through its owner |  | 1 | 1 | identity.principal, orders.pos_shift, platform.workstation | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.order_event | tenant | 16 | scope_path |  | 0 | 15 |  | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.order_line | tenant | 23 | venue_id |  | 16 | 10 | catalogue.inventory_reservation, catalogue.performance, catalogue.variant, orders.sales_order | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.order_line_discount | tenant | 6 | through its owner |  | 12 | 3 | orders.order_line, promotions.promotion | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.order_line_eligibility | tenant | 7 | through its owner |  | 12 | 1 | orders.order_line | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.payment | tenant | 18 | through its owner |  | 26 | 17 | orders.sales_order | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.payment_link | tenant | 14 | scope_path |  | 2 | 1 | orders.sales_order | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.pos_shift | tenant | 31 | scope_path |  | 12 | 10 | identity.principal, platform.scope, platform.workstation | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.pos_shift_approval | tenant | 6 | through its owner |  | 12 | 1 | orders.pos_shift | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.pos_shift_incident | tenant | 6 | through its owner |  | 12 | 2 | orders.pos_shift | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.refund | tenant | 20 | through its owner |  | 4 | 3 | identity.principal, orders.sales_order | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.refund_policy | tenant | 8 | venue_id |  | 2 | 1 | platform.scope | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.refund_policy_time_band | tenant | 4 | through its owner |  | 1 | 1 | orders.refund_policy | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.resale_listing | tenant | 16 | scope_path |  | 1 | 1 | access.entitlement | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.reservation | tenant | 7 | venue_id |  | 7 | 4 | orders.sales_order, platform.scope | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.reservation_line | tenant | 14 | through its owner |  | 4 | 1 | orders.reservation | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.sales_order | tenant | 26 | scope_path |  | 32 | 16 | identity.principal, orders.pos_shift, pii.subject, platform.scope, platform.workstation | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.stored_value_authorisation | tenant | 9 | scope_path |  | 0 | 1 |  | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.ticket_template | tenant | 10 | tenant root (one tenant per database; no tenant_id by design) |  | 5 | 4 |  | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.ticket_template_channel | tenant | 3 | tenant root (one tenant per database; no tenant_id by design) |  | 4 | 3 | orders.ticket_template | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.ticket_transfer | tenant | 12 | through its owner |  | 3 | 2 | orders.sales_order, pii.subject | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.till_shift_policy | tenant | 11 | scope_path |  | 2 | 1 |  | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.visit_reminder | tenant | 7 | scope_path |  | 2 | 1 | orders.sales_order | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ORDERS | orders.wallet_pass | tenant | 9 | scope_path |  | 1 | 1 | access.entitlement | used by the first release | OrderService | backend/tenant/010-orders.sql
MIG-ACCESS | access.access_incident | tenant | 12 | scope_path |  | 0 | 1 |  | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.access_point | tenant | 18 | scope_path |  | 12 | 6 | platform.scope | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.access_point_group | tenant | 8 | scope_path |  | 4 | 2 |  | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.admission_rules | tenant | 21 | scope_path |  | 4 | 3 |  | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.biometric_audit_event | tenant | 18 | scope_path |  | 0 | 2 |  | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.biometric_profile | tenant | 37 | scope_path |  | 6 | 4 |  | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.blacklist | tenant | 10 | scope_path |  | 2 | 1 | identity.principal | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.configuration_change | tenant | 11 | scope_path |  | 0 | 18 |  | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.credential_policy | tenant | 32 | scope_path |  | 4 | 3 |  | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.device_binding | tenant | 15 | scope_path |  | 1 | 1 |  | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.device_placement | tenant | 18 | scope_path |  | 1 | 1 | platform.device | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.entitlement | tenant | 31 | scope_path |  | 19 | 7 | catalogue.product, orders.sales_order, platform.scope | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.entry_rule_point | tenant | 5 | through its owner |  | 1 | 1 | access.admission_rules | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.face_reenrolment_attempt | tenant | 15 | scope_path |  | 1 | 1 |  | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.gate_mode_change | tenant | 13 | scope_path |  | 2 | 1 |  | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.gate_mode_policy | tenant | 12 | scope_path |  | 3 | 1 |  | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.parking_entitlement | tenant | 12 | subject |  | 2 | 1 | access.parking_facility, orders.sales_order, pii.subject | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.parking_facility | tenant | 14 | venue_id |  | 2 | 1 | platform.scope | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-ACCESS | access.scan_event | tenant | 23 | scope_path | yes | 4 | 1 | access.access_point, access.entitlement, identity.principal, platform.scope | used by the first release | AccessService | backend/tenant/010-access.sql
MIG-MARKETING | marketing.agent_availability | tenant | 7 | tenant root (one tenant per database; no tenant_id by design) |  | 2 | 1 | identity.principal | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.attribution_touch | tenant | 8 | through its owner |  | 2 | 0 | marketing.campaign, marketing.journey, orders.sales_order, pii.subject | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.booking_consent_record | tenant | 20 | scope_path |  | 2 | 1 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.campaign | tenant | 22 | venue_id |  | 5 | 4 | identity.principal, marketing.segment, platform.scope | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.campaign_target | tenant | 7 | tenant root (one tenant per database; no tenant_id by design) |  | 0 | 2 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.campaign_variant | tenant | 10 | scope_path |  | 4 | 2 | marketing.campaign | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.case | tenant | 23 | venue_id |  | 5 | 3 | identity.principal, orders.sales_order, pii.subject, platform.scope | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.case_message | tenant | 11 | tenant root (one tenant per database; no tenant_id by design) |  | 1 | 1 | identity.principal, marketing.case | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.challenge | tenant | 14 | scope_path |  | 2 | 1 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.challenge_progress | tenant | 9 | through its owner |  | 1 | 0 | marketing.challenge, pii.subject | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.consent_propagation | tenant | 9 | tenant root (one tenant per database; no tenant_id by design) |  | 0 | 2 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.consent_purpose | tenant | 8 | tenant root (one tenant per database; no tenant_id by design) |  | 3 | 1 | platform.tenant | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.consent_purpose_channel | tenant | 3 | tenant root (one tenant per database; no tenant_id by design) |  | 2 | 1 | marketing.consent_purpose | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.consent_question | tenant | 11 | scope_path |  | 12 | 2 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.consent_question_version | tenant | 6 | tenant root (one tenant per database; no tenant_id by design) |  | 11 | 2 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.consent_record | tenant | 11 | subject |  | 8 | 6 | identity.principal, orders.sales_order, pii.subject | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.conversation | tenant | 21 | venue_id |  | 2 | 2 | identity.principal, marketing.case, pii.subject, platform.scope | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.conversation_message | tenant | 8 | through its owner |  | 2 | 2 | ai.activity, marketing.conversation | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.conversation_message_attachment | tenant | 4 | through its owner |  | 2 | 1 | marketing.conversation_message | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.cookie_banner_design | tenant | 18 | scope_path |  | 3 | 1 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.customer_badge | tenant | 9 | tenant root (one tenant per database; no tenant_id by design) |  | 2 | 1 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.device_consent | tenant | 16 | scope_path |  | 4 | 2 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.device_consent_category | tenant | 4 | through its owner |  | 4 | 1 | marketing.device_consent | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.form_definition | tenant | 16 | scope_path |  | 4 | 1 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.form_definition_field | tenant | 23 | scope_path |  | 3 | 2 | marketing.form_definition | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.form_submission | tenant | 12 | subject |  | 3 | 1 | pii.subject | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.guest_device | tenant | 14 | subject |  | 2 | 1 | pii.subject | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.guest_document | tenant | 9 | subject |  | 2 | 1 | marketing.consent_purpose, pii.subject | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.guest_preference | tenant | 7 | subject |  | 2 | 1 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.guest_profile | tenant | 23 | through its owner |  | 12 | 5 | marketing.loyalty_position, marketing.segment, pii.subject, platform.guest_link | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.invitation | tenant | 13 | scope_path |  | 1 | 1 | catalogue.performance, catalogue.product, ledger.cost_center | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.invitation_campaign | tenant | 11 | scope_path |  | 2 | 1 | catalogue.product | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.journey | tenant | 9 | scope_path |  | 0 | 0 |  | referenced by marketing.attribution_touch | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.lost_item | tenant | 17 | venue_id |  | 1 | 1 | platform.scope | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.loyalty_position | tenant | 12 | through its owner |  | 7 | 2 | marketing.loyalty_programme, pii.subject | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.loyalty_programme | tenant | 7 | venue_id |  | 6 | 2 | ledger.account, platform.scope | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.loyalty_rule | tenant | 9 | tenant root (one tenant per database; no tenant_id by design) |  | 1 | 1 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.message_dispatch | tenant | 18 | subject | yes | 2 | 5 | marketing.campaign, marketing.campaign_variant, pii.subject | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.message_template | tenant | 12 | tenant root (one tenant per database; no tenant_id by design) |  | 4 | 2 | platform.tenant | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.message_template_version | tenant | 16 | tenant root (one tenant per database; no tenant_id by design) |  | 1 | 2 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.points_earning_rule | tenant | 6 | through its owner |  | 3 | 2 | marketing.loyalty_programme | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.points_redemption_rule | tenant | 13 | tenant root (one tenant per database; no tenant_id by design) |  | 1 | 1 | catalogue.product | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.privacy_notice_governance | tenant | 14 | scope_path |  | 0 | 1 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.programme_tier | tenant | 11 | through its owner |  | 4 | 2 | marketing.loyalty_programme | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.referral | tenant | 10 | scope_path |  | 1 | 1 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.review | tenant | 13 | venue_id |  | 1 | 1 | identity.principal, marketing.case, orders.sales_order, pii.subject, platform.scope | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.reward | tenant | 10 | tenant root (one tenant per database; no tenant_id by design) |  | 2 | 1 | catalogue.product | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.segment | tenant | 14 | venue_id |  | 3 | 1 | platform.scope | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.segment_criterion | tenant | 6 | through its owner |  | 4 | 4 | marketing.segment | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.subscription | tenant | 8 | subject |  | 2 | 1 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.tracking_technology | tenant | 23 | scope_path |  | 4 | 1 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.waiver_field_rule | tenant | 5 | through its owner |  | 1 | 1 | marketing.form_definition_field | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.waiver_requirement | tenant | 30 | scope_path |  | 1 | 1 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.waiver_requirement_event | tenant | 10 | scope_path |  | 0 | 1 |  | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-MARKETING | marketing.wishlist_item | tenant | 12 | subject |  | 2 | 1 | catalogue.performance, pii.subject | used by the first release | MarketingService | backend/tenant/010-marketing.sql
MIG-FNB | fnb.allergen_verdict | tenant | 9 | tenant root (one tenant per database; no tenant_id by design) |  | 0 | 1 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.bill_split | tenant | 3 | through its owner |  | 1 | 1 | fnb.table_visit | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.cold_chain_event | tenant | 9 | tenant root (one tenant per database; no tenant_id by design) |  | 2 | 1 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.corrective_action | tenant | 13 | scope_path |  | 4 | 4 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.course_rule | tenant | 7 | scope_path |  | 2 | 1 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.delivery_location | tenant | 12 | venue_id |  | 7 | 2 | fnb.dining_table, platform.scope, seating.seat | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.delivery_location_outlet | tenant | 3 | tenant root (one tenant per database; no tenant_id by design) |  | 2 | 2 | fnb.delivery_location, platform.outlet | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.delivery_policy | tenant | 16 | scope_path |  | 4 | 1 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.dining_table | tenant | 9 | tenant root (one tenant per database; no tenant_id by design) |  | 10 | 3 | platform.outlet | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.kitchen_exception | tenant | 9 | tenant root (one tenant per database; no tenant_id by design) |  | 1 | 2 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.kitchen_sla | tenant | 3 | tenant root (one tenant per database; no tenant_id by design) |  | 2 | 1 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.kitchen_station | tenant | 10 | tenant root (one tenant per database; no tenant_id by design) |  | 5 | 1 | platform.outlet | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.kitchen_ticket | tenant | 16 | through its owner |  | 22 | 9 | identity.principal, platform.outlet | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.kitchen_ticket_line | tenant | 14 | through its owner |  | 19 | 3 | fnb.kitchen_station, fnb.kitchen_ticket | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.location_session | tenant | 10 | venue_id |  | 2 | 1 | fnb.delivery_location, fnb.table_visit, pii.subject, platform.outlet, platform.scope | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.menu | tenant | 8 | through its owner |  | 7 | 6 | platform.outlet | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.menu_item | tenant | 17 | through its owner |  | 14 | 6 | catalogue.variant, fnb.kitchen_station | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.menu_item_modifier | tenant | 5 | tenant root (one tenant per database; no tenant_id by design) |  | 2 | 1 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.menu_schedule | tenant | 9 | scope_path |  | 1 | 1 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.menu_section | tenant | 5 | through its owner |  | 5 | 3 | fnb.menu | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.menu_version | tenant | 12 | scope_path |  | 2 | 1 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.modifier_group | tenant | 6 | scope_path |  | 4 | 1 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.modifier_option | tenant | 7 | through its owner |  | 2 | 1 | fnb.modifier_group | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.order_fulfilment | tenant | 10 | scope_path |  | 0 | 1 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.production_plan | tenant | 6 | tenant root (one tenant per database; no tenant_id by design) |  | 3 | 2 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.production_plan_line | tenant | 7 | tenant root (one tenant per database; no tenant_id by design) |  | 2 | 1 | fnb.production_plan | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.production_run | tenant | 11 | through its owner |  | 0 | 1 | fnb.recipe | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.recipe | tenant | 4 | through its owner |  | 2 | 1 | fnb.menu_item | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.recipe_ingredient | tenant | 6 | through its owner |  | 1 | 1 | fnb.recipe, inventory.inventory_item | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.reservation_table | tenant | 4 | tenant root (one tenant per database; no tenant_id by design) |  | 6 | 4 | fnb.dining_table | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.service_order | tenant | 17 | through its owner |  | 17 | 9 | fnb.kitchen_ticket, fnb.table_visit, orders.sales_order, platform.outlet | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.service_order_line | tenant | 12 | through its owner |  | 12 | 1 | access.entitlement, fnb.service_order | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.sold_out_item | tenant | 10 | tenant root (one tenant per database; no tenant_id by design) |  | 1 | 0 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.sub_bill | tenant | 11 | through its owner |  | 1 | 1 | fnb.bill_split | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.substitution_rule | tenant | 10 | tenant root (one tenant per database; no tenant_id by design) |  | 2 | 1 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.table_combination | tenant | 6 | scope_path |  | 2 | 1 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.table_reservation | tenant | 24 | through its owner |  | 6 | 4 | fnb.table_visit, pii.subject, platform.outlet | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.table_session | tenant | 9 | through its owner |  | 2 | 1 | fnb.dining_table, fnb.table_visit, pii.subject, platform.outlet | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.table_visit | tenant | 16 | through its owner |  | 11 | 8 | fnb.dining_table, identity.principal, pii.subject, platform.outlet | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.temperature_log | tenant | 11 | tenant root (one tenant per database; no tenant_id by design) |  | 2 | 1 |  | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-FNB | fnb.waitlist_entry | tenant | 11 | through its owner |  | 3 | 2 | pii.subject, platform.outlet | used by the first release | FnbService | backend/tenant/010-fnb.sql
MIG-PAYMENTS | payments.dunning_case | tenant | 14 | scope_path |  | 4 | 1 | orders.sales_order | used by the first release | OrderService | backend/tenant/010-payments.sql
MIG-PAYMENTS | payments.dunning_policy | tenant | 8 | scope_path |  | 2 | 1 |  | used by the first release | OrderService | backend/tenant/010-payments.sql
MIG-PAYMENTS | payments.instalment | tenant | 9 | through its owner |  | 2 | 1 | payments.instalment_plan | used by the first release | OrderService | backend/tenant/010-payments.sql
MIG-PAYMENTS | payments.instalment_plan | tenant | 11 | scope_path |  | 2 | 1 |  | used by the first release | OrderService | backend/tenant/010-payments.sql
MIG-PAYMENTS | payments.instalment_policy | tenant | 10 | scope_path |  | 2 | 1 |  | used by the first release | OrderService | backend/tenant/010-payments.sql
MIG-PAYMENTS | payments.method | tenant | 16 | scope_path |  | 0 | 0 |  | referenced by payments.payment_attempt | OrderService | backend/tenant/010-payments.sql
MIG-PAYMENTS | payments.payment_attempt | tenant | 19 | scope_path |  | 0 | 2 | orders.payment, orders.sales_order, payments.method, payments.provider_connection | used by the first release | OrderService | backend/tenant/010-payments.sql
MIG-PAYMENTS | payments.provider | tenant | 15 | scope_path |  | 3 | 1 |  | used by the first release | OrderService | backend/tenant/010-payments.sql
MIG-PAYMENTS | payments.provider_connection | tenant | 12 | scope_path |  | 3 | 1 |  | used by the first release | OrderService | backend/tenant/010-payments.sql
MIG-PAYMENTS | payments.routing_rule | tenant | 9 | scope_path |  | 0 | 1 |  | used by the first release | OrderService | backend/tenant/010-payments.sql
MIG-PAYMENTS | payments.stored_forward | tenant | 9 | scope_path |  | 2 | 0 |  | used by the first release | OrderService | backend/tenant/010-payments.sql
MIG-PAYMENTS | payments.token | tenant | 9 | subject |  | 4 | 1 | marketing.consent_purpose, pii.subject | used by the first release | OrderService | backend/tenant/010-payments.sql
MIG-QUEUE | queue.entry | tenant | 25 | through its owner |  | 4 | 2 | access.entitlement, pii.subject, queue.queue | used by the first release | VenueOpsService | backend/tenant/010-queue.sql
MIG-QUEUE | queue.queue | tenant | 40 | venue_id |  | 6 | 2 | access.access_point, catalogue.product, maintenance.asset, platform.scope, queue.queue | used by the first release | VenueOpsService | backend/tenant/010-queue.sql
MIG-QUEUE | queue.queue_operating_window | tenant | 4 | through its owner |  | 3 | 1 | queue.queue | used by the first release | VenueOpsService | backend/tenant/010-queue.sql
MIG-QUEUE | queue.reading | tenant | 8 | through its owner |  | 5 | 0 | queue.queue | used by the first release | VenueOpsService | backend/tenant/010-queue.sql
MIG-RETAIL | retail.merchandise | tenant | 16 | through its owner |  | 5 | 2 | catalogue.variant, inventory.inventory_item, platform.outlet | used by the first release | RetailService | backend/tenant/010-retail.sql
MIG-RETAIL | retail.reservation | tenant | 8 | through its owner |  | 1 | 1 | pii.subject, platform.outlet | used by the first release | RetailService | backend/tenant/010-retail.sql
MIG-RETAIL | retail.reservation_line | tenant | 5 | through its owner |  | 1 | 1 | retail.merchandise, retail.reservation | used by the first release | RetailService | backend/tenant/010-retail.sql
MIG-RETAIL | retail.return | tenant | 14 | tenant root (one tenant per database; no tenant_id by design) |  | 1 | 1 | identity.principal, orders.refund, retail.sale | used by the first release | RetailService | backend/tenant/010-retail.sql
MIG-RETAIL | retail.return_line | tenant | 9 | tenant root (one tenant per database; no tenant_id by design) |  | 1 | 1 | retail.merchandise, retail.return | used by the first release | RetailService | backend/tenant/010-retail.sql
MIG-RETAIL | retail.return_policy | tenant | 10 | through its owner |  | 2 | 1 | platform.outlet | used by the first release | RetailService | backend/tenant/010-retail.sql
MIG-RETAIL | retail.sale | tenant | 13 | subject |  | 5 | 2 | orders.pos_shift, orders.sales_order, pii.subject, platform.outlet | used by the first release | RetailService | backend/tenant/010-retail.sql
MIG-RETAIL | retail.sale_line | tenant | 13 | tenant root (one tenant per database; no tenant_id by design) |  | 4 | 1 | retail.merchandise, retail.sale | used by the first release | RetailService | backend/tenant/010-retail.sql
MIG-RETAIL | retail.shop_and_drop | tenant | 15 | venue_id |  | 3 | 2 | access.entitlement, fnb.delivery_location, identity.principal, pii.subject, platform.scope, retail.sale | used by the first release | RetailService | backend/tenant/010-retail.sql
MIG-RETAIL | retail.shop_and_drop_line | tenant | 7 | through its owner |  | 3 | 1 | retail.merchandise, retail.shop_and_drop | used by the first release | RetailService | backend/tenant/010-retail.sql
MIG-VENUEMAP | venuemap.import_job | tenant | 14 | tenant root (one tenant per database; no tenant_id by design) |  | 2 | 1 | venuemap.map | used by the first release | VenueOpsService | backend/tenant/010-venuemap.sql
MIG-VENUEMAP | venuemap.map | tenant | 19 | scope_path |  | 11 | 3 | assets.media_asset, platform.scope | used by the first release | VenueOpsService | backend/tenant/010-venuemap.sql
MIG-VENUEMAP | venuemap.map_version | tenant | 10 | tenant root (one tenant per database; no tenant_id by design) |  | 2 | 1 | assets.media_asset | used by the first release | VenueOpsService | backend/tenant/010-venuemap.sql
MIG-VENUEMAP | venuemap.path | tenant | 10 | through its owner |  | 6 | 1 | venuemap.map | used by the first release | VenueOpsService | backend/tenant/010-venuemap.sql
MIG-VENUEMAP | venuemap.placed_resource | tenant | 11 | through its owner |  | 6 | 1 | catalogue.variant, resources.resource | used by the first release | VenueOpsService | backend/tenant/010-venuemap.sql
MIG-VENUEMAP | venuemap.point | tenant | 21 | through its owner |  | 10 | 2 | access.access_point, catalogue.product, platform.outlet, venuemap.map | used by the first release | VenueOpsService | backend/tenant/010-venuemap.sql
MIG-VENUEMAP | venuemap.visit_plan | tenant | 14 | scope_path |  | 6 | 3 | marketing.guest_profile, orders.cart | used by the first release | VenueOpsService | backend/tenant/010-venuemap.sql
MIG-VENUEMAP | venuemap.visit_plan_item | tenant | 19 | through its owner |  | 6 | 2 | catalogue.performance, catalogue.product, promotions.bundle, venuemap.point, venuemap.visit_plan | used by the first release | VenueOpsService | backend/tenant/010-venuemap.sql

## Services
Service | Owner | Tier | Operations in release | All operations | Tables it owns in release | Points | If down
AccessService | Hrushikant Patkar | commerce | 35 | 258 | 19 | 68 | Down means the gates stop. Runs at the edge with a local decision cache.
AiService | Tanmay Dukhande | engagement | 65 | 144 | 49 | 121 | Down degrades suggestions and the concierge. Nothing that takes money depends on it.
CatalogueService | Hrushikant Patkar | commerce | 74 | 451 | 50 | 135 | A bad publish reaches every workstation. Versioned and rollback-able for that reason.
FnbService | Tanmay Dukhande | operations | 78 | 138 | 41 | 155 | Down means the kitchen falls back to paper. Offline-capable by design.
IdentityService | Pranay Shinde | foundation | 40 | 94 | 23 | 65 | A restart is an outage everywhere. Deploys go out first and alone.
InventoryService | Pranay Shinde | operations | 7 | 59 | 12 | 12 | Down blocks receiving and counting; selling continues from the till's cache.
LedgerService | Tanmay Dukhande | commerce | 15 | 72 | 18 | 27 | Correctness over availability. A ledger that is briefly unavailable is recoverable; one that is briefly wrong is not.
MarketingService | Pranay Shinde | engagement | 75 | 278 | 55 | 125 | Down stops campaigns and guest lookup. Neither stops trading.
OrderService | Pranay Shinde | commerce | 98 | 299 | 51 | 208 | Down means no sales. Highest availability target in the platform.
PlatformService | Pranay Shinde | platform | 22 | 228 | 24 | 36 | Down blocks provisioning and the developer API. Trading is unaffected.
ReportingService | Tanmay Dukhande | platform | 18 | 51 | 15 | 34 | Down stops dashboards. Nothing operational depends on it.
RetailService | Hrushikant Patkar | operations | 16 | 25 | 10 | 28 | Down means the shop stops; the gates and the restaurant do not.
TenancyService | Hrushikant Patkar | foundation | 32 | 212 | 28 | 64 | Same as identity — nothing runs without a scope.
VenueOpsService | Hrushikant Patkar | operations | 78 | 291 | 46 | 148 | Down degrades venue operations. Selling and admitting continue.
WalletService | Pranay Shinde | commerce | 14 | 70 | 22 | 33 | It holds a liability owed to a customer. A wallet that double-spends is a financial loss, not a bug report. Deduction order across credit lots is FEFO and is decided here, once, rather than per caller.
WhiteLabelService | Tanmay Dukhande | platform | 93 | 108 | 29 | 143 | Down freezes the current published config. Guests see the last good version.

## APIs
Service | Group | Operation | Method | Path | Request schema | Response schema | Permission | Part | Wave | Task | Reads | Writes | Summary
AccessService | access | approveManualOverrideSupervisor | PUT | /manual-override-supervisor | ManualOverrideSupervisorApprovalInput | ManualOverrideSupervisorApprovalView | ACCESS_OVERRIDE | setup | 1 | SVC-ACCESS-ACCESS-1 | access.access_point, access.scan_event, cache:idempotency, identity.principal | access.scan_event, cache:idempotency | Manual Override & Supervisor Approval
AccessService | access | bindCredentialDevice | POST | /my/credentials/{credentialId}/device-bindings | CredentialDeviceBindingInput | AccessDeviceBinding |  | core | 1 | SVC-ACCESS-ACCESS-1 | access.credential_policy, access.device_binding, access.entitlement, cache:idempotency | access.device_binding, cache:idempotency | Bind my credential to this device
AccessService | access | deleteAccessPointGroup | DELETE | /access-point-groups/{groupId} |  |  | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-1 | access.access_point_group, access.gate_mode_policy, cache:idempotency | access.access_point_group, access.configuration_change, cache:idempotency | Delete an access-point group
AccessService | access | enrolFacePass | POST | /face-pass/enrolments |  | FacePassEnrolment | GUEST_MANAGE | core | 1 | SVC-ACCESS-ACCESS-1 | access.biometric_profile, access.face_reenrolment_attempt, cache:idempotency, marketing.consent_record, pii.subject, pii.subject_biometric | access.biometric_audit_event, access.face_reenrolment_attempt, cache:idempotency, marketing.consent_record, pii.subject_biometric, platform.outbox | Register a facial profile against an entitlement
AccessService | access | enrolFaceTag | POST | /face-tag/enrolments |  | FacePassEnrolment | GUEST_MANAGE | core | 1 | SVC-ACCESS-ACCESS-2 | access.biometric_profile, cache:idempotency, pii.subject_biometric | cache:idempotency, pii.subject_biometric, platform.outbox | Capture a same-visit facial model, deleted when the ticket is fully redeemed
AccessService | access | getEntitlement | GET | /entitlements/{entitlementId} |  | Entitlement | ORDER_VIEW | core | 1 | SVC-ACCESS-ACCESS-2 | access.entitlement, catalogue.entitlement_template, identity.delegated_access |  | One entitlement, with what remains on it
AccessService | access | getEntitlementCredential | GET | /entitlements/{entitlementId}/credential |  | object | ORDER_VIEW | core | 1 | SVC-ACCESS-ACCESS-2 | access.entitlement | access.entitlement | The thing that gets scanned
AccessService | access | getEntitlementHistory | GET | /entitlements/{entitlementId}/history |  | array of object | ORDER_VIEW | core | 1 | SVC-ACCESS-ACCESS-2 | access.entitlement, access.scan_event |  | Every scan, freeze, share and reissue against it
AccessService | access | getFacePassEnrolment | GET | /face-pass/enrolments/{enrolmentId} |  | FacePassEnrolment | GUEST_VIEW | core | 1 | SVC-ACCESS-ACCESS-3 | pii.subject_biometric |  | Whether a pass has a face registered, and when
AccessService | access | listEntitlements | GET | /my/entitlements/all |  | object |  | core | 1 | SVC-ACCESS-ACCESS-3 | access.admission_rules, access.entitlement, catalogue.product |  | Every entitlement this guest holds, including expired
AccessService | access | listMyEntitlements | GET | /guests/me/entitlements |  | object | ORDER_VIEW | core | 1 | SVC-ACCESS-ACCESS-3 | access.entitlement, catalogue.entitlement_template, catalogue.product, identity.delegated_access |  | Every ticket, pass and membership this guest holds
AccessService | access | listParkingFacilities | GET | /parking-facilities |  | object | PARKING_CONFIGURE | core | 1 | SVC-ACCESS-ACCESS-3 | access.parking_facility |  | Car parks at a venue, and how each integrates
AccessService | access | revokeFacePass | DELETE | /face-pass/enrolments/{enrolmentId} |  |  | GUEST_MANAGE | core | 1 | SVC-ACCESS-ACCESS-4 | cache:idempotency, pii.subject_biometric | access.biometric_audit_event, cache:idempotency, pii.subject_biometric, platform.outbox | Remove a facial profile
AccessService | access | setAccessPointGroup | PUT | /access-point-groups | AccessAccessPointGroup | AccessAccessPointGroup | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-4 | access.access_point, access.access_point_group, cache:idempotency | access.access_point_group, access.configuration_change, cache:idempotency | Create or replace an access-point group
AccessService | access | setBiometricVerificationProfile | PUT | /biometric-verification-profile | BiometricVerificationProfileBuilderInput | BiometricVerificationProfileBuilderView | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-4 | access.access_point, access.biometric_profile, cache:idempotency | access.biometric_profile, access.configuration_change, cache:idempotency | Biometric Verification Profile Builder
AccessService | access | setBleBeaconGeofence | PUT | /ble-beacon-geofence | BleBeaconGeofenceConfigurationInput | BleBeaconGeofenceConfigurationView | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-4 | access.access_point, access.device_placement, cache:idempotency | access.access_point, access.configuration_change, access.device_placement, cache:idempotency | BLE Beacon & Geofence Configuration
AccessService | access | setCredentialActivationDisplay | PUT | /credential-activation-display | CredentialActivationDisplayRulesInput | CredentialActivationDisplayRulesView | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-5 | access.credential_policy, cache:idempotency | access.configuration_change, access.credential_policy, cache:idempotency | Save a credential activation and display rule
AccessService | access | setDeviceBindingPolicy | PUT | /device-binding-policy | DeviceBindingPolicyInput | AccessCredentialPolicy | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-5 | access.credential_policy, cache:idempotency | access.configuration_change, access.credential_policy, cache:idempotency | Set the device binding policy of a venue
AccessService | access | setFaceMatchingVerification | PUT | /face-matching-verification | FaceMatchingVerificationThresholdsInput | FaceMatchingVerificationThresholdsView | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-5 | access.biometric_profile, cache:idempotency | access.biometric_profile, access.configuration_change, cache:idempotency | Save face matching and verification thresholds
AccessService | access | setFacePassEnrollment | PUT | /face-pass-enrollment | FacePassEnrollmentConfigurationInput | FacePassEnrollmentConfigurationView | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-5 | access.biometric_profile, cache:idempotency | access.biometric_profile, access.configuration_change, cache:idempotency | Face Pass Enrollment Configuration
AccessService | access | setFaceTagTemporaryEnrollment | PUT | /face-tag-temporary | FaceTagTemporaryEnrollmentInput | FaceTagTemporaryEnrollmentView | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-6 | access.biometric_profile, cache:idempotency | access.biometric_profile, access.configuration_change, cache:idempotency | Save a Face Tag profile
AccessService | access | setGateModePolicy | PUT | /gate-mode-policies | AccessGateModePolicy | AccessGateModePolicy | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-6 | access.access_point_group, access.gate_mode_policy, cache:idempotency | access.configuration_change, access.gate_mode_policy, cache:idempotency | Set a policy for a non-standard gate mode
AccessService | access | setParkingFacility | PUT | /parking-facilities | ParkingFacility | ParkingFacility | PARKING_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-6 | access.parking_facility, cache:idempotency | access.configuration_change, access.parking_facility, cache:idempotency | Configure a car park and its integration
AccessService | access | setVirtualTicketIdentity | PUT | /virtual-ticket-identity | VirtualTicketIdentityMasterRecordConfigurationInput | VirtualTicketIdentityMasterRecordConfigurationView | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-6 | access.credential_policy, cache:idempotency | access.configuration_change, access.credential_policy, cache:idempotency | Virtual Ticket Identity & Master Record Configuration
AccessService | access | setVisualAccessRule | PUT | /visual-access-rule | VisualAccessRuleBuilderInput | VisualAccessRuleBuilderView | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESS-7 | access.admission_rules, access.entry_rule_point, cache:idempotency | access.admission_rules, access.configuration_change, access.entry_rule_point, cache:idempotency | Visual Access Rule Builder
AccessService | access | updateParkingEntitlement | PATCH | /parking-entitlements/{entitlementId} | UpdateParkingEntitlementRequest | ParkingEntitlement |  | core | 1 | SVC-ACCESS-ACCESS-7 | access.parking_entitlement, cache:idempotency | access.parking_entitlement, cache:idempotency | Change the plate, or revoke
AccessService | accessPoint | addBlacklistEntry | POST | /blacklist |  | BlacklistEntry | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESSPOINT-1 | access.blacklist, cache:idempotency | access.blacklist, cache:idempotency | Blacklist a media code
AccessService | accessPoint | createAccessPoint | POST | /access-points | CreateAccessPointRequest | AccessPoint | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESSPOINT-1 | access.access_point, cache:idempotency | access.access_point, access.configuration_change, cache:idempotency | Create an access point
AccessService | accessPoint | createAdmissionRules | POST | /admission-rules | AdmissionRules | AdmissionRules | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESSPOINT-1 | access.admission_rules, cache:idempotency | access.admission_rules, access.configuration_change, cache:idempotency | Create an admission profile
AccessService | accessPoint | setAccessPointDirection | PUT | /access-points/{accessPointId}/direction |  | AccessPoint | ACCESS_DIRECTION_SET | setup | 1 | SVC-ACCESS-ACCESSPOINT-1 | access.access_point, access.gate_mode_change | access.access_point | Switch a gate's direction live
AccessService | accessPoint | setAccessPointGeofence | PUT | /access-points/{accessPointId}/geofence | AccessPointGeofence | AccessPoint | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESSPOINT-2 | access.access_point, cache:idempotency | access.access_point, access.configuration_change, cache:idempotency | Set a geofence for handheld validation
AccessService | accessPoint | setTurnstileMode | PUT | /access-points/{accessPointId}/mode |  | AccessPoint | TURNSTILE_MODE_SET | setup | 1 | SVC-ACCESS-ACCESSPOINT-2 | access.access_point, access.access_point_group, access.gate_mode_change, access.gate_mode_policy, cache:idempotency | access.access_incident, access.access_point, access.gate_mode_change, cache:idempotency | Set the operating mode of an access point
AccessService | accessPoint | updateAccessPoint | PATCH | /access-points/{accessPointId} |  | AccessPoint | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESSPOINT-2 | access.access_point, cache:idempotency | access.access_point, access.configuration_change, cache:idempotency | Update an access point
AccessService | accessPoint | updateAdmissionRules | PUT | /admission-rules/{profileId} | AdmissionRules | AdmissionRules | ACCESS_POINT_CONFIGURE | setup | 1 | SVC-ACCESS-ACCESSPOINT-2 | access.admission_rules, cache:idempotency | access.admission_rules, access.configuration_change, cache:idempotency | Update an admission profile
AccessService | general | getParkingEntitlement | GET | /parking-entitlements/{entitlementId} |  | ParkingEntitlement |  | core | 1 | SVC-ACCESS-GENERAL-1 | access.parking_entitlement |  | One of the guest's parking entitlements
AiService | actions | overrideAiDecision | POST | /decision-records/{decisionRecordId}/override |  | AiIntervention | AI_APPROVE | core | 1 | SVC-AI-ACTIONS-1 | ai.decision_record, ai.intervention, cache:idempotency | ai.decision_record, ai.intervention, cache:idempotency | Override an AI decision
AiService | ai | getTranslationProposals | GET | /ai/translate/{translationJobId} |  | TranslationProposals | TENANT_CONFIGURE | core | 1 | SVC-AI-AI-1 | ai.proposed_action |  | Follow a translation job
AiService | ai | proposeTranslations | POST | /ai/translate |  | TranslationProposals | TENANT_CONFIGURE | core | 1 | SVC-AI-AI-1 | ai.policy, ai.provider, cache:idempotency, control.content_block, marketing.message_template, marketing.message_template_version | ai.activity, ai.proposed_action, cache:idempotency | Fill translation gaps with a first pass, for a human to edit
AiService | ai | proposeVenueLabels | POST | /ai/venue-map/{mapId}/propose-labels |  | array of VenueLabelProposal | VENUE_MAP_MANAGE | core | 1 | SVC-AI-AI-1 | ai.policy, ai.provider, cache:idempotency, qdrant:knowledge, venuemap.import_job, venuemap.point | ai.activity, ai.proposed_action, cache:idempotency | Suggest what each extracted shape is
AiService | ai | requestSuggestion | POST | /ai/suggestions |  | Suggestion | AI_USE | core | 1 | SVC-AI-AI-1 | ai.capability_maturity, ai.forecast_point, ai.forecast_version, ai.history_observation, ai.insight, ai.operational_requirement, ai.policy, ai.provider, ai.rec_decline, ai.release, ai.suggestion, ai.venue_settings, cache:idempotency, cache:rec-candidates, fnb.production_plan, inventory.movement, inventory.stock_batch, marketing.attribution_touch, marketing.segment, queue.queue, queue.reading, venuemap.point, venuemap.visit_plan, venuemap.visit_plan_item | ai.activity, ai.suggestion, cache:idempotency | Ask for an answer, however it is currently produced
AiService | ai | setSuggestionProvider | PUT | /ai/suggestion-providers |  | object | AI_CONFIGURE | setup | 1 | SVC-AI-AI-2 | ai.policy, ai.provider, ai.release, cache:idempotency | ai.policy, cache:idempotency, cache:resolution | Point a question at a rule, a model, or both
AiService | ai | testAiProvider | POST | /ai-providers/{providerId}/test |  | object | AI_CONFIGURE | core | 1 | SVC-AI-AI-2 | ai.provider, cache:idempotency | ai.activity, ai.provider, cache:idempotency | Check the key works before anyone relies on it
AiService | assist | createAiConversation | POST | /conversations |  | AiConversation | AI_USE | core | 1 | SVC-AI-ASSIST-1 | ai.conversation, cache:idempotency | ai.conversation, cache:idempotency | Open a conversation
AiService | assist | listAiConversations | GET | /conversations |  | object | AI_USE | core | 1 | SVC-AI-ASSIST-1 | ai.conversation |  | A principal's conversation history
AiService | assist | sendAiMessage | POST | /conversations/{conversationId}/messages |  | AiMessage | AI_USE | core | 1 | SVC-AI-ASSIST-1 | ai.assistant_profile, ai.capability, ai.chunk_embedding, ai.conversation, ai.knowledge_document, ai.message, ai.policy, ai.proposed_action, ai.provider, cache:answer, cache:idempotency, qdrant:knowledge | ai.activity, ai.decision_record, ai.knowledge_gap, ai.message, ai.proposed_action, cache:answer, cache:idempotency, qdrant:knowledge | Ask
AiService | config | getAiByokEnablement | GET | /tenants/{tenantId}/byok |  | AiByokEnablement | AI_CONFIGURE | core | 1 | SVC-AI-CONFIG-1 | ai.byok_enablement |  | Whether a tenant may bring its own key
AiService | config | getAiPolicy | GET | /policy |  | AiPolicy | AI_CONFIGURE | core | 1 | SVC-AI-CONFIG-1 | ai.policy |  | What the assistant may do here
AiService | config | listAiProviders | GET | /providers |  | array of AiProvider | AI_CONFIGURE | core | 1 | SVC-AI-CONFIG-1 | ai.provider |  | Configured providers and their order
AiService | config | setAiByokEnablement | PUT | /tenants/{tenantId}/byok | AiByokEnablement | AiByokEnablement | PLATFORM_AI_MANAGE | setup | 1 | SVC-AI-CONFIG-1 | ai.byok_enablement, cache:idempotency | ai.byok_enablement, cache:idempotency | Enable or disable bring-your-own-key for a tenant (platform)
AiService | config | setAiPolicy | PUT | /policy | AiPolicy | AiPolicy | AI_CONFIGURE | setup | 1 | SVC-AI-CONFIG-2 | ai.policy, cache:idempotency | ai.policy, cache:idempotency | Set the policy
AiService | configure | getGuidedChoiceSuggestion | GET | /guided-choice-suggestions/{suggestionId} |  | AiGuidedChoiceSuggestion | AI_USE | core | 1 | SVC-AI-CONFIGURE-1 | ai.guided_choice_suggestion |  | The reasons behind a Help me choose suggestion
AiService | configure | suggestGuidedChoice | POST | /venues/{venueId}/guided-choice-suggestions |  | AiGuidedChoiceSuggestion | AI_USE | core | 1 | SVC-AI-CONFIGURE-1 | ai.guided_choice_suggestion, ai.policy, ai.prompt_template, cache:idempotency | ai.activity, ai.decision_record, ai.guided_choice_suggestion, cache:idempotency | Suggest a Help me choose set-up from the venue's catalogue
AiService | forecast | createForecastScenario | POST | /forecast-scenarios | AiForecastScenario | AiForecastScenario | AI_USE | setup | 1 | SVC-AI-FORECAST-1 | ai.forecast_point, ai.forecast_scenario, ai.forecast_version, cache:idempotency | ai.forecast_point, ai.forecast_scenario, cache:idempotency | Run a what-if
AiService | forecast | decideOperationalRequirement | POST | /operational-requirements/{requirementId}/decide |  | AiOperationalRequirement | AI_USE | setup | 1 | SVC-AI-FORECAST-1 | ai.operational_requirement, cache:idempotency | ai.decision_record, ai.operational_requirement, cache:idempotency | Accept, modify or reject a requirement
AiService | forecast | getAiVenueSettings | GET | /venues/{venueId}/ai-settings |  | AiVenueSettings | AI_USE | core | 1 | SVC-AI-FORECAST-1 | ai.venue_settings |  | The venue AI profile the baselines stand on
AiService | forecast | getForecast | GET | /forecasts |  | object | AI_USE | core | 1 | SVC-AI-FORECAST-1 | ai.forecast_definition, ai.forecast_point, ai.forecast_version |  | Forecast values
AiService | forecast | getForecastAccuracy | GET | /forecast-accuracy |  | object | AI_USE | core | 1 | SVC-AI-FORECAST-2 | ai.forecast_accuracy |  | Measured forecast accuracy
AiService | forecast | getVenueHistoryImport | GET | /history-imports/{importId} |  | AiHistoryImport | AI_USE | core | 1 | SVC-AI-FORECAST-2 | ai.history_import |  | One history import, with its findings
AiService | forecast | importVenueHistory | POST | /venues/{venueId}/history-imports |  | AiHistoryImport | AI_CONFIGURE | core | 1 | SVC-AI-FORECAST-2 | ai.history_import, assets.media_asset, cache:idempotency | ai.history_import, ai.history_observation, cache:idempotency | Import the venue's own historical exports for the AI baselines
AiService | forecast | listForecastVersions | GET | /forecast-versions |  | object | AI_USE | core | 1 | SVC-AI-FORECAST-2 | ai.forecast_version |  | Forecast versions
AiService | forecast | listOperationalRequirements | GET | /operational-requirements |  | object | AI_USE | core | 1 | SVC-AI-FORECAST-3 | ai.forecast_version, ai.operational_requirement |  | Requirements derived from the forecast
AiService | forecast | listVenueHistoryImports | GET | /venues/{venueId}/history-imports |  | object | AI_USE | core | 1 | SVC-AI-FORECAST-3 | ai.history_import |  | The venue's history imports
AiService | forecast | publishForecastVersion | POST | /forecast-versions/{versionId}/publish |  | AiForecastVersion | AI_USE | setup | 1 | SVC-AI-FORECAST-3 | ai.forecast_definition, ai.forecast_version, cache:idempotency | ai.decision_record, ai.forecast_version, ai.operational_requirement, cache:idempotency | Publish a forecast version
AiService | forecast | runForecast | POST | /forecast-definitions/{definitionKey}/runs |  | AiForecastVersion | AI_CONFIGURE | setup | 1 | SVC-AI-FORECAST-3 | ai.forecast_definition, ai.forecast_version, ai.history_observation, ai.venue_settings, cache:idempotency | ai.forecast_point, ai.forecast_version, cache:idempotency | Run a forecast now
AiService | forecast | setAiVenueSettings | PUT | /venues/{venueId}/ai-settings | AiVenueSettings | AiVenueSettings | AI_CONFIGURE | core | 1 | SVC-AI-FORECAST-4 | ai.venue_settings, cache:idempotency | ai.venue_settings, cache:idempotency | Set the venue AI profile
AiService | forecast | setForecastDefinition | PUT | /forecast-definitions/{definitionKey} | AiForecastDefinition | AiForecastDefinition | AI_CONFIGURE | setup | 1 | SVC-AI-FORECAST-4 | ai.forecast_definition, cache:idempotency | ai.forecast_definition, cache:idempotency | Define a forecast
AiService | generate | proposeMarketingContent | POST | /ai/content-drafts |  | AiContentDraftSet | AI_USE | core | 1 | SVC-AI-GENERATE-1 | ai.capability, ai.governance_policy_version, ai.policy, ai.prompt_template, ai.provider, cache:idempotency, catalogue.event, catalogue.product, control.content_block, marketing.campaign, marketing.message_template, promotions.promotion, whitelabel.banner, whitelabel.content_page, whitelabel.homepage_section, whitelabel.promo_block | ai.activity, ai.decision_record, ai.proposed_action, cache:idempotency | Draft marketing content for a person to edit and apply
AiService | governance | createAiGovernancePolicyDraft | POST | /governance/policy-drafts |  | AiGovernancePolicyVersion | AI_CONFIGURE | setup | 1 | SVC-AI-GOVERNANCE-1 | ai.governance_policy, ai.governance_policy_version, cache:idempotency | ai.governance_policy, ai.governance_policy_version, cache:idempotency | Draft a governance policy, or a new version of one
AiService | governance | decideProposedAction | POST | /proposed-actions/{actionId}/decide |  | ProposedAction | AI_USE | core | 1 | SVC-AI-GOVERNANCE-1 | ai.action_plan, ai.proposed_action, cache:idempotency | ai.action_plan, ai.activity, ai.decision_record, ai.proposed_action, cache:idempotency | Approve or reject a proposal
AiService | governance | evaluateAiGovernance | POST | /governance/evaluate |  | AiGovernanceDecision |  | core | 1 | SVC-AI-GOVERNANCE-1 | ai.capability, ai.governance_policy_version, ai.policy, ai.policy_exception, cache:governance-policy, cache:idempotency | ai.decision_record, cache:idempotency | Ask the governance decision point (service callers)
AiService | governance | getAiUsage | GET | /usage |  | AiUsageReport | AI_AUDIT_VIEW | core | 1 | SVC-AI-GOVERNANCE-1 | ai.activity, ai.model |  | Usage, cost and performance
AiService | governance | getEffectiveAiPolicy | GET | /governance/effective-policy |  | AiEffectivePolicy | AI_USE | core | 1 | SVC-AI-GOVERNANCE-2 | ai.capability, ai.governance_policy, ai.governance_policy_version, ai.policy, ai.policy_exception |  | The policy in force for a capability at a scope
AiService | governance | listAiCapabilities | GET | /governance/capabilities |  | object | AI_USE | core | 1 | SVC-AI-GOVERNANCE-2 | ai.capability |  | The capability registry
AiService | governance | listAiGovernancePolicyVersions | GET | /governance/policy-versions |  | object | AI_USE | core | 1 | SVC-AI-GOVERNANCE-2 | ai.governance_policy, ai.governance_policy_version |  | Governance policies and their versions
AiService | governance | pauseAiCapability | POST | /governance/capabilities/{capabilityKey}/pause |  | AiCapabilityRegistration | AI_CONFIGURE | core | 1 | SVC-AI-GOVERNANCE-2 | ai.capability, cache:idempotency | ai.action_plan, ai.capability, ai.decision_record, ai.intervention, cache:idempotency | Stop a capability now
AiService | governance | publishAiGovernancePolicy | POST | /governance/policy-versions/{versionId}/publish |  | AiGovernancePolicyVersion | AI_APPROVE | setup | 1 | SVC-AI-GOVERNANCE-3 | ai.governance_policy_version, cache:idempotency | ai.decision_record, ai.governance_policy, ai.governance_policy_version, cache:governance-policy, cache:idempotency | Publish a simulated policy version
AiService | governance | revokeAiPolicyException | POST | /governance/policy-exceptions/{exceptionId}/revoke |  | AiPolicyException | AI_APPROVE | core | 1 | SVC-AI-GOVERNANCE-3 | ai.policy_exception, cache:idempotency | ai.decision_record, ai.policy_exception, cache:idempotency | End an exception before it expires
AiService | governance | simulateAiGovernancePolicy | POST | /governance/policy-versions/{versionId}/simulate |  | AiPolicySimulation | AI_CONFIGURE | setup | 1 | SVC-AI-GOVERNANCE-3 | ai.decision_record, ai.governance_policy_version, cache:idempotency | ai.governance_policy_version, cache:idempotency | Test a draft policy before it is published
AiService | insights | decideAiInsight | POST | /insights/{insightId}/decide |  | AiInsight | AI_USE | setup | 1 | SVC-AI-INSIGHTS-1 | ai.insight, cache:idempotency | ai.anomaly_detector, ai.insight, cache:idempotency | Review, accept, reject or mark an insight actioned
AiService | insights | explainMetricChange | POST | /insights/explain-metric-change |  | AiMetricChangeExplanation | AI_USE | setup | 1 | SVC-AI-INSIGHTS-1 | ai.insight, ai.policy, cache:idempotency | ai.activity, ai.insight, cache:idempotency | Why did this metric change
AiService | knowledge | configureAssistantProfile | PUT | /assistant-profiles/{profileKey} | AiAssistantProfile | AiAssistantProfile | AI_CONFIGURE | setup | 1 | SVC-AI-KNOWLEDGE-1 | ai.assistant_profile, ai.policy, cache:idempotency | ai.assistant_profile, cache:idempotency | Define an assistant profile
AiService | knowledge | recordAnswerFeedback | POST | /messages/{messageId}/feedback |  | AiAnswerFeedback | AI_USE | core | 1 | SVC-AI-KNOWLEDGE-1 | ai.answer_feedback, ai.message, cache:idempotency | ai.answer_feedback, ai.knowledge_gap, cache:idempotency | Say whether an answer helped
AiService | models | listAiEvaluations | GET | /evaluations |  | object | AI_USE | core | 1 | SVC-AI-MODELS-1 | ai.eval_run, ai.eval_suite |  | Evaluation runs
AiService | models | listAiTrainingRuns | GET | /training-runs |  | object | AI_USE | core | 1 | SVC-AI-MODELS-1 | ai.eval_run, ai.release, ai.training_run |  | The per-tenant training and backtest runs
AiService | models | promoteAiRelease | POST | /releases/{releaseId}/promote |  | AiRelease | AI_USE | setup | 1 | SVC-AI-MODELS-1 | ai.eval_run, ai.governance_alert, ai.release, cache:idempotency | ai.decision_record, ai.forecast_definition, ai.governance_alert, ai.policy, ai.release, cache:idempotency | Promote a release to its next stage (a person)
AiService | models | publishPromptTemplate | POST | /prompt-templates/{templateKey}/versions |  | AiPromptTemplate | AI_APPROVE | setup | 1 | SVC-AI-MODELS-1 | ai.prompt_template, cache:idempotency | ai.prompt_template, ai.release, cache:idempotency | Publish a prompt template version
AiService | models | rollbackAiRelease | POST | /releases/{releaseId}/rollback |  | AiRelease | AI_APPROVE | setup | 1 | SVC-AI-MODELS-2 | ai.release, cache:idempotency | ai.decision_record, ai.forecast_definition, ai.policy, ai.release, cache:idempotency | Roll a release back
AiService | models | runAiEvaluation | POST | /evaluations |  | AiEvaluationRun | AI_CONFIGURE | setup | 1 | SVC-AI-MODELS-2 | ai.eval_run, ai.eval_suite, ai.release, cache:idempotency | ai.eval_run, ai.release, cache:idempotency | Evaluate a candidate
AiService | models | setAiModel | PUT | /models/{modelId} | AiModel | AiModel | PLATFORM_AI_MANAGE | setup | 1 | SVC-AI-MODELS-2 | ai.model, cache:idempotency | ai.model, cache:idempotency | Add or change a platform model (platform)
AiService | monitoring | containAiIncident | POST | /incidents/{incidentId}/contain |  | AiIncident | AI_APPROVE | setup | 1 | SVC-AI-MONITORING-1 | ai.incident, cache:idempotency | ai.capability, ai.decision_record, ai.incident, ai.intervention, ai.policy_exception, ai.release, cache:idempotency | Contain an incident
AiService | monitoring | listAiGovernanceAlerts | GET | /governance-alerts |  | object | AI_USE | core | 1 | SVC-AI-MONITORING-1 | ai.governance_alert |  | Governance alerts
AiService | monitoring | listAiIncidents | GET | /incidents |  | object | AI_USE | core | 1 | SVC-AI-MONITORING-1 | ai.incident |  | AI incidents
AiService | monitoring | openAiIncident | POST | /incidents |  | AiIncident | AI_CONFIGURE | core | 1 | SVC-AI-MONITORING-1 | ai.governance_alert, ai.incident, cache:idempotency | ai.governance_alert, ai.incident, cache:idempotency | Open an AI incident
AiService | recommend | decideRecommendations | POST | /recommendations/decide |  | AiRecommendationResult | AI_USE | core | 1 | SVC-AI-RECOMMEND-1 | ai.rec_decline, ai.release, cache:idempotency, cache:rec-candidates, cache:rec-features | ai.decision_record, ai.rec_decision, cache:idempotency | Fill a recommendation slot
AiService | recommend | recordRecommendationEvents | POST | /recommendations/events |  |  | AI_USE | core | 1 | SVC-AI-RECOMMEND-1 | ai.rec_decision, cache:idempotency | ai.rec_decline, ai.rec_event, cache:idempotency | Report what happened to recommended items
AiService | retrieval | createKnowledgeCollection | POST | /collections | KnowledgeCollection | KnowledgeCollection | AI_CONFIGURE | setup | 1 | SVC-AI-RETRIEVAL-1 | ai.chunk_embedding, ai.knowledge_collection, cache:idempotency, qdrant:knowledge | ai.knowledge_collection, cache:idempotency, qdrant:knowledge | Create a collection
AiService | retrieval | ingestKnowledgeDocument | POST | /collections/{collectionId}/documents | KnowledgeDocument | KnowledgeDocument | AI_CONFIGURE | setup | 1 | SVC-AI-RETRIEVAL-1 | ai.chunk_embedding, ai.knowledge_collection, ai.knowledge_document, cache:embedding, cache:idempotency, qdrant:knowledge | ai.chunk_embedding, ai.knowledge_document, cache:embedding, cache:idempotency, qdrant:knowledge | Add a document
AiService | retrieval | reindexSource | POST | /index-sources/{sourceId}/reindex |  | IndexJob | AI_CONFIGURE | setup | 1 | SVC-AI-RETRIEVAL-1 | ai.index_job, ai.index_source, assets.media_asset, cache:embedding, cache:idempotency, catalogue.entitlement_template, catalogue.product, fnb.menu_item, maintenance.inspection_template, marketing.case, reporting.report_definition, retail.merchandise, whitelabel.content_page, whitelabel.faq_entry, whitelabel.policy | ai.chunk_embedding, ai.index_entry, ai.index_job, cache:embedding, cache:idempotency, qdrant:knowledge | Rebuild a source
AiService | retrieval | semanticSearch | POST | /search |  | array of SearchResult | AI_USE | core | 1 | SVC-AI-RETRIEVAL-1 | ai.chunk_embedding, ai.knowledge_collection, ai.knowledge_document, assets.media_asset, cache:answer, cache:idempotency, catalogue.product, qdrant:knowledge | ai.activity, cache:answer, cache:idempotency, qdrant:knowledge | Search meaning, not words
AiService | retrieval | setIndexSource | PUT | /index-sources | IndexSource | IndexSource | AI_CONFIGURE | setup | 1 | SVC-AI-RETRIEVAL-2 | ai.index_source, ai.knowledge_collection, cache:idempotency | ai.index_source, cache:idempotency | Declare a source indexed
CatalogueService | availability | getSeatAvailability | GET | /performances/{performanceId}/seat-availability |  | SeatAvailability | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-AVAILABILITY-1 | seating.seat, seating.seat_category, seating.seat_reservation |  | Seat status for a performance
CatalogueService | bundle | createBundle | POST | /bundles | CreateBundleRequest | Bundle | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-BUNDLE-1 | cache:idempotency, fnb.menu_item, promotions.allocation_component, promotions.bundle, promotions.bundle_choice_group, promotions.bundle_choice_option, promotions.bundle_component | cache:idempotency, promotions.allocation_component, promotions.bundle, promotions.bundle_choice_group, promotions.bundle_choice_option, promotions.bundle_component, promotions.promotion_audit | Create a bundle
CatalogueService | bundle | getBundle | GET | /bundles/{bundleId} |  | Bundle | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-BUNDLE-1 | promotions.allocation_component, promotions.bundle, promotions.bundle_choice_group, promotions.bundle_choice_option, promotions.bundle_component |  | Read a bundle with components and allocation
CatalogueService | bundle | getLatestBundle | GET | /catalogue/bundles/latest |  | CatalogueBundle | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-BUNDLE-1 | catalogue.published_bundle |  | Pull the current bundle for this workstation's venue
CatalogueService | bundle | listCatalogueBundles | GET | /catalogue/bundles |  | array of BundleSummary | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-BUNDLE-1 | catalogue.product, catalogue.published_bundle |  | List published catalogue bundles
CatalogueService | bundle | publishBundle | POST | /catalogue/bundles |  | BundleSummary | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-BUNDLE-2 | cache:idempotency, catalogue.price, catalogue.price_list, catalogue.product, catalogue.published_bundle, catalogue.variant, platform.sale_board, platform.sale_board_tile | cache:idempotency, catalogue.published_bundle | Compute, sign and publish a catalogue bundle
CatalogueService | bundle | updateBundle | PATCH | /bundles/{bundleId} |  | Bundle | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-BUNDLE-2 | cache:idempotency, promotions.allocation_component, promotions.bundle, promotions.bundle_choice_group, promotions.bundle_choice_option, promotions.bundle_component | cache:idempotency, promotions.allocation_component, promotions.bundle, promotions.bundle_component, promotions.promotion_audit | Amend a bundle
CatalogueService | capacity | getAvailability | GET | /availability |  | PerformanceAvailabilityPage | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-CAPACITY-1 | catalogue.channel_capacity, catalogue.inventory_reservation, catalogue.performance |  | Live remaining capacity
CatalogueService | catalogue | bulkChangePrices | POST | /products/bulk-price |  | BulkPriceResult | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-CATALOGUE-1 | cache:idempotency, catalogue.price_list, catalogue.product | cache:idempotency, catalogue.price_list, catalogue.product_version | Reprice a category or a whole catalogue
CatalogueService | catalogue | cloneProduct | POST | /products/{productId}/clone |  | Product | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-CATALOGUE-1 | catalogue.product, catalogue.product_media, catalogue.variant | cache:idempotency, catalogue.product, catalogue.product_media, catalogue.variant | Copy a product as a new draft
CatalogueService | catalogue | commitCatalogueImport | POST | /products/import/{jobId}/commit |  | CatalogueImportJob | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-CATALOGUE-1 | cache:idempotency, catalogue.import_job | cache:idempotency, catalogue.import_job, catalogue.product, catalogue.variant | Apply a parsed catalogue import
CatalogueService | catalogue | getMyMemberships | GET | /guests/me/memberships |  | array of GuestMembership | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-CATALOGUE-1 | access.entitlement, catalogue.product, marketing.loyalty_position |  | A guest's own memberships, benefits and history
CatalogueService | catalogue | joinWaitlist | POST | /waitlist-entries | WaitlistEntry | WaitlistEntry |  | core | 1 |  | cache:idempotency, catalogue.channel_capacity, catalogue.performance, catalogue.waitlist_entry | cache:idempotency, catalogue.waitlist_entry | Ask to be told if capacity frees up
CatalogueService | catalogue | leaveWaitlist | DELETE | /waitlist-entries/{entryId} |  |  |  | core | 1 |  | cache:idempotency, catalogue.waitlist_entry | cache:idempotency, catalogue.waitlist_entry | Stop waiting
CatalogueService | catalogue | listProductCategories | GET | /product-categories |  | array of ProductCategoryNode | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-CATALOGUE-2 | catalogue.product, catalogue.product_category |  | The merchandise hierarchy — categories, brands, collections
CatalogueService | catalogue | searchCatalogue | GET | /search |  | array of object |  | core | 1 | SVC-CATALOGUE-CATALOGUE-2 | catalogue.event, catalogue.product, catalogue.product_eligibility_rule, catalogue.product_media, catalogue.variant, whitelabel.guided_choice_answer |  | Find something by name
CatalogueService | catalogue | setProductCategories | PUT | /product-categories |  | array of ProductCategory | PRODUCT_CONFIGURE | core | 1 | SVC-CATALOGUE-CATALOGUE-2 | cache:idempotency, catalogue.product, catalogue.product_category, whitelabel.booking_flow | cache:idempotency, catalogue.product_category | Define the hierarchy, in the order a guest sees it
CatalogueService | category | createSeatCategory | POST | /seat-categories |  | SeatCategory | CAPACITY_CONFIGURE | setup | 1 | SVC-CATALOGUE-CATEGORY-1 | cache:idempotency, seating.seat_category, seating.seat_price_band | cache:idempotency, seating.seat_category, seating.seat_price_band | Create a seat category
CatalogueService | category | updateSeatCategory | PATCH | /seat-categories/{seatCategoryId} |  | SeatCategory | CAPACITY_CONFIGURE | setup | 1 | SVC-CATALOGUE-CATEGORY-1 | seating.seat_category, seating.seat_price_band | seating.seat_price_band | Rename, re-rank or re-price a seat category
CatalogueService | coupon | createCouponCampaign | POST | /coupon-campaigns | CreateCouponCampaignRequest | CouponCampaign | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-COUPON-1 | cache:idempotency, promotions.coupon_campaign | cache:idempotency, promotions.coupon_campaign, promotions.promotion_audit | Create a coupon campaign
CatalogueService | coupon | generateCouponCodes | POST | /coupon-campaigns/{campaignId}/codes |  | object | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-COUPON-1 | cache:idempotency, promotions.coupon_campaign | cache:idempotency, promotions.coupon_code, promotions.coupon_code_batch, promotions.promotion_audit | Generate codes in bulk
CatalogueService | coupon | getCouponCode | GET | /coupon-codes/{code} |  | CouponCode | PRICE_VIEW | core | 1 | SVC-CATALOGUE-COUPON-1 | promotions.coupon_code |  | Look up a code
CatalogueService | drafted | setCodeDistributionManager | PUT | /code-distribution-manager | CodeDistributionAssignmentManagerInput | CodeDistributionAssignmentManagerView | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-DRAFTED-1 | cache:idempotency, promotions.code_assignment, promotions.coupon_code, promotions.coupon_code_batch | cache:idempotency, promotions.code_assignment, promotions.coupon_code, promotions.promotion_audit | Code Distribution & Assignment Manager
CatalogueService | entitlement | createEntitlementTemplate | POST | /entitlement-templates | EntitlementTemplate | EntitlementTemplate | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-ENTITLEMENT-1 | cache:idempotency, catalogue.entitlement_template | cache:idempotency, catalogue.entitlement_template | Create an entitlement template
CatalogueService | entitlement | setEntitlementTemplateBlackoutDates | PUT | /entitlement-templates/{templateId}/blackout-dates |  | EntitlementTemplate | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-ENTITLEMENT-1 | catalogue.entitlement_template | catalogue.entitlement_template | Set the dates a product's entitlement does not admit
CatalogueService | evaluation | evaluatePromotions | POST | /promotions/evaluate | EvaluatePromotionsRequest | PromotionEvaluation | PRICE_VIEW | core | 1 | SVC-CATALOGUE-EVALUATION-1 | cache:idempotency, catalogue.price_list, promotions.coupon_code, promotions.promotion, promotions.promotion_rule | cache:idempotency, promotions.promotion_evaluation_trace | Evaluate promotions against a cart
CatalogueService | event | createEvent | POST | /events | CreateEventRequest | Event | EVENT_CONFIGURE | setup | 1 | SVC-CATALOGUE-EVENT-1 | cache:idempotency, catalogue.event | cache:idempotency, catalogue.event | Create an event
CatalogueService | event | createPerformances | POST | /events/{eventId}/performances | CreatePerformancesRequest | object | PERFORMANCE_CONFIGURE | setup | 1 | SVC-CATALOGUE-EVENT-1 | cache:idempotency, catalogue.performance | cache:idempotency, catalogue.performance | Create performances, singly or by schedule
CatalogueService | event | enterWaitingRoom | POST | /performances/{performanceId}/waiting-room/entries |  | WaitingRoomEntry |  | core | 1 | SVC-CATALOGUE-EVENT-1 |  |  | Join the on-sale waiting room for a performance
CatalogueService | event | getPerformance | GET | /performances/{performanceId} |  | Performance | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-EVENT-1 | catalogue.performance |  | Read a performance
CatalogueService | event | getWaitingRoomPosition | GET | /performances/{performanceId}/waiting-room/entries/{waitingEntryId} |  | WaitingRoomEntry |  | core | 1 | SVC-CATALOGUE-EVENT-2 |  |  | Where a waiting guest is, and the admission token once admitted
CatalogueService | event | listEvents | GET | /events |  | object | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-EVENT-2 | catalogue.event |  | List events
CatalogueService | event | listPerformances | GET | /events/{eventId}/performances |  | object | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-EVENT-2 | catalogue.performance, catalogue.product, catalogue.product_category |  | List performances of an event
CatalogueService | event | updateEvent | PATCH | /events/{eventId} |  | Event | EVENT_CONFIGURE | setup | 1 | SVC-CATALOGUE-EVENT-2 | cache:idempotency, catalogue.event | cache:idempotency, catalogue.event | Amend an event
CatalogueService | event | updatePerformance | PATCH | /performances/{performanceId} |  | Performance | PERFORMANCE_CONFIGURE | setup | 1 | SVC-CATALOGUE-EVENT-3 | cache:idempotency, catalogue.performance | cache:idempotency, catalogue.performance | Amend a performance
CatalogueService | events | cloneEvent | POST | /events/{eventId}/clone | CloneEventRequest | object | EVENT_CONFIGURE | setup | 1 | SVC-CATALOGUE-EVENTS-1 | cache:idempotency, catalogue.event, catalogue.event_capacity_profile, catalogue.event_registration, catalogue.event_resource_plan, catalogue.event_schedule, catalogue.performance | cache:idempotency, catalogue.event, catalogue.event_capacity_profile, catalogue.event_registration, catalogue.event_resource_plan, catalogue.event_schedule, catalogue.performance | Copy an event, choosing what comes with it
CatalogueService | events | setEventLifecycleState | POST | /events/{eventId}/lifecycle |  |  | EVENT_CONFIGURE | setup | 1 | SVC-CATALOGUE-EVENTS-1 | cache:idempotency, catalogue.channel_capacity, catalogue.event, catalogue.event_capacity_profile, catalogue.event_resource_plan, catalogue.event_schedule, catalogue.performance, catalogue.price_list | cache:idempotency, catalogue.event, catalogue.performance, platform.outbox | Draft, planned, on sale, live, closed, cancelled
CatalogueService | hold | createSeatHold | POST | /seat-holds | CreateSeatHoldRequest | SeatHold | ORDER_CREATE | core | 1 | SVC-CATALOGUE-HOLD-1 | cache:idempotency, seating.seat_reservation | cache:idempotency, platform.outbox, seating.seat_reservation | Hold specific seats
CatalogueService | hold | extendSeatHold | POST | /seat-holds/{holdId}/extend |  | SeatHold | ORDER_CREATE | core | 1 | SVC-CATALOGUE-HOLD-1 | cache:idempotency, seating.seat_reservation | cache:idempotency, seating.seat_reservation | Extend a hold
CatalogueService | hold | getSeatHold | GET | /seat-holds/{holdId} |  | SeatHold | ORDER_VIEW | core | 1 | SVC-CATALOGUE-HOLD-1 | seating.seat_reservation |  | Read a hold
CatalogueService | hold | relinquishSeatHold | DELETE | /seat-holds/{holdId} |  |  | ORDER_CREATE | core | 1 | SVC-CATALOGUE-HOLD-1 | seating.seat_reservation | platform.outbox, seating.seat_reservation | Release a hold
CatalogueService | lease | acquireInventoryHold | POST | /inventory-holds | AcquireLeaseRequest | InventoryHold | ORDER_CREATE | core | 1 | SVC-CATALOGUE-LEASE-1 | cache:idempotency, catalogue.channel_envelope, catalogue.channel_capacity, catalogue.inventory_reservation, platform.workstation | cache:idempotency, catalogue.channel_envelope, catalogue.channel_capacity, catalogue.inventory_reservation | Acquire an inventory hold
CatalogueService | lease | convertInventoryHold | POST | /inventory-holds/{inventoryHoldId}/convert |  | InventoryHold |  | setup | 1 | SVC-CATALOGUE-LEASE-1 | cache:idempotency, catalogue.channel_envelope, catalogue.channel_capacity, catalogue.inventory_reservation | cache:idempotency, catalogue.channel_envelope, catalogue.channel_capacity, catalogue.inventory_reservation, platform.outbox, seating.seat_reservation, seating.seat_reservation_item | Turn a paid hold into sold units
CatalogueService | lease | listInventoryHolds | GET | /inventory-holds |  | object | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-LEASE-1 | catalogue.inventory_reservation |  | List inventory holds
CatalogueService | pricing | copyPriceList | POST | /price-lists/{priceListId}/copy |  | object | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-PRICING-1 | cache:idempotency, catalogue.price_list | cache:idempotency, catalogue.price_list | Copy a price list, optionally with an adjustment
CatalogueService | pricing | createPriceList | POST | /price-lists | CreatePriceListRequest | PriceList | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-PRICING-1 | cache:idempotency, catalogue.price_list | cache:idempotency, catalogue.price_list | Create a price list
CatalogueService | pricing | setPrices | PUT | /price-lists/{priceListId}/prices |  | object | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-PRICING-1 | cache:idempotency, catalogue.price_list | cache:idempotency, cache:resolution, catalogue.price_list | Set prices in bulk
CatalogueService | pricing | updatePriceList | PATCH | /price-lists/{priceListId} |  | PriceList | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-PRICING-1 | cache:idempotency, catalogue.price_list | cache:idempotency, catalogue.price_list | Amend a price list
CatalogueService | product | checkBookingEligibility | POST | /eligibility-checks | EligibilityCheckRequest | EligibilityCheckResult | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-PRODUCT-1 | catalogue.product, catalogue.product_eligibility_rule |  | Can this party take part
CatalogueService | product | getGroupPackageDefinition | GET | /products/{productId}/group-package |  | GroupPackageDefinition | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-PRODUCT-1 | catalogue.group_package |  | A school-trip format or party package
CatalogueService | product | getProduct | GET | /products/{productId} |  | Product | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-PRODUCT-1 | catalogue.product, catalogue.product_media |  | Read a product
CatalogueService | product | getProductEligibilityRule | GET | /products/{productId}/eligibility-rule |  | ProductEligibilityRule | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-PRODUCT-1 | catalogue.product_eligibility_rule |  | Who may take part: age, height, supervision
CatalogueService | product | listAlternativeCodes | GET | /products/{productId}/alternative-codes |  | array of AlternativeCode | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-PRODUCT-2 | catalogue.alternative_code |  | External identifiers for a product
CatalogueService | product | listGroupPackages | GET | /group-packages |  | object | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-PRODUCT-2 | catalogue.group_package |  | The school-trip formats or party packages on offer
CatalogueService | product | listProductVariants | GET | /products/{productId}/variants |  | object | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-PRODUCT-2 | catalogue.variant |  | List generated variants
CatalogueService | product | listProducts | GET | /products |  | object | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-PRODUCT-2 | catalogue.product, catalogue.product_category, catalogue.product_eligibility_rule, catalogue.product_media, whitelabel.guided_choice_answer |  | List products
CatalogueService | product | resolveProductByCode | GET | /products/resolve |  | ProductVariant | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-PRODUCT-3 | catalogue.variant |  | Resolve a partner code to a product
CatalogueService | product | setAlternativeCodes | PUT | /products/{productId}/alternative-codes |  | array of AlternativeCode | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-PRODUCT-3 | cache:idempotency, catalogue.alternative_code | cache:idempotency, catalogue.alternative_code | Set external identifiers
CatalogueService | product | setGroupPackageDefinition | PUT | /products/{productId}/group-package | GroupPackageDefinition | GroupPackageDefinition | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-PRODUCT-3 | catalogue.group_package | catalogue.group_package | Define a school-trip format or party package
CatalogueService | product | setProductEligibilityRule | PUT | /products/{productId}/eligibility-rule | ProductEligibilityRule | ProductEligibilityRule | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-PRODUCT-3 | catalogue.product_eligibility_rule | catalogue.product_eligibility_rule | Set age, height and supervision limits
CatalogueService | product | updateProduct | PATCH | /products/{productId} | UpdateProductRequest | Product | PRODUCT_CONFIGURE | core | 1 | SVC-CATALOGUE-PRODUCT-4 | cache:idempotency, catalogue.product, catalogue.product_media, whitelabel.booking_flow | cache:idempotency, catalogue.product, catalogue.product_media | Update a product
CatalogueService | product | updateProductVariant | PATCH | /products/{productId}/variants/{variantId} |  | ProductVariant | PRODUCT_CONFIGURE | setup | 1 | SVC-CATALOGUE-PRODUCT-4 | catalogue.variant | catalogue.variant | Describe a variant
CatalogueService | promotion | analysePromotionConflicts | GET | /promotions/{promotionId}/conflicts |  | ConflictAnalysis | PRICE_VIEW | core | 1 | SVC-CATALOGUE-PROMOTION-1 | promotions.promotion |  | Analyse stacking against live promotions
CatalogueService | promotion | createPromotion | POST | /promotions | CreatePromotionRequest | Promotion | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-PROMOTION-1 | cache:idempotency, promotions.promotion | cache:idempotency, promotions.promotion, promotions.promotion_audit | Create a promotion
CatalogueService | promotion | getPromotion | GET | /promotions/{promotionId} |  | Promotion or GuestPromotion | PRICE_VIEW | core | 1 | SVC-CATALOGUE-PROMOTION-1 | promotions.promotion |  | Read a promotion
CatalogueService | promotion | getPromotionUsage | GET | /promotions/{promotionId}/usage |  | PromotionUsage | PRICE_VIEW | core | 1 | SVC-CATALOGUE-PROMOTION-1 | promotions.promotion |  | Redemption count and discount given
CatalogueService | promotion | listPromotions | GET | /promotions |  | object | PRICE_VIEW | core | 1 | SVC-CATALOGUE-PROMOTION-2 | promotions.promotion |  | List promotions
CatalogueService | promotion | publishPromotion | POST | /promotions/{promotionId}/publish |  | Promotion | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-PROMOTION-2 | cache:idempotency, promotions.promotion, promotions.promotion_channel_publication | cache:idempotency, platform.outbox, promotions.promotion, promotions.promotion_audit, promotions.promotion_channel_publication | Publish a promotion
CatalogueService | promotion | updatePromotion | PATCH | /promotions/{promotionId} |  | Promotion | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-PROMOTION-2 | cache:idempotency, promotions.promotion, promotions.promotion_channel_publication | cache:idempotency, promotions.promotion, promotions.promotion_audit, promotions.promotion_channel_publication | Amend a promotion
CatalogueService | promotions | setPromotionVariants | PUT | /promotions/{promotionId}/variants |  | object | PRICE_CONFIGURE | setup | 1 | SVC-CATALOGUE-PROMOTIONS-1 | cache:idempotency, promotions.promotion, promotions.promotion_variant | cache:idempotency, promotions.promotion, promotions.promotion_audit, promotions.promotion_variant | A/B test two versions against each other
CatalogueService | recommendation | recommendSeats | POST | /performances/{performanceId}/seat-recommendations | SeatRecommendationRequest | object | PRODUCT_VIEW | core | 1 | SVC-CATALOGUE-RECOMMENDATION-1 | catalogue.performance, seating.accessible, seating.recommendation_rule, seating.seat, seating.seat_block_item, seating.seat_category, seating.seat_reservation, seating.seat_reservation_item, seating.seat_price_band |  | Recommend seats for a party
CatalogueService | seatMap | editSeatMapStructure | PATCH | /seat-maps/{seatMapId}/structure |  | object | CAPACITY_CONFIGURE | setup | 1 | SVC-CATALOGUE-SEATMAP-1 | cache:idempotency, seating.seat_map | cache:idempotency, seating.seat_map, seating.section, seating.seat | Build a seat map by hand
CatalogueService | seating | setAccessibleSeating | PUT | /accessible-seating | AccessibleSeating | AccessibleSeating | CAPACITY_CONFIGURE | setup | 1 | SVC-CATALOGUE-SEATING-1 | seating.accessible | seating.accessible | Define accessible seats, routes and eligibility
CatalogueService | seating | setSeatRecommendationRules | PUT | /seat-recommendation-rules | SeatRecommendationRules | SeatRecommendationRules | CAPACITY_CONFIGURE | setup | 1 | SVC-CATALOGUE-SEATING-1 | seating.recommendation_rule | seating.recommendation_rule | Scoring for best seat, best value, closest, family and accessible
FnbService | bill | closeTableVisit | POST | /table-visits/{visitId}/close |  | object | ORDER_CREATE | core | 1 | SVC-FNB-BILL-1 | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.service_order, fnb.service_order_line, fnb.table_visit | cache:idempotency, fnb.service_order, fnb.table_visit | Settle and close a visit
FnbService | bill | getBill | GET | /table-visits/{visitId}/bill |  | Bill | ORDER_VIEW | core | 1 | SVC-FNB-BILL-1 | fnb.service_order, fnb.table_session, orders.payment |  | Bill for a visit
FnbService | bill | splitBill | POST | /table-visits/{visitId}/bill/split | SplitBillRequest | BillSplit | ORDER_MODIFY | core | 1 | SVC-FNB-BILL-1 | cache:idempotency, fnb.bill_split, fnb.sub_bill | cache:idempotency, fnb.bill_split, fnb.sub_bill | Split a bill
FnbService | fnb | attachModifierGroup | PUT | /menu-items/{menuItemId}/modifier-groups |  | MenuItem | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-FNB-1 | cache:idempotency, fnb.menu_item, fnb.modifier_group | cache:idempotency, cache:resolution, fnb.menu_item, fnb.menu_item_modifier | Give an item its choices
FnbService | fnb | buildProductionPlan | POST | /production-plans | ProductionPlan | ProductionPlan | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-FNB-1 | ai.suggestion, cache:idempotency, fnb.menu_item, fnb.menu_item_modifier, fnb.production_plan, fnb.production_plan_line, fnb.recipe | cache:idempotency, fnb.production_plan, fnb.production_plan_line | Turn a forecast into a prep list
FnbService | fnb | chaseStation | POST | /kitchen-stations/{stationId}/chase |  |  | ORDER_MODIFY | core | 1 | SVC-FNB-FNB-1 | cache:idempotency, fnb.kitchen_station, fnb.kitchen_ticket | cache:idempotency, fnb.kitchen_exception | The pass asks a station where an item is
FnbService | fnb | createTableReservation | POST | /table-reservations | TableReservation | TableReservation |  | core | 1 | SVC-FNB-FNB-1 | cache:idempotency, fnb.dining_table, fnb.reservation_table, fnb.table_reservation | cache:idempotency, fnb.reservation_table, fnb.table_reservation | Book a table in advance
FnbService | fnb | createTableReservationForGuest | POST | /outlets/{outletId}/table-reservations | TableReservation | TableReservation | ORDER_CREATE | core | 1 | SVC-FNB-FNB-2 | fnb.reservation_table, fnb.table_reservation | fnb.reservation_table, fnb.table_reservation | Book a table for a guest (staff)
FnbService | fnb | escalateCorrectiveAction | POST | /food-safety/corrective-actions/{actionId}/escalate |  | CorrectiveAction | INCIDENT_MANAGE | setup | 1 | SVC-FNB-FNB-2 | cache:idempotency, fnb.corrective_action, identity.principal | cache:idempotency, fnb.corrective_action | Escalate a finding
FnbService | fnb | fireCourse | POST | /kitchen-tickets/{ticketId}/fire |  | KitchenTicket | ORDER_MODIFY | core | 1 | SVC-FNB-FNB-2 | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line | cache:idempotency, fnb.kitchen_ticket | Send a held course to the pass
FnbService | fnb | getCourseRules | GET | /outlets/{outletId}/course-rules |  | CourseRules | PRODUCT_VIEW | core | 1 | SVC-FNB-FNB-2 | fnb.course_rule |  | How this outlet courses by default (read)
FnbService | fnb | getHaccpStatus | GET | /food-safety/status |  | object | INCIDENT_VIEW | core | 1 | SVC-FNB-FNB-3 | fnb.cold_chain_event, fnb.corrective_action, fnb.temperature_log |  | Where this venue stands, right now
FnbService | fnb | getKitchenSla | GET | /outlets/{outletId}/kitchen-sla |  | KitchenSla | PRODUCT_VIEW | core | 1 | SVC-FNB-FNB-3 | fnb.kitchen_sla |  | How long a ticket may sit before it is late (read)
FnbService | fnb | holdCourse | POST | /kitchen-tickets/{ticketId}/hold |  | KitchenTicket | ORDER_MODIFY | core | 1 | SVC-FNB-FNB-3 | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line | cache:idempotency, fnb.kitchen_ticket | Stop a course going out
FnbService | fnb | joinRestaurantWaitlist | POST | /waitlist | RestaurantWaitlist | RestaurantWaitlist | ORDER_MODIFY | core | 1 | SVC-FNB-FNB-3 | cache:idempotency, fnb.dining_table, fnb.waitlist_entry, platform.outlet | cache:idempotency, fnb.waitlist_entry | Add a party to an outlet's waitlist
FnbService | fnb | leaveRestaurantWaitlist | POST | /waitlist/{entryId}/leave |  | RestaurantWaitlist | ORDER_MODIFY | core | 1 | SVC-FNB-FNB-4 | fnb.waitlist_entry | fnb.waitlist_entry | Take a party off an outlet's waitlist
FnbService | fnb | list86Events | GET | /outlets/{outletId}/86-events |  | object | PRODUCT_VIEW | core | 1 | SVC-FNB-FNB-4 | fnb.menu_item, fnb.sold_out_item |  | What came off the menu today, when, and for how long
FnbService | fnb | listMyTableReservations | GET | /me/table-reservations |  | object |  | core | 1 | SVC-FNB-FNB-4 | fnb.reservation_table, fnb.table_reservation, fnb.waitlist_entry |  | The guest's own table bookings and waitlist places
FnbService | fnb | listTableCombinations | GET | /outlets/{outletId}/table-combinations |  | object | PRODUCT_VIEW | core | 1 | SVC-FNB-FNB-4 | fnb.table_combination |  | The outlet's table combinations
FnbService | fnb | listTableReservations | GET | /table-reservations |  | object | ORDER_MODIFY | core | 1 | SVC-FNB-FNB-5 | fnb.dining_table, fnb.reservation_table, fnb.table_reservation |  | Bookings for a service period
FnbService | fnb | logColdChain | POST | /food-safety/cold-chain | ColdChainEvent | ColdChainEvent | INCIDENT_REPORT | setup | 1 | SVC-FNB-FNB-5 | cache:idempotency, fnb.cold_chain_event, inventory.goods_receipt | cache:idempotency, fnb.cold_chain_event, fnb.corrective_action | The temperature a delivery arrived at, and what was decided
FnbService | fnb | logKitchenException | POST | /kitchen-exceptions |  | KitchenException | INCIDENT_REPORT | core | 1 | SVC-FNB-FNB-5 | cache:idempotency, fnb.kitchen_exception, fnb.kitchen_station | cache:idempotency, fnb.kitchen_exception | Something went wrong that is not a refire
FnbService | fnb | logTemperature | POST | /food-safety/temperature-logs | TemperatureLog | object | INCIDENT_REPORT | setup | 1 | SVC-FNB-FNB-5 | cache:idempotency, fnb.corrective_action, fnb.temperature_log, platform.scope | cache:idempotency, fnb.corrective_action, fnb.temperature_log | Record a temperature check, in range or not
FnbService | fnb | markOrderCollected | POST | /orders/{orderId}/collected |  | FnbOrder | ORDER_MODIFY | core | 1 | SVC-FNB-FNB-6 | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.service_order, fnb.service_order_line | cache:idempotency, fnb.kitchen_ticket, fnb.service_order | The guest took it
FnbService | fnb | notifyServer | POST | /table-visits/{visitId}/notify-server |  |  | ORDER_MODIFY | core | 1 | SVC-FNB-FNB-6 | cache:idempotency, fnb.table_visit, identity.principal | cache:idempotency, marketing.message_dispatch | The kitchen calls the server to the pass
FnbService | fnb | printOrderLabel | POST | /kitchen-tickets/{ticketId}/label |  | OrderLabel | ORDER_VIEW | core | 1 | SVC-FNB-FNB-6 | fnb.kitchen_ticket |  | A label for the bag
FnbService | fnb | publishMenu | POST | /menus/{menuId}/publish |  | MenuVersion | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-FNB-6 | cache:idempotency, fnb.menu, fnb.menu_item, fnb.menu_section, fnb.menu_version | cache:idempotency, cache:resolution, fnb.menu | Make the draft live, now or on a date
FnbService | fnb | rebalanceStationLoad | POST | /kitchen-stations/rebalance | StationRebalance | StationRebalance | PRODUCT_CONFIGURE | core | 1 | SVC-FNB-FNB-7 | cache:idempotency, fnb.kitchen_station | cache:idempotency, cache:resolution, fnb.kitchen_station | Move work between stations mid-service
FnbService | fnb | recallKitchenTicket | POST | /kitchen-tickets/{ticketId}/recall |  | KitchenTicket | ORDER_MODIFY | core | 1 | SVC-FNB-FNB-7 | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line | cache:idempotency, fnb.kitchen_ticket | Bring back a ticket that was bumped by mistake
FnbService | fnb | refireItem | POST | /kitchen-tickets/{ticketId}/refire |  | KitchenTicket | ORDER_MODIFY | core | 1 | SVC-FNB-FNB-7 | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line | cache:idempotency, fnb.kitchen_ticket_line, inventory.movement | Make it again
FnbService | fnb | releaseProductionPlan | POST | /production-plans/{planId}/release |  | ProductionPlan | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-FNB-7 | cache:idempotency, fnb.production_plan, fnb.production_plan_line | cache:idempotency, fnb.production_plan, fnb.production_run | Make the plan real
FnbService | fnb | requestBill | POST | /table-visits/{visitId}/request-bill |  | TableVisit | ORDER_MODIFY | core | 1 | SVC-FNB-FNB-8 | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.service_order, fnb.service_order_line, fnb.table_visit | cache:idempotency, fnb.table_visit | The party asked to pay
FnbService | fnb | rollbackMenu | POST | /menus/{menuId}/rollback |  | MenuVersion | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-FNB-8 | cache:idempotency, fnb.menu, fnb.menu_item, fnb.menu_section, fnb.menu_version | cache:idempotency, cache:resolution, fnb.menu, fnb.menu_version | Put the previous version back
FnbService | fnb | scheduleMenuPublish | POST | /menus/{menuId}/schedule |  | MenuSchedule | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-FNB-8 | cache:idempotency, fnb.menu, fnb.menu_schedule | cache:idempotency, cache:resolution, fnb.menu, fnb.menu_schedule | Publish it on a date, not now
FnbService | fnb | seatTableReservation | POST | /table-reservations/{reservationId}/seat |  | TableReservation | ORDER_MODIFY | core | 1 | SVC-FNB-FNB-8 | cache:idempotency, fnb.dining_table, fnb.reservation_table, fnb.table_reservation | cache:idempotency, fnb.reservation_table, fnb.table_reservation, fnb.table_session, fnb.table_visit | The party arrived and has been sat down
FnbService | fnb | setCourseRules | PUT | /outlets/{outletId}/course-rules | CourseRules | CourseRules | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-FNB-9 | cache:idempotency, fnb.course_rule | cache:idempotency, cache:resolution, fnb.course_rule | How this outlet courses by default
FnbService | fnb | setKitchenSla | PUT | /outlets/{outletId}/kitchen-sla | KitchenSla | KitchenSla | PRODUCT_CONFIGURE | core | 1 | SVC-FNB-FNB-9 | cache:idempotency, fnb.kitchen_sla | cache:idempotency, cache:resolution, fnb.kitchen_sla | How long a ticket may sit before it is late
FnbService | fnb | setSubstitutionRules | PUT | /substitution-rules |  | array of SubstitutionRule | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-FNB-9 | cache:idempotency, fnb.substitution_rule | cache:idempotency, cache:resolution, fnb.substitution_rule | What may replace what
FnbService | fnb | setTableCombinations | PUT | /outlets/{outletId}/table-combinations |  | object | PRODUCT_CONFIGURE | core | 1 | SVC-FNB-FNB-9 | cache:idempotency, fnb.dining_table, fnb.table_combination | cache:idempotency, cache:resolution, fnb.dining_table, fnb.table_combination | Which tables can be pushed together, and to what capacity
FnbService | fnb | signCorrectiveAction | POST | /food-safety/corrective-actions/{actionId}/sign |  | CorrectiveAction | INCIDENT_MANAGE | setup | 1 | SVC-FNB-FNB-10 | cache:idempotency, fnb.corrective_action, identity.principal | cache:idempotency, fnb.corrective_action | Say what was done, and put a name to it
FnbService | fnb | transferTableVisit | POST | /table-visits/{visitId}/transfer |  | TableVisit | ORDER_MODIFY | core | 1 | SVC-FNB-FNB-10 | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.service_order, fnb.service_order_line, fnb.table_visit, identity.principal | cache:idempotency, fnb.table_visit | Move a check to another server
FnbService | fnb | updateTableReservation | PATCH | /table-reservations/{reservationId} | TableReservation | TableReservation |  | core | 1 | SVC-FNB-FNB-10 | cache:idempotency, fnb.reservation_table, fnb.table_reservation | cache:idempotency, fnb.reservation_table, fnb.table_reservation | Change or cancel a booking
FnbService | guestOrdering | claimLocationSession | POST | /location-sessions |  | LocationSession |  | core | 1 | SVC-FNB-GUESTORDERING-1 | cache:idempotency, fnb.delivery_location, fnb.dining_table, fnb.location_session, fnb.table_visit | cache:idempotency, fnb.location_session, fnb.table_visit | Tell the platform where the guest is
FnbService | guestOrdering | createDeliveryLocation | POST | /delivery-locations |  | DeliveryLocation | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-GUESTORDERING-1 | cache:idempotency, fnb.delivery_location, fnb.dining_table, platform.outlet | cache:idempotency, fnb.delivery_location, fnb.delivery_location_outlet | Add a place food can be delivered to
FnbService | guestOrdering | createGuestFnbOrder | POST | /guest-orders | CreateGuestOrderRequest | GuestOrderResult |  | core | 1 | SVC-FNB-GUESTORDERING-1 | cache:idempotency, fnb.delivery_policy, fnb.location_session, fnb.menu_item, fnb.menu_item_modifier, inventory.movement | cache:idempotency, fnb.kitchen_ticket, fnb.order_fulfilment, fnb.service_order, platform.outbox | A guest orders food
FnbService | guestOrdering | getFnbDeliveryPolicy | GET | /fnb-delivery-policy |  | FnbDeliveryPolicy | PRODUCT_VIEW | core | 1 | SVC-FNB-GUESTORDERING-1 | fnb.delivery_policy |  | How an outlet does takeaway and delivery
FnbService | guestOrdering | getGuestBill | GET | /table-sessions/{sessionId}/bill |  | Bill |  | core | 1 | SVC-FNB-GUESTORDERING-2 | fnb.service_order, fnb.table_session, orders.payment |  | The bill for the guest's table
FnbService | guestOrdering | getGuestMenu | GET | /outlets/{outletId}/guest-menu |  | GuestMenu |  | core | 1 | SVC-FNB-GUESTORDERING-2 | fnb.modifier_group, fnb.modifier_option |  | The menu a guest sees
FnbService | guestOrdering | getGuestOrderStatus | GET | /guest-orders/{orderId} |  | GuestOrderStatus |  | core | 1 | SVC-FNB-GUESTORDERING-2 | fnb.delivery_location, fnb.kitchen_ticket, fnb.service_order |  | Track an order
FnbService | guestOrdering | listBookableOutlets | GET | /venues/{venueId}/bookable-outlets |  | object |  | core | 1 | SVC-FNB-GUESTORDERING-2 |  |  | The restaurants a guest can book a table at
FnbService | guestOrdering | listDeliveryLocations | GET | /venues/{venueId}/delivery-locations |  | object |  | core | 1 | SVC-FNB-GUESTORDERING-3 | fnb.delivery_location, fnb.delivery_location_outlet |  | Where an order can be delivered
FnbService | guestOrdering | listDiningOutlets | GET | /venues/{venueId}/dining |  | object |  | core | 1 | SVC-FNB-GUESTORDERING-3 | fnb.menu, fnb.service_order, platform.outlet |  | Where a guest can eat, right now
FnbService | guestOrdering | listFulfilmentSlots | GET | /outlets/{outletId}/fulfilment-slots |  | object |  | core | 1 | SVC-FNB-GUESTORDERING-3 | fnb.delivery_policy, platform.outlet |  | Collection times or delivery windows still open
FnbService | guestOrdering | recordOrderHandover | POST | /guest-orders/{orderId}/delivery |  | GuestOrderStatus | ORDER_MODIFY | core | 1 | SVC-FNB-GUESTORDERING-3 | cache:idempotency, fnb.delivery_location, fnb.delivery_location_outlet, fnb.service_order | cache:idempotency, fnb.service_order | Record that an order reached the guest
FnbService | guestOrdering | setDeliveryLocationOutletMapping | PUT | /venues/{venueId}/delivery-location-outlets |  | array of DeliveryLocation | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-GUESTORDERING-4 | cache:idempotency, fnb.delivery_location, platform.outlet | cache:idempotency, cache:resolution, fnb.delivery_location_outlet | Set which outlets deliver to which delivery locations
FnbService | guestOrdering | setFnbDeliveryPolicy | PUT | /fnb-delivery-policy | FnbDeliveryPolicy | FnbDeliveryPolicy | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-GUESTORDERING-4 | fnb.delivery_policy | fnb.delivery_policy | Set takeaway and delivery rules
FnbService | guestOrdering | updateDeliveryLocation | PATCH | /delivery-locations/{locationId} |  | DeliveryLocation | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-GUESTORDERING-4 | cache:idempotency, fnb.delivery_location | cache:idempotency, fnb.delivery_location | Rename a delivery location, or take it out of service
FnbService | kitchen | listKitchenStations | GET | /kitchen/stations |  | object | PRODUCT_VIEW | core | 1 | SVC-FNB-KITCHEN-1 | fnb.kitchen_station |  | List preparation stations and their routing
FnbService | kitchen | listKitchenTickets | GET | /kitchen/tickets |  | object | ORDER_VIEW | core | 1 | SVC-FNB-KITCHEN-1 | fnb.kitchen_ticket, fnb.kitchen_ticket_line |  | Kitchen ticket queue
FnbService | kitchen | prioritiseKitchenTicket | POST | /kitchen/tickets/{ticketId}/prioritise |  | KitchenTicket | ORDER_MODIFY | core | 1 | SVC-FNB-KITCHEN-1 | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line | cache:idempotency, fnb.kitchen_ticket | Move a ticket up the queue
FnbService | kitchen | setKitchenTicketStatus | PUT | /kitchen/tickets/{ticketId}/status |  | KitchenTicket | ORDER_MODIFY | core | 1 | SVC-FNB-KITCHEN-1 | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line | cache:idempotency, fnb.kitchen_ticket, platform.outbox | Advance a kitchen ticket
FnbService | menu | createMenu | POST | /menus | CreateMenuRequest | Menu | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-MENU-1 | cache:idempotency, fnb.menu, fnb.menu_item, fnb.menu_section | cache:idempotency, fnb.menu, fnb.menu_item, fnb.menu_section | Create a menu
FnbService | menu | setItemAvailability | PUT | /menu-items/{itemId}/availability |  | MenuItem | PRODUCT_CONFIGURE | core | 1 | SVC-FNB-MENU-1 | cache:idempotency, fnb.menu_item | cache:idempotency, fnb.menu_item | Mark an item available or eighty-sixed
FnbService | menu | setMenuSections | PUT | /menus/{menuId}/sections |  | Menu | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-MENU-1 | cache:idempotency, fnb.menu, fnb.menu_item, fnb.menu_section | cache:idempotency, fnb.menu, fnb.menu_item, fnb.menu_section | Set menu sections and their item ordering
FnbService | menu | updateMenu | PATCH | /menus/{menuId} |  | Menu | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-MENU-1 | cache:idempotency, fnb.menu, fnb.menu_item, fnb.menu_section | cache:idempotency, fnb.menu, fnb.menu_item, fnb.menu_section | Amend a menu
FnbService | modifier | createModifierGroup | POST | /modifier-groups | ModifierGroup | ModifierGroup | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-MODIFIER-1 | cache:idempotency, fnb.modifier_group, fnb.modifier_option | cache:idempotency, fnb.modifier_group, fnb.modifier_option | Create a modifier group
FnbService | order | createFnbOrder | POST | /fnb-orders | CreateFnbOrderRequest | FnbOrder | ORDER_CREATE | core | 1 | SVC-FNB-ORDER-1 | fnb.kitchen_station, fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.menu_item, fnb.service_order, fnb.service_order_line | fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.service_order, fnb.service_order_line, platform.idempotency_record, platform.outbox | Place an F&B order
FnbService | order | getFnbOrder | GET | /fnb-orders/{orderId} |  | FnbOrder | ORDER_VIEW | core | 1 | SVC-FNB-ORDER-1 | fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.service_order, fnb.service_order_line |  | Read an F&B order
FnbService | order | listFnbOrders | GET | /fnb-orders |  | object | ORDER_VIEW | core | 1 | SVC-FNB-ORDER-1 | fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.service_order, fnb.service_order_line |  | List F&B orders
FnbService | production | setRecipe | PUT | /recipes | Recipe | Recipe | PRODUCT_CONFIGURE | setup | 1 | SVC-FNB-PRODUCTION-1 | cache:idempotency, fnb.menu_item, fnb.modifier_group, fnb.recipe, fnb.recipe_ingredient, fnb.substitution_rule, inventory.inventory_item | cache:idempotency, fnb.allergen_verdict, fnb.menu_item, fnb.recipe, fnb.recipe_ingredient | Define a recipe for a menu item
FnbService | service | acceptFnbOrder | POST | /fnb-orders/{orderId}/accept |  | FnbOrder | ORDER_MODIFY | core | 1 | SVC-FNB-SERVICE-1 | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.service_order, fnb.service_order_line | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.service_order, platform.outbox | The outlet takes the order
FnbService | service | cancelFnbOrder | POST | /fnb-orders/{orderId}/cancel |  | FnbOrder | ORDER_MODIFY | core | 1 | SVC-FNB-SERVICE-1 | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.service_order, fnb.service_order_line | cache:idempotency, fnb.service_order | Cancel an order
FnbService | table | clearTable | POST | /tables/{tableId}/clear |  | TableState | ORDER_MODIFY | core | 1 | SVC-FNB-TABLE-1 | cache:idempotency, fnb.dining_table, fnb.table_visit | cache:idempotency, fnb.dining_table, fnb.table_visit | Mark a table cleared and free
FnbService | table | getTableMap | GET | /outlets/{outletId}/tables |  | TableMap | ORDER_VIEW | core | 1 | SVC-FNB-TABLE-1 | fnb.dining_table, fnb.table_visit |  | Table map with live state
FnbService | table | getTableVisit | GET | /table-visits/{visitId} |  | TableVisit | ORDER_VIEW | core | 1 | SVC-FNB-TABLE-1 | fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.service_order, fnb.service_order_line, fnb.table_visit |  | Read a visit with all its orders
FnbService | table | openTableVisit | POST | /table-visits | OpenTableVisitRequest | TableVisit | ORDER_CREATE | core | 1 | SVC-FNB-TABLE-1 | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.service_order, fnb.service_order_line, fnb.table_visit | cache:idempotency, fnb.service_order, fnb.table_visit | Seat a party and open a visit
FnbService | table | setTableLayout | PUT | /outlets/{outletId}/tables |  | TableMap | PRODUCT_CONFIGURE | core | 1 | SVC-FNB-TABLE-2 | cache:idempotency, fnb.dining_table, fnb.table_visit | cache:idempotency, fnb.dining_table | Configure the table layout
FnbService | table | updateTableVisit | PATCH | /table-visits/{visitId} |  | TableVisit | ORDER_MODIFY | core | 1 | SVC-FNB-TABLE-2 | cache:idempotency, fnb.kitchen_ticket, fnb.kitchen_ticket_line, fnb.service_order, fnb.service_order_line, fnb.table_visit | cache:idempotency, fnb.service_order, fnb.table_visit | Amend covers, move table, or reassign server
IdentityService | administration | createRole | POST | /roles |  | Role | ROLE_MANAGE | setup | 1 | SVC-IDENTITY-ADMINISTRATION-1 | cache:idempotency, identity.capability_template, identity.role, identity.role_permission, identity.segregation_rule | cache:idempotency, cache:resolution, identity.role, identity.role_permission | Create a role
IdentityService | administration | listOwnPlatformStaffGrants | GET | /platform-staff-grants/mine |  | object | PLATFORM_TENANT_ACCESS | core | 1 | SVC-IDENTITY-ADMINISTRATION-1 | identity.platform_staff_grant |  | The calling platform operator's own grants into this tenant
IdentityService | administration | listPrincipals | GET | /principals |  | object | USER_MANAGE | core | 1 | SVC-IDENTITY-ADMINISTRATION-1 | identity.principal |  | List principals
IdentityService | administration | listRoles | GET | /roles |  | object | ROLE_MANAGE | core | 1 | SVC-IDENTITY-ADMINISTRATION-1 | identity.role, identity.role_permission |  | List roles
IdentityService | administration | openPlatformStaffGrant | POST | /platform-staff-grants |  | PlatformStaffGrant | PLATFORM_TENANT_ACCESS | core | 1 | SVC-IDENTITY-ADMINISTRATION-2 | identity.platform_staff_grant | identity.platform_staff_grant | A platform operator opens a time-boxed grant into this tenant
IdentityService | administration | setCapabilityTemplate | PUT | /capability-templates | CapabilityTemplate | CapabilityTemplate | ROLE_MANAGE | setup | 1 | SVC-IDENTITY-ADMINISTRATION-2 | identity.capability_template | identity.capability_template | Save a tick-set under a name
IdentityService | administration | updatePrincipal | PATCH | /principals/{principalId} |  | Principal | USER_MANAGE | core | 1 | SVC-IDENTITY-ADMINISTRATION-2 | cache:idempotency, identity.principal | cache:idempotency, identity.principal | Update or deactivate a principal
IdentityService | administration | updateRole | PATCH | /roles/{roleId} |  | Role | ROLE_MANAGE | setup | 1 | SVC-IDENTITY-ADMINISTRATION-2 | identity.role | identity.role | Rename a role or change its description
IdentityService | guestAuth | deleteGuestAccount | DELETE | /auth/guest/account |  | object |  | core | 1 | SVC-IDENTITY-GUESTAUTH-1 | cache:idempotency, pii.subject | cache:idempotency, pii.subject, platform.dsar_request | Self-service account deletion
IdentityService | guestAuth | getGuestSession | GET | /auth/guest/session |  | GuestSession |  | core | 1 | SVC-IDENTITY-GUESTAUTH-1 | identity.guest_session, identity.mfa_method, pii.subject |  | Read the current guest session
IdentityService | guestAuth | getMyIdentityVerification | GET | /auth/guest/identity-verifications/current |  | IdentityGuestVerification |  | core | 1 | SVC-IDENTITY-GUESTAUTH-1 | identity.guest_identity_verification |  | The guest's own latest identity verification
IdentityService | guestAuth | guestLogout | DELETE | /auth/guest/session |  |  |  | core | 1 | SVC-IDENTITY-GUESTAUTH-1 | identity.guest_session | identity.guest_session | End a guest session
IdentityService | guestAuth | guestPasswordLogin | POST | /auth/guest/password |  | GuestSession |  | core | 1 | SVC-IDENTITY-GUESTAUTH-2 | identity.guest_credential, identity.mfa_method, identity.password_policy, pii.subject_contact | identity.guest_credential, identity.guest_session, platform.outbox | Sign in with an email or mobile and a password
IdentityService | guestAuth | guestSocialLogin | POST | /auth/guest/social |  | GuestSession |  | core | 1 | SVC-IDENTITY-GUESTAUTH-2 | cache:idempotency, identity.mfa_method, pii.subject_contact | cache:idempotency, identity.guest_session, pii.subject, platform.outbox | Sign in with Apple or Google
IdentityService | guestAuth | guestUaePassLogin | POST | /auth/guest/uae-pass |  | GuestSession |  | core | 1 | SVC-IDENTITY-GUESTAUTH-2 | cache:idempotency, identity.mfa_method, pii.subject_contact | cache:idempotency, identity.guest_session, pii.subject, pii.subject_document, platform.outbox | Sign in with a national identity provider
IdentityService | guestAuth | linkGuestCheckout | POST | /auth/guest/link-checkout |  | object |  | core | 1 | SVC-IDENTITY-GUESTAUTH-2 | cache:idempotency, orders.sales_order, pii.subject_contact | cache:idempotency, orders.sales_order, pii.subject | Attach a guest checkout to an account
IdentityService | guestAuth | registerGuest | POST | /auth/guest/register | RegisterGuestRequest | GuestSession |  | core | 1 | SVC-IDENTITY-GUESTAUTH-3 | cache:idempotency, identity.mfa_method, pii.subject | cache:idempotency, identity.guest_credential, identity.guest_session, pii.subject, pii.subject_contact, platform.outbox | Create a guest account
IdentityService | guestAuth | requestGuestOtp | POST | /auth/guest/otp |  | object |  | core | 1 | SVC-IDENTITY-GUESTAUTH-3 | cache:idempotency, pii.subject_contact | cache:idempotency, identity.otp_challenge, platform.outbox | Request a one-time code
IdentityService | guestAuth | submitGuestIdentityDocument | POST | /auth/guest/identity-verifications | IdentityGuestDocumentSubmission | IdentityGuestVerification |  | core | 1 | SVC-IDENTITY-GUESTAUTH-3 | assets.media_asset, cache:idempotency, identity.guest_identity_verification, identity.guest_verification_policy | cache:idempotency, identity.guest_identity_verification, pii.subject_document | Submit an identity document for verification
IdentityService | guestAuth | verifyGuestOtp | POST | /auth/guest/otp/verify |  | GuestSession |  | core | 1 | SVC-IDENTITY-GUESTAUTH-3 | cache:idempotency, identity.mfa_method, identity.otp_challenge, pii.subject_contact | cache:idempotency, identity.guest_session, pii.subject_contact, platform.outbox | Verify a one-time code and issue a session
IdentityService | identity | changeOwnCredential | POST | /auth/credential | ChangeCredentialRequest |  |  | core | 1 | SVC-IDENTITY-IDENTITY-1 | cache:idempotency, identity.password_policy, identity.principal, identity.principal_credential | cache:idempotency, identity.principal_credential, identity.session | Change the caller's own password or PIN
IdentityService | identity | exportSubjectData | POST | /guests/{subjectId}/data-export |  | object | GUEST_VIEW_PII | core | 1 | SVC-IDENTITY-IDENTITY-1 | access.entitlement, cache:idempotency, marketing.consent_record, marketing.form_submission, marketing.guest_document, marketing.guest_profile, orders.sales_order, pii.subject | cache:idempotency, platform.dsar_request | Everything the platform holds about one guest
IdentityService | identity | forceLogout | POST | /auth/sessions/{sessionId}/force-logout |  |  | SESSION_FORCE_LOGOUT | core | 1 | SVC-IDENTITY-IDENTITY-1 | cache:idempotency, identity.delegated_access, identity.principal, identity.principal_credential, identity.session, platform.workstation | cache:idempotency, identity.session | Supervisor termination of an abandoned session
IdentityService | identity | getCurrentSession | GET | /auth/session |  | Session |  | core | 1 | SVC-IDENTITY-IDENTITY-1 | cache:resolution, identity.delegated_access, identity.principal, identity.role, identity.session | cache:resolution | Current session and effective permissions
IdentityService | identity | grantDelegation | POST | /guests/{subjectId}/delegations |  | DelegatedAccess | GUEST_MANAGE | core | 1 | SVC-IDENTITY-IDENTITY-2 | cache:idempotency, identity.delegated_access, pii.subject | cache:idempotency, identity.delegated_access | Let one guest act for another
IdentityService | identity | listDelegations | GET | /guests/{subjectId}/delegations |  | object | GUEST_VIEW | core | 1 | SVC-IDENTITY-IDENTITY-2 | identity.delegated_access, marketing.guest_profile, pii.subject |  | Who may act for this guest, and for whom they may act
IdentityService | identity | login | POST | /auth/login | LoginRequest | LoginResponse |  | core | 1 | SVC-IDENTITY-IDENTITY-2 | cache:idempotency, identity.delegated_access, identity.mfa_method, identity.principal, identity.principal_credential, identity.role | cache:idempotency, identity.refresh_token, identity.session, platform.outbox | Authenticate and open a session
IdentityService | identity | refreshToken | POST | /auth/refresh |  | TokenPair |  | core | 1 | SVC-IDENTITY-IDENTITY-2 | cache:idempotency, identity.refresh_token, identity.session | cache:idempotency, identity.refresh_token, identity.session | Rotate the access token
IdentityService | identity | selectRole | POST | /auth/select-role |  | Session |  | core | 1 | SVC-IDENTITY-IDENTITY-3 | cache:idempotency, identity.delegated_access, identity.role, identity.session | cache:idempotency, identity.session | Choose a role for a multi-role session
IdentityService | identity | setGuestVerificationPolicy | PUT | /guest-verification-policy | IdentityGuestVerificationPolicy | IdentityGuestVerificationPolicy | TENANT_CONFIGURE | setup | 1 | SVC-IDENTITY-IDENTITY-3 | cache:idempotency, identity.guest_verification_policy | cache:idempotency, identity.guest_verification_policy | Set which verifications a guest must pass, and when
IdentityService | identity | setPasswordPolicy | PUT | /password-policy | PasswordPolicy | PasswordPolicy | TENANT_CONFIGURE | setup | 1 | SVC-IDENTITY-IDENTITY-3 | cache:idempotency, identity.password_policy | cache:idempotency, identity.password_policy | Length, breach check, lockout and step-up
IdentityService | identity | setSegregationRules | PUT | /segregation-rules |  | array of SegregationRule | ROLE_MANAGE | setup | 1 | SVC-IDENTITY-IDENTITY-3 | cache:idempotency, identity.delegated_access, identity.segregation_rule | cache:idempotency, identity.segregation_rule | Which permissions may not be held together
IdentityService | identity | verifyGuestEmail | POST | /auth/guest/verify-email |  | object | GUEST_VIEW | core | 1 | SVC-IDENTITY-IDENTITY-4 | cache:idempotency, identity.otp_challenge, pii.subject | cache:idempotency, identity.otp_challenge, marketing.message_dispatch, pii.subject | Send a verification link, or consume one
IdentityService | mfa | createMfaChallenge | POST | /auth/mfa/challenge |  | object |  | core | 1 | SVC-IDENTITY-MFA-1 | cache:idempotency, identity.mfa_method | cache:idempotency, identity.mfa_challenge | Second factor at staff sign-in, and step-up for a sensitive action
IdentityService | mfa | enrolMfaMethod | POST | /auth/mfa/methods |  | MfaEnrolment |  | core | 1 | SVC-IDENTITY-MFA-1 | cache:idempotency, identity.mfa_recovery_code, identity.principal | cache:idempotency, identity.mfa_method, identity.mfa_recovery_code | Enrol an MFA method
IdentityService | mfa | listMfaMethods | GET | /auth/mfa/methods |  | array of MfaMethod |  | core | 1 | SVC-IDENTITY-MFA-1 | identity.mfa_method |  | Enrolled MFA methods
IdentityService | mfa | removeMfaMethod | DELETE | /auth/mfa/methods/{methodId} |  |  |  | core | 1 | SVC-IDENTITY-MFA-1 | cache:idempotency, identity.mfa_method | cache:idempotency, identity.mfa_method | Remove an MFA method
IdentityService | mfa | verifyMfaChallenge | POST | /auth/mfa/challenge/{challengeId}/verify |  | object |  | core | 1 | SVC-IDENTITY-MFA-2 | cache:idempotency, identity.mfa_challenge, identity.mfa_recovery_code | cache:idempotency, identity.mfa_challenge, identity.mfa_recovery_code, identity.session, platform.outbox | Complete a sign-in or step-up challenge
IdentityService | mfa | verifyMfaEnrolment | POST | /auth/mfa/methods/{methodId} |  | MfaMethod |  | core | 1 | SVC-IDENTITY-MFA-2 | cache:idempotency, identity.mfa_method | cache:idempotency, identity.mfa_method | Complete enrolment
IdentityService | session | listActiveSessions | GET | /auth/sessions |  | object | SESSION_FORCE_LOGOUT | core | 1 | SVC-IDENTITY-SESSION-1 | identity.principal, identity.session |  | List active sessions
InventoryService | inventory | bulkUpdateProducts | POST | /products/bulk |  | object | PRODUCT_CONFIGURE | setup | 1 |  | cache:idempotency, catalogue.price, catalogue.product, inventory.inventory_item | cache:idempotency, cache:resolution, catalogue.price, catalogue.product, inventory.inventory_item | Change many products at once, with a preview
InventoryService | inventory | listSerialisedItems | GET | /serialised-items |  | object | PRODUCT_VIEW | core | 1 | SVC-INVENTORY-INVENTORY-1 | inventory.inventory_item, inventory.serialised_item, inventory.stock_batch |  | Where each individual item is
InventoryService | item | createInventoryItem | POST | /inventory-items | CreateInventoryItemRequest | InventoryItem | PRODUCT_CONFIGURE | setup | 1 | SVC-INVENTORY-ITEM-1 | cache:idempotency, inventory.inventory_item | cache:idempotency, inventory.inventory_item | Create an inventory item
InventoryService | item | setInventoryKitDefinition | PUT | /inventory-items/{itemId}/kit-definition | InventoryKitDefinition | InventoryKitDefinition | PRODUCT_CONFIGURE | setup | 1 | SVC-INVENTORY-ITEM-1 | cache:idempotency, inventory.inventory_item, inventory.kit_component, inventory.movement | cache:idempotency, cache:resolution, inventory.kit_component | Make an item a kit of other stocked items
InventoryService | item | updateInventoryItem | PATCH | /inventory-items/{itemId} |  | InventoryItem | PRODUCT_CONFIGURE | setup | 1 | SVC-INVENTORY-ITEM-1 | cache:idempotency, inventory.inventory_item | cache:idempotency, inventory.inventory_item | Amend an item
InventoryService | receipt | createGoodsReceipt | POST | /goods-receipts | CreateGoodsReceiptRequest | GoodsReceipt | PROCUREMENT_RECEIVE | setup | 1 | SVC-INVENTORY-RECEIPT-1 | cache:idempotency, inventory.goods_receipt, inventory.goods_receipt_line | cache:idempotency, inventory.goods_receipt, inventory.goods_receipt_line, platform.outbox | Receive goods against a purchase order
InventoryService | receipt | rejectReceivedGoods | POST | /goods-receipts/{receiptId}/reject |  | GoodsReceipt | PROCUREMENT_RECEIVE | setup | 1 | SVC-INVENTORY-RECEIPT-1 | cache:idempotency, inventory.goods_receipt, inventory.goods_receipt_line | cache:idempotency, inventory.goods_receipt, inventory.goods_receipt_line | Reject received goods
LedgerService | finance | ingestFxRates | POST | /fx-rates/ingest |  | object | LEDGER_APPROVE | setup | 1 | SVC-LEDGER-FINANCE-1 | ledger.fx_rate, platform.region_settings | cache:idempotency, ledger.fx_rate | Pull rates from the configured provider
LedgerService | finance | setFxProvider | PUT | /fx-rates/providers |  | array of FxProviderAssignment | LEDGER_APPROVE | setup | 1 | SVC-LEDGER-FINANCE-1 | ledger.fx_provider_assignment, platform.region_settings | cache:idempotency, ledger.fx_provider_assignment, platform.region_settings | Which provider serves which purpose
LedgerService | fiscal | createLegalEntity | POST | /legal-entities | LegalEntity | LegalEntity | ACCOUNT_CONFIGURE | setup | 1 | SVC-LEDGER-FISCAL-1 | cache:idempotency, ledger.legal_entity | cache:idempotency, ledger.legal_entity | Create a legal entity
LedgerService | ledger | listFxRates | GET | /fx-rates |  | object | LEDGER_VIEW | core | 1 | SVC-LEDGER-LEDGER-1 | ledger.fx_rate |  | The rates in force
LedgerService | ledger | setFxRate | PUT | /fx-rates | FxRate | FxRate | LEDGER_APPROVE | setup | 1 | SVC-LEDGER-LEDGER-1 | cache:idempotency, ledger.fx_rate | cache:idempotency, ledger.fx_rate | Set a rate
LedgerService | tax | createTaxCode | POST | /tax-codes | CreateTaxCodeRequest | TaxCode | TAX_CONFIGURE | setup | 1 | SVC-LEDGER-TAX-1 | cache:idempotency, ledger.tax_code | cache:idempotency, ledger.tax_code | Create a tax code
LedgerService | tax | getTaxDocumentRendition | GET | /tax-documents/{documentId}/rendition |  | FinTaxDocumentRendition | LEDGER_VIEW | core | 1 | SVC-LEDGER-TAX-1 | ledger.credit_memo, ledger.tax_invoice |  | The PDF of a tax invoice or credit memo, in a language
LedgerService | tax | getTaxInvoice | GET | /tax-invoices/{invoiceId} |  | FinTaxInvoice | LEDGER_VIEW | core | 1 | SVC-LEDGER-TAX-1 | ledger.credit_memo, ledger.einvoice_transmission, ledger.tax_invoice, ledger.tax_invoice_line |  | One tax invoice, with its lines, VAT per rate and credit memos
LedgerService | tax | issueCreditMemo | POST | /tax-invoices/{invoiceId}/credit-memos | FinIssueCreditMemoRequest | FinCreditMemo | LEDGER_POST | core | 1 | SVC-LEDGER-TAX-1 | cache:idempotency, ledger.credit_memo, ledger.credit_memo_line, ledger.tax_invoice, ledger.tax_invoice_line, ledger.tax_invoice_template, orders.refund | cache:idempotency, ledger.credit_memo, ledger.credit_memo_line, ledger.tax_invoice, ledger.tax_invoice_line, ledger.tax_invoice_template, platform.audit_record, platform.outbox | Credit all or part of a tax invoice
LedgerService | tax | issueTaxInvoice | POST | /tax-invoices | FinIssueTaxInvoiceRequest | FinTaxInvoice | LEDGER_POST | core | 1 | SVC-LEDGER-TAX-2 | cache:idempotency, ledger.legal_entity, ledger.tax_code, ledger.tax_invoice, ledger.tax_invoice_line, ledger.tax_invoice_template, orders.order_line, orders.payment, orders.sales_order | cache:idempotency, ledger.tax_invoice, ledger.tax_invoice_line, ledger.tax_invoice_template, platform.audit_record, platform.outbox | Issue a tax invoice for one or more paid orders
LedgerService | tax | listCreditMemos | GET | /credit-memos |  | object | LEDGER_VIEW | core | 1 | SVC-LEDGER-TAX-2 | ledger.credit_memo, ledger.credit_memo_line |  | Credit memos issued, newest first
LedgerService | tax | listTaxInvoices | GET | /tax-invoices |  | object | LEDGER_VIEW | core | 1 | SVC-LEDGER-TAX-2 | ledger.tax_invoice, ledger.tax_invoice_line |  | Tax invoices issued, newest first
LedgerService | tax | setEInvoicingProvider | PUT | /e-invoicing/providers | FinEInvoicingProvider | FinEInvoicingProvider | TAX_CONFIGURE | setup | 1 | SVC-LEDGER-TAX-2 | cache:idempotency, ledger.einvoice_transmission, ledger.einvoicing_provider, ledger.legal_entity | cache:idempotency, cache:resolution, ledger.einvoicing_provider, platform.audit_record | Connect a legal entity to its accredited e-invoicing service provider
LedgerService | tax | transmitEInvoices | POST | /e-invoicing/transmissions |  | object | LEDGER_POST | setup | 1 | SVC-LEDGER-TAX-3 | cache:idempotency, ledger.credit_memo, ledger.credit_memo_line, ledger.einvoice_transmission, ledger.einvoicing_provider, ledger.tax_invoice, ledger.tax_invoice_line | cache:idempotency, ledger.einvoice_transmission, platform.outbox | Send issued tax documents to the e-invoicing provider
LedgerService | tax | updateTaxCode | PATCH | /tax-codes/{taxCodeId} |  | TaxCode | TAX_CONFIGURE | setup | 1 | SVC-LEDGER-TAX-3 | cache:idempotency, ledger.tax_code | cache:idempotency, ledger.tax_code | Amend a tax code
MarketingService | campaign | createCampaign | POST | /campaigns | CreateCampaignRequest | Campaign | MARKETING_MANAGE | setup | 1 | SVC-MARKETING-CAMPAIGN-1 | cache:idempotency, marketing.campaign, marketing.campaign_variant, marketing.segment_criterion | cache:idempotency, marketing.campaign, marketing.campaign_target, marketing.campaign_variant, marketing.segment_criterion | Create a campaign
MarketingService | campaign | launchCampaign | POST | /campaigns/{campaignId}/launch |  | LaunchResult | MARKETING_SEND | setup | 1 | SVC-MARKETING-CAMPAIGN-1 | cache:idempotency, marketing.attribution_touch, marketing.campaign, marketing.campaign_variant | cache:idempotency, marketing.campaign, marketing.message_dispatch | Launch or schedule a campaign
MarketingService | campaign | stopCampaign | POST | /campaigns/{campaignId}/stop |  | Campaign | MARKETING_SEND | setup | 1 | SVC-MARKETING-CAMPAIGN-1 | cache:idempotency, marketing.campaign, marketing.campaign_variant, marketing.segment_criterion | cache:idempotency, marketing.campaign, marketing.segment_criterion | Stop a campaign mid-send
MarketingService | campaign | updateCampaign | PATCH | /campaigns/{campaignId} |  | Campaign | MARKETING_MANAGE | setup | 1 | SVC-MARKETING-CAMPAIGN-1 | cache:idempotency, marketing.campaign, marketing.campaign_variant, marketing.segment_criterion | cache:idempotency, marketing.campaign, marketing.campaign_target, marketing.campaign_variant, marketing.segment_criterion | Amend, pause or resume a campaign
MarketingService | consent | claimDeviceConsent | POST | /guests/{subjectId}/consents/claim-device | ClaimDeviceConsentRequest | ConsentState |  | core | 1 | SVC-MARKETING-CONSENT-1 | cache:idempotency, marketing.consent_record, marketing.device_consent, marketing.device_consent_category, marketing.guest_profile, marketing.tracking_technology | cache:idempotency, marketing.consent_propagation, marketing.consent_record, marketing.device_consent, platform.outbox | Attach a browser's cookie decision to the guest who turned out to own it
MarketingService | consent | createConsentQuestion | POST | /consent-questions | ConsentQuestion | ConsentQuestion | GUEST_MANAGE | core | 1 | SVC-MARKETING-CONSENT-1 | marketing.consent_question, marketing.consent_question_version | marketing.consent_question, marketing.consent_question_version | Define a consent question
MarketingService | consent | getCookieConsentRuntime | GET | /storefront/cookie-consent |  | CookieConsentRuntime |  | core | 1 | SVC-MARKETING-CONSENT-1 | marketing.cookie_banner_design, marketing.device_consent, marketing.device_consent_category, marketing.tracking_technology |  | What the page must show and what it may load
MarketingService | consent | getDeviceConsentHistory | GET | /consent/device/history |  | object |  | core | 1 | SVC-MARKETING-CONSENT-1 | marketing.device_consent, marketing.device_consent_category |  | A visitor's own cookie decisions, oldest first
MarketingService | consent | getGuestConsents | GET | /guests/{subjectId}/consents |  | ConsentState | GUEST_VIEW | core | 1 | SVC-MARKETING-CONSENT-2 | marketing.consent_purpose, marketing.consent_record, pii.subject |  | Read a guest's consent state
MarketingService | consent | listConsentAnswers | GET | /consent-answers |  | object | GUEST_VIEW | core | 1 | SVC-MARKETING-CONSENT-2 | marketing.booking_consent_record |  | The consent records given at booking
MarketingService | consent | listConsentPurposes | GET | /consent-purposes |  | object | GUEST_VIEW | core | 1 | SVC-MARKETING-CONSENT-2 | cache:resolution, marketing.consent_purpose, marketing.consent_purpose_channel | cache:resolution | Configured consent purposes
MarketingService | consent | listConsentQuestions | GET | /consent-questions |  | object | GUEST_VIEW | core | 1 | SVC-MARKETING-CONSENT-2 | marketing.consent_question, marketing.consent_question_version |  | The consent questions a venue asks at booking
MarketingService | consent | listPublishedTrackingTechnologies | GET | /storefront/cookie-consent/technologies |  | object |  | core | 1 | SVC-MARKETING-CONSENT-3 | marketing.tracking_technology |  | The approved cookie registry, as the preference centre shows it
MarketingService | consent | recordConsent | POST | /guests/{subjectId}/consents | RecordConsentRequest | ConsentState | GUEST_MANAGE | core | 1 | SVC-MARKETING-CONSENT-3 | cache:idempotency, marketing.consent_record, marketing.guest_profile | cache:idempotency, marketing.consent_propagation, marketing.consent_record, marketing.guest_profile | Record a consent decision
MarketingService | consent | recordConsentAnswers | POST | /consent-answers | RecordConsentAnswersRequest | object | ORDER_CREATE | core | 1 | SVC-MARKETING-CONSENT-3 | marketing.booking_consent_record | marketing.booking_consent_record | Answer the consent questions a booking asks
MarketingService | consent | recordDeviceConsent | POST | /consent/device | RecordDeviceConsentRequest | DeviceConsent |  | core | 1 | SVC-MARKETING-CONSENT-3 | cache:idempotency, marketing.cookie_banner_design, marketing.device_consent, marketing.device_consent_category | cache:idempotency, marketing.device_consent, marketing.device_consent_category, pii.consent_identifier, platform.outbox | Record a visitor's cookie decision, before anyone is known
MarketingService | consent | setConsentPurposes | PUT | /consent-purposes |  | array of ConsentPurposeConfig | GUEST_MANAGE | core | 1 | SVC-MARKETING-CONSENT-4 | cache:idempotency, marketing.consent_purpose, marketing.consent_purpose_channel | cache:idempotency, cache:resolution, marketing.consent_purpose, marketing.consent_purpose_channel | Configure consent purposes
MarketingService | consent | setCookieBannerDesign | PUT | /cookie-banner-preference | CookieBannerPreferenceCenterDesignerView | CookieBannerPreferenceCenterDesignerView | GUEST_MANAGE | setup | 1 | SVC-MARKETING-CONSENT-4 | marketing.cookie_banner_design | marketing.cookie_banner_design | Save a cookie banner design as a new version
MarketingService | consent | setDynamicFieldQuestion | PUT | /dynamic-field-question | DynamicFieldsQuestionsConditionalLogicView | DynamicFieldsQuestionsConditionalLogicView | GUEST_MANAGE | setup | 1 | SVC-MARKETING-CONSENT-4 | marketing.form_definition_field, marketing.waiver_field_rule | marketing.form_definition_field, marketing.waiver_field_rule | Create, change or remove one field of a draft waiver version
MarketingService | consent | setTrackingTechnology | PUT | /cookie-tracking-digital | CookieTrackingDigitalTechnologyRegistryView | CookieTrackingDigitalTechnologyRegistryView | GUEST_MANAGE | setup | 1 | SVC-MARKETING-CONSENT-4 | marketing.tracking_technology | marketing.tracking_technology | Add, classify or retire a tracking technology
MarketingService | consent | updateConsentQuestion | PATCH | /consent-questions/{questionId} | ConsentQuestion | ConsentQuestion | GUEST_MANAGE | core | 1 | SVC-MARKETING-CONSENT-5 | marketing.consent_question, marketing.consent_question_version | marketing.consent_question, marketing.consent_question_version | Reword, re-scope or retire a consent question
MarketingService | feedback | submitReview | POST | /reviews | SubmitReviewRequest | Review |  | core | 1 | SVC-MARKETING-FEEDBACK-1 | cache:idempotency, marketing.case, marketing.review | cache:idempotency, marketing.case, marketing.review | Submit a review
MarketingService | guest | addToWishlist | POST | /guests/{subjectId}/wishlist |  | Wishlist |  | core | 1 | SVC-MARKETING-GUEST-1 | cache:idempotency, marketing.wishlist_item | cache:idempotency, marketing.wishlist_item | Save an item
MarketingService | guest | getWishlist | GET | /guests/{subjectId}/wishlist |  | Wishlist |  | core | 1 | SVC-MARKETING-GUEST-1 | marketing.wishlist_item |  | Read a guest's saved items
MarketingService | guest | listGuestDevices | GET | /guests/{subjectId}/devices |  | object |  | core | 1 | SVC-MARKETING-GUEST-1 | marketing.guest_device |  | A guest's registered devices
MarketingService | guest | registerGuestDevice | POST | /guests/{subjectId}/devices |  | GuestDevice |  | core | 1 | SVC-MARKETING-GUEST-1 | cache:idempotency, marketing.guest_device | cache:idempotency, marketing.guest_device | Register a device for push
MarketingService | guest | removeFromWishlist | DELETE | /guests/{subjectId}/wishlist/{itemId} |  |  |  | core | 1 | SVC-MARKETING-GUEST-2 | cache:idempotency, marketing.guest_profile | cache:idempotency, marketing.guest_profile | Remove a saved item
MarketingService | guest | revokeGuestDevice | DELETE | /guests/{subjectId}/devices/{deviceId} |  |  |  | core | 1 | SVC-MARKETING-GUEST-2 | cache:idempotency, marketing.guest_profile | cache:idempotency, marketing.guest_profile | Revoke a device registration
MarketingService | guest | searchGuests | GET | /guests |  | object | GUEST_VIEW | core | 1 | SVC-MARKETING-GUEST-2 | marketing.guest_profile |  | Search guest profiles
MarketingService | loyalty | awardBadge | POST | /customers/{customerId}/badges | MarketingCustomerBadge | MarketingCustomerBadge | MARKETING_MANAGE | setup | 1 | SVC-MARKETING-LOYALTY-1 | marketing.customer_badge | marketing.customer_badge | Award a badge
MarketingService | loyalty | createLoyaltyProgramme | POST | /loyalty/programmes | LoyaltyProgramme | LoyaltyProgramme | MARKETING_MANAGE | setup | 1 | SVC-MARKETING-LOYALTY-1 | cache:idempotency, marketing.loyalty_programme, marketing.points_earning_rule, marketing.programme_tier | cache:idempotency, marketing.loyalty_programme, marketing.points_earning_rule, marketing.programme_tier | Create a loyalty programme
MarketingService | loyalty | getGuestLoyalty | GET | /guests/{subjectId}/loyalty |  | LoyaltyPosition | GUEST_VIEW | core | 1 | SVC-MARKETING-LOYALTY-1 | marketing.loyalty_position |  | A guest's loyalty position
MarketingService | loyalty | listCustomerBadges | GET | /customers/{customerId}/badges |  | object | MARKETING_VIEW | core | 1 | SVC-MARKETING-LOYALTY-1 | marketing.customer_badge |  | Badges a guest holds
MarketingService | loyalty | listLeaderboard | GET | /loyalty/leaderboard |  | object |  | core | 1 | SVC-MARKETING-LOYALTY-2 | marketing.loyalty_position |  | Standings, by nickname
MarketingService | loyalty | listLoyaltyProgrammes | GET | /loyalty/programmes |  | object | MARKETING_VIEW | core | 1 | SVC-MARKETING-LOYALTY-2 | marketing.loyalty_programme, marketing.points_earning_rule, marketing.programme_tier |  | List loyalty programmes
MarketingService | loyalty | listRewards | GET | /loyalty/rewards |  | object | MARKETING_VIEW | core | 1 | SVC-MARKETING-LOYALTY-2 | marketing.reward |  | What points can be turned into
MarketingService | loyalty | setLeaderboardNickname | PUT | /loyalty/leaderboard-nickname |  | LoyaltyPosition |  | core | 1 | SVC-MARKETING-LOYALTY-2 | marketing.loyalty_position | marketing.loyalty_position | Choose the name shown on the board
MarketingService | loyalty | setLoyaltyRules | PUT | /loyalty/programmes/{programmeId}/rules | LoyaltyRuleSet | LoyaltyRuleSet | MARKETING_MANAGE | setup | 1 | SVC-MARKETING-LOYALTY-3 | marketing.loyalty_rule, marketing.points_redemption_rule, marketing.programme_tier | marketing.loyalty_rule, marketing.points_redemption_rule, marketing.programme_tier | Replace a programme's rules as one set
MarketingService | loyalty | setReward | PUT | /loyalty/rewards | MarketingReward | MarketingReward | MARKETING_MANAGE | setup | 1 | SVC-MARKETING-LOYALTY-3 | marketing.reward | marketing.reward | Define a reward and its points cost
MarketingService | loyalty | updateLoyaltyProgramme | PATCH | /loyalty/programmes/{programmeId} |  | LoyaltyProgramme | MARKETING_MANAGE | setup | 1 | SVC-MARKETING-LOYALTY-3 | cache:idempotency, marketing.loyalty_programme, marketing.points_earning_rule, marketing.programme_tier | cache:idempotency, marketing.loyalty_programme, marketing.points_earning_rule | Change a loyalty programme
MarketingService | marketing | createChallenge | POST | /challenges | Challenge | Challenge | MARKETING_MANAGE | setup | 1 | SVC-MARKETING-MARKETING-1 | cache:idempotency, catalogue.event, marketing.challenge, marketing.loyalty_programme | cache:idempotency, marketing.challenge | Define a challenge, mission or streak
MarketingService | marketing | createForm | POST | /forms | FormDefinition | FormDefinition | MARKETING_MANAGE | setup | 1 | SVC-MARKETING-MARKETING-1 | cache:idempotency, catalogue.product, marketing.form_definition, marketing.form_definition_field | cache:idempotency, marketing.form_definition, marketing.form_definition_field | Define a waiver, survey or capture form
MarketingService | marketing | createInvitationCampaign | POST | /invitation-campaigns | InvitationCampaign | InvitationCampaign | MARKETING_MANAGE | setup | 1 | SVC-MARKETING-MARKETING-1 | cache:idempotency, catalogue.event, catalogue.product, marketing.invitation_campaign | cache:idempotency, marketing.invitation_campaign | A quota-bounded, addressed invitation
MarketingService | marketing | createReferral | POST | /referrals | Referral | Referral | MARKETING_MANAGE | core | 1 | SVC-MARKETING-MARKETING-1 | cache:idempotency, marketing.guest_profile, marketing.referral, promotions.promotion | cache:idempotency, marketing.referral | Issue a referral code
MarketingService | marketing | createUrlRedirect | POST | /seo-redirects | UrlRedirect | UrlRedirect | MARKETING_MANAGE | core | 1 | SVC-MARKETING-MARKETING-2 | cache:idempotency, control.url_redirect | cache:idempotency, cache:resolution, control.url_redirect | 301, 302 and custom redirects
MarketingService | marketing | getForm | GET | /forms/{formId} |  | FormDefinition | GUEST_VIEW | core | 1 | SVC-MARKETING-MARKETING-2 | marketing.form_definition, marketing.form_definition_field |  | One form, to fill in or to edit
MarketingService | marketing | getGuestConversation | GET | /my/conversations/{conversationId} |  | GuestConversation |  | core | 1 | AI-ENGINE-CONCIERGE |  |  | The guest's own handed-over conversation, with the agent's replies and the queue position
MarketingService | marketing | getLoyaltyPosition | GET | /loyalty/position |  | object |  | core | 1 | SVC-MARKETING-MARKETING-2 | marketing.loyalty_programme |  | A guest's points, tier and what is within reach
MarketingService | marketing | getMarketingSubscription | GET | /marketing-subscriptions |  | array of MarketingSubscription | MARKETING_VIEW | core | 1 |  | marketing.subscription |  | What this guest has opted into
MarketingService | marketing | getMyChallenges | GET | /guests/me/challenges |  | array of object | MARKETING_VIEW | core | 1 | SVC-MARKETING-MARKETING-2 | marketing.challenge, marketing.challenge_progress |  | Active challenges and how far along I am
MarketingService | marketing | getMyProfile | GET | /guests/me/profile |  | object | GUEST_VIEW | core | 1 | SVC-MARKETING-MARKETING-3 | marketing.guest_preference, marketing.guest_profile |  | A guest reading their own details
MarketingService | marketing | getSeoMetadata | GET | /seo-metadata |  | SeoMetadata | MARKETING_VIEW | core | 1 | SVC-MARKETING-MARKETING-3 | control.seo_metadata |  | The metadata in force for one page
MarketingService | marketing | getWaiverStatus | GET | /guests/{subjectId}/waiver-status |  | object | GUEST_VIEW | core | 1 | SVC-MARKETING-MARKETING-3 | access.entitlement, catalogue.product, marketing.form_definition, marketing.form_submission |  | Whether this guest may be issued a ticket that requires a waiver
MarketingService | marketing | handoverToAgent | POST | /conversations/{conversationId}/handover |  | Conversation |  | core | 1 | SVC-MARKETING-MARKETING-3 | cache:idempotency, marketing.agent_availability, marketing.conversation, marketing.conversation_message, marketing.conversation_message_attachment | cache:idempotency, marketing.conversation, platform.outbox | Pass an assistant conversation to a person
MarketingService | marketing | identifyGuest | POST | /guests/identify |  | GuestIdentification | GUEST_VIEW | core | 1 | SVC-MARKETING-MARKETING-4 | access.blacklist, access.entitlement, marketing.guest_profile, marketing.loyalty_position, pii.subject |  | Resolve any identifier to a guest
MarketingService | marketing | listMyCases | GET | /my/cases |  | object |  | core | 1 | SVC-MARKETING-MARKETING-4 | marketing.case, pii.subject |  | The cases this guest raised
MarketingService | marketing | raiseMyCase | POST | /my/cases |  | Case |  | core | 1 | SVC-MARKETING-MARKETING-4 | cache:idempotency, marketing.case | cache:idempotency, marketing.case | Report something — lost property, a complaint, a question
MarketingService | marketing | recordLostItem | POST | /lost-items | LostItem | LostItem | CASE_MANAGE | core | 1 | SVC-MARKETING-MARKETING-4 | cache:idempotency, marketing.lost_item, pii.subject, venuemap.point | cache:idempotency, marketing.lost_item | Report something lost, or hand something in
MarketingService | marketing | redeemLoyaltyPoints | POST | /loyalty/redemptions |  | LoyaltyPosition | LOYALTY_REDEEM | core | 1 | SVC-MARKETING-MARKETING-5 | cache:idempotency, marketing.loyalty_position, marketing.loyalty_programme | cache:idempotency, marketing.loyalty_position, orders.stored_value_authorisation | Spend points
MarketingService | marketing | replyToMyCase | POST | /my/cases/{caseId}/messages |  | CaseDetail |  | core | 1 | SVC-MARKETING-MARKETING-5 | cache:idempotency, marketing.case, marketing.case_message | cache:idempotency, marketing.case, marketing.case_message | Reply on a case the guest raised
MarketingService | marketing | respondToInvitation | POST | /invitations/{token}/respond |  | Invitation | GUEST_VIEW | core | 1 | SVC-MARKETING-MARKETING-5 | cache:idempotency, marketing.invitation, marketing.invitation_campaign, orders.invitation | cache:idempotency, marketing.invitation | Accept or decline
MarketingService | marketing | sendConversationMessage | POST | /conversations/{conversationId}/messages |  | ConversationMessage | CASE_MANAGE | setup | 1 | SVC-MARKETING-MARKETING-5 | cache:idempotency, marketing.conversation, marketing.conversation_message, marketing.conversation_message_attachment | cache:idempotency, marketing.conversation, marketing.conversation_message, marketing.conversation_message_attachment | Say something, as a guest or an agent
MarketingService | marketing | sendGuestConversationMessage | POST | /my/conversations/{conversationId}/messages |  | GuestConversationMessage |  | core | 1 | AI-ENGINE-CONCIERGE |  | marketing.conversation_message | Write to the agent, as the guest, in the guest's own handed-over conversation
MarketingService | marketing | setAgentAvailability | PUT | /agent-availability |  | AgentAvailability | CASE_MANAGE | setup | 1 | SVC-MARKETING-MARKETING-6 | cache:idempotency, identity.principal, marketing.agent_availability | cache:idempotency, marketing.agent_availability | An agent goes available, away or offline
MarketingService | marketing | setMarketingSubscription | PUT | /marketing-subscriptions | MarketingSubscription | MarketingSubscription | MARKETING_VIEW | core | 1 |  | marketing.subscription | marketing.subscription | Subscribe or unsubscribe
MarketingService | marketing | setSeoMetadata | PUT | /seo-metadata | SeoMetadata | SeoMetadata | MARKETING_MANAGE | core | 1 | SVC-MARKETING-MARKETING-6 | cache:idempotency, catalogue.product, control.seo_metadata | cache:idempotency, cache:resolution, control.seo_metadata | Titles, descriptions, canonicals and hreflang
MarketingService | marketing | submitForm | POST | /form-submissions | FormSubmission | FormSubmission | GUEST_VIEW | core | 1 | SVC-MARKETING-MARKETING-6 | cache:idempotency, marketing.consent_record, marketing.form_definition, marketing.form_submission, marketing.waiver_requirement, pii.subject | cache:idempotency, marketing.consent_record, marketing.form_submission, marketing.waiver_requirement, marketing.waiver_requirement_event | Sign a waiver, answer a survey, capture details
MarketingService | marketing | updateGuestPreferences | PUT | /guests/{subjectId}/preferences | GuestPreferences | GuestPreferences | GUEST_MANAGE | core | 1 | SVC-MARKETING-MARKETING-6 | cache:idempotency, marketing.guest_preference, marketing.guest_profile | cache:idempotency, marketing.guest_preference, marketing.guest_profile | The things a regular should not have to say twice
MarketingService | marketing | updateMyProfile | PATCH | /guests/me/profile |  | GuestProfile | GUEST_VIEW | core | 1 | SVC-MARKETING-MARKETING-7 | cache:idempotency, marketing.guest_profile | cache:idempotency, marketing.guest_profile, pii.subject | A guest correcting their own details
MarketingService | marketing | uploadGuestDocument | POST | /guest-documents | GuestDocument | GuestDocument | GUEST_VIEW_PII | setup | 1 | SVC-MARKETING-MARKETING-7 | cache:idempotency, marketing.consent_record, marketing.guest_document, pii.subject | cache:idempotency, marketing.guest_document | Store a guest photo, ID or signed document
MarketingService | message | createMessageTemplate | POST | /message-templates | MessageTemplate | MessageTemplate | MARKETING_MANAGE | setup | 1 | SVC-MARKETING-MESSAGE-1 | cache:idempotency, marketing.message_template | cache:idempotency, marketing.message_template, marketing.message_template_version | Create a message template
MarketingService | message | listMyNotifications | GET | /me/notifications |  | object |  | core | 1 | SVC-MARKETING-MESSAGE-1 | marketing.message_dispatch |  | The signed-in guest's notification feed
MarketingService | message | markMyNotificationsRead | POST | /me/notifications/read |  | object |  | core | 1 | SVC-MARKETING-MESSAGE-1 | cache:idempotency, marketing.message_dispatch | cache:idempotency, marketing.message_dispatch | Mark the signed-in guest's notifications read
MarketingService | message | updateMessageTemplate | PATCH | /message-templates/{templateId} |  | MessageTemplate | MARKETING_MANAGE | setup | 1 | SVC-MARKETING-MESSAGE-1 | cache:idempotency, marketing.message_template | cache:idempotency, marketing.message_template, marketing.message_template_version | Change a message template
MarketingService | segment | createSegment | POST | /segments | CreateSegmentRequest | Segment | MARKETING_MANAGE | setup | 1 | SVC-MARKETING-SEGMENT-1 | cache:idempotency, marketing.segment, marketing.segment_criterion | cache:idempotency, marketing.segment, marketing.segment_criterion | Create a segment
OrderService | cart | abandonCart | DELETE | /carts/{cartId} |  |  |  | core | 1 | SVC-ORDER-CART-1 | cache:idempotency, orders.cart | cache:idempotency, catalogue.inventory_reservation, orders.cart | Empty it deliberately
OrderService | cart | addCartLine | POST | /carts/{cartId}/lines | AddCartLineRequest | Cart |  | core | 1 | SVC-ORDER-CART-1 | catalogue.channel_capacity, catalogue.performance, catalogue.variant, marketing.consent_question, marketing.consent_question_version, orders.cart, orders.cart_line | orders.cart, orders.cart_line, platform.idempotency_record | Add something
OrderService | cart | applyCartPromoCode | POST | /carts/{cartId}/promo-codes | ApplyCartPromoCodeRequest | Cart |  | core | 1 | SVC-ORDER-CART-1 | marketing.consent_question, marketing.consent_question_version, orders.cart, orders.cart_line, promotions.coupon_campaign, promotions.coupon_code | orders.cart, orders.cart_line | Apply a promo code to the cart
OrderService | cart | checkoutCart | POST | /carts/{cartId}/checkout |  | Order |  | core | 1 | SVC-ORDER-CART-1 | catalogue.inventory_reservation, marketing.consent_question, orders.cart, orders.cart_line, orders.fraud_rule, orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.payment, orders.sales_order | marketing.consent_record, orders.cart, orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.sales_order, platform.idempotency_record, platform.outbox | Turn the cart into an order
OrderService | cart | claimCart | POST | /carts/{cartId}/claim |  | CartMergeResult |  | core | 1 | SVC-ORDER-CART-2 | cache:idempotency, marketing.consent_question, marketing.consent_question_version, orders.cart, orders.cart_line, pii.subject | cache:idempotency, orders.cart, orders.cart_line | Attach an anonymous cart to a guest
OrderService | cart | createCart | POST | /carts |  | Cart |  | core | 1 | SVC-ORDER-CART-2 | cache:idempotency, marketing.consent_question, marketing.consent_question_version, orders.cart, orders.cart_line, pii.subject, platform.scope | cache:idempotency, orders.cart | Start a cart
OrderService | cart | extendCart | POST | /carts/{cartId}/extend |  | Cart |  | core | 1 | SVC-ORDER-CART-2 | cache:idempotency, catalogue.inventory_reservation, marketing.consent_question, marketing.consent_question_version, orders.cart, orders.cart_line | cache:idempotency, catalogue.inventory_reservation, orders.cart | Give the guest more time
OrderService | cart | getCart | GET | /carts/{cartId} |  | Cart |  | core | 1 | SVC-ORDER-CART-2 | catalogue.channel_capacity, catalogue.inventory_reservation, marketing.consent_question, marketing.consent_question_version, orders.cart, orders.cart_line, promotions.promotion |  | The cart, priced and checked, right now
OrderService | cart | removeCartLine | DELETE | /carts/{cartId}/lines/{lineId} |  | Cart |  | core | 1 | SVC-ORDER-CART-3 | cache:idempotency, marketing.consent_question, marketing.consent_question_version, orders.cart, orders.cart_line | cache:idempotency, catalogue.inventory_reservation, orders.cart_line | Take something out
OrderService | cart | updateCartLine | PATCH | /carts/{cartId}/lines/{lineId} |  | Cart |  | core | 1 | SVC-ORDER-CART-3 | cache:idempotency, catalogue.channel_capacity, marketing.consent_question, marketing.consent_question_version, orders.cart, orders.cart_line | cache:idempotency, catalogue.inventory_reservation, orders.cart_line | Change a quantity
OrderService | cash | createCashMovement | POST | /shifts/{shiftId}/cash-movements | CreateCashMovementRequest | CashMovement | CASH_LIFT | core | 1 | SVC-ORDER-CASH-1 | cache:idempotency, orders.cash_count_line, orders.cash_movement | cache:idempotency, orders.cash_count_line, orders.cash_movement | Record a cash lift or add
OrderService | cash | listCashMovements | GET | /shifts/{shiftId}/cash-movements |  | object | REPORT_VIEW_WORKSTATION | core | 1 | SVC-ORDER-CASH-1 | orders.cash_count_line, orders.cash_movement |  | Lifts, adds and the opening float
OrderService | drafted | listGroupArrivalCheck | GET | /group-arrival-check |  | array of GroupArrivalCheckInAdmissionOperationsView | ORDER_VIEW | core | 1 | SVC-ORDER-DRAFTED-1 | access.entitlement, access.scan_event, orders.group_booking, orders.group_participant, orders.group_visit_plan |  | Group Arrival, Check-In & Admission Operations
OrderService | dunning | listMyPaymentIssues | GET | /guests/me/payment-issues |  | object |  | core | 1 | SVC-ORDER-DUNNING-1 | payments.dunning_case |  | A guest's own failed recurring payments
OrderService | dunning | retryMyDunningPayment | POST | /dunning-cases/{caseId}/retry | RetryDunningPaymentRequest | DunningCase |  | core | 1 | SVC-ORDER-DUNNING-1 | cache:idempotency, orders.payment, payments.dunning_case, payments.dunning_policy | cache:idempotency, orders.payment, payments.dunning_case | Retry a declined membership payment now
OrderService | order | appendEntitlementToMedia | POST | /media/{mediaCode}/entitlements | AppendEntitlementRequest | AppendEntitlementResult | ORDER_CREATE | core | 1 | SVC-ORDER-ORDER-1 | access.entitlement, cache:idempotency, orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.payment, orders.sales_order | access.entitlement, cache:idempotency, orders.order_line, orders.payment, orders.sales_order, platform.outbox | Add something to a ticket the guest already holds
OrderService | order | applyManualDiscount | POST | /orders/{orderId}/discounts | ManualDiscountRequest | Order | ORDER_DISCOUNT | core | 1 | SVC-ORDER-ORDER-1 | cache:idempotency, orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.payment, orders.sales_order | cache:idempotency, orders.order_line, orders.order_line_discount, orders.payment, orders.sales_order | Apply a discount a cashier chose
OrderService | order | claimTicketTransfer | POST | /ticket-transfers/{transferId}/claim |  | TicketTransfer |  | core | 1 | SVC-ORDER-ORDER-1 | access.entitlement, cache:idempotency, orders.ticket_transfer | access.entitlement, cache:idempotency, orders.ticket_transfer, platform.outbox | Claim transferred tickets
OrderService | order | createOrder | POST | /orders | CreateOrderRequest | Order | ORDER_CREATE | core | 1 | SVC-ORDER-ORDER-1 | cache:idempotency, orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.payment, orders.sales_order | cache:idempotency, orders.order_event, orders.order_line, orders.payment, orders.sales_order, platform.outbox, promotions.promotion_evaluation_trace | Create an order
OrderService | order | exchangeOrderLines | POST | /orders/{orderId}/exchanges | ExchangeOrderRequest | OrderExchangeResult | ORDER_EXCHANGE | core | 1 | SVC-ORDER-ORDER-2 | cache:idempotency, orders.sales_order | cache:idempotency, orders.order_event, orders.sales_order, platform.outbox | Exchange lines for different products or dates
OrderService | order | getMediaEntitlements | GET | /media/{mediaCode}/entitlements |  | MediaEntitlements | ORDER_VIEW | core | 1 | SVC-ORDER-ORDER-2 | access.entitlement, access.scan_event, catalogue.entitlement_template, orders.sales_order, pii.subject |  | What is already on this media
OrderService | order | getOrder | GET | /orders/{orderId} |  | Order | ORDER_VIEW | core | 1 | SVC-ORDER-ORDER-2 | orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.payment, orders.sales_order |  | Read an order
OrderService | order | getOrderCalendarEvent | GET | /orders/{orderId}/calendar-event |  | string | ORDER_VIEW | core | 1 | SVC-ORDER-ORDER-2 | orders.order_line, orders.sales_order, platform.scope |  | The visit as a calendar entry
OrderService | order | getOrderStatement | GET | /orders/{orderId}/statement |  | OrderStatement | ORDER_VIEW | core | 1 | SVC-ORDER-ORDER-3 | ledger.posting, orders.payment, orders.refund, orders.sales_order |  | Full financial history of an order
OrderService | order | getVisitReminder | GET | /orders/{orderId}/reminder |  | VisitReminder | ORDER_VIEW | core | 1 | SVC-ORDER-ORDER-3 | orders.visit_reminder |  | The guest's reminder for this booking
OrderService | order | holdOrder | POST | /orders/{orderId}/hold |  | Order | ORDER_MODIFY | core | 1 | SVC-ORDER-ORDER-3 | cache:idempotency, orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.payment, orders.sales_order | cache:idempotency, orders.order_event, orders.order_line, orders.payment, orders.sales_order | Park a sale and free the till
OrderService | order | listOrders | GET | /orders |  | object | ORDER_VIEW | core | 1 | SVC-ORDER-ORDER-3 | orders.order_line, orders.sales_order |  | List orders
OrderService | order | listTicketTransfers | GET | /ticket-transfers |  | object |  | core | 1 | SVC-ORDER-ORDER-4 | orders.ticket_transfer |  | The ticket transfers this guest sent or received
OrderService | order | modifyOrder | POST | /orders/{orderId}/modify | ModifyOrderRequest | OrderModificationResult | ORDER_MODIFY | core | 1 | SVC-ORDER-ORDER-4 | cache:idempotency, orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.payment, orders.sales_order | cache:idempotency, orders.order_event, orders.order_line, orders.payment, orders.sales_order | Add or remove lines on an existing order
OrderService | order | reprintOrder | POST | /orders/{orderId}/reprints |  | object | ORDER_REPRINT | core | 1 | SVC-ORDER-ORDER-4 | cache:idempotency, orders.sales_order | cache:idempotency, orders.sales_order | Reprint or resend tickets
OrderService | order | rescheduleOrder | POST | /orders/{orderId}/reschedule |  | OrderExchangeResult | ORDER_RESCHEDULE | core | 1 | SVC-ORDER-ORDER-4 | cache:idempotency, orders.sales_order | cache:idempotency, orders.order_event, orders.sales_order | Move an order to another performance
OrderService | order | resumeOrder | POST | /orders/{orderId}/resume |  | OrderResumeResult | ORDER_MODIFY | core | 1 | SVC-ORDER-ORDER-5 | cache:idempotency, orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.payment, orders.sales_order | cache:idempotency, orders.order_event, orders.order_line, orders.payment, orders.sales_order | Bring a parked sale back to a till
OrderService | order | setVisitReminder | PUT | /orders/{orderId}/reminder | VisitReminder | VisitReminder | ORDER_VIEW | core | 1 | SVC-ORDER-ORDER-5 | orders.visit_reminder | orders.visit_reminder | Turn a visit reminder on or off
OrderService | order | transferOrderTickets | POST | /orders/{orderId}/transfer |  | TicketTransfer |  | core | 1 | SVC-ORDER-ORDER-5 | access.entitlement, cache:idempotency, orders.ticket_transfer | access.entitlement, cache:idempotency, orders.ticket_transfer, platform.outbox | Transfer tickets to another guest
OrderService | order | voidOrder | POST | /orders/{orderId}/voids |  | Order | ORDER_VOID | core | 1 | SVC-ORDER-ORDER-5 | cache:idempotency, orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.payment, orders.sales_order | cache:idempotency, orders.order_event, orders.order_line, orders.payment, orders.sales_order, platform.outbox | Void an order
OrderService | orders | cloneTicketTemplate | POST | /ticket-templates/{templateId}/clone | CloneTicketTemplateInput | TicketTemplate | PRODUCT_CONFIGURE | setup | 1 | SVC-ORDER-ORDERS-1 | orders.ticket_template, orders.ticket_template_channel | orders.ticket_template, orders.ticket_template_channel | Create a ticket template from an existing one
OrderService | orders | createResaleListing | POST | /resale-listings | CreateResaleListingRequest | ResaleListing | ORDER_CREATE | core | 1 | SVC-ORDER-ORDERS-1 | access.entitlement, cache:idempotency, catalogue.entitlement_template, orders.resale_listing, orders.sales_order | cache:idempotency, orders.resale_listing, platform.outbox | List an entitlement for resale
OrderService | orders | createTicketTemplate | POST | /ticket-templates | TicketTemplateRequest | TicketTemplate | PRODUCT_CONFIGURE | setup | 1 | SVC-ORDER-ORDERS-1 | cache:idempotency, orders.ticket_template, orders.ticket_template_channel | cache:idempotency, orders.ticket_template, orders.ticket_template_channel | Create a ticket template
OrderService | orders | getBillingStatement | GET | /billing-statements/{statementId} |  | BillingStatement | ORDER_VIEW | core | 1 | SVC-ORDER-ORDERS-1 | ledger.tax_invoice_line, orders.payment, orders.sales_order, payments.dunning_case |  | One statement, with its lines
OrderService | orders | getGroupBooking | GET | /group-bookings/{groupBookingId} |  | GroupBooking | ORDER_VIEW | core | 1 | SVC-ORDER-ORDERS-2 | orders.group_booking, orders.sales_order, pii.subject |  | A group, its leader and its name-capture duty
OrderService | orders | getPaymentLink | GET | /payment-links/{token} |  | object | ORDER_VIEW | core | 1 | SVC-ORDER-ORDERS-2 | orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.payment_link, orders.reservation, orders.sales_order, platform.scope |  | What a guest holding a link is being asked to pay for
OrderService | orders | importTicketTemplate | POST | /ticket-templates/imports | TicketTemplateImportInput | TicketTemplate | PRODUCT_CONFIGURE | setup | 1 | SVC-ORDER-ORDERS-2 | orders.ticket_template, orders.ticket_template_channel | orders.ticket_template, orders.ticket_template_channel | Import a ticket template definition
OrderService | orders | issueWalletPass | POST | /wallet-passes |  | WalletPass | ORDER_VIEW | core | 1 | SVC-ORDER-ORDERS-2 | access.entitlement, cache:idempotency, orders.ticket_template, orders.wallet_pass | cache:idempotency, orders.wallet_pass | Generate an Apple or Google wallet pass
OrderService | orders | listBillingStatements | GET | /billing-statements |  | object | ORDER_VIEW | core | 1 | SVC-ORDER-ORDERS-3 | orders.payment, orders.sales_order, payments.dunning_case |  | What was charged, when, and against which agreement
OrderService | orders | listMyOrders | GET | /my/orders |  | object |  | core | 1 | SVC-ORDER-ORDERS-3 | orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.payment, orders.sales_order, pii.subject |  | The orders this guest placed
OrderService | orders | listPaymentTokens | GET | /payment-tokens |  | object | ORDER_VIEW | core | 1 | SVC-ORDER-ORDERS-3 | payments.token |  | A guest's saved payment methods
OrderService | orders | payByLink | POST | /payment-links/{token}/pay |  | object | ORDER_CREATE | core | 1 | SVC-ORDER-ORDERS-3 | cache:idempotency, orders.payment_link, orders.reservation, orders.sales_order, payments.provider | access.entitlement, cache:idempotency, orders.payment, orders.payment_link, orders.reservation, orders.sales_order, platform.outbox | Pay for a booking taken at a till
OrderService | orders | previewProductTickets | GET | /products/{productId}/ticket-previews |  | array of TicketProof | PRODUCT_VIEW | core | 1 | SVC-ORDER-ORDERS-4 |  |  | Preview a product's PDF ticket and wallet passes
OrderService | orders | recordGroupCheckIn | POST | /group-bookings/{groupBookingId}/check-in | GroupCheckInRequest | GroupVisitPlan | ORDER_MODIFY | core | 1 | SVC-ORDER-ORDERS-4 | orders.group_booking, orders.group_visit_plan | orders.group_visit_plan, orders.order_event | Record a group's arrival at the venue
OrderService | orders | reissueEntitlement | POST | /entitlements/{entitlementId}/reissue |  | ReissuedEntitlement | ORDER_EXCHANGE | core | 1 | SVC-ORDER-ORDERS-4 | access.entitlement, cache:idempotency, catalogue.product | access.entitlement, cache:idempotency, platform.outbox | Zero-value reissue of an expired entitlement for a later date
OrderService | orders | requestGroupBooking | POST | /group-booking-requests | GroupBookingRequest | GroupBooking |  | core | 1 | SVC-ORDER-ORDERS-4 | cache:idempotency, catalogue.group_package, catalogue.product, orders.group_booking | cache:idempotency, orders.group_booking, orders.sales_order | Ask for a school trip or a birthday party
OrderService | orders | setPaymentProvider | PUT | /payment-providers | SetPaymentProviderRequest | PaymentProvider | TENANT_CONFIGURE | setup | 1 | SVC-ORDER-ORDERS-5 | cache:idempotency, payments.provider | cache:idempotency, payments.provider, payments.routing_rule | Configure a gateway and its routing
OrderService | orders | shareEntitlement | POST | /entitlements/{entitlementId}/share |  | EntitlementShare | ORDER_MODIFY | core | 1 | SVC-ORDER-ORDERS-5 | access.entitlement, cache:idempotency, catalogue.entitlement_template, identity.delegated_access | access.entitlement, cache:idempotency, identity.delegated_access, platform.outbox | Let somebody else use this, without giving it away
OrderService | orders | storePaymentToken | POST | /payment-tokens |  | PaymentToken | ORDER_CREATE | core | 1 | SVC-ORDER-ORDERS-5 | cache:idempotency, marketing.consent_record, payments.provider, payments.token | cache:idempotency, marketing.consent_record, payments.token, platform.outbox | Save a payment method for future use
OrderService | orders | updateTicketTemplate | PATCH | /ticket-templates/{templateId} | TicketTemplateRequest | TicketTemplate | PRODUCT_CONFIGURE | setup | 1 | SVC-ORDER-ORDERS-5 | cache:idempotency, orders.ticket_template, orders.ticket_template_channel | cache:idempotency, orders.ticket_template | Change or retire a ticket template
OrderService | payment | addTip | POST | /payments/{paymentId}/tip |  | Payment | ORDER_MODIFY | core | 1 | SVC-ORDER-PAYMENT-1 | cache:idempotency, orders.payment | cache:idempotency, orders.payment | Record a tip against a payment
OrderService | payment | capturePayment | POST | /payments/{paymentId}/capture |  | Payment | ORDER_CREATE | core | 1 | SVC-ORDER-PAYMENT-1 | ledger.fx_rate, orders.payment, payments.provider_connection | cache:idempotency, catalogue.channel_capacity, catalogue.inventory_reservation, ledger.journal_entry, ledger.journal_line, orders.order_event, orders.payment, payments.payment_attempt, platform.idempotency_record, platform.outbox | Capture a previously authorised payment
OrderService | payment | createPayment | POST | /payments | CreatePaymentRequest | Payment | ORDER_CREATE | core | 1 | SVC-ORDER-PAYMENT-1 | catalogue.inventory_reservation, ledger.fx_rate, orders.order_line, orders.payment, orders.sales_order, payments.provider_connection | cache:idempotency, catalogue.channel_capacity, catalogue.inventory_reservation, ledger.journal_entry, ledger.journal_line, orders.order_event, orders.payment, payments.payment_attempt, platform.idempotency_record, platform.outbox | Take a payment against an order
OrderService | payment | inquirePaymentStatus | POST | /payments/{paymentId}/inquiry |  | Payment | ORDER_CREATE | core | 1 | SVC-ORDER-PAYMENT-1 | cache:idempotency, orders.payment | cache:idempotency, orders.payment, platform.outbox | Ask the provider what actually happened
OrderService | payments | createInstalmentPlan | POST | /instalment-plans |  | PayInstalmentPlan | ORDER_CREATE | core | 1 | SVC-ORDER-PAYMENTS-1 | cache:idempotency, orders.payment, orders.sales_order, payments.instalment, payments.instalment_plan, payments.instalment_policy, payments.token | cache:idempotency, orders.payment, payments.instalment, payments.instalment_plan, platform.outbox | Split an order's payment into scheduled instalments on a stored card
OrderService | payments | createPaymentProviderConnection | POST | /payment-providers | PaymentProviderConnection | PaymentProviderConnection | PAYMENT_PROVIDER_MANAGE | setup | 1 | SVC-ORDER-PAYMENTS-1 | payments.provider_connection | payments.provider_connection | Connect a provider
OrderService | payments | listInstalmentPlans | GET | /instalment-plans |  | object | PAYMENT_VIEW | core | 1 | SVC-ORDER-PAYMENTS-1 | payments.instalment, payments.instalment_plan |  | Instalment plans and their schedules
OrderService | payments | setDunningPolicy | PUT | /dunning-policy | DunningPolicy | DunningPolicy | PAYMENT_CONFIGURE | setup | 1 | SVC-ORDER-PAYMENTS-1 | payments.dunning_policy | payments.dunning_policy | Set the retry schedule and what happens when it runs out
OrderService | payments | setInstalmentPolicy | PUT | /instalment-policy | PayInstalmentPolicy | PayInstalmentPolicy | PAYMENT_CONFIGURE | setup | 1 | SVC-ORDER-PAYMENTS-2 | cache:idempotency, payments.instalment_policy | cache:idempotency, cache:resolution, payments.instalment_policy | Set which products may be paid in instalments, how many and how often
OrderService | policy | setRefundPolicy | PUT | /venues/{venueId}/refund-policy | RefundPolicy | RefundPolicy | REGION_CONFIGURE | setup | 1 | SVC-ORDER-POLICY-1 | cache:idempotency, orders.refund_policy, orders.refund_policy_time_band | cache:idempotency, cache:resolution, orders.refund_policy, orders.refund_policy_time_band | Set a venue's refund policy
OrderService | refund | createRefund | POST | /orders/{orderId}/refunds | CreateRefundRequest | Refund | ORDER_REFUND | core | 1 | SVC-ORDER-REFUND-1 | cache:idempotency, orders.fraud_rule, orders.payment, orders.refund, orders.sales_order | cache:idempotency, ledger.journal_entry, ledger.posting, orders.order_event, orders.refund, platform.outbox | Refund an order, wholly or in part
OrderService | refund | createRefundRequest | POST | /refund-requests |  | object |  | core | 1 | SVC-ORDER-REFUND-1 | cache:idempotency, orders.fraud_rule, orders.refund_policy, orders.sales_order | cache:idempotency, orders.refund | Guest-initiated refund request
OrderService | refund | listOrderRefunds | GET | /orders/{orderId}/refunds |  | object | ORDER_VIEW | core | 1 | SVC-ORDER-REFUND-1 | orders.refund |  | List refunds against an order
OrderService | reservation | cancelReservation | DELETE | /reservations/{reservationId} |  |  | ORDER_CANCEL | core | 1 | SVC-ORDER-RESERVATION-1 | cache:idempotency, orders.reservation | cache:idempotency, orders.order_event, orders.reservation | Cancel a reservation
OrderService | reservation | convertReservation | POST | /reservations/{reservationId}/convert |  | Order | ORDER_CREATE | core | 1 | SVC-ORDER-RESERVATION-1 | cache:idempotency, orders.order_line, orders.order_line_discount, orders.order_line_eligibility, orders.payment, orders.sales_order | cache:idempotency, orders.order_event, orders.order_line, orders.payment, orders.sales_order, promotions.promotion_evaluation_trace | Convert a reservation into an order
OrderService | reservation | createReservation | POST | /reservations | CreateReservationRequest | Reservation | ORDER_CREATE | core | 1 | SVC-ORDER-RESERVATION-1 | cache:idempotency, orders.reservation, orders.reservation_line | cache:idempotency, orders.order_event, orders.reservation, orders.reservation_line | Hold without payment
OrderService | reservation | extendReservation | POST | /reservations/{reservationId}/extend |  | Reservation | ORDER_CREATE | core | 1 | SVC-ORDER-RESERVATION-1 | cache:idempotency, orders.reservation, orders.reservation_line | cache:idempotency, orders.order_event, orders.reservation | Extend a reservation
OrderService | reservation | getReservation | GET | /reservations/{reservationId} |  | Reservation | ORDER_VIEW | core | 1 | SVC-ORDER-RESERVATION-2 | orders.reservation, orders.reservation_line |  | Read a reservation
OrderService | reservation | listReservations | GET | /reservations |  | object | ORDER_VIEW | core | 1 | SVC-ORDER-RESERVATION-2 | orders.reservation, orders.reservation_line |  | List reservations
OrderService | shift | acceptShiftVariance | POST | /shifts/{shiftId}/accept-variance |  | Shift | OVERSHORT_ACCEPT | core | 1 | SVC-ORDER-SHIFT-1 | cache:idempotency, orders.deposit_box, orders.pos_shift, orders.pos_shift_approval, orders.pos_shift_incident | cache:idempotency, orders.deposit_box, orders.pos_shift, platform.outbox | Accept an over/short beyond the threshold
OrderService | shift | allocateDepositBox | POST | /deposit-boxes | DepositBox | DepositBox | SHIFT_OPEN | core | 1 | SVC-ORDER-SHIFT-1 | cache:idempotency, identity.principal, orders.deposit_box, orders.deposit_box_foreign_holding, orders.deposit_box_opening_denomination, platform.workstation | cache:idempotency, orders.cash_movement, orders.deposit_box, orders.deposit_box_foreign_holding, orders.deposit_box_opening_denomination | Give a cashier a box and a float
OrderService | shift | approveShiftOpen | POST | /shifts/{shiftId}/approve-open |  | Shift | SHIFT_APPROVE_OPEN | core | 1 | SVC-ORDER-SHIFT-1 | cache:idempotency, orders.pos_shift, orders.pos_shift_approval, orders.pos_shift_incident | cache:idempotency, orders.pos_shift | Approve a shift opening outside tolerance
OrderService | shift | closeShift | POST | /shifts/{shiftId}/close |  | ShiftCloseResult | SHIFT_CLOSE | core | 1 | SVC-ORDER-SHIFT-1 | cache:idempotency, ledger.fx_rate, orders.cash_count_line, orders.cash_movement, orders.payment, orders.pos_shift, orders.pos_shift_approval, orders.pos_shift_incident, platform.venue_settings | cache:idempotency, ledger.journal_entry, orders.cash_count_line, orders.pos_shift, platform.outbox | Blind close-out
OrderService | shift | getCurrentShift | GET | /shifts/current |  | Shift | SHIFT_OPEN | core | 1 | SVC-ORDER-SHIFT-2 | orders.pos_shift, orders.pos_shift_approval, orders.pos_shift_incident |  | The open or suspended shift on the session's workstation
OrderService | shift | getShiftCountLines | GET | /shifts/{shiftId}/count-lines |  | object | REPORT_VIEW_WORKSTATION | core | 1 | SVC-ORDER-SHIFT-2 | orders.cash_count_line |  | The denomination breakdown of a shift's counts
OrderService | shift | getTillShiftPolicy | GET | /venues/{venueId}/till-shift-policy |  | TillShiftPolicy | SCOPE_VIEW | core | 1 | SVC-ORDER-SHIFT-2 | orders.till_shift_policy |  | The rules every till in the venue opens and closes to
OrderService | shift | getWorkstationShift | GET | /shifts/current/overview |  | Shift | REPORT_VIEW_WORKSTATION | core | 1 | SVC-ORDER-SHIFT-2 | orders.pos_shift, orders.pos_shift_approval, orders.pos_shift_incident |  | Read the open or suspended shift on the session's workstation, without the right to open one
OrderService | shift | giveShiftVarianceReason | POST | /shifts/{shiftId}/variance-reason | ShiftVarianceReasonRequest | ShiftCountReceipt | SHIFT_CLOSE | core | 1 | SVC-ORDER-SHIFT-3 |  | orders.pos_shift, platform.outbox | Give the reason for a difference within the threshold, and close the shift
OrderService | shift | listDenominations | GET | /denominations |  | array of Denomination | SHIFT_OPEN | core | 1 | SVC-ORDER-SHIFT-3 | platform.denomination, platform.region_settings |  | The notes and coins a till counts
OrderService | shift | listDepositBoxes | GET | /deposit-boxes |  | object | SHIFT_OPEN | core | 1 | SVC-ORDER-SHIFT-3 | identity.principal, orders.deposit_box, orders.deposit_box_foreign_holding, orders.deposit_box_opening_denomination |  | Cash boxes and who holds them
OrderService | shift | listShifts | GET | /shifts |  | object | REPORT_VIEW_WORKSTATION | core | 1 | SVC-ORDER-SHIFT-3 | orders.pos_shift, orders.pos_shift_approval, orders.pos_shift_incident |  | List shifts
OrderService | shift | openShift | POST | /shifts | OpenShiftRequest | Shift | SHIFT_OPEN | core | 1 | SVC-ORDER-SHIFT-4 | cache:idempotency, identity.principal, orders.cash_count_line, orders.pos_shift, orders.pos_shift_approval, orders.pos_shift_incident, platform.venue_settings, platform.workstation | cache:idempotency, orders.cash_count_line, orders.pos_shift, orders.pos_shift_approval, orders.pos_shift_incident | Open a shift
OrderService | shift | recordNoSale | POST | /shifts/{shiftId}/no-sale |  | NoSaleEvent | CASH_NO_SALE | core | 1 | SVC-ORDER-SHIFT-4 | cache:idempotency, orders.no_sale_event | cache:idempotency, orders.no_sale_event | Open the Deposit Box without a sale
OrderService | shift | rejectShiftVariance | POST | /shifts/{shiftId}/reject-variance |  | Shift | OVERSHORT_ACCEPT | core | 1 | SVC-ORDER-SHIFT-4 | orders.pos_shift, orders.pos_shift_approval, orders.pos_shift_incident | orders.pos_shift, orders.pos_shift_incident | Send a counted shift back for a recount
OrderService | shift | reopenShift | POST | /shifts/{shiftId}/reopen |  | Shift | SHIFT_REOPEN | core | 1 | SVC-ORDER-SHIFT-4 | cache:idempotency, orders.pos_shift, orders.pos_shift_approval, orders.pos_shift_incident | cache:idempotency, orders.pos_shift | Reopen a shift closed in error
OrderService | shift | resumeShift | POST | /shifts/{shiftId}/resume |  | Shift | SHIFT_OPEN | core | 1 | SVC-ORDER-SHIFT-5 | cache:idempotency, orders.pos_shift, orders.pos_shift_approval, orders.pos_shift_incident | cache:idempotency, orders.pos_shift | Resume a suspended shift
OrderService | shift | setDenominations | PUT | /denominations | SetDenominationsRequest | array of Denomination | REGION_CONFIGURE | setup | 1 | SVC-ORDER-SHIFT-5 | cache:idempotency, platform.denomination | cache:idempotency, platform.denomination | Set the notes and coins a region's tills count
OrderService | shift | setTillShiftPolicy | PUT | /venues/{venueId}/till-shift-policy | TillShiftPolicy | TillShiftPolicy | WORKSTATION_CONFIGURE | core | 1 | SVC-ORDER-SHIFT-5 | orders.till_shift_policy | orders.till_shift_policy | Set the rules every till in the venue opens and closes to
OrderService | shift | submitShiftCount | POST | /shifts/{shiftId}/count | CloseShiftRequest | ShiftCountReceipt | SHIFT_CLOSE | core | 1 | SVC-ORDER-SHIFT-5 | cache:idempotency, ledger.fx_rate, orders.cash_count_line, orders.cash_movement, orders.payment, orders.pos_shift, orders.pos_shift_approval, orders.pos_shift_incident, platform.venue_settings | cache:idempotency, ledger.journal_entry, orders.cash_count_line, orders.pos_shift, platform.outbox | The cashier's blind count, closing their own shift
OrderService | shift | suspendShift | POST | /shifts/{shiftId}/suspend |  | Shift | SHIFT_SUSPEND | core | 1 | SVC-ORDER-SHIFT-6 | cache:idempotency, orders.pos_shift, orders.pos_shift_approval, orders.pos_shift_incident | cache:idempotency, orders.pos_shift | Suspend a shift so another user can log in
OrderService | shift | withdrawFromDepositBox | POST | /deposit-boxes/{boxId}/withdraw |  | DepositBox | CASH_LIFT | core | 1 | SVC-ORDER-SHIFT-6 | cache:idempotency, orders.deposit_box, orders.deposit_box_foreign_holding, orders.deposit_box_opening_denomination | cache:idempotency, orders.cash_movement, orders.deposit_box, orders.deposit_box_foreign_holding, orders.deposit_box_opening_denomination | A supervisor takes cash out mid-shift
OrderService | sync | listSyncRejections | GET | /sync/rejections |  | object | ORDER_VIEW | core | 1 | SVC-ORDER-SYNC-1 | sync.rejection |  | Entries the server refused
OrderService | sync | syncOrders | POST | /sync/orders |  | OrderSyncResult | ORDER_CREATE | core | 1 | SVC-ORDER-SYNC-1 | catalogue.inventory_reservation, catalogue.price_list, catalogue.variant, orders.sales_order | catalogue.channel_capacity, catalogue.inventory_reservation, ledger.price_variance, orders.order_line, orders.order_line_discount, orders.payment, orders.sales_order, platform.idempotency_record, platform.outbox, sync.rejection | Replay orders recorded offline
PlatformService | licensing | addLicenceAddOn | POST | /tenants/{tenantId}/licences/add-ons | LicenceAddOn | LicencePosition | PLATFORM_TENANT_MANAGE | setup | 1 | SVC-PLATFORM-LICENSING-1 | cache:idempotency, control.licence_add_on | cache:idempotency, control.licence_add_on, control.licence_add_on_limit | License a module outside the plan
PlatformService | licensing | getTenantLicences | GET | /tenants/{tenantId}/licences |  | LicencePosition | PLATFORM_TENANT_VIEW | core | 1 | SVC-PLATFORM-LICENSING-1 | control.licence_add_on, subscription.contract, subscription.plan |  | What a tenant is licensed to use
PlatformService | plan | createPlan | POST | /plans | CreatePlanRequest | Plan | PLATFORM_PLAN_MANAGE | setup | 1 | SVC-PLATFORM-PLAN-1 | cache:idempotency, control.tenant, subscription.plan, subscription.plan_limit, subscription.plan_module | cache:idempotency, subscription.plan, subscription.plan_limit, subscription.plan_module | Create a subscription plan
PlatformService | plan | createPlanVersion | POST | /plans/{planId} | CreatePlanRequest | Plan | PLATFORM_PLAN_MANAGE | setup | 1 | SVC-PLATFORM-PLAN-1 | cache:idempotency, control.tenant, subscription.plan, subscription.plan_limit, subscription.plan_module | cache:idempotency, subscription.plan, subscription.plan_limit, subscription.plan_module | Publish a new version of a plan
PlatformService | publicApi | certifyIntegration | POST | /listings/{listingId}/certify |  | IntegrationListing | DEVELOPER_ADMIN | setup | 1 | SVC-PLATFORM-PUBLICAPI-1 | cache:idempotency, control.api_version, control.integration_listing | cache:idempotency, control.integration_listing | Approve, reject or revoke a certification
PlatformService | publicApi | createApiClient | POST | /api-clients | ApiClient | object | DEVELOPER_MANAGE | setup | 1 | SVC-PLATFORM-PUBLICAPI-1 | cache:idempotency, control.api_client, control.api_licence, control.developer_account, control.integration_listing | cache:idempotency, control.api_client | Create a client with scopes and an environment
PlatformService | publicApi | decideProductionAccess | POST | /production-access-requests/{requestId}/decide |  | ProductionAccessRequest | DEVELOPER_ADMIN | setup | 1 | SVC-PLATFORM-PUBLICAPI-1 | cache:idempotency, control.integration_listing, control.production_access_request | cache:idempotency, control.api_client, control.production_access_request | Approve or reject production access
PlatformService | publicApi | deprecateApiVersion | POST | /api-versions/{version}/deprecate |  | ApiVersion | DEVELOPER_ADMIN | setup | 1 | SVC-PLATFORM-PUBLICAPI-1 | cache:idempotency, control.api_client, control.api_version | cache:idempotency, control.api_version, marketing.message_dispatch | Announce a sunset date and notify subscribers
PlatformService | publicApi | registerDeveloper | POST | /developers | DeveloperAccount | DeveloperAccount | DEVELOPER_VIEW | setup | 1 | SVC-PLATFORM-PUBLICAPI-2 | cache:idempotency, control.developer_account | cache:idempotency, control.developer_account | Register a developer or organisation
PlatformService | publicApi | rotateApiCredential | POST | /api-clients/{clientId}/credentials |  | object | DEVELOPER_MANAGE | setup | 1 | SVC-PLATFORM-PUBLICAPI-2 | cache:idempotency, control.api_client | cache:idempotency, control.api_client | Issue a new secret, with an overlap window
PlatformService | publicApi | setApiClientStatus | POST | /api-clients/{clientId}/status |  | ApiClient | DEVELOPER_MANAGE | setup | 1 | SVC-PLATFORM-PUBLICAPI-2 | control.api_client | control.api_client | Suspend or reactivate an integration, reversibly
PlatformService | publicApi | setApiLicensing | PUT | /api-licensing | ApiLicence | ApiLicence | DEVELOPER_ADMIN | setup | 1 | SVC-PLATFORM-PUBLICAPI-2 | cache:idempotency, control.api_licence | cache:idempotency, cache:resolution, control.api_licence | Which API modules a tenant has licensed, and on what terms
PlatformService | publicApi | setDeveloperMembers | PUT | /developers/{developerId}/members |  | array of DeveloperMember | DEVELOPER_MANAGE | setup | 1 | SVC-PLATFORM-PUBLICAPI-3 | cache:idempotency, control.developer_account, control.developer_member | cache:idempotency, control.developer_account, control.developer_member | Who at this organisation may do what
PlatformService | subscription | listModuleCatalogue | GET | /module-catalogue |  | array of ModuleListing | PLATFORM_PLAN_MANAGE | core | 1 | SVC-PLATFORM-SUBSCRIPTION-1 | subscription.module_listing |  | Modules, their dependencies and their commercial treatment
PlatformService | subscription | setModuleListing | PUT | /module-catalogue | ModuleListing | ModuleListing | PLATFORM_PLAN_MANAGE | setup | 1 | SVC-PLATFORM-SUBSCRIPTION-1 | subscription.module_listing | subscription.module_listing | Define a module's dependencies, incompatibilities and price
PlatformService | subscription | setSubscription | PUT | /tenants/{tenantId}/subscription | SetSubscriptionRequest | Subscription | PLATFORM_TENANT_MANAGE | setup | 1 | SVC-PLATFORM-SUBSCRIPTION-1 | cache:idempotency, subscription.contract, subscription.plan | cache:idempotency, subscription.contract | Assign or change a subscription
PlatformService | tenant | createTenant | POST | /tenants | CreateTenantRequest | Tenant | PLATFORM_TENANT_MANAGE | setup | 1 | SVC-PLATFORM-TENANT-1 | cache:idempotency, control.tenant | cache:idempotency, control.tenant | Create a tenant
PlatformService | tenant | listTenants | GET | /tenants |  | object | PLATFORM_TENANT_VIEW | core | 1 | SVC-PLATFORM-TENANT-1 | control.tenant |  | List tenants
PlatformService | tenant | reactivateTenant | POST | /tenants/{tenantId}/reactivate |  | Tenant | PLATFORM_TENANT_MANAGE | setup | 1 | SVC-PLATFORM-TENANT-1 | cache:idempotency, control.tenant | cache:idempotency, control.tenant | Lift a suspension
PlatformService | tenant | suspendTenant | POST | /tenants/{tenantId}/suspend |  | Tenant | PLATFORM_TENANT_MANAGE | setup | 1 | SVC-PLATFORM-TENANT-1 | cache:idempotency, control.tenant | cache:idempotency, control.tenant, platform.outbox | Suspend a tenant
PlatformService | tenant | terminateTenant | POST | /tenants/{tenantId}/terminate |  | TerminationSchedule | PLATFORM_TENANT_TERMINATE | setup | 1 | SVC-PLATFORM-TENANT-2 | cache:idempotency, control.tenant, subscription.contract | cache:idempotency, control.tenant, subscription.contract | Begin termination
PlatformService | tenant | updateTenant | PATCH | /tenants/{tenantId} |  | Tenant | PLATFORM_TENANT_MANAGE | setup | 1 | SVC-PLATFORM-TENANT-2 | cache:idempotency, control.tenant | cache:idempotency, control.tenant | Amend tenant details
ReportingService | catalogue | createReport | POST | /reports | CreateReportRequest | ReportDefinition | REPORT_MANAGE | setup | 1 | SVC-REPORTING-CATALOGUE-1 | cache:idempotency, reporting.report_column, reporting.report_definition, reporting.report_filter, reporting.report_parameter | cache:idempotency, reporting.report_column, reporting.report_definition, reporting.report_definition_version, reporting.report_filter, reporting.report_parameter | Create a custom report definition
ReportingService | catalogue | deleteReport | DELETE | /reports/{reportId} |  |  | REPORT_MANAGE | setup | 1 | SVC-REPORTING-CATALOGUE-1 | cache:idempotency, reporting.report_definition | cache:idempotency, reporting.report_definition | Retire a report definition
ReportingService | catalogue | getReport | GET | /reports/{reportId} |  | ReportDefinition | REPORT_VIEW_VENUE | core | 1 | SVC-REPORTING-CATALOGUE-1 | reporting.report_column, reporting.report_definition, reporting.report_definition_version, reporting.report_filter, reporting.report_parameter |  | Read a report definition
ReportingService | catalogue | listReports | GET | /reports |  | object | REPORT_VIEW_VENUE | core | 1 | SVC-REPORTING-CATALOGUE-1 | reporting.report_column, reporting.report_definition, reporting.report_filter, reporting.report_parameter |  | List available report definitions
ReportingService | catalogue | updateReport | PUT | /reports/{reportId} | CreateReportRequest | ReportDefinition | REPORT_MANAGE | setup | 1 | SVC-REPORTING-CATALOGUE-2 | cache:idempotency, reporting.report_column, reporting.report_definition, reporting.report_filter, reporting.report_parameter | cache:idempotency, reporting.report_column, reporting.report_definition, reporting.report_definition_version, reporting.report_filter, reporting.report_parameter | Publish a new version of a definition
ReportingService | dashboard | createDashboard | POST | /dashboards | CreateDashboardRequest | Dashboard | REPORT_MANAGE | setup | 1 | SVC-REPORTING-DASHBOARD-1 | cache:idempotency, reporting.dashboard, reporting.dashboard_tile | cache:idempotency, reporting.dashboard, reporting.dashboard_tile | Create a dashboard
ReportingService | dashboard | getDashboard | GET | /dashboards/{dashboardId} |  | DashboardData | REPORT_VIEW_VENUE | core | 1 | SVC-REPORTING-DASHBOARD-1 | reporting.dashboard, reporting.dashboard_tile |  | Read a dashboard with tile data
ReportingService | dashboard | listDashboards | GET | /dashboards |  | array of Dashboard | REPORT_VIEW_VENUE | core | 1 | SVC-REPORTING-DASHBOARD-1 | reporting.dashboard, reporting.dashboard_tile |  | List dashboards
ReportingService | dashboard | recordDashboardView | POST | /dashboards/{dashboardId}/views |  |  | REPORT_VIEW_VENUE | core | 1 | SVC-REPORTING-DASHBOARD-1 | cache:idempotency, reporting.dashboard | cache:idempotency, reporting.dashboard_view | Record that a dashboard was opened
ReportingService | dashboard | updateDashboard | PUT | /dashboards/{dashboardId} | CreateDashboardRequest | Dashboard | REPORT_MANAGE | setup | 1 | SVC-REPORTING-DASHBOARD-2 | cache:idempotency, reporting.dashboard, reporting.dashboard_tile | cache:idempotency, reporting.dashboard, reporting.dashboard_tile | Update a dashboard
ReportingService | execution | runReport | POST | /reports/{reportId}/run | RunReportRequest | ReportResult | REPORT_VIEW_VENUE | core | 1 | SVC-REPORTING-EXECUTION-1 | cache:idempotency, reporting.execution, reporting.report_definition, reporting.report_parameter | cache:idempotency, reporting.execution | Run a report
ReportingService | naturalLanguage | askReportingQuestion | POST | /reports/ask |  | NaturalLanguageAnswer | REPORT_VIEW_VENUE | core | 1 | SVC-REPORTING-NATURALLANGUAGE-1 | ai.policy, ai.provider, cache:idempotency, reporting.kpi_definition, reporting.natural_language_query, reporting.report_column, reporting.report_filter, reporting.semantic_model | ai.activity, cache:idempotency, platform.outbox, reporting.natural_language_query, reporting.report_column, reporting.report_filter | Natural-language reporting query
ReportingService | naturalLanguage | saveNaturalLanguageQuery | POST | /reports/ask/{conversationId}/save |  | ReportDefinition | REPORT_MANAGE | setup | 1 | SVC-REPORTING-NATURALLANGUAGE-1 | ai.policy, ai.provider, cache:idempotency, reporting.report_column, reporting.report_definition, reporting.report_filter, reporting.report_parameter | ai.activity, cache:idempotency, platform.outbox, reporting.natural_language_query, reporting.report_column, reporting.report_definition, reporting.report_filter, reporting.report_parameter | Save a natural-language answer as a report definition
ReportingService | reporting | createKpi | POST | /kpis | KpiDefinition | KpiDefinition | REPORT_MANAGE | setup | 1 | SVC-REPORTING-REPORTING-1 | reporting.kpi_definition | reporting.kpi_definition | Define a KPI once, for everywhere
ReportingService | reporting | deleteDashboard | DELETE | /dashboards/{dashboardId} |  |  | REPORT_MANAGE | setup | 1 | SVC-REPORTING-REPORTING-1 | cache:idempotency, reporting.dashboard, reporting.dashboard_tile | cache:idempotency, reporting.dashboard | Archive a dashboard
ReportingService | reporting | listAlerts | GET | /alerts |  | array of Alert | REPORT_VIEW_VENUE | core | 1 | SVC-REPORTING-REPORTING-1 | reporting.alert, reporting.alert_rule |  | What is currently wrong
ReportingService | reporting | setAlertRule | PUT | /alert-rules | AlertRule | AlertRule | REPORT_MANAGE | setup | 1 | SVC-REPORTING-REPORTING-1 | cache:idempotency, identity.role, reporting.alert_rule | cache:idempotency, reporting.alert_rule | Watch a metric and tell somebody
ReportingService | reporting | setSemanticModel | PUT | /semantic-model | SemanticModel | SemanticModel | REPORT_MANAGE | setup | 1 | SVC-REPORTING-REPORTING-2 | reporting.semantic_model | reporting.semantic_model | Publish the catalogue
RetailService | floor | collectShopAndDrop | POST | /shop-and-drop/{dropId}/collect |  | ShopAndDrop | ORDER_MODIFY | core | 1 | SVC-RETAIL-FLOOR-1 | cache:idempotency, retail.shop_and_drop, retail.shop_and_drop_line | cache:idempotency, retail.shop_and_drop | Hand the goods over
RetailService | floor | createShopAndDrop | POST | /shop-and-drop |  | ShopAndDrop | ORDER_CREATE | core | 1 | SVC-RETAIL-FLOOR-1 | cache:idempotency, retail.shop_and_drop, retail.shop_and_drop_line | cache:idempotency, retail.shop_and_drop, retail.shop_and_drop_line | Buy now, collect on the way out
RetailService | floor | lookupMerchandise | GET | /merchandise/lookup |  | PriceCheck | PRODUCT_VIEW | core | 1 | SVC-RETAIL-FLOOR-1 | retail.merchandise |  | Price and stock check by barcode
RetailService | floor | lookupShopAndDrop | GET | /shop-and-drop/lookup |  | array of ShopAndDrop | ORDER_VIEW | core | 1 | SVC-RETAIL-FLOOR-1 | retail.shop_and_drop, retail.shop_and_drop_line |  | Find a guest's dropped goods
RetailService | floor | reserveMerchandise | POST | /outlets/{outletId}/reserve |  | MerchandiseReservation | ORDER_CREATE | core | 1 | SVC-RETAIL-FLOOR-2 | cache:idempotency, inventory.movement, inventory.stock_earmark, retail.reservation, retail.reservation_line | cache:idempotency, inventory.stock_earmark, retail.reservation, retail.reservation_line | Reserve an item for collection
RetailService | merchandise | createMerchandise | POST | /merchandise | CreateMerchandiseRequest | MerchandiseItem | PRODUCT_CONFIGURE | setup | 1 | SVC-RETAIL-MERCHANDISE-1 | cache:idempotency, retail.merchandise | cache:idempotency, retail.merchandise | Create a merchandise item
RetailService | merchandise | listMerchandise | GET | /merchandise |  | object | PRODUCT_VIEW | core | 1 | SVC-RETAIL-MERCHANDISE-1 | retail.merchandise |  | List merchandise
RetailService | merchandise | updateMerchandise | PATCH | /merchandise/{merchandiseId} |  | MerchandiseItem | PRODUCT_CONFIGURE | setup | 1 | SVC-RETAIL-MERCHANDISE-1 | cache:idempotency, retail.merchandise | cache:idempotency, retail.merchandise | Amend a merchandise item
RetailService | return | createRetailReturn | POST | /retail-returns | CreateRetailReturnRequest | RetailReturn | ORDER_REFUND | core | 1 | SVC-RETAIL-RETURN-1 | cache:idempotency, inventory.kit_component, retail.return, retail.return_line | cache:idempotency, inventory.movement, retail.return, retail.return_line | Accept a return
RetailService | return | getReturnPolicy | GET | /outlets/{outletId}/return-policy |  | ReturnPolicy | ORDER_VIEW | core | 1 | SVC-RETAIL-RETURN-1 | cache:resolution, retail.return_policy | cache:resolution | Read the retail return policy
RetailService | return | lookupRetailSale | GET | /retail-sales/lookup |  | object | ORDER_VIEW | core | 1 | SVC-RETAIL-RETURN-1 | retail.sale, retail.sale_line |  | Find a sale from a receipt
RetailService | return | setReturnPolicy | PUT | /outlets/{outletId}/return-policy | ReturnPolicy | ReturnPolicy | REGION_CONFIGURE | setup | 1 | SVC-RETAIL-RETURN-1 | cache:idempotency, retail.return_policy | cache:idempotency, cache:resolution, retail.return_policy | Set the retail return policy
RetailService | sale | createRetailSale | POST | /retail-sales | CreateRetailSaleRequest | RetailSale | ORDER_CREATE | core | 1 | SVC-RETAIL-SALE-1 | cache:idempotency, inventory.kit_component, retail.sale, retail.sale_line | cache:idempotency, inventory.movement, retail.sale, retail.sale_line | Sell merchandise
RetailService | sale | getRetailSale | GET | /retail-sales/{saleId} |  | RetailSale | ORDER_VIEW | core | 1 | SVC-RETAIL-SALE-1 | retail.sale, retail.sale_line |  | Read a retail sale
RetailService | sale | listRetailSales | GET | /retail-sales |  | object | ORDER_VIEW | core | 1 | SVC-RETAIL-SALE-1 | retail.sale, retail.sale_line |  | List retail sales
RetailService | sale | reprintReceipt | POST | /retail-sales/{saleId}/reprint |  | object | ORDER_REPRINT | core | 1 | SVC-RETAIL-SALE-1 | cache:idempotency, retail.sale | cache:idempotency, retail.sale | Reprint or resend a receipt
TenancyService | approvals | approveMatrixMultiLevel | PUT | /matrix-multi-level | ApprovalMatrixMultiLevelApprovalConfigurationInput | ApprovalMatrixMultiLevelApprovalConfigurationView | APPROVAL_CONFIGURE | setup | 1 | SVC-TENANCY-APPROVALS-1 | approvals.matrix, approvals.rule, cache:idempotency | approvals.matrix, approvals.rule, cache:idempotency | Approval Matrix & Multi-Level Approval Configuration
TenancyService | approvals | approveRoleAuthorityDelegation | PUT | /role-authority-delegation | RolesAuthorityDelegationApprovalLimitsInput | RolesAuthorityDelegationApprovalLimitsView | APPROVAL_CONFIGURE | setup | 1 | SVC-TENANCY-APPROVALS-1 | approvals.delegation, approvals.matrix, approvals.rule, cache:idempotency, identity.delegated_access, identity.principal | approvals.delegation, cache:idempotency | Roles, Authority, Delegation & Approval Limits
TenancyService | attendance | recordAttendance | POST | /attendance/clock |  | AttendanceRecord | ATTENDANCE_RECORD | core | 1 | SVC-TENANCY-ATTENDANCE-1 | access.access_point, cache:idempotency, workforce.attendance, workforce.attendance_amendment, workforce.rota_assignment | cache:idempotency, workforce.attendance | Clock in, clock out, or take a break
TenancyService | delegation | createApprovalDelegation | POST | /delegations | ApprovalDelegation | ApprovalDelegation | APPROVAL_DECIDE | setup | 1 | SVC-TENANCY-DELEGATION-1 | approvals.delegation, approvals.matrix, approvals.rule, cache:idempotency, identity.delegated_access, identity.principal | approvals.delegation, cache:idempotency | Delegate approval authority
TenancyService | devices | setDeviceAssignment | PUT | /devices/{deviceId}/assignment | DeviceAssignment | DeviceAssignment | DEVICE_MANAGE | core | 1 | SVC-TENANCY-DEVICES-1 | tenancy.device_assignment | tenancy.device_assignment | Who owns it, who holds it, and where it is
TenancyService | general | getDeviceAssignment | GET | /devices/{deviceId}/assignment |  | DeviceAssignment | DEVICE_VIEW | core | 1 | SVC-TENANCY-GENERAL-1 | tenancy.device_assignment |  | Where a device is assigned
TenancyService | identity | setRolePermissions | PUT | /roles/{roleId}/permissions |  | object | ROLE_MANAGE | setup | 1 | SVC-TENANCY-IDENTITY-1 | cache:idempotency, identity.role, identity.role_permission, identity.segregation_rule | cache:idempotency, cache:resolution, identity.role_permission, platform.audit_record | What this role may do
TenancyService | matrix | setApprovalExternalProvider | PUT | /approval-external-providers | ApprovalExternalProvider | ApprovalExternalProvider | APPROVAL_CONFIGURE | setup | 1 | SVC-TENANCY-MATRIX-1 | approvals.external_provider, cache:idempotency, control.api_client | approvals.external_provider, cache:idempotency | Register a third-party workflow system as an approver
TenancyService | matrix | setApprovalMatrix | PUT | /approval-matrices | ApprovalMatrix | ApprovalMatrix | APPROVAL_CONFIGURE | setup | 1 | SVC-TENANCY-MATRIX-1 | approvals.external_provider, approvals.matrix, approvals.rule, cache:idempotency | approvals.matrix, approvals.rule, cache:idempotency | Configure what requires approval
TenancyService | region | getRegionSettings | GET | /regions/{regionId}/settings |  | RegionSettings | SCOPE_VIEW | core | 1 | SVC-TENANCY-REGION-1 | cache:resolution, platform.region_settings | cache:resolution | Read region settings
TenancyService | region | updateRegionSettings | PUT | /regions/{regionId}/settings | RegionSettings | RegionSettings | REGION_CONFIGURE | setup | 1 | SVC-TENANCY-REGION-1 | cache:idempotency, platform.region_settings | cache:idempotency, cache:resolution, platform.region_settings | Update region settings
TenancyService | request | createApprovalRequest | POST | /approval-requests | CreateApprovalRequest | ApprovalRequest | APPROVAL_REQUEST | core | 1 | SVC-TENANCY-REQUEST-1 | approvals.decision, approvals.delegation, approvals.matrix, approvals.request, approvals.rule, cache:idempotency, identity.principal | approvals.request, cache:idempotency | Raise a request
TenancyService | request | decideApprovalRequest | POST | /approval-requests/{requestId}/decide |  | ApprovalRequest | APPROVAL_DECIDE | core | 1 | SVC-TENANCY-REQUEST-1 | approvals.decision, approvals.request, approvals.rule, cache:idempotency, identity.principal | approvals.decision, approvals.request, cache:idempotency, control.partner_agreement, control.partner_application, control.partner_change_request, marketing.privacy_notice_governance, platform.outbox | Approve, reject, return or ask for information
TenancyService | request | evaluateApprovalRequirement | POST | /approval-requests/evaluate |  | ApprovalRequirement | APPROVAL_VIEW | core | 1 | SVC-TENANCY-REQUEST-1 | approvals.delegation, approvals.matrix, approvals.rule, cache:idempotency, identity.delegated_access, platform.scope | cache:idempotency | Does this need approval, and from whom
TenancyService | request | listApprovalRequests | GET | /approval-requests |  | object | APPROVAL_VIEW | core | 1 | SVC-TENANCY-REQUEST-1 | approvals.decision, approvals.request |  | Requests awaiting a decision, or already decided
TenancyService | rota | createRotaAssignment | POST | /rota-assignments | RotaAssignment | RotaAssignment | WORKFORCE_MANAGE | setup | 1 | SVC-TENANCY-ROTA-1 | cache:idempotency, identity.delegated_access, identity.principal, platform.workstation, workforce.rota_assignment | cache:idempotency, workforce.rota_assignment | Put someone on the rota
TenancyService | rota | listRotaAssignments | GET | /rota-assignments |  | object | WORKFORCE_VIEW | core | 1 | SVC-TENANCY-ROTA-1 | identity.principal, workforce.rota_assignment |  | The rota
TenancyService | rota | updateRotaAssignment | PATCH | /rota-assignments/{assignmentId} | RotaAssignment | RotaAssignment | WORKFORCE_MANAGE | setup | 1 | SVC-TENANCY-ROTA-1 | cache:idempotency, workforce.rota_assignment | cache:idempotency, workforce.rota_assignment | Move or cancel an assignment
TenancyService | scope | createOrgUnit | POST | /org-units | CreateScopeNodeRequest | OrgUnit | SCOPE_MANAGE | setup | 1 | SVC-TENANCY-SCOPE-1 | cache:idempotency, platform.scope | cache:idempotency, cache:resolution, platform.scope | Create a scope node
TenancyService | scope | listOrgUnits | GET | /org-units |  | object | SCOPE_VIEW | core | 1 | SVC-TENANCY-SCOPE-1 | cache:resolution, platform.scope | cache:resolution | List scope nodes visible to the session
TenancyService | scope | updateOrgUnit | PATCH | /org-units/{orgUnitId} |  | OrgUnit | SCOPE_MANAGE | setup | 1 | SVC-TENANCY-SCOPE-1 | cache:idempotency, platform.scope | cache:idempotency, cache:resolution, platform.scope | Rename or deactivate a scope node
TenancyService | tenancy | getWorkstationHealth | GET | /workstations/{workstationId}/health |  | object | DEVICE_VIEW | core | 1 | SVC-TENANCY-TENANCY-1 | platform.device, platform.device_heartbeat, platform.workstation |  | A score a manager can sort by, and what is dragging it down
TenancyService | tenancy | setVenueSettings | PUT | /venues/{venueId}/settings | VenueSettings | VenueSettings | TENANT_CONFIGURE | setup | 1 | SVC-TENANCY-TENANCY-1 | access.access_point, cache:idempotency, platform.venue_settings | cache:idempotency, cache:resolution, platform.venue_settings | Set support hours, quiet hours, segregated access and alerting
TenancyService | tenancy | setVenueSettingsDefaults | PUT | /venue-settings-defaults | VenueSettings | VenueSettings | TENANT_CONFIGURE | setup | 1 | SVC-TENANCY-TENANCY-1 | platform.venue_settings | platform.venue_settings | Set the tenant's default for every venue setting
TenancyService | workstation | configureWorkstation | PUT | /workstations/{workstationId} | ConfigureWorkstationRequest | Workstation | WORKSTATION_CONFIGURE | core | 1 | SVC-TENANCY-WORKSTATION-1 | cache:idempotency, platform.device, platform.workstation | cache:idempotency, platform.device, platform.workstation | Configure a workstation
TenancyService | workstation | createOutlet | POST | /outlets | Outlet | Outlet | REGION_CONFIGURE | setup | 1 | SVC-TENANCY-WORKSTATION-1 | cache:idempotency, platform.outlet | cache:idempotency, platform.outlet | Create an outlet
TenancyService | workstation | createSaleBoard | POST | /sale-boards | SaleBoard | SaleBoard | WORKSTATION_CONFIGURE | setup | 1 | SVC-TENANCY-WORKSTATION-1 | cache:idempotency, platform.sale_board | cache:idempotency, platform.sale_board, platform.sale_board_page, platform.sale_board_tile | Create a sale board
TenancyService | workstation | getOutlet | GET | /outlets/{outletId} |  | Outlet | SCOPE_VIEW | core | 1 | SVC-TENANCY-WORKSTATION-1 | platform.outlet |  | Read an outlet
TenancyService | workstation | listDevices | GET | /devices |  | object | DEVICE_VIEW | core | 1 | SVC-TENANCY-WORKSTATION-2 | platform.device |  | List registered devices
TenancyService | workstation | listSaleBoards | GET | /sale-boards |  | array of SaleBoard | SCOPE_VIEW | core | 1 | SVC-TENANCY-WORKSTATION-2 | platform.sale_board, platform.sale_board_page, platform.sale_board_tile |  | List sale boards
TenancyService | workstation | updateOutlet | PATCH | /outlets/{outletId} |  | Outlet | REGION_CONFIGURE | setup | 1 | SVC-TENANCY-WORKSTATION-2 | cache:idempotency, platform.outlet | cache:idempotency, platform.outlet | Amend an outlet
TenancyService | workstation | updateSaleBoard | PUT | /sale-boards/{saleBoardId} | SaleBoard | SaleBoard | WORKSTATION_CONFIGURE | setup | 1 | SVC-TENANCY-WORKSTATION-2 | cache:idempotency, platform.sale_board | cache:idempotency, platform.sale_board, platform.sale_board_page, platform.sale_board_tile | Update a sale board
VenueOpsService | asset | deleteMediaAsset | DELETE | /media/{mediaId} |  |  | ASSET_LIBRARY_MANAGE | core | 1 | SVC-VENUEOPS-ASSET-1 | assets.media_usage, cache:idempotency | assets.media_usage, cache:idempotency | Delete an asset
VenueOpsService | asset | getMediaAsset | GET | /media/{mediaId} |  | MediaAssetDetail | ASSET_LIBRARY_VIEW | core | 1 | SVC-VENUEOPS-ASSET-1 | assets.media_asset, assets.media_usage |  | Read an asset with derivatives and usage
VenueOpsService | asset | replaceMediaAsset | POST | /media/{mediaId}/replace |  | MediaReplaceResult | ASSET_LIBRARY_MANAGE | core | 1 | SVC-VENUEOPS-ASSET-1 | assets.media_asset, cache:idempotency | assets.asset_version, assets.media_asset, assets.media_fingerprint, cache:idempotency | Replace the file behind an asset
VenueOpsService | asset | searchMedia | GET | /media |  | object | ASSET_LIBRARY_VIEW | core | 1 | SVC-VENUEOPS-ASSET-1 | assets.media_asset |  | Search the asset library
VenueOpsService | asset | updateMediaAsset | PATCH | /media/{mediaId} |  | MediaAsset | ASSET_LIBRARY_MANAGE | core | 1 | SVC-VENUEOPS-ASSET-2 | assets.media_asset, assets.media_collection, assets.media_usage, cache:idempotency | assets.media_asset, assets.media_collection_member, cache:idempotency | Amend metadata, tags or rights
VenueOpsService | card | getGameCard | GET | /game-cards/{cardCode} |  | GameCard |  | core | 1 | SVC-VENUEOPS-CARD-1 | games.card, games.credit_ledger |  | Read a card's balances
VenueOpsService | card | issueGameCard | POST | /game-cards | IssueGameCardRequest | GameCard | ORDER_CREATE | core | 1 | SVC-VENUEOPS-CARD-1 | cache:idempotency, games.card | cache:idempotency, games.card | Issue or activate a game card
VenueOpsService | collection | createCollection | POST | /media/collections |  | Collection | ASSET_LIBRARY_MANAGE | core | 1 | SVC-VENUEOPS-COLLECTION-1 | assets.media_collection, cache:idempotency | assets.media_collection, assets.media_collection_member, cache:idempotency | Create a collection
VenueOpsService | collection | listCollections | GET | /media/collections |  | array of Collection | ASSET_LIBRARY_VIEW | core | 1 | SVC-VENUEOPS-COLLECTION-1 | assets.media_collection, assets.media_collection_member |  | List collections
VenueOpsService | departure | getNextTransportDeparture | GET | /transport/departures/next |  | DepartureOffer |  | core | 1 | SVC-VENUEOPS-DEPARTURE-1 | catalogue.channel_capacity, transport.departure, transport.fare_matrix_cell, transport.fare_passenger_type, transport.fare_table, transport.route, transport.route_stop, transport.station, transport.timetable |  | Next Available Trip
VenueOpsService | departure | searchTransportDepartures | GET | /transport/departures |  | object |  | core | 1 | SVC-VENUEOPS-DEPARTURE-1 | catalogue.channel_capacity, transport.departure, transport.fare_matrix_cell, transport.fare_passenger_type, transport.fare_table, transport.route, transport.route_stop, transport.station, transport.timetable |  | Search Trips — departures between two stations on a date
VenueOpsService | departure | updateTransportDeparture | PATCH | /transport/departures/{departureId} |  | Departure | TRANSPORT_MANAGE | setup | 1 | SVC-VENUEOPS-DEPARTURE-1 | transport.departure | transport.departure | Change a departure's coach or capacity
VenueOpsService | entry | getWaitingGuest | GET | /waiting-guests/{entryId} |  | WaitingGuest |  | core | 1 | SVC-VENUEOPS-ENTRY-1 | queue.entry |  | Read a queue entry
VenueOpsService | entry | joinQueue | POST | /waiting-guests | JoinQueueRequest | WaitingGuest |  | core | 1 | SVC-VENUEOPS-ENTRY-1 | cache:idempotency, marketing.loyalty_position, promotions.promotion, queue.entry, queue.queue | cache:idempotency, queue.entry | Join a virtual queue
VenueOpsService | entry | leaveQueue | DELETE | /waiting-guests/{entryId} |  |  |  | core | 1 | SVC-VENUEOPS-ENTRY-1 | cache:idempotency, queue.entry | cache:idempotency, queue.entry | Leave a queue
VenueOpsService | fare | getTransportFareTable | GET | /transport/routes/{routeId}/fare-table |  | FareTable |  | core | 1 | SVC-VENUEOPS-FARE-1 | transport.fare_matrix_cell, transport.fare_passenger_type, transport.fare_table |  | A route's fares and passenger types
VenueOpsService | fare | quoteTransportFare | POST | /transport/fare-quotes | FareQuoteRequest | FareQuote |  | core | 1 | SVC-VENUEOPS-FARE-1 | transport.fare_matrix_cell, transport.fare_passenger_type, transport.fare_table, transport.pass_type, transport.route_stop |  | Price a one-way trip or a pass for a party
VenueOpsService | fare | setTransportFareTable | PUT | /transport/routes/{routeId}/fare-table | SetFareTableRequest | FareTable | TRANSPORT_PRICE | setup | 1 | SVC-VENUEOPS-FARE-1 | transport.fare_matrix_cell, transport.fare_passenger_type, transport.fare_table, transport.route | transport.fare_matrix_cell, transport.fare_passenger_type, transport.fare_table | Set a route's fares and passenger types
VenueOpsService | favourite | deleteFavouriteRoute | DELETE | /transport/favourite-routes/{favouriteId} |  |  |  | core | 1 | SVC-VENUEOPS-FAVOURITE-1 | cache:idempotency, transport.favourite_route | cache:idempotency, transport.favourite_route | Remove a saved route
VenueOpsService | favourite | listMyFavouriteRoutes | GET | /transport/favourite-routes |  | object |  | core | 1 | SVC-VENUEOPS-FAVOURITE-1 | transport.favourite_route |  | The caller's saved routes
VenueOpsService | favourite | saveFavouriteRoute | POST | /transport/favourite-routes |  | FavouriteRoute |  | core | 1 | SVC-VENUEOPS-FAVOURITE-1 | transport.favourite_route, transport.station | transport.favourite_route | Save route
VenueOpsService | general | getTransportDeparture | GET | /transport/departures/{departureId} |  | DepartureOffer |  | core | 1 | SVC-VENUEOPS-GENERAL-1 | catalogue.channel_capacity, transport.departure, transport.fare_matrix_cell, transport.fare_passenger_type, transport.fare_table, transport.route, transport.route_stop, transport.station, transport.timetable |  | One departure, as a guest books it
VenueOpsService | inspection | createInspectionTemplate | POST | /inspection-templates | InspectionTemplate | InspectionTemplate | INSPECTION_MANAGE | setup | 1 | SVC-VENUEOPS-INSPECTION-1 | cache:idempotency, maintenance.inspection_template, maintenance.inspection_template_item | cache:idempotency, maintenance.inspection_template, maintenance.inspection_template_item | Create an inspection template
VenueOpsService | networkImport | applyTransportNetworkImport | POST | /transport/network-imports/{importId}/apply |  | TransportNetworkImport | TRANSPORT_MANAGE | setup | 1 | SVC-VENUEOPS-NETWORKIMPORT-1 | transport.network_import | transport.fare_table, transport.route, transport.route_stop, transport.station, transport.timetable, transport.timetable_run | Apply a previewed import to the network
VenueOpsService | networkImport | importTransportNetwork | POST | /transport/network-imports | ImportTransportNetworkRequest | TransportNetworkImport | TRANSPORT_MANAGE | setup | 1 | SVC-VENUEOPS-NETWORKIMPORT-1 | transport.network_import | transport.network_import | Read a network file into a preview
VenueOpsService | pass | createTransportPassType | POST | /transport/pass-types | CreatePassTypeRequest | PassType | TRANSPORT_PRICE | setup | 1 | SVC-VENUEOPS-PASS-1 | transport.pass_type | transport.pass_type | Define a multi-trip or unlimited pass
VenueOpsService | pass | listTransportPassOffers | GET | /transport/pass-offers |  | object |  | core | 1 | SVC-VENUEOPS-PASS-1 | transport.fare_matrix_cell, transport.fare_table, transport.pass_type, transport.route, transport.route_stop |  | Multi-trip passes for a pair of stations, priced, with the saving
VenueOpsService | pass | updateTransportPassType | PATCH | /transport/pass-types/{passTypeId} |  | PassType | TRANSPORT_PRICE | setup | 1 | SVC-VENUEOPS-PASS-1 | transport.pass_type | transport.pass_type | Amend or retire a pass type
VenueOpsService | queue | createQueue | POST | /queues | CreateQueueRequest | Queue | QUEUE_MANAGE | setup | 1 | SVC-VENUEOPS-QUEUE-1 | cache:idempotency, queue.queue, queue.queue_operating_window | cache:idempotency, queue.queue, queue.queue_operating_window | Create a queue
VenueOpsService | queue | listQueues | GET | /queues |  | object | QUEUE_VIEW | core | 1 | SVC-VENUEOPS-QUEUE-1 | queue.queue, queue.queue_operating_window |  | List queues
VenueOpsService | queue | updateQueue | PATCH | /queues/{queueId} |  | Queue | QUEUE_MANAGE | setup | 1 | SVC-VENUEOPS-QUEUE-1 | cache:idempotency, queue.queue, queue.queue_operating_window | cache:idempotency, queue.queue | Amend queue configuration
VenueOpsService | resources | cloneResource | POST | /resources/{resourceId}/clone |  | array of Resource | RESOURCE_MANAGE | setup | 1 | SVC-VENUEOPS-RESOURCES-1 | resources.resource | resources.resource | Copy a resource and its configuration into new ones
VenueOpsService | resources | createResource | POST | /resources | Resource | Resource | RESOURCE_MANAGE | setup | 1 | SVC-VENUEOPS-RESOURCES-1 | cache:idempotency, resources.resource | cache:idempotency, resources.resource | Define a bookable resource
VenueOpsService | resources | createResourceBlock | POST | /resource-blocks | ResourceBlock | ResourceBlock | RESOURCE_MANAGE | setup | 1 | SVC-VENUEOPS-RESOURCES-1 | resources.resource_block | resources.resource_block | Take a resource out of service for a window, with a reason
VenueOpsService | resources | createResourceHold | POST | /resource-holds | CreateResourceHoldRequest | ResourceHold | ORDER_CREATE | core | 1 | SVC-VENUEOPS-RESOURCES-1 | resources.booking, resources.resource, resources.resource_block, resources.resource_reservation, venuemap.map, venuemap.placed_resource | resources.resource_reservation | Hold a specific resource picked on the map
VenueOpsService | resources | createResourcePackage | POST | /resource-packages | ResourcePackage | ResourcePackage | RESOURCE_CONFIGURE | setup | 1 | SVC-VENUEOPS-RESOURCES-2 | resources.resource_package, resources.resource_requirement | resources.resource_package, resources.resource_requirement | Define a reusable combination
VenueOpsService | resources | extendResourceHold | POST | /resource-holds/{holdId}/extend |  | ResourceHold | ORDER_CREATE | core | 1 | SVC-VENUEOPS-RESOURCES-2 | resources.resource_reservation | resources.resource_reservation | Extend a resource hold
VenueOpsService | resources | getMapResourceAvailability | GET | /resource-availability |  | MapResourceAvailability | RESOURCE_VIEW | core | 1 | SVC-VENUEOPS-RESOURCES-2 | maintenance.work_order, resources.booking, resources.resource, resources.resource_block, resources.resource_reservation, venuemap.map, venuemap.map_version, venuemap.placed_resource |  | Every bookable resource on a venue map, free or taken, in one call
VenueOpsService | resources | getResourceAvailability | GET | /resources/{resourceId}/availability |  | ResourceAvailability | RESOURCE_VIEW | core | 1 | SVC-VENUEOPS-RESOURCES-2 | maintenance.work_order, resources.booking, resources.resource, resources.resource_block, resources.resource_reservation |  | When it is free, with conflicts already resolved
VenueOpsService | resources | getResourceHold | GET | /resource-holds/{holdId} |  | ResourceHold | ORDER_VIEW | core | 1 | SVC-VENUEOPS-RESOURCES-3 | resources.resource_reservation |  | Read a resource hold
VenueOpsService | resources | listProductStartTimes | GET | /resource-start-times |  | object | RESOURCE_VIEW | core | 1 | SVC-VENUEOPS-RESOURCES-3 | resources.booking, resources.resource, resources.resource_block, resources.resource_reservation, resources.resource_requirement, resources.resource_schedule |  | Start times a space sold by the hour can be booked at, for one length on one day
VenueOpsService | resources | releaseResourceBlock | DELETE | /resource-blocks/{blockId} |  |  | RESOURCE_MANAGE | setup | 1 | SVC-VENUEOPS-RESOURCES-3 | cache:idempotency, resources.resource_block | cache:idempotency, resources.resource_block | Put it back into service
VenueOpsService | resources | relinquishResourceHold | DELETE | /resource-holds/{holdId} |  |  | ORDER_CREATE | core | 1 | SVC-VENUEOPS-RESOURCES-3 | cache:idempotency, resources.resource_reservation | cache:idempotency, resources.resource_reservation | Give up a resource hold
VenueOpsService | resources | setExperienceResourceRequirements | PUT | /experiences/{experienceId}/resource-requirements |  | array of ResourceRequirement | RESOURCE_CONFIGURE | setup | 1 | SVC-VENUEOPS-RESOURCES-4 | resources.resource_requirement | resources.resource_requirement | Bind resource requirements to an experience
VenueOpsService | resources | setResourceLifecycleState | POST | /resources/{resourceId}/state |  | Resource | RESOURCE_MANAGE | setup | 1 | SVC-VENUEOPS-RESOURCES-4 | resources.resource | resources.resource | Move a resource through its lifecycle, with a reason
VenueOpsService | resources | setResourceSchedule | PUT | /resources/{resourceId}/schedule | ResourceSchedule | ResourceSchedule | RESOURCE_CONFIGURE | setup | 1 | SVC-VENUEOPS-RESOURCES-4 | resources.resource_schedule | resources.resource_schedule | Operating hours, working pattern and bookable slots
VenueOpsService | resources | updateResource | PUT | /resources/{resourceId} | Resource | Resource | RESOURCE_MANAGE | setup | 1 | SVC-VENUEOPS-RESOURCES-4 | resources.resource | resources.resource | Change a resource
VenueOpsService | resources | updateResourcePackage | PUT | /resource-packages/{packageId} | ResourcePackage | ResourcePackage | RESOURCE_CONFIGURE | setup | 1 | SVC-VENUEOPS-RESOURCES-5 | resources.resource_package, resources.resource_requirement | resources.resource_package, resources.resource_requirement | Change a combination
VenueOpsService | rights | getExpiringRights | GET | /media/rights-expiring |  | array of ExpiringMedia | ASSET_LIBRARY_VIEW | core | 1 | SVC-VENUEOPS-RIGHTS-1 | assets.media_asset, assets.media_usage |  | Assets whose licence is expiring or expired
VenueOpsService | route | createTransportRoute | POST | /transport/routes | CreateTransportRouteRequest | TransportRoute | TRANSPORT_MANAGE | setup | 1 | SVC-VENUEOPS-ROUTE-1 | transport.route, transport.route_stop, transport.station | transport.route, transport.route_stop | Define a route with its ordered stops
VenueOpsService | route | getTransportRoute | GET | /transport/routes/{routeId} |  | TransportRoute |  | core | 1 | SVC-VENUEOPS-ROUTE-1 | transport.route, transport.route_stop, transport.station |  | A route with its stops
VenueOpsService | route | getTransportRouteMap | GET | /transport/routes/{routeId}/map |  | RouteMap |  | core | 1 | SVC-VENUEOPS-ROUTE-1 | transport.route, transport.route_stop, transport.station |  | The route drawn for a map, with the journey highlighted
VenueOpsService | route | listTransportRoutes | GET | /transport/routes |  | object |  | core | 1 | SVC-VENUEOPS-ROUTE-1 | transport.route, transport.route_stop, transport.station |  | Routes, optionally those serving a pair of stations
VenueOpsService | route | setTransportRouteStatus | PUT | /transport/routes/{routeId}/status |  | TransportRoute | TRANSPORT_MANAGE | setup | 1 | SVC-VENUEOPS-ROUTE-2 | transport.departure, transport.fare_table, transport.route, transport.route_stop, transport.station | transport.route | Activate, suspend or retire a route
VenueOpsService | route | updateTransportRoute | PATCH | /transport/routes/{routeId} |  | TransportRoute | TRANSPORT_MANAGE | setup | 1 | SVC-VENUEOPS-ROUTE-2 | transport.route, transport.route_stop, transport.station, transport.timetable | transport.route, transport.route_stop | Amend a route
VenueOpsService | station | createTransportStation | POST | /transport/stations | CreateStationRequest | Station | TRANSPORT_MANAGE | setup | 1 | SVC-VENUEOPS-STATION-1 | transport.station | transport.station | Add a station
VenueOpsService | station | listTransportStations | GET | /transport/stations |  | object |  | core | 1 | SVC-VENUEOPS-STATION-1 | transport.station |  | Stations of a venue's transport network
VenueOpsService | station | updateTransportStation | PATCH | /transport/stations/{stationId} |  | Station | TRANSPORT_MANAGE | setup | 1 | SVC-VENUEOPS-STATION-1 | transport.station | transport.station | Amend or deactivate a station
VenueOpsService | timetable | createTransportTimetable | POST | /transport/routes/{routeId}/timetables | CreateTimetableRequest | Timetable | TRANSPORT_MANAGE | setup | 1 | SVC-VENUEOPS-TIMETABLE-1 | transport.route, transport.timetable, transport.timetable_run | transport.timetable, transport.timetable_run | Draft a timetable for a route
VenueOpsService | timetable | publishTransportTimetable | POST | /transport/timetables/{timetableId}/publish |  | Timetable | TRANSPORT_MANAGE | setup | 1 | SVC-VENUEOPS-TIMETABLE-1 | transport.timetable, transport.timetable_run | transport.departure, transport.timetable | Publish a timetable and release its departures
VenueOpsService | timetable | withdrawTransportTimetable | POST | /transport/timetables/{timetableId}/withdraw |  | Timetable | TRANSPORT_MANAGE | setup | 1 | SVC-VENUEOPS-TIMETABLE-1 | transport.timetable, transport.timetable_run | transport.timetable | Withdraw a published timetable
VenueOpsService | upload | completeUpload | POST | /media/uploads/{uploadId}/complete |  | MediaAsset | ASSET_LIBRARY_MANAGE | core | 1 | SVC-VENUEOPS-UPLOAD-1 | assets.media_asset, assets.media_upload, cache:idempotency | assets.media_asset, assets.media_fingerprint, cache:idempotency | Confirm an upload and create the asset
VenueOpsService | upload | createUpload | POST | /media/uploads |  | UploadTicket | ASSET_LIBRARY_MANAGE | core | 1 | SVC-VENUEOPS-UPLOAD-1 | assets.media_upload, cache:idempotency | assets.media_upload, cache:idempotency | Request a signed upload URL
VenueOpsService | venueMap | createVenueMap | POST | /venue-maps | VenueMap | VenueMap | VENUE_MAP_MANAGE | setup | 1 | SVC-VENUEOPS-VENUEMAP-1 | assets.media_asset, cache:idempotency, platform.scope, venuemap.map | cache:idempotency, venuemap.map | Start a map
VenueOpsService | venueMap | getVenueMap | GET | /venue-maps/{mapId} |  | VenueMapDetail | VENUE_MAP_VIEW | core | 1 | SVC-VENUEOPS-VENUEMAP-1 | assets.media_asset, venuemap.map, venuemap.path, venuemap.placed_resource, venuemap.point |  | A map with its points and paths
VenueOpsService | venueMap | getVenueMapGraph | GET | /venue-maps/{mapId}/graph |  | VenueMapGraph | VENUE_MAP_VIEW | core | 1 | SVC-VENUEOPS-VENUEMAP-1 | cache:resolution, venuemap.map, venuemap.path, venuemap.point | cache:resolution | The navigation graph, ready to route over
VenueOpsService | venueMap | importVenueGeometry | POST | /venue-maps/{mapId}/import |  | VenueMapImportJob | VENUE_MAP_MANAGE | setup | 1 | SVC-VENUEOPS-VENUEMAP-1 | cache:idempotency, venuemap.import_job, venuemap.map | cache:idempotency, venuemap.import_job, venuemap.path, venuemap.point | Read a drawing into shapes
VenueOpsService | venueMap | listBookableVenueMaps | GET | /bookable-venue-maps |  | BookableVenueMaps | VENUE_MAP_VIEW | core | 1 | SVC-VENUEOPS-VENUEMAP-2 | venuemap.map, venuemap.map_version, venuemap.placed_resource |  | The published maps of a venue that carry bookable spots
VenueOpsService | venueMap | publishVenueMap | POST | /venue-maps/{mapId}/publish |  | VenueMap | VENUE_MAP_PUBLISH | setup | 1 | SVC-VENUEOPS-VENUEMAP-2 | assets.media_asset, cache:idempotency, platform.outlet, venuemap.map, venuemap.path, venuemap.placed_resource, venuemap.point | cache:idempotency, cache:resolution, venuemap.map, venuemap.map_version | Make the draft the one guests see
VenueOpsService | venueMap | setPlacedResource | POST | /venue-maps/{mapId}/resources | SetPlacedResourceRequest | PlacedResource | VENUE_MAP_MANAGE | setup | 1 | SVC-VENUEOPS-VENUEMAP-2 | venuemap.placed_resource | venuemap.placed_resource | Place or amend a bookable resource on the map
VenueOpsService | venueMap | setVenueMapArtwork | POST | /venue-maps/{mapId}/artwork |  | VenueMap | VENUE_MAP_MANAGE | setup | 1 | SVC-VENUEOPS-VENUEMAP-2 | venuemap.map | venuemap.map | Set the illustrated map guests see, and how it lines up with the plan
VenueOpsService | venueMap | setVenuePoint | POST | /venue-maps/{mapId}/points | SetVenuePointRequest | VenuePoint | VENUE_MAP_MANAGE | setup | 1 | SVC-VENUEOPS-VENUEMAP-3 | access.access_point, assets.media_asset, cache:idempotency, catalogue.product, platform.outlet, promotions.bundle, venuemap.map, venuemap.point | cache:idempotency, venuemap.point | Place or amend a point of interest
VenueOpsService | visitPlan | bookVisitPlan | POST | /visit-plans/{planId}/booking |  | VisitPlanBooking |  | core | 1 | SVC-VENUEOPS-VISITPLAN-1 | cache:idempotency, catalogue.channel_capacity, catalogue.performance, catalogue.product, catalogue.variant, orders.cart, orders.cart_line, promotions.bundle, venuemap.visit_plan, venuemap.visit_plan_item | cache:idempotency, catalogue.inventory_reservation, orders.cart, orders.cart_line, venuemap.visit_plan | Book this plan — turn it into cart lines
VenueOpsService | visitPlan | generateVisitPlan | POST | /visit-plans | VisitPlanRequest | VisitPlan |  | core | 1 | SVC-VENUEOPS-VISITPLAN-1 | cache:idempotency, catalogue.performance, catalogue.product, catalogue.product_eligibility_rule, catalogue.variant, queue.reading, venuemap.map, venuemap.path, venuemap.point, venuemap.visit_plan, venuemap.visit_plan_item | cache:idempotency, venuemap.visit_plan, venuemap.visit_plan_item | Build a visit plan from the party, the dates and what they like
VenueOpsService | visitPlan | getVisitPlan | GET | /visit-plans/{planId} |  | VisitPlan |  | core | 1 | SVC-VENUEOPS-VISITPLAN-1 | venuemap.visit_plan, venuemap.visit_plan_item |  | A visit plan, at its current version or an earlier one
VenueOpsService | visitPlan | listVisitPlanAlternatives | GET | /visit-plans/{planId}/items/{itemId}/alternatives |  | object |  | core | 1 | SVC-VENUEOPS-VISITPLAN-1 | catalogue.performance, catalogue.product, catalogue.product_eligibility_rule, queue.reading, venuemap.path, venuemap.point, venuemap.visit_plan, venuemap.visit_plan_item |  | What could take this item's place
VenueOpsService | visitPlan | updateVisitPlan | PUT | /visit-plans/{planId} | VisitPlanUpdate | VisitPlan |  | core | 1 | SVC-VENUEOPS-VISITPLAN-2 | cache:idempotency, catalogue.performance, catalogue.product_eligibility_rule, queue.reading, venuemap.path, venuemap.point, venuemap.visit_plan, venuemap.visit_plan_item | cache:idempotency, venuemap.visit_plan, venuemap.visit_plan_item | Swap, remove, add, move or undo, as a new version
VenueOpsService | waitTime | getWaitTimes | GET | /queues/wait-times |  | array of WaitTime |  | core | 1 | SVC-VENUEOPS-WAITTIME-1 | queue.entry, queue.queue, queue.reading |  | Wait times across a venue
WalletService | card | loadGameCredits | POST | /game-cards/{cardCode}/load |  | Wallet | WALLET_OPERATE | core | 1 | SVC-WALLET-CARD-1 | cache:idempotency, games.card, wallet.balance, wallet.credit_lot, wallet.wallet | cache:idempotency, games.card, platform.outbox, wallet.balance, wallet.credit_lot, wallet.wallet, wallet.wallet_transaction | Load credits onto a card
WalletService | giftCard | getGiftCard | GET | /gift-cards/{cardCode} |  | GiftCard | WALLET_VIEW | core | 1 | SVC-WALLET-GIFTCARD-1 | wallet.gift_card |  | Check a gift card balance
WalletService | retail | getWalletAutoReloadSetting | GET | /wallets/{walletId}/auto-reload |  | WalletAutoReloadSetting | WALLET_VIEW | core | 1 | SVC-WALLET-RETAIL-1 | wallet.auto_reload_setting, wallet.wallet |  | A wallet's own auto top-up, if the holder set one
WalletService | retail | getWalletExitBalance | GET | /wallets/{walletId}/exit-balance |  | WalletExitBalance | WALLET_VIEW | core | 1 | SVC-WALLET-RETAIL-1 | payments.stored_forward, wallet.balance, wallet.credit_lot, wallet.refund_policy, wallet.wallet |  | What the holder owes or is owed on leaving
WalletService | retail | setWalletAutoReloadSetting | PUT | /wallets/{walletId}/auto-reload | WalletAutoReloadSetting | WalletAutoReloadSetting | WALLET_OPERATE | core | 1 | SVC-WALLET-RETAIL-1 | cache:idempotency, payments.token, wallet.auto_reload_setting, wallet.funding_rule, wallet.wallet | cache:idempotency, cache:resolution, wallet.auto_reload_setting | Top the wallet up automatically from a stored card when it runs low
WalletService | retail | settleWalletAtExit | POST | /wallets/{walletId}/exit-settlement |  | WalletExitSettlement | WALLET_OPERATE | core | 1 | SVC-WALLET-RETAIL-1 | cache:idempotency, payments.stored_forward, wallet.balance, wallet.credit_lot, wallet.exit_settlement, wallet.refund_policy, wallet.wallet | cache:idempotency, orders.payment, orders.refund, platform.outbox, wallet.exit_settlement, wallet.wallet, wallet.wallet_transaction | Settle a short balance, or refund a credit, when the holder leaves
WalletService | retail | transferWalletBalance | POST | /wallets/{walletId}/transfer |  | WalletTransaction | WALLET_OPERATE | core | 1 | SVC-WALLET-RETAIL-2 | cache:idempotency, pii.subject, wallet.wallet, wallet.wallet_transaction | cache:idempotency, wallet.wallet, wallet.wallet_transaction | Send balance to another guest
WalletService | wallet | getWallet | GET | /wallets/{subjectId} |  | Wallet | WALLET_VIEW | core | 1 | SVC-WALLET-WALLET-1 | wallet.credit_lot, wallet.wallet |  | Read a guest wallet
WalletService | wallet | listWalletTransactions | GET | /wallets/{subjectId}/transactions |  | object | WALLET_VIEW | core | 1 | SVC-WALLET-WALLET-1 | wallet.wallet_transaction |  | Wallet transaction history
WalletService | wallet | publishWalletConfiguration | POST | /wallet-configuration/publish |  | WalletConfigurationVersion | WALLET_CONFIGURE | setup | 1 | SVC-WALLET-WALLET-1 | cache:idempotency, wallet.accounting_mapping, wallet.authentication_policy, wallet.channel_rule, wallet.configuration_version, wallet.consumption_policy, wallet.credit_type, wallet.funding_rule, wallet.integration_mapping, wallet.reconciliation_source, wallet.refund_policy, wallet.risk_rule_set, wallet.transfer_rule, wallet.wallet_type | cache:idempotency, wallet.configuration_version, wallet.configuration_version_snapshot | Validate and publish the wallet configuration as a version
WalletService | wallet | restoreWalletConfigurationVersion | POST | /wallet-configuration/versions/{version}/restore |  | WalletConfigurationVersion | WALLET_CONFIGURE | setup | 1 | SVC-WALLET-WALLET-1 | cache:idempotency, wallet.configuration_version, wallet.configuration_version_snapshot | cache:idempotency, wallet.accounting_mapping, wallet.authentication_policy, wallet.channel_rule, wallet.consumption_policy, wallet.credit_type, wallet.funding_rule, wallet.integration_mapping, wallet.reconciliation_source, wallet.refund_policy, wallet.risk_rule_set, wallet.transfer_rule, wallet.wallet_type | Put a previous wallet configuration back as the working draft
WalletService | wallet | setWalletFundingRules | PUT | /wallet-funding-rules | WalletFundingRules | WalletFundingRules | WALLET_CONFIGURE | setup | 1 | SVC-WALLET-WALLET-2 | wallet.funding_rule | wallet.funding_rule | Amounts, channels, bonuses, limits and velocity
WalletService | wallet | setWalletRefundPolicy | PUT | /wallet-refund-policy | WalletRefundPolicy | WalletRefundPolicy | WALLET_CONFIGURE | setup | 1 | SVC-WALLET-WALLET-2 | wallet.refund_policy | wallet.refund_policy | What a refund puts back, and where
WalletService | wallet | topUpWallet | POST | /wallets/{subjectId}/top-ups |  | Wallet | WALLET_OPERATE | core | 1 | SVC-WALLET-WALLET-2 | cache:idempotency, wallet.balance, wallet.credit_lot, wallet.wallet | cache:idempotency, platform.outbox, wallet.balance, wallet.credit_lot, wallet.wallet, wallet.wallet_transaction | Add value to a wallet
WhiteLabelService | appPublishing | getAppBuild | GET | /tenant-config/app-builds/{appBuildId} |  | AppBuild | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-APPPUBLISHING-1 | whitelabel.app_build |  | One app build, with its package and store status
WhiteLabelService | appPublishing | getStoreAccounts | GET | /tenant-config/store-accounts |  | StorePublishingChecklist | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-APPPUBLISHING-1 | whitelabel.config_version, whitelabel.store_account, whitelabel.tenant_config |  | The client's store accounts and the publishing checklist
WhiteLabelService | appPublishing | listAppBuilds | GET | /tenant-config/app-builds |  | object | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-APPPUBLISHING-1 | whitelabel.app_build |  | The tenant's app builds, newest first
WhiteLabelService | appPublishing | requestAppBuild | POST | /tenant-config/app-builds |  | AppBuild | TENANT_PUBLISH | core | 1 | SVC-WHITELABEL-APPPUBLISHING-1 | whitelabel.app_build, whitelabel.config_version, whitelabel.store_account | cache:idempotency, whitelabel.app_build | Build the branded app for a store
WhiteLabelService | appPublishing | setStoreAccounts | PUT | /tenant-config/store-accounts |  | StorePublishingChecklist | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-APPPUBLISHING-2 | whitelabel.store_account | cache:idempotency, whitelabel.store_account | Record the client's own Apple and Google store accounts and listings
WhiteLabelService | bookingFlows | createBookingFlowDefinition | POST | /venues/{venueId}/booking-flows | BookingFlow | BookingFlow | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-BOOKINGFLOWS-1 | whitelabel.booking_flow, whitelabel.booking_flow_step | cache:idempotency, whitelabel.booking_flow, whitelabel.booking_flow_step | Pick a booking flow for a venue
WhiteLabelService | bookingFlows | deleteBookingFlow | DELETE | /booking-flows/{bookingFlowId} |  |  | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-BOOKINGFLOWS-1 | catalogue.product, catalogue.product_category, whitelabel.booking_flow | cache:idempotency, whitelabel.booking_flow, whitelabel.booking_flow_step | Remove a booking flow from a venue
WhiteLabelService | bookingFlows | getBookingFlow | GET | /booking-flows/{bookingFlowId} |  | BookingFlow | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-BOOKINGFLOWS-1 | whitelabel.booking_flow, whitelabel.booking_flow_step |  | Read one of a venue's booking flows, every step included
WhiteLabelService | bookingFlows | getPublishedBookingFlow | GET | /venues/{venueId}/booking-flow |  | BookingFlow |  | core | 1 | SVC-WHITELABEL-BOOKINGFLOWS-1 | catalogue.product, catalogue.product_category, whitelabel.booking_flow, whitelabel.booking_flow_step, whitelabel.config_version |  | The published booking flow a product or category books through
WhiteLabelService | bookingFlows | listBookingFlowTypes | GET | /booking-flow-types |  | object | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-BOOKINGFLOWS-2 |  |  | The booking flow types a venue can pick from, with their steps
WhiteLabelService | bookingFlows | listBookingFlows | GET | /venues/{venueId}/booking-flows |  | object | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-BOOKINGFLOWS-2 | whitelabel.booking_flow, whitelabel.booking_flow_step |  | A venue's booking flows, in the working draft
WhiteLabelService | bookingFlows | updateBookingFlowDefinition | PATCH | /booking-flows/{bookingFlowId} |  | BookingFlow | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-BOOKINGFLOWS-2 | whitelabel.booking_flow, whitelabel.booking_flow_step | cache:idempotency, whitelabel.booking_flow, whitelabel.booking_flow_step | Reorder a flow's steps, switch optional steps, change its settings
WhiteLabelService | bookingFlows | validateBookingFlow | POST | /booking-flows/{bookingFlowId}/validate |  | BookingFlowValidation | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-BOOKINGFLOWS-2 | whitelabel.booking_flow, whitelabel.booking_flow_step | cache:idempotency, whitelabel.booking_flow_step | Check a flow against its type
WhiteLabelService | brand | getAppIcons | GET | /tenant-config/app-icons |  | AppIcons | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-BRAND-1 | whitelabel.tenant_config |  | Read app icon set
WhiteLabelService | brand | getBrandIdentity | GET | /tenant-config/brand |  | BrandIdentity | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-BRAND-1 | whitelabel.tenant_config |  | Read brand identity
WhiteLabelService | brand | setAppIcons | PUT | /tenant-config/app-icons |  | AppIcons | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-BRAND-1 | cache:idempotency, whitelabel.tenant_config | cache:idempotency, whitelabel.tenant_config | Set app icons
WhiteLabelService | brand | setBrandIdentity | PUT | /tenant-config/brand | BrandIdentity | BrandIdentity | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-BRAND-1 | cache:idempotency, whitelabel.tenant_config | cache:idempotency, whitelabel.tenant_config | Set logo, favicon and splash
WhiteLabelService | branding | getBookingFlowConfig | GET | /tenant-config/booking-flow |  | BookingFlowConfig | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-BRANDING-1 | whitelabel.tenant_config |  | How the guest booking flow looks and steps
WhiteLabelService | branding | setBookingFlowConfig | PUT | /tenant-config/booking-flow | BookingFlowConfig | BookingFlowConfig | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-BRANDING-1 | cache:idempotency, whitelabel.tenant_config | cache:idempotency, cache:resolution, whitelabel.tenant_config | Set how the guest booking flow looks and steps
WhiteLabelService | content | createBanner | POST | /tenant-config/banners | Banner | Banner | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-CONTENT-1 | cache:idempotency, whitelabel.banner | cache:idempotency, whitelabel.banner | Create a banner
WhiteLabelService | content | createContentPage | POST | /tenant-config/pages | ContentPage | ContentPage | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-CONTENT-1 | cache:idempotency, whitelabel.content_page | cache:idempotency, whitelabel.content_page | Create a content page
WhiteLabelService | content | createGuidedChoice | POST | /venues/{venueId}/guided-choices | GuidedChoice | GuidedChoice | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-CONTENT-1 | whitelabel.guided_choice, whitelabel.guided_choice_answer, whitelabel.guided_choice_question | whitelabel.guided_choice, whitelabel.guided_choice_answer, whitelabel.guided_choice_question | Set up Help me choose for a venue
WhiteLabelService | content | createPromoBlock | POST | /tenant-config/promo-blocks | PromoBlock | PromoBlock | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-CONTENT-1 | cache:idempotency, whitelabel.promo_block | cache:idempotency, whitelabel.promo_block | Create a promotional block
WhiteLabelService | content | deleteBanner | DELETE | /tenant-config/banners/{bannerId} |  |  | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-CONTENT-2 | cache:idempotency, whitelabel.tenant_config | cache:idempotency, whitelabel.tenant_config | Delete a banner
WhiteLabelService | content | deleteContentPage | DELETE | /tenant-config/pages/{pageId} |  |  | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-CONTENT-2 | cache:idempotency, whitelabel.tenant_config | cache:idempotency, whitelabel.tenant_config | Delete a content page
WhiteLabelService | content | deleteGuidedChoice | DELETE | /guided-choices/{guidedChoiceId} |  |  | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-CONTENT-2 | cache:idempotency, whitelabel.guided_choice, whitelabel.guided_choice_answer, whitelabel.guided_choice_question | cache:idempotency, whitelabel.guided_choice, whitelabel.guided_choice_answer, whitelabel.guided_choice_question | Delete a Help me choose set-up, or dismiss a suggestion
WhiteLabelService | content | deletePromoBlock | DELETE | /tenant-config/promo-blocks/{promoBlockId} |  |  | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-CONTENT-2 | cache:idempotency, whitelabel.promo_block | cache:idempotency, whitelabel.promo_block | Delete a promotional block
WhiteLabelService | content | getPublishedGuidedChoice | GET | /venues/{venueId}/guided-choice |  | GuidedChoice |  | core | 1 | SVC-WHITELABEL-CONTENT-3 | whitelabel.guided_choice, whitelabel.guided_choice_answer, whitelabel.guided_choice_question |  | The venue's published Help me choose
WhiteLabelService | content | listBanners | GET | /tenant-config/banners |  | object | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-CONTENT-3 | whitelabel.banner |  | List banners
WhiteLabelService | content | listContentPages | GET | /tenant-config/pages |  | object | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-CONTENT-3 | whitelabel.content_page |  | List custom content pages
WhiteLabelService | content | listGuidedChoices | GET | /venues/{venueId}/guided-choices |  | object | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-CONTENT-3 | whitelabel.guided_choice, whitelabel.guided_choice_answer, whitelabel.guided_choice_question |  | List a venue's Help me choose set-ups
WhiteLabelService | content | listPolicies | GET | /tenant-config/policies |  | array of Policy | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-CONTENT-4 | whitelabel.policy |  | List legal policies
WhiteLabelService | content | listPromoBlocks | GET | /tenant-config/promo-blocks |  | array of PromoBlock | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-CONTENT-4 | whitelabel.promo_block |  | List promotional blocks
WhiteLabelService | content | listPublishedContentPages | GET | /storefront/pages |  | object |  | core | 1 | SVC-WHITELABEL-CONTENT-4 |  |  | The live content pages, readable before sign-in
WhiteLabelService | content | listPublishedFaqs | GET | /storefront/faqs |  | array of PublishedFaqCategory |  | core | 1 | SVC-WHITELABEL-CONTENT-4 |  |  | The published FAQs, readable before sign-in
WhiteLabelService | content | listPublishedPolicies | GET | /storefront/policies |  | array of PublishedPolicy |  | core | 1 | SVC-WHITELABEL-CONTENT-5 |  |  | The tenant's current legal policies, readable before sign-in
WhiteLabelService | content | proposeGuidedChoice | POST | /venues/{venueId}/guided-choice-suggestions |  | GuidedChoice |  | core | 1 | SVC-WHITELABEL-CONTENT-5 | whitelabel.guided_choice, whitelabel.guided_choice_answer, whitelabel.guided_choice_question | whitelabel.guided_choice, whitelabel.guided_choice_answer, whitelabel.guided_choice_question | Record an AI-proposed Help me choose set-up for review
WhiteLabelService | content | publishGuidedChoice | POST | /guided-choices/{guidedChoiceId}/publish |  | GuidedChoice | TENANT_PUBLISH | core | 1 | SVC-WHITELABEL-CONTENT-5 | whitelabel.booking_flow, whitelabel.guided_choice, whitelabel.guided_choice_answer, whitelabel.guided_choice_question | cache:idempotency, whitelabel.guided_choice | Publish a Help me choose set-up to guests
WhiteLabelService | content | setFaqs | PUT | /tenant-config/faqs |  | array of FaqCategory | TENANT_CONFIGURE | setup | 1 | SVC-WHITELABEL-CONTENT-5 | cache:idempotency, whitelabel.faq_category, whitelabel.faq_entry | cache:idempotency, whitelabel.faq_category, whitelabel.faq_entry | Set FAQ categories and entries
WhiteLabelService | content | setPolicy | PUT | /tenant-config/policies/{policyKind} |  | Policy | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-CONTENT-6 | cache:idempotency, whitelabel.policy | cache:idempotency, whitelabel.policy | Publish a policy version
WhiteLabelService | content | unpublishGuidedChoice | POST | /guided-choices/{guidedChoiceId}/unpublish |  | GuidedChoice | TENANT_PUBLISH | core | 1 | SVC-WHITELABEL-CONTENT-6 | whitelabel.guided_choice, whitelabel.guided_choice_answer, whitelabel.guided_choice_question | whitelabel.guided_choice | Take a Help me choose set-up off the guest app
WhiteLabelService | content | updateBanner | PATCH | /tenant-config/banners/{bannerId} |  | Banner | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-CONTENT-6 | cache:idempotency, whitelabel.banner | cache:idempotency, whitelabel.banner | Amend or activate a banner
WhiteLabelService | content | updateContentPage | PUT | /tenant-config/pages/{pageId} | UpdateContentPageRequest | ContentPage | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-CONTENT-6 | cache:idempotency, whitelabel.content_page | cache:idempotency, whitelabel.content_page | Amend a content page
WhiteLabelService | content | updateGuidedChoice | PATCH | /guided-choices/{guidedChoiceId} |  | GuidedChoice | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-CONTENT-7 | cache:idempotency, whitelabel.guided_choice, whitelabel.guided_choice_answer, whitelabel.guided_choice_question | cache:idempotency, whitelabel.guided_choice, whitelabel.guided_choice_answer, whitelabel.guided_choice_question | Edit a Help me choose set-up, or review a suggestion
WhiteLabelService | content | updatePromoBlock | PATCH | /tenant-config/promo-blocks/{promoBlockId} |  | PromoBlock | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-CONTENT-7 | cache:idempotency, whitelabel.promo_block | cache:idempotency, whitelabel.promo_block | Amend a promotional block
WhiteLabelService | homepage | getHomepageLayout | GET | /tenant-config/homepage |  | HomepageLayout | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-HOMEPAGE-1 | whitelabel.homepage_layout, whitelabel.homepage_section |  | Read homepage layout
WhiteLabelService | homepage | listLandingPageTemplates | GET | /landing-page-templates |  | object | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-HOMEPAGE-1 | whitelabel.homepage_layout, whitelabel.homepage_section |  | The landing-page templates TICVAI provides
WhiteLabelService | homepage | setHomepageLayout | PUT | /tenant-config/homepage | HomepageLayout | HomepageLayout | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-HOMEPAGE-1 | cache:idempotency, whitelabel.homepage_layout, whitelabel.homepage_section | cache:idempotency, whitelabel.homepage_layout, whitelabel.homepage_section | Set homepage section order
WhiteLabelService | modules | getFeatureToggles | GET | /tenant-config/features |  | array of FeatureToggle | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-MODULES-1 | cache:resolution, whitelabel.feature_toggle | cache:resolution | Read tenant feature toggles
WhiteLabelService | modules | getModuleEnablement | GET | /tenant-config/modules |  | array of ModuleEnablement | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-MODULES-1 | cache:resolution, control.licence_add_on, subscription.contract, subscription.plan, whitelabel.module_enablement | cache:resolution | Read module enablement
WhiteLabelService | modules | setFeatureToggles | PUT | /tenant-config/features |  | array of FeatureToggle | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-MODULES-1 | cache:idempotency, whitelabel.feature_toggle | cache:idempotency, cache:resolution, whitelabel.feature_toggle | Set feature toggles
WhiteLabelService | modules | setLanguages | PUT | /tenant-config/languages |  | LanguageConfig | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-MODULES-1 | cache:idempotency, whitelabel.tenant_config | cache:idempotency, whitelabel.tenant_config | Set enabled languages and default
WhiteLabelService | modules | setModuleEnablement | PUT | /tenant-config/modules |  | array of ModuleEnablement | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-MODULES-2 | cache:idempotency, control.licence_add_on, subscription.contract, subscription.plan, whitelabel.module_enablement | cache:idempotency, cache:resolution, whitelabel.module_enablement | Enable or disable modules
WhiteLabelService | navigation | buildDeepLink | POST | /deep-links |  | object | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-NAVIGATION-1 |  |  | Build a deep link to a target
WhiteLabelService | navigation | getDeepLinkScheme | GET | /deep-links |  | DeepLinkScheme | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-NAVIGATION-1 |  |  | The published deep-link scheme
WhiteLabelService | navigation | getNavigation | GET | /tenant-config/navigation |  | NavigationConfig | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-NAVIGATION-1 | cache:resolution, whitelabel.navigation_config, whitelabel.navigation_item | cache:resolution | Read navigation
WhiteLabelService | navigation | setHeader | PUT | /tenant-config/header | HeaderConfig | HeaderConfig | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-NAVIGATION-1 | cache:idempotency, whitelabel.tenant_config | cache:idempotency, whitelabel.tenant_config | Configure the header
WhiteLabelService | navigation | setNavigation | PUT | /tenant-config/navigation | NavigationConfig | NavigationConfig | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-NAVIGATION-2 | cache:idempotency, whitelabel.navigation_config, whitelabel.navigation_item | cache:idempotency, cache:resolution, whitelabel.navigation_config, whitelabel.navigation_item | Set main and overflow navigation
WhiteLabelService | overview | getPublishedTenantConfig | GET | /storefront/tenant-config |  | PublishedTenantConfig |  | core | 1 | SVC-WHITELABEL-OVERVIEW-1 | whitelabel.footer_config, whitelabel.footer_config_column, whitelabel.footer_config_social_link, whitelabel.homepage_layout, whitelabel.homepage_section, whitelabel.navigation_config, whitelabel.navigation_item |  | The published guest-facing configuration, before anyone signs in
WhiteLabelService | overview | getTenantAppStatus | GET | /tenant-config/status |  | TenantAppStatus |  | core | 1 | SVC-WHITELABEL-OVERVIEW-1 | whitelabel.config_version, whitelabel.tenant_config |  | App status and recent changes
WhiteLabelService | overview | getTenantConfig | GET | /tenant-config |  | TenantConfig | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-OVERVIEW-1 | whitelabel.booking_flow, whitelabel.booking_flow_step, whitelabel.feature_toggle, whitelabel.footer_config, whitelabel.footer_config_column, whitelabel.footer_config_social_link, whitelabel.homepage_layout, whitelabel.homepage_section, whitelabel.module_enablement, whitelabel.navigation_config, whitelabel.navigation_item, whitelabel.tenant_config |  | Full working configuration
WhiteLabelService | overview | listAnalyticsProviders | GET | /tenant-config/analytics-providers |  | object | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-OVERVIEW-1 | whitelabel.analytics_provider |  | The analytics platforms the storefront and app report to
WhiteLabelService | overview | recordStorefrontSessionEvents | POST | /storefront/session-events | WhiteLabelStorefrontSessionBatch |  |  | core | 1 | SVC-WHITELABEL-OVERVIEW-2 | cache:idempotency | cache:idempotency, platform.outbox | Report a batch of browsing behaviour for fraud prevention, hashed and without personal data
WhiteLabelService | overview | setAnalyticsProvider | PUT | /tenant-config/analytics-providers | StorefrontAnalyticsProvider | StorefrontAnalyticsProvider | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-OVERVIEW-2 | cache:idempotency, whitelabel.analytics_provider | cache:idempotency, whitelabel.analytics_provider | Connect the storefront and app to an analytics platform
WhiteLabelService | overview | setMaintenanceMode | PUT | /tenant-config/status |  | TenantAppStatus | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-OVERVIEW-2 | cache:idempotency, whitelabel.tenant_config | cache:idempotency, whitelabel.tenant_config | Enable or clear maintenance mode, and set the live app status
WhiteLabelService | publishing | createPreview | POST | /tenant-config/preview |  | Preview | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-PUBLISHING-1 | cache:idempotency, whitelabel.tenant_config | cache:idempotency, whitelabel.tenant_config | Generate a preview link
WhiteLabelService | publishing | diffConfigVersion | GET | /tenant-config/versions/{version}/diff |  | ConfigDiff | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-PUBLISHING-1 | whitelabel.tenant_config |  | Compare a version against the working draft
WhiteLabelService | publishing | exportSitePackage | POST | /site-package |  | SitePackage | TENANT_PUBLISH | core | 1 | SVC-WHITELABEL-PUBLISHING-1 | whitelabel.site_package | whitelabel.site_package | Generate a site package (self-hosted)
WhiteLabelService | publishing | getPublishReviewPolicy | GET | /publish-review-policy |  | PublishReviewPolicy | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-PUBLISHING-1 | whitelabel.publish_review_policy |  | Whether publishing needs a review
WhiteLabelService | publishing | getSitePackage | GET | /site-package/{packageId} |  | SitePackage | TENANT_PUBLISH | core | 1 | SVC-WHITELABEL-PUBLISHING-2 | whitelabel.site_package |  | A site package and its download link
WhiteLabelService | publishing | getSiteSetupProgress | GET | /tenant-config/site-setup |  | SiteSetupProgress | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-PUBLISHING-2 | whitelabel.booking_flow, whitelabel.config_version, whitelabel.site_setup_progress, whitelabel.tenant_config |  | Where the tenant is in the Site Builder
WhiteLabelService | publishing | listConfigVersions | GET | /tenant-config/versions |  | object | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-PUBLISHING-2 | whitelabel.config_version |  | Version history
WhiteLabelService | publishing | publishTenantConfig | POST | /tenant-config/publish |  | ConfigVersion | TENANT_PUBLISH | core | 1 | SVC-WHITELABEL-PUBLISHING-2 | whitelabel.booking_flow, whitelabel.booking_flow_step, whitelabel.config_version, whitelabel.tenant_config | cache:idempotency, platform.outbox, whitelabel.config_version | Publish the working draft
WhiteLabelService | publishing | restoreConfigVersion | POST | /tenant-config/versions/{version}/restore |  | TenantConfig | TENANT_PUBLISH | core | 1 | SVC-WHITELABEL-PUBLISHING-3 | cache:idempotency, whitelabel.booking_flow, whitelabel.booking_flow_step, whitelabel.feature_toggle, whitelabel.footer_config, whitelabel.footer_config_column, whitelabel.footer_config_social_link, whitelabel.homepage_layout, whitelabel.homepage_section, whitelabel.module_enablement, whitelabel.navigation_config, whitelabel.navigation_item, whitelabel.tenant_config | cache:idempotency, cache:resolution, whitelabel.feature_toggle, whitelabel.homepage_section, whitelabel.module_enablement, whitelabel.navigation_item, whitelabel.tenant_config | Restore a previous version
WhiteLabelService | publishing | setPublishReviewPolicy | PUT | /publish-review-policy | PublishReviewPolicy | PublishReviewPolicy | TENANT_PUBLISH | core | 1 | SVC-WHITELABEL-PUBLISHING-3 | whitelabel.publish_review_policy | whitelabel.publish_review_policy | Switch the publish review step on or off
WhiteLabelService | publishing | setSiteSetupProgress | PUT | /tenant-config/site-setup | SiteSetupProgress | SiteSetupProgress | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-PUBLISHING-3 | whitelabel.config_version, whitelabel.site_setup_progress | cache:idempotency, whitelabel.site_setup_progress | Save the Site Builder's progress
WhiteLabelService | publishing | validateTenantConfig | POST | /tenant-config/validate |  | ConfigValidationReport | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-PUBLISHING-3 | whitelabel.booking_flow, whitelabel.booking_flow_step, whitelabel.tenant_config | cache:idempotency | Validate the working draft
WhiteLabelService | theme | getFonts | GET | /tenant-config/fonts |  | FontConfig | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-THEME-1 | whitelabel.tenant_config |  | Read font configuration
WhiteLabelService | theme | getTheme | GET | /tenant-config/theme |  | Theme | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-THEME-1 | cache:resolution, whitelabel.tenant_config | cache:resolution | Read colour theme
WhiteLabelService | theme | setFonts | PUT | /tenant-config/fonts | FontConfig | FontConfig | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-THEME-1 | cache:idempotency, whitelabel.tenant_config | cache:idempotency, whitelabel.tenant_config | Set fonts
WhiteLabelService | theme | setTheme | PUT | /tenant-config/theme | Theme | Theme | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-THEME-1 | cache:idempotency, whitelabel.tenant_config | cache:idempotency, cache:resolution, whitelabel.tenant_config | Set colour theme
WhiteLabelService | white-label | claimCustomDomain | POST | /tenant-domains |  | CustomDomain | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-WHITE-LABEL-1 | cache:idempotency, control.tenant, whitelabel.custom_domain | cache:idempotency, whitelabel.custom_domain | Claim a domain and get a verification token
WhiteLabelService | white-label | getPlatformSubdomain | GET | /platform-subdomain |  | PlatformSubdomain | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-WHITE-LABEL-1 |  |  | The tenant's platform subdomain
WhiteLabelService | white-label | listCustomDomains | GET | /tenant-domains |  | array of CustomDomain | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-WHITE-LABEL-1 | whitelabel.custom_domain |  | The domains this tenant has claimed
WhiteLabelService | white-label | regenerateDomainToken | POST | /tenant-domains/{domainId}/token |  | CustomDomain | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-WHITE-LABEL-1 | whitelabel.custom_domain | whitelabel.custom_domain | Issue a new validation token
WhiteLabelService | white-label | relinquishCustomDomain | DELETE | /tenant-domains/{domainId} |  |  | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-WHITE-LABEL-2 | whitelabel.custom_domain | whitelabel.custom_domain | Give the domain up
WhiteLabelService | white-label | setPrimaryDomain | POST | /tenant-domains/{domainId}/primary |  | CustomDomain | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-WHITE-LABEL-2 | whitelabel.custom_domain | whitelabel.custom_domain | Make a domain the primary one
WhiteLabelService | white-label | verifyCustomDomain | POST | /tenant-domains/{domainId}/verify |  | CustomDomain | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-WHITE-LABEL-2 | cache:idempotency, whitelabel.custom_domain | cache:idempotency, whitelabel.custom_domain | Check the record and issue the certificate
WhiteLabelService | whiteLabel | createContentBlock | POST | /content-blocks | ContentBlock | ContentBlock | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-WHITELABEL-1 | cache:idempotency, control.content_block, marketing.segment | cache:idempotency, control.content_block | Author a block of content
WhiteLabelService | whiteLabel | listContentBlocks | GET | /content-blocks |  | object | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-WHITELABEL-1 | control.content_block |  | The content blocks of a page
WhiteLabelService | whiteLabel | publishContentBlock | POST | /content-blocks/{blockId}/publish |  | ContentBlock | TENANT_PUBLISH | core | 1 | SVC-WHITELABEL-WHITELABEL-1 | cache:idempotency, control.content_block, identity.principal | cache:idempotency, cache:resolution, control.content_block | Publish now, or schedule it
WhiteLabelService | whiteLabel | setFooter | PUT | /footer | FooterConfig | FooterConfig | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-WHITELABEL-1 | cache:idempotency, whitelabel.footer_config, whitelabel.footer_config_column, whitelabel.footer_config_social_link | cache:idempotency, cache:resolution, whitelabel.footer_config, whitelabel.footer_config_column, whitelabel.footer_config_social_link | Footer columns, legal links and social
WhiteLabelService | whiteLabel | updateContentBlock | PATCH | /content-blocks/{blockId} |  | ContentBlock | TENANT_CONFIGURE | core | 1 | SVC-WHITELABEL-WHITELABEL-2 | control.content_block | control.content_block | Change a draft content block

## API schemas
Contract | Schema | Fields | Stored as | Used as request | Used as response | Operations | Description
access | AccessAccessPointGroup | 8 | access.access_point_group | 1 | 1 | setAccessPointGroup | A named group of access points in one venue (e.g.
access | AccessCredentialPolicy | 32 | access.credential_policy | 0 | 1 | setDeviceBindingPolicy | One credential policy of one kind for a venue - activation and display rule, transfer policy, Virtual Ticket identity configuration or device binding policy; merges the proposed credential_display_ru…
access | AccessDeviceBinding | 15 | access.device_binding | 0 | 1 | bindCredentialDevice | One guest device bound to a credential, with its registration, last activation and security status; the binding policy in force is a deviceBinding row of access.credential_policy (declared 29 Septemb…
access | AccessGateModePolicy | 12 | access.gate_mode_policy | 1 | 1 | setGateModePolicy | One policy for a non-standard gate mode (free spin or count only as freeFlow, emergency as dropArm): who may activate it, on which gate group, whether a reason is required, emergency code, notificati…
access | AccessPoint | 18 | access.access_point | 0 | 5 | createAccessPoint, setAccessPointDirection, setAccessPointGeofence, setTurnstileMode, updateAccessPoint
access | AccessPointGeofence | 5 |  | 1 | 0 | setAccessPointGeofence | Where a handheld may validate for one access point, and what happens outside it.
access | AdmissionRules | 21 | access.admission_rules | 2 | 2 | createAdmissionRules, updateAdmissionRules
access | BiometricVerificationProfileBuilderInput | 11 | none — request only; no existing table shares a single field with this, so nothing the package stores today is what this configures | 1 | 0 | setBiometricVerificationProfile | What Biometric Verification Profile Builder submits.
access | BiometricVerificationProfileBuilderView | 10 | none — projection over access state, assembled at read time from tables that already exist | 0 | 1 | setBiometricVerificationProfile | What Biometric Verification Profile Builder displays.
access | BlacklistEntry | 9 | access.blacklist | 0 | 1 | addBlacklistEntry
access | BleBeaconGeofenceConfigurationInput | 13 | none — request only; no existing table shares a single field with this, so nothing the package stores today is what this configures | 1 | 0 | setBleBeaconGeofence | What BLE Beacon & Geofence Configuration submits.
access | BleBeaconGeofenceConfigurationView | 13 | none — projection over access state, assembled at read time from tables that already exist | 0 | 1 | setBleBeaconGeofence | What BLE Beacon & Geofence Configuration displays.
access | CreateAccessPointRequest | 7 |  | 1 | 0 | createAccessPoint
access | CredentialActivationDisplayRulesInput | 6 | none — request only; the write configures the rules the matching View reads back (decided 29 September, VM close-out) | 1 | 0 | setCredentialActivationDisplay | What Credential Activation & Display Rules submits (decided 29 September, VM close-out).
access | CredentialActivationDisplayRulesView | 5 | none — projection over access state, assembled at read time from tables that already exist | 0 | 1 | setCredentialActivationDisplay | What Credential Activation & Display Rules displays.
access | CredentialDeviceBindingInput | 5 | none — request only; written as access.device_binding (declared 29 September, writers pass) | 1 | 0 | bindCredentialDevice
access | DeviceBindingPolicyInput | 4 | none — request only; written as the deviceBinding row of access.credential_policy (declared 29 September, writers pass) | 1 | 0 | setDeviceBindingPolicy
access | Entitlement | 33 | access.entitlement | 0 | 1 | getEntitlement | What a guest actually holds.
access | FaceMatchingVerificationThresholdsInput | 13 | none — request only; the write configures the rules the matching View reads back (decided 29 September, VM close-out) | 1 | 0 | setFaceMatchingVerification | What Face Matching & Verification Thresholds submits (decided 29 September, VM close-out).
access | FaceMatchingVerificationThresholdsView | 12 | none — projection over access state, assembled at read time from tables that already exist | 0 | 1 | setFaceMatchingVerification | What Face Matching & Verification Thresholds displays.
access | FacePassEnrollmentConfigurationInput | 11 | none — request only; no existing table shares a single field with this, so nothing the package stores today is what this configures | 1 | 0 | setFacePassEnrollment | What Face Pass Enrollment Configuration submits.
access | FacePassEnrollmentConfigurationView | 10 | none — projection over access state, assembled at read time from tables that already exist | 0 | 1 | setFacePassEnrollment | What Face Pass Enrollment Configuration displays.
access | FacePassEnrolment | 15 | pii.subject_biometric | 0 | 3 | enrolFacePass, enrolFaceTag, getFacePassEnrolment | 3.2.43.
access | FaceTagTemporaryEnrollmentInput | 10 | none — request only; the write configures the rules the matching View reads back (decided 29 September, VM close-out) | 1 | 0 | setFaceTagTemporaryEnrollment | What Face Tag Temporary Enrollment submits (decided 29 September, VM close-out).
access | FaceTagTemporaryEnrollmentView | 10 | none — projection over access state, assembled at read time from tables that already exist | 0 | 1 | setFaceTagTemporaryEnrollment | What Face Tag Temporary Enrollment displays.
access | ManualOverrideSupervisorApprovalInput | 7 | none — request only; no existing table shares a single field with this, so nothing the package stores today is what this configures | 1 | 0 | approveManualOverrideSupervisor | What Manual Override & Supervisor Approval submits.
access | ManualOverrideSupervisorApprovalView | 7 | none — projection over access state, assembled at read time from tables that already exist | 0 | 1 | approveManualOverrideSupervisor | What Manual Override & Supervisor Approval displays.
access | ParkingEntitlement | 12 | access.parking_entitlement | 0 | 2 | getParkingEntitlement, updateParkingEntitlement | Issued at payment of an order that contains a parking product (decided 28 September, audit R166).
access | ParkingFacility | 14 | access.parking_facility | 1 | 1 | setParkingFacility
access | UpdateParkingEntitlementRequest | 3 | none — request only; applied to access.parking_entitlement | 1 | 0 | updateParkingEntitlement | The body of updateParkingEntitlement: only what changes.
access | VirtualTicketIdentityMasterRecordConfigurationInput | 10 | none — request only; no existing table shares a single field with this, so nothing the package stores today is what this configures | 1 | 0 | setVirtualTicketIdentity | What Virtual Ticket Identity & Master Record Configuration submits.
access | VirtualTicketIdentityMasterRecordConfigurationView | 10 | none — projection over access state, assembled at read time from tables that already exist | 0 | 1 | setVirtualTicketIdentity | What Virtual Ticket Identity & Master Record Configuration displays.
access | VisualAccessRuleBuilderInput | 8 | none — request only; no existing table shares a single field with this, so nothing the package stores today is what this configures | 1 | 0 | setVisualAccessRule | What Visual Access Rule Builder submits.
access | VisualAccessRuleBuilderView | 8 | none — projection over access state, assembled at read time from tables that already exist | 0 | 1 | setVisualAccessRule | What Visual Access Rule Builder displays.
ai | AiAnswerFeedback | 11 | ai.answer_feedback | 0 | 1 | recordAnswerFeedback | What a person thought of an answer (AIC-062).
ai | AiAssistantProfile | 14 | ai.assistant_profile | 1 | 1 | configureAssistantProfile | One assistant runtime, many profiles (design 5.10, C5; AIC-069..080).
ai | AiByokEnablement | 11 | ai.byok_enablement | 1 | 2 | getAiByokEnablement, setAiByokEnablement | Whether a tenant may bring its own model key (decided 29 September, design 8 on 5.9).
ai | AiCapabilityRegistration | 18 | ai.capability | 0 | 1 | pauseAiCapability | An entry in the capability registry (design 3.1 Registry, AIC-144, AIC-145; ADM-520).
ai | AiContentDraftSet | 4 | none — each draft is an ai.proposed_action row (kind content); proposedActionId is its id | 0 | 1 | proposeMarketingContent | What proposeMarketingContent drafted: one entry per variant per locale.
ai | AiConversation | 8 | ai.conversation | 0 | 1 | createAiConversation
ai | AiEffectivePolicy | 8 | none — resolved from published policy versions, exceptions and ai.policy | 0 | 1 | getEffectiveAiPolicy | The policy in force for a capability at a scope (AIC-153, AIC-165; ADM-525, ADM-528): the intersection of the capability, governance policy and the tenant or venue AI policy, with where each part cam…
ai | AiEvaluationRun | 14 | ai.eval_run | 0 | 1 | runAiEvaluation | One evaluation of a candidate against its baseline: offline golden set, backtest or shadow comparison.
ai | AiForecastDefinition | 20 | ai.forecast_definition | 1 | 1 | setForecastDefinition | What is forecast, at what grain, for what horizon, how often and by which producer (design 3.1 Forecast, 5.2; ADM-500).
ai | AiForecastScenario | 9 | ai.forecast_scenario | 1 | 1 | createForecastScenario | A what-if against a published version (ADM-507, ADM-517, BO-931).
ai | AiForecastVersion | 18 | ai.forecast_version | 0 | 2 | publishForecastVersion, runForecast | An immutable forecast version (AIP-032): producer, model version, data cut-off, horizon and status.
ai | AiGovernanceDecision | 7 | none — computed; a block also writes ai.decision_record | 0 | 1 | evaluateAiGovernance | The governance decision point's answer (design 3.8, AIC-166): outcome, policy version, conditions, required approvals and an explanation.
ai | AiGovernancePolicyVersion | 12 | ai.governance_policy_version | 0 | 2 | createAiGovernancePolicyDraft, publishAiGovernancePolicy | One version of a governance policy.
ai | AiGuidedChoiceSuggestion | 13 | ai.guided_choice_suggestion | 0 | 2 | getGuidedChoiceSuggestion, suggestGuidedChoice | One Help me choose suggestion for a venue (design 3.11, decided 29 September; C7 at autonomy "suggest").
ai | AiHistoryImport | 19 | ai.history_import | 0 | 2 | getVenueHistoryImport, importVenueHistory | One import of a venue's own history (29 September, AI functions review).
ai | AiIncident | 20 | ai.incident | 0 | 2 | containAiIncident, openAiIncident | An AI governance incident (ADM-556): detection, containment, investigation, remediation and closure.
ai | AiInsight | 22 | ai.insight | 0 | 1 | decideAiInsight | An insight with a lifecycle (AIP-181): new, reviewed, accepted or rejected, actioned, measured.
ai | AiIntervention | 11 | ai.intervention | 0 | 1 | overrideAiDecision | A person stepping in (AIC-187, ADM-535, ADM-536): an override, pause, resume, stop, retry or rollback, with the original AI decision and the human one side by side.
ai | AiMessage | 15 | ai.message | 0 | 1 | sendAiMessage
ai | AiMetricChangeExplanation | 9 | none — computed; written as an ai.insight of kind rootCause when kept | 0 | 1 | explainMetricChange | Why a metric changed (AIP-176..180, ANL-056): drivers with their contribution, computed from the semantic layer.
ai | AiModel | 20 | ai.model | 1 | 1 | setAiModel | The model catalogue (design 3.1 Registry, 3.3; AIC-013, AIC-026).
ai | AiOperationalRequirement | 17 | ai.operational_requirement | 0 | 1 | decideOperationalRequirement | A requirement derived from a forecast version (design 2.2 C step 6, AIP-067): staff, POS, gates, F&B, stock or resources, computed with the tenant's productivity standards.
ai | AiPolicy | 31 | ai.policy | 1 | 2 | getAiPolicy, setAiPolicy
ai | AiPolicyException | 13 | ai.policy_exception | 0 | 1 | revokeAiPolicyException | A temporary, recorded exception to a governance policy (AIC-162, ADM-526): an expiry, an approver and compensating controls.
ai | AiPolicySimulation | 4 | none — computed; summary kept on ai.governance_policy_version.simulationSummary | 0 | 1 | simulateAiGovernancePolicy | What a draft policy version would have decided over recorded decisions and the test cases (ADM-527).
ai | AiPromptTemplate | 13 | ai.prompt_template | 0 | 1 | publishPromptTemplate | The prompt registry (design 3.1 Registry, AIC-022).
ai | AiProvider | 27 | ai.provider | 0 | 1 | listAiProviders
ai | AiRecommendationResult | 5 | none — written as ai.rec_decision after the response | 0 | 1 | decideRecommendations | The recommendation slot's content (design 2.2 A).
ai | AiRelease | 18 | ai.release | 0 | 2 | promoteAiRelease, rollbackAiRelease | The release pointer per capability and tenant (design 3.5): draft, offline evaluation, shadow, canary, production, monitored.
ai | AiUsageReport | 7 | none — aggregated from ai.activity | 0 | 1 | getAiUsage
ai | AiVenueSettings | 15 | ai.venue_settings | 1 | 2 | getAiVenueSettings, setAiVenueSettings | The venue AI profile (29 September, AI functions review): the figures a venue gives at onboarding so every data-driven answer is useful before it has history.
ai | IndexJob | 14 | ai.index_job | 0 | 1 | reindexSource
ai | IndexSource | 14 | ai.index_source | 1 | 1 | setIndexSource | One declaration per indexed table.
ai | KnowledgeCollection | 12 | ai.knowledge_collection | 1 | 1 | createKnowledgeCollection
ai | KnowledgeDocument | 12 | ai.knowledge_document | 1 | 1 | ingestKnowledgeDocument
ai | ProposedAction | 19 | ai.proposed_action | 0 | 1 | decideProposedAction
ai | SearchResult | 10 | none — computed | 0 | 1 | semanticSearch
ai | Suggestion | 13 | ai.suggestion | 0 | 1 | requestSuggestion | One answer to one question, with its reasoning and its confidence.
ai | TranslationProposals | 4 | none — each draft is an ai.proposed_action row (one per block and language), applied to the block only when an operator saves it through the block's own write (ADR-0020); CHG-FXC-004 | 0 | 2 | getTranslationProposals, proposeTranslations | What proposeTranslations drafted.
ai | VenueLabelProposal | 8 | none — each proposal is an ai.proposed_action row; proposalId is its id | 0 | 1 | proposeVenueLabels | 1.4.24.
approvals | ApprovalDelegation | 13 | approvals.delegation | 1 | 1 | createApprovalDelegation
approvals | ApprovalExternalProvider | 16 | approvals.external_provider | 1 | 1 | setApprovalExternalProvider | 11.1.65 (29 September, build pass).
approvals | ApprovalMatrix | 7 | approvals.matrix | 1 | 1 | setApprovalMatrix
approvals | ApprovalMatrixMultiLevelApprovalConfigurationInput | 19 | none — request only; written as one approvals.rule row (ApprovalRule) of the approvals.matrix for the kind and scope it names, field by field in approveMatrixMultiLevel (CHG-FXC-005) | 1 | 0 | approveMatrixMultiLevel | What Approval Matrix & Multi-Level Approval Configuration submits.
approvals | ApprovalMatrixMultiLevelApprovalConfigurationView | 19 | none — projection over approvals state, assembled at read time from tables that already exist | 0 | 1 | approveMatrixMultiLevel | What Approval Matrix & Multi-Level Approval Configuration displays.
approvals | ApprovalRequest | 33 | approvals.request | 0 | 2 | createApprovalRequest, decideApprovalRequest
approvals | ApprovalRequirement | 6 | none — computed | 0 | 1 | evaluateApprovalRequirement | The answer to "does this need approval", returned before the action.
approvals | CreateApprovalRequest | 11 | none — request only | 1 | 0 | createApprovalRequest
approvals | RolesAuthorityDelegationApprovalLimitsInput | 19 | none — request only; written as one approvals.delegation row (ApprovalDelegation), field by field in approveRoleAuthorityDelegation (CHG-FXC-005) | 1 | 0 | approveRoleAuthorityDelegation | What Roles, Authority, Delegation & Approval Limits submits.
approvals | RolesAuthorityDelegationApprovalLimitsView | 19 | none — projection over approvals state, assembled at read time from tables that already exist | 0 | 1 | approveRoleAuthorityDelegation | What Roles, Authority, Delegation & Approval Limits displays.
assets | Collection | 7 | assets.media_collection | 0 | 2 | createCollection, listCollections
assets | ExpiringMedia | 9 | none — computed | 0 | 1 | getExpiringRights
assets | MediaAsset | 25 | assets.media_asset | 0 | 2 | completeUpload, updateMediaAsset
assets | MediaAssetDetail | 29 | assets.media_asset | 0 | 1 | getMediaAsset
assets | MediaReplaceResult | 4 | none — computed | 0 | 1 | replaceMediaAsset
assets | UploadTicket | 12 | assets.media_upload | 0 | 1 | createUpload
catalogue | AcquireLeaseRequest | 7 |  | 1 | 0 | acquireInventoryHold | The body of acquireInventoryHold.
catalogue | AlternativeCode | 5 | catalogue.alternative_code | 0 | 2 | listAlternativeCodes, setAlternativeCodes
catalogue | BulkPriceResult | 4 |  | 0 | 1 | bulkChangePrices | 2.9.9.
catalogue | BundleSummary | 10 | none — projection over bundle | 0 | 2 | listCatalogueBundles, publishBundle | One published catalogue bundle — the signed snapshot terminals pull (ADR-0013).
catalogue | CatalogueBundle | 9 | catalogue.published_bundle | 0 | 1 | getLatestBundle
catalogue | CatalogueImportJob | 26 | catalogue.import_job | 0 | 1 | commitCatalogueImport | 1.4.2.
catalogue | CloneEventRequest | 4 | none — request only | 1 | 0 | cloneEvent | The body of cloneEvent.
catalogue | CreateEventRequest | 4 |  | 1 | 0 | createEvent
catalogue | CreatePerformancesRequest | 9 |  | 1 | 0 | createPerformances
catalogue | CreatePriceListRequest | 24 |  | 1 | 0 | createPriceList
catalogue | EligibilityCheckRequest | 2 |  | 1 | 0 | checkBookingEligibility | Request only.
catalogue | EligibilityCheckResult | 3 | none — computed per request | 0 | 1 | checkBookingEligibility
catalogue | EntitlementTemplate | 33 | catalogue.entitlement_template | 1 | 2 | createEntitlementTemplate, setEntitlementTemplateBlackoutDates
catalogue | Event | 10 | catalogue.event | 0 | 2 | createEvent, updateEvent
catalogue | GroupPackageDefinition | 11 | catalogue.group_package | 1 | 2 | getGroupPackageDefinition, setGroupPackageDefinition
catalogue | GuestMembership | 11 |  | 0 | 1 | getMyMemberships | 19.2.26 to 19.2.28.
catalogue | InventoryHold | 18 | catalogue.inventory_reservation | 0 | 2 | acquireInventoryHold, convertInventoryHold
catalogue | Performance | 12 | catalogue.performance | 0 | 2 | getPerformance, updatePerformance
catalogue | PerformanceAvailabilityPage | 3 | none — computed on read | 0 | 1 | getAvailability | The getAvailability answer (named 29 September, rev 3 REV3-1).
catalogue | PriceList | 30 | catalogue.price_list | 0 | 2 | createPriceList, updatePriceList
catalogue | Product | 46 | catalogue.product + catalogue.product_media | 0 | 3 | cloneProduct, getProduct, updateProduct
catalogue | ProductCategory | 12 | catalogue.product_category | 0 | 1 | setProductCategories | Retail Board 2 of the client's design set, 20 August.
catalogue | ProductCategoryNode | 13 | none — projection over catalogue.product_category | 0 | 1 | listProductCategories | One node of the tree listProductCategories returns.
catalogue | ProductEligibilityRule | 15 | catalogue.product_eligibility_rule | 1 | 2 | getProductEligibilityRule, setProductEligibilityRule | Participation limits for one product.
catalogue | ProductVariant | 9 | catalogue.variant | 0 | 2 | resolveProductByCode, updateProductVariant
catalogue | UpdateProductRequest | 15 |  | 1 | 0 | updateProduct
catalogue | WaitingRoomEntry | 8 | none — transient, held in the room's Redis counters and never in a table | 0 | 2 | enterWaitingRoom, getWaitingRoomPosition | One guest's place in a performance's waiting room (ADR-0066).
catalogue | WaitlistEntry | 11 | catalogue.waitlist_entry | 1 | 1 | joinWaitlist
finance | CreateTaxCodeRequest | 8 |  | 1 | 0 | createTaxCode
finance | FinCreditMemo | 31 | ledger.credit_memo + ledger.credit_memo_line | 0 | 1 | issueCreditMemo | 5.7.94.
finance | FinEInvoicingProvider | 12 | ledger.einvoicing_provider | 1 | 1 | setEInvoicingProvider | 6.1.1.
finance | FinIssueCreditMemoRequest | 6 | none — request only | 1 | 0 | issueCreditMemo
finance | FinIssueTaxInvoiceRequest | 6 | none — request only | 1 | 0 | issueTaxInvoice
finance | FinTaxDocumentRendition | 7 | none — a signed link to the stored PDF | 0 | 1 | getTaxDocumentRendition
finance | FinTaxInvoice | 41 | ledger.tax_invoice + ledger.tax_invoice_line | 0 | 2 | getTaxInvoice, issueTaxInvoice | 5.7.93, 5.10.3.
finance | FxProviderAssignment | 5 | ledger.fx_provider_assignment | 0 | 1 | setFxProvider | Which provider serves one FX purpose in one region, as setFxProvider sets it and ingestFxRates reads it.
finance | FxRate | 13 | ledger.fx_rate | 1 | 1 | setFxRate | Also the setFxRate body.
finance | LegalEntity | 11 | ledger.legal_entity | 1 | 1 | createLegalEntity | Also the createLegalEntity body.
finance | TaxCode | 12 | ledger.tax_code | 0 | 2 | createTaxCode, updateTaxCode
fnb | Bill | 8 | none — computed from visit orders | 0 | 2 | getBill, getGuestBill
fnb | BillSplit | 4 | fnb.bill_split + fnb.sub_bill | 0 | 1 | splitBill
fnb | ColdChainEvent | 9 | fnb.cold_chain_event | 1 | 1 | logColdChain | Board 5G.
fnb | CorrectiveAction | 13 | fnb.corrective_action | 0 | 2 | escalateCorrectiveAction, signCorrectiveAction | What was done about a finding, and who signed it.
fnb | CourseRules | 6 | fnb.course_rule | 1 | 2 | getCourseRules, setCourseRules | An outlet's coursing default.
fnb | CreateFnbOrderRequest | 7 | none — request only | 1 | 0 | createFnbOrder
fnb | CreateGuestOrderRequest | 8 |  | 1 | 0 | createGuestFnbOrder
fnb | CreateMenuRequest | 4 | none — request only | 1 | 0 | createMenu
fnb | DeliveryLocation | 12 | fnb.delivery_location | 0 | 3 | createDeliveryLocation, setDeliveryLocationOutletMapping, updateDeliveryLocation
fnb | FnbDeliveryPolicy | 16 | fnb.delivery_policy | 1 | 2 | getFnbDeliveryPolicy, setFnbDeliveryPolicy
fnb | FnbOrder | 19 | fnb.service_order + fnb.service_order_line | 0 | 5 | acceptFnbOrder, cancelFnbOrder, createFnbOrder, getFnbOrder, markOrderCollected
fnb | GuestMenu | 7 | none — projection over fnb.menu, fnb.menu_item and availability | 0 | 1 | getGuestMenu
fnb | GuestOrderResult | 9 | none — projection over fnb_order | 0 | 1 | createGuestFnbOrder
fnb | GuestOrderStatus | 6 | none — projection over kitchen_ticket | 0 | 2 | getGuestOrderStatus, recordOrderHandover
fnb | KitchenException | 9 | fnb.kitchen_exception | 0 | 1 | logKitchenException | Board 3, 24 August.
fnb | KitchenSla | 3 | fnb.kitchen_sla | 1 | 2 | getKitchenSla, setKitchenSla | How long a ticket may sit, per service mode, and what pushes it up the rail (setKitchenSla).
fnb | KitchenTicket | 17 | fnb.kitchen_ticket + fnb.kitchen_ticket_line | 0 | 6 | fireCourse, holdCourse, prioritiseKitchenTicket, recallKitchenTicket, refireItem, setKitchenTicketStatus
fnb | LocationSession | 9 | fnb.location_session | 0 | 1 | claimLocationSession
fnb | Menu | 9 | fnb.menu | 0 | 3 | createMenu, setMenuSections, updateMenu
fnb | MenuItem | 17 | fnb.menu_item | 0 | 2 | attachModifierGroup, setItemAvailability
fnb | MenuSchedule | 9 | fnb.menu_schedule | 0 | 1 | scheduleMenuPublish | A publish dated for later (scheduleMenuPublish, or publishMenu with an effectiveAt).
fnb | MenuVersion | 13 | fnb.menu_version | 0 | 2 | publishMenu, rollbackMenu | One published state of a menu, kept.
fnb | ModifierGroup | 7 | fnb.modifier_group + fnb.modifier_option | 1 | 1 | createModifierGroup | An F&B modifier is a choice added to a dish at the moment of ordering — *no onions*, *extra cheese*, *cooked medium*.
fnb | OpenTableVisitRequest | 6 | none — request only | 1 | 0 | openTableVisit
fnb | OrderLabel | 8 | none — rendered from the kitchen ticket and its order | 0 | 1 | printOrderLabel | What goes on the bag (printOrderLabel).
fnb | ProductionPlan | 7 | fnb.production_plan + fnb.production_plan_line | 1 | 2 | buildProductionPlan, releaseProductionPlan | Board 2M.
fnb | Recipe | 5 | fnb.recipe + fnb.recipe_ingredient | 1 | 1 | setRecipe
fnb | RestaurantWaitlist | 11 | fnb.waitlist_entry | 1 | 2 | joinRestaurantWaitlist, leaveRestaurantWaitlist | BL-130.
fnb | SplitBillRequest | 6 | none — request only | 1 | 0 | splitBill
fnb | StationRebalance | 2 |  | 1 | 1 | rebalanceStationLoad | A temporary move of work between stations (rebalanceStationLoad).
fnb | SubstitutionRule | 10 | fnb.substitution_rule | 0 | 1 | setSubstitutionRules | Board 2L, 24 August.
fnb | TableMap | 3 | none — projection | 0 | 2 | getTableMap, setTableLayout
fnb | TableReservation | 19 | fnb.table_reservation | 3 | 4 | createTableReservation, createTableReservationForGuest, seatTableReservation, updateTableReservation
fnb | TableState | 14 | none — projection over table and visit | 0 | 1 | clearTable
fnb | TableVisit | 17 | fnb.table_visit | 0 | 5 | getTableVisit, openTableVisit, requestBill, transferTableVisit, updateTableVisit
fnb | TemperatureLog | 11 | fnb.temperature_log | 1 | 0 | logTemperature | Board 5J of the client F&B pack, 20 August.
games | GameCard | 15 | games.card | 0 | 2 | getGameCard, issueGameCard
games | IssueGameCardRequest | 7 | none — request only | 1 | 0 | issueGameCard
identity | CapabilityTemplate | 9 | identity.capability_template | 1 | 1 | setCapabilityTemplate | 3.3.23, BL-110.
identity | ChangeCredentialRequest | 3 |  | 1 | 0 | changeOwnCredential | Request only.
identity | DelegatedAccess | 18 | identity.delegated_access | 0 | 1 | grantDelegation
identity | GuestSession | 11 | none — Redis session registry | 0 | 6 | getGuestSession, guestPasswordLogin, guestSocialLogin, guestUaePassLogin, registerGuest, verifyGuestOtp
identity | IdentityGuestDocumentSubmission | 7 | none — request only; the document goes to pii.subject_document and the verification to identity.guest_identity_verification | 1 | 0 | submitGuestIdentityDocument
identity | IdentityGuestVerification | 13 | identity.guest_identity_verification | 0 | 2 | getMyIdentityVerification, submitGuestIdentityDocument | One guest identity-document verification (5.3.21; decided 29 September, build pass): the document it checks, its status, the method and who decided.
identity | IdentityGuestVerificationPolicy | 14 | identity.guest_verification_policy | 1 | 1 | setGuestVerificationPolicy | The tenant's configurable identity workflow for guests (5.3.21; decided 29 September, build pass).
identity | LoginRequest | 5 |  | 1 | 0 | login | workstationId is required for a device door and absent from a browser door (CHG-DOOR-001, 2 October 2026).
identity | LoginResponse | 9 | none — computed | 0 | 1 | login
identity | MfaEnrolment | 7 | none — transient | 0 | 1 | enrolMfaMethod
identity | MfaMethod | 8 | identity.mfa_method | 0 | 2 | listMfaMethods, verifyMfaEnrolment
identity | PasswordPolicy | 13 | identity.password_policy | 1 | 1 | setPasswordPolicy | BL-144.
identity | PlatformStaffGrant | 9 | identity.platform_staff_grant | 0 | 1 | openPlatformStaffGrant | One platform operator's time-boxed access into this tenant (decided 28 September, audit R098).
identity | Principal | 9 | identity.principal | 0 | 1 | updatePrincipal
identity | RegisterGuestRequest | 6 |  | 1 | 0 | registerGuest
identity | Role | 10 | identity.role | 0 | 2 | createRole, updateRole
identity | SegregationRule | 9 | identity.segregation_rule | 0 | 1 | setSegregationRules | BL-147, 3.3.31 and 11.1.24.
identity | Session | 11 |  | 0 | 2 | getCurrentSession, selectRole
identity | TokenPair | 3 | none — transient | 0 | 1 | refreshToken
inventory | CreateGoodsReceiptRequest | 6 | none — request only | 1 | 0 | createGoodsReceipt
inventory | CreateInventoryItemRequest | 16 | none — request only | 1 | 0 | createInventoryItem
inventory | GoodsReceipt | 12 | inventory.goods_receipt + inventory.goods_receipt_line | 0 | 2 | createGoodsReceipt, rejectReceivedGoods
inventory | InventoryItem | 26 | inventory.inventory_item | 0 | 2 | createInventoryItem, updateInventoryItem
inventory | InventoryKitDefinition | 2 | none — composed of the item's inventory.kit_component rows | 1 | 1 | setInventoryKitDefinition | 4.4.20.
maintenance | InspectionTemplate | 10 | maintenance.inspection_template + maintenance.inspection_template_item | 1 | 1 | createInspectionTemplate
marketing-crm | AgentAvailability | 7 | marketing.agent_availability | 0 | 1 | setAgentAvailability
marketing-crm | Campaign | 24 | marketing.campaign | 0 | 3 | createCampaign, stopCampaign, updateCampaign
marketing-crm | Case | 23 | marketing.case | 0 | 1 | raiseMyCase
marketing-crm | CaseDetail | 26 | marketing.case | 0 | 1 | replyToMyCase
marketing-crm | Challenge | 14 | marketing.challenge | 1 | 1 | createChallenge | BL-022, CF-137.
marketing-crm | ClaimDeviceConsentRequest | 1 | none — request only | 1 | 0 | claimDeviceConsent
marketing-crm | ConsentPurposeConfig | 7 | marketing.consent_purpose + marketing.consent_purpose_channel | 0 | 1 | setConsentPurposes
marketing-crm | ConsentQuestion | 11 | marketing.consent_question + marketing.consent_question_version | 2 | 2 | createConsentQuestion, updateConsentQuestion | A venue-defined consent question asked at booking (decided 29 September, rev 3 REV3-26).
marketing-crm | ConsentState | 2 | none — projection over consent_record | 0 | 3 | claimDeviceConsent, getGuestConsents, recordConsent
marketing-crm | Conversation | 22 | marketing.conversation | 0 | 1 | handoverToAgent | 22.8.
marketing-crm | ConversationMessage | 8 | marketing.conversation_message + marketing.conversation_message_attachment | 0 | 1 | sendConversationMessage
marketing-crm | CookieBannerPreferenceCenterDesignerView | 21 | marketing.cookie_banner_design | 1 | 1 | setCookieBannerDesign | One version of a cookie banner and preference-centre design (pack 17.1.6).
marketing-crm | CookieConsentRuntime | 6 | none — assembled at read time from marketing.cookie_banner_design, marketing.tracking_technology and marketing.device_consent | 0 | 1 | getCookieConsentRuntime | What getCookieConsentRuntime gives the storefront tag loader and the app SDK gate (2.6.52, 2.6.58).
marketing-crm | CookieTrackingDigitalTechnologyRegistryView | 22 | marketing.tracking_technology | 1 | 1 | setTrackingTechnology | One governed tracking technology (pack 17.1.5 Registry Fields; BL-073 §4a).
marketing-crm | CreateCampaignRequest | 14 | none — request only | 1 | 0 | createCampaign
marketing-crm | CreateSegmentRequest | 11 | none — request only | 1 | 0 | createSegment
marketing-crm | DeviceConsent | 17 | marketing.device_consent + marketing.device_consent_category | 0 | 1 | recordDeviceConsent | One cookie decision by a visitor nobody has identified yet (BL-073 §4b, decided 29 September).
marketing-crm | DynamicFieldsQuestionsConditionalLogicView | 17 | marketing.form_definition_field + marketing.waiver_field_rule | 1 | 1 | setDynamicFieldQuestion | One field of a waiver version (pack 11.1.4).
marketing-crm | FormDefinition | 17 | marketing.form_definition + marketing.form_definition_field | 1 | 2 | createForm, getForm | CF-129, CL-04.
marketing-crm | FormSubmission | 12 | marketing.form_submission | 1 | 1 | submitForm | The acceptance record, and it is evidence.
marketing-crm | GuestConversation | 5 | none — a guest view of marketing.conversation and its guest-visible messages | 0 | 1 | getGuestConversation | A handed-over conversation as the guest sees it (getGuestConversation; Chinmay, 3 October 2026, Pattern 4; CHG-GCF-004).
marketing-crm | GuestConversationMessage | 5 | none — a guest view of marketing.conversation_message | 0 | 1 | sendGuestConversationMessage | One message as the guest sees it.
marketing-crm | GuestDevice | 14 | marketing.guest_device | 0 | 1 | registerGuestDevice
marketing-crm | GuestDocument | 9 | marketing.guest_document | 1 | 1 | uploadGuestDocument | BL-133.
marketing-crm | GuestIdentification | 7 |  | 0 | 1 | identifyGuest | The answer to "who is this" at a till, resolved from any identifier.
marketing-crm | GuestPreferences | 8 | marketing.guest_preference | 1 | 1 | updateGuestPreferences | What the guest likes, kept apart from what they permit (consent) and from who they are (the profile).
marketing-crm | GuestProfile | 17 | marketing.guest_profile | 0 | 1 | updateMyProfile
marketing-crm | InvitationCampaign | 11 | marketing.invitation_campaign | 1 | 1 | createInvitationCampaign | BL-150.
marketing-crm | LaunchResult | 5 | none — computed | 0 | 1 | launchCampaign
marketing-crm | LostItem | 17 | marketing.lost_item | 1 | 1 | recordLostItem | BL-021.
marketing-crm | LoyaltyPosition | 11 | marketing.loyalty_position | 0 | 3 | getGuestLoyalty, redeemLoyaltyPoints, setLeaderboardNickname
marketing-crm | LoyaltyProgramme | 9 | marketing.loyalty_programme + marketing.points_earning_rule + marketing.programme_tier | 1 | 2 | createLoyaltyProgramme, updateLoyaltyProgramme
marketing-crm | LoyaltyRuleSet | 4 | none — composed from the rule tables of one programme | 1 | 1 | setLoyaltyRules | Every rule a programme runs on, read and written as one thing.
marketing-crm | MarketingCustomerBadge | 9 | marketing.customer_badge | 1 | 1 | awardBadge | Taken from the backend workbook, 20 September.
marketing-crm | MarketingReward | 10 | marketing.reward | 1 | 1 | setReward | Taken from the backend workbook, 20 September.
marketing-crm | MarketingSubscription | 8 | marketing.subscription | 1 | 2 | getMarketingSubscription, setMarketingSubscription | Drafted 4 September.
marketing-crm | MessageTemplate | 11 | marketing.message_template | 1 | 2 | createMessageTemplate, updateMessageTemplate
marketing-crm | RecordConsentAnswersRequest | 4 | none — request only | 1 | 0 | recordConsentAnswers
marketing-crm | RecordConsentRequest | 6 | none — request only | 1 | 0 | recordConsent
marketing-crm | RecordDeviceConsentRequest | 11 | none — request only | 1 | 0 | recordDeviceConsent | What the banner or preference centre sends to recordDeviceConsent.
marketing-crm | Referral | 10 | marketing.referral | 1 | 1 | createReferral | BL-034.
marketing-crm | Review | 13 | marketing.review | 0 | 1 | submitReview
marketing-crm | Segment | 15 | marketing.segment + marketing.segment_criterion | 0 | 1 | createSegment
marketing-crm | SeoMetadata | 15 | control.seo_metadata | 1 | 2 | getSeoMetadata, setSeoMetadata | 22.11.1 to 22.11.12, CF-137.
marketing-crm | SubmitReviewRequest | 8 | none — request only | 1 | 0 | submitReview
marketing-crm | UrlRedirect | 9 | control.url_redirect | 1 | 1 | createUrlRedirect | 22.11.7.
marketing-crm | Wishlist | 2 | none — wrapper. The items are the table, keyed by subject | 0 | 2 | addToWishlist, getWishlist
orders | AddCartLineRequest | 10 | none — request only | 1 | 0 | addCartLine
orders | AppendEntitlementRequest | 5 | none — request only | 1 | 0 | appendEntitlementToMedia
orders | AppendEntitlementResult | 3 | none — computed | 0 | 1 | appendEntitlementToMedia
orders | ApplyCartPromoCodeRequest | 1 | none — request only | 1 | 0 | applyCartPromoCode
orders | BillingStatement | 10 | none — computed from orders.payment and payments.dunning_case | 0 | 1 | getBillingStatement | 2.14.19-2.14.23, 5.7.96, BL-100.
orders | Cart | 21 | orders.cart | 0 | 7 | addCartLine, applyCartPromoCode, createCart, extendCart, getCart, removeCartLine, updateCartLine
orders | CartMergeResult | 3 | none — computed | 0 | 1 | claimCart
orders | CloneTicketTemplateInput | 4 | none — request only | 1 | 0 | cloneTicketTemplate | What cloneTicketTemplate takes (decided 29 September, readiness close-out).
orders | CreateOrderRequest | 9 |  | 1 | 0 | createOrder
orders | CreatePaymentRequest | 12 |  | 1 | 0 | createPayment
orders | CreateRefundRequest | 8 |  | 1 | 0 | createRefund
orders | CreateResaleListingRequest | 3 | none — request only | 1 | 0 | createResaleListing | Request only; persisted as ResaleListing.
orders | CreateReservationRequest | 5 |  | 1 | 0 | createReservation
orders | EntitlementShare | 7 | none — a view of the identity.delegated_access row shareEntitlement writes | 0 | 1 | shareEntitlement | A second person's right to present an entitlement the owner still holds.
orders | ExchangeOrderRequest | 6 |  | 1 | 0 | exchangeOrderLines
orders | GroupArrivalCheckInAdmissionOperationsView | 17 | none — projection over orders state, assembled at read time from tables that already exist | 0 | 1 | listGroupArrivalCheck | What Group Arrival, Check-In & Admission Operations displays.
orders | GroupBooking | 21 | orders.group_booking | 0 | 2 | getGroupBooking, requestGroupBooking | BL-028.
orders | GroupBookingRequest | 10 |  | 1 | 0 | requestGroupBooking | Request only.
orders | GroupCheckInRequest | 6 | none — request only; lands in the check-in columns of `orders.group_visit_plan` | 1 | 0 | recordGroupCheckIn | What the group check-in desk records (BO-280).
orders | GroupVisitPlan | 27 | orders.group_visit_plan | 0 | 1 | recordGroupCheckIn | The day-of-visit record for one group booking: the operational plan, the sales-to-operations handover, and the group check-in (DM5, 29 September: data model for the agreed operations; MoM 31 Aug 4.7-…
orders | Invitation | 13 | orders.invitation | 0 | 1 | respondToInvitation | 8.1.3 to 8.1.5.
orders | ManualDiscountRequest | 8 | none — request only | 1 | 0 | applyManualDiscount
orders | MediaEntitlements | 7 | none — projection over entitlement and scan history | 0 | 1 | getMediaEntitlements
orders | ModifyOrderRequest | 5 |  | 1 | 0 | modifyOrder
orders | Order | 31 | orders.sales_order + orders.order_line | 0 | 7 | applyManualDiscount, checkoutCart, convertReservation, createOrder, getOrder, holdOrder, voidOrder
orders | OrderExchangeResult | 8 | none — computed | 0 | 2 | exchangeOrderLines, rescheduleOrder
orders | OrderModificationResult | 7 | none — computed | 0 | 1 | modifyOrder
orders | OrderResumeResult | 3 | none — computed | 0 | 1 | resumeOrder
orders | OrderStatement | 8 | none — computed from order, payment, refund and ledger | 0 | 1 | getOrderStatement
orders | OrderSyncResult | 3 | none — computed | 0 | 1 | syncOrders
orders | Payment | 19 | orders.payment | 0 | 4 | addTip, capturePayment, createPayment, inquirePaymentStatus
orders | PaymentProvider | 15 | payments.provider | 0 | 1 | setPaymentProvider | BL-116, CF-131.
orders | PaymentToken | 9 | payments.token | 0 | 1 | storePaymentToken | BL-116.
orders | Refund | 20 | orders.refund | 0 | 1 | createRefund
orders | RefundPolicy | 9 | orders.refund_policy + orders.refund_policy_time_band | 1 | 1 | setRefundPolicy | Venue-configured.
orders | ReissuedEntitlement | 5 | none — computed; both entitlements live in access.entitlement | 0 | 1 | reissueEntitlement | The zero-value reissue — the old entitlement voided, the new one issued, and the reason that links them.
orders | ResaleListing | 16 | orders.resale_listing | 0 | 1 | createResaleListing | BL-060.
orders | Reservation | 8 | orders.reservation + orders.reservation_line | 0 | 3 | createReservation, extendReservation, getReservation | An unpaid hold, not a booking.
orders | SetPaymentProviderRequest | 16 | none — request only; the provider lands in payments.provider and its rules in payments.routing_rule | 1 | 0 | setPaymentProvider | Request only.
orders | TicketProof | 5 | none — rendered on request, nothing is stored | 0 | 1 | previewProductTickets | A sample ticket from a template, marked as a proof on the artefact itself so it cannot be presented at a gate.
orders | TicketTemplate | 11 | orders.ticket_template + orders.ticket_template_channel | 0 | 4 | cloneTicketTemplate, createTicketTemplate, importTicketTemplate, updateTicketTemplate | BL-102.
orders | TicketTemplateImportInput | 3 | none — request only | 1 | 0 | importTicketTemplate | What importTicketTemplate takes (decided 29 September, readiness close-out).
orders | TicketTemplateRequest | 10 |  | 2 | 0 | createTicketTemplate, updateTicketTemplate | Request only; persisted as TicketTemplate.
orders | TicketTransfer | 12 | orders.ticket_transfer | 0 | 2 | claimTicketTransfer, transferOrderTickets
orders | VisitReminder | 7 | orders.visit_reminder | 1 | 2 | getVisitReminder, setVisitReminder | One reminder per booking, set by the guest.
orders | WalletPass | 9 | orders.wallet_pass | 0 | 1 | issueWalletPass | BL-029.
payments | DunningCase | 14 | payments.dunning_case | 0 | 1 | retryMyDunningPayment | BL-100.
payments | DunningPolicy | 8 | payments.dunning_policy | 1 | 1 | setDunningPolicy | 2.14.19-2.14.23, BL-100.
payments | PayInstalmentPlan | 12 | payments.instalment_plan + payments.instalment | 0 | 1 | createInstalmentPlan | 4.2.17.
payments | PayInstalmentPolicy | 9 | payments.instalment_policy | 1 | 1 | setInstalmentPolicy | 4.2.17, 2.14.19.
payments | PaymentProviderConnection | 12 | payments.provider_connection | 1 | 1 | createPaymentProviderConnection | Boards 2.2 and 2.4.
payments | RetryDunningPaymentRequest | 1 |  | 1 | 0 | retryMyDunningPayment | Request only.
promotions | Bundle | 22 | promotions.bundle + promotions.bundle_component | 0 | 3 | createBundle, getBundle, updateBundle
promotions | CodeDistributionAssignmentManagerInput | 5 | none — request only; stored as one promotions.code_assignment row (CouponCodeAssignment) and the coupon codes it assigns (CHG-FXC-005) | 1 | 0 | setCodeDistributionManager | What Code Distribution & Assignment Manager submits.
promotions | CodeDistributionAssignmentManagerView | 12 | none — projection over promotions state, assembled at read time from tables that already exist | 0 | 1 | setCodeDistributionManager | What Code Distribution & Assignment Manager displays.
promotions | ConflictAnalysis | 3 | none — computed | 0 | 1 | analysePromotionConflicts
promotions | CouponCampaign | 14 | promotions.coupon_campaign | 0 | 1 | createCouponCampaign
promotions | CouponCode | 16 | promotions.coupon_code | 0 | 1 | getCouponCode
promotions | CreateBundleRequest | 17 | none — request only | 1 | 0 | createBundle
promotions | CreateCouponCampaignRequest | 10 | none — request only | 1 | 0 | createCouponCampaign
promotions | CreatePromotionRequest | 17 | none — request only | 1 | 0 | createPromotion
promotions | EvaluatePromotionsRequest | 8 | none — request only | 1 | 0 | evaluatePromotions
promotions | Promotion | 24 | promotions.promotion | 0 | 3 | createPromotion, publishPromotion, updatePromotion
promotions | PromotionEvaluation | 4 | none — computed | 0 | 1 | evaluatePromotions
promotions | PromotionUsage | 7 | none — aggregated from ledger and orders | 0 | 1 | getPromotionUsage
public-api | ApiClient | 14 | control.api_client | 1 | 1 | createApiClient, setApiClientStatus | CF-135a.
public-api | ApiLicence | 9 | control.api_licence | 1 | 1 | setApiLicensing | 13.3.24, decision D5.
public-api | ApiVersion | 9 | control.api_version | 0 | 1 | deprecateApiVersion | 13.1.31 to 13.1.35, ADR-0026.
public-api | DeveloperAccount | 8 | control.developer_account | 1 | 1 | registerDeveloper | 13.1.6 to 13.1.9.
public-api | DeveloperMember | 7 | control.developer_member | 0 | 1 | setDeveloperMembers | One person at a developer organisation (setDeveloperMembers, 4 October 2026, CHG-FXC-005).
public-api | IntegrationListing | 12 | control.integration_listing | 0 | 1 | certifyIntegration | 13.1.50, decision D1.
public-api | ProductionAccessRequest | 14 | control.production_access_request | 0 | 1 | decideProductionAccess | A developer's request for production keys (17 September minutes, M17-06): sandbox, then certification, then production.
queue | CreateQueueRequest | 20 | none — request only | 1 | 0 | createQueue
queue | JoinQueueRequest | 8 | none — request only | 1 | 0 | joinQueue
queue | Queue | 31 | queue.queue + queue.queue_operating_window | 0 | 2 | createQueue, updateQueue
queue | WaitTime | 11 | none — computed from readings and throughput | 0 | 1 | getWaitTimes
queue | WaitingGuest | 25 | queue.entry | 0 | 2 | getWaitingGuest, joinQueue
reporting | Alert | 18 | reporting.alert | 0 | 1 | listAlerts | A raised alert.
reporting | AlertRule | 13 | reporting.alert_rule | 1 | 1 | setAlertRule | BL-152, CF-134.
reporting | CreateDashboardRequest | 6 | none — request only | 2 | 0 | createDashboard, updateDashboard
reporting | CreateReportRequest | 10 | none — request only | 2 | 0 | createReport, updateReport
reporting | Dashboard | 11 | reporting.dashboard + reporting.dashboard_tile | 0 | 3 | createDashboard, listDashboards, updateDashboard
reporting | DashboardData | 12 | none — computed | 0 | 1 | getDashboard
reporting | KpiDefinition | 12 | reporting.kpi_definition | 1 | 1 | createKpi | BI boards 2.5 and 10.2.
reporting | NaturalLanguageAnswer | 13 | none — computed | 0 | 1 | askReportingQuestion
reporting | ReportDefinition | 19 | reporting.report_definition + reporting.report_column + reporting.report_filter | 0 | 4 | createReport, getReport, saveNaturalLanguageQuery, updateReport
reporting | ReportResult | 8 | none — result set, cached in object storage | 0 | 1 | runReport
reporting | RunReportRequest | 5 | none — request only | 1 | 0 | runReport
reporting | SemanticModel | 5 | reporting.semantic_model | 1 | 1 | setSemanticModel | BI boards 3.3 and 10.6.
resources | CreateResourceHoldRequest | 8 | none — request only | 1 | 0 | createResourceHold
resources | MapResourceAvailability | 6 | none — computed from placed resources, bookings, holds and blocks | 0 | 1 | getMapResourceAvailability | What getMapResourceAvailability returns: every placed resource on one map, for one window, in one answer (rev 3 REV3-15).
resources | Resource | 17 | resources.resource | 2 | 4 | cloneResource, createResource, setResourceLifecycleState, updateResource | A specific object, not a quantity of interchangeable ones.
resources | ResourceAvailability | 3 |  | 0 | 1 | getResourceAvailability | Free windows, with setup and teardown already subtracted.
resources | ResourceBlock | 8 | resources.resource_block | 1 | 1 | createResourceBlock | Board 2.07.
resources | ResourceHold | 15 | resources.resource_reservation | 0 | 3 | createResourceHold, extendResourceHold, getResourceHold | A guest's pick on the map, held while they pay (decided 29 September, rev 3 REV3-15).
resources | ResourcePackage | 14 | resources.resource_package | 2 | 2 | createResourcePackage, updateResourcePackage | Board 1.08.
resources | ResourceRequirement | 12 | resources.resource_requirement | 0 | 1 | setExperienceResourceRequirements | A type and a quantity, never a named resource.
resources | ResourceSchedule | 9 | resources.resource_schedule | 1 | 1 | setResourceSchedule | Boards 2.03 and 2.04.
retail | CreateMerchandiseRequest | 12 | none — request only | 1 | 0 | createMerchandise
retail | CreateRetailReturnRequest | 7 | none — request only | 1 | 0 | createRetailReturn
retail | CreateRetailSaleRequest | 7 | none — request only | 1 | 0 | createRetailSale
retail | MerchandiseItem | 16 | retail.merchandise | 0 | 2 | createMerchandise, updateMerchandise
retail | MerchandiseReservation | 9 | retail.reservation + retail.reservation_line | 0 | 1 | reserveMerchandise
retail | PriceCheck | 10 | none — computed | 0 | 1 | lookupMerchandise
retail | RetailReturn | 15 | retail.return + retail.return_line | 0 | 1 | createRetailReturn
retail | RetailSale | 14 | retail.sale + retail.sale_line | 0 | 2 | createRetailSale, getRetailSale
retail | ReturnPolicy | 10 | retail.return_policy | 1 | 2 | getReturnPolicy, setReturnPolicy
retail | ShopAndDrop | 15 | retail.shop_and_drop + retail.shop_and_drop_line | 0 | 3 | collectShopAndDrop, createShopAndDrop, lookupShopAndDrop
seating | AccessibleSeating | 5 | seating.accessible | 1 | 1 | setAccessibleSeating | Boards 7.6 to 7.8.
seating | CreateSeatHoldRequest | 5 | none — request only | 1 | 0 | createSeatHold
seating | SeatAvailability | 7 | none — computed from seat, hold and block | 0 | 1 | getSeatAvailability
seating | SeatCategory | 8 | seating.seat_category | 0 | 2 | createSeatCategory, updateSeatCategory
seating | SeatHold | 11 | seating.seat_reservation | 0 | 3 | createSeatHold, extendSeatHold, getSeatHold
seating | SeatRecommendationRequest | 6 | none — request only | 1 | 0 | recommendSeats
seating | SeatRecommendationRules | 6 | seating.recommendation_rule | 1 | 1 | setSeatRecommendationRules | Board 9, and the 21 August minute: *"best-seat ranking… must be configurable per seat map/event."* Five kinds, one scoring model — five algorithms would eventually contradict each other.
shift | CashMovement | 14 | orders.cash_movement | 0 | 1 | createCashMovement
shift | CloseShiftRequest | 6 |  | 1 | 0 | submitShiftCount
shift | CreateCashMovementRequest | 7 |  | 1 | 0 | createCashMovement
shift | Denomination | 7 | platform.denomination | 0 | 2 | listDenominations, setDenominations | Raised in review by Tanmay: denominations belong in a table, not in JSON.
shift | DepositBox | 18 | orders.deposit_box + orders.deposit_box_opening_denomination + orders.deposit_box_foreign_holding | 1 | 2 | allocateDepositBox, withdrawFromDepositBox | 5.8.
shift | NoSaleEvent | 8 | orders.no_sale_event | 0 | 1 | recordNoSale
shift | OpenShiftRequest | 5 |  | 1 | 0 | openShift
shift | SetDenominationsRequest | 3 |  | 1 | 0 | setDenominations | Request only.
shift | Shift | 36 | orders.pos_shift + orders.pos_shift_approval + orders.pos_shift_incident | 0 | 9 | acceptShiftVariance, approveShiftOpen, getCurrentShift, getWorkstationShift, openShift, rejectShiftVariance, reopenShift, resumeShift, suspendShift | approvals and incidents are child rows (26 September, pull audit R099): orders.pos_shift_approval and orders.pos_shift_incident, one row per item, keyed to the shift.
shift | ShiftCloseResult | 7 | none — computed | 0 | 1 | closeShift
shift | ShiftCountReceipt | 6 | none — computed | 0 | 2 | giveShiftVarianceReason, submitShiftCount | What submitShiftCount returns to the cashier: what happens next, never the figure (CHG-FIN-003).
shift | ShiftVarianceReasonRequest | 2 | orders.pos_shift | 1 | 0 | giveShiftVarianceReason | The reason for a difference within the threshold, given after the blind count is locked (giveShiftVarianceReason; the client's policy of 6 October 2026, T10.1; CHG-R4-019).
shift | TillShiftPolicy | 11 | orders.till_shift_policy | 1 | 2 | getTillShiftPolicy, setTillShiftPolicy | The venue's opening, closing and exception rules for every till (CHG-CSP-020; POS-019; DI-309).
subscription | CreatePlanRequest | 13 | none — request only | 2 | 0 | createPlan, createPlanVersion
subscription | CreateTenantRequest | 6 | none — request only | 1 | 0 | createTenant
subscription | LicenceAddOn | 7 | control.licence_add_on + control.licence_add_on_limit | 1 | 0 | addLicenceAddOn | Belongs to the tenant, not the plan.
subscription | LicencePosition | 5 | none — union of the tenant's plan (control.tenant.plan_id -> subscription.plan_module, subscription.plan_limit) and its add-ons (control.licence_add_on, control.licence_add_on_limit by tenant_id) | 0 | 2 | addLicenceAddOn, getTenantLicences
subscription | ModuleListing | 14 | subscription.module_listing | 1 | 2 | listModuleCatalogue, setModuleListing | Board 4.6.
subscription | Plan | 18 | subscription.plan + subscription.plan_module + subscription.plan_limit | 0 | 2 | createPlan, createPlanVersion | A plan's modules and limits are rows, keyed on plan_id.
subscription | SetSubscriptionRequest | 5 | none — request only | 1 | 0 | setSubscription
subscription | Subscription | 11 | subscription.contract | 0 | 1 | setSubscription
subscription | Tenant | 22 | control.tenant | 0 | 4 | createTenant, reactivateTenant, suspendTenant, updateTenant
subscription | TerminationSchedule | 6 | none — projection of control.tenant's termination columns (termination_scheduled_at, termination_retention_until, termination_requested_by_principal_id); isReversible is computed from the retention date | 0 | 1 | terminateTenant
tenancy | ConfigureWorkstationRequest | 14 |  | 1 | 0 | configureWorkstation
tenancy | CreateScopeNodeRequest | 4 |  | 1 | 0 | createOrgUnit
tenancy | DeviceAssignment | 11 | tenancy.device_assignment | 1 | 2 | getDeviceAssignment, setDeviceAssignment | 16.2.9 to 16.2.11.
tenancy | OrgUnit | 8 | platform.scope | 0 | 2 | createOrgUnit, updateOrgUnit
tenancy | Outlet | 17 | platform.outlet | 1 | 3 | createOutlet, getOutlet, updateOutlet
tenancy | RegionSettings | 17 | platform.region_settings | 1 | 2 | getRegionSettings, updateRegionSettings
tenancy | SaleBoard | 7 | platform.sale_board | 2 | 3 | createSaleBoard, listSaleBoards, updateSaleBoard
tenancy | VenueSettings | 31 | platform.venue_settings | 2 | 2 | setVenueSettings, setVenueSettingsDefaults | Venue-level operational configuration that no other level can answer.
tenancy | Workstation | 23 | platform.workstation | 0 | 1 | configureWorkstation
transport | CreatePassTypeRequest | 11 | none — request only | 1 | 0 | createTransportPassType
transport | CreateStationRequest | 6 | none — request only | 1 | 0 | createTransportStation
transport | CreateTimetableRequest | 7 | none — request only | 1 | 0 | createTransportTimetable
transport | CreateTransportRouteRequest | 8 | none — request only | 1 | 0 | createTransportRoute
transport | Departure | 11 | transport.departure | 0 | 1 | updateTransportDeparture
transport | DepartureOffer | 12 | none — projection | 0 | 2 | getNextTransportDeparture, getTransportDeparture
transport | FareQuote | 7 | none — computed | 0 | 1 | quoteTransportFare
transport | FareQuoteRequest | 7 | none — request only | 1 | 0 | quoteTransportFare
transport | FareTable | 10 | transport.fare_table + transport.fare_passenger_type + transport.fare_matrix_cell | 0 | 2 | getTransportFareTable, setTransportFareTable
transport | FavouriteRoute | 10 | transport.favourite_route | 0 | 1 | saveFavouriteRoute | Unique per guest, venue and ordered pair of stations.
transport | ImportTransportNetworkRequest | 3 | none — request only | 1 | 0 | importTransportNetwork
transport | PassType | 14 | transport.pass_type | 0 | 2 | createTransportPassType, updateTransportPassType
transport | RouteMap | 6 | none — projection | 0 | 1 | getTransportRouteMap
transport | SetFareTableRequest | 6 | none — request only | 1 | 0 | setTransportFareTable
transport | Station | 8 | transport.station | 0 | 2 | createTransportStation, updateTransportStation
transport | Timetable | 13 | transport.timetable + transport.timetable_run | 0 | 3 | createTransportTimetable, publishTransportTimetable, withdrawTransportTimetable
transport | TransportNetworkImport | 11 | transport.network_import | 0 | 2 | applyTransportNetworkImport, importTransportNetwork
transport | TransportRoute | 13 | transport.route + transport.route_stop | 0 | 4 | createTransportRoute, getTransportRoute, setTransportRouteStatus, updateTransportRoute
venue-map | BookableVenueMaps | 2 |  | 0 | 1 | listBookableVenueMaps | What listBookableVenueMaps returns: the published maps of one venue that carry bookable spots (decided 29 September, readiness close-out).
venue-map | PlacedResource | 12 | venuemap.placed_resource | 0 | 1 | setPlacedResource | A bookable resource where it stands on the map (decided 29 September, rev 3 REV3-15 and GAP-C2): cabana B09 on the Beach, 15 guests, Large.
venue-map | SetPlacedResourceRequest | 13 |  | 1 | 0 | setPlacedResource | What setPlacedResource takes: a PlacedResource without its server-owned fields.
venue-map | SetVenuePointRequest | 23 |  | 1 | 0 | setVenuePoint | What setVenuePoint takes: a VenuePoint without its server-owned fields, plus the point to amend.
venue-map | VenueMap | 19 | venuemap.map | 1 | 3 | createVenueMap, publishVenueMap, setVenueMapArtwork | A park map, or a floor plan.
venue-map | VenueMapDetail | 6 |  | 0 | 1 | getVenueMap | 19.2.55.
venue-map | VenueMapGraph | 6 |  | 0 | 1 | getVenueMapGraph | 19.2.56.
venue-map | VenueMapImportJob | 15 | venuemap.import_job | 0 | 1 | importVenueGeometry | Two-phase, following seating.ImportJob, and carrying its lesson: a job that finds nothing is not a successful job.
venue-map | VenuePoint | 22 | venuemap.point | 0 | 1 | setVenuePoint | 19.2.57 to 19.2.60.
venue-map | VisitPlan | 17 | venuemap.visit_plan | 0 | 3 | generateVisitPlan, getVisitPlan, updateVisitPlan | A guest's visit plan (29 September, MOB-6): the Plan tab.
venue-map | VisitPlanBooking | 5 | none — computed; the lines are orders.cart_line rows | 0 | 1 | bookVisitPlan | What bookVisitPlan returns (29 September, MOB-6): the cart handoff.
venue-map | VisitPlanRequest | 13 | none — request only; kept as `inputs` on venuemap.visit_plan | 1 | 0 | generateVisitPlan | What generateVisitPlan takes (29 September, MOB-6): the Plan tab's form on GST-051 and WEB-050.
venue-map | VisitPlanUpdate | 2 | none — request only; lands as a new version of venuemap.visit_plan_item rows | 1 | 0 | updateVisitPlan | What updateVisitPlan takes (29 September, MOB-6).
wallet | GiftCard | 9 | wallet.gift_card | 0 | 1 | getGiftCard
wallet | Wallet | 10 | wallet.wallet + wallet.credit_lot | 0 | 3 | getWallet, loadGameCredits, topUpWallet
wallet | WalletAutoReloadSetting | 10 | wallet.auto_reload_setting | 1 | 2 | getWalletAutoReloadSetting, setWalletAutoReloadSetting | 4.2.17, 4.3.28.
wallet | WalletConfigurationVersion | 6 | wallet.configuration_version | 0 | 2 | publishWalletConfiguration, restoreWalletConfigurationVersion | Boards 1.10 and 10.8.
wallet | WalletExitBalance | 8 | none — computed from wallet.wallet, wallet.credit_lot and held offline transactions | 0 | 1 | getWalletExitBalance
wallet | WalletExitSettlement | 13 | wallet.exit_settlement | 0 | 1 | settleWalletAtExit | 4.3.4.
wallet | WalletFundingRules | 12 | wallet.funding_rule | 1 | 1 | setWalletFundingRules | Board 2, which is the 27 August minute one screen for one.
wallet | WalletRefundPolicy | 7 | wallet.refund_policy | 1 | 1 | setWalletRefundPolicy | Boards 7.4 and 7.5.
wallet | WalletTransaction | 11 | wallet.wallet_transaction | 0 | 1 | transferWalletBalance
white-label | AppBuild | 15 | whitelabel.app_build | 0 | 2 | getAppBuild, requestAppBuild | One build of the tenant's branded app (decided 24 September, M24-08).
white-label | AppIcons | 5 | none — embedded in tenant_config | 0 | 2 | getAppIcons, setAppIcons
white-label | Banner | 11 | whitelabel.banner | 1 | 2 | createBanner, updateBanner
white-label | BookingFlow | 11 | whitelabel.booking_flow | 1 | 4 | createBookingFlowDefinition, getBookingFlow, getPublishedBookingFlow, updateBookingFlowDefinition | A venue's booking flow (decided 29 September, W12: operators pick their flows, see which steps are required, set their own order).
white-label | BookingFlowConfig | 29 | none — embedded in tenant_config | 1 | 2 | getBookingFlowConfig, setBookingFlowConfig | Set per tenant, with a per-venue override (decided 29 September, rev 3 CFG-11).
white-label | BookingFlowValidation | 2 | none — computed | 0 | 1 | validateBookingFlow
white-label | BrandIdentity | 12 | none — embedded in tenant_config | 1 | 2 | getBrandIdentity, setBrandIdentity | Every *AssetRef here is a MediaAsset id from the assets library (createUpload then completeUpload), PNG or SVG and at most 2 MB (decided 28 September, audit R270).
white-label | ConfigDiff | 3 | none — computed | 0 | 1 | diffConfigVersion
white-label | ConfigValidationReport | 4 | none — computed | 0 | 1 | validateTenantConfig
white-label | ConfigVersion | 13 | whitelabel.config_version | 0 | 1 | publishTenantConfig
white-label | ContentBlock | 12 | control.content_block | 1 | 3 | createContentBlock, publishContentBlock, updateContentBlock | BL-172.
white-label | ContentPage | 11 | whitelabel.content_page | 1 | 2 | createContentPage, updateContentPage
white-label | CustomDomain | 17 | whitelabel.custom_domain | 0 | 5 | claimCustomDomain, listCustomDomains, regenerateDomainToken, setPrimaryDomain, verifyCustomDomain | 24 August.
white-label | DeepLinkScheme | 3 | none — derived from the primary domain and the published configuration | 0 | 1 | getDeepLinkScheme | The URL patterns a tenant's own site uses to link into the storefront and the app (CHG-CSA-037).
white-label | FaqCategory | 5 | whitelabel.faq_category + whitelabel.faq_entry | 0 | 1 | setFaqs
white-label | FeatureToggle | 5 | whitelabel.feature_toggle | 0 | 2 | getFeatureToggles, setFeatureToggles
white-label | FontConfig | 6 | none — embedded in tenant_config | 1 | 2 | getFonts, setFonts
white-label | FooterConfig | 6 | whitelabel.footer_config + whitelabel.footer_config_column + whitelabel.footer_config_social_link | 1 | 1 | setFooter | BL-002.
white-label | GuidedChoice | 14 | whitelabel.guided_choice + whitelabel.guided_choice_question + whitelabel.guided_choice_answer | 1 | 6 | createGuidedChoice, getPublishedGuidedChoice, proposeGuidedChoice, publishGuidedChoice, unpublishGuidedChoice, updateGuidedChoice | Help me choose (decided 29 September, rev 3 REV3-11).
white-label | HeaderConfig | 5 | none — embedded in tenant_config | 1 | 1 | setHeader
white-label | HomepageLayout | 4 | whitelabel.homepage_layout + whitelabel.homepage_section | 1 | 2 | getHomepageLayout, setHomepageLayout | The client-approved web and app wireframes are the layout (Chinmay, 2 October, workbook Q163; CHG-CSA-040): sections, their order and their options follow the approved wireframes and change only wher…
white-label | LanguageConfig | 5 | none — embedded in tenant_config | 0 | 1 | setLanguages
white-label | ModuleEnablement | 5 | whitelabel.module_enablement | 0 | 2 | getModuleEnablement, setModuleEnablement
white-label | NavigationConfig | 4 | whitelabel.navigation_config + whitelabel.navigation_item | 1 | 2 | getNavigation, setNavigation | The mobile tab set is venue configuration (decided 29 September, MOB-1; 29 September brief decision 6).
white-label | PlatformSubdomain | 4 | none — derived from the tenant's slug and its cell | 0 | 1 | getPlatformSubdomain | Every tenant's own address on TICVAI (Chinmay, 2 October: "subdomain plus CNAME"; DI-283; CHG-CSA-043).
white-label | Policy | 9 | whitelabel.policy | 0 | 2 | listPolicies, setPolicy
white-label | Preview | 7 | none — short-lived, cache only | 0 | 1 | createPreview
white-label | PromoBlock | 11 | whitelabel.promo_block | 1 | 3 | createPromoBlock, listPromoBlocks, updatePromoBlock
white-label | PublishReviewPolicy | 4 | whitelabel.publish_review_policy | 1 | 2 | getPublishReviewPolicy, setPublishReviewPolicy | Whether publishing goes through a review step (CHG-CSA-042).
white-label | PublishedFaqCategory | 4 | none — a public projection of whitelabel.faq_category + whitelabel.faq_entry | 0 | 1 | listPublishedFaqs | One FAQ category with its published entries only (listPublishedFaqs).
white-label | PublishedPolicy | 6 | none — a public projection of whitelabel.policy | 0 | 1 | listPublishedPolicies | The current version of one policy as a guest reads it (listPublishedPolicies).
white-label | PublishedTenantConfig | 25 | none — computed from the current ConfigVersion snapshot and the live status on whitelabel.tenant_config | 0 | 1 | getPublishedTenantConfig | The public view of the tenant's configuration (getPublishedTenantConfig, decided 2 October, GFIX-1).
white-label | SitePackage | 9 | whitelabel.site_package | 0 | 2 | exportSitePackage, getSitePackage | A self-hosting package of one published version (exportSitePackage, CHG-CSA-038).
white-label | SiteSetupProgress | 7 | whitelabel.site_setup_progress | 1 | 2 | getSiteSetupProgress, setSiteSetupProgress | The Site Builder's saved progress, one row per tenant (decided 29 September, W12 and M24-05).
white-label | StorePublishingChecklist | 2 | none — computed | 0 | 2 | getStoreAccounts, setStoreAccounts
white-label | StorefrontAnalyticsProvider | 13 | whitelabel.analytics_provider | 1 | 1 | setAnalyticsProvider | One analytics platform the storefront or app reports to (22.10.29, 29 September build).
white-label | TenantAppStatus | 19 | none — computed | 0 | 2 | getTenantAppStatus, setMaintenanceMode | Computed on read.
white-label | TenantConfig | 28 | whitelabel.tenant_config | 0 | 2 | getTenantConfig, restoreConfigVersion | The tenant's working draft, one row per tenant (see the header).
white-label | Theme | 10 | none — embedded in tenant_config | 1 | 2 | getTheme, setTheme
white-label | UpdateContentPageRequest | 8 | none — request only; the fields land on whitelabel.content_page | 1 | 0 | updateContentPage | The body of updateContentPage: the fields a tenant edits.
white-label | WhiteLabelStorefrontSessionBatch | 8 | none — request only; published as storefront.sessionEvent through platform.outbox | 1 | 0 | recordStorefrontSessionEvents | One beacon from the storefront or guest-app runtime (8.3.40; decided 29 September, build pass, group G2).
workforce | AttendanceRecord | 16 | workforce.attendance | 0 | 1 | recordAttendance
workforce | RotaAssignment | 17 | workforce.rota_assignment | 2 | 2 | createRotaAssignment, updateRotaAssignment

## Fields
Service | Operation | Where | Field | Type | Required | Notes
OrderService | abandonCart | param (path) | cartId | string (uuid) | yes
OrderService | abandonCart | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | acceptFnbOrder | request | estimatedReadyAt | string (date-time)
FnbService | acceptFnbOrder | request | stationId | string (uuid)
FnbService | acceptFnbOrder | request | recordedAt | string (date-time) | yes | Device time of the act (offline-capable; replayed in this order).
FnbService | acceptFnbOrder | response | id | string (uuid) | yes
FnbService | acceptFnbOrder | response | orderNumber | string | yes
FnbService | acceptFnbOrder | response | outletId | string (uuid) | yes
FnbService | acceptFnbOrder | response | paymentTiming | object |  | The outlet's payment timing when the order was placed (CHG-CSA-010), kept as a snapshot. (read-only)
FnbService | acceptFnbOrder | response | sentToKitchenAt | string (date-time) |  | When the order's kitchen tickets were created. (read-only; nullable)
FnbService | acceptFnbOrder | response | serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery) | yes
FnbService | acceptFnbOrder | response | tableVisitId | string (uuid) |  | (nullable)
FnbService | acceptFnbOrder | response | status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) | yes | The full lifecycle from 4.6.35.
FnbService | acceptFnbOrder | response | lines | array of object | yes
FnbService | acceptFnbOrder | response | lines[].id | string (uuid) | yes
FnbService | acceptFnbOrder | response | lines[].menuItemId | string (uuid) | yes
FnbService | acceptFnbOrder | response | lines[].quantity | integer | yes | (min 1)
FnbService | acceptFnbOrder | response | lines[].modifierOptionIds | array of string (uuid)
FnbService | acceptFnbOrder | response | lines[].note | string |  | Free text to the kitchen. (max length 200)
FnbService | acceptFnbOrder | response | lines[].seatNumber | integer |  | Which cover ordered it. (nullable)
FnbService | acceptFnbOrder | response | lines[].course | integer |  | Course grouping, so the kitchen fires in sequence. (nullable)
FnbService | acceptFnbOrder | response | lines[].redeemEntitlementId | string |  | A meal combo redeemed at the till or by a scan (29 September, MOB-4; applied 30 September). (nullable)
FnbService | acceptFnbOrder | response | lines[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) |  | The full lifecycle from 4.6.35.
FnbService | acceptFnbOrder | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | acceptFnbOrder | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | acceptFnbOrder | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | acceptFnbOrder | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | acceptFnbOrder | response | lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | acceptFnbOrder | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | acceptFnbOrder | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | acceptFnbOrder | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | acceptFnbOrder | response | salesOrderId | string (uuid) |  | Retyped 29 September (SD-046), and format: uuid since ADR-0056 (30 September): every id is a uuid, so this joins orders.sales_order.id. (nullable)
FnbService | acceptFnbOrder | response | updatedAt | string (date-time) |  | Taken from their fnb.order. (nullable)
FnbService | acceptFnbOrder | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | acceptFnbOrder | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | acceptFnbOrder | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | acceptFnbOrder | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | acceptFnbOrder | response | taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | acceptFnbOrder | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | acceptFnbOrder | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | acceptFnbOrder | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | acceptFnbOrder | response | kitchenTicketId | string (uuid) |  | (nullable)
FnbService | acceptFnbOrder | response | kitchenTickets | array of KitchenTicket |  | The kitchen tickets this order created, one per station (SD-046). (read-only)
FnbService | acceptFnbOrder | response | kitchenTickets[].id | string (uuid) | yes
FnbService | acceptFnbOrder | response | kitchenTickets[].orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | acceptFnbOrder | response | kitchenTickets[].orderNumber | string
FnbService | acceptFnbOrder | response | kitchenTickets[].outletId | string (uuid) | yes
FnbService | acceptFnbOrder | response | kitchenTickets[].tableLabel | string |  | (nullable)
FnbService | acceptFnbOrder | response | kitchenTickets[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | acceptFnbOrder | response | kitchenTickets[].coursing | object |  | BL-131. (nullable)
FnbService | acceptFnbOrder | response | kitchenTickets[].buzzerCode | string |  | BL-128. (nullable)
FnbService | acceptFnbOrder | response | kitchenTickets[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | acceptFnbOrder | response | kitchenTickets[].priority | integer |  | Higher fires sooner.
FnbService | acceptFnbOrder | response | kitchenTickets[].prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | acceptFnbOrder | response | kitchenTickets[].prioritiseReason | string |  | (nullable)
FnbService | acceptFnbOrder | response | kitchenTickets[].lines | array of object | yes
FnbService | acceptFnbOrder | response | kitchenTickets[].lines[].lineId | string (uuid) | yes
FnbService | acceptFnbOrder | response | kitchenTickets[].lines[].name | string | yes
FnbService | acceptFnbOrder | response | kitchenTickets[].lines[].quantity | integer | yes
FnbService | acceptFnbOrder | response | kitchenTickets[].lines[].modifiers | array of string
FnbService | acceptFnbOrder | response | kitchenTickets[].lines[].note | string |  | (nullable)
FnbService | acceptFnbOrder | response | kitchenTickets[].lines[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | acceptFnbOrder | response | kitchenTickets[].lines[].refireOfLineId | string (uuid) |  | Set on a refire. (read-only; nullable)
FnbService | acceptFnbOrder | response | kitchenTickets[].lines[].refireReason | object |  | (read-only; nullable)
FnbService | acceptFnbOrder | response | kitchenTickets[].lines[].isChargeable | boolean |  | A refire's chargeable flag. (read-only; nullable)
FnbService | acceptFnbOrder | response | kitchenTickets[].lines[].course | integer |  | (nullable)
FnbService | acceptFnbOrder | response | kitchenTickets[].lines[].stationId | string (uuid) |  | (nullable)
FnbService | acceptFnbOrder | response | kitchenTickets[].lines[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | acceptFnbOrder | response | kitchenTickets[].createdAt | string (date-time) | yes
FnbService | acceptFnbOrder | response | kitchenTickets[].targetReadyAt | string (date-time) |  | (nullable)
FnbService | acceptFnbOrder | response | kitchenTickets[].elapsedSeconds | integer
FnbService | acceptFnbOrder | response | kitchenTickets[].visitId | string (uuid) |  | The table visit the ticket is for (4 October 2026, CHG-FXC-011; KIT-002): the {visitId} notifyServer takes. (read-only; nullable)
FnbService | acceptFnbOrder | response | estimatedReadyAt | string (date-time) |  | (nullable)
FnbService | acceptFnbOrder | response | createdAt | string (date-time) | yes
FnbService | acceptFnbOrder | response | recordedAt | string (date-time)
FnbService | acceptFnbOrder | response | syncedAt | string (date-time) |  | (nullable)
FnbService | acceptFnbOrder | param (path) | orderId | string (uuid) | yes
FnbService | acceptFnbOrder | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | acceptShiftVariance | request | reason | string | yes | Retained for audit. (min length 3; max length 500)
OrderService | acceptShiftVariance | request | supervisorStepUp | object |  | The supervisor accepting, signing on this device (CHG-RUL-019).
OrderService | acceptShiftVariance | request | supervisorStepUp.principalId | string (uuid) | yes | The supervisor signing.
OrderService | acceptShiftVariance | request | supervisorStepUp.credential | string | yes | The supervisor's staff PIN, as they sign in at a till with it. (max length 512)
OrderService | acceptShiftVariance | response | id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | acceptShiftVariance | response | workstationId | string (uuid) | yes
OrderService | acceptShiftVariance | response | venueId | string (uuid) | yes
OrderService | acceptShiftVariance | response | scopePath | string | yes
OrderService | acceptShiftVariance | response | principalId | string (uuid) | yes | Who opened it.
OrderService | acceptShiftVariance | response | principalDisplayName | string
OrderService | acceptShiftVariance | response | incidents | array of object |  | BL-097.
OrderService | acceptShiftVariance | response | incidents[].kind | enum (noSale, drawerOpen, override, voidAfterPayment, guestDispute, tillJam, priceQuery, other)
OrderService | acceptShiftVariance | response | incidents[].at | string (date-time)
OrderService | acceptShiftVariance | response | incidents[].principalId | string (uuid)
OrderService | acceptShiftVariance | response | incidents[].note | string |  | (nullable)
OrderService | acceptShiftVariance | response | status | ShiftStatus: enum (pendingApproval, open, suspended, pendingVariance, pendingClosure, closed, autoClosed) | yes
OrderService | acceptShiftVariance | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | acceptShiftVariance | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | acceptShiftVariance | response | depositBoxCode | string |  | (nullable)
OrderService | acceptShiftVariance | response | bagNumber | string |  | (nullable)
OrderService | acceptShiftVariance | response | openingFloat | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | acceptShiftVariance | response | openingFloat.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | acceptShiftVariance | response | openingFloat.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | acceptShiftVariance | response | openingFloat.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | acceptShiftVariance | response | salesTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | acceptShiftVariance | response | salesTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | acceptShiftVariance | response | salesTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | acceptShiftVariance | response | salesTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | acceptShiftVariance | response | refundsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | acceptShiftVariance | response | refundsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | acceptShiftVariance | response | refundsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | acceptShiftVariance | response | refundsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | acceptShiftVariance | response | liftsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | acceptShiftVariance | response | liftsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | acceptShiftVariance | response | liftsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | acceptShiftVariance | response | liftsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | acceptShiftVariance | response | expectedCash | object |  | 26 September, pull audit R207. (read-only; nullable)
OrderService | acceptShiftVariance | response | expectedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | acceptShiftVariance | response | expectedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | acceptShiftVariance | response | expectedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | acceptShiftVariance | response | countedCash | object |  | What the close count found. (read-only; nullable)
OrderService | acceptShiftVariance | response | countedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | acceptShiftVariance | response | countedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | acceptShiftVariance | response | countedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | acceptShiftVariance | response | variance | object |  | Counted minus expected, as ShiftCloseResult.variance. (read-only; nullable)
OrderService | acceptShiftVariance | response | variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | acceptShiftVariance | response | variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | acceptShiftVariance | response | variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | acceptShiftVariance | response | cashierReason | enum (tillError, unrecordedRefund, miscount, other) |  | What the cashier said went wrong, given with the blind count (CloseShiftRequest.cashierReason, DI-803) without seeing the variance; the supervisor reads it beside the variance on BO-040 (CHG-FIN-003). (read-only; nullable)
OrderService | acceptShiftVariance | response | cashierNote | string |  | The cashier's note with the count (CloseShiftRequest.notes; CHG-FIN-003). (max length 1000; read-only; nullable)
OrderService | acceptShiftVariance | response | varianceReasonRequired | boolean |  | Computed, not stored (CHG-R4-019): true while the shift is pendingClosure because its count differs from the expected figure within the threshold and no cashierReason is recorded. (read-only)
OrderService | acceptShiftVariance | response | heldLeaseCount | integer |  | Inventory leases currently held by this workstation.
OrderService | acceptShiftVariance | response | openedAt | string (date-time) | yes
OrderService | acceptShiftVariance | response | businessDate | string (date) |  | The business day the shift belongs to (12 October 2026, CHG-R6-032): the venue-local date of openedAt taken against the venue's businessDayCutoff (tenancy VenueSettings, inheriting the tenant default… (read-only)
OrderService | acceptShiftVariance | response | recordedAt | string (date-time) |  | When the device recorded the open.
OrderService | acceptShiftVariance | response | suspendedAt | string (date-time) |  | (nullable)
OrderService | acceptShiftVariance | response | suspendReason | string |  | The reason given to suspendShift. (max length 200; nullable)
OrderService | acceptShiftVariance | response | closedAt | string (date-time) |  | (nullable)
OrderService | acceptShiftVariance | response | closedByPrincipalId | string (uuid) |  | Who submitted the close count. (nullable)
OrderService | acceptShiftVariance | response | recountRequestedAt | string (date-time) |  | Set by rejectShiftVariance, cleared by the cashier's recount (decided 2 October 2026, Chinmay; DEC-175; CHG-CSP-013; DI-804). (read-only; nullable)
OrderService | acceptShiftVariance | response | recountRequestedByPrincipalId | string (uuid) |  | The supervisor who sent the count back (CHG-CSP-013). (read-only; nullable)
OrderService | acceptShiftVariance | response | recountReason | string |  | The supervisor's reason, shown to the cashier; never an amount (CHG-CSP-013, CHG-FIN-003). (max length 500; read-only; nullable)
OrderService | acceptShiftVariance | response | countNumber | integer |  | How many close counts the shift has had: 0 before the first, 1 after it, 2 after a recount (CHG-CSP-013). (min 0; read-only)
OrderService | acceptShiftVariance | response | syncedAt | string (date-time) |  | Null while the shift has unsynced operations. (nullable)
OrderService | acceptShiftVariance | response | approvals | array of object
OrderService | acceptShiftVariance | response | approvals[].kind | enum (open, close, variance) | yes | open from approveShiftOpen, close from approveShiftClose, variance from acceptShiftVariance.
OrderService | acceptShiftVariance | response | approvals[].principalId | string (uuid) | yes
OrderService | acceptShiftVariance | response | approvals[].at | string (date-time) | yes
OrderService | acceptShiftVariance | response | approvals[].reason | string
OrderService | acceptShiftVariance | param (path) | shiftId | string (uuid) | yes
OrderService | acceptShiftVariance | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | acquireInventoryHold | request | holderKind | InventoryHoldHolderKind: enum (workstation, cart) |  | Who holds the units (decided 29 September, SD-023). (default workstation)
CatalogueService | acquireInventoryHold | request | cartId | string (uuid) |  | Required when holderKind is cart, else 400. (nullable)
CatalogueService | acquireInventoryHold | request | channel | object |  | Which channel's allocation to draw from.
CatalogueService | acquireInventoryHold | request | id | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | acquireInventoryHold | request | channelCapacityId | string (uuid) | yes
CatalogueService | acquireInventoryHold | request | requestedUnits | integer | yes | (min 1)
CatalogueService | acquireInventoryHold | request | ttlSeconds | integer | yes | Short TTLs limit stranding when a terminal dies; long TTLs survive longer outages. (min 30; max 3600; default 900)
CatalogueService | acquireInventoryHold | response | id | string | yes
CatalogueService | acquireInventoryHold | response | channelCapacityId | string (uuid) | yes
CatalogueService | acquireInventoryHold | response | holderKind | InventoryHoldHolderKind: enum (workstation, cart) | yes | Who holds the units (decided 29 September, SD-023). (default workstation)
CatalogueService | acquireInventoryHold | response | holderWorkstationId | string (uuid) |  | The holding workstation when holderKind is workstation; null on a cart hold, because a browser has none (SD-023, 29 September). (nullable)
CatalogueService | acquireInventoryHold | response | holderCartId | string (uuid) |  | The holding cart (orders.cart) when holderKind is cart (SD-023, 29 September). (nullable)
CatalogueService | acquireInventoryHold | response | convertedOrderId | string (uuid) |  | The paid order the hold was converted for, set by convertInventoryHold. (read-only; nullable)
CatalogueService | acquireInventoryHold | response | convertedAt | string (date-time) |  | (read-only; nullable)
CatalogueService | acquireInventoryHold | response | parentLeaseId | string |  | Present when sub-leased from a venue edge node. (nullable)
CatalogueService | acquireInventoryHold | response | requestedUnits | integer
CatalogueService | acquireInventoryHold | response | channel | object |  | Allocation this lease draws from.
CatalogueService | acquireInventoryHold | response | grantedUnits | integer | yes | May be less than requested — a partial grant is not an error.
CatalogueService | acquireInventoryHold | response | consumedUnits | integer | yes
CatalogueService | acquireInventoryHold | response | status | LeaseStatus: enum (active, expired, released, forceReleased, converted) | yes | states/lease.yaml.
CatalogueService | acquireInventoryHold | response | acquiredAt | string (date-time) | yes
CatalogueService | acquireInventoryHold | response | expiresAt | string (date-time) | yes
CatalogueService | acquireInventoryHold | response | releasedAt | string (date-time) |  | (nullable)
CatalogueService | acquireInventoryHold | response | forceReleasedByPrincipalId | string (uuid) |  | (nullable)
CatalogueService | acquireInventoryHold | response | forceReleaseReason | string |  | (nullable)
CatalogueService | acquireInventoryHold | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | acquireInventoryHold | param (header) | X-Admission-Token | string |  | The on-sale waiting room's admission token (ADR-0066, accepted 1 October).
AccessService | addBlacklistEntry | request | mediaCode | string | yes | (max length 256)
AccessService | addBlacklistEntry | request | reason | string | yes | (min length 3; max length 500)
AccessService | addBlacklistEntry | request | expiresAt | string (date-time)
AccessService | addBlacklistEntry | request | listType | enum (blacklist, whitelist) |  | A whitelist entry waits for a second approver (DEC-254; CHG-CSP-031). (default blacklist)
AccessService | addBlacklistEntry | request | disableScope | enum (entireCredential, venueAccess, attractionAccess, reEntry, fastPass, specificEntitlement) |  | What the entry disables (BlacklistEntry.disableScope). (default entireCredential)
AccessService | addBlacklistEntry | response | mediaCode | string | yes | Unique within the tenant (decided 28 September, audit R108): one entry per code.
AccessService | addBlacklistEntry | response | reason | string | yes
AccessService | addBlacklistEntry | response | addedAt | string (date-time) | yes
AccessService | addBlacklistEntry | response | addedByPrincipalId | string (uuid) | yes
AccessService | addBlacklistEntry | response | expiresAt | string (date-time) |  | (nullable)
AccessService | addBlacklistEntry | response | listType | enum (blacklist, whitelist) |  | A blacklist entry refuses the media; a whitelist entry is an approved exception to a restriction (added 29 September, data-model close-out DM1). (default blacklist)
AccessService | addBlacklistEntry | response | disableScope | enum (entireCredential, venueAccess, attractionAccess, reEntry, fastPass, specificEntitlement) |  | What the entry disables (added 29 September, data-model close-out DM1). (default entireCredential)
AccessService | addBlacklistEntry | response | distributedTo | array of enum (centralPlatform, venueEdge, onlineGates, offlineRevocationPackage) |  | Where the restriction has been distributed so far, as listCredentialDisableBlacklist returns it (added 29 September, data-model close-out DM1).
AccessService | addBlacklistEntry | response | scopePath | string |  | The partition key (ADR-0005).
AccessService | addBlacklistEntry | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | addCartLine | request | variantId | string (uuid) | yes
OrderService | addCartLine | request | quantity | integer | yes | (min 1)
OrderService | addCartLine | request | performanceId | string (uuid)
OrderService | addCartLine | request | bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | addCartLine | request | bookedWindow.startsAt | string (date-time) | yes
OrderService | addCartLine | request | bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | addCartLine | request | recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | addCartLine | request | tableReservationId | string (uuid) |  | A table deposit line (decided 29 September, rev 3 REV3-8b): the fnb.TableReservation in awaitingDeposit this pays for, sent with variantId set to the booking's deposit.variantId and quantity 1. (nullable)
OrderService | addCartLine | request | seatIds | array of string (uuid) |  | At most VenueSettings.seating.maxSeatsPerGuestOrder seats per booking on a guest channel (default 10, bounds 1 to 50, decided 29 September, rev 3 REV3-7); at most 10 per sale on staff and POS (audit… (max items 50)
OrderService | addCartLine | request | resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant and quantity is 1. (nullable)
OrderService | addCartLine | request | parentLineId | string (uuid) |  | For an add-on attaching to a ticket already in the cart. (nullable)
OrderService | addCartLine | request | attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | addCartLine | request | attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | addCartLine | request | attributes.transport.routeId | string (uuid) | yes | The transport.TransportRoute.
OrderService | addCartLine | request | attributes.transport.fromStationId | string (uuid) | yes | Boarding station, a stop of the route.
OrderService | addCartLine | request | attributes.transport.toStationId | string (uuid) | yes | Alighting station, a later stop of the route.
OrderService | addCartLine | request | attributes.transport.passengerTypeCode | string |  | The fare table's passenger type (adult, child, ...). (pattern ^[a-z][a-zA-Z0-9]{0,31}$; nullable)
OrderService | addCartLine | request | attributes.transport.passTypeId | string (uuid) |  | Pass purchase only. (nullable)
OrderService | addCartLine | request | attributes.transport.passEntitlementId | string (uuid) |  | A seat reserved with a pass already owned. (nullable)
OrderService | addCartLine | response | id | string (uuid) | yes
OrderService | addCartLine | response | token | string |  | How an anonymous guest returns to their cart, including from a recovery email. (read-only)
OrderService | addCartLine | response | venueId | string (uuid) | yes
OrderService | addCartLine | response | channel | SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) | yes | Where a sale came from.
OrderService | addCartLine | response | subjectId | string (uuid) |  | Null while anonymous. (nullable)
OrderService | addCartLine | response | status | CartStatus: enum (active, expiring, expired, abandoned, checkedOut) | yes
OrderService | addCartLine | response | lines | array of CartLine | yes
OrderService | addCartLine | response | lines[].id | string (uuid) | yes
OrderService | addCartLine | response | lines[].variantId | string (uuid) | yes
OrderService | addCartLine | response | lines[].productName | string |  | (read-only)
OrderService | addCartLine | response | lines[].quantity | integer | yes | (min 1)
OrderService | addCartLine | response | lines[].performanceId | string (uuid) |  | (nullable)
OrderService | addCartLine | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | addCartLine | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | addCartLine | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | addCartLine | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | addCartLine | response | lines[].tableReservationId | string (uuid) |  | Set on a table deposit line only (decided 29 September, rev 3 REV3-8b): the fnb.TableReservation this line secures. (nullable)
OrderService | addCartLine | response | lines[].seatIds | array of string (uuid) |  | (max items 50)
OrderService | addCartLine | response | lines[].resourceHoldId | string (uuid) |  | The resources.ResourceHold this line buys (decided 29 September, rev 3 REV3-15). (nullable)
OrderService | addCartLine | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | addCartLine | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | addCartLine | response | lines[].parentLineId | string (uuid) |  | The line this add-on is attached to, from AddCartLineRequest.parentLineId. (nullable)
OrderService | addCartLine | response | lines[].overridePrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | addCartLine | response | lines[].overridePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | addCartLine | response | lines[].overridePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | addCartLine | response | lines[].overridePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | addCartLine | response | lines[].overrideReason | enum (priceMatch, serviceRecovery, negotiated, damagedGoods, staffSale, error) |  | BL-085. (nullable)
OrderService | addCartLine | response | lines[].feeKind | enum (booking, transaction, service, delivery, convenience, cancellation) |  | A fee is a line, not an adjustment. (nullable)
OrderService | addCartLine | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | addCartLine | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | addCartLine | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | addCartLine | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | addCartLine | response | lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | addCartLine | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | addCartLine | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | addCartLine | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | addCartLine | response | lines[].inventoryHoldId | string |  | The capacity held for this line — a catalogue.InventoryHold.id, typed as that id is. (nullable)
OrderService | addCartLine | response | lines[].leaseExpiresAt | string (date-time) |  | Shown to the guest. (nullable)
OrderService | addCartLine | response | lines[].isAvailable | boolean |  | Re-checked on every read. (read-only)
OrderService | addCartLine | response | conflicts | array of CartConflict
OrderService | addCartLine | response | conflicts[].kind | enum (overlappingTime, sameSessionDifferentVenue, exceedsPartySize, requiresPrerequisite, consentBlocksBooking)
OrderService | addCartLine | response | conflicts[].lineIds | array of string (uuid)
OrderService | addCartLine | response | conflicts[].message | string
OrderService | addCartLine | response | conflicts[].isBlocking | boolean |  | Most are not.
OrderService | addCartLine | response | consentQuestions | array of object |  | The consent questions this cart's products and flow ask (decided 29 September, rev 3 REV3-26), computed on read at their current version as the union of each line's published booking flow's white-lab… (read-only)
OrderService | addCartLine | response | consentQuestions[].id | string (uuid) | yes | (read-only)
OrderService | addCartLine | response | consentQuestions[].kind | ConsentQuestionKind: enum (swim, scuba, risk, custom) | yes | What the question is about (decided 29 September, rev 3 REV3-26).
OrderService | addCartLine | response | consentQuestions[].text | object | yes | The question as the guest reads it, per locale.
OrderService | addCartLine | response | consentQuestions[].helpText | object |  | (nullable)
OrderService | addCartLine | response | consentQuestions[].version | integer | yes | Raised by one each time the question changes (updateConsentQuestion). (min 1; read-only)
OrderService | addCartLine | response | consentQuestions[].scope | enum (perPerson, perBooking) | yes | Asked for each declared person, or once for the whole booking. (default perPerson)
OrderService | addCartLine | response | consentQuestions[].required | boolean | yes | Checkout waits until it is answered (orders.checkoutCart 422 consentRequired). (default True)
OrderService | addCartLine | response | consentQuestions[].blockingAnswer | enum (yes, no, none) | yes | The answer that stops the booking, for the person or the booking it covers. (default none)
OrderService | addCartLine | response | consentQuestions[].status | enum (active, retired) | yes | (default active)
OrderService | addCartLine | response | consentQuestions[].scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | addCartLine | response | consentQuestions[].updatedAt | string (date-time) |  | (read-only)
OrderService | addCartLine | response | consentQuestions[].lineIds | array of string (uuid) |  | The cart lines that ask it.
OrderService | addCartLine | response | consentQuestions[].answered | boolean |  | Every person (for perPerson) or the booking (for perBooking) has an answer.
OrderService | addCartLine | response | subtotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | addCartLine | response | subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | addCartLine | response | subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | addCartLine | response | subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | addCartLine | response | discountTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | addCartLine | response | discountTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | addCartLine | response | discountTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | addCartLine | response | discountTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | addCartLine | response | taxTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | addCartLine | response | taxTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | addCartLine | response | taxTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | addCartLine | response | taxTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | addCartLine | response | total | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | addCartLine | response | total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | addCartLine | response | total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | addCartLine | response | total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | addCartLine | response | appliedPromotionIds | array of string (uuid) |  | Re-evaluated on every read.
OrderService | addCartLine | response | couponCodes | array of string |  | The promo codes the guest entered through applyCartPromoCode (decided 28 September, audit R073 (e)). (read-only)
OrderService | addCartLine | response | expiresAt | string (date-time) |  | The earliest lease expiry in the cart, or the cart's own window where it holds none.
OrderService | addCartLine | response | extensionsUsed | integer |  | (read-only)
OrderService | addCartLine | response | maxExtensions | integer |  | (read-only)
OrderService | addCartLine | response | locale | string
OrderService | addCartLine | response | createdAt | string (date-time)
OrderService | addCartLine | response | updatedAt | string (date-time)
OrderService | addCartLine | param (path) | cartId | string (uuid) | yes
OrderService | addCartLine | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | addCartLine | param (header) | X-Admission-Token | string |  | The on-sale waiting room's admission token (ADR-0066, accepted 1 October).
PlatformService | addLicenceAddOn | request | tenantId | string (uuid) |  | The tenant the add-on was sold to — the tenantId in the path, never the body. (read-only)
PlatformService | addLicenceAddOn | request | moduleKey | string | yes
PlatformService | addLicenceAddOn | request | limitOverrides | array of EntitlementLimit
PlatformService | addLicenceAddOn | request | limitOverrides[].metric | UsageMetric: enum (venues, workstations, activeUsers, devices, brandedApps, aiTokens, apiCalls, storageGb, …) | yes
PlatformService | addLicenceAddOn | request | limitOverrides[].limit | integer | yes | Null means unlimited. (nullable)
PlatformService | addLicenceAddOn | request | limitOverrides[].overageAllowed | boolean |  | (default False)
PlatformService | addLicenceAddOn | request | limitOverrides[].overageUnitPrice | Money |  | On the wire this is three fields; in the database it is one column.
PlatformService | addLicenceAddOn | request | limitOverrides[].overageUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
PlatformService | addLicenceAddOn | request | limitOverrides[].overageUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
PlatformService | addLicenceAddOn | request | limitOverrides[].overageUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
PlatformService | addLicenceAddOn | request | price | Money |  | On the wire this is three fields; in the database it is one column.
PlatformService | addLicenceAddOn | request | price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
PlatformService | addLicenceAddOn | request | price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
PlatformService | addLicenceAddOn | request | price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
PlatformService | addLicenceAddOn | request | validFrom | string (date)
PlatformService | addLicenceAddOn | request | validTo | string (date) |  | (nullable)
PlatformService | addLicenceAddOn | request | note | string |  | (max length 500)
PlatformService | addLicenceAddOn | response | poweredByRemovable | boolean |  | Whether the tenant's licence lets it switch "Powered by TICVAI" off (Chinmay, 2 October, workbook Q160 and the pre-apply round; CHG-CSA-036). (default False; read-only)
PlatformService | addLicenceAddOn | response | tenantId | string (uuid) | yes
PlatformService | addLicenceAddOn | response | planId | string (uuid) |  | (nullable)
PlatformService | addLicenceAddOn | response | licensedModules | array of object | yes | Union of plan modules and add-ons.
PlatformService | addLicenceAddOn | response | licensedModules[].moduleKey | string | yes
PlatformService | addLicenceAddOn | response | licensedModules[].displayName | string
PlatformService | addLicenceAddOn | response | licensedModules[].source | enum (plan, addOn) | yes
PlatformService | addLicenceAddOn | response | licensedModules[].validTo | string (date) |  | (nullable)
PlatformService | addLicenceAddOn | response | limits | array of EntitlementLimit | yes
PlatformService | addLicenceAddOn | response | limits[].metric | UsageMetric: enum (venues, workstations, activeUsers, devices, brandedApps, aiTokens, apiCalls, storageGb, …) | yes
PlatformService | addLicenceAddOn | response | limits[].limit | integer | yes | Null means unlimited. (nullable)
PlatformService | addLicenceAddOn | response | limits[].overageAllowed | boolean |  | (default False)
PlatformService | addLicenceAddOn | response | limits[].overageUnitPrice | Money |  | On the wire this is three fields; in the database it is one column.
PlatformService | addLicenceAddOn | response | limits[].overageUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
PlatformService | addLicenceAddOn | response | limits[].overageUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
PlatformService | addLicenceAddOn | response | limits[].overageUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
PlatformService | addLicenceAddOn | param (path) | tenantId | string (uuid) | yes
PlatformService | addLicenceAddOn | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | addTip | request | amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | addTip | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | addTip | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | addTip | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | addTip | request | source | enum (terminalPrompt, cashierEntered, guestApp, serviceCharge) | yes | serviceCharge is not a tip and is separated deliberately — it is revenue in most jurisdictions, and pooling it with tips is how a payroll dispute starts.
OrderService | addTip | request | allocateToPrincipalId | string (uuid) |  | Where the venue allocates rather than pools.
OrderService | addTip | request | recordedAt | string (date-time) | yes
OrderService | addTip | response | id | string (uuid) | yes
OrderService | addTip | response | orderId | string (uuid) | yes
OrderService | addTip | response | tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | addTip | response | tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | addTip | response | tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale.
OrderService | addTip | response | tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | addTip | response | tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | addTip | response | tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | addTip | response | fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | addTip | response | fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | addTip | response | changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | addTip | response | amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | addTip | response | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | addTip | response | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | addTip | response | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | addTip | response | changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | addTip | response | changeAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | addTip | response | changeAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | addTip | response | changeAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | addTip | response | status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | addTip | response | providerName | string |  | (nullable)
OrderService | addTip | response | providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | addTip | response | providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | addTip | response | terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | addTip | response | nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | addTip | response | nextAction.kind | enum (redirect, terminal)
OrderService | addTip | response | nextAction.url | string (uri) |  | (nullable)
OrderService | addTip | response | nextAction.expiresAt | string (date-time) |  | (nullable)
OrderService | addTip | response | lastInquiryAt | string (date-time) |  | (nullable)
OrderService | addTip | response | recordedAt | string (date-time) | yes
OrderService | addTip | response | syncedAt | string (date-time) |  | (nullable)
OrderService | addTip | param (path) | paymentId | string (uuid) | yes
OrderService | addTip | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | addToWishlist | request | variantId | string (uuid) | yes
MarketingService | addToWishlist | request | performanceId | string (uuid) |  | Saving a specific date rather than the product generally. (nullable)
MarketingService | addToWishlist | request | note | string |  | (max length 200)
MarketingService | addToWishlist | response | subjectId | string (uuid) | yes
MarketingService | addToWishlist | response | items | array of object | yes
MarketingService | addToWishlist | response | items[].id | string (uuid) | yes
MarketingService | addToWishlist | response | items[].variantId | string (uuid) | yes
MarketingService | addToWishlist | response | items[].productName | string
MarketingService | addToWishlist | response | items[].performanceId | string (uuid) |  | (nullable)
MarketingService | addToWishlist | response | items[].performanceStartsAt | string (date-time) |  | (nullable)
MarketingService | addToWishlist | response | items[].price | Money |  | On the wire this is three fields; in the database it is one column.
MarketingService | addToWishlist | response | items[].price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
MarketingService | addToWishlist | response | items[].price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
MarketingService | addToWishlist | response | items[].price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
MarketingService | addToWishlist | response | items[].imageAssetRef | string |  | (nullable)
MarketingService | addToWishlist | response | items[].isAvailable | boolean | yes | False where the product has been withdrawn or the performance has passed.
MarketingService | addToWishlist | response | items[].unavailableReason | string |  | (nullable)
MarketingService | addToWishlist | response | items[].note | string |  | (nullable)
MarketingService | addToWishlist | response | items[].addedAt | string (date-time) | yes
MarketingService | addToWishlist | param (path) | subjectId | string (uuid) | yes
MarketingService | addToWishlist | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | allocateDepositBox | request | id | string (uuid) |  | (read-only)
OrderService | allocateDepositBox | request | cashierPrincipalId | string (uuid) | yes
OrderService | allocateDepositBox | request | cashierName | string |  | (read-only)
OrderService | allocateDepositBox | request | venueId | string (uuid) | yes
OrderService | allocateDepositBox | request | workstationId | string (uuid) |  | Where it is being used now. (nullable)
OrderService | allocateDepositBox | request | shiftId | string (uuid) |  | The shift trading from this box. (nullable)
OrderService | allocateDepositBox | request | status | DepositBoxStatus: enum (allocated, open, suspended, closing, closed, reconciled)
OrderService | allocateDepositBox | request | openingFloat | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | allocateDepositBox | request | openingFloat.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | request | openingFloat.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | request | openingFloat.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | request | openingDenominations | array of object |  | 5.8.3.
OrderService | allocateDepositBox | request | openingDenominations[].denominationId | string (uuid) | yes | References platform.denomination, as CashCountLine.denominationId does.
OrderService | allocateDepositBox | request | openingDenominations[].count | integer | yes | (min 0)
OrderService | allocateDepositBox | request | withdrawnTotal | object |  | Reduces the expected close figure. (read-only)
OrderService | allocateDepositBox | request | withdrawnTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | request | withdrawnTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | request | withdrawnTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | request | overDrawerLimit | boolean |  | The box holds more than its till's drawer limit (decided 2 October 2026, Chinmay, BO-042; DEC-179; CHG-CSP-016): computed on read from the box's expected cash against tenancy.Workstation.cashDrawerLi… (default False; read-only)
OrderService | allocateDepositBox | request | foreignHoldings | array of object |  | 4.6.11 and 6.1.10.
OrderService | allocateDepositBox | request | foreignHoldings[].currency | string | yes | Stored, because it is the one thing that is not the region's. (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | request | foreignHoldings[].expectedAmount | object |  | The sum of tenders taken in this currency during the shift.
OrderService | allocateDepositBox | request | foreignHoldings[].expectedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | request | foreignHoldings[].expectedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | request | foreignHoldings[].expectedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | request | foreignHoldings[].countedAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | allocateDepositBox | request | foreignHoldings[].countedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | request | foreignHoldings[].countedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | request | foreignHoldings[].countedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | request | foreignHoldings[].variance | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | allocateDepositBox | request | foreignHoldings[].variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | request | foreignHoldings[].variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | request | foreignHoldings[].variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | request | foreignHoldings[].baseEquivalent | object |  | At the rates on the payments, not today's.
OrderService | allocateDepositBox | request | foreignHoldings[].baseEquivalent.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | request | foreignHoldings[].baseEquivalent.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | request | foreignHoldings[].baseEquivalent.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | request | expectedTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | allocateDepositBox | request | expectedTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | request | expectedTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | request | expectedTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | request | countedTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | allocateDepositBox | request | countedTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | request | countedTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | request | countedTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | request | variance | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | allocateDepositBox | request | variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | request | variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | request | variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | request | closedByPrincipalId | string (uuid) |  | Flagged where it is not the holder. (nullable)
OrderService | allocateDepositBox | request | allocatedAt | string (date-time) |  | When the device recorded the allocation.
OrderService | allocateDepositBox | request | closedAt | string (date-time) |  | (nullable)
OrderService | allocateDepositBox | response | id | string (uuid) |  | (read-only)
OrderService | allocateDepositBox | response | cashierPrincipalId | string (uuid) | yes
OrderService | allocateDepositBox | response | cashierName | string |  | (read-only)
OrderService | allocateDepositBox | response | venueId | string (uuid) | yes
OrderService | allocateDepositBox | response | workstationId | string (uuid) |  | Where it is being used now. (nullable)
OrderService | allocateDepositBox | response | shiftId | string (uuid) |  | The shift trading from this box. (nullable)
OrderService | allocateDepositBox | response | status | DepositBoxStatus: enum (allocated, open, suspended, closing, closed, reconciled)
OrderService | allocateDepositBox | response | openingFloat | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | allocateDepositBox | response | openingFloat.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | response | openingFloat.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | response | openingFloat.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | response | openingDenominations | array of object |  | 5.8.3.
OrderService | allocateDepositBox | response | openingDenominations[].denominationId | string (uuid) | yes | References platform.denomination, as CashCountLine.denominationId does.
OrderService | allocateDepositBox | response | openingDenominations[].count | integer | yes | (min 0)
OrderService | allocateDepositBox | response | withdrawnTotal | object |  | Reduces the expected close figure. (read-only)
OrderService | allocateDepositBox | response | withdrawnTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | response | withdrawnTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | response | withdrawnTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | response | overDrawerLimit | boolean |  | The box holds more than its till's drawer limit (decided 2 October 2026, Chinmay, BO-042; DEC-179; CHG-CSP-016): computed on read from the box's expected cash against tenancy.Workstation.cashDrawerLi… (default False; read-only)
OrderService | allocateDepositBox | response | foreignHoldings | array of object |  | 4.6.11 and 6.1.10.
OrderService | allocateDepositBox | response | foreignHoldings[].currency | string | yes | Stored, because it is the one thing that is not the region's. (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | response | foreignHoldings[].expectedAmount | object |  | The sum of tenders taken in this currency during the shift.
OrderService | allocateDepositBox | response | foreignHoldings[].expectedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | response | foreignHoldings[].expectedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | response | foreignHoldings[].expectedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | response | foreignHoldings[].countedAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | allocateDepositBox | response | foreignHoldings[].countedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | response | foreignHoldings[].countedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | response | foreignHoldings[].countedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | response | foreignHoldings[].variance | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | allocateDepositBox | response | foreignHoldings[].variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | response | foreignHoldings[].variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | response | foreignHoldings[].variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | response | foreignHoldings[].baseEquivalent | object |  | At the rates on the payments, not today's.
OrderService | allocateDepositBox | response | foreignHoldings[].baseEquivalent.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | response | foreignHoldings[].baseEquivalent.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | response | foreignHoldings[].baseEquivalent.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | response | expectedTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | allocateDepositBox | response | expectedTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | response | expectedTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | response | expectedTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | response | countedTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | allocateDepositBox | response | countedTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | response | countedTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | response | countedTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | response | variance | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | allocateDepositBox | response | variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | allocateDepositBox | response | variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | allocateDepositBox | response | variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | allocateDepositBox | response | closedByPrincipalId | string (uuid) |  | Flagged where it is not the holder. (nullable)
OrderService | allocateDepositBox | response | allocatedAt | string (date-time) |  | When the device recorded the allocation.
OrderService | allocateDepositBox | response | closedAt | string (date-time) |  | (nullable)
OrderService | allocateDepositBox | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | analysePromotionConflicts | response | promotionId | string (uuid) | yes
CatalogueService | analysePromotionConflicts | response | conflicts | array of object | yes
CatalogueService | analysePromotionConflicts | response | conflicts[].otherPromotionId | string (uuid) | yes
CatalogueService | analysePromotionConflicts | response | conflicts[].otherPromotionCode | string | yes
CatalogueService | analysePromotionConflicts | response | conflicts[].overlap | enum (products, period, channel, full) | yes
CatalogueService | analysePromotionConflicts | response | conflicts[].combinedDiscount | number | yes | Combined percentage where both apply to the same line.
CatalogueService | analysePromotionConflicts | response | conflicts[].isBlocking | boolean |  | True where the combination would produce a line price of zero or below (decided 28 September, audit R101).
CatalogueService | analysePromotionConflicts | response | conflicts[].isNearZero | boolean |  | True where the combination leaves a net line price above zero but below the venue setting promotions.nearZeroLinePrice (proposed AED 1.00; decided 28 September, audit R096 (5)).
CatalogueService | analysePromotionConflicts | response | worstCaseDiscount | number | yes | Largest combined discount any single line could receive.
CatalogueService | analysePromotionConflicts | param (path) | promotionId | string (uuid) | yes
OrderService | appendEntitlementToMedia | request | id | string (uuid) | yes | Client-generated UUIDv7 of the new order this creates, and its idempotency key — it must equal the Idempotency-Key header.
OrderService | appendEntitlementToMedia | request | lines | array of object | yes | (min items 1)
OrderService | appendEntitlementToMedia | request | lines[].variantId | string (uuid) | yes
OrderService | appendEntitlementToMedia | request | lines[].quantity | integer | yes | (min 1)
OrderService | appendEntitlementToMedia | request | lines[].performanceId | string (uuid) |  | (nullable)
OrderService | appendEntitlementToMedia | request | paymentMethod | enum (card, cash, wallet, giftCard, chargeToAccount)
OrderService | appendEntitlementToMedia | request | note | string |  | (max length 300)
OrderService | appendEntitlementToMedia | request | recordedAt | string (date-time) | yes
OrderService | appendEntitlementToMedia | response | order | object | yes | A new order.
OrderService | appendEntitlementToMedia | response | order.id | string (uuid) | yes | The client UUIDv7 from CreateOrderRequest.id.
OrderService | appendEntitlementToMedia | response | order.orderNumber | string |  | The number a guest reads and a cashier types. (read-only)
OrderService | appendEntitlementToMedia | response | order.channel | object | yes | Where it came from.
OrderService | appendEntitlementToMedia | response | order.channelProfileId | string (uuid) |  | The named sales channel the order came through (catalogue SalesChannelProfile.id), set by the server from the caller: a partner user's or reseller's channel, an API key's channel. (read-only; nullable)
OrderService | appendEntitlementToMedia | response | order.venueId | string (uuid) | yes
OrderService | appendEntitlementToMedia | response | order.scopePath | string | yes
OrderService | appendEntitlementToMedia | response | order.status | OrderStatus: enum (pending, held, paid, partiallyPaid, completed, voided, refunded, partiallyRefunded, …) | yes | held is a parked sale — the cashier freed the till and the guest will return.
OrderService | appendEntitlementToMedia | response | order.currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | appendEntitlementToMedia | response | order.currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | appendEntitlementToMedia | response | order.grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | appendEntitlementToMedia | response | order.grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | appendEntitlementToMedia | response | order.grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | appendEntitlementToMedia | response | order.grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | appendEntitlementToMedia | response | order.taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | appendEntitlementToMedia | response | order.taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | appendEntitlementToMedia | response | order.taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | appendEntitlementToMedia | response | order.taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | appendEntitlementToMedia | response | order.netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | appendEntitlementToMedia | response | order.netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | appendEntitlementToMedia | response | order.netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | appendEntitlementToMedia | response | order.netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | appendEntitlementToMedia | response | order.refundedAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | appendEntitlementToMedia | response | order.refundedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | appendEntitlementToMedia | response | order.refundedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | appendEntitlementToMedia | response | order.refundedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | appendEntitlementToMedia | response | order.chargeCurrency | string |  | The currency the guest selected and is charged in (CHG-FIN-001, 2 October 2026). (pattern ^[A-Z]{3}$; read-only; nullable)
OrderService | appendEntitlementToMedia | response | order.chargeFxRate | object |  | Units of chargeCurrency per one unit of the base currency, from the region's tender rate in force at checkout (finance.FxRate), stored on the order so the payment, the receipt, the tax invoice and an… (read-only; nullable)
OrderService | appendEntitlementToMedia | response | order.chargeFxRateId | string (uuid) |  | The finance.FxRate row the rate was taken from, for audit. (read-only; nullable)
OrderService | appendEntitlementToMedia | response | order.chargeTotal | object |  | grossAmount converted at chargeFxRate and rounded to the charge currency's scale: what the guest pays and what the payment request to the provider asks for (CHG-FIN-001). (read-only)
OrderService | appendEntitlementToMedia | response | order.chargeTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | appendEntitlementToMedia | response | order.chargeTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | appendEntitlementToMedia | response | order.chargeTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | appendEntitlementToMedia | response | order.chargeRateLockedUntil | string (date-time) |  | The quote holds until then (the cart lease). (read-only; nullable)
OrderService | appendEntitlementToMedia | response | order.droppedPromotions | array of object |  | Promotions left off this order at checkout because their budget cap would have been exceeded (decided 28 September, audit R101 (8)). (read-only)
OrderService | appendEntitlementToMedia | response | order.droppedPromotions[].promotionId | string (uuid) | yes
OrderService | appendEntitlementToMedia | response | order.droppedPromotions[].name | string
OrderService | appendEntitlementToMedia | response | order.droppedPromotions[].reason | enum (budgetCapReached)
OrderService | appendEntitlementToMedia | response | order.totalPriceVariance | object |  | Sum across lines.
OrderService | appendEntitlementToMedia | response | order.totalPriceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | appendEntitlementToMedia | response | order.totalPriceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | appendEntitlementToMedia | response | order.totalPriceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | appendEntitlementToMedia | response | order.lines | array of OrderLine | yes
OrderService | appendEntitlementToMedia | response | order.lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | appendEntitlementToMedia | response | order.lines[].variantId | string (uuid) | yes
OrderService | appendEntitlementToMedia | response | order.lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | appendEntitlementToMedia | response | order.lines[].performanceId | string (uuid)
OrderService | appendEntitlementToMedia | response | order.lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | appendEntitlementToMedia | response | order.lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | appendEntitlementToMedia | response | order.lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | appendEntitlementToMedia | response | order.lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | appendEntitlementToMedia | response | order.lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | appendEntitlementToMedia | response | order.lines[].quantity | integer | yes | (min 1)
OrderService | appendEntitlementToMedia | response | order.lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | appendEntitlementToMedia | response | order.lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | appendEntitlementToMedia | response | order.lines[].holderName | string |  | (nullable)
OrderService | appendEntitlementToMedia | response | order.lines[].dataMaskValues | object |  | Deliberately open.
OrderService | appendEntitlementToMedia | response | order.lines[].serverUnitPrice | object | yes | What the server computed on ingest.
OrderService | appendEntitlementToMedia | response | order.lines[].priceVariance | object |  | Server minus quoted.
OrderService | appendEntitlementToMedia | response | order.lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | appendEntitlementToMedia | response | order.lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | appendEntitlementToMedia | response | order.lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | appendEntitlementToMedia | response | order.lines[].entitlementIds | array of string (uuid) |  | The entitlements this line issued.
OrderService | appendEntitlementToMedia | response | order.lines[].crossRegionRightIds | array of string |  | Redemption rights propagated to other cells for this line.
OrderService | appendEntitlementToMedia | response | order.lines[].reprintCount | integer |  | How many times this line's tickets were reprinted or resent. (min 0; default 0; read-only)
OrderService | appendEntitlementToMedia | response | order.lines[].venueId | string (uuid) |  | The order's venue, copied onto the line (ADR-0044's own example; system-design review SD-008, 29 September) so a line is scoped and partitionable without its order. (read-only)
OrderService | appendEntitlementToMedia | response | order.lines[].discounts | array of OrderLineDiscount |  | The discounts applied to this line, one row each (system-design review SD-008, 29 September). (read-only)
OrderService | appendEntitlementToMedia | response | order.payments | array of Payment
OrderService | appendEntitlementToMedia | response | order.payments[].id | string (uuid) | yes
OrderService | appendEntitlementToMedia | response | order.payments[].orderId | string (uuid) | yes
OrderService | appendEntitlementToMedia | response | order.payments[].tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | appendEntitlementToMedia | response | order.payments[].tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | appendEntitlementToMedia | response | order.payments[].tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale.
OrderService | appendEntitlementToMedia | response | order.payments[].fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | appendEntitlementToMedia | response | order.payments[].fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | appendEntitlementToMedia | response | order.payments[].changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | appendEntitlementToMedia | response | order.payments[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | appendEntitlementToMedia | response | order.payments[].changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | appendEntitlementToMedia | response | order.payments[].status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | appendEntitlementToMedia | response | order.payments[].providerName | string |  | (nullable)
OrderService | appendEntitlementToMedia | response | order.payments[].providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | appendEntitlementToMedia | response | order.payments[].providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | appendEntitlementToMedia | response | order.payments[].terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | appendEntitlementToMedia | response | order.payments[].nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | appendEntitlementToMedia | response | order.payments[].lastInquiryAt | string (date-time) |  | (nullable)
OrderService | appendEntitlementToMedia | response | order.payments[].recordedAt | string (date-time) | yes
OrderService | appendEntitlementToMedia | response | order.payments[].syncedAt | string (date-time) |  | (nullable)
OrderService | appendEntitlementToMedia | response | order.principalId | string (uuid)
OrderService | appendEntitlementToMedia | response | order.workstationId | string (uuid)
OrderService | appendEntitlementToMedia | response | order.shiftId | string (uuid) |  | (nullable)
OrderService | appendEntitlementToMedia | response | order.subjectId | string (uuid) |  | (nullable)
OrderService | appendEntitlementToMedia | response | order.holdLabel | string |  | The label a cashier gave when parking it with holdOrder — how they find it again. (max length 60; read-only; nullable)
OrderService | appendEntitlementToMedia | response | order.heldUntil | string (date-time) |  | When a held order expires and is voided (states/order.yaml), from holdOrder's holdUntil. (read-only; nullable)
OrderService | appendEntitlementToMedia | response | order.createdAt | string (date-time) | yes
OrderService | appendEntitlementToMedia | response | order.recordedAt | string (date-time) | yes
OrderService | appendEntitlementToMedia | response | order.syncedAt | string (date-time) |  | (nullable)
OrderService | appendEntitlementToMedia | response | media | object | yes | The full set now on the media, so the cashier can say what the QR does.
OrderService | appendEntitlementToMedia | response | media.mediaCode | string | yes
OrderService | appendEntitlementToMedia | response | media.mediaKind | enum (qr, wristband, card, nfc, mobilePass)
OrderService | appendEntitlementToMedia | response | media.subjectId | string (uuid) |  | (nullable)
OrderService | appendEntitlementToMedia | response | media.isValid | boolean | yes
OrderService | appendEntitlementToMedia | response | media.invalidReason | string |  | (nullable)
OrderService | appendEntitlementToMedia | response | media.canAcceptMore | boolean |  | False where the media has been surrendered, expired or blocked.
OrderService | appendEntitlementToMedia | response | media.entitlements | array of object | yes
OrderService | appendEntitlementToMedia | response | media.entitlements[].entitlementId | string (uuid)
OrderService | appendEntitlementToMedia | response | media.entitlements[].name | string
OrderService | appendEntitlementToMedia | response | media.entitlements[].kind | enum (admission, locker, fnb, retail, parking, rental, experience, membership)
OrderService | appendEntitlementToMedia | response | media.entitlements[].orderId | string (uuid)
OrderService | appendEntitlementToMedia | response | media.entitlements[].addedAt | string (date-time)
OrderService | appendEntitlementToMedia | response | media.entitlements[].status | object |  | Replaced isRedeemed on 17 August.
OrderService | appendEntitlementToMedia | response | media.entitlements[].entriesUsed | integer
OrderService | appendEntitlementToMedia | response | media.entitlements[].entriesAllowed | integer |  | (nullable)
OrderService | appendEntitlementToMedia | response | media.entitlements[].redeemedAt | string (date-time) |  | (nullable)
OrderService | appendEntitlementToMedia | response | media.entitlements[].transferredToSubjectId | string (uuid) |  | (nullable)
OrderService | appendEntitlementToMedia | response | media.entitlements[].validTo | string (date-time) |  | (nullable)
OrderService | appendEntitlementToMedia | response | addedEntitlementIds | array of string (uuid)
OrderService | appendEntitlementToMedia | param (path) | mediaCode | string | yes | The QR, wristband or card the guest is already carrying.
OrderService | appendEntitlementToMedia | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | applyCartPromoCode | request | code | string | yes | The code as the guest typed it. (min length 1; max length 100)
OrderService | applyCartPromoCode | response | id | string (uuid) | yes
OrderService | applyCartPromoCode | response | token | string |  | How an anonymous guest returns to their cart, including from a recovery email. (read-only)
OrderService | applyCartPromoCode | response | venueId | string (uuid) | yes
OrderService | applyCartPromoCode | response | channel | SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) | yes | Where a sale came from.
OrderService | applyCartPromoCode | response | subjectId | string (uuid) |  | Null while anonymous. (nullable)
OrderService | applyCartPromoCode | response | status | CartStatus: enum (active, expiring, expired, abandoned, checkedOut) | yes
OrderService | applyCartPromoCode | response | lines | array of CartLine | yes
OrderService | applyCartPromoCode | response | lines[].id | string (uuid) | yes
OrderService | applyCartPromoCode | response | lines[].variantId | string (uuid) | yes
OrderService | applyCartPromoCode | response | lines[].productName | string |  | (read-only)
OrderService | applyCartPromoCode | response | lines[].quantity | integer | yes | (min 1)
OrderService | applyCartPromoCode | response | lines[].performanceId | string (uuid) |  | (nullable)
OrderService | applyCartPromoCode | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | applyCartPromoCode | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | applyCartPromoCode | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | applyCartPromoCode | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | applyCartPromoCode | response | lines[].tableReservationId | string (uuid) |  | Set on a table deposit line only (decided 29 September, rev 3 REV3-8b): the fnb.TableReservation this line secures. (nullable)
OrderService | applyCartPromoCode | response | lines[].seatIds | array of string (uuid) |  | (max items 50)
OrderService | applyCartPromoCode | response | lines[].resourceHoldId | string (uuid) |  | The resources.ResourceHold this line buys (decided 29 September, rev 3 REV3-15). (nullable)
OrderService | applyCartPromoCode | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | applyCartPromoCode | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | applyCartPromoCode | response | lines[].parentLineId | string (uuid) |  | The line this add-on is attached to, from AddCartLineRequest.parentLineId. (nullable)
OrderService | applyCartPromoCode | response | lines[].overridePrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | applyCartPromoCode | response | lines[].overridePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyCartPromoCode | response | lines[].overridePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyCartPromoCode | response | lines[].overridePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyCartPromoCode | response | lines[].overrideReason | enum (priceMatch, serviceRecovery, negotiated, damagedGoods, staffSale, error) |  | BL-085. (nullable)
OrderService | applyCartPromoCode | response | lines[].feeKind | enum (booking, transaction, service, delivery, convenience, cancellation) |  | A fee is a line, not an adjustment. (nullable)
OrderService | applyCartPromoCode | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | applyCartPromoCode | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyCartPromoCode | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyCartPromoCode | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyCartPromoCode | response | lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | applyCartPromoCode | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyCartPromoCode | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyCartPromoCode | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyCartPromoCode | response | lines[].inventoryHoldId | string |  | The capacity held for this line — a catalogue.InventoryHold.id, typed as that id is. (nullable)
OrderService | applyCartPromoCode | response | lines[].leaseExpiresAt | string (date-time) |  | Shown to the guest. (nullable)
OrderService | applyCartPromoCode | response | lines[].isAvailable | boolean |  | Re-checked on every read. (read-only)
OrderService | applyCartPromoCode | response | conflicts | array of CartConflict
OrderService | applyCartPromoCode | response | conflicts[].kind | enum (overlappingTime, sameSessionDifferentVenue, exceedsPartySize, requiresPrerequisite, consentBlocksBooking)
OrderService | applyCartPromoCode | response | conflicts[].lineIds | array of string (uuid)
OrderService | applyCartPromoCode | response | conflicts[].message | string
OrderService | applyCartPromoCode | response | conflicts[].isBlocking | boolean |  | Most are not.
OrderService | applyCartPromoCode | response | consentQuestions | array of object |  | The consent questions this cart's products and flow ask (decided 29 September, rev 3 REV3-26), computed on read at their current version as the union of each line's published booking flow's white-lab… (read-only)
OrderService | applyCartPromoCode | response | consentQuestions[].id | string (uuid) | yes | (read-only)
OrderService | applyCartPromoCode | response | consentQuestions[].kind | ConsentQuestionKind: enum (swim, scuba, risk, custom) | yes | What the question is about (decided 29 September, rev 3 REV3-26).
OrderService | applyCartPromoCode | response | consentQuestions[].text | object | yes | The question as the guest reads it, per locale.
OrderService | applyCartPromoCode | response | consentQuestions[].helpText | object |  | (nullable)
OrderService | applyCartPromoCode | response | consentQuestions[].version | integer | yes | Raised by one each time the question changes (updateConsentQuestion). (min 1; read-only)
OrderService | applyCartPromoCode | response | consentQuestions[].scope | enum (perPerson, perBooking) | yes | Asked for each declared person, or once for the whole booking. (default perPerson)
OrderService | applyCartPromoCode | response | consentQuestions[].required | boolean | yes | Checkout waits until it is answered (orders.checkoutCart 422 consentRequired). (default True)
OrderService | applyCartPromoCode | response | consentQuestions[].blockingAnswer | enum (yes, no, none) | yes | The answer that stops the booking, for the person or the booking it covers. (default none)
OrderService | applyCartPromoCode | response | consentQuestions[].status | enum (active, retired) | yes | (default active)
OrderService | applyCartPromoCode | response | consentQuestions[].scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | applyCartPromoCode | response | consentQuestions[].updatedAt | string (date-time) |  | (read-only)
OrderService | applyCartPromoCode | response | consentQuestions[].lineIds | array of string (uuid) |  | The cart lines that ask it.
OrderService | applyCartPromoCode | response | consentQuestions[].answered | boolean |  | Every person (for perPerson) or the booking (for perBooking) has an answer.
OrderService | applyCartPromoCode | response | subtotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | applyCartPromoCode | response | subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyCartPromoCode | response | subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyCartPromoCode | response | subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyCartPromoCode | response | discountTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | applyCartPromoCode | response | discountTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyCartPromoCode | response | discountTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyCartPromoCode | response | discountTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyCartPromoCode | response | taxTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | applyCartPromoCode | response | taxTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyCartPromoCode | response | taxTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyCartPromoCode | response | taxTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyCartPromoCode | response | total | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | applyCartPromoCode | response | total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyCartPromoCode | response | total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyCartPromoCode | response | total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyCartPromoCode | response | appliedPromotionIds | array of string (uuid) |  | Re-evaluated on every read.
OrderService | applyCartPromoCode | response | couponCodes | array of string |  | The promo codes the guest entered through applyCartPromoCode (decided 28 September, audit R073 (e)). (read-only)
OrderService | applyCartPromoCode | response | expiresAt | string (date-time) |  | The earliest lease expiry in the cart, or the cart's own window where it holds none.
OrderService | applyCartPromoCode | response | extensionsUsed | integer |  | (read-only)
OrderService | applyCartPromoCode | response | maxExtensions | integer |  | (read-only)
OrderService | applyCartPromoCode | response | locale | string
OrderService | applyCartPromoCode | response | createdAt | string (date-time)
OrderService | applyCartPromoCode | response | updatedAt | string (date-time)
OrderService | applyCartPromoCode | param (path) | cartId | string (uuid) | yes
OrderService | applyCartPromoCode | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | applyManualDiscount | request | id | string (uuid) | yes | Client-generated UUIDv7 of this discount, and its idempotency key — it must equal the Idempotency-Key header.
OrderService | applyManualDiscount | request | lineId | string (uuid) |  | Omit to discount the order rather than a line. (nullable)
OrderService | applyManualDiscount | request | amount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | applyManualDiscount | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | request | percentage | number |  | (min 0; max 100)
OrderService | applyManualDiscount | request | reason | string | yes | Required, and free text rather than a code list. (min length 3; max length 300)
OrderService | applyManualDiscount | request | reasonCode | string |  | Optional alongside the free text, where the venue maintains a list. (nullable)
OrderService | applyManualDiscount | request | approverPrincipalId | string (uuid) |  | Required above the venue threshold. (nullable)
OrderService | applyManualDiscount | request | recordedAt | string (date-time) | yes
OrderService | applyManualDiscount | response | id | string (uuid) | yes | The client UUIDv7 from CreateOrderRequest.id.
OrderService | applyManualDiscount | response | orderNumber | string |  | The number a guest reads and a cashier types. (read-only)
OrderService | applyManualDiscount | response | channel | object | yes | Where it came from.
OrderService | applyManualDiscount | response | channelProfileId | string (uuid) |  | The named sales channel the order came through (catalogue SalesChannelProfile.id), set by the server from the caller: a partner user's or reseller's channel, an API key's channel. (read-only; nullable)
OrderService | applyManualDiscount | response | venueId | string (uuid) | yes
OrderService | applyManualDiscount | response | scopePath | string | yes
OrderService | applyManualDiscount | response | status | OrderStatus: enum (pending, held, paid, partiallyPaid, completed, voided, refunded, partiallyRefunded, …) | yes | held is a parked sale — the cashier freed the till and the guest will return.
OrderService | applyManualDiscount | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | applyManualDiscount | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | applyManualDiscount | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | applyManualDiscount | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | applyManualDiscount | response | netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | refundedAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | applyManualDiscount | response | refundedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | refundedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | refundedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | chargeCurrency | string |  | The currency the guest selected and is charged in (CHG-FIN-001, 2 October 2026). (pattern ^[A-Z]{3}$; read-only; nullable)
OrderService | applyManualDiscount | response | chargeFxRate | object |  | Units of chargeCurrency per one unit of the base currency, from the region's tender rate in force at checkout (finance.FxRate), stored on the order so the payment, the receipt, the tax invoice and an… (read-only; nullable)
OrderService | applyManualDiscount | response | chargeFxRateId | string (uuid) |  | The finance.FxRate row the rate was taken from, for audit. (read-only; nullable)
OrderService | applyManualDiscount | response | chargeTotal | object |  | grossAmount converted at chargeFxRate and rounded to the charge currency's scale: what the guest pays and what the payment request to the provider asks for (CHG-FIN-001). (read-only)
OrderService | applyManualDiscount | response | chargeTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | chargeTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | chargeTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | chargeRateLockedUntil | string (date-time) |  | The quote holds until then (the cart lease). (read-only; nullable)
OrderService | applyManualDiscount | response | droppedPromotions | array of object |  | Promotions left off this order at checkout because their budget cap would have been exceeded (decided 28 September, audit R101 (8)). (read-only)
OrderService | applyManualDiscount | response | droppedPromotions[].promotionId | string (uuid) | yes
OrderService | applyManualDiscount | response | droppedPromotions[].name | string
OrderService | applyManualDiscount | response | droppedPromotions[].reason | enum (budgetCapReached)
OrderService | applyManualDiscount | response | totalPriceVariance | object |  | Sum across lines.
OrderService | applyManualDiscount | response | totalPriceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | totalPriceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | totalPriceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | lines | array of OrderLine | yes
OrderService | applyManualDiscount | response | lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | applyManualDiscount | response | lines[].variantId | string (uuid) | yes
OrderService | applyManualDiscount | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | applyManualDiscount | response | lines[].performanceId | string (uuid)
OrderService | applyManualDiscount | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | applyManualDiscount | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | applyManualDiscount | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | applyManualDiscount | response | lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | applyManualDiscount | response | lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | applyManualDiscount | response | lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | applyManualDiscount | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | applyManualDiscount | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | applyManualDiscount | response | lines[].quantity | integer | yes | (min 1)
OrderService | applyManualDiscount | response | lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | applyManualDiscount | response | lines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | applyManualDiscount | response | lines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | applyManualDiscount | response | lines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | applyManualDiscount | response | lines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | applyManualDiscount | response | lines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | applyManualDiscount | response | lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | applyManualDiscount | response | lines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | lines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | lines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | lines[].holderName | string |  | (nullable)
OrderService | applyManualDiscount | response | lines[].dataMaskValues | object |  | Deliberately open.
OrderService | applyManualDiscount | response | lines[].serverUnitPrice | object | yes | What the server computed on ingest.
OrderService | applyManualDiscount | response | lines[].serverUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | lines[].serverUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | lines[].serverUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | lines[].priceVariance | object |  | Server minus quoted.
OrderService | applyManualDiscount | response | lines[].priceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | lines[].priceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | lines[].priceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | applyManualDiscount | response | lines[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | lines[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | lines[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | applyManualDiscount | response | lines[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | lines[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | lines[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | applyManualDiscount | response | lines[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | lines[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | lines[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | lines[].entitlementIds | array of string (uuid) |  | The entitlements this line issued.
OrderService | applyManualDiscount | response | lines[].crossRegionRightIds | array of string |  | Redemption rights propagated to other cells for this line.
OrderService | applyManualDiscount | response | lines[].reprintCount | integer |  | How many times this line's tickets were reprinted or resent. (min 0; default 0; read-only)
OrderService | applyManualDiscount | response | lines[].venueId | string (uuid) |  | The order's venue, copied onto the line (ADR-0044's own example; system-design review SD-008, 29 September) so a line is scoped and partitionable without its order. (read-only)
OrderService | applyManualDiscount | response | lines[].discounts | array of OrderLineDiscount |  | The discounts applied to this line, one row each (system-design review SD-008, 29 September). (read-only)
OrderService | applyManualDiscount | response | lines[].discounts[].id | string (uuid) | yes
OrderService | applyManualDiscount | response | lines[].discounts[].promotionId | string (uuid) |  | The promotion that gave it. (nullable)
OrderService | applyManualDiscount | response | lines[].discounts[].source | enum (promotion, promoCode, manual, bundle, member) | yes
OrderService | applyManualDiscount | response | lines[].discounts[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | applyManualDiscount | response | lines[].discounts[].reason | string |  | A cashier's reason for a manual discount. (max length 200; nullable)
OrderService | applyManualDiscount | response | payments | array of Payment
OrderService | applyManualDiscount | response | payments[].id | string (uuid) | yes
OrderService | applyManualDiscount | response | payments[].orderId | string (uuid) | yes
OrderService | applyManualDiscount | response | payments[].tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | applyManualDiscount | response | payments[].tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | payments[].tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale.
OrderService | applyManualDiscount | response | payments[].tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | payments[].tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | payments[].tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | payments[].fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | applyManualDiscount | response | payments[].fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | applyManualDiscount | response | payments[].changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | applyManualDiscount | response | payments[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | applyManualDiscount | response | payments[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | payments[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | payments[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | payments[].changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | applyManualDiscount | response | payments[].changeAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | applyManualDiscount | response | payments[].changeAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | applyManualDiscount | response | payments[].changeAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | applyManualDiscount | response | payments[].status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | applyManualDiscount | response | payments[].providerName | string |  | (nullable)
OrderService | applyManualDiscount | response | payments[].providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | applyManualDiscount | response | payments[].providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | applyManualDiscount | response | payments[].terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | applyManualDiscount | response | payments[].nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | applyManualDiscount | response | payments[].nextAction.kind | enum (redirect, terminal)
OrderService | applyManualDiscount | response | payments[].nextAction.url | string (uri) |  | (nullable)
OrderService | applyManualDiscount | response | payments[].nextAction.expiresAt | string (date-time) |  | (nullable)
OrderService | applyManualDiscount | response | payments[].lastInquiryAt | string (date-time) |  | (nullable)
OrderService | applyManualDiscount | response | payments[].recordedAt | string (date-time) | yes
OrderService | applyManualDiscount | response | payments[].syncedAt | string (date-time) |  | (nullable)
OrderService | applyManualDiscount | response | principalId | string (uuid)
OrderService | applyManualDiscount | response | workstationId | string (uuid)
OrderService | applyManualDiscount | response | shiftId | string (uuid) |  | (nullable)
OrderService | applyManualDiscount | response | subjectId | string (uuid) |  | (nullable)
OrderService | applyManualDiscount | response | holdLabel | string |  | The label a cashier gave when parking it with holdOrder — how they find it again. (max length 60; read-only; nullable)
OrderService | applyManualDiscount | response | heldUntil | string (date-time) |  | When a held order expires and is voided (states/order.yaml), from holdOrder's holdUntil. (read-only; nullable)
OrderService | applyManualDiscount | response | createdAt | string (date-time) | yes
OrderService | applyManualDiscount | response | recordedAt | string (date-time) | yes
OrderService | applyManualDiscount | response | syncedAt | string (date-time) |  | (nullable)
OrderService | applyManualDiscount | param (path) | orderId | string (uuid) | yes
OrderService | applyManualDiscount | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | applyTransportNetworkImport | response | id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | applyTransportNetworkImport | response | venueId | string (uuid) | yes | (read-only)
VenueOpsService | applyTransportNetworkImport | response | format | enum (csvBundle, gtfs) | yes
VenueOpsService | applyTransportNetworkImport | response | sourceRef | string (uuid) | yes
VenueOpsService | applyTransportNetworkImport | response | status | TransportNetworkImportStatus: enum (validating, previewReady, failed, applied, expired) | yes | validating → previewReady or failed; previewReady → applied, or expired after 7 days unapplied (proposed, client to correct).
VenueOpsService | applyTransportNetworkImport | response | preview | object |  | What applying would write. (read-only; nullable)
VenueOpsService | applyTransportNetworkImport | response | preview.stationsToCreate | integer |  | (min 0)
VenueOpsService | applyTransportNetworkImport | response | preview.stationsToUpdate | integer |  | (min 0)
VenueOpsService | applyTransportNetworkImport | response | preview.routesToCreate | integer |  | (min 0)
VenueOpsService | applyTransportNetworkImport | response | preview.routesToUpdate | integer |  | (min 0)
VenueOpsService | applyTransportNetworkImport | response | preview.stopsToWrite | integer |  | (min 0)
VenueOpsService | applyTransportNetworkImport | response | preview.timetablesToCreate | integer |  | (min 0)
VenueOpsService | applyTransportNetworkImport | response | findings | array of TransportNetworkImportFinding |  | (max items 1000; read-only)
VenueOpsService | applyTransportNetworkImport | response | findings[].code | enum (nothingFound, fileMissing, headerMismatch, stationCodeDuplicate, stationCoordinatesMissing, routeCodeDuplicate, routeStopUnknownStation, routeOffsetsNotIncreasing, …) | yes | stationCoordinatesMissing is a warning (the station is listed and left off the map); routeActiveStopsChanged is a warning (those stops are skipped); every other code is an error and blocks the apply.
VenueOpsService | applyTransportNetworkImport | response | findings[].severity | enum (error, warning) | yes
VenueOpsService | applyTransportNetworkImport | response | findings[].file | string |  | e.g. (nullable)
VenueOpsService | applyTransportNetworkImport | response | findings[].row | integer |  | (min 1; nullable)
VenueOpsService | applyTransportNetworkImport | response | findings[].reference | string |  | The station (nullable)
VenueOpsService | applyTransportNetworkImport | response | findings[].message | string | yes | (max length 500)
VenueOpsService | applyTransportNetworkImport | response | createdBy | string (uuid) |  | (read-only)
VenueOpsService | applyTransportNetworkImport | response | createdAt | string (date-time) |  | (read-only)
VenueOpsService | applyTransportNetworkImport | response | appliedBy | string (uuid) |  | (read-only; nullable)
VenueOpsService | applyTransportNetworkImport | response | appliedAt | string (date-time) |  | (read-only; nullable)
VenueOpsService | applyTransportNetworkImport | param (path) | importId | string (uuid) | yes
VenueOpsService | applyTransportNetworkImport | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | approveManualOverrideSupervisor | request | supervisorId | string | yes | Approving supervisor
AccessService | approveManualOverrideSupervisor | request | scanId | string | yes | The denied scan being overridden
AccessService | approveManualOverrideSupervisor | request | selectType | enum (guestService, ticketingError, operationalException, managementAuthorization, technicalFailure, eventException, other) | yes | Override reason category
AccessService | approveManualOverrideSupervisor | request | reasonNote | string |  | Free-text justification
AccessService | approveManualOverrideSupervisor | request | accessPointId | string |  | Gate
AccessService | approveManualOverrideSupervisor | request | deviceId | string |  | Device
AccessService | approveManualOverrideSupervisor | request | originalDecision | string |  | Original validation decision, read only and never rewritten
AccessService | approveManualOverrideSupervisor | response | supervisorId | string | yes | Approving supervisor
AccessService | approveManualOverrideSupervisor | response | scanId | string | yes | The denied scan being overridden
AccessService | approveManualOverrideSupervisor | response | selectType | enum (guestService, ticketingError, operationalException, managementAuthorization, technicalFailure, eventException, other) | yes | Override reason category
AccessService | approveManualOverrideSupervisor | response | reasonNote | string |  | Free-text justification
AccessService | approveManualOverrideSupervisor | response | accessPointId | string |  | Gate
AccessService | approveManualOverrideSupervisor | response | deviceId | string |  | Device
AccessService | approveManualOverrideSupervisor | response | originalDecision | string |  | Original validation decision, read only and never rewritten
AccessService | approveManualOverrideSupervisor | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | approveMatrixMultiLevel | request | code | string | yes | Stable rule code the PUT upserts by
TenancyService | approveMatrixMultiLevel | request | approvalMode | enum (single, sequential, parallel, anyOne, allMustApprove, conditional, multiLevel) | yes | How approvers at this rule combine
TenancyService | approveMatrixMultiLevel | request | amount | Money |  | On the wire this is three fields; in the database it is one column.
TenancyService | approveMatrixMultiLevel | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | approveMatrixMultiLevel | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | approveMatrixMultiLevel | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | approveMatrixMultiLevel | request | percentage | number |  | Percentage
TenancyService | approveMatrixMultiLevel | request | module | string |  | Module
TenancyService | approveMatrixMultiLevel | request | product | string |  | Product
TenancyService | approveMatrixMultiLevel | request | venue | string |  | Venue
TenancyService | approveMatrixMultiLevel | request | department | string |  | Department
TenancyService | approveMatrixMultiLevel | request | customerType | string |  | Customer Type
TenancyService | approveMatrixMultiLevel | request | risk | string |  | Risk
TenancyService | approveMatrixMultiLevel | request | exceptionType | string |  | Exception Type
TenancyService | approveMatrixMultiLevel | request | legalEntity | string |  | Legal Entity
TenancyService | approveMatrixMultiLevel | request | minimumApprovals | integer |  | N in N-of-M: approvals needed from the approver group
TenancyService | approveMatrixMultiLevel | request | rejectionBehavior | enum (rejectRequest, returnToPreviousLevel, returnToRequester) |  | What a rejection at this level does
TenancyService | approveMatrixMultiLevel | request | requestChanges | boolean |  | Approvers may return the request for changes
TenancyService | approveMatrixMultiLevel | request | delegate | boolean |  | Approvers may delegate
TenancyService | approveMatrixMultiLevel | request | reassign | boolean |  | The request may be reassigned
TenancyService | approveMatrixMultiLevel | request | skipConditions | string |  | Skip Conditions
TenancyService | approveMatrixMultiLevel | request | requiredApproverRole | string |  | Role that must always approve, e.g.
TenancyService | approveMatrixMultiLevel | response | code | string | yes | Stable rule code the PUT upserts by
TenancyService | approveMatrixMultiLevel | response | approvalMode | enum (single, sequential, parallel, anyOne, allMustApprove, conditional, multiLevel) | yes | How approvers at this rule combine
TenancyService | approveMatrixMultiLevel | response | amount | Money |  | On the wire this is three fields; in the database it is one column.
TenancyService | approveMatrixMultiLevel | response | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | approveMatrixMultiLevel | response | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | approveMatrixMultiLevel | response | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | approveMatrixMultiLevel | response | percentage | number |  | Percentage
TenancyService | approveMatrixMultiLevel | response | module | string |  | Module
TenancyService | approveMatrixMultiLevel | response | product | string |  | Product
TenancyService | approveMatrixMultiLevel | response | venue | string |  | Venue
TenancyService | approveMatrixMultiLevel | response | department | string |  | Department
TenancyService | approveMatrixMultiLevel | response | customerType | string |  | Customer Type
TenancyService | approveMatrixMultiLevel | response | risk | string |  | Risk
TenancyService | approveMatrixMultiLevel | response | exceptionType | string |  | Exception Type
TenancyService | approveMatrixMultiLevel | response | legalEntity | string |  | Legal Entity
TenancyService | approveMatrixMultiLevel | response | minimumApprovals | integer |  | N in N-of-M: approvals needed from the approver group
TenancyService | approveMatrixMultiLevel | response | rejectionBehavior | enum (rejectRequest, returnToPreviousLevel, returnToRequester) |  | What a rejection at this level does
TenancyService | approveMatrixMultiLevel | response | requestChanges | boolean |  | Approvers may return the request for changes
TenancyService | approveMatrixMultiLevel | response | delegate | boolean |  | Approvers may delegate
TenancyService | approveMatrixMultiLevel | response | reassign | boolean |  | The request may be reassigned
TenancyService | approveMatrixMultiLevel | response | skipConditions | string |  | Skip Conditions
TenancyService | approveMatrixMultiLevel | response | requiredApproverRole | string |  | Role that must always approve, e.g.
TenancyService | approveMatrixMultiLevel | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | approveRoleAuthorityDelegation | request | user | string |  | User
TenancyService | approveRoleAuthorityDelegation | request | role | string |  | Role
TenancyService | approveRoleAuthorityDelegation | request | position | string |  | Position
TenancyService | approveRoleAuthorityDelegation | request | department | string |  | Department
TenancyService | approveRoleAuthorityDelegation | request | venue | string |  | Venue
TenancyService | approveRoleAuthorityDelegation | request | businessUnit | string |  | Business Unit
TenancyService | approveRoleAuthorityDelegation | request | legalEntity | string |  | Legal Entity
TenancyService | approveRoleAuthorityDelegation | request | region | string |  | Region
TenancyService | approveRoleAuthorityDelegation | request | delegator | string | yes | Delegator
TenancyService | approveRoleAuthorityDelegation | request | delegate | string | yes | Delegate
TenancyService | approveRoleAuthorityDelegation | request | scope | string |  | Scope
TenancyService | approveRoleAuthorityDelegation | request | start | string (date-time) | yes | Delegation start
TenancyService | approveRoleAuthorityDelegation | request | end | string (date-time) | yes | Delegation end
TenancyService | approveRoleAuthorityDelegation | request | reason | string |  | Reason
TenancyService | approveRoleAuthorityDelegation | request | delegationType | enum (leave, travel, vacancy, eventOperations) |  | Why temporary authority is granted
TenancyService | approveRoleAuthorityDelegation | request | requiredRole | string |  | Required role
TenancyService | approveRoleAuthorityDelegation | request | authorityAmount | Money |  | On the wire this is three fields; in the database it is one column.
TenancyService | approveRoleAuthorityDelegation | request | authorityAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | approveRoleAuthorityDelegation | request | authorityAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | approveRoleAuthorityDelegation | request | authorityAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | approveRoleAuthorityDelegation | request | requestKind | string |  | What the authority limit covers, e.g.
TenancyService | approveRoleAuthorityDelegation | request | authorityPercentage | number |  | Percentage limit where the authority is a percentage, e.g.
TenancyService | approveRoleAuthorityDelegation | response | user | string |  | User
TenancyService | approveRoleAuthorityDelegation | response | role | string |  | Role
TenancyService | approveRoleAuthorityDelegation | response | position | string |  | Position
TenancyService | approveRoleAuthorityDelegation | response | department | string |  | Department
TenancyService | approveRoleAuthorityDelegation | response | venue | string |  | Venue
TenancyService | approveRoleAuthorityDelegation | response | businessUnit | string |  | Business Unit
TenancyService | approveRoleAuthorityDelegation | response | legalEntity | string |  | Legal Entity
TenancyService | approveRoleAuthorityDelegation | response | region | string |  | Region
TenancyService | approveRoleAuthorityDelegation | response | delegator | string | yes | Delegator
TenancyService | approveRoleAuthorityDelegation | response | delegate | string | yes | Delegate
TenancyService | approveRoleAuthorityDelegation | response | scope | string |  | Scope
TenancyService | approveRoleAuthorityDelegation | response | start | string (date-time) | yes | Delegation start
TenancyService | approveRoleAuthorityDelegation | response | end | string (date-time) | yes | Delegation end
TenancyService | approveRoleAuthorityDelegation | response | reason | string |  | Reason
TenancyService | approveRoleAuthorityDelegation | response | delegationType | enum (leave, travel, vacancy, eventOperations) |  | Why temporary authority is granted
TenancyService | approveRoleAuthorityDelegation | response | requiredRole | string |  | Required role
TenancyService | approveRoleAuthorityDelegation | response | authorityAmount | Money |  | On the wire this is three fields; in the database it is one column.
TenancyService | approveRoleAuthorityDelegation | response | authorityAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | approveRoleAuthorityDelegation | response | authorityAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | approveRoleAuthorityDelegation | response | authorityAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | approveRoleAuthorityDelegation | response | requestKind | string |  | What the authority limit covers, e.g.
TenancyService | approveRoleAuthorityDelegation | response | authorityPercentage | number |  | Percentage limit where the authority is a percentage, e.g.
TenancyService | approveRoleAuthorityDelegation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | approveShiftOpen | request | reason | string | yes | (min length 3; max length 300)
OrderService | approveShiftOpen | response | id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | approveShiftOpen | response | workstationId | string (uuid) | yes
OrderService | approveShiftOpen | response | venueId | string (uuid) | yes
OrderService | approveShiftOpen | response | scopePath | string | yes
OrderService | approveShiftOpen | response | principalId | string (uuid) | yes | Who opened it.
OrderService | approveShiftOpen | response | principalDisplayName | string
OrderService | approveShiftOpen | response | incidents | array of object |  | BL-097.
OrderService | approveShiftOpen | response | incidents[].kind | enum (noSale, drawerOpen, override, voidAfterPayment, guestDispute, tillJam, priceQuery, other)
OrderService | approveShiftOpen | response | incidents[].at | string (date-time)
OrderService | approveShiftOpen | response | incidents[].principalId | string (uuid)
OrderService | approveShiftOpen | response | incidents[].note | string |  | (nullable)
OrderService | approveShiftOpen | response | status | ShiftStatus: enum (pendingApproval, open, suspended, pendingVariance, pendingClosure, closed, autoClosed) | yes
OrderService | approveShiftOpen | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | approveShiftOpen | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | approveShiftOpen | response | depositBoxCode | string |  | (nullable)
OrderService | approveShiftOpen | response | bagNumber | string |  | (nullable)
OrderService | approveShiftOpen | response | openingFloat | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | approveShiftOpen | response | openingFloat.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | approveShiftOpen | response | openingFloat.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | approveShiftOpen | response | openingFloat.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | approveShiftOpen | response | salesTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | approveShiftOpen | response | salesTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | approveShiftOpen | response | salesTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | approveShiftOpen | response | salesTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | approveShiftOpen | response | refundsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | approveShiftOpen | response | refundsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | approveShiftOpen | response | refundsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | approveShiftOpen | response | refundsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | approveShiftOpen | response | liftsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | approveShiftOpen | response | liftsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | approveShiftOpen | response | liftsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | approveShiftOpen | response | liftsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | approveShiftOpen | response | expectedCash | object |  | 26 September, pull audit R207. (read-only; nullable)
OrderService | approveShiftOpen | response | expectedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | approveShiftOpen | response | expectedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | approveShiftOpen | response | expectedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | approveShiftOpen | response | countedCash | object |  | What the close count found. (read-only; nullable)
OrderService | approveShiftOpen | response | countedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | approveShiftOpen | response | countedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | approveShiftOpen | response | countedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | approveShiftOpen | response | variance | object |  | Counted minus expected, as ShiftCloseResult.variance. (read-only; nullable)
OrderService | approveShiftOpen | response | variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | approveShiftOpen | response | variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | approveShiftOpen | response | variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | approveShiftOpen | response | cashierReason | enum (tillError, unrecordedRefund, miscount, other) |  | What the cashier said went wrong, given with the blind count (CloseShiftRequest.cashierReason, DI-803) without seeing the variance; the supervisor reads it beside the variance on BO-040 (CHG-FIN-003). (read-only; nullable)
OrderService | approveShiftOpen | response | cashierNote | string |  | The cashier's note with the count (CloseShiftRequest.notes; CHG-FIN-003). (max length 1000; read-only; nullable)
OrderService | approveShiftOpen | response | varianceReasonRequired | boolean |  | Computed, not stored (CHG-R4-019): true while the shift is pendingClosure because its count differs from the expected figure within the threshold and no cashierReason is recorded. (read-only)
OrderService | approveShiftOpen | response | heldLeaseCount | integer |  | Inventory leases currently held by this workstation.
OrderService | approveShiftOpen | response | openedAt | string (date-time) | yes
OrderService | approveShiftOpen | response | businessDate | string (date) |  | The business day the shift belongs to (12 October 2026, CHG-R6-032): the venue-local date of openedAt taken against the venue's businessDayCutoff (tenancy VenueSettings, inheriting the tenant default… (read-only)
OrderService | approveShiftOpen | response | recordedAt | string (date-time) |  | When the device recorded the open.
OrderService | approveShiftOpen | response | suspendedAt | string (date-time) |  | (nullable)
OrderService | approveShiftOpen | response | suspendReason | string |  | The reason given to suspendShift. (max length 200; nullable)
OrderService | approveShiftOpen | response | closedAt | string (date-time) |  | (nullable)
OrderService | approveShiftOpen | response | closedByPrincipalId | string (uuid) |  | Who submitted the close count. (nullable)
OrderService | approveShiftOpen | response | recountRequestedAt | string (date-time) |  | Set by rejectShiftVariance, cleared by the cashier's recount (decided 2 October 2026, Chinmay; DEC-175; CHG-CSP-013; DI-804). (read-only; nullable)
OrderService | approveShiftOpen | response | recountRequestedByPrincipalId | string (uuid) |  | The supervisor who sent the count back (CHG-CSP-013). (read-only; nullable)
OrderService | approveShiftOpen | response | recountReason | string |  | The supervisor's reason, shown to the cashier; never an amount (CHG-CSP-013, CHG-FIN-003). (max length 500; read-only; nullable)
OrderService | approveShiftOpen | response | countNumber | integer |  | How many close counts the shift has had: 0 before the first, 1 after it, 2 after a recount (CHG-CSP-013). (min 0; read-only)
OrderService | approveShiftOpen | response | syncedAt | string (date-time) |  | Null while the shift has unsynced operations. (nullable)
OrderService | approveShiftOpen | response | approvals | array of object
OrderService | approveShiftOpen | response | approvals[].kind | enum (open, close, variance) | yes | open from approveShiftOpen, close from approveShiftClose, variance from acceptShiftVariance.
OrderService | approveShiftOpen | response | approvals[].principalId | string (uuid) | yes
OrderService | approveShiftOpen | response | approvals[].at | string (date-time) | yes
OrderService | approveShiftOpen | response | approvals[].reason | string
OrderService | approveShiftOpen | param (path) | shiftId | string (uuid) | yes
OrderService | approveShiftOpen | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
ReportingService | askReportingQuestion | request | question | string | yes | (min length 3; max length 1000)
ReportingService | askReportingQuestion | request | conversationId | string |  | Continue a prior exchange for follow-up questions.
ReportingService | askReportingQuestion | request | venueId | string (uuid) |  | Narrows the answer to one venue.
ReportingService | askReportingQuestion | response | conversationId | string | yes
ReportingService | askReportingQuestion | response | question | string | yes
ReportingService | askReportingQuestion | response | interpretation | string | yes | What the question was understood to mean, in plain language.
ReportingService | askReportingQuestion | response | semanticSpec | object |  | What the model returned instead of SQL (design 2.2 E, 5.7): metric, dimensions, filters, period, comparison, as validated against the semantic model. (nullable)
ReportingService | askReportingQuestion | response | semanticSpec.metric | string | yes | A measure field code in the SemanticModel, or a KpiDefinition.code.
ReportingService | askReportingQuestion | response | semanticSpec.dimensions | array of string |  | Field codes to group by. (max items 5)
ReportingService | askReportingQuestion | response | semanticSpec.filters | array of object
ReportingService | askReportingQuestion | response | semanticSpec.filters[].field | string | yes | A SemanticModel field code.
ReportingService | askReportingQuestion | response | semanticSpec.filters[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, isNull, …) | yes
ReportingService | askReportingQuestion | response | semanticSpec.filters[].values | array of object |  | Open on purpose; typed by the field.
ReportingService | askReportingQuestion | response | semanticSpec.period | string | yes | ISO 8601 interval in the venue's time zone, e.g.
ReportingService | askReportingQuestion | response | semanticSpec.comparison | enum (previousPeriod, samePeriodLastYear, target, benchmark) |  | As getKpiValues compareTo. (nullable)
ReportingService | askReportingQuestion | response | semanticSpec.semanticModelVersion | integer |  | The SemanticModel.version the spec was validated and compiled against. (read-only)
ReportingService | askReportingQuestion | response | generatedQuery | object |  | The query the spec compiled to: data source, columns, filters, grouping, and the compiled SQL in compiledSql. (nullable)
ReportingService | askReportingQuestion | response | generatedQuery.dataSource | DataSource: enum (orders, orderLines, payments, refunds, shifts, scanEvents, entitlements, products, …) |  | What a report may be built over.
ReportingService | askReportingQuestion | response | generatedQuery.columns | array of ReportColumn
ReportingService | askReportingQuestion | response | generatedQuery.columns[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | askReportingQuestion | response | generatedQuery.columns[].field | string | yes
ReportingService | askReportingQuestion | response | generatedQuery.columns[].label | string
ReportingService | askReportingQuestion | response | generatedQuery.columns[].aggregation | object |  | (default none)
ReportingService | askReportingQuestion | response | generatedQuery.columns[].sortOrder | integer
ReportingService | askReportingQuestion | response | generatedQuery.columns[].sortDirection | enum (asc, desc)
ReportingService | askReportingQuestion | response | generatedQuery.columns[].format | string |  | (nullable)
ReportingService | askReportingQuestion | response | generatedQuery.columns[].role | enum (dimension, measure) |  | What the column is to a chart (decided 2 October 2026, Chinmay; CHG-FIN-007). (nullable)
ReportingService | askReportingQuestion | response | generatedQuery.columns[].encoding | enum (category, x, y, series, value, size, colour, location, …) |  | Which field well the column fills (CHG-FIN-007), the binding the twenty marks of DashboardTile.visualisation need. (nullable)
ReportingService | askReportingQuestion | response | generatedQuery.columns[].axis | enum (primary, secondary) |  | For a measure on a combo, the axis it is drawn against. (nullable)
ReportingService | askReportingQuestion | response | generatedQuery.columns[].seriesType | enum (bar, line, area) |  | For a measure on a combo, how that series is drawn (CHG-FIN-007). (nullable)
ReportingService | askReportingQuestion | response | generatedQuery.columns[].hierarchyLevel | integer |  | For matrix rows and columns, treemap nesting and decompositionTree levels, the depth of this dimension, 1 outermost. (min 1; nullable)
ReportingService | askReportingQuestion | response | generatedQuery.columns[].unitLabel | string |  | The unit an axis states, for example "AED" or "Admissions". (max length 40; nullable)
ReportingService | askReportingQuestion | response | generatedQuery.filters | array of ReportFilter
ReportingService | askReportingQuestion | response | generatedQuery.filters[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | askReportingQuestion | response | generatedQuery.filters[].field | string | yes
ReportingService | askReportingQuestion | response | generatedQuery.filters[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, contains, …) | yes
ReportingService | askReportingQuestion | response | generatedQuery.filters[].value | object |  | Open on purpose; its type is the field's.
ReportingService | askReportingQuestion | response | generatedQuery.filters[].values | array of object |  | The values for in and notIn, or exactly two (from, to) for between.
ReportingService | askReportingQuestion | response | generatedQuery.filters[].isParameter | boolean |  | Prompted at run time rather than fixed. (default False)
ReportingService | askReportingQuestion | response | generatedQuery.groupBy | array of string
ReportingService | askReportingQuestion | response | generatedQuery.compiledSql | string |  | The SQL the semantic spec compiled to, exactly as run on the analytical replica (29 September, design 5.7). (nullable)
ReportingService | askReportingQuestion | response | result | object | yes | Null when the question is outside the semantic model. (nullable)
ReportingService | askReportingQuestion | response | result.executionId | string | yes
ReportingService | askReportingQuestion | response | result.columns | array of object | yes
ReportingService | askReportingQuestion | response | result.columns[].key | string
ReportingService | askReportingQuestion | response | result.columns[].label | string
ReportingService | askReportingQuestion | response | result.columns[].type | FieldType: enum (string, integer, decimal, money, boolean, date, dateTime, uuid, …)
ReportingService | askReportingQuestion | response | result.rows | array of object | yes | Open on purpose; the shape is columns.
ReportingService | askReportingQuestion | response | result.totals | object |  | Aggregated columns only, keyed and typed as a row is.
ReportingService | askReportingQuestion | response | result.rowCount | integer
ReportingService | askReportingQuestion | response | result.nextCursor | string |  | (nullable)
ReportingService | askReportingQuestion | response | result.generatedAt | string (date-time)
ReportingService | askReportingQuestion | response | result.dataAsOf | string (date-time) |  | Replica position the result was read at.
ReportingService | askReportingQuestion | response | dataAsOf | string (date-time) |  | Replica position the answer was read at, the result's dataAsOf, stated beside the answer so a figure that moved is not argued about. (nullable)
ReportingService | askReportingQuestion | response | reliability | ReportingAnswerReliability: enum (grounded, partial, conflictingSources, insufficientEvidence) | yes | How far an analytics answer can be relied on (decided 29 September, AI system design 5.6): a category, never a bare percentage.
ReportingService | askReportingQuestion | response | unavailableReason | object |  | Set only when reliability is insufficientEvidence because the question is outside the semantic model ("not available yet"); names which part is not modelled. (nullable)
ReportingService | askReportingQuestion | response | confidence | number |  | Superseded by reliability on 29 September (design 5.6, never a bare percentage for analytics). (min 0; max 1)
ReportingService | askReportingQuestion | response | suggestedFollowUps | array of string
ReportingService | askReportingQuestion | response | modelVersion | string
ReportingService | askReportingQuestion | response | tokensUsed | integer
ReportingService | askReportingQuestion | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | attachModifierGroup | request | groupIds | array of string (uuid) | yes
FnbService | attachModifierGroup | response | id | string (uuid) | yes
FnbService | attachModifierGroup | response | productVariantId | string (uuid) | yes | The catalogue variant this item links to, for reporting, stock and tax class only.
FnbService | attachModifierGroup | response | name | string | yes
FnbService | attachModifierGroup | response | description | string |  | (nullable)
FnbService | attachModifierGroup | response | price | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | attachModifierGroup | response | price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | attachModifierGroup | response | price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | attachModifierGroup | response | price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | attachModifierGroup | response | dailyCount | integer |  | How many portions the kitchen set for today (setMenuItemDailyCount; Chinmay, 2 October, workbook Q194; CHG-CSA-017). (min 0; read-only; nullable)
FnbService | attachModifierGroup | response | remainingCount | integer |  | What is left of dailyCount ("6 left" on the till and the guest menu). (min 0; read-only; nullable)
FnbService | attachModifierGroup | response | sortOrder | integer
FnbService | attachModifierGroup | response | modifierGroupIds | array of string (uuid)
FnbService | attachModifierGroup | response | stationId | string (uuid) |  | (nullable)
FnbService | attachModifierGroup | response | menuSectionId | string (uuid) |  | The section the item sits in, set by setMenuSections and applyMenuActions (moveSection). (read-only; nullable)
FnbService | attachModifierGroup | response | isStockTracked | boolean |  | True where a recipe exists.
FnbService | attachModifierGroup | response | isAvailable | boolean | yes
FnbService | attachModifierGroup | response | unavailableReason | string |  | (nullable)
FnbService | attachModifierGroup | response | restoreAt | string (date-time) |  | When an unavailable item comes back on its own (setItemAvailability). (nullable)
FnbService | attachModifierGroup | response | preparationMinutes | integer |  | (nullable)
FnbService | attachModifierGroup | response | allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | attachModifierGroup | param (path) | menuItemId | string (uuid) | yes
FnbService | attachModifierGroup | param (header) | If-Match | string |  | Optimistic concurrency for serverWins (system-design review SD-013, 29 September; ADR-0031).
FnbService | attachModifierGroup | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | awardBadge | request | id | string (uuid)
MarketingService | awardBadge | request | customerId | string (uuid) | yes
MarketingService | awardBadge | request | badgeId | string (uuid) | yes
MarketingService | awardBadge | request | challengeId | string (uuid) |  | (nullable)
MarketingService | awardBadge | request | sourceType | string |  | (max length 30; nullable)
MarketingService | awardBadge | request | sourceReferenceId | string (uuid) |  | (nullable)
MarketingService | awardBadge | request | awardedAt | string (date-time) | yes
MarketingService | awardBadge | request | expiresAt | string (date-time) |  | (nullable)
MarketingService | awardBadge | request | status | string | yes | (max length 20)
MarketingService | awardBadge | response | id | string (uuid)
MarketingService | awardBadge | response | customerId | string (uuid) | yes
MarketingService | awardBadge | response | badgeId | string (uuid) | yes
MarketingService | awardBadge | response | challengeId | string (uuid) |  | (nullable)
MarketingService | awardBadge | response | sourceType | string |  | (max length 30; nullable)
MarketingService | awardBadge | response | sourceReferenceId | string (uuid) |  | (nullable)
MarketingService | awardBadge | response | awardedAt | string (date-time) | yes
MarketingService | awardBadge | response | expiresAt | string (date-time) |  | (nullable)
MarketingService | awardBadge | response | status | string | yes | (max length 20)
MarketingService | awardBadge | param (path) | customerId | string (uuid) | yes
MarketingService | awardBadge | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | bindCredentialDevice | request | deviceId | string | yes | The app's stable device identifier (max length 128)
AccessService | bindCredentialDevice | request | deviceReference | string |  | (max length 200; nullable)
AccessService | bindCredentialDevice | request | appInstallationId | string |  | (max length 128; nullable)
AccessService | bindCredentialDevice | request | os | string |  | (max length 64; nullable)
AccessService | bindCredentialDevice | request | otp | string |  | Verified one-time code, where the policy is otpVerificationRequired and this is a device change (max length 12; nullable)
AccessService | bindCredentialDevice | response | id | string (uuid) | yes
AccessService | bindCredentialDevice | response | subjectId | string (uuid) |  | The guest (pii.subject) (nullable)
AccessService | bindCredentialDevice | response | entitlementId | string (uuid) | yes
AccessService | bindCredentialDevice | response | credentialBindingId | string (uuid) |  | (nullable)
AccessService | bindCredentialDevice | response | deviceId | string | yes | (max length 200)
AccessService | bindCredentialDevice | response | deviceReference | string |  | (max length 200; nullable)
AccessService | bindCredentialDevice | response | appInstallationId | string |  | (max length 200; nullable)
AccessService | bindCredentialDevice | response | os | string |  | (max length 50; nullable)
AccessService | bindCredentialDevice | response | registeredAt | string (date-time) | yes
AccessService | bindCredentialDevice | response | lastActivatedAt | string (date-time) |  | (nullable)
AccessService | bindCredentialDevice | response | lastKnownVenueId | string (uuid) |  | (nullable)
AccessService | bindCredentialDevice | response | securityStatus | enum (normal, suspicious, blocked) | yes | (default normal)
AccessService | bindCredentialDevice | response | deactivatedAt | string (date-time) |  | Set when the binding is removed (deactivation, or a transfer of the credential) (nullable)
AccessService | bindCredentialDevice | response | scopePath | string | yes | ltree of the owning scope node
AccessService | bindCredentialDevice | response | updatedAt | string (date-time) |  | (read-only)
AccessService | bindCredentialDevice | param (path) | credentialId | string (uuid) | yes | The Virtual Ticket (access.entitlement.id); decided 29 September, writers pass
AccessService | bindCredentialDevice | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | bookVisitPlan | request | baseVersion | integer | yes | The version the guest is looking at. (min 1)
VenueOpsService | bookVisitPlan | request | cartId | string (uuid) |  | The guest's open cart. (nullable)
VenueOpsService | bookVisitPlan | request | itemIds | array of string (uuid) |  | Only these items.
VenueOpsService | bookVisitPlan | request | includeAddOns | boolean |  | Also add the add-ons the guest accepted on the plan (VisitPlanItem.addOnAccepted). (default True)
VenueOpsService | bookVisitPlan | response | planId | string (uuid) | yes
VenueOpsService | bookVisitPlan | response | cartId | string (uuid) | yes
VenueOpsService | bookVisitPlan | response | added | array of object | yes
VenueOpsService | bookVisitPlan | response | added[].itemId | string (uuid)
VenueOpsService | bookVisitPlan | response | added[].cartLineId | string (uuid)
VenueOpsService | bookVisitPlan | response | added[].leaseExpiresAt | string (date-time) |  | (nullable)
VenueOpsService | bookVisitPlan | response | notAdded | array of object | yes | Items that could not be added, with the addCartLine refusal each met.
VenueOpsService | bookVisitPlan | response | notAdded[].itemId | string (uuid)
VenueOpsService | bookVisitPlan | response | notAdded[].reason | string |  | The orders CartProblem code, e.g.
VenueOpsService | bookVisitPlan | response | freeItems | integer |  | Stops that need nothing bought.
VenueOpsService | bookVisitPlan | param (path) | planId | string (uuid) | yes
VenueOpsService | bookVisitPlan | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | buildDeepLink | request | target | LinkTarget | yes
WhiteLabelService | buildDeepLink | request | target.kind | enum (module, contentPage, product, event, externalUrl, appSection, none) | yes | appSection points at a section of the guest mobile app (decided 29 September, MOB-1), so the bottom navigation can hold Home, Explore, Plan and Tickets.
WhiteLabelService | buildDeepLink | request | target.moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) |  | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | buildDeepLink | request | target.appSection | enum (home, explore, plan, tickets, map, account, buyTickets) |  | Required when kind is appSection.
WhiteLabelService | buildDeepLink | request | target.contentPageId | string (uuid)
WhiteLabelService | buildDeepLink | request | target.productId | string (uuid)
WhiteLabelService | buildDeepLink | request | target.eventId | string (uuid)
WhiteLabelService | buildDeepLink | request | target.url | string
WhiteLabelService | buildDeepLink | request | utm | object |  | Campaign tags appended to the link, e.g.
WhiteLabelService | buildDeepLink | response | url | string | yes
WhiteLabelService | buildDeepLink | response | appLink | string |  | The universal or app link that opens the app where installed. (nullable)
FnbService | buildProductionPlan | request | id | string (uuid) | yes
FnbService | buildProductionPlan | request | outletId | string (uuid)
FnbService | buildProductionPlan | request | forDate | string (date) | yes | The trading day this prep list is for, in the Region's time zone; a business date, closing at the venue's businessDayCutoff (tenancy VenueSettings, default 00:00; CHG-R6-032).
FnbService | buildProductionPlan | request | status | enum (draft, released, superseded, cancelled) | yes
FnbService | buildProductionPlan | request | basedOnSuggestionId | string (uuid) |  | The forecast it started from. (nullable)
FnbService | buildProductionPlan | request | lines | array of object | yes
FnbService | buildProductionPlan | request | lines[].itemId | string (uuid) | yes
FnbService | buildProductionPlan | request | lines[].suggestedQuantity | number |  | (nullable)
FnbService | buildProductionPlan | request | lines[].plannedQuantity | number | yes
FnbService | buildProductionPlan | request | lines[].uom | string
FnbService | buildProductionPlan | request | lines[].stationId | string (uuid) |  | (nullable)
FnbService | buildProductionPlan | request | releasedRunIds | array of string (uuid) |  | (read-only)
FnbService | buildProductionPlan | response | id | string (uuid) | yes
FnbService | buildProductionPlan | response | outletId | string (uuid)
FnbService | buildProductionPlan | response | forDate | string (date) | yes | The trading day this prep list is for, in the Region's time zone; a business date, closing at the venue's businessDayCutoff (tenancy VenueSettings, default 00:00; CHG-R6-032).
FnbService | buildProductionPlan | response | status | enum (draft, released, superseded, cancelled) | yes
FnbService | buildProductionPlan | response | basedOnSuggestionId | string (uuid) |  | The forecast it started from. (nullable)
FnbService | buildProductionPlan | response | lines | array of object | yes
FnbService | buildProductionPlan | response | lines[].itemId | string (uuid) | yes
FnbService | buildProductionPlan | response | lines[].suggestedQuantity | number |  | (nullable)
FnbService | buildProductionPlan | response | lines[].plannedQuantity | number | yes
FnbService | buildProductionPlan | response | lines[].uom | string
FnbService | buildProductionPlan | response | lines[].stationId | string (uuid) |  | (nullable)
FnbService | buildProductionPlan | response | releasedRunIds | array of string (uuid) |  | (read-only)
FnbService | buildProductionPlan | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | bulkChangePrices | request | dryRun | boolean |  | (default True)
CatalogueService | bulkChangePrices | request | selection | object | yes | A selection, not a list of ids.
CatalogueService | bulkChangePrices | request | selection.categoryId | string (uuid) |  | (nullable)
CatalogueService | bulkChangePrices | request | selection.productKind | string |  | (nullable)
CatalogueService | bulkChangePrices | request | selection.priceListId | string (uuid) |  | (nullable)
CatalogueService | bulkChangePrices | request | selection.channel | SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) |  | Where a sale came from.
CatalogueService | bulkChangePrices | request | adjustment | object | yes
CatalogueService | bulkChangePrices | request | adjustment.mode | enum (percentage, absolute, setTo) | yes
CatalogueService | bulkChangePrices | request | adjustment.value | string | yes | A decimal string, never a float (naming-and-style 5.1). (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | bulkChangePrices | request | adjustment.roundTo | string |  | An increment in the region's currency, as a decimal string (0.5, 5). (pattern ^\d+(\.\d{1,4})?$; nullable)
CatalogueService | bulkChangePrices | request | effectiveFrom | string (date-time) |  | (nullable)
CatalogueService | bulkChangePrices | response | applied | boolean | yes
CatalogueService | bulkChangePrices | response | productsMatched | integer | yes
CatalogueService | bulkChangePrices | response | pricesChanged | integer
CatalogueService | bulkChangePrices | response | skipped | array of object |  | Products the selection matched and the adjustment could not touch — a fixed-price bundle, a partner net rate, a product in an open period.
CatalogueService | bulkChangePrices | response | skipped[].productId | string (uuid)
CatalogueService | bulkChangePrices | response | skipped[].reason | string
CatalogueService | bulkChangePrices | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
InventoryService | bulkUpdateProducts | request | previewOnly | boolean |  | (default True)
InventoryService | bulkUpdateProducts | request | selector | object | yes
InventoryService | bulkUpdateProducts | request | changes | object | yes
InventoryService | bulkUpdateProducts | response | matched | integer
InventoryService | bulkUpdateProducts | response | succeeded | integer
InventoryService | bulkUpdateProducts | response | failed | integer
InventoryService | bulkUpdateProducts | response | failures | array of object |  | One entry per product the change was refused for.
InventoryService | bulkUpdateProducts | response | failures[].productId | string (uuid) | yes
InventoryService | bulkUpdateProducts | response | failures[].code | string | yes | The validation rule the product failed, as in Problem.errors[].code.
InventoryService | bulkUpdateProducts | response | failures[].message | string
InventoryService | bulkUpdateProducts | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | cancelFnbOrder | request | recordedAt | string (date-time) | yes | Device time of the act (offline-capable; replayed in this order).
FnbService | cancelFnbOrder | request | reason | enum (outletRefused, guestCancelled, itemUnavailable, tooLong, error) | yes
FnbService | cancelFnbOrder | request | note | string |  | (max length 300)
FnbService | cancelFnbOrder | request | recordWaste | boolean |  | Where preparation had started.
FnbService | cancelFnbOrder | response | id | string (uuid) | yes
FnbService | cancelFnbOrder | response | orderNumber | string | yes
FnbService | cancelFnbOrder | response | outletId | string (uuid) | yes
FnbService | cancelFnbOrder | response | paymentTiming | object |  | The outlet's payment timing when the order was placed (CHG-CSA-010), kept as a snapshot. (read-only)
FnbService | cancelFnbOrder | response | sentToKitchenAt | string (date-time) |  | When the order's kitchen tickets were created. (read-only; nullable)
FnbService | cancelFnbOrder | response | serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery) | yes
FnbService | cancelFnbOrder | response | tableVisitId | string (uuid) |  | (nullable)
FnbService | cancelFnbOrder | response | status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) | yes | The full lifecycle from 4.6.35.
FnbService | cancelFnbOrder | response | lines | array of object | yes
FnbService | cancelFnbOrder | response | lines[].id | string (uuid) | yes
FnbService | cancelFnbOrder | response | lines[].menuItemId | string (uuid) | yes
FnbService | cancelFnbOrder | response | lines[].quantity | integer | yes | (min 1)
FnbService | cancelFnbOrder | response | lines[].modifierOptionIds | array of string (uuid)
FnbService | cancelFnbOrder | response | lines[].note | string |  | Free text to the kitchen. (max length 200)
FnbService | cancelFnbOrder | response | lines[].seatNumber | integer |  | Which cover ordered it. (nullable)
FnbService | cancelFnbOrder | response | lines[].course | integer |  | Course grouping, so the kitchen fires in sequence. (nullable)
FnbService | cancelFnbOrder | response | lines[].redeemEntitlementId | string |  | A meal combo redeemed at the till or by a scan (29 September, MOB-4; applied 30 September). (nullable)
FnbService | cancelFnbOrder | response | lines[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) |  | The full lifecycle from 4.6.35.
FnbService | cancelFnbOrder | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | cancelFnbOrder | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | cancelFnbOrder | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | cancelFnbOrder | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | cancelFnbOrder | response | lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | cancelFnbOrder | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | cancelFnbOrder | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | cancelFnbOrder | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | cancelFnbOrder | response | salesOrderId | string (uuid) |  | Retyped 29 September (SD-046), and format: uuid since ADR-0056 (30 September): every id is a uuid, so this joins orders.sales_order.id. (nullable)
FnbService | cancelFnbOrder | response | updatedAt | string (date-time) |  | Taken from their fnb.order. (nullable)
FnbService | cancelFnbOrder | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | cancelFnbOrder | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | cancelFnbOrder | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | cancelFnbOrder | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | cancelFnbOrder | response | taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | cancelFnbOrder | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | cancelFnbOrder | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | cancelFnbOrder | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | cancelFnbOrder | response | kitchenTicketId | string (uuid) |  | (nullable)
FnbService | cancelFnbOrder | response | kitchenTickets | array of KitchenTicket |  | The kitchen tickets this order created, one per station (SD-046). (read-only)
FnbService | cancelFnbOrder | response | kitchenTickets[].id | string (uuid) | yes
FnbService | cancelFnbOrder | response | kitchenTickets[].orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | cancelFnbOrder | response | kitchenTickets[].orderNumber | string
FnbService | cancelFnbOrder | response | kitchenTickets[].outletId | string (uuid) | yes
FnbService | cancelFnbOrder | response | kitchenTickets[].tableLabel | string |  | (nullable)
FnbService | cancelFnbOrder | response | kitchenTickets[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | cancelFnbOrder | response | kitchenTickets[].coursing | object |  | BL-131. (nullable)
FnbService | cancelFnbOrder | response | kitchenTickets[].buzzerCode | string |  | BL-128. (nullable)
FnbService | cancelFnbOrder | response | kitchenTickets[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | cancelFnbOrder | response | kitchenTickets[].priority | integer |  | Higher fires sooner.
FnbService | cancelFnbOrder | response | kitchenTickets[].prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | cancelFnbOrder | response | kitchenTickets[].prioritiseReason | string |  | (nullable)
FnbService | cancelFnbOrder | response | kitchenTickets[].lines | array of object | yes
FnbService | cancelFnbOrder | response | kitchenTickets[].lines[].lineId | string (uuid) | yes
FnbService | cancelFnbOrder | response | kitchenTickets[].lines[].name | string | yes
FnbService | cancelFnbOrder | response | kitchenTickets[].lines[].quantity | integer | yes
FnbService | cancelFnbOrder | response | kitchenTickets[].lines[].modifiers | array of string
FnbService | cancelFnbOrder | response | kitchenTickets[].lines[].note | string |  | (nullable)
FnbService | cancelFnbOrder | response | kitchenTickets[].lines[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | cancelFnbOrder | response | kitchenTickets[].lines[].refireOfLineId | string (uuid) |  | Set on a refire. (read-only; nullable)
FnbService | cancelFnbOrder | response | kitchenTickets[].lines[].refireReason | object |  | (read-only; nullable)
FnbService | cancelFnbOrder | response | kitchenTickets[].lines[].isChargeable | boolean |  | A refire's chargeable flag. (read-only; nullable)
FnbService | cancelFnbOrder | response | kitchenTickets[].lines[].course | integer |  | (nullable)
FnbService | cancelFnbOrder | response | kitchenTickets[].lines[].stationId | string (uuid) |  | (nullable)
FnbService | cancelFnbOrder | response | kitchenTickets[].lines[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | cancelFnbOrder | response | kitchenTickets[].createdAt | string (date-time) | yes
FnbService | cancelFnbOrder | response | kitchenTickets[].targetReadyAt | string (date-time) |  | (nullable)
FnbService | cancelFnbOrder | response | kitchenTickets[].elapsedSeconds | integer
FnbService | cancelFnbOrder | response | kitchenTickets[].visitId | string (uuid) |  | The table visit the ticket is for (4 October 2026, CHG-FXC-011; KIT-002): the {visitId} notifyServer takes. (read-only; nullable)
FnbService | cancelFnbOrder | response | estimatedReadyAt | string (date-time) |  | (nullable)
FnbService | cancelFnbOrder | response | createdAt | string (date-time) | yes
FnbService | cancelFnbOrder | response | recordedAt | string (date-time)
FnbService | cancelFnbOrder | response | syncedAt | string (date-time) |  | (nullable)
FnbService | cancelFnbOrder | param (path) | orderId | string (uuid) | yes
FnbService | cancelFnbOrder | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | cancelReservation | param (path) | reservationId | string (uuid) | yes
OrderService | cancelReservation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | capturePayment | request | amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | capturePayment | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | capturePayment | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | capturePayment | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | capturePayment | response | id | string (uuid) | yes
OrderService | capturePayment | response | orderId | string (uuid) | yes
OrderService | capturePayment | response | tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | capturePayment | response | tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | capturePayment | response | tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale.
OrderService | capturePayment | response | tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | capturePayment | response | tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | capturePayment | response | tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | capturePayment | response | fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | capturePayment | response | fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | capturePayment | response | changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | capturePayment | response | amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | capturePayment | response | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | capturePayment | response | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | capturePayment | response | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | capturePayment | response | changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | capturePayment | response | changeAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | capturePayment | response | changeAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | capturePayment | response | changeAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | capturePayment | response | status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | capturePayment | response | providerName | string |  | (nullable)
OrderService | capturePayment | response | providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | capturePayment | response | providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | capturePayment | response | terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | capturePayment | response | nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | capturePayment | response | nextAction.kind | enum (redirect, terminal)
OrderService | capturePayment | response | nextAction.url | string (uri) |  | (nullable)
OrderService | capturePayment | response | nextAction.expiresAt | string (date-time) |  | (nullable)
OrderService | capturePayment | response | lastInquiryAt | string (date-time) |  | (nullable)
OrderService | capturePayment | response | recordedAt | string (date-time) | yes
OrderService | capturePayment | response | syncedAt | string (date-time) |  | (nullable)
OrderService | capturePayment | param (path) | paymentId | string (uuid) | yes
OrderService | capturePayment | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
PlatformService | certifyIntegration | request | decision | enum (certify, reject, revoke) | yes
PlatformService | certifyIntegration | request | certifiedUntil | string (date) |  | (nullable)
PlatformService | certifyIntegration | request | notes | string |  | (nullable)
PlatformService | certifyIntegration | response | id | string (uuid) | yes | (read-only)
PlatformService | certifyIntegration | response | developerId | string (uuid) | yes
PlatformService | certifyIntegration | response | name | string | yes
PlatformService | certifyIntegration | response | category | enum (crm, marketing, accounting, hotel, transport, analytics, accessibility, other) | yes
PlatformService | certifyIntegration | response | description | string
PlatformService | certifyIntegration | response | integrationUrl | string
PlatformService | certifyIntegration | response | requiredScopes | array of string
PlatformService | certifyIntegration | response | status | enum (draft, submitted, inReview, certified, rejected, revoked, delisted) | yes | (read-only)
PlatformService | certifyIntegration | response | certifiedUntil | string (date) |  | Certification expires. (read-only; nullable)
PlatformService | certifyIntegration | response | certifiedAgainstVersion | string |  | (read-only; nullable)
PlatformService | certifyIntegration | response | listingFeeModel | enum (none, flat, revenueShare) |  | (nullable)
PlatformService | certifyIntegration | response | visibility | enum (public, private) |  | private: certified for production access and never shown in the marketplace (17 September minutes, M17-06). (default public)
PlatformService | certifyIntegration | param (path) | listingId | string (uuid) | yes
PlatformService | certifyIntegration | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | changeOwnCredential | request | method | enum (password, pin) | yes | Which credential is being changed.
IdentityService | changeOwnCredential | request | currentCredential | string | yes | (max length 512)
IdentityService | changeOwnCredential | request | newCredential | string | yes | (max length 512)
IdentityService | changeOwnCredential | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | chaseStation | request | ticketId | string (uuid) | yes
FnbService | chaseStation | request | lineId | string (uuid) |  | (nullable)
FnbService | chaseStation | request | recordedAt | string (date-time) | yes | Device time of the chase.
FnbService | chaseStation | param (path) | stationId | string (uuid) | yes
FnbService | chaseStation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | checkBookingEligibility | request | productIds | array of string | yes | (min items 1)
CatalogueService | checkBookingEligibility | request | party | array of EligibilityDeclaration | yes | (min items 1)
CatalogueService | checkBookingEligibility | request | party[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
CatalogueService | checkBookingEligibility | request | party[].ageYears | integer |  | (nullable)
CatalogueService | checkBookingEligibility | request | party[].heightBandIndex | integer |  | Which band of the rule's heightBandsCm, counting from 0. (nullable)
CatalogueService | checkBookingEligibility | request | party[].confidentSwimmer | boolean |  | Superseded by the consent record for the product's swim consent question (decided 29 September, rev 3 REV3-26); see ProductEligibilityRule.swimAbility. (nullable)
CatalogueService | checkBookingEligibility | request | party[].guardianSigned | boolean |  | (default False)
CatalogueService | checkBookingEligibility | response | eligible | boolean | yes
CatalogueService | checkBookingEligibility | response | guests | array of object
CatalogueService | checkBookingEligibility | response | guests[].index | integer
CatalogueService | checkBookingEligibility | response | guests[].eligible | boolean
CatalogueService | checkBookingEligibility | response | guests[].reasons | array of enum (tooYoung, tooOld, tooShort, tooTall, needsAdult, needsGuardianSignature, needsSwimmer)
CatalogueService | checkBookingEligibility | response | waiverRequired | boolean
CatalogueService | checkBookingEligibility | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | checkoutCart | request | subjectId | string (uuid) |  | The guest the order is for.
OrderService | checkoutCart | request | chargeCurrency | string |  | The currency the guest selected to pay in (decided 2 October 2026, Chinmay; CHG-FIN-001). (pattern ^[A-Z]{3}$; nullable)
OrderService | checkoutCart | request | marketingConsents | array of object |  | Marketing opt-ins given at checkout (29 September, M18-15).
OrderService | checkoutCart | request | marketingConsents[].channel | enum (email, sms, whatsapp, push) | yes
OrderService | checkoutCart | request | marketingConsents[].purpose | string | yes | The consent purpose code (marketing ConsentPurpose), for example marketing. (max length 60)
OrderService | checkoutCart | request | marketingConsents[].granted | boolean | yes | True only when the guest ticked it.
OrderService | checkoutCart | request | marketingConsents[].noticeVersion | string |  | The version of the consent notice shown. (max length 40)
OrderService | checkoutCart | request | attendees | array of object |  | The named holder for each cart line that needs one.
OrderService | checkoutCart | request | attendees[].lineId | string (uuid) | yes | A CartLine.id in this cart.
OrderService | checkoutCart | request | attendees[].holderName | string | yes
OrderService | checkoutCart | response | id | string (uuid) | yes | The client UUIDv7 from CreateOrderRequest.id.
OrderService | checkoutCart | response | orderNumber | string |  | The number a guest reads and a cashier types. (read-only)
OrderService | checkoutCart | response | channel | object | yes | Where it came from.
OrderService | checkoutCart | response | channelProfileId | string (uuid) |  | The named sales channel the order came through (catalogue SalesChannelProfile.id), set by the server from the caller: a partner user's or reseller's channel, an API key's channel. (read-only; nullable)
OrderService | checkoutCart | response | venueId | string (uuid) | yes
OrderService | checkoutCart | response | scopePath | string | yes
OrderService | checkoutCart | response | status | OrderStatus: enum (pending, held, paid, partiallyPaid, completed, voided, refunded, partiallyRefunded, …) | yes | held is a parked sale — the cashier freed the till and the guest will return.
OrderService | checkoutCart | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | checkoutCart | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | checkoutCart | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | checkoutCart | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | checkoutCart | response | netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | refundedAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | checkoutCart | response | refundedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | refundedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | refundedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | chargeCurrency | string |  | The currency the guest selected and is charged in (CHG-FIN-001, 2 October 2026). (pattern ^[A-Z]{3}$; read-only; nullable)
OrderService | checkoutCart | response | chargeFxRate | object |  | Units of chargeCurrency per one unit of the base currency, from the region's tender rate in force at checkout (finance.FxRate), stored on the order so the payment, the receipt, the tax invoice and an… (read-only; nullable)
OrderService | checkoutCart | response | chargeFxRateId | string (uuid) |  | The finance.FxRate row the rate was taken from, for audit. (read-only; nullable)
OrderService | checkoutCart | response | chargeTotal | object |  | grossAmount converted at chargeFxRate and rounded to the charge currency's scale: what the guest pays and what the payment request to the provider asks for (CHG-FIN-001). (read-only)
OrderService | checkoutCart | response | chargeTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | chargeTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | chargeTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | chargeRateLockedUntil | string (date-time) |  | The quote holds until then (the cart lease). (read-only; nullable)
OrderService | checkoutCart | response | droppedPromotions | array of object |  | Promotions left off this order at checkout because their budget cap would have been exceeded (decided 28 September, audit R101 (8)). (read-only)
OrderService | checkoutCart | response | droppedPromotions[].promotionId | string (uuid) | yes
OrderService | checkoutCart | response | droppedPromotions[].name | string
OrderService | checkoutCart | response | droppedPromotions[].reason | enum (budgetCapReached)
OrderService | checkoutCart | response | totalPriceVariance | object |  | Sum across lines.
OrderService | checkoutCart | response | totalPriceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | totalPriceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | totalPriceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | lines | array of OrderLine | yes
OrderService | checkoutCart | response | lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | checkoutCart | response | lines[].variantId | string (uuid) | yes
OrderService | checkoutCart | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | checkoutCart | response | lines[].performanceId | string (uuid)
OrderService | checkoutCart | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | checkoutCart | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | checkoutCart | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | checkoutCart | response | lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | checkoutCart | response | lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | checkoutCart | response | lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | checkoutCart | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | checkoutCart | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | checkoutCart | response | lines[].quantity | integer | yes | (min 1)
OrderService | checkoutCart | response | lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | checkoutCart | response | lines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | checkoutCart | response | lines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | checkoutCart | response | lines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | checkoutCart | response | lines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | checkoutCart | response | lines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | checkoutCart | response | lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | checkoutCart | response | lines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | lines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | lines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | lines[].holderName | string |  | (nullable)
OrderService | checkoutCart | response | lines[].dataMaskValues | object |  | Deliberately open.
OrderService | checkoutCart | response | lines[].serverUnitPrice | object | yes | What the server computed on ingest.
OrderService | checkoutCart | response | lines[].serverUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | lines[].serverUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | lines[].serverUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | lines[].priceVariance | object |  | Server minus quoted.
OrderService | checkoutCart | response | lines[].priceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | lines[].priceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | lines[].priceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | checkoutCart | response | lines[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | lines[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | lines[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | checkoutCart | response | lines[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | lines[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | lines[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | checkoutCart | response | lines[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | lines[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | lines[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | lines[].entitlementIds | array of string (uuid) |  | The entitlements this line issued.
OrderService | checkoutCart | response | lines[].crossRegionRightIds | array of string |  | Redemption rights propagated to other cells for this line.
OrderService | checkoutCart | response | lines[].reprintCount | integer |  | How many times this line's tickets were reprinted or resent. (min 0; default 0; read-only)
OrderService | checkoutCart | response | lines[].venueId | string (uuid) |  | The order's venue, copied onto the line (ADR-0044's own example; system-design review SD-008, 29 September) so a line is scoped and partitionable without its order. (read-only)
OrderService | checkoutCart | response | lines[].discounts | array of OrderLineDiscount |  | The discounts applied to this line, one row each (system-design review SD-008, 29 September). (read-only)
OrderService | checkoutCart | response | lines[].discounts[].id | string (uuid) | yes
OrderService | checkoutCart | response | lines[].discounts[].promotionId | string (uuid) |  | The promotion that gave it. (nullable)
OrderService | checkoutCart | response | lines[].discounts[].source | enum (promotion, promoCode, manual, bundle, member) | yes
OrderService | checkoutCart | response | lines[].discounts[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | checkoutCart | response | lines[].discounts[].reason | string |  | A cashier's reason for a manual discount. (max length 200; nullable)
OrderService | checkoutCart | response | payments | array of Payment
OrderService | checkoutCart | response | payments[].id | string (uuid) | yes
OrderService | checkoutCart | response | payments[].orderId | string (uuid) | yes
OrderService | checkoutCart | response | payments[].tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | checkoutCart | response | payments[].tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | payments[].tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale.
OrderService | checkoutCart | response | payments[].tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | payments[].tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | payments[].tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | payments[].fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | checkoutCart | response | payments[].fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | checkoutCart | response | payments[].changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | checkoutCart | response | payments[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | checkoutCart | response | payments[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | payments[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | payments[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | payments[].changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | checkoutCart | response | payments[].changeAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | checkoutCart | response | payments[].changeAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | checkoutCart | response | payments[].changeAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | checkoutCart | response | payments[].status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | checkoutCart | response | payments[].providerName | string |  | (nullable)
OrderService | checkoutCart | response | payments[].providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | checkoutCart | response | payments[].providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | checkoutCart | response | payments[].terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | checkoutCart | response | payments[].nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | checkoutCart | response | payments[].nextAction.kind | enum (redirect, terminal)
OrderService | checkoutCart | response | payments[].nextAction.url | string (uri) |  | (nullable)
OrderService | checkoutCart | response | payments[].nextAction.expiresAt | string (date-time) |  | (nullable)
OrderService | checkoutCart | response | payments[].lastInquiryAt | string (date-time) |  | (nullable)
OrderService | checkoutCart | response | payments[].recordedAt | string (date-time) | yes
OrderService | checkoutCart | response | payments[].syncedAt | string (date-time) |  | (nullable)
OrderService | checkoutCart | response | principalId | string (uuid)
OrderService | checkoutCart | response | workstationId | string (uuid)
OrderService | checkoutCart | response | shiftId | string (uuid) |  | (nullable)
OrderService | checkoutCart | response | subjectId | string (uuid) |  | (nullable)
OrderService | checkoutCart | response | holdLabel | string |  | The label a cashier gave when parking it with holdOrder — how they find it again. (max length 60; read-only; nullable)
OrderService | checkoutCart | response | heldUntil | string (date-time) |  | When a held order expires and is voided (states/order.yaml), from holdOrder's holdUntil. (read-only; nullable)
OrderService | checkoutCart | response | createdAt | string (date-time) | yes
OrderService | checkoutCart | response | recordedAt | string (date-time) | yes
OrderService | checkoutCart | response | syncedAt | string (date-time) |  | (nullable)
OrderService | checkoutCart | param (path) | cartId | string (uuid) | yes
OrderService | checkoutCart | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | claimCart | response | cart | Cart | yes
OrderService | claimCart | response | cart.id | string (uuid) | yes
OrderService | claimCart | response | cart.token | string |  | How an anonymous guest returns to their cart, including from a recovery email. (read-only)
OrderService | claimCart | response | cart.venueId | string (uuid) | yes
OrderService | claimCart | response | cart.channel | SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) | yes | Where a sale came from.
OrderService | claimCart | response | cart.subjectId | string (uuid) |  | Null while anonymous. (nullable)
OrderService | claimCart | response | cart.status | CartStatus: enum (active, expiring, expired, abandoned, checkedOut) | yes
OrderService | claimCart | response | cart.lines | array of CartLine | yes
OrderService | claimCart | response | cart.lines[].id | string (uuid) | yes
OrderService | claimCart | response | cart.lines[].variantId | string (uuid) | yes
OrderService | claimCart | response | cart.lines[].productName | string |  | (read-only)
OrderService | claimCart | response | cart.lines[].quantity | integer | yes | (min 1)
OrderService | claimCart | response | cart.lines[].performanceId | string (uuid) |  | (nullable)
OrderService | claimCart | response | cart.lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | claimCart | response | cart.lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | claimCart | response | cart.lines[].tableReservationId | string (uuid) |  | Set on a table deposit line only (decided 29 September, rev 3 REV3-8b): the fnb.TableReservation this line secures. (nullable)
OrderService | claimCart | response | cart.lines[].seatIds | array of string (uuid) |  | (max items 50)
OrderService | claimCart | response | cart.lines[].resourceHoldId | string (uuid) |  | The resources.ResourceHold this line buys (decided 29 September, rev 3 REV3-15). (nullable)
OrderService | claimCart | response | cart.lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | claimCart | response | cart.lines[].parentLineId | string (uuid) |  | The line this add-on is attached to, from AddCartLineRequest.parentLineId. (nullable)
OrderService | claimCart | response | cart.lines[].overridePrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | claimCart | response | cart.lines[].overrideReason | enum (priceMatch, serviceRecovery, negotiated, damagedGoods, staffSale, error) |  | BL-085. (nullable)
OrderService | claimCart | response | cart.lines[].feeKind | enum (booking, transaction, service, delivery, convenience, cancellation) |  | A fee is a line, not an adjustment. (nullable)
OrderService | claimCart | response | cart.lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | claimCart | response | cart.lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | claimCart | response | cart.lines[].inventoryHoldId | string |  | The capacity held for this line — a catalogue.InventoryHold.id, typed as that id is. (nullable)
OrderService | claimCart | response | cart.lines[].leaseExpiresAt | string (date-time) |  | Shown to the guest. (nullable)
OrderService | claimCart | response | cart.lines[].isAvailable | boolean |  | Re-checked on every read. (read-only)
OrderService | claimCart | response | cart.conflicts | array of CartConflict
OrderService | claimCart | response | cart.conflicts[].kind | enum (overlappingTime, sameSessionDifferentVenue, exceedsPartySize, requiresPrerequisite, consentBlocksBooking)
OrderService | claimCart | response | cart.conflicts[].lineIds | array of string (uuid)
OrderService | claimCart | response | cart.conflicts[].message | string
OrderService | claimCart | response | cart.conflicts[].isBlocking | boolean |  | Most are not.
OrderService | claimCart | response | cart.consentQuestions | array of object |  | The consent questions this cart's products and flow ask (decided 29 September, rev 3 REV3-26), computed on read at their current version as the union of each line's published booking flow's white-lab… (read-only)
OrderService | claimCart | response | cart.consentQuestions[].id | string (uuid) | yes | (read-only)
OrderService | claimCart | response | cart.consentQuestions[].kind | ConsentQuestionKind: enum (swim, scuba, risk, custom) | yes | What the question is about (decided 29 September, rev 3 REV3-26).
OrderService | claimCart | response | cart.consentQuestions[].text | object | yes | The question as the guest reads it, per locale.
OrderService | claimCart | response | cart.consentQuestions[].helpText | object |  | (nullable)
OrderService | claimCart | response | cart.consentQuestions[].version | integer | yes | Raised by one each time the question changes (updateConsentQuestion). (min 1; read-only)
OrderService | claimCart | response | cart.consentQuestions[].scope | enum (perPerson, perBooking) | yes | Asked for each declared person, or once for the whole booking. (default perPerson)
OrderService | claimCart | response | cart.consentQuestions[].required | boolean | yes | Checkout waits until it is answered (orders.checkoutCart 422 consentRequired). (default True)
OrderService | claimCart | response | cart.consentQuestions[].blockingAnswer | enum (yes, no, none) | yes | The answer that stops the booking, for the person or the booking it covers. (default none)
OrderService | claimCart | response | cart.consentQuestions[].status | enum (active, retired) | yes | (default active)
OrderService | claimCart | response | cart.consentQuestions[].scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | claimCart | response | cart.consentQuestions[].updatedAt | string (date-time) |  | (read-only)
OrderService | claimCart | response | cart.consentQuestions[].lineIds | array of string (uuid) |  | The cart lines that ask it.
OrderService | claimCart | response | cart.consentQuestions[].answered | boolean |  | Every person (for perPerson) or the booking (for perBooking) has an answer.
OrderService | claimCart | response | cart.subtotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | claimCart | response | cart.subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | claimCart | response | cart.subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | claimCart | response | cart.subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | claimCart | response | cart.discountTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | claimCart | response | cart.discountTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | claimCart | response | cart.discountTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | claimCart | response | cart.discountTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | claimCart | response | cart.taxTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | claimCart | response | cart.taxTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | claimCart | response | cart.taxTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | claimCart | response | cart.taxTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | claimCart | response | cart.total | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | claimCart | response | cart.total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | claimCart | response | cart.total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | claimCart | response | cart.total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | claimCart | response | cart.appliedPromotionIds | array of string (uuid) |  | Re-evaluated on every read.
OrderService | claimCart | response | cart.couponCodes | array of string |  | The promo codes the guest entered through applyCartPromoCode (decided 28 September, audit R073 (e)). (read-only)
OrderService | claimCart | response | cart.expiresAt | string (date-time) |  | The earliest lease expiry in the cart, or the cart's own window where it holds none.
OrderService | claimCart | response | cart.extensionsUsed | integer |  | (read-only)
OrderService | claimCart | response | cart.maxExtensions | integer |  | (read-only)
OrderService | claimCart | response | cart.locale | string
OrderService | claimCart | response | cart.createdAt | string (date-time)
OrderService | claimCart | response | cart.updatedAt | string (date-time)
OrderService | claimCart | response | mergedLineCount | integer
OrderService | claimCart | response | droppedLines | array of object |  | Reported, never silent.
OrderService | claimCart | response | droppedLines[].productName | string
OrderService | claimCart | response | droppedLines[].reason | enum (noCapacity, expired, notSellableOnChannel, duplicate)
OrderService | claimCart | param (path) | cartId | string (uuid) | yes
OrderService | claimCart | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | claimCustomDomain | request | hostname | string | yes
WhiteLabelService | claimCustomDomain | request | kind | enum (guestWeb, guestApp, partnerPortal, developerPortal) | yes
WhiteLabelService | claimCustomDomain | request | verificationMethod | enum (dnsTxt, cname, httpFile) |  | (default dnsTxt)
WhiteLabelService | claimCustomDomain | response | id | string (uuid) | yes
WhiteLabelService | claimCustomDomain | response | tenantId | string (uuid) | yes
WhiteLabelService | claimCustomDomain | response | hostname | string | yes
WhiteLabelService | claimCustomDomain | response | kind | enum (guestWeb, guestApp, partnerPortal, developerPortal)
WhiteLabelService | claimCustomDomain | response | status | enum (pending, verifying, verified, issuing, active, failed, expired, revoked) | yes
WhiteLabelService | claimCustomDomain | response | verificationMethod | enum (dnsTxt, cname, httpFile)
WhiteLabelService | claimCustomDomain | response | verificationToken | string |  | (read-only)
WhiteLabelService | claimCustomDomain | response | verificationRecord | object |  | The record the tenant must publish, which claimCustomDomain promises and the claim had nowhere to hold. (read-only)
WhiteLabelService | claimCustomDomain | response | verificationRecord.type | enum (TXT, CNAME, httpFile) | yes
WhiteLabelService | claimCustomDomain | response | verificationRecord.name | string | yes | The DNS name to create, or for httpFile the URL path on hostname.
WhiteLabelService | claimCustomDomain | response | verificationRecord.value | string | yes | The record's value, CNAME target or file content.
WhiteLabelService | claimCustomDomain | response | certificateExpiresAt | string (date-time) |  | Renewal is a job, not a reminder. (nullable)
WhiteLabelService | claimCustomDomain | response | lastCheckedAt | string (date-time) |  | (nullable)
WhiteLabelService | claimCustomDomain | response | failureReason | string |  | (nullable)
WhiteLabelService | claimCustomDomain | response | routing | enum (cname, delegatedSubdomain, apex) |  | How the hostname reaches TICVAI (Chinmay, 2 October: "subdomain plus CNAME"; CHG-CSA-043). (default cname)
WhiteLabelService | claimCustomDomain | response | dnsRecords | array of object |  | Every record the tenant must publish, with what is observed now (CHG-CSA-043): the TXT _dnsauth record, the CNAME, and CAA or NS where they apply. (read-only)
WhiteLabelService | claimCustomDomain | response | dnsRecords[].type | enum (TXT, CNAME, CAA, NS) | yes
WhiteLabelService | claimCustomDomain | response | dnsRecords[].name | string | yes
WhiteLabelService | claimCustomDomain | response | dnsRecords[].expectedValue | string | yes
WhiteLabelService | claimCustomDomain | response | dnsRecords[].observedValue | string |  | (nullable)
WhiteLabelService | claimCustomDomain | response | dnsRecords[].status | enum (ok, missing, wrong) | yes
WhiteLabelService | claimCustomDomain | response | revalidation | enum (none, pendingRevalidation, timedOut) |  | The two waits CMS-017 shows beside status (CHG-CSA-043). (default none; read-only)
WhiteLabelService | claimCustomDomain | response | isCnameLost | boolean |  | Takeover warning (CHG-CSA-043). (read-only)
WhiteLabelService | claimCustomDomain | response | isPrimary | boolean |  | The tenant's primary domain for its kind; the others redirect to it (setPrimaryDomain). (read-only)
WhiteLabelService | claimCustomDomain | response | readiness | object |  | Per-domain setup a guest needs (CHG-CSA-043): the UAE Pass redirect URI registered for this hostname, the Apple Pay merchant domain verified, and the app links (Apple app-site association, Android as… (read-only)
WhiteLabelService | claimCustomDomain | response | readiness.uaePassRedirect | enum (ready, pending, notApplicable)
WhiteLabelService | claimCustomDomain | response | readiness.applePayDomain | enum (ready, pending, notApplicable)
WhiteLabelService | claimCustomDomain | response | readiness.appLinks | enum (ready, pending, notApplicable)
WhiteLabelService | claimCustomDomain | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | claimDeviceConsent | request | consentKey | string | yes | (max length 64)
MarketingService | claimDeviceConsent | response | subjectId | string (uuid) | yes
MarketingService | claimDeviceConsent | response | purposes | array of object | yes
MarketingService | claimDeviceConsent | response | purposes[].purpose | ConsentPurpose: enum (marketing, personalisation, profiling, thirdPartySharing, aiProcessing, transactional) | yes
MarketingService | claimDeviceConsent | response | purposes[].decision | ConsentDecision: enum (granted, withdrawn, notAsked) | yes
MarketingService | claimDeviceConsent | response | purposes[].channels | array of MessageChannel: enum (email, sms, whatsapp, push, inApp, post)
MarketingService | claimDeviceConsent | response | purposes[].noticeVersion | string |  | (nullable)
MarketingService | claimDeviceConsent | response | purposes[].requiresRenewal | boolean | yes | True where the notice has been superseded since consent was given.
MarketingService | claimDeviceConsent | response | purposes[].decidedAt | string (date-time) |  | (nullable)
MarketingService | claimDeviceConsent | param (path) | subjectId | string (uuid) | yes
MarketingService | claimDeviceConsent | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | claimLocationSession | request | locationCode | string |  | From the QR or NFC tag.
FnbService | claimLocationSession | request | seatReference | object |  | For seated venues where the seat is the address and there is no code to scan.
FnbService | claimLocationSession | request | seatReference.performanceId | string (uuid)
FnbService | claimLocationSession | request | seatReference.seatId | string
FnbService | claimLocationSession | request | partySize | integer |  | (min 1)
FnbService | claimLocationSession | response | id | string (uuid) | yes
FnbService | claimLocationSession | response | locationId | string (uuid) | yes
FnbService | claimLocationSession | response | kind | DeliveryLocationKind: enum (table, seat, cabana, sunbed, poolside, box, suite, lawn, …) | yes | 4.6.26.
FnbService | claimLocationSession | response | label | string | yes
FnbService | claimLocationSession | response | outletId | string (uuid) |  | The outlet serving this location. (nullable)
FnbService | claimLocationSession | response | visitId | string (uuid) |  | The table visit this session orders onto, where the location is a table. (nullable)
FnbService | claimLocationSession | response | joinedExistingVisit | boolean
FnbService | claimLocationSession | response | subjectId | string (uuid)
FnbService | claimLocationSession | response | expiresAt | string (date-time) | yes | Sessions expire so a guest who leaves cannot order to a lounger now occupied by someone else.
FnbService | claimLocationSession | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | claimTicketTransfer | request | claimToken | string | yes | The token carried in the claim link, checked against TicketTransfer.claimToken.
OrderService | claimTicketTransfer | response | id | string (uuid) | yes
OrderService | claimTicketTransfer | response | orderId | string (uuid) | yes
OrderService | claimTicketTransfer | response | ticketIds | array of string (uuid) | yes | The entitlements offered — Entitlement.id values, since a ticket is an entitlement.
OrderService | claimTicketTransfer | response | fromSubjectId | string (uuid)
OrderService | claimTicketTransfer | response | toSubjectId | string (uuid) |  | Set only on claim. (nullable)
OrderService | claimTicketTransfer | response | recipientAddressMasked | string
OrderService | claimTicketTransfer | response | status | enum (offered, claimed, expired, cancelled) | yes
OrderService | claimTicketTransfer | response | claimUrl | string |  | (nullable)
OrderService | claimTicketTransfer | response | claimToken | string (password) |  | What claimTicketTransfer checks the presented claimToken against.
OrderService | claimTicketTransfer | response | offeredAt | string (date-time) | yes
OrderService | claimTicketTransfer | response | claimedAt | string (date-time) |  | (nullable)
OrderService | claimTicketTransfer | response | expiresAt | string (date-time) | yes | An unclaimed transfer expires and the tickets return.
OrderService | claimTicketTransfer | param (path) | transferId | string (uuid) | yes
OrderService | claimTicketTransfer | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | clearTable | request | recordedAt | string (date-time) | yes | Device time of the act (offline-capable; replayed in this order).
FnbService | clearTable | response | id | string (uuid) | yes
FnbService | clearTable | response | label | string | yes | The table code, unique per venue (decided 28 September, audit R108). (max length 32)
FnbService | clearTable | response | capacity | integer | yes | (min 1)
FnbService | clearTable | response | zone | string |  | (nullable)
FnbService | clearTable | response | position | object
FnbService | clearTable | response | position.x | number
FnbService | clearTable | response | position.y | number
FnbService | clearTable | response | shape | enum (round, square, rectangle, booth, bar)
FnbService | clearTable | response | isOutOfService | boolean |  | Damaged, or its section closed. (default False)
FnbService | clearTable | response | codeGeneration | integer |  | Which printing of the location's ordering code is current (4 October 2026, CHG-FXC-009). (min 1; default 1)
FnbService | clearTable | response | status | TableStatus: enum (free, seated, ordered, billRequested, needsClearing, reserved, outOfService) | yes
FnbService | clearTable | response | visitId | string (uuid) |  | (nullable)
FnbService | clearTable | response | covers | integer |  | (nullable)
FnbService | clearTable | response | seatedAt | string (date-time) |  | (nullable)
FnbService | clearTable | response | serverPrincipalId | string (uuid) |  | (nullable)
FnbService | clearTable | response | billTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | clearTable | response | billTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | clearTable | response | billTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | clearTable | response | billTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | clearTable | param (path) | tableId | string (uuid) | yes
FnbService | clearTable | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | cloneEvent | request | include | array of enum (schedule, pricing, seatMap, capacityProfile, resourceRequirements, staffPlan, registrationForm, accessRules)
CatalogueService | cloneEvent | request | shiftDatesByDays | integer |  | (nullable)
CatalogueService | cloneEvent | request | newName | string |  | (nullable)
CatalogueService | cloneEvent | request | newCode | string |  | The copy's event code (6 October 2026, CHG-R4-016). (max length 64; nullable)
CatalogueService | cloneEvent | response | eventId | string (uuid)
CatalogueService | cloneEvent | response | code | string |  | The copy's event code, as sent in newCode or as the server chose it (CHG-R4-016).
CatalogueService | cloneEvent | param (path) | eventId | string (uuid) | yes
CatalogueService | cloneEvent | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | cloneProduct | request | code | string | yes
CatalogueService | cloneProduct | request | name | string | yes
CatalogueService | cloneProduct | request | includeVariants | boolean |  | (default True)
CatalogueService | cloneProduct | request | includePrices | boolean |  | (default False)
CatalogueService | cloneProduct | response | id | string (uuid) | yes
CatalogueService | cloneProduct | response | code | string | yes | (max length 64)
CatalogueService | cloneProduct | response | familyKey | string |  | The same product at another location (decided 29 September, rev 3 REV3-18). (max length 64; pattern ^[A-Za-z0-9_-]+$; nullable)
CatalogueService | cloneProduct | response | name | string | yes | (max length 200)
CatalogueService | cloneProduct | response | description | string
CatalogueService | cloneProduct | response | nameLocalised | object |  | The product's name in each language the venue sells in (6 October 2026, CHG-R4-011), keyed by ISO 639-1 code, e.g. (nullable)
CatalogueService | cloneProduct | response | descriptionLocalised | object |  | The product's description in each language, as nameLocalised; falls back to description (6 October 2026, CHG-R4-011). (nullable)
CatalogueService | cloneProduct | response | kind | ProductKind: enum (admission, timedAdmission, datedAdmission, openDated, seated, membership, bundle, fnb, …) | yes | openDated added 24 August from the client's *Create Ticket Flow* board, which names six main ticket types and this was the one with no kind: valid on any date within an eligible range, rather than fo…
CatalogueService | cloneProduct | response | venueId | string (uuid) | yes
CatalogueService | cloneProduct | response | scopePath | string | yes
CatalogueService | cloneProduct | response | createdByPrincipalId | string (uuid) |  | 1.4.18. (read-only)
CatalogueService | cloneProduct | response | approvedByPrincipalId | string (uuid) |  | (read-only; nullable)
CatalogueService | cloneProduct | response | responsibleDepartmentId | string (uuid) |  | Who owns this product commercially. (nullable)
CatalogueService | cloneProduct | response | onSaleFrom | string (date-time) |  | 1.4.8. (nullable)
CatalogueService | cloneProduct | response | onSaleTo | string (date-time) |  | Retires the product automatically. (nullable)
CatalogueService | cloneProduct | response | categoryId | string (uuid) |  | Taken from their fnb.product and retail.product, 20 September. (nullable)
CatalogueService | cloneProduct | response | lifecycleState | ProductLifecycleState: enum (draft, inReview, approved, live, withdrawn, archived)
CatalogueService | cloneProduct | response | isSellable | boolean | yes | True only when live and carried by a published bundle. (read-only)
CatalogueService | cloneProduct | response | isStockTracked | boolean |  | Taken from their fnb.product, 20 September. (default False)
CatalogueService | cloneProduct | response | hasVariants | boolean | yes
CatalogueService | cloneProduct | response | variantCount | integer
CatalogueService | cloneProduct | response | segmentTags | array of string |  | 7.3.5.
CatalogueService | cloneProduct | response | codeSchema | string |  | 7.3.4 specifies [ParkCode]-[ProductType]-[Variant]. (read-only)
CatalogueService | cloneProduct | response | channels | array of Channel: enum (pos, kiosk, web, mobile, b2b, ota, callCentre)
CatalogueService | cloneProduct | response | entitlementTemplateId | string (uuid) |  | What the buyer receives. (nullable)
CatalogueService | cloneProduct | response | blockedOffline | boolean |  | True for seated and retail.
CatalogueService | cloneProduct | response | dataMaskValues | object |  | Custom fields.
CatalogueService | cloneProduct | response | guestListing | GuestListing: enum (bookable, infoOnly, hidden) |  | How a product appears to a guest (decided 29 September, rev 3 REV3-14). (default bookable)
CatalogueService | cloneProduct | response | notBookableLabel | object |  | The label a guest reads on an infoOnly product, e.g. (nullable)
CatalogueService | cloneProduct | response | salesContact | object |  | Who a guest contacts to book a view-only product (decided 29 September, W3), e.g. (nullable)
CatalogueService | cloneProduct | response | salesContact.phone | string |  | (max length 32; nullable)
CatalogueService | cloneProduct | response | salesContact.email | string (email) |  | (max length 254; nullable)
CatalogueService | cloneProduct | response | salesContact.note | object |  | A line shown under the contact, e.g. (nullable)
CatalogueService | cloneProduct | response | bookingFlowId | string (uuid) |  | The booking flow this product is sold through (decided 29 September, W8 and W12): a white-label BookingFlow of the venue, which orders the guest's steps (for a workshop, the product first and then th… (nullable)
CatalogueService | cloneProduct | response | displayTags | array of ProductDisplayTag |  | Short facts a guest reads on the ticket card and under *Read more*: *2 Hours*, *Min 1.10 m*, *Free adult entry*, *Valid 90 days*, *Emirates ID* (decided 29 September, 23SEP-3). (max items 6)
CatalogueService | cloneProduct | response | displayTags[].kind | enum (clock, height, free, calendar, id) | yes | clock a duration, height a height rule, free something included free, calendar a validity, id a document the guest must bring.
CatalogueService | cloneProduct | response | displayTags[].label | object | yes | What the guest reads, e.g.
CatalogueService | cloneProduct | response | displayTags[].derived | boolean |  | True on a tag the server derived on read because the venue set none. (default False; read-only)
CatalogueService | cloneProduct | response | media | array of ProductMedia |  | The product's own photos and video (decided 29 September, 23SEP-4). (max items 20)
CatalogueService | cloneProduct | response | media[].assetId | string (uuid) | yes | A MediaAsset of assets.yaml, in status ready.
CatalogueService | cloneProduct | response | media[].kind | enum (image, video) | yes
CatalogueService | cloneProduct | response | media[].isPrimary | boolean | yes | The item *Read more* opens on and a listing shows. (default False)
CatalogueService | cloneProduct | response | media[].displayOrder | integer |  | (default 100)
CatalogueService | cloneProduct | response | media[].altText | object |  | (nullable)
CatalogueService | cloneProduct | response | consentQuestionIds | array of string (uuid) |  | The consent questions a guest answers when booking this product, in the order they are asked (decided 29 September, rev 3 REV3-26): *Are you able to swim?*, *Do you hold a scuba certification?*, *I a… (max items 10)
CatalogueService | cloneProduct | response | requiresTimeWindow | boolean |  | True for a space sold by the hour, e.g. (default False)
CatalogueService | cloneProduct | response | productOwnerPrincipalId | string (uuid) |  | The product owner (29 September, data model DM3), set with setProductContextOwnership. (nullable)
CatalogueService | cloneProduct | response | operationalContact | string |  | A principal id or a name, as the context screen takes it. (max length 200; nullable)
CatalogueService | cloneProduct | response | businessUnitId | string (uuid) |  | (nullable)
CatalogueService | cloneProduct | response | legalEntityId | string (uuid) |  | A ledger.legal_entity, read through finance. (nullable)
CatalogueService | cloneProduct | response | attractionId | string (uuid) |  | (nullable)
CatalogueService | cloneProduct | response | siteId | string (uuid) |  | (nullable)
CatalogueService | cloneProduct | response | locationId | string (uuid) |  | (nullable)
CatalogueService | cloneProduct | response | brandId | string (uuid) |  | The brand, as the context screen names it (a catalogue brand category). (nullable)
CatalogueService | cloneProduct | response | marketCode | string |  | (max length 40; nullable)
CatalogueService | cloneProduct | response | salesTerritory | string |  | (max length 100; nullable)
CatalogueService | cloneProduct | response | eventId | string (uuid) |  | The event this product sells admission to (4 October 2026, CHG-FXC-011; WEB-002, WEB-004): a product page finds its event and the event's performances (Performance.eventId) give it dates. (nullable)
CatalogueService | cloneProduct | param (path) | productId | string (uuid) | yes
CatalogueService | cloneProduct | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | cloneResource | request | count | integer |  | Forty strollers in one act. (default 1)
VenueOpsService | cloneResource | request | codePattern | string |  | (nullable)
VenueOpsService | cloneResource | param (path) | resourceId | string (uuid) | yes
VenueOpsService | cloneResource | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | cloneTicketTemplate | request | name | string | yes | (max length 120)
OrderService | cloneTicketTemplate | request | source | enum (existingTemplate, venueTemplate, productTemplate) | yes | What the template in the path is (decided 29 September, readiness close-out).
OrderService | cloneTicketTemplate | request | venueId | string (uuid) |  | The venue whose template is copied. (nullable)
OrderService | cloneTicketTemplate | request | productId | string (uuid) |  | The product the template issues for. (nullable)
OrderService | cloneTicketTemplate | response | id | string (uuid) | yes
OrderService | cloneTicketTemplate | response | name | string | yes
OrderService | cloneTicketTemplate | response | isRecyclable | boolean |  | BL-103. (default False)
OrderService | cloneTicketTemplate | response | recycleAfterDays | integer |  | A quarantine before reissue. (nullable)
OrderService | cloneTicketTemplate | response | mediaType | enum (thermalTicket, a4Pdf, wristband, rfidCard, walletPass, qrOnly, sms) | yes
OrderService | cloneTicketTemplate | response | appliesToProductKinds | array of string
OrderService | cloneTicketTemplate | response | appliesToChannels | array of SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …)
OrderService | cloneTicketTemplate | response | selectionPriority | integer |  | 2.16.x. (default 100)
OrderService | cloneTicketTemplate | response | layoutRef | string
OrderService | cloneTicketTemplate | response | localeVariants | object
OrderService | cloneTicketTemplate | response | isActive | boolean | yes
OrderService | cloneTicketTemplate | param (path) | templateId | string (uuid) | yes
OrderService | cloneTicketTemplate | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | closeShift | request | countedCash | array of CountedDenominationLine | yes | The cashier's blind count, one line per denomination counted (decided 29 September, readiness close-out; our build plan). (min items 1)
OrderService | closeShift | request | countedCash[].denominationId | string (uuid) | yes | References platform.denomination (Denomination.id) — face value, kind and counting order live there.
OrderService | closeShift | request | countedCash[].count | integer | yes | How many of this note or coin were counted. (min 0; max 100000)
OrderService | closeShift | request | countedCash[].total | object |  | count times the face value, in the denomination's currency.
OrderService | closeShift | request | countedCash[].total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | request | countedCash[].total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | request | countedCash[].total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | request | nonCashDeclared | array of object |  | Declared totals per non-cash tender, for reconciliation against captured payments.
OrderService | closeShift | request | nonCashDeclared[].tender | string | yes
OrderService | closeShift | request | nonCashDeclared[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | closeShift | request | nonCashDeclared[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | request | nonCashDeclared[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | request | nonCashDeclared[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | request | notes | string |  | The cashier's note on the count. (max length 1000)
OrderService | closeShift | request | cashierReason | enum (tillError, unrecordedRefund, miscount, other) |  | Anything the cashier knows went wrong in the shift (DI-803: till error, unrecorded refund, miscount, other). (nullable)
OrderService | closeShift | request | releaseHeldLeases | boolean |  | Return unsold inventory leases held by this workstation (ADR-0013 C103). (default True)
OrderService | closeShift | request | recordedAt | string (date-time) | yes
OrderService | closeShift | request | supervisorStepUp | object |  | The supervisor closing the shift, signing on this device (CHG-RUL-019).
OrderService | closeShift | request | supervisorStepUp.principalId | string (uuid) | yes | The supervisor signing.
OrderService | closeShift | request | supervisorStepUp.credential | string | yes | The supervisor's staff PIN, as they sign in at a till with it. (max length 512)
OrderService | closeShift | response | shift | Shift | yes | approvals and incidents are child rows (26 September, pull audit R099): orders.pos_shift_approval and orders.pos_shift_incident, one row per item, keyed to the shift.
OrderService | closeShift | response | shift.id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | closeShift | response | shift.workstationId | string (uuid) | yes
OrderService | closeShift | response | shift.venueId | string (uuid) | yes
OrderService | closeShift | response | shift.scopePath | string | yes
OrderService | closeShift | response | shift.principalId | string (uuid) | yes | Who opened it.
OrderService | closeShift | response | shift.principalDisplayName | string
OrderService | closeShift | response | shift.incidents | array of object |  | BL-097.
OrderService | closeShift | response | shift.incidents[].kind | enum (noSale, drawerOpen, override, voidAfterPayment, guestDispute, tillJam, priceQuery, other)
OrderService | closeShift | response | shift.incidents[].at | string (date-time)
OrderService | closeShift | response | shift.incidents[].principalId | string (uuid)
OrderService | closeShift | response | shift.incidents[].note | string |  | (nullable)
OrderService | closeShift | response | shift.status | ShiftStatus: enum (pendingApproval, open, suspended, pendingVariance, pendingClosure, closed, autoClosed) | yes
OrderService | closeShift | response | shift.currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | shift.currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | closeShift | response | shift.depositBoxCode | string |  | (nullable)
OrderService | closeShift | response | shift.bagNumber | string |  | (nullable)
OrderService | closeShift | response | shift.openingFloat | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | closeShift | response | shift.openingFloat.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | response | shift.openingFloat.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | shift.openingFloat.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | response | shift.salesTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | closeShift | response | shift.salesTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | response | shift.salesTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | shift.salesTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | response | shift.refundsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | closeShift | response | shift.refundsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | response | shift.refundsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | shift.refundsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | response | shift.liftsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | closeShift | response | shift.liftsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | response | shift.liftsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | shift.liftsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | response | shift.expectedCash | object |  | 26 September, pull audit R207. (read-only; nullable)
OrderService | closeShift | response | shift.expectedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | response | shift.expectedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | shift.expectedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | response | shift.countedCash | object |  | What the close count found. (read-only; nullable)
OrderService | closeShift | response | shift.countedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | response | shift.countedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | shift.countedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | response | shift.variance | object |  | Counted minus expected, as ShiftCloseResult.variance. (read-only; nullable)
OrderService | closeShift | response | shift.variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | response | shift.variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | shift.variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | response | shift.cashierReason | enum (tillError, unrecordedRefund, miscount, other) |  | What the cashier said went wrong, given with the blind count (CloseShiftRequest.cashierReason, DI-803) without seeing the variance; the supervisor reads it beside the variance on BO-040 (CHG-FIN-003). (read-only; nullable)
OrderService | closeShift | response | shift.cashierNote | string |  | The cashier's note with the count (CloseShiftRequest.notes; CHG-FIN-003). (max length 1000; read-only; nullable)
OrderService | closeShift | response | shift.varianceReasonRequired | boolean |  | Computed, not stored (CHG-R4-019): true while the shift is pendingClosure because its count differs from the expected figure within the threshold and no cashierReason is recorded. (read-only)
OrderService | closeShift | response | shift.heldLeaseCount | integer |  | Inventory leases currently held by this workstation.
OrderService | closeShift | response | shift.openedAt | string (date-time) | yes
OrderService | closeShift | response | shift.businessDate | string (date) |  | The business day the shift belongs to (12 October 2026, CHG-R6-032): the venue-local date of openedAt taken against the venue's businessDayCutoff (tenancy VenueSettings, inheriting the tenant default… (read-only)
OrderService | closeShift | response | shift.recordedAt | string (date-time) |  | When the device recorded the open.
OrderService | closeShift | response | shift.suspendedAt | string (date-time) |  | (nullable)
OrderService | closeShift | response | shift.suspendReason | string |  | The reason given to suspendShift. (max length 200; nullable)
OrderService | closeShift | response | shift.closedAt | string (date-time) |  | (nullable)
OrderService | closeShift | response | shift.closedByPrincipalId | string (uuid) |  | Who submitted the close count. (nullable)
OrderService | closeShift | response | shift.recountRequestedAt | string (date-time) |  | Set by rejectShiftVariance, cleared by the cashier's recount (decided 2 October 2026, Chinmay; DEC-175; CHG-CSP-013; DI-804). (read-only; nullable)
OrderService | closeShift | response | shift.recountRequestedByPrincipalId | string (uuid) |  | The supervisor who sent the count back (CHG-CSP-013). (read-only; nullable)
OrderService | closeShift | response | shift.recountReason | string |  | The supervisor's reason, shown to the cashier; never an amount (CHG-CSP-013, CHG-FIN-003). (max length 500; read-only; nullable)
OrderService | closeShift | response | shift.countNumber | integer |  | How many close counts the shift has had: 0 before the first, 1 after it, 2 after a recount (CHG-CSP-013). (min 0; read-only)
OrderService | closeShift | response | shift.syncedAt | string (date-time) |  | Null while the shift has unsynced operations. (nullable)
OrderService | closeShift | response | shift.approvals | array of object
OrderService | closeShift | response | shift.approvals[].kind | enum (open, close, variance) | yes | open from approveShiftOpen, close from approveShiftClose, variance from acceptShiftVariance.
OrderService | closeShift | response | shift.approvals[].principalId | string (uuid) | yes
OrderService | closeShift | response | shift.approvals[].at | string (date-time) | yes
OrderService | closeShift | response | shift.approvals[].reason | string
OrderService | closeShift | response | expectedCash | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | closeShift | response | expectedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | response | expectedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | expectedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | response | countedCash | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | closeShift | response | countedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | response | countedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | countedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | response | variance | object | yes | Counted minus expected.
OrderService | closeShift | response | variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | response | variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | response | requiresAcceptance | boolean | yes | True when the variance exceeds the venue's shiftVarianceThreshold (audit R094).
OrderService | closeShift | response | varianceReasonRequired | boolean |  | True when the variance is non-zero and within the threshold and the body gave no cashierReason: the shift is held in pendingClosure until giveShiftVarianceReason or approveShiftClose records a reason… (default False)
OrderService | closeShift | response | nonCashVariances | array of object
OrderService | closeShift | response | nonCashVariances[].tender | string | yes
OrderService | closeShift | response | nonCashVariances[].declared | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | closeShift | response | nonCashVariances[].declared.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | response | nonCashVariances[].declared.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | nonCashVariances[].declared.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | response | nonCashVariances[].captured | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | closeShift | response | nonCashVariances[].captured.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | response | nonCashVariances[].captured.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | nonCashVariances[].captured.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | response | nonCashVariances[].variance | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | closeShift | response | nonCashVariances[].variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | closeShift | response | nonCashVariances[].variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | closeShift | response | nonCashVariances[].variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | closeShift | param (path) | shiftId | string (uuid) | yes
OrderService | closeShift | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | closeTableVisit | request | payments | array of object | yes | Empty only at a payFirst outlet with nothing left to pay (CHG-RUL-001). (min items 0)
FnbService | closeTableVisit | request | payments[].subBillId | string |  | The sub-bill this payment settles. (nullable)
FnbService | closeTableVisit | request | payments[].tender | string | yes
FnbService | closeTableVisit | request | payments[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | closeTableVisit | request | payments[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | closeTableVisit | request | payments[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | closeTableVisit | request | payments[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | closeTableVisit | request | gratuity | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | closeTableVisit | request | gratuity.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | closeTableVisit | request | gratuity.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | closeTableVisit | request | gratuity.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | closeTableVisit | response | visit | TableVisit | yes
FnbService | closeTableVisit | response | visit.id | string (uuid) | yes
FnbService | closeTableVisit | response | visit.tableId | string (uuid) | yes
FnbService | closeTableVisit | response | visit.tableLabel | string
FnbService | closeTableVisit | response | visit.outletId | string (uuid) | yes
FnbService | closeTableVisit | response | visit.covers | integer | yes
FnbService | closeTableVisit | response | visit.status | enum (open, billRequested, settled, merged, cancelled) | yes
FnbService | closeTableVisit | response | visit.serverPrincipalId | string (uuid) |  | (nullable)
FnbService | closeTableVisit | response | visit.subjectId | string (uuid) |  | (nullable)
FnbService | closeTableVisit | response | visit.orders | array of FnbOrder | yes
FnbService | closeTableVisit | response | visit.orders[].id | string (uuid) | yes
FnbService | closeTableVisit | response | visit.orders[].orderNumber | string | yes
FnbService | closeTableVisit | response | visit.orders[].outletId | string (uuid) | yes
FnbService | closeTableVisit | response | visit.orders[].paymentTiming | object |  | The outlet's payment timing when the order was placed (CHG-CSA-010), kept as a snapshot. (read-only)
FnbService | closeTableVisit | response | visit.orders[].sentToKitchenAt | string (date-time) |  | When the order's kitchen tickets were created. (read-only; nullable)
FnbService | closeTableVisit | response | visit.orders[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery) | yes
FnbService | closeTableVisit | response | visit.orders[].tableVisitId | string (uuid) |  | (nullable)
FnbService | closeTableVisit | response | visit.orders[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) | yes | The full lifecycle from 4.6.35.
FnbService | closeTableVisit | response | visit.orders[].lines | array of object | yes
FnbService | closeTableVisit | response | visit.orders[].salesOrderId | string (uuid) |  | Retyped 29 September (SD-046), and format: uuid since ADR-0056 (30 September): every id is a uuid, so this joins orders.sales_order.id. (nullable)
FnbService | closeTableVisit | response | visit.orders[].updatedAt | string (date-time) |  | Taken from their fnb.order. (nullable)
FnbService | closeTableVisit | response | visit.orders[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | closeTableVisit | response | visit.orders[].taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | closeTableVisit | response | visit.orders[].kitchenTicketId | string (uuid) |  | (nullable)
FnbService | closeTableVisit | response | visit.orders[].kitchenTickets | array of KitchenTicket |  | The kitchen tickets this order created, one per station (SD-046). (read-only)
FnbService | closeTableVisit | response | visit.orders[].estimatedReadyAt | string (date-time) |  | (nullable)
FnbService | closeTableVisit | response | visit.orders[].createdAt | string (date-time) | yes
FnbService | closeTableVisit | response | visit.orders[].recordedAt | string (date-time)
FnbService | closeTableVisit | response | visit.orders[].syncedAt | string (date-time) |  | (nullable)
FnbService | closeTableVisit | response | visit.mergedIntoVisitId | string (uuid) |  | (nullable)
FnbService | closeTableVisit | response | visit.mergedFromVisitIds | array of string (uuid)
FnbService | closeTableVisit | response | visit.runningTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | closeTableVisit | response | visit.runningTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | closeTableVisit | response | visit.runningTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | closeTableVisit | response | visit.runningTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | closeTableVisit | response | visit.gratuity | object |  | The gratuity taken at closeTableVisit. (read-only; nullable)
FnbService | closeTableVisit | response | visit.gratuity.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | closeTableVisit | response | visit.gratuity.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | closeTableVisit | response | visit.gratuity.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | closeTableVisit | response | visit.openedAt | string (date-time) | yes
FnbService | closeTableVisit | response | visit.closedAt | string (date-time) |  | (nullable)
FnbService | closeTableVisit | response | visit.serviceStage | string |  | Where the table is in its service (4 October 2026, CHG-FXC-003): the last stage setServiceStage recorded (its stage value), null before the first. (read-only; nullable)
FnbService | closeTableVisit | response | visit.serviceStageRecordedAt | string (date-time) |  | (read-only; nullable)
FnbService | closeTableVisit | response | orderIds | array of string | yes
FnbService | closeTableVisit | param (path) | visitId | string (uuid) | yes
FnbService | closeTableVisit | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
RetailService | collectShopAndDrop | request | lineIds | array of string
RetailService | collectShopAndDrop | request | verifiedBy | enum (entitlementScan, receipt, dropReference, staffOverride)
RetailService | collectShopAndDrop | request | note | string |  | (max length 500)
RetailService | collectShopAndDrop | request | recordedAt | string (date-time) | yes
RetailService | collectShopAndDrop | response | id | string | yes
RetailService | collectShopAndDrop | response | dropReference | string | yes | Short and readable.
RetailService | collectShopAndDrop | response | saleId | string |  | The till sale. (nullable)
RetailService | collectShopAndDrop | response | orderId | string (uuid) |  | The paid online order that created this collection (audit R236). (nullable)
RetailService | collectShopAndDrop | response | entitlementId | string |  | The ticket that claims these goods. (nullable)
RetailService | collectShopAndDrop | response | subjectId | string (uuid) |  | (nullable)
RetailService | collectShopAndDrop | response | collectionPointId | string (uuid) | yes
RetailService | collectShopAndDrop | response | collectionPointName | string
RetailService | collectShopAndDrop | response | status | enum (awaitingCollection, partiallyCollected, collected, uncollected, disposed) | yes
RetailService | collectShopAndDrop | response | lines | array of object
RetailService | collectShopAndDrop | response | lines[].lineId | string
RetailService | collectShopAndDrop | response | lines[].merchandiseId | string (uuid)
RetailService | collectShopAndDrop | response | lines[].name | string
RetailService | collectShopAndDrop | response | lines[].quantity | integer
RetailService | collectShopAndDrop | response | lines[].collectedQuantity | integer
RetailService | collectShopAndDrop | response | droppedAt | string (date-time)
RetailService | collectShopAndDrop | response | collectBy | string (date-time) | yes
RetailService | collectShopAndDrop | response | collectedAt | string (date-time) |  | (nullable)
RetailService | collectShopAndDrop | response | collectedByPrincipalId | string (uuid) |  | (nullable)
RetailService | collectShopAndDrop | response | verifiedBy | string |  | (nullable)
RetailService | collectShopAndDrop | param (path) | dropId | string (uuid) | yes
RetailService | collectShopAndDrop | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | commitCatalogueImport | response | id | string (uuid) | yes
CatalogueService | commitCatalogueImport | response | status | enum (parsing, previewReady, committing, committed, failed) | yes
CatalogueService | commitCatalogueImport | response | outcome | enum (parsed, parsedWithFindings, nothingFound, unreadable)
CatalogueService | commitCatalogueImport | response | parsedCount | integer | yes
CatalogueService | commitCatalogueImport | response | createCount | integer
CatalogueService | commitCatalogueImport | response | updateCount | integer
CatalogueService | commitCatalogueImport | response | findings | array of object |  | What an operator sees before committing — missing prices, duplicate codes, unknown categories, codes that do not match the tenant's schema.
CatalogueService | commitCatalogueImport | response | findings[].row | integer
CatalogueService | commitCatalogueImport | response | findings[].severity | enum (error, warning)
CatalogueService | commitCatalogueImport | response | findings[].message | string
CatalogueService | commitCatalogueImport | response | scopePath | string |  | The partition key (ADR-0005).
CatalogueService | commitCatalogueImport | response | jobKind | enum (productImport, environmentTransfer, pricingBulkUpdate, pricingImport) |  | One job table for every catalogue bulk operation (29 September, data model DM3): product import (the original use), environment transfer (ADM-124) and bulk pricing update or import (ADM-080). (default productImport)
CatalogueService | commitCatalogueImport | response | direction | enum (export, import, None) |  | (nullable)
CatalogueService | commitCatalogueImport | response | sourceEnvironment | enum (development, sandbox, uat, staging, production, None) |  | (nullable)
CatalogueService | commitCatalogueImport | response | targetEnvironment | enum (development, sandbox, uat, staging, production, None) |  | (nullable)
CatalogueService | commitCatalogueImport | response | productIds | array of string (uuid)
CatalogueService | commitCatalogueImport | response | components | array of string |  | Transfer components, per ProductImportExportEnvironmentTransferView.components.
CatalogueService | commitCatalogueImport | response | referenceMappings | object |  | [{kind, sourceRef, targetRef}]. (nullable)
CatalogueService | commitCatalogueImport | response | missingReferences | array of string
CatalogueService | commitCatalogueImport | response | fileId | string (uuid) |  | (nullable)
CatalogueService | commitCatalogueImport | response | sourceFormat | string |  | (max length 40; nullable)
CatalogueService | commitCatalogueImport | response | columnMappings | object |  | [{sourceColumn, targetField, suggestedByAi, confirmed}]. (nullable)
CatalogueService | commitCatalogueImport | response | parameters | object |  | Bulk pricing: {selectBy, selectionValues, operation, adjustmentPercent, adjustmentAmount, targetCurrency, effectivePeriodFrom, effectivePeriodTo}. (nullable)
CatalogueService | commitCatalogueImport | response | warningCount | integer |  | (default 0)
CatalogueService | commitCatalogueImport | response | errorCount | integer |  | (default 0)
CatalogueService | commitCatalogueImport | response | changeRequestId | string (uuid) |  | (read-only; nullable)
CatalogueService | commitCatalogueImport | response | requestedByPrincipalId | string (uuid) |  | (read-only; nullable)
CatalogueService | commitCatalogueImport | response | createdAt | string (date-time) |  | (read-only)
CatalogueService | commitCatalogueImport | response | completedAt | string (date-time) |  | (read-only; nullable)
CatalogueService | commitCatalogueImport | param (path) | jobId | string (uuid) | yes
CatalogueService | commitCatalogueImport | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | completeUpload | request | title | LocalisedText
VenueOpsService | completeUpload | request | altText | LocalisedText
VenueOpsService | completeUpload | request | tags | array of string
VenueOpsService | completeUpload | request | collectionIds | array of string (uuid)
VenueOpsService | completeUpload | request | rights | MediaRights |  | Licensing terms.
VenueOpsService | completeUpload | request | rights.licenceKind | enum (owned, royaltyFree, rightsManaged, creativeCommons, editorialOnly, unknown)
VenueOpsService | completeUpload | request | rights.licensor | string |  | (nullable)
VenueOpsService | completeUpload | request | rights.licenceReference | string |  | (nullable)
VenueOpsService | completeUpload | request | rights.validFrom | string (date) |  | (nullable)
VenueOpsService | completeUpload | request | rights.validTo | string (date) |  | (nullable)
VenueOpsService | completeUpload | request | rights.permittedUses | array of enum (web, print, socialMedia, inVenue, advertising, internal)
VenueOpsService | completeUpload | request | rights.attributionRequired | boolean |  | (default False)
VenueOpsService | completeUpload | request | rights.attributionText | string |  | (nullable)
VenueOpsService | completeUpload | request | rights.permittedTerritories | array of string |  | ISO country or region codes.
VenueOpsService | completeUpload | request | rights.permittedChannels | array of string |  | Distribution channel codes, checked by setMediaDistributionChannels.
VenueOpsService | completeUpload | request | rights.modelReleaseHeld | boolean |  | (default False)
VenueOpsService | completeUpload | request | rights.renewalOwner | string (uuid) |  | (nullable)
VenueOpsService | completeUpload | response | id | string (uuid) | yes
VenueOpsService | completeUpload | response | kind | MediaKind: enum (image, video, audio, document, vector, font, archive, model3d) | yes | model3d added 3 October 2026 (r1 additions; ADR-0069 action item 4): a glTF binary (model/gltf-binary, .glb) venue model, at most 40 MB.
VenueOpsService | completeUpload | response | status | MediaStatus: enum (processing, ready, quarantined, failed, archived) | yes
VenueOpsService | completeUpload | response | filename | string | yes
VenueOpsService | completeUpload | response | contentType | string | yes
VenueOpsService | completeUpload | response | sizeBytes | integer | yes
VenueOpsService | completeUpload | response | title | LocalisedText
VenueOpsService | completeUpload | response | description | object |  | Set by updateMediaAsset and matched by searchMedia's search.
VenueOpsService | completeUpload | response | altText | object |  | Required before use in a guest-facing surface.
VenueOpsService | completeUpload | response | width | integer |  | (nullable)
VenueOpsService | completeUpload | response | height | integer |  | (nullable)
VenueOpsService | completeUpload | response | durationSeconds | number |  | (nullable)
VenueOpsService | completeUpload | response | customMetadata | object |  | BL-178. (nullable)
VenueOpsService | completeUpload | response | sharedWithTenantIds | array of string (uuid) |  | BL-178.
VenueOpsService | completeUpload | response | tags | array of string
VenueOpsService | completeUpload | response | categoryId | string (uuid) |  | The asset's category, one of MediaTaxonomy.categories[].id; null while unclassified. (nullable)
VenueOpsService | completeUpload | response | venueId | string (uuid) |  | (nullable)
VenueOpsService | completeUpload | response | url | string |  | Signed and expiring for private assets; stable CDN URL for public ones.
VenueOpsService | completeUpload | response | thumbnailUrl | string |  | (nullable)
VenueOpsService | completeUpload | response | referenceCount | integer | yes | How many surfaces reference this asset.
VenueOpsService | completeUpload | response | rights | MediaRights |  | Licensing terms.
VenueOpsService | completeUpload | response | rights.licenceKind | enum (owned, royaltyFree, rightsManaged, creativeCommons, editorialOnly, unknown)
VenueOpsService | completeUpload | response | rights.licensor | string |  | (nullable)
VenueOpsService | completeUpload | response | rights.licenceReference | string |  | (nullable)
VenueOpsService | completeUpload | response | rights.validFrom | string (date) |  | (nullable)
VenueOpsService | completeUpload | response | rights.validTo | string (date) |  | (nullable)
VenueOpsService | completeUpload | response | rights.permittedUses | array of enum (web, print, socialMedia, inVenue, advertising, internal)
VenueOpsService | completeUpload | response | rights.attributionRequired | boolean |  | (default False)
VenueOpsService | completeUpload | response | rights.attributionText | string |  | (nullable)
VenueOpsService | completeUpload | response | rights.permittedTerritories | array of string |  | ISO country or region codes.
VenueOpsService | completeUpload | response | rights.permittedChannels | array of string |  | Distribution channel codes, checked by setMediaDistributionChannels.
VenueOpsService | completeUpload | response | rights.modelReleaseHeld | boolean |  | (default False)
VenueOpsService | completeUpload | response | rights.renewalOwner | string (uuid) |  | (nullable)
VenueOpsService | completeUpload | response | isRightsExpired | boolean
VenueOpsService | completeUpload | response | version | integer
VenueOpsService | completeUpload | response | uploadedByPrincipalId | string (uuid)
VenueOpsService | completeUpload | response | createdAt | string (date-time) | yes
VenueOpsService | completeUpload | param (path) | uploadId | string (uuid) | yes
VenueOpsService | completeUpload | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | configureAssistantProfile | request | id | string (uuid) |  | (read-only)
AiService | configureAssistantProfile | request | profileKey | string | yes
AiService | configureAssistantProfile | request | name | string
AiService | configureAssistantProfile | request | audience | enum (staff, guest, support) | yes
AiService | configureAssistantProfile | request | roleIds | array of string (uuid)
AiService | configureAssistantProfile | request | module | object |  | (nullable)
AiService | configureAssistantProfile | request | collectionIds | array of string (uuid) |  | Knowledge collections it retrieves from.
AiService | configureAssistantProfile | request | toolKeys | array of string |  | Registered tools it may propose (an assistant only reads; a change request goes to the configuration assistant, AIC-078).
AiService | configureAssistantProfile | request | modelTask | string |  | The gateway task, e.g.
AiService | configureAssistantProfile | request | guestCapabilityScope | array of string |  | For a guest profile: the same values as AiPolicy.guestCapabilityScope, narrowed.
AiService | configureAssistantProfile | request | locales | array of string
AiService | configureAssistantProfile | request | handoverTarget | string |  | Where "ask a person" goes: a support queue or a staff role. (nullable)
AiService | configureAssistantProfile | request | isActive | boolean |  | (default True)
AiService | configureAssistantProfile | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | configureAssistantProfile | response | id | string (uuid) |  | (read-only)
AiService | configureAssistantProfile | response | profileKey | string | yes
AiService | configureAssistantProfile | response | name | string
AiService | configureAssistantProfile | response | audience | enum (staff, guest, support) | yes
AiService | configureAssistantProfile | response | roleIds | array of string (uuid)
AiService | configureAssistantProfile | response | module | object |  | (nullable)
AiService | configureAssistantProfile | response | collectionIds | array of string (uuid) |  | Knowledge collections it retrieves from.
AiService | configureAssistantProfile | response | toolKeys | array of string |  | Registered tools it may propose (an assistant only reads; a change request goes to the configuration assistant, AIC-078).
AiService | configureAssistantProfile | response | modelTask | string |  | The gateway task, e.g.
AiService | configureAssistantProfile | response | guestCapabilityScope | array of string |  | For a guest profile: the same values as AiPolicy.guestCapabilityScope, narrowed.
AiService | configureAssistantProfile | response | locales | array of string
AiService | configureAssistantProfile | response | handoverTarget | string |  | Where "ask a person" goes: a support queue or a staff role. (nullable)
AiService | configureAssistantProfile | response | isActive | boolean |  | (default True)
AiService | configureAssistantProfile | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | configureAssistantProfile | param (path) | profileKey | string | yes
AiService | configureAssistantProfile | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | configureWorkstation | request | cashierInputMode | enum (keyboard, touch, scanner, hybrid) |  | BL-061. (default hybrid)
TenancyService | configureWorkstation | request | guestDisplayContent | array of enum (lineItems, total, loyaltyBalance, promotions, branding, upsell, queuePosition) |  | What the guest-facing screen shows while a sale is in progress.
TenancyService | configureWorkstation | request | loadedMediaStockId | string (uuid) |  | BL-095. (nullable)
TenancyService | configureWorkstation | request | mediaStockRemaining | integer |  | Decremented on issue. (read-only; nullable)
TenancyService | configureWorkstation | request | name | string | yes | (max length 200)
TenancyService | configureWorkstation | request | saleBoardId | string (uuid) |  | This till's own layout, overriding its outlet's (DEC-183; CHG-CSP-006). (nullable)
TenancyService | configureWorkstation | request | outletId | string (uuid) |  | The outlet this till stands in (CHG-CSP-006). (nullable)
TenancyService | configureWorkstation | request | cashDrawerLimit | Money |  | This till's drawer limit; null inherits VenueSettings.cashDrawerLimit (DEC-179; CHG-CSP-016). (nullable)
TenancyService | configureWorkstation | request | departmentId | string (uuid) |  | (nullable)
TenancyService | configureWorkstation | request | accessPointId | string (uuid) |  | (nullable)
TenancyService | configureWorkstation | request | devices | array of DeviceBinding
TenancyService | configureWorkstation | request | devices[].kind | DeviceKind: enum (receiptPrinter, ticketPrinter, labelPrinter, cashDrawer, barcodeScanner, rfidReader, nfcReader, cardReader, …) | yes | mobileHandset (18.1.5, added 29 September): a staff phone or tablet running the staff app, registered for push and bound to no workstation.
TenancyService | configureWorkstation | request | devices[].driver | string | yes | Driver identifier.
TenancyService | configureWorkstation | request | devices[].identifier | string |  | Serial
TenancyService | configureWorkstation | request | devices[].isRequired | boolean |  | When true, the workstation refuses to open a shift if the device is absent. (default False)
TenancyService | configureWorkstation | request | deploymentProfile | DeploymentProfile: enum (terminalLocal, venueEdge, thin) |  | How this workstation obtains catalogue and inventory (ADR-0013).
TenancyService | configureWorkstation | request | edgeNodeId | string (uuid) |  | (nullable)
TenancyService | configureWorkstation | request | isActive | boolean |  | (default True)
TenancyService | configureWorkstation | response | id | string (uuid) | yes
TenancyService | configureWorkstation | response | code | string | yes | (max length 64)
TenancyService | configureWorkstation | response | name | string | yes | (max length 200)
TenancyService | configureWorkstation | response | venueId | string (uuid) | yes
TenancyService | configureWorkstation | response | regionId | string (uuid) | yes
TenancyService | configureWorkstation | response | departmentId | string (uuid) |  | (nullable)
TenancyService | configureWorkstation | response | outletId | string (uuid) |  | The outlet this till stands in (CHG-CSP-006). (nullable)
TenancyService | configureWorkstation | response | scopePath | string | yes
TenancyService | configureWorkstation | response | saleBoard | object | yes | Determines which front end loads.
TenancyService | configureWorkstation | response | saleBoard.id | string (uuid) | yes
TenancyService | configureWorkstation | response | saleBoard.kind | SaleBoardKind: enum (ticketing, fnb, retail, mixed) | yes
TenancyService | configureWorkstation | response | saleBoard.name | string
TenancyService | configureWorkstation | response | saleBoardSource | enum (outlet, workstation) |  | Where saleBoard came from (decided 2 October 2026, Chinmay, BO-109: "Per outlet, with a till override"; DEC-183; CHG-CSP-006): outlet when the till uses its outlet's layout, workstation when this til… (read-only)
TenancyService | configureWorkstation | response | cashDrawerLimit | Money |  | This till's drawer limit, overriding the venue's (VenueSettings.cashDrawerLimit; DEC-179; CHG-CSP-016). (nullable)
TenancyService | configureWorkstation | response | accessPointId | string (uuid) |  | Inherited from the workstation, never selected by the operator. (nullable)
TenancyService | configureWorkstation | response | devices | array of DeviceBinding
TenancyService | configureWorkstation | response | devices[].kind | DeviceKind: enum (receiptPrinter, ticketPrinter, labelPrinter, cashDrawer, barcodeScanner, rfidReader, nfcReader, cardReader, …) | yes | mobileHandset (18.1.5, added 29 September): a staff phone or tablet running the staff app, registered for push and bound to no workstation.
TenancyService | configureWorkstation | response | devices[].driver | string | yes | Driver identifier.
TenancyService | configureWorkstation | response | devices[].identifier | string |  | Serial
TenancyService | configureWorkstation | response | devices[].isRequired | boolean |  | When true, the workstation refuses to open a shift if the device is absent. (default False)
TenancyService | configureWorkstation | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
TenancyService | configureWorkstation | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
TenancyService | configureWorkstation | response | timeZone | string | yes
TenancyService | configureWorkstation | response | deploymentProfile | DeploymentProfile: enum (terminalLocal, venueEdge, thin) |  | How this workstation obtains catalogue and inventory (ADR-0013).
TenancyService | configureWorkstation | response | edgeNodeId | string (uuid) |  | Present when deploymentProfile is venueEdge. (nullable)
TenancyService | configureWorkstation | response | healthScore | integer |  | Board 1 of the client's POS set. (min 0; max 100; read-only; nullable)
TenancyService | configureWorkstation | response | configurationProfileId | string (uuid) |  | Which profile this workstation runs, and at which version. (nullable)
TenancyService | configureWorkstation | response | catalogueState | CatalogueState |  | The workstation's local catalogue position.
TenancyService | configureWorkstation | response | catalogueState.appliedBundleVersion | string | yes
TenancyService | configureWorkstation | response | catalogueState.appliedAt | string (date-time) | yes
TenancyService | configureWorkstation | response | catalogueState.staleAfter | string (date-time) | yes | Beyond this the terminal refuses to trade.
TenancyService | configureWorkstation | response | catalogueState.isStale | boolean | yes
TenancyService | configureWorkstation | response | catalogueState.pendingBundleVersion | string |  | Published but not yet applied. (nullable)
TenancyService | configureWorkstation | response | offlineCapable | boolean |  | Derived from deploymentProfile.
TenancyService | configureWorkstation | response | isActive | boolean
TenancyService | configureWorkstation | param (path) | workstationId | string (uuid) | yes
TenancyService | configureWorkstation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | containAiIncident | request | actions | array of object | yes | (min items 1)
AiService | containAiIncident | request | actions[].action | enum (pauseCapability, rollbackRelease, revokeException, disableTool) | yes
AiService | containAiIncident | request | actions[].targetRef | string | yes
AiService | containAiIncident | request | note | string |  | (max length 1000; nullable)
AiService | containAiIncident | response | id | string (uuid) |  | (read-only)
AiService | containAiIncident | response | reference | string | yes | (read-only)
AiService | containAiIncident | response | title | string | yes
AiService | containAiIncident | response | kind | enum (governance, operational, both)
AiService | containAiIncident | response | severity | enum (low, medium, high, critical) | yes
AiService | containAiIncident | response | status | enum (open, contained, investigating, remediating, closed) | yes | (read-only)
AiService | containAiIncident | response | capabilityKeys | array of string
AiService | containAiIncident | response | alertIds | array of string (uuid)
AiService | containAiIncident | response | operationalIncidentRef | string |  | The linked operational incident, where both apply (AIC-250). (nullable)
AiService | containAiIncident | response | containment | array of object |  | (read-only)
AiService | containAiIncident | response | containment[].action | string
AiService | containAiIncident | response | containment[].targetRef | string
AiService | containAiIncident | response | containment[].at | string (date-time)
AiService | containAiIncident | response | containment[].byPrincipalId | string (uuid)
AiService | containAiIncident | response | rootCause | string |  | (nullable)
AiService | containAiIncident | response | remediation | string |  | (nullable)
AiService | containAiIncident | response | impact | string |  | The post-incident review's impact (closeAiIncident, CHG-CSA-045). (nullable)
AiService | containAiIncident | response | controlFailure | string |  | (nullable)
AiService | containAiIncident | response | lessonsLearned | string |  | (nullable)
AiService | containAiIncident | response | ownerPrincipalId | string (uuid) |  | (nullable)
AiService | containAiIncident | response | openedAt | string (date-time) |  | (read-only)
AiService | containAiIncident | response | containedAt | string (date-time) |  | (read-only; nullable)
AiService | containAiIncident | response | closedAt | string (date-time) |  | (read-only; nullable)
AiService | containAiIncident | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | containAiIncident | param (path) | incidentId | string (uuid) | yes
AiService | containAiIncident | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | convertInventoryHold | request | orderId | string (uuid) | yes | The paid order the units are sold to.
CatalogueService | convertInventoryHold | request | units | integer |  | Units sold, when fewer than the hold grants (a line reduced before payment). (min 1)
CatalogueService | convertInventoryHold | response | id | string | yes
CatalogueService | convertInventoryHold | response | channelCapacityId | string (uuid) | yes
CatalogueService | convertInventoryHold | response | holderKind | InventoryHoldHolderKind: enum (workstation, cart) | yes | Who holds the units (decided 29 September, SD-023). (default workstation)
CatalogueService | convertInventoryHold | response | holderWorkstationId | string (uuid) |  | The holding workstation when holderKind is workstation; null on a cart hold, because a browser has none (SD-023, 29 September). (nullable)
CatalogueService | convertInventoryHold | response | holderCartId | string (uuid) |  | The holding cart (orders.cart) when holderKind is cart (SD-023, 29 September). (nullable)
CatalogueService | convertInventoryHold | response | convertedOrderId | string (uuid) |  | The paid order the hold was converted for, set by convertInventoryHold. (read-only; nullable)
CatalogueService | convertInventoryHold | response | convertedAt | string (date-time) |  | (read-only; nullable)
CatalogueService | convertInventoryHold | response | parentLeaseId | string |  | Present when sub-leased from a venue edge node. (nullable)
CatalogueService | convertInventoryHold | response | requestedUnits | integer
CatalogueService | convertInventoryHold | response | channel | object |  | Allocation this lease draws from.
CatalogueService | convertInventoryHold | response | grantedUnits | integer | yes | May be less than requested — a partial grant is not an error.
CatalogueService | convertInventoryHold | response | consumedUnits | integer | yes
CatalogueService | convertInventoryHold | response | status | LeaseStatus: enum (active, expired, released, forceReleased, converted) | yes | states/lease.yaml.
CatalogueService | convertInventoryHold | response | acquiredAt | string (date-time) | yes
CatalogueService | convertInventoryHold | response | expiresAt | string (date-time) | yes
CatalogueService | convertInventoryHold | response | releasedAt | string (date-time) |  | (nullable)
CatalogueService | convertInventoryHold | response | forceReleasedByPrincipalId | string (uuid) |  | (nullable)
CatalogueService | convertInventoryHold | response | forceReleaseReason | string |  | (nullable)
CatalogueService | convertInventoryHold | param (path) | inventoryHoldId | string (uuid) | yes
CatalogueService | convertInventoryHold | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | convertReservation | response | id | string (uuid) | yes | The client UUIDv7 from CreateOrderRequest.id.
OrderService | convertReservation | response | orderNumber | string |  | The number a guest reads and a cashier types. (read-only)
OrderService | convertReservation | response | channel | object | yes | Where it came from.
OrderService | convertReservation | response | channelProfileId | string (uuid) |  | The named sales channel the order came through (catalogue SalesChannelProfile.id), set by the server from the caller: a partner user's or reseller's channel, an API key's channel. (read-only; nullable)
OrderService | convertReservation | response | venueId | string (uuid) | yes
OrderService | convertReservation | response | scopePath | string | yes
OrderService | convertReservation | response | status | OrderStatus: enum (pending, held, paid, partiallyPaid, completed, voided, refunded, partiallyRefunded, …) | yes | held is a parked sale — the cashier freed the till and the guest will return.
OrderService | convertReservation | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | convertReservation | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | convertReservation | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | convertReservation | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | convertReservation | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | convertReservation | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | convertReservation | response | taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | convertReservation | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | convertReservation | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | convertReservation | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | convertReservation | response | netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | convertReservation | response | netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | convertReservation | response | netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | convertReservation | response | netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | convertReservation | response | refundedAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | convertReservation | response | refundedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | convertReservation | response | refundedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | convertReservation | response | refundedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | convertReservation | response | chargeCurrency | string |  | The currency the guest selected and is charged in (CHG-FIN-001, 2 October 2026). (pattern ^[A-Z]{3}$; read-only; nullable)
OrderService | convertReservation | response | chargeFxRate | object |  | Units of chargeCurrency per one unit of the base currency, from the region's tender rate in force at checkout (finance.FxRate), stored on the order so the payment, the receipt, the tax invoice and an… (read-only; nullable)
OrderService | convertReservation | response | chargeFxRateId | string (uuid) |  | The finance.FxRate row the rate was taken from, for audit. (read-only; nullable)
OrderService | convertReservation | response | chargeTotal | object |  | grossAmount converted at chargeFxRate and rounded to the charge currency's scale: what the guest pays and what the payment request to the provider asks for (CHG-FIN-001). (read-only)
OrderService | convertReservation | response | chargeTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | convertReservation | response | chargeTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | convertReservation | response | chargeTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | convertReservation | response | chargeRateLockedUntil | string (date-time) |  | The quote holds until then (the cart lease). (read-only; nullable)
OrderService | convertReservation | response | droppedPromotions | array of object |  | Promotions left off this order at checkout because their budget cap would have been exceeded (decided 28 September, audit R101 (8)). (read-only)
OrderService | convertReservation | response | droppedPromotions[].promotionId | string (uuid) | yes
OrderService | convertReservation | response | droppedPromotions[].name | string
OrderService | convertReservation | response | droppedPromotions[].reason | enum (budgetCapReached)
OrderService | convertReservation | response | totalPriceVariance | object |  | Sum across lines.
OrderService | convertReservation | response | totalPriceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | convertReservation | response | totalPriceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | convertReservation | response | totalPriceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | convertReservation | response | lines | array of OrderLine | yes
OrderService | convertReservation | response | lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | convertReservation | response | lines[].variantId | string (uuid) | yes
OrderService | convertReservation | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | convertReservation | response | lines[].performanceId | string (uuid)
OrderService | convertReservation | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | convertReservation | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | convertReservation | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | convertReservation | response | lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | convertReservation | response | lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | convertReservation | response | lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | convertReservation | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | convertReservation | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | convertReservation | response | lines[].quantity | integer | yes | (min 1)
OrderService | convertReservation | response | lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | convertReservation | response | lines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | convertReservation | response | lines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | convertReservation | response | lines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | convertReservation | response | lines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | convertReservation | response | lines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | convertReservation | response | lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | convertReservation | response | lines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | convertReservation | response | lines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | convertReservation | response | lines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | convertReservation | response | lines[].holderName | string |  | (nullable)
OrderService | convertReservation | response | lines[].dataMaskValues | object |  | Deliberately open.
OrderService | convertReservation | response | lines[].serverUnitPrice | object | yes | What the server computed on ingest.
OrderService | convertReservation | response | lines[].serverUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | convertReservation | response | lines[].serverUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | convertReservation | response | lines[].serverUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | convertReservation | response | lines[].priceVariance | object |  | Server minus quoted.
OrderService | convertReservation | response | lines[].priceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | convertReservation | response | lines[].priceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | convertReservation | response | lines[].priceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | convertReservation | response | lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | convertReservation | response | lines[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | convertReservation | response | lines[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | convertReservation | response | lines[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | convertReservation | response | lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | convertReservation | response | lines[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | convertReservation | response | lines[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | convertReservation | response | lines[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | convertReservation | response | lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | convertReservation | response | lines[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | convertReservation | response | lines[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | convertReservation | response | lines[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | convertReservation | response | lines[].entitlementIds | array of string (uuid) |  | The entitlements this line issued.
OrderService | convertReservation | response | lines[].crossRegionRightIds | array of string |  | Redemption rights propagated to other cells for this line.
OrderService | convertReservation | response | lines[].reprintCount | integer |  | How many times this line's tickets were reprinted or resent. (min 0; default 0; read-only)
OrderService | convertReservation | response | lines[].venueId | string (uuid) |  | The order's venue, copied onto the line (ADR-0044's own example; system-design review SD-008, 29 September) so a line is scoped and partitionable without its order. (read-only)
OrderService | convertReservation | response | lines[].discounts | array of OrderLineDiscount |  | The discounts applied to this line, one row each (system-design review SD-008, 29 September). (read-only)
OrderService | convertReservation | response | lines[].discounts[].id | string (uuid) | yes
OrderService | convertReservation | response | lines[].discounts[].promotionId | string (uuid) |  | The promotion that gave it. (nullable)
OrderService | convertReservation | response | lines[].discounts[].source | enum (promotion, promoCode, manual, bundle, member) | yes
OrderService | convertReservation | response | lines[].discounts[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | convertReservation | response | lines[].discounts[].reason | string |  | A cashier's reason for a manual discount. (max length 200; nullable)
OrderService | convertReservation | response | payments | array of Payment
OrderService | convertReservation | response | payments[].id | string (uuid) | yes
OrderService | convertReservation | response | payments[].orderId | string (uuid) | yes
OrderService | convertReservation | response | payments[].tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | convertReservation | response | payments[].tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | convertReservation | response | payments[].tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale.
OrderService | convertReservation | response | payments[].tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | convertReservation | response | payments[].tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | convertReservation | response | payments[].tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | convertReservation | response | payments[].fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | convertReservation | response | payments[].fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | convertReservation | response | payments[].changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | convertReservation | response | payments[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | convertReservation | response | payments[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | convertReservation | response | payments[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | convertReservation | response | payments[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | convertReservation | response | payments[].changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | convertReservation | response | payments[].changeAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | convertReservation | response | payments[].changeAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | convertReservation | response | payments[].changeAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | convertReservation | response | payments[].status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | convertReservation | response | payments[].providerName | string |  | (nullable)
OrderService | convertReservation | response | payments[].providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | convertReservation | response | payments[].providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | convertReservation | response | payments[].terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | convertReservation | response | payments[].nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | convertReservation | response | payments[].nextAction.kind | enum (redirect, terminal)
OrderService | convertReservation | response | payments[].nextAction.url | string (uri) |  | (nullable)
OrderService | convertReservation | response | payments[].nextAction.expiresAt | string (date-time) |  | (nullable)
OrderService | convertReservation | response | payments[].lastInquiryAt | string (date-time) |  | (nullable)
OrderService | convertReservation | response | payments[].recordedAt | string (date-time) | yes
OrderService | convertReservation | response | payments[].syncedAt | string (date-time) |  | (nullable)
OrderService | convertReservation | response | principalId | string (uuid)
OrderService | convertReservation | response | workstationId | string (uuid)
OrderService | convertReservation | response | shiftId | string (uuid) |  | (nullable)
OrderService | convertReservation | response | subjectId | string (uuid) |  | (nullable)
OrderService | convertReservation | response | holdLabel | string |  | The label a cashier gave when parking it with holdOrder — how they find it again. (max length 60; read-only; nullable)
OrderService | convertReservation | response | heldUntil | string (date-time) |  | When a held order expires and is voided (states/order.yaml), from holdOrder's holdUntil. (read-only; nullable)
OrderService | convertReservation | response | createdAt | string (date-time) | yes
OrderService | convertReservation | response | recordedAt | string (date-time) | yes
OrderService | convertReservation | response | syncedAt | string (date-time) |  | (nullable)
OrderService | convertReservation | param (path) | reservationId | string (uuid) | yes
OrderService | convertReservation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | copyPriceList | request | code | string | yes | (max length 64)
CatalogueService | copyPriceList | request | name | string | yes | (max length 200)
CatalogueService | copyPriceList | request | adjustmentPercent | number |  | Applied to every copied price.
CatalogueService | copyPriceList | request | roundTo | string |  | Round adjusted prices to this increment, e.g. (pattern ^\d+(\.\d{1,4})?$)
CatalogueService | copyPriceList | request | validFrom | string (date-time)
CatalogueService | copyPriceList | request | validTo | string (date-time)
CatalogueService | copyPriceList | response | priceList | PriceList
CatalogueService | copyPriceList | response | priceList.id | string (uuid) | yes
CatalogueService | copyPriceList | response | priceList.code | string | yes
CatalogueService | copyPriceList | response | priceList.name | string | yes
CatalogueService | copyPriceList | response | priceList.venueId | string (uuid) | yes
CatalogueService | copyPriceList | response | priceList.currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
CatalogueService | copyPriceList | response | priceList.currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
CatalogueService | copyPriceList | response | priceList.channels | array of Channel: enum (pos, kiosk, web, mobile, b2b, ota, callCentre) | yes
CatalogueService | copyPriceList | response | priceList.validFrom | string (date-time) |  | (nullable)
CatalogueService | copyPriceList | response | priceList.validTo | string (date-time) |  | (nullable)
CatalogueService | copyPriceList | response | priceList.priority | integer |  | Where lists overlap, higher priority wins.
CatalogueService | copyPriceList | response | priceList.description | string |  | Price list master fields (29 September, data model DM3), set with createPriceList and updatePriceList since setPriceListMaster was retired in r2 (BC-008, CHG-CLN-001). (nullable)
CatalogueService | copyPriceList | response | priceList.priceListType | enum (standardRetail, venue, attraction, event, membership, group, corporate, b2b, …) |  | (default standardRetail)
CatalogueService | copyPriceList | response | priceList.status | object |  | (default active)
CatalogueService | copyPriceList | response | priceList.ownerPrincipalId | string (uuid) |  | (nullable)
CatalogueService | copyPriceList | response | priceList.tags | array of string
CatalogueService | copyPriceList | response | priceList.legalEntityId | string (uuid) |  | (nullable)
CatalogueService | copyPriceList | response | priceList.brand | string |  | (max length 100; nullable)
CatalogueService | copyPriceList | response | priceList.businessUnit | string |  | (max length 100; nullable)
CatalogueService | copyPriceList | response | priceList.countryCode | string |  | (max length 2; pattern ^[A-Z]{2}$; nullable)
CatalogueService | copyPriceList | response | priceList.marketCode | string |  | (max length 40; nullable)
CatalogueService | copyPriceList | response | priceList.scopeLevel | enum (global, country, market, brand, venue, event, businessUnit) |  | (default venue)
CatalogueService | copyPriceList | response | priceList.defaultPriceCategoryId | string (uuid) |  | (nullable)
CatalogueService | copyPriceList | response | priceList.roundingProfileId | string (uuid) |  | (nullable)
CatalogueService | copyPriceList | response | priceList.priceResolutionPolicyId | string (uuid) |  | (nullable)
CatalogueService | copyPriceList | response | priceList.allowOverrides | boolean |  | (default False)
CatalogueService | copyPriceList | response | priceList.allowInheritance | boolean |  | (default True)
CatalogueService | copyPriceList | response | priceList.allowMultipleCurrencies | boolean |  | (default False)
CatalogueService | copyPriceList | response | priceList.allowProductSpecificRates | boolean |  | (default True)
CatalogueService | copyPriceList | response | priceList.clonedFromPriceListId | string (uuid) |  | (nullable)
CatalogueService | copyPriceList | response | priceList.currentVersion | integer |  | The active catalogue.price_list_version. (read-only; nullable)
CatalogueService | copyPriceList | response | copiedPriceCount | integer
CatalogueService | copyPriceList | param (path) | priceListId | string (uuid) | yes
CatalogueService | copyPriceList | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | createAccessPoint | request | code | string | yes | (max length 64)
AccessService | createAccessPoint | request | name | string | yes | (max length 200)
AccessService | createAccessPoint | request | venueId | string (uuid) | yes
AccessService | createAccessPoint | request | direction | Direction: enum (entry, exit, reentry, crossover) | yes
AccessService | createAccessPoint | request | antiPassbackEnabled | boolean |  | (default False)
AccessService | createAccessPoint | request | requiresExitBeforeReentry | boolean |  | (default False)
AccessService | createAccessPoint | request | driver | string
AccessService | createAccessPoint | response | id | string (uuid) | yes
AccessService | createAccessPoint | response | code | string | yes
AccessService | createAccessPoint | response | name | string | yes
AccessService | createAccessPoint | response | venueId | string (uuid) | yes
AccessService | createAccessPoint | response | scopePath | string
AccessService | createAccessPoint | response | externalCredentialSources | object |  | BL-108.
AccessService | createAccessPoint | response | scanAnomalyRules | object |  | BL-104.
AccessService | createAccessPoint | response | operatingMode | object | yes | Set by the podium with setTurnstileMode, and it wins (audit R221). (default normal)
AccessService | createAccessPoint | response | vehicleLocationCapture | boolean |  | BL-023. (default False)
AccessService | createAccessPoint | response | mode | object |  | Narrows operatingMode only: freeRotation or closed within normal or podium, null otherwise and whenever the turnstile validates in its fixed direction (audit R221). (nullable)
AccessService | createAccessPoint | response | direction | object |  | Fixed per access point (audit R221): set in the back office by createAccessPoint and updateAccessPoint, never by the podium.
AccessService | createAccessPoint | response | temporaryClosure | object |  | What the access point does while its attraction is temporarily closed (decided 2 October 2026, Chinmay, batch 6 set 9, BO-147: "Deny + reopening time + a virtual-queue return window where enabled"; D… (nullable)
AccessService | createAccessPoint | response | temporaryClosure.isClosed | boolean |  | (default False)
AccessService | createAccessPoint | response | temporaryClosure.reason | string |  | Shown to staff; the guest sees "Attraction temporarily closed". (max length 200; nullable)
AccessService | createAccessPoint | response | temporaryClosure.reopensAt | string (date-time) |  | When it is expected to reopen; shown to the guest when known. (nullable)
AccessService | createAccessPoint | response | temporaryClosure.offerVirtualQueueReturn | boolean |  | Offer a virtual-queue return window at the denied scan, where the attraction has a queue. (default False)
AccessService | createAccessPoint | response | temporaryClosure.queueId | string (uuid) |  | The virtual queue the return window is taken in. (nullable)
AccessService | createAccessPoint | response | antiPassbackEnabled | boolean
AccessService | createAccessPoint | response | requiresExitBeforeReentry | boolean |  | Written by createAccessPoint and updateAccessPoint, and returned so the edit form reads back what it wrote. (default False)
AccessService | createAccessPoint | response | driver | string |  | Driver identifier for the controller behind this access point, as written by createAccessPoint and updateAccessPoint. (nullable)
AccessService | createAccessPoint | response | geofence | object |  | Written by setAccessPointGeofence; null until one is set. (nullable)
AccessService | createAccessPoint | response | geofence.latitude | number
AccessService | createAccessPoint | response | geofence.longitude | number
AccessService | createAccessPoint | response | geofence.radiusMetres | integer |  | (min 5; max 5000)
AccessService | createAccessPoint | response | geofence.enforcement | enum (off, warn, deny) | yes | off keeps the fence on record and checks nothing; warn lets a validation from outside the fence through with a warning; deny refuses it.
AccessService | createAccessPoint | response | geofence.allowProximityBeacon | boolean |  | Accept a BLE proximity assertion in place of GPS.
AccessService | createAccessPoint | response | isActive | boolean | yes
AccessService | createAccessPoint | response | lastHeartbeatAt | string (date-time) |  | (nullable)
AccessService | createAccessPoint | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | createAdmissionRules | request | id | string (uuid) | yes | Server-assigned. (read-only)
AccessService | createAdmissionRules | request | code | string | yes | (max length 64)
AccessService | createAdmissionRules | request | perProductRules | object |  | BL-059.
AccessService | createAdmissionRules | request | name | string | yes | (max length 200)
AccessService | createAdmissionRules | request | openMinutesBefore | integer | yes | How long before a performance validation opens.
AccessService | createAdmissionRules | request | closeMinutesAfter | integer | yes
AccessService | createAdmissionRules | request | maxDurationMinutes | integer |  | (nullable)
AccessService | createAdmissionRules | request | requiresExitBeforeReentry | boolean |  | (default False)
AccessService | createAdmissionRules | request | maxReentries | integer |  | (nullable)
AccessService | createAdmissionRules | request | entryLimit | object |  | How many times the credential may enter (decided 29 September, VM close-out).
AccessService | createAdmissionRules | request | entryLimit.mode | enum (unlimited, once, nTimes, nPerDay, nPerPeriod) | yes | (default unlimited)
AccessService | createAdmissionRules | request | entryLimit.count | integer |  | N for nTimes, nPerDay and nPerPeriod; required for those modes (422 without it) (min 1)
AccessService | createAdmissionRules | request | entryLimit.periodDays | integer |  | The period for nPerPeriod (min 1)
AccessService | createAdmissionRules | request | exitScan | enum (required, optional, none) |  | (decided 29 September, VM close-out) required: re-entry needs a recorded exit. (default optional)
AccessService | createAdmissionRules | request | maxExits | integer |  | Null is unlimited (decided 29 September, VM close-out) (min 0; nullable)
AccessService | createAdmissionRules | request | reEntryWindowMinutes | integer |  | Minutes after an exit within which re-entry is allowed; null is any time the credential is valid (decided 29 September, VM close-out) (min 1; nullable)
AccessService | createAdmissionRules | request | sameDayOnly | boolean |  | Re-entry only on the day of the exit (decided 29 September, VM close-out) (default True)
AccessService | createAdmissionRules | request | designatedAccessPointIds | array of string (uuid) |  | Re-entry only through these access points; empty is any allowed access point (decided 29 September, VM close-out)
AccessService | createAdmissionRules | request | validity | object |  | When the credential is valid (decided 29 September, VM close-out).
AccessService | createAdmissionRules | request | validity.anchor | enum (fixedRange, afterSale, afterActivation, afterFirstUse) | yes | fixedRange uses from and to; the others count days from the event
AccessService | createAdmissionRules | request | validity.days | integer |  | N days after the anchor; required unless the anchor is fixedRange (min 1)
AccessService | createAdmissionRules | request | validity.from | string (date)
AccessService | createAdmissionRules | request | validity.to | string (date) |  | Inclusive.
AccessService | createAdmissionRules | request | validity.endOf | enum (day, week, month, year) |  | Validity runs to the end of the day, week, month or year the relative period ends in (nullable)
AccessService | createAdmissionRules | request | validity.daysOfWeek | array of enum (mon, tue, wed, thu, fri, sat, sun) |  | Empty is every day
AccessService | createAdmissionRules | request | validity.dayTypes | array of enum (peakDates, offPeakDates, holidays, seasons, eventDates) |  | Calendar day types on which access is allowed; empty is every day type
AccessService | createAdmissionRules | request | validity.blackoutDates | array of string (date) |  | Dates on which access is refused whatever else allows it
AccessService | createAdmissionRules | request | crossover | object |  | Crossover between parks (decided 29 September, VM close-out). (nullable)
AccessService | createAdmissionRules | request | crossover.allowedParkOrgUnitIds | array of string (uuid) | yes | (min items 2)
AccessService | createAdmissionRules | request | crossover.parkOrder | array of string (uuid) |  | Required order of parks, if any; empty is any order
AccessService | createAdmissionRules | request | crossover.sameDayOnly | boolean |  | (default True)
AccessService | createAdmissionRules | request | crossover.differentDayAccess | boolean |  | (default False)
AccessService | createAdmissionRules | request | crossover.dayPattern | enum (consecutiveFromFirstScan, flexibleWithinValidity) |  | (default flexibleWithinValidity)
AccessService | createAdmissionRules | request | crossover.maxParkEntries | integer |  | Null is unlimited (min 1; nullable)
AccessService | createAdmissionRules | request | crossover.crossoverQuantity | integer |  | How many crossovers; null is unlimited (min 1; nullable)
AccessService | createAdmissionRules | request | crossover.crossoverAfterTime | string |  | Earliest venue-local time HH:MM a crossover is allowed (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
AccessService | createAdmissionRules | request | crossover.prerequisiteParkOrgUnitId | string (uuid) |  | The park that must be entered first (nullable)
AccessService | createAdmissionRules | request | crossover.reEntryAfterCrossover | boolean |  | (default False)
AccessService | createAdmissionRules | request | allowedAccessPointIds | array of string (uuid) |  | Empty means any access point in the venue.
AccessService | createAdmissionRules | request | reEntryVerification | enum (credentialOnly, credentialUvStamp, credentialFace, credentialOperator, custom) |  | What a re-entering guest must show besides the credential, as listEntryTemporaryExit returns it (added 29 September, data-model close-out DM1). (default credentialOnly)
AccessService | createAdmissionRules | request | ruleConditions | object |  | The visual rule builder body setVisualAccessRule writes: appliesTo (products or credential types), conditions, logic (AND / OR / NOT over the conditions), decision (allow, deny, referToOperator, over… (nullable)
AccessService | createAdmissionRules | request | scopePath | string |  | The partition key (ADR-0005).
AccessService | createAdmissionRules | response | id | string (uuid) | yes | Server-assigned. (read-only)
AccessService | createAdmissionRules | response | code | string | yes | (max length 64)
AccessService | createAdmissionRules | response | perProductRules | object |  | BL-059.
AccessService | createAdmissionRules | response | name | string | yes | (max length 200)
AccessService | createAdmissionRules | response | openMinutesBefore | integer | yes | How long before a performance validation opens.
AccessService | createAdmissionRules | response | closeMinutesAfter | integer | yes
AccessService | createAdmissionRules | response | maxDurationMinutes | integer |  | (nullable)
AccessService | createAdmissionRules | response | requiresExitBeforeReentry | boolean |  | (default False)
AccessService | createAdmissionRules | response | maxReentries | integer |  | (nullable)
AccessService | createAdmissionRules | response | entryLimit | object |  | How many times the credential may enter (decided 29 September, VM close-out).
AccessService | createAdmissionRules | response | entryLimit.mode | enum (unlimited, once, nTimes, nPerDay, nPerPeriod) | yes | (default unlimited)
AccessService | createAdmissionRules | response | entryLimit.count | integer |  | N for nTimes, nPerDay and nPerPeriod; required for those modes (422 without it) (min 1)
AccessService | createAdmissionRules | response | entryLimit.periodDays | integer |  | The period for nPerPeriod (min 1)
AccessService | createAdmissionRules | response | exitScan | enum (required, optional, none) |  | (decided 29 September, VM close-out) required: re-entry needs a recorded exit. (default optional)
AccessService | createAdmissionRules | response | maxExits | integer |  | Null is unlimited (decided 29 September, VM close-out) (min 0; nullable)
AccessService | createAdmissionRules | response | reEntryWindowMinutes | integer |  | Minutes after an exit within which re-entry is allowed; null is any time the credential is valid (decided 29 September, VM close-out) (min 1; nullable)
AccessService | createAdmissionRules | response | sameDayOnly | boolean |  | Re-entry only on the day of the exit (decided 29 September, VM close-out) (default True)
AccessService | createAdmissionRules | response | designatedAccessPointIds | array of string (uuid) |  | Re-entry only through these access points; empty is any allowed access point (decided 29 September, VM close-out)
AccessService | createAdmissionRules | response | validity | object |  | When the credential is valid (decided 29 September, VM close-out).
AccessService | createAdmissionRules | response | validity.anchor | enum (fixedRange, afterSale, afterActivation, afterFirstUse) | yes | fixedRange uses from and to; the others count days from the event
AccessService | createAdmissionRules | response | validity.days | integer |  | N days after the anchor; required unless the anchor is fixedRange (min 1)
AccessService | createAdmissionRules | response | validity.from | string (date)
AccessService | createAdmissionRules | response | validity.to | string (date) |  | Inclusive.
AccessService | createAdmissionRules | response | validity.endOf | enum (day, week, month, year) |  | Validity runs to the end of the day, week, month or year the relative period ends in (nullable)
AccessService | createAdmissionRules | response | validity.daysOfWeek | array of enum (mon, tue, wed, thu, fri, sat, sun) |  | Empty is every day
AccessService | createAdmissionRules | response | validity.dayTypes | array of enum (peakDates, offPeakDates, holidays, seasons, eventDates) |  | Calendar day types on which access is allowed; empty is every day type
AccessService | createAdmissionRules | response | validity.blackoutDates | array of string (date) |  | Dates on which access is refused whatever else allows it
AccessService | createAdmissionRules | response | crossover | object |  | Crossover between parks (decided 29 September, VM close-out). (nullable)
AccessService | createAdmissionRules | response | crossover.allowedParkOrgUnitIds | array of string (uuid) | yes | (min items 2)
AccessService | createAdmissionRules | response | crossover.parkOrder | array of string (uuid) |  | Required order of parks, if any; empty is any order
AccessService | createAdmissionRules | response | crossover.sameDayOnly | boolean |  | (default True)
AccessService | createAdmissionRules | response | crossover.differentDayAccess | boolean |  | (default False)
AccessService | createAdmissionRules | response | crossover.dayPattern | enum (consecutiveFromFirstScan, flexibleWithinValidity) |  | (default flexibleWithinValidity)
AccessService | createAdmissionRules | response | crossover.maxParkEntries | integer |  | Null is unlimited (min 1; nullable)
AccessService | createAdmissionRules | response | crossover.crossoverQuantity | integer |  | How many crossovers; null is unlimited (min 1; nullable)
AccessService | createAdmissionRules | response | crossover.crossoverAfterTime | string |  | Earliest venue-local time HH:MM a crossover is allowed (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
AccessService | createAdmissionRules | response | crossover.prerequisiteParkOrgUnitId | string (uuid) |  | The park that must be entered first (nullable)
AccessService | createAdmissionRules | response | crossover.reEntryAfterCrossover | boolean |  | (default False)
AccessService | createAdmissionRules | response | allowedAccessPointIds | array of string (uuid) |  | Empty means any access point in the venue.
AccessService | createAdmissionRules | response | reEntryVerification | enum (credentialOnly, credentialUvStamp, credentialFace, credentialOperator, custom) |  | What a re-entering guest must show besides the credential, as listEntryTemporaryExit returns it (added 29 September, data-model close-out DM1). (default credentialOnly)
AccessService | createAdmissionRules | response | ruleConditions | object |  | The visual rule builder body setVisualAccessRule writes: appliesTo (products or credential types), conditions, logic (AND / OR / NOT over the conditions), decision (allow, deny, referToOperator, over… (nullable)
AccessService | createAdmissionRules | response | scopePath | string |  | The partition key (ADR-0005).
AccessService | createAdmissionRules | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | createAiConversation | request | module | object | yes | Which part of the platform the conversation is about (8.4.1).
AiService | createAiConversation | request | locale | string |  | 8.4.3.
AiService | createAiConversation | response | id | string (uuid) | yes
AiService | createAiConversation | response | principalId | string (uuid) | yes
AiService | createAiConversation | response | scopePath | string
AiService | createAiConversation | response | module | ModuleKey: enum (core, ticketing, access, fnb, retail, inventory, seating, membership, …) | yes | What a tenant buys, and what a screen belongs to.
AiService | createAiConversation | response | locale | string
AiService | createAiConversation | response | messageCount | integer
AiService | createAiConversation | response | startedAt | string (date-time) | yes
AiService | createAiConversation | response | lastMessageAt | string (date-time)
AiService | createAiConversation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | createAiGovernancePolicyDraft | request | policyId | string (uuid) |  | An existing policy to draft the next version of. (nullable)
AiService | createAiGovernancePolicyDraft | request | policyKey | string |  | Required for a new policy. (nullable)
AiService | createAiGovernancePolicyDraft | request | name | string |  | (nullable)
AiService | createAiGovernancePolicyDraft | request | kind | enum (action, data, scope, autonomy, approval, environment) |  | (nullable)
AiService | createAiGovernancePolicyDraft | request | capabilityKeys | array of string
AiService | createAiGovernancePolicyDraft | request | rules | array of AiGovernanceRule | yes | (min items 1)
AiService | createAiGovernancePolicyDraft | request | rules[].effect | AiGovernanceOutcome: enum (allow, allowWithConditions, prepareOnly, approvalRequired, escalate, block) | yes | What the governance decision point returns (design 3.8, AIC-166).
AiService | createAiGovernancePolicyDraft | request | rules[].capabilityKeys | array of string |  | Registered capabilities it applies to.
AiService | createAiGovernancePolicyDraft | request | rules[].actions | array of enum (read, analyze, recommend, generate, prepare, create, modify, publish, …) |  | ADM-523: what AI may do, from reading to executing.
AiService | createAiGovernancePolicyDraft | request | rules[].dataCategories | array of string |  | Data categories (ADM-524), e.g.
AiService | createAiGovernancePolicyDraft | request | rules[].purposes | array of string |  | Permitted purposes for those categories (AIC-156, AIR-182).
AiService | createAiGovernancePolicyDraft | request | rules[].maxAmount | object |  | Above this value the effect escalates one step (for example to approvalRequired). (nullable)
AiService | createAiGovernancePolicyDraft | request | rules[].maxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
AiService | createAiGovernancePolicyDraft | request | rules[].maxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
AiService | createAiGovernancePolicyDraft | request | rules[].maxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
AiService | createAiGovernancePolicyDraft | request | rules[].roleIds | array of string (uuid) |  | Roles the rule applies to; empty means every role.
AiService | createAiGovernancePolicyDraft | request | rules[].environments | array of enum (development, sandbox, staging, production) |  | ADM-525.
AiService | createAiGovernancePolicyDraft | request | rules[].conditions | object |  | Conditions attached to an allowWithConditions effect, for example maskFields or requireCitation. (nullable)
AiService | createAiGovernancePolicyDraft | request | changeNote | string |  | (nullable)
AiService | createAiGovernancePolicyDraft | response | id | string (uuid) |  | (read-only)
AiService | createAiGovernancePolicyDraft | response | policyId | string (uuid) | yes
AiService | createAiGovernancePolicyDraft | response | version | integer | yes | (min 1)
AiService | createAiGovernancePolicyDraft | response | status | enum (draft, simulated, published, superseded) | yes
AiService | createAiGovernancePolicyDraft | response | rules | array of AiGovernanceRule |  | The rules of one policy version, stored with the version as one jsonb column.
AiService | createAiGovernancePolicyDraft | response | rules[].effect | AiGovernanceOutcome: enum (allow, allowWithConditions, prepareOnly, approvalRequired, escalate, block) | yes | What the governance decision point returns (design 3.8, AIC-166).
AiService | createAiGovernancePolicyDraft | response | rules[].capabilityKeys | array of string |  | Registered capabilities it applies to.
AiService | createAiGovernancePolicyDraft | response | rules[].actions | array of enum (read, analyze, recommend, generate, prepare, create, modify, publish, …) |  | ADM-523: what AI may do, from reading to executing.
AiService | createAiGovernancePolicyDraft | response | rules[].dataCategories | array of string |  | Data categories (ADM-524), e.g.
AiService | createAiGovernancePolicyDraft | response | rules[].purposes | array of string |  | Permitted purposes for those categories (AIC-156, AIR-182).
AiService | createAiGovernancePolicyDraft | response | rules[].maxAmount | object |  | Above this value the effect escalates one step (for example to approvalRequired). (nullable)
AiService | createAiGovernancePolicyDraft | response | rules[].maxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
AiService | createAiGovernancePolicyDraft | response | rules[].maxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
AiService | createAiGovernancePolicyDraft | response | rules[].maxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
AiService | createAiGovernancePolicyDraft | response | rules[].roleIds | array of string (uuid) |  | Roles the rule applies to; empty means every role.
AiService | createAiGovernancePolicyDraft | response | rules[].environments | array of enum (development, sandbox, staging, production) |  | ADM-525.
AiService | createAiGovernancePolicyDraft | response | rules[].conditions | object |  | Conditions attached to an allowWithConditions effect, for example maskFields or requireCitation. (nullable)
AiService | createAiGovernancePolicyDraft | response | changeNote | string |  | (nullable)
AiService | createAiGovernancePolicyDraft | response | simulationSummary | object |  | The last simulateAiGovernancePolicy result: decisions that would change, by outcome. (read-only; nullable)
AiService | createAiGovernancePolicyDraft | response | draftedByPrincipalId | string (uuid) |  | (read-only)
AiService | createAiGovernancePolicyDraft | response | publishedByPrincipalId | string (uuid) |  | (read-only; nullable)
AiService | createAiGovernancePolicyDraft | response | publishedAt | string (date-time) |  | (read-only; nullable)
AiService | createAiGovernancePolicyDraft | response | supersededAt | string (date-time) |  | (read-only; nullable)
AiService | createAiGovernancePolicyDraft | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | createAiGovernancePolicyDraft | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
PlatformService | createApiClient | request | id | string (uuid) | yes | (read-only)
PlatformService | createApiClient | request | developerId | string (uuid) | yes
PlatformService | createApiClient | request | name | string | yes
PlatformService | createApiClient | request | clientId | string |  | (read-only)
PlatformService | createApiClient | request | environment | enum (sandbox, production) | yes | Bound to one, stated on the object rather than by naming convention.
PlatformService | createApiClient | request | scopes | array of string | yes | Resolved against the tenant's licence at token issue (13.3.24).
PlatformService | createApiClient | request | issuedBy | enum (partner, ticvai) |  | Who generated the key (M17-06): a developer for a sandbox key, TICVAI for a production key issued on an approved requestProductionAccess. (read-only)
PlatformService | createApiClient | request | certificationListingId | string (uuid) |  | For a production client, the certified integration it was issued against. (nullable)
PlatformService | createApiClient | request | credentialTtlDays | integer |  | Key lifetime. (min 1; max 730; nullable)
PlatformService | createApiClient | request | expiresAt | string (date-time) |  | When the key stops working unless rotated. (read-only; nullable)
PlatformService | createApiClient | request | allowedTenantIds | array of string (uuid) |  | 13.1.46.
PlatformService | createApiClient | request | ipAllowList | array of string |  | 13.1.38.
PlatformService | createApiClient | request | status | enum (active, suspended, revoked) | yes | (read-only)
PlatformService | createApiClient | request | lastUsedAt | string (date-time) |  | A credential unused for a year is a credential nobody will notice being stolen. (read-only; nullable)
PlatformService | createApiClient | response | client | ApiClient |  | CF-135a.
PlatformService | createApiClient | response | client.id | string (uuid) | yes | (read-only)
PlatformService | createApiClient | response | client.developerId | string (uuid) | yes
PlatformService | createApiClient | response | client.name | string | yes
PlatformService | createApiClient | response | client.clientId | string |  | (read-only)
PlatformService | createApiClient | response | client.environment | enum (sandbox, production) | yes | Bound to one, stated on the object rather than by naming convention.
PlatformService | createApiClient | response | client.scopes | array of string | yes | Resolved against the tenant's licence at token issue (13.3.24).
PlatformService | createApiClient | response | client.issuedBy | enum (partner, ticvai) |  | Who generated the key (M17-06): a developer for a sandbox key, TICVAI for a production key issued on an approved requestProductionAccess. (read-only)
PlatformService | createApiClient | response | client.certificationListingId | string (uuid) |  | For a production client, the certified integration it was issued against. (nullable)
PlatformService | createApiClient | response | client.credentialTtlDays | integer |  | Key lifetime. (min 1; max 730; nullable)
PlatformService | createApiClient | response | client.expiresAt | string (date-time) |  | When the key stops working unless rotated. (read-only; nullable)
PlatformService | createApiClient | response | client.allowedTenantIds | array of string (uuid) |  | 13.1.46.
PlatformService | createApiClient | response | client.ipAllowList | array of string |  | 13.1.38.
PlatformService | createApiClient | response | client.status | enum (active, suspended, revoked) | yes | (read-only)
PlatformService | createApiClient | response | client.lastUsedAt | string (date-time) |  | A credential unused for a year is a credential nobody will notice being stolen. (read-only; nullable)
PlatformService | createApiClient | response | clientSecret | string (password)
PlatformService | createApiClient | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | createApprovalDelegation | request | id | string (uuid) |  | (read-only)
TenancyService | createApprovalDelegation | request | delegatorPrincipalId | string (uuid) | yes | A principal id (identity.Principal.id).
TenancyService | createApprovalDelegation | request | delegatePrincipalId | string (uuid) | yes | A principal id, resolved to a name the same way as delegatorPrincipalId.
TenancyService | createApprovalDelegation | request | kinds | array of ApprovalKind: enum (refund, priceOverride, discountOverride, complimentaryTicket, membershipCancellation, accessPermissionChange, configurationChange, aiRecommendation, …) |  | Absent means everything the delegator may approve.
TenancyService | createApprovalDelegation | request | maxAmount | object |  | A delegate may be given less authority than the delegator, never more.
TenancyService | createApprovalDelegation | request | maxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | createApprovalDelegation | request | maxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | createApprovalDelegation | request | maxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | createApprovalDelegation | request | from | string (date-time) | yes
TenancyService | createApprovalDelegation | request | to | string (date-time) | yes | Required.
TenancyService | createApprovalDelegation | request | reason | string
TenancyService | createApprovalDelegation | request | isActive | boolean |  | (read-only)
TenancyService | createApprovalDelegation | request | scopePath | string |  | The partition key (ADR-0005).
TenancyService | createApprovalDelegation | request | delegationType | string |  | The composite screen's delegationType (planned absence, temporary cover ...), for display and reporting; the engine treats every delegation alike (4 October 2026, CHG-FXC-005). (nullable)
TenancyService | createApprovalDelegation | request | maxPercentage | number |  | A percentage cap beside maxAmount (the composite's authorityPercentage, CHG-FXC-005). (nullable)
TenancyService | createApprovalDelegation | request | requiredRoleId | string (uuid) |  | A role the delegate must hold for the delegation to act (the composite's requiredRole); checked when the delegate decides, refused with 409 at creation where the delegate does not hold it (CHG-FXC-00… (nullable)
TenancyService | createApprovalDelegation | response | id | string (uuid) |  | (read-only)
TenancyService | createApprovalDelegation | response | delegatorPrincipalId | string (uuid) | yes | A principal id (identity.Principal.id).
TenancyService | createApprovalDelegation | response | delegatePrincipalId | string (uuid) | yes | A principal id, resolved to a name the same way as delegatorPrincipalId.
TenancyService | createApprovalDelegation | response | kinds | array of ApprovalKind: enum (refund, priceOverride, discountOverride, complimentaryTicket, membershipCancellation, accessPermissionChange, configurationChange, aiRecommendation, …) |  | Absent means everything the delegator may approve.
TenancyService | createApprovalDelegation | response | maxAmount | object |  | A delegate may be given less authority than the delegator, never more.
TenancyService | createApprovalDelegation | response | maxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | createApprovalDelegation | response | maxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | createApprovalDelegation | response | maxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | createApprovalDelegation | response | from | string (date-time) | yes
TenancyService | createApprovalDelegation | response | to | string (date-time) | yes | Required.
TenancyService | createApprovalDelegation | response | reason | string
TenancyService | createApprovalDelegation | response | isActive | boolean |  | (read-only)
TenancyService | createApprovalDelegation | response | scopePath | string |  | The partition key (ADR-0005).
TenancyService | createApprovalDelegation | response | delegationType | string |  | The composite screen's delegationType (planned absence, temporary cover ...), for display and reporting; the engine treats every delegation alike (4 October 2026, CHG-FXC-005). (nullable)
TenancyService | createApprovalDelegation | response | maxPercentage | number |  | A percentage cap beside maxAmount (the composite's authorityPercentage, CHG-FXC-005). (nullable)
TenancyService | createApprovalDelegation | response | requiredRoleId | string (uuid) |  | A role the delegate must hold for the delegation to act (the composite's requiredRole); checked when the delegate decides, refused with 409 at creation where the delegate does not hold it (CHG-FXC-00… (nullable)
TenancyService | createApprovalDelegation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | createApprovalRequest | request | id | string (uuid) | yes
TenancyService | createApprovalRequest | request | kind | ApprovalKind: enum (refund, priceOverride, discountOverride, complimentaryTicket, membershipCancellation, accessPermissionChange, configurationChange, aiRecommendation, …) | yes | 11.1.7 and 11.1.30–11.1.37.
TenancyService | createApprovalRequest | request | subjectContract | string | yes | Which contract owns the thing being approved.
TenancyService | createApprovalRequest | request | subjectType | string | yes
TenancyService | createApprovalRequest | request | subjectId | string | yes | A reference, never a copy.
TenancyService | createApprovalRequest | request | scopePath | string | yes
TenancyService | createApprovalRequest | request | summary | string | yes | What the approver sees in their queue before opening it. (max length 300)
TenancyService | createApprovalRequest | request | amount | Money |  | On the wire this is three fields; in the database it is one column.
TenancyService | createApprovalRequest | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | createApprovalRequest | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | createApprovalRequest | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | createApprovalRequest | request | attributes | object
TenancyService | createApprovalRequest | request | justification | string |  | (max length 1000)
TenancyService | createApprovalRequest | request | isDraft | boolean |  | True saves the request at draft without routing it; submitApprovalRequest sends it later (decided 28 September, audit R129). (default False)
TenancyService | createApprovalRequest | response | id | string | yes
TenancyService | createApprovalRequest | response | kind | ApprovalKind: enum (refund, priceOverride, discountOverride, complimentaryTicket, membershipCancellation, accessPermissionChange, configurationChange, aiRecommendation, …) | yes | 11.1.7 and 11.1.30–11.1.37.
TenancyService | createApprovalRequest | response | rerouteOnNoApprover | boolean |  | BL-154. (default True)
TenancyService | createApprovalRequest | response | outOfOfficeDelegateId | string (uuid) |  | (nullable)
TenancyService | createApprovalRequest | response | allowEmailApproval | boolean |  | Approving from an email link with no second factor is the weakest path in the system, so it is off by default and available only below a configured value. (default False)
TenancyService | createApprovalRequest | response | reopenedFrom | string (uuid) |  | Reopening a decided approval creates a new one that points back. (nullable)
TenancyService | createApprovalRequest | response | status | ApprovalStatus: enum (draft, pending, escalated, returned, informationRequested, approved, rejected, withdrawn, …) | yes
TenancyService | createApprovalRequest | response | subjectContract | string
TenancyService | createApprovalRequest | response | subjectType | string
TenancyService | createApprovalRequest | response | subjectId | string
TenancyService | createApprovalRequest | response | scopePath | string
TenancyService | createApprovalRequest | response | summary | string
TenancyService | createApprovalRequest | response | amount | Money |  | On the wire this is three fields; in the database it is one column.
TenancyService | createApprovalRequest | response | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | createApprovalRequest | response | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | createApprovalRequest | response | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | createApprovalRequest | response | justification | string |  | (nullable)
TenancyService | createApprovalRequest | response | requestedByPrincipalId | string (uuid) | yes
TenancyService | createApprovalRequest | response | matrixVersion | integer
TenancyService | createApprovalRequest | response | mode | ApprovalMode: enum (sequential, parallel, consensus, majority) |  | 11.1.43–11.1.46.
TenancyService | createApprovalRequest | response | currentLevel | integer
TenancyService | createApprovalRequest | response | totalLevels | integer
TenancyService | createApprovalRequest | response | pendingApprovers | array of object
TenancyService | createApprovalRequest | response | pendingApprovers[].principalId | string (uuid)
TenancyService | createApprovalRequest | response | pendingApprovers[].displayName | string
TenancyService | createApprovalRequest | response | pendingApprovers[].isDelegate | boolean
TenancyService | createApprovalRequest | response | decisions | array of ApprovalDecision |  | Every decision at every level, in order.
TenancyService | createApprovalRequest | response | decisions[].id | string (uuid) |  | Added 20 August. (read-only)
TenancyService | createApprovalRequest | response | decisions[].level | integer | yes
TenancyService | createApprovalRequest | response | decisions[].principalId | string (uuid) | yes
TenancyService | createApprovalRequest | response | decisions[].displayName | string
TenancyService | createApprovalRequest | response | decisions[].isDelegate | boolean
TenancyService | createApprovalRequest | response | decisions[].delegatedFrom | string (uuid) |  | (nullable)
TenancyService | createApprovalRequest | response | decisions[].decision | enum (approve, reject) | yes
TenancyService | createApprovalRequest | response | decisions[].comment | string |  | (nullable)
TenancyService | createApprovalRequest | response | decisions[].reason | string |  | (nullable)
TenancyService | createApprovalRequest | response | decisions[].usedMfa | boolean
TenancyService | createApprovalRequest | response | decisions[].signatureRef | string |  | (nullable)
TenancyService | createApprovalRequest | response | decisions[].decidedAt | string (date-time) | yes
TenancyService | createApprovalRequest | response | escalations | array of object |  | 11.1.48.
TenancyService | createApprovalRequest | response | escalations[].at | string (date-time)
TenancyService | createApprovalRequest | response | escalations[].reason | string
TenancyService | createApprovalRequest | response | escalations[].fromLevel | integer
TenancyService | createApprovalRequest | response | escalations[].toLevel | integer
TenancyService | createApprovalRequest | response | escalations[].wasAutomatic | boolean
TenancyService | createApprovalRequest | response | resubmittedFromId | string |  | (nullable)
TenancyService | createApprovalRequest | response | reopenedFromId | string |  | (nullable)
TenancyService | createApprovalRequest | response | slaDueAt | string (date-time) |  | (nullable)
TenancyService | createApprovalRequest | response | slaBreached | boolean
TenancyService | createApprovalRequest | response | expiresAt | string (date-time) |  | (nullable)
TenancyService | createApprovalRequest | response | assignedToPrincipalId | string (uuid) |  | Who claimed or was assigned the request in a shared queue (assignApprovalRequest; DI-723; CHG-CSP-042). (read-only; nullable)
TenancyService | createApprovalRequest | response | assignedToDepartmentId | string (uuid) |  | The department queue it was assigned to, where it went to a department rather than a person (CHG-CSP-042). (read-only; nullable)
TenancyService | createApprovalRequest | response | assignedAt | string (date-time) |  | (read-only; nullable)
TenancyService | createApprovalRequest | response | requestedAt | string (date-time) | yes
TenancyService | createApprovalRequest | response | completedAt | string (date-time) |  | (nullable)
TenancyService | createApprovalRequest | response | aiAssessment | object |  | AI context for the reviewer, never an input to the decision (11.1.73 to 11.1.75; MoM 8 September; 29 September, build pass, group G2). (read-only; nullable)
TenancyService | createApprovalRequest | response | aiAssessment.riskScore | integer |  | (min 0; max 100)
TenancyService | createApprovalRequest | response | aiAssessment.riskBand | enum (low, medium, high, critical)
TenancyService | createApprovalRequest | response | aiAssessment.priorityScore | integer |  | (min 0; max 100)
TenancyService | createApprovalRequest | response | aiAssessment.escalationSuggestion | object |  | A suggestion a person may act on through escalateApprovalRequest, or the tenant's own SLA policy may; nothing escalates because of it.
TenancyService | createApprovalRequest | response | aiAssessment.escalationSuggestion.action | enum (escalate, addBackupApprover, none)
TenancyService | createApprovalRequest | response | aiAssessment.escalationSuggestion.reason | string |  | (nullable)
TenancyService | createApprovalRequest | response | aiAssessment.signals | array of object |  | The signals behind the scores, largest first, as ai.AiApprovalRequestScore.signals. (max items 10)
TenancyService | createApprovalRequest | response | aiAssessment.signals[].code | string
TenancyService | createApprovalRequest | response | aiAssessment.signals[].contribution | number
TenancyService | createApprovalRequest | response | aiAssessment.signals[].detail | string |  | (nullable)
TenancyService | createApprovalRequest | response | aiAssessment.scoreId | string (uuid) |  | The ai.approval_request_score row it was copied from; ai.getApprovalRequestScore gives the full context.
TenancyService | createApprovalRequest | response | aiAssessment.decisionRecordId | string |  | The ai decision record, for the audit of what the AI said and why.
TenancyService | createApprovalRequest | response | aiAssessment.assessedAt | string (date-time)
TenancyService | createApprovalRequest | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | createBanner | request | id | string (uuid) | yes | (read-only)
WhiteLabelService | createBanner | request | title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | createBanner | request | subtitle | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | createBanner | request | imageAssetRef | string (uuid) | yes
WhiteLabelService | createBanner | request | placement | enum (homepageHero, homepageBlock, explore, checkout)
WhiteLabelService | createBanner | request | linkTarget | LinkTarget
WhiteLabelService | createBanner | request | linkTarget.kind | enum (module, contentPage, product, event, externalUrl, appSection, none) | yes | appSection points at a section of the guest mobile app (decided 29 September, MOB-1), so the bottom navigation can hold Home, Explore, Plan and Tickets.
WhiteLabelService | createBanner | request | linkTarget.moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) |  | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | createBanner | request | linkTarget.appSection | enum (home, explore, plan, tickets, map, account, buyTickets) |  | Required when kind is appSection.
WhiteLabelService | createBanner | request | linkTarget.contentPageId | string (uuid)
WhiteLabelService | createBanner | request | linkTarget.productId | string (uuid)
WhiteLabelService | createBanner | request | linkTarget.eventId | string (uuid)
WhiteLabelService | createBanner | request | linkTarget.url | string
WhiteLabelService | createBanner | request | startsAt | string (date-time) | yes
WhiteLabelService | createBanner | request | endsAt | string (date-time) |  | Must follow startsAt when set (decided 28 September, audit R163). (nullable)
WhiteLabelService | createBanner | request | state | object |  | Moved by updateBanner between draft and scheduled, and by the schedule timer from scheduled to active and active to expired at startsAt and endsAt, in the tenant's timezone (states/schedule.yaml). (read-only)
WhiteLabelService | createBanner | request | sortOrder | integer
WhiteLabelService | createBanner | request | isActive | boolean
WhiteLabelService | createBanner | response | id | string (uuid) | yes | (read-only)
WhiteLabelService | createBanner | response | title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | createBanner | response | subtitle | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | createBanner | response | imageAssetRef | string (uuid) | yes
WhiteLabelService | createBanner | response | placement | enum (homepageHero, homepageBlock, explore, checkout)
WhiteLabelService | createBanner | response | linkTarget | LinkTarget
WhiteLabelService | createBanner | response | linkTarget.kind | enum (module, contentPage, product, event, externalUrl, appSection, none) | yes | appSection points at a section of the guest mobile app (decided 29 September, MOB-1), so the bottom navigation can hold Home, Explore, Plan and Tickets.
WhiteLabelService | createBanner | response | linkTarget.moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) |  | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | createBanner | response | linkTarget.appSection | enum (home, explore, plan, tickets, map, account, buyTickets) |  | Required when kind is appSection.
WhiteLabelService | createBanner | response | linkTarget.contentPageId | string (uuid)
WhiteLabelService | createBanner | response | linkTarget.productId | string (uuid)
WhiteLabelService | createBanner | response | linkTarget.eventId | string (uuid)
WhiteLabelService | createBanner | response | linkTarget.url | string
WhiteLabelService | createBanner | response | startsAt | string (date-time) | yes
WhiteLabelService | createBanner | response | endsAt | string (date-time) |  | Must follow startsAt when set (decided 28 September, audit R163). (nullable)
WhiteLabelService | createBanner | response | state | object |  | Moved by updateBanner between draft and scheduled, and by the schedule timer from scheduled to active and active to expired at startsAt and endsAt, in the tenant's timezone (states/schedule.yaml). (read-only)
WhiteLabelService | createBanner | response | sortOrder | integer
WhiteLabelService | createBanner | response | isActive | boolean
WhiteLabelService | createBanner | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | createBookingFlowDefinition | request | id | string (uuid) |  | (read-only)
WhiteLabelService | createBookingFlowDefinition | request | venueId | string (uuid) |  | From the path of createBookingFlowDefinition. (read-only)
WhiteLabelService | createBookingFlowDefinition | request | flowTypeKey | BookingFlowTypeKey: enum (datedDayPass, timedEntry, openDated, seatedFixedPerformance, seatedDateTimeSeatMap, experienceWorkshop, surfSession, meetingRoomHourly, …) | yes | The flow types the system catalogue offers (decided 29 September, W12; impact.md b).
WhiteLabelService | createBookingFlowDefinition | request | name | string | yes | Staff-facing, e.g. (max length 80)
WhiteLabelService | createBookingFlowDefinition | request | isDefaultForType | boolean |  | At most one per venue and type; setting it takes it from the previous default. (default False)
WhiteLabelService | createBookingFlowDefinition | request | isEnabled | boolean |  | A disabled flow is kept and not published; products naming it fall back to the default. (default True)
WhiteLabelService | createBookingFlowDefinition | request | steps | array of BookingFlowStep |  | Every step of the type, in the venue's order. (max items 30)
WhiteLabelService | createBookingFlowDefinition | request | steps[].id | string (uuid) |  | (read-only)
WhiteLabelService | createBookingFlowDefinition | request | steps[].bookingFlowId | string (uuid) |  | (read-only)
WhiteLabelService | createBookingFlowDefinition | request | steps[].stepKey | BookingFlowStepKey: enum (location, helpMeChoose, product, date, time, performance, level, language, …) | yes | Every step a guest booking flow can hold (decided 29 September, W12).
WhiteLabelService | createBookingFlowDefinition | request | steps[].enabled | boolean | yes | A required step cannot be off; the flow saves and isValid turns false.
WhiteLabelService | createBookingFlowDefinition | request | steps[].sortOrder | integer | yes | (min 0)
WhiteLabelService | createBookingFlowDefinition | request | steps[].requirement | enum (required, optional, conditional) |  | From the flow type, so the CMS can mark the step without a second read. (read-only)
WhiteLabelService | createBookingFlowDefinition | request | steps[].settings | object |  | The step's own settings, by the names the type's stepSettings gives for this step (e.g. (default {})
WhiteLabelService | createBookingFlowDefinition | request | settings | BookingFlowLevelSettings |  | The settings that belong to one flow, not to the venue (decided 29 September, W12).
WhiteLabelService | createBookingFlowDefinition | request | settings.performanceReveal | enum (dateTimeTicket, allAtOnce) |  | Performance reveal (rev 3 REV3-2). (default dateTimeTicket)
WhiteLabelService | createBookingFlowDefinition | request | settings.signInAt | enum (afterAddOns, atPayment) |  | Where the guest is asked to sign in, or for a guest-checkout code (rev 3 REV3-3). (default afterAddOns)
WhiteLabelService | createBookingFlowDefinition | request | settings.seatEventDateMode | enum (inlineStep, popupOnSeatMap) |  | Date and time on a seated event (rev 3 REV3-4). (default inlineStep)
WhiteLabelService | createBookingFlowDefinition | request | settings.extrasStep | enum (auto, always, never) |  | auto shows the extras step only when the cart's products have add-ons; never is the same as turning the optional extras step off. (default auto)
WhiteLabelService | createBookingFlowDefinition | request | settings.quickTour | boolean |  | Quick tour (rev 3 REV3-20). (default False)
WhiteLabelService | createBookingFlowDefinition | request | settings.consentQuestionIds | array of string (uuid) |  | The flow's own consent questions (rev 3 REV3-26). (max items 10; default [])
WhiteLabelService | createBookingFlowDefinition | request | isValid | boolean |  | Whether the flow passes validateBookingFlow; worked out in the same transaction as each write. (read-only)
WhiteLabelService | createBookingFlowDefinition | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | createBookingFlowDefinition | request | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | createBookingFlowDefinition | response | id | string (uuid) |  | (read-only)
WhiteLabelService | createBookingFlowDefinition | response | venueId | string (uuid) |  | From the path of createBookingFlowDefinition. (read-only)
WhiteLabelService | createBookingFlowDefinition | response | flowTypeKey | BookingFlowTypeKey: enum (datedDayPass, timedEntry, openDated, seatedFixedPerformance, seatedDateTimeSeatMap, experienceWorkshop, surfSession, meetingRoomHourly, …) | yes | The flow types the system catalogue offers (decided 29 September, W12; impact.md b).
WhiteLabelService | createBookingFlowDefinition | response | name | string | yes | Staff-facing, e.g. (max length 80)
WhiteLabelService | createBookingFlowDefinition | response | isDefaultForType | boolean |  | At most one per venue and type; setting it takes it from the previous default. (default False)
WhiteLabelService | createBookingFlowDefinition | response | isEnabled | boolean |  | A disabled flow is kept and not published; products naming it fall back to the default. (default True)
WhiteLabelService | createBookingFlowDefinition | response | steps | array of BookingFlowStep |  | Every step of the type, in the venue's order. (max items 30)
WhiteLabelService | createBookingFlowDefinition | response | steps[].id | string (uuid) |  | (read-only)
WhiteLabelService | createBookingFlowDefinition | response | steps[].bookingFlowId | string (uuid) |  | (read-only)
WhiteLabelService | createBookingFlowDefinition | response | steps[].stepKey | BookingFlowStepKey: enum (location, helpMeChoose, product, date, time, performance, level, language, …) | yes | Every step a guest booking flow can hold (decided 29 September, W12).
WhiteLabelService | createBookingFlowDefinition | response | steps[].enabled | boolean | yes | A required step cannot be off; the flow saves and isValid turns false.
WhiteLabelService | createBookingFlowDefinition | response | steps[].sortOrder | integer | yes | (min 0)
WhiteLabelService | createBookingFlowDefinition | response | steps[].requirement | enum (required, optional, conditional) |  | From the flow type, so the CMS can mark the step without a second read. (read-only)
WhiteLabelService | createBookingFlowDefinition | response | steps[].settings | object |  | The step's own settings, by the names the type's stepSettings gives for this step (e.g. (default {})
WhiteLabelService | createBookingFlowDefinition | response | settings | BookingFlowLevelSettings |  | The settings that belong to one flow, not to the venue (decided 29 September, W12).
WhiteLabelService | createBookingFlowDefinition | response | settings.performanceReveal | enum (dateTimeTicket, allAtOnce) |  | Performance reveal (rev 3 REV3-2). (default dateTimeTicket)
WhiteLabelService | createBookingFlowDefinition | response | settings.signInAt | enum (afterAddOns, atPayment) |  | Where the guest is asked to sign in, or for a guest-checkout code (rev 3 REV3-3). (default afterAddOns)
WhiteLabelService | createBookingFlowDefinition | response | settings.seatEventDateMode | enum (inlineStep, popupOnSeatMap) |  | Date and time on a seated event (rev 3 REV3-4). (default inlineStep)
WhiteLabelService | createBookingFlowDefinition | response | settings.extrasStep | enum (auto, always, never) |  | auto shows the extras step only when the cart's products have add-ons; never is the same as turning the optional extras step off. (default auto)
WhiteLabelService | createBookingFlowDefinition | response | settings.quickTour | boolean |  | Quick tour (rev 3 REV3-20). (default False)
WhiteLabelService | createBookingFlowDefinition | response | settings.consentQuestionIds | array of string (uuid) |  | The flow's own consent questions (rev 3 REV3-26). (max items 10; default [])
WhiteLabelService | createBookingFlowDefinition | response | isValid | boolean |  | Whether the flow passes validateBookingFlow; worked out in the same transaction as each write. (read-only)
WhiteLabelService | createBookingFlowDefinition | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | createBookingFlowDefinition | response | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | createBookingFlowDefinition | param (path) | venueId | string (uuid) | yes
WhiteLabelService | createBookingFlowDefinition | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | createBundle | request | code | string | yes | (max length 64)
CatalogueService | createBundle | request | name | string | yes | (max length 200)
CatalogueService | createBundle | request | description | string |  | (max length 1000)
CatalogueService | createBundle | request | venueId | string (uuid) | yes
CatalogueService | createBundle | request | kind | BundleKind: enum (fixed, dynamic, mandatory, optional, promotional) | yes
CatalogueService | createBundle | request | price | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | createBundle | request | price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createBundle | request | price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createBundle | request | price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createBundle | request | components | array of BundleComponent | yes | (min items 0)
CatalogueService | createBundle | request | components[].id | string (uuid) |  | Added 20 August. (read-only)
CatalogueService | createBundle | request | components[].variantId | string (uuid) | yes
CatalogueService | createBundle | request | components[].componentKind | BundleComponentKind: enum (admission, fnbMenuItem, retail, addOn, other) |  | What a bundle component entitles the guest to (decided 29 September, MOB-4). (default admission)
CatalogueService | createBundle | request | components[].menuItemId | string (uuid) |  | The F&B menu item a fnbMenuItem component entitles the guest to (decided 29 September, MOB-4): the meal of a *meal combo with admission*. (nullable)
CatalogueService | createBundle | request | components[].redeemAtOutletIds | array of string (uuid) |  | Outlets that redeem an fnbMenuItem component; empty means any outlet of the component's venue that has the menu item on a live menu (MOB-4). (max items 20)
CatalogueService | createBundle | request | components[].quantity | integer | yes | (min 1)
CatalogueService | createBundle | request | components[].isOptional | boolean |  | (default False)
CatalogueService | createBundle | request | components[].substituteVariantIds | array of string (uuid) |  | For dynamic bundles — guest chooses among these.
CatalogueService | createBundle | request | components[].substitutionTriggers | array of enum (soldOut, capacityExhausted, productSuspended, venueClosed, externalApiUnavailable, inventoryBelowThreshold) |  | When a substitute from substituteVariantIds may replace this component (Dynamic Component Substitution Engine). (nullable)
CatalogueService | createBundle | request | components[].substitutionPriceEffect | enum (samePrice, surcharge, reducedPrice) |  | What a substitution does to the bundle price. (default samePrice)
CatalogueService | createBundle | request | components[].substitutionApproval | enum (none, customer, operator) |  | Who must accept a substitution before it stands. (default customer)
CatalogueService | createBundle | request | components[].venueId | string (uuid) |  | Where this component is redeemed. (nullable)
CatalogueService | createBundle | request | choiceGroups | array of BundleChoiceGroup |  | Dynamic bundles (3.5.10).
CatalogueService | createBundle | request | choiceGroups[].id | string (uuid) |  | (read-only)
CatalogueService | createBundle | request | choiceGroups[].label | string | yes | What the guest is asked.
CatalogueService | createBundle | request | choiceGroups[].choose | integer | yes | How many options the guest picks. (min 1)
CatalogueService | createBundle | request | choiceGroups[].allowDuplicates | boolean |  | Whether the same option may be picked twice. (default False)
CatalogueService | createBundle | request | choiceGroups[].options | array of object | yes | The rows of promotions.bundle_choice_option, one per option, each keyed to its group. (min items 2)
CatalogueService | createBundle | request | choiceGroups[].options[].id | string (uuid) |  | (read-only)
CatalogueService | createBundle | request | choiceGroups[].options[].variantId | string (uuid) | yes
CatalogueService | createBundle | request | choiceGroups[].options[].quantity | integer |  | (default 1)
CatalogueService | createBundle | request | choiceGroups[].options[].isDefault | boolean |  | (default False)
CatalogueService | createBundle | request | choiceGroups[].unavailableBehaviour | enum (hideOption, hideBundle) |  | An option that has sold out for the chosen date is not offered. (default hideOption)
CatalogueService | createBundle | request | allocation | object | yes
CatalogueService | createBundle | request | allocation.method | object | yes | Proportional to list price by default. (default proRataListPrice)
CatalogueService | createBundle | request | allocation.components | array of AllocationComponent | yes
CatalogueService | createBundle | request | allocation.components[].id | string (uuid) |  | Added 20 August. (read-only)
CatalogueService | createBundle | request | allocation.components[].variantId | string (uuid) | yes
CatalogueService | createBundle | request | allocation.components[].percentage | number |  | (min 0; max 100)
CatalogueService | createBundle | request | allocation.components[].fixedAmount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createBundle | request | allocation.components[].listPrice | object |  | For proRataListPrice — weights derived from list prices.
CatalogueService | createBundle | request | allocation.components[].revenueAccountId | string (uuid)
CatalogueService | createBundle | request | allocation.components[].legalEntityId | string (uuid) |  | Set where the component is earned by a different legal entity. (nullable)
CatalogueService | createBundle | request | allocation.components[].venueId | string (uuid) |  | (nullable)
CatalogueService | createBundle | request | validFrom | string (date-time)
CatalogueService | createBundle | request | validTo | string (date-time)
CatalogueService | createBundle | request | campaignId | string (uuid) |  | The commercial campaign (promotions.campaign) the bundle is sold under. (nullable)
CatalogueService | createBundle | request | ownerPrincipalId | string (uuid) |  | The bundle owner (Bundle Definition & Setup). (nullable)
CatalogueService | createBundle | request | category | string |  | The bundle category the setup screen files it under. (max length 100; nullable)
CatalogueService | createBundle | request | isStandaloneProduct | boolean |  | Whether the bundle appears as a product in its own right, or only as an offer on another product. (default True)
CatalogueService | createBundle | request | isRecommendedAtCheckout | boolean |  | Whether checkout recommends the bundle. (default False)
CatalogueService | createBundle | request | requiredVariantIds | array of string (uuid) |  | Products that must already be in the basket for the bundle to be sold (the setup screen's "requires another product"). (nullable)
CatalogueService | createBundle | response | code | string | yes | (max length 64)
CatalogueService | createBundle | response | name | string | yes | (max length 200)
CatalogueService | createBundle | response | description | string |  | (max length 1000)
CatalogueService | createBundle | response | venueId | string (uuid) | yes
CatalogueService | createBundle | response | kind | BundleKind: enum (fixed, dynamic, mandatory, optional, promotional) | yes
CatalogueService | createBundle | response | price | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | createBundle | response | price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createBundle | response | price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createBundle | response | price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createBundle | response | components | array of BundleComponent | yes | (min items 0)
CatalogueService | createBundle | response | components[].id | string (uuid) |  | Added 20 August. (read-only)
CatalogueService | createBundle | response | components[].variantId | string (uuid) | yes
CatalogueService | createBundle | response | components[].componentKind | BundleComponentKind: enum (admission, fnbMenuItem, retail, addOn, other) |  | What a bundle component entitles the guest to (decided 29 September, MOB-4). (default admission)
CatalogueService | createBundle | response | components[].menuItemId | string (uuid) |  | The F&B menu item a fnbMenuItem component entitles the guest to (decided 29 September, MOB-4): the meal of a *meal combo with admission*. (nullable)
CatalogueService | createBundle | response | components[].redeemAtOutletIds | array of string (uuid) |  | Outlets that redeem an fnbMenuItem component; empty means any outlet of the component's venue that has the menu item on a live menu (MOB-4). (max items 20)
CatalogueService | createBundle | response | components[].quantity | integer | yes | (min 1)
CatalogueService | createBundle | response | components[].isOptional | boolean |  | (default False)
CatalogueService | createBundle | response | components[].substituteVariantIds | array of string (uuid) |  | For dynamic bundles — guest chooses among these.
CatalogueService | createBundle | response | components[].substitutionTriggers | array of enum (soldOut, capacityExhausted, productSuspended, venueClosed, externalApiUnavailable, inventoryBelowThreshold) |  | When a substitute from substituteVariantIds may replace this component (Dynamic Component Substitution Engine). (nullable)
CatalogueService | createBundle | response | components[].substitutionPriceEffect | enum (samePrice, surcharge, reducedPrice) |  | What a substitution does to the bundle price. (default samePrice)
CatalogueService | createBundle | response | components[].substitutionApproval | enum (none, customer, operator) |  | Who must accept a substitution before it stands. (default customer)
CatalogueService | createBundle | response | components[].venueId | string (uuid) |  | Where this component is redeemed. (nullable)
CatalogueService | createBundle | response | choiceGroups | array of BundleChoiceGroup |  | Dynamic bundles (3.5.10).
CatalogueService | createBundle | response | choiceGroups[].id | string (uuid) |  | (read-only)
CatalogueService | createBundle | response | choiceGroups[].label | string | yes | What the guest is asked.
CatalogueService | createBundle | response | choiceGroups[].choose | integer | yes | How many options the guest picks. (min 1)
CatalogueService | createBundle | response | choiceGroups[].allowDuplicates | boolean |  | Whether the same option may be picked twice. (default False)
CatalogueService | createBundle | response | choiceGroups[].options | array of object | yes | The rows of promotions.bundle_choice_option, one per option, each keyed to its group. (min items 2)
CatalogueService | createBundle | response | choiceGroups[].options[].id | string (uuid) |  | (read-only)
CatalogueService | createBundle | response | choiceGroups[].options[].variantId | string (uuid) | yes
CatalogueService | createBundle | response | choiceGroups[].options[].quantity | integer |  | (default 1)
CatalogueService | createBundle | response | choiceGroups[].options[].isDefault | boolean |  | (default False)
CatalogueService | createBundle | response | choiceGroups[].unavailableBehaviour | enum (hideOption, hideBundle) |  | An option that has sold out for the chosen date is not offered. (default hideOption)
CatalogueService | createBundle | response | allocation | object | yes
CatalogueService | createBundle | response | allocation.method | object | yes | Proportional to list price by default. (default proRataListPrice)
CatalogueService | createBundle | response | allocation.components | array of AllocationComponent | yes
CatalogueService | createBundle | response | allocation.components[].id | string (uuid) |  | Added 20 August. (read-only)
CatalogueService | createBundle | response | allocation.components[].variantId | string (uuid) | yes
CatalogueService | createBundle | response | allocation.components[].percentage | number |  | (min 0; max 100)
CatalogueService | createBundle | response | allocation.components[].fixedAmount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createBundle | response | allocation.components[].listPrice | object |  | For proRataListPrice — weights derived from list prices.
CatalogueService | createBundle | response | allocation.components[].revenueAccountId | string (uuid)
CatalogueService | createBundle | response | allocation.components[].legalEntityId | string (uuid) |  | Set where the component is earned by a different legal entity. (nullable)
CatalogueService | createBundle | response | allocation.components[].venueId | string (uuid) |  | (nullable)
CatalogueService | createBundle | response | validFrom | string (date-time)
CatalogueService | createBundle | response | validTo | string (date-time)
CatalogueService | createBundle | response | campaignId | string (uuid) |  | The commercial campaign (promotions.campaign) the bundle is sold under. (nullable)
CatalogueService | createBundle | response | ownerPrincipalId | string (uuid) |  | The bundle owner (Bundle Definition & Setup). (nullable)
CatalogueService | createBundle | response | category | string |  | The bundle category the setup screen files it under. (max length 100; nullable)
CatalogueService | createBundle | response | isStandaloneProduct | boolean |  | Whether the bundle appears as a product in its own right, or only as an offer on another product. (default True)
CatalogueService | createBundle | response | isRecommendedAtCheckout | boolean |  | Whether checkout recommends the bundle. (default False)
CatalogueService | createBundle | response | requiredVariantIds | array of string (uuid) |  | Products that must already be in the basket for the bundle to be sold (the setup screen's "requires another product"). (nullable)
CatalogueService | createBundle | response | id | string (uuid) | yes
CatalogueService | createBundle | response | savingsAmount | object | yes | Sum of component list prices less the bundle price.
CatalogueService | createBundle | response | savingsAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createBundle | response | savingsAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createBundle | response | savingsAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createBundle | response | savingsPercentage | number
CatalogueService | createBundle | response | hasBeenSold | boolean | yes | True locks components and allocation against amendment.
CatalogueService | createBundle | response | isActive | boolean | yes
CatalogueService | createBundle | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | createCampaign | request | name | string | yes | (max length 200)
MarketingService | createCampaign | request | kind | CampaignKind: enum (oneOff, scheduled, triggered, recurring) | yes
MarketingService | createCampaign | request | channel | MessageChannel: enum (email, sms, whatsapp, push, inApp, post) | yes
MarketingService | createCampaign | request | venueId | string (uuid)
MarketingService | createCampaign | request | segmentId | string (uuid) | yes
MarketingService | createCampaign | request | content | CampaignContent | yes
MarketingService | createCampaign | request | content.templateId | string (uuid) | yes
MarketingService | createCampaign | request | content.subjectOverride | object
MarketingService | createCampaign | request | content.mergeDefaults | object |  | Fallback values for the template's mergeFields, by name, used where a guest has no value.
MarketingService | createCampaign | request | content.promotionId | string (uuid) |  | Offer carried by the campaign. (nullable)
MarketingService | createCampaign | request | trigger | CampaignTrigger
MarketingService | createCampaign | request | trigger.event | enum (bookingConfirmed, visitCompleted, membershipExpiring, birthday, abandonedCart, firstVisit, inactivity, entitlementExpiring) |  | entitlementExpiring (29 September, build pass, group G2; 5.5.30) fires on entitlement.expiringSoon: a ticket or pass the guest still holds comes within its template's expiryNoticeDays of validTo.
MarketingService | createCampaign | request | trigger.delayHours | integer
MarketingService | createCampaign | request | trigger.conditions | array of SegmentCriterion
MarketingService | createCampaign | request | trigger.conditions[].attribute | string | yes | Behavioural or profile attribute — visit count, last visit, lifetime value, product purchased, membership tier, venue visited, language.
MarketingService | createCampaign | request | trigger.conditions[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, exists, …) | yes
MarketingService | createCampaign | request | trigger.conditions[].value | object
MarketingService | createCampaign | request | trigger.conditions[].values | array of object
MarketingService | createCampaign | request | scheduledFor | string (date-time)
MarketingService | createCampaign | request | consentPurpose | object |  | (default marketing)
MarketingService | createCampaign | request | sendWindow | object |  | Hours during which sending is permitted.
MarketingService | createCampaign | request | sendWindow.startTime | string
MarketingService | createCampaign | request | sendWindow.endTime | string
MarketingService | createCampaign | request | sendWindow.timeZone | string
MarketingService | createCampaign | request | sendTimeMode | enum (fixed, optimised) |  | optimised sends each recipient at the hour ai.requestSuggestion (kind sendTime) gives for them, inside sendWindow (29 September, build pass, group G2; 22.3.19). (default fixed)
MarketingService | createCampaign | request | optimiseChannel | boolean |  | With sendTimeMode optimised, route each recipient to the channel the suggestion names, among the channels they consented to (22.9.16). (default False)
MarketingService | createCampaign | request | variants | array of MarketingCampaignVariant |  | A/B (or up to five-way) content and subject variants (29 September, build pass, group G2; 22.1.17, BO-772). (max items 5; nullable)
MarketingService | createCampaign | request | variants[].id | string (uuid) |  | (read-only)
MarketingService | createCampaign | request | variants[].campaignId | string (uuid) |  | (read-only)
MarketingService | createCampaign | request | variants[].label | string | yes | A, B, C... (max length 20)
MarketingService | createCampaign | request | variants[].subjectOverride | object |  | Subject line by locale. (nullable)
MarketingService | createCampaign | request | variants[].templateId | string (uuid) |  | A different template for this variant; null uses the campaign's content.templateId. (nullable)
MarketingService | createCampaign | request | variants[].splitPercent | integer |  | Share of the test group; null splits evenly. (min 1; max 100; nullable)
MarketingService | createCampaign | request | variants[].source | enum (manual, aiDraft) |  | (default manual)
MarketingService | createCampaign | request | variants[].aiDecisionRecordId | string |  | The decision record of the ai.proposeMarketingContent draft it came from, for aiDraft. (nullable)
MarketingService | createCampaign | request | variants[].isWinner | boolean |  | (default False; read-only)
MarketingService | createCampaign | request | variants[].scopePath | string |  | The partition key (ADR-0005), the campaign's. (read-only)
MarketingService | createCampaign | request | abTest | object |  | How the variants are tested. (nullable)
MarketingService | createCampaign | request | abTest.testPercent | integer |  | Share of the audience the variants are tested on; 100 splits everyone and picks no winner. (min 5; max 100; default 20)
MarketingService | createCampaign | request | abTest.successMetric | enum (openRate, clickRate, conversionRate, attributedRevenue) |  | (default clickRate)
MarketingService | createCampaign | request | abTest.decideAfterHours | integer |  | (min 1; max 168; default 4)
MarketingService | createCampaign | request | abTest.winnerRule | enum (automatic, manual) |  | (default automatic)
MarketingService | createCampaign | request | abTest.minimumSamplePerVariant | integer |  | Below this many sends per variant no winner is declared automatically; a person picks. (min 1; default 500)
MarketingService | createCampaign | request | abTest.winningVariantId | string (uuid) |  | Set by the automatic rule, or by a person through updateCampaign. (nullable)
MarketingService | createCampaign | response | name | string | yes | (max length 200)
MarketingService | createCampaign | response | kind | CampaignKind: enum (oneOff, scheduled, triggered, recurring) | yes
MarketingService | createCampaign | response | channel | MessageChannel: enum (email, sms, whatsapp, push, inApp, post) | yes
MarketingService | createCampaign | response | venueId | string (uuid)
MarketingService | createCampaign | response | segmentId | string (uuid) | yes
MarketingService | createCampaign | response | content | CampaignContent | yes
MarketingService | createCampaign | response | content.templateId | string (uuid) | yes
MarketingService | createCampaign | response | content.subjectOverride | object
MarketingService | createCampaign | response | content.mergeDefaults | object |  | Fallback values for the template's mergeFields, by name, used where a guest has no value.
MarketingService | createCampaign | response | content.promotionId | string (uuid) |  | Offer carried by the campaign. (nullable)
MarketingService | createCampaign | response | trigger | CampaignTrigger
MarketingService | createCampaign | response | trigger.event | enum (bookingConfirmed, visitCompleted, membershipExpiring, birthday, abandonedCart, firstVisit, inactivity, entitlementExpiring) |  | entitlementExpiring (29 September, build pass, group G2; 5.5.30) fires on entitlement.expiringSoon: a ticket or pass the guest still holds comes within its template's expiryNoticeDays of validTo.
MarketingService | createCampaign | response | trigger.delayHours | integer
MarketingService | createCampaign | response | trigger.conditions | array of SegmentCriterion
MarketingService | createCampaign | response | trigger.conditions[].attribute | string | yes | Behavioural or profile attribute — visit count, last visit, lifetime value, product purchased, membership tier, venue visited, language.
MarketingService | createCampaign | response | trigger.conditions[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, exists, …) | yes
MarketingService | createCampaign | response | trigger.conditions[].value | object
MarketingService | createCampaign | response | trigger.conditions[].values | array of object
MarketingService | createCampaign | response | scheduledFor | string (date-time)
MarketingService | createCampaign | response | consentPurpose | object |  | (default marketing)
MarketingService | createCampaign | response | sendWindow | object |  | Hours during which sending is permitted.
MarketingService | createCampaign | response | sendWindow.startTime | string
MarketingService | createCampaign | response | sendWindow.endTime | string
MarketingService | createCampaign | response | sendWindow.timeZone | string
MarketingService | createCampaign | response | sendTimeMode | enum (fixed, optimised) |  | optimised sends each recipient at the hour ai.requestSuggestion (kind sendTime) gives for them, inside sendWindow (29 September, build pass, group G2; 22.3.19). (default fixed)
MarketingService | createCampaign | response | optimiseChannel | boolean |  | With sendTimeMode optimised, route each recipient to the channel the suggestion names, among the channels they consented to (22.9.16). (default False)
MarketingService | createCampaign | response | variants | array of MarketingCampaignVariant |  | A/B (or up to five-way) content and subject variants (29 September, build pass, group G2; 22.1.17, BO-772). (max items 5; nullable)
MarketingService | createCampaign | response | variants[].id | string (uuid) |  | (read-only)
MarketingService | createCampaign | response | variants[].campaignId | string (uuid) |  | (read-only)
MarketingService | createCampaign | response | variants[].label | string | yes | A, B, C... (max length 20)
MarketingService | createCampaign | response | variants[].subjectOverride | object |  | Subject line by locale. (nullable)
MarketingService | createCampaign | response | variants[].templateId | string (uuid) |  | A different template for this variant; null uses the campaign's content.templateId. (nullable)
MarketingService | createCampaign | response | variants[].splitPercent | integer |  | Share of the test group; null splits evenly. (min 1; max 100; nullable)
MarketingService | createCampaign | response | variants[].source | enum (manual, aiDraft) |  | (default manual)
MarketingService | createCampaign | response | variants[].aiDecisionRecordId | string |  | The decision record of the ai.proposeMarketingContent draft it came from, for aiDraft. (nullable)
MarketingService | createCampaign | response | variants[].isWinner | boolean |  | (default False; read-only)
MarketingService | createCampaign | response | variants[].scopePath | string |  | The partition key (ADR-0005), the campaign's. (read-only)
MarketingService | createCampaign | response | abTest | object |  | How the variants are tested. (nullable)
MarketingService | createCampaign | response | abTest.testPercent | integer |  | Share of the audience the variants are tested on; 100 splits everyone and picks no winner. (min 5; max 100; default 20)
MarketingService | createCampaign | response | abTest.successMetric | enum (openRate, clickRate, conversionRate, attributedRevenue) |  | (default clickRate)
MarketingService | createCampaign | response | abTest.decideAfterHours | integer |  | (min 1; max 168; default 4)
MarketingService | createCampaign | response | abTest.winnerRule | enum (automatic, manual) |  | (default automatic)
MarketingService | createCampaign | response | abTest.minimumSamplePerVariant | integer |  | Below this many sends per variant no winner is declared automatically; a person picks. (min 1; default 500)
MarketingService | createCampaign | response | abTest.winningVariantId | string (uuid) |  | Set by the automatic rule, or by a person through updateCampaign. (nullable)
MarketingService | createCampaign | response | id | string (uuid) | yes
MarketingService | createCampaign | response | budgetCap | Money |  | On the wire this is three fields; in the database it is one column.
MarketingService | createCampaign | response | budgetCap.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
MarketingService | createCampaign | response | budgetCap.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
MarketingService | createCampaign | response | budgetCap.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
MarketingService | createCampaign | response | budgetSpent | object |  | BL-169. (read-only)
MarketingService | createCampaign | response | budgetSpent.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
MarketingService | createCampaign | response | budgetSpent.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
MarketingService | createCampaign | response | budgetSpent.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
MarketingService | createCampaign | response | status | CampaignStatus: enum (draft, scheduled, sending, paused, completed, stopped, failed) | yes
MarketingService | createCampaign | response | isPaused | boolean
MarketingService | createCampaign | response | createdByPrincipalId | string (uuid)
MarketingService | createCampaign | response | createdAt | string (date-time) | yes
MarketingService | createCampaign | response | launchedAt | string (date-time) |  | (nullable)
MarketingService | createCampaign | response | completedAt | string (date-time) |  | (nullable)
MarketingService | createCampaign | response | sentCount | integer |  | How many messages went out, counted from marketing.message_dispatch at read time rather than kept as a counter on the campaign row, so it cannot drift from the dispatch records it summarises. (read-only)
MarketingService | createCampaign | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createCart | request | venueId | string (uuid) | yes
OrderService | createCart | request | channel | SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) | yes | Where a sale came from.
OrderService | createCart | request | subjectId | string (uuid) |  | (nullable)
OrderService | createCart | request | locale | string
OrderService | createCart | response | id | string (uuid) | yes
OrderService | createCart | response | token | string |  | How an anonymous guest returns to their cart, including from a recovery email. (read-only)
OrderService | createCart | response | venueId | string (uuid) | yes
OrderService | createCart | response | channel | SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) | yes | Where a sale came from.
OrderService | createCart | response | subjectId | string (uuid) |  | Null while anonymous. (nullable)
OrderService | createCart | response | status | CartStatus: enum (active, expiring, expired, abandoned, checkedOut) | yes
OrderService | createCart | response | lines | array of CartLine | yes
OrderService | createCart | response | lines[].id | string (uuid) | yes
OrderService | createCart | response | lines[].variantId | string (uuid) | yes
OrderService | createCart | response | lines[].productName | string |  | (read-only)
OrderService | createCart | response | lines[].quantity | integer | yes | (min 1)
OrderService | createCart | response | lines[].performanceId | string (uuid) |  | (nullable)
OrderService | createCart | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | createCart | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | createCart | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | createCart | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | createCart | response | lines[].tableReservationId | string (uuid) |  | Set on a table deposit line only (decided 29 September, rev 3 REV3-8b): the fnb.TableReservation this line secures. (nullable)
OrderService | createCart | response | lines[].seatIds | array of string (uuid) |  | (max items 50)
OrderService | createCart | response | lines[].resourceHoldId | string (uuid) |  | The resources.ResourceHold this line buys (decided 29 September, rev 3 REV3-15). (nullable)
OrderService | createCart | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | createCart | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | createCart | response | lines[].parentLineId | string (uuid) |  | The line this add-on is attached to, from AddCartLineRequest.parentLineId. (nullable)
OrderService | createCart | response | lines[].overridePrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | createCart | response | lines[].overridePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createCart | response | lines[].overridePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createCart | response | lines[].overridePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createCart | response | lines[].overrideReason | enum (priceMatch, serviceRecovery, negotiated, damagedGoods, staffSale, error) |  | BL-085. (nullable)
OrderService | createCart | response | lines[].feeKind | enum (booking, transaction, service, delivery, convenience, cancellation) |  | A fee is a line, not an adjustment. (nullable)
OrderService | createCart | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | createCart | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createCart | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createCart | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createCart | response | lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | createCart | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createCart | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createCart | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createCart | response | lines[].inventoryHoldId | string |  | The capacity held for this line — a catalogue.InventoryHold.id, typed as that id is. (nullable)
OrderService | createCart | response | lines[].leaseExpiresAt | string (date-time) |  | Shown to the guest. (nullable)
OrderService | createCart | response | lines[].isAvailable | boolean |  | Re-checked on every read. (read-only)
OrderService | createCart | response | conflicts | array of CartConflict
OrderService | createCart | response | conflicts[].kind | enum (overlappingTime, sameSessionDifferentVenue, exceedsPartySize, requiresPrerequisite, consentBlocksBooking)
OrderService | createCart | response | conflicts[].lineIds | array of string (uuid)
OrderService | createCart | response | conflicts[].message | string
OrderService | createCart | response | conflicts[].isBlocking | boolean |  | Most are not.
OrderService | createCart | response | consentQuestions | array of object |  | The consent questions this cart's products and flow ask (decided 29 September, rev 3 REV3-26), computed on read at their current version as the union of each line's published booking flow's white-lab… (read-only)
OrderService | createCart | response | consentQuestions[].id | string (uuid) | yes | (read-only)
OrderService | createCart | response | consentQuestions[].kind | ConsentQuestionKind: enum (swim, scuba, risk, custom) | yes | What the question is about (decided 29 September, rev 3 REV3-26).
OrderService | createCart | response | consentQuestions[].text | object | yes | The question as the guest reads it, per locale.
OrderService | createCart | response | consentQuestions[].helpText | object |  | (nullable)
OrderService | createCart | response | consentQuestions[].version | integer | yes | Raised by one each time the question changes (updateConsentQuestion). (min 1; read-only)
OrderService | createCart | response | consentQuestions[].scope | enum (perPerson, perBooking) | yes | Asked for each declared person, or once for the whole booking. (default perPerson)
OrderService | createCart | response | consentQuestions[].required | boolean | yes | Checkout waits until it is answered (orders.checkoutCart 422 consentRequired). (default True)
OrderService | createCart | response | consentQuestions[].blockingAnswer | enum (yes, no, none) | yes | The answer that stops the booking, for the person or the booking it covers. (default none)
OrderService | createCart | response | consentQuestions[].status | enum (active, retired) | yes | (default active)
OrderService | createCart | response | consentQuestions[].scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | createCart | response | consentQuestions[].updatedAt | string (date-time) |  | (read-only)
OrderService | createCart | response | consentQuestions[].lineIds | array of string (uuid) |  | The cart lines that ask it.
OrderService | createCart | response | consentQuestions[].answered | boolean |  | Every person (for perPerson) or the booking (for perBooking) has an answer.
OrderService | createCart | response | subtotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | createCart | response | subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createCart | response | subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createCart | response | subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createCart | response | discountTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | createCart | response | discountTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createCart | response | discountTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createCart | response | discountTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createCart | response | taxTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | createCart | response | taxTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createCart | response | taxTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createCart | response | taxTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createCart | response | total | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | createCart | response | total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createCart | response | total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createCart | response | total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createCart | response | appliedPromotionIds | array of string (uuid) |  | Re-evaluated on every read.
OrderService | createCart | response | couponCodes | array of string |  | The promo codes the guest entered through applyCartPromoCode (decided 28 September, audit R073 (e)). (read-only)
OrderService | createCart | response | expiresAt | string (date-time) |  | The earliest lease expiry in the cart, or the cart's own window where it holds none.
OrderService | createCart | response | extensionsUsed | integer |  | (read-only)
OrderService | createCart | response | maxExtensions | integer |  | (read-only)
OrderService | createCart | response | locale | string
OrderService | createCart | response | createdAt | string (date-time)
OrderService | createCart | response | updatedAt | string (date-time)
OrderService | createCart | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createCashMovement | request | id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createCashMovement | request | kind | CashMovementKind: enum (openingFloat, lift, add) | yes | openingFloat is written by openShift; lift by createCashMovement and by withdrawFromDepositBox, which is a lift from one cashier's box; add by createCashMovement.
OrderService | createCashMovement | request | amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createCashMovement | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createCashMovement | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createCashMovement | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createCashMovement | request | denominations | array of CashCountLine |  | A count is a list of lines and the line is the row. (min items 1)
OrderService | createCashMovement | request | denominations[].id | string (uuid)
OrderService | createCashMovement | request | denominations[].shiftId | string (uuid) | yes | A UUIDv7, as Shift.id and orders.pos_shift.id are.
OrderService | createCashMovement | request | denominations[].depositBoxId | string (uuid) |  | (nullable)
OrderService | createCashMovement | request | denominations[].countKind | enum (openingFloat, close, movement) |  | Which count this line belongs to — the opening float (openShift), the close (closeShift) or a lift or add (createCashMovement).
OrderService | createCashMovement | request | denominations[].cashMovementId | string (uuid) |  | The movement this line counts, where countKind is movement. (nullable)
OrderService | createCashMovement | request | denominations[].denominationId | string (uuid) | yes | References platform.denomination — face value, kind and sort order live there.
OrderService | createCashMovement | request | denominations[].countedQuantity | integer | yes | How many of this note or coin were in the drawer. (min 0)
OrderService | createCashMovement | request | denominations[].countedValue | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | createCashMovement | request | denominations[].countedValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createCashMovement | request | denominations[].countedValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createCashMovement | request | denominations[].countedValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createCashMovement | request | denominations[].countedBy | string (uuid) |  | (nullable)
OrderService | createCashMovement | request | denominations[].countedAt | string (date-time)
OrderService | createCashMovement | request | denominations[].recountOf | string (uuid) |  | A recount points at what it replaces rather than overwriting it. (nullable)
OrderService | createCashMovement | request | reference | string |  | Safe drop reference or bag number. (max length 64)
OrderService | createCashMovement | request | reason | string |  | (max length 500)
OrderService | createCashMovement | request | recordedAt | string (date-time) | yes
OrderService | createCashMovement | response | id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createCashMovement | response | kind | CashMovementKind: enum (openingFloat, lift, add) | yes | openingFloat is written by openShift; lift by createCashMovement and by withdrawFromDepositBox, which is a lift from one cashier's box; add by createCashMovement.
OrderService | createCashMovement | response | amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createCashMovement | response | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createCashMovement | response | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createCashMovement | response | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createCashMovement | response | denominations | array of CashCountLine |  | A count is a list of lines and the line is the row. (min items 1)
OrderService | createCashMovement | response | denominations[].id | string (uuid)
OrderService | createCashMovement | response | denominations[].shiftId | string (uuid) | yes | A UUIDv7, as Shift.id and orders.pos_shift.id are.
OrderService | createCashMovement | response | denominations[].depositBoxId | string (uuid) |  | (nullable)
OrderService | createCashMovement | response | denominations[].countKind | enum (openingFloat, close, movement) |  | Which count this line belongs to — the opening float (openShift), the close (closeShift) or a lift or add (createCashMovement).
OrderService | createCashMovement | response | denominations[].cashMovementId | string (uuid) |  | The movement this line counts, where countKind is movement. (nullable)
OrderService | createCashMovement | response | denominations[].denominationId | string (uuid) | yes | References platform.denomination — face value, kind and sort order live there.
OrderService | createCashMovement | response | denominations[].countedQuantity | integer | yes | How many of this note or coin were in the drawer. (min 0)
OrderService | createCashMovement | response | denominations[].countedValue | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | createCashMovement | response | denominations[].countedValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createCashMovement | response | denominations[].countedValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createCashMovement | response | denominations[].countedValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createCashMovement | response | denominations[].countedBy | string (uuid) |  | (nullable)
OrderService | createCashMovement | response | denominations[].countedAt | string (date-time)
OrderService | createCashMovement | response | denominations[].recountOf | string (uuid) |  | A recount points at what it replaces rather than overwriting it. (nullable)
OrderService | createCashMovement | response | reference | string |  | Safe drop reference or bag number. (max length 64)
OrderService | createCashMovement | response | reason | string |  | (max length 500)
OrderService | createCashMovement | response | recordedAt | string (date-time) | yes
OrderService | createCashMovement | response | shiftId | string (uuid) | yes
OrderService | createCashMovement | response | depositBoxId | string (uuid) |  | The box the cash moved in or out of. (nullable)
OrderService | createCashMovement | response | witnessPrincipalId | string (uuid) |  | The cashier who countersigned a withdrawal. (nullable)
OrderService | createCashMovement | response | withdrawalReason | object |  | (nullable)
OrderService | createCashMovement | response | authorisedByPrincipalId | string (uuid) | yes | The principal who authorised the movement, recorded for audit.
OrderService | createCashMovement | response | sequence | integer | yes | Monotonic within the shift.
OrderService | createCashMovement | response | syncedAt | string (date-time) |  | (nullable)
OrderService | createCashMovement | param (path) | shiftId | string (uuid) | yes
OrderService | createCashMovement | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | createChallenge | request | id | string (uuid) | yes | (read-only)
MarketingService | createChallenge | request | name | string | yes
MarketingService | createChallenge | request | kind | enum (visit, spend, ride, collection, streak, referral, survey, social, …) | yes | What an entrant does to progress.
MarketingService | createChallenge | request | scope | enum (individual, family, group, team) |  | 22.6.7 and 22.6.8. (default individual)
MarketingService | createChallenge | request | goal | object | yes | What completes it.
MarketingService | createChallenge | request | goal.metric | string
MarketingService | createChallenge | request | goal.target | number
MarketingService | createChallenge | request | goal.withinDays | integer |  | (nullable)
MarketingService | createChallenge | request | eventId | string (uuid) |  | (nullable)
MarketingService | createChallenge | request | rewardKind | enum (badge, loyaltyPoints, walletCredit, voucher, entitlement, none) |  | 22.6.13.
MarketingService | createChallenge | request | rewardValue | integer |  | Points, for rewardKind: loyaltyPoints only. (min 1; nullable)
MarketingService | createChallenge | request | rewardAmount | object |  | The credit, for rewardKind: walletCredit only. (nullable)
MarketingService | createChallenge | request | rewardAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
MarketingService | createChallenge | request | rewardAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
MarketingService | createChallenge | request | rewardAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
MarketingService | createChallenge | request | badgeAssetId | string (uuid) |  | (nullable)
MarketingService | createChallenge | request | startsAt | string (date-time)
MarketingService | createChallenge | request | endsAt | string (date-time) |  | (nullable)
MarketingService | createChallenge | request | status | enum (draft, active, paused, ended, archived) | yes | (read-only)
MarketingService | createChallenge | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | createChallenge | response | id | string (uuid) | yes | (read-only)
MarketingService | createChallenge | response | name | string | yes
MarketingService | createChallenge | response | kind | enum (visit, spend, ride, collection, streak, referral, survey, social, …) | yes | What an entrant does to progress.
MarketingService | createChallenge | response | scope | enum (individual, family, group, team) |  | 22.6.7 and 22.6.8. (default individual)
MarketingService | createChallenge | response | goal | object | yes | What completes it.
MarketingService | createChallenge | response | goal.metric | string
MarketingService | createChallenge | response | goal.target | number
MarketingService | createChallenge | response | goal.withinDays | integer |  | (nullable)
MarketingService | createChallenge | response | eventId | string (uuid) |  | (nullable)
MarketingService | createChallenge | response | rewardKind | enum (badge, loyaltyPoints, walletCredit, voucher, entitlement, none) |  | 22.6.13.
MarketingService | createChallenge | response | rewardValue | integer |  | Points, for rewardKind: loyaltyPoints only. (min 1; nullable)
MarketingService | createChallenge | response | rewardAmount | object |  | The credit, for rewardKind: walletCredit only. (nullable)
MarketingService | createChallenge | response | rewardAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
MarketingService | createChallenge | response | rewardAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
MarketingService | createChallenge | response | rewardAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
MarketingService | createChallenge | response | badgeAssetId | string (uuid) |  | (nullable)
MarketingService | createChallenge | response | startsAt | string (date-time)
MarketingService | createChallenge | response | endsAt | string (date-time) |  | (nullable)
MarketingService | createChallenge | response | status | enum (draft, active, paused, ended, archived) | yes | (read-only)
MarketingService | createChallenge | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | createChallenge | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | createCollection | request | name | string | yes | (max length 200)
VenueOpsService | createCollection | request | description | string |  | (max length 1000)
VenueOpsService | createCollection | request | venueId | string (uuid)
VenueOpsService | createCollection | request | parentCollectionId | string (uuid)
VenueOpsService | createCollection | response | id | string (uuid) | yes
VenueOpsService | createCollection | response | name | string | yes | Unique per tenant (decided 28 September, audit R108).
VenueOpsService | createCollection | response | description | string |  | (nullable)
VenueOpsService | createCollection | response | venueId | string (uuid) |  | (nullable)
VenueOpsService | createCollection | response | parentCollectionId | string (uuid) |  | (nullable)
VenueOpsService | createCollection | response | assetCount | integer | yes
VenueOpsService | createCollection | response | coverAssetId | string (uuid) |  | (nullable)
VenueOpsService | createCollection | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | createConsentQuestion | request | id | string (uuid) | yes | (read-only)
MarketingService | createConsentQuestion | request | kind | ConsentQuestionKind: enum (swim, scuba, risk, custom) | yes | What the question is about (decided 29 September, rev 3 REV3-26).
MarketingService | createConsentQuestion | request | text | object | yes | The question as the guest reads it, per locale.
MarketingService | createConsentQuestion | request | helpText | object |  | (nullable)
MarketingService | createConsentQuestion | request | version | integer | yes | Raised by one each time the question changes (updateConsentQuestion). (min 1; read-only)
MarketingService | createConsentQuestion | request | scope | enum (perPerson, perBooking) | yes | Asked for each declared person, or once for the whole booking. (default perPerson)
MarketingService | createConsentQuestion | request | required | boolean | yes | Checkout waits until it is answered (orders.checkoutCart 422 consentRequired). (default True)
MarketingService | createConsentQuestion | request | blockingAnswer | enum (yes, no, none) | yes | The answer that stops the booking, for the person or the booking it covers. (default none)
MarketingService | createConsentQuestion | request | status | enum (active, retired) | yes | (default active)
MarketingService | createConsentQuestion | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | createConsentQuestion | request | updatedAt | string (date-time) |  | (read-only)
MarketingService | createConsentQuestion | response | id | string (uuid) | yes | (read-only)
MarketingService | createConsentQuestion | response | kind | ConsentQuestionKind: enum (swim, scuba, risk, custom) | yes | What the question is about (decided 29 September, rev 3 REV3-26).
MarketingService | createConsentQuestion | response | text | object | yes | The question as the guest reads it, per locale.
MarketingService | createConsentQuestion | response | helpText | object |  | (nullable)
MarketingService | createConsentQuestion | response | version | integer | yes | Raised by one each time the question changes (updateConsentQuestion). (min 1; read-only)
MarketingService | createConsentQuestion | response | scope | enum (perPerson, perBooking) | yes | Asked for each declared person, or once for the whole booking. (default perPerson)
MarketingService | createConsentQuestion | response | required | boolean | yes | Checkout waits until it is answered (orders.checkoutCart 422 consentRequired). (default True)
MarketingService | createConsentQuestion | response | blockingAnswer | enum (yes, no, none) | yes | The answer that stops the booking, for the person or the booking it covers. (default none)
MarketingService | createConsentQuestion | response | status | enum (active, retired) | yes | (default active)
MarketingService | createConsentQuestion | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | createConsentQuestion | response | updatedAt | string (date-time) |  | (read-only)
MarketingService | createConsentQuestion | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | createContentBlock | request | id | string (uuid) | yes | (read-only)
WhiteLabelService | createContentBlock | request | pageId | string (uuid) |  | (nullable)
WhiteLabelService | createContentBlock | request | kind | enum (richText, image, video, gallery, cta, faq, form, embed, …) | yes
WhiteLabelService | createContentBlock | request | position | integer
WhiteLabelService | createContentBlock | request | body | object |  | Typed by kind, and validated against the block's own schema at save.
WhiteLabelService | createContentBlock | request | localeVariants | object |  | Per-locale bodies, not per-locale pages.
WhiteLabelService | createContentBlock | request | status | enum (draft, scheduled, published, expired, archived) | yes | Created as draft; moved by publishContentBlock and the publishAt/expireAt timer (states/content-block.yaml), never by the body of a create. (read-only)
WhiteLabelService | createContentBlock | request | publishAt | string (date-time) |  | Content scheduling, which the configuration model had no room for. (nullable)
WhiteLabelService | createContentBlock | request | expireAt | string (date-time) |  | (nullable)
WhiteLabelService | createContentBlock | request | audienceSegmentId | string (uuid) |  | Personalisation, evaluated at render. (nullable)
WhiteLabelService | createContentBlock | request | approvedByPrincipalId | string (uuid) |  | (read-only; nullable)
WhiteLabelService | createContentBlock | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | createContentBlock | response | id | string (uuid) | yes | (read-only)
WhiteLabelService | createContentBlock | response | pageId | string (uuid) |  | (nullable)
WhiteLabelService | createContentBlock | response | kind | enum (richText, image, video, gallery, cta, faq, form, embed, …) | yes
WhiteLabelService | createContentBlock | response | position | integer
WhiteLabelService | createContentBlock | response | body | object |  | Typed by kind, and validated against the block's own schema at save.
WhiteLabelService | createContentBlock | response | localeVariants | object |  | Per-locale bodies, not per-locale pages.
WhiteLabelService | createContentBlock | response | status | enum (draft, scheduled, published, expired, archived) | yes | Created as draft; moved by publishContentBlock and the publishAt/expireAt timer (states/content-block.yaml), never by the body of a create. (read-only)
WhiteLabelService | createContentBlock | response | publishAt | string (date-time) |  | Content scheduling, which the configuration model had no room for. (nullable)
WhiteLabelService | createContentBlock | response | expireAt | string (date-time) |  | (nullable)
WhiteLabelService | createContentBlock | response | audienceSegmentId | string (uuid) |  | Personalisation, evaluated at render. (nullable)
WhiteLabelService | createContentBlock | response | approvedByPrincipalId | string (uuid) |  | (read-only; nullable)
WhiteLabelService | createContentBlock | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | createContentBlock | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | createContentPage | request | id | string (uuid) | yes | (read-only)
WhiteLabelService | createContentPage | request | slug | string | yes | (pattern ^[a-z0-9-]+$)
WhiteLabelService | createContentPage | request | title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | createContentPage | request | body | LocalisedRichText | yes | Keyed by language code.
WhiteLabelService | createContentPage | request | isEnabled | boolean |  | BL-005. (default True)
WhiteLabelService | createContentPage | request | status | object | yes | Created as draft, published by publishTenantConfig, archived through updateContentPage (states/content.yaml). (read-only)
WhiteLabelService | createContentPage | request | iconAssetRef | string (uuid) |  | (nullable)
WhiteLabelService | createContentPage | request | categoryCode | string |  | (nullable)
WhiteLabelService | createContentPage | request | sortOrder | integer
WhiteLabelService | createContentPage | request | isReferenced | boolean |  | True when navigation or the homepage links to this page. (read-only)
WhiteLabelService | createContentPage | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | createContentPage | response | id | string (uuid) | yes | (read-only)
WhiteLabelService | createContentPage | response | slug | string | yes | (pattern ^[a-z0-9-]+$)
WhiteLabelService | createContentPage | response | title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | createContentPage | response | body | LocalisedRichText | yes | Keyed by language code.
WhiteLabelService | createContentPage | response | isEnabled | boolean |  | BL-005. (default True)
WhiteLabelService | createContentPage | response | status | object | yes | Created as draft, published by publishTenantConfig, archived through updateContentPage (states/content.yaml). (read-only)
WhiteLabelService | createContentPage | response | iconAssetRef | string (uuid) |  | (nullable)
WhiteLabelService | createContentPage | response | categoryCode | string |  | (nullable)
WhiteLabelService | createContentPage | response | sortOrder | integer
WhiteLabelService | createContentPage | response | isReferenced | boolean |  | True when navigation or the homepage links to this page. (read-only)
WhiteLabelService | createContentPage | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | createContentPage | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | createContentPage | param (header) | Prefer | enum (validate-only) |  | Validate, do not write (29 September, AI system design 2.3 and 2.2 D step 4).
CatalogueService | createCouponCampaign | request | code | string | yes | (max length 64)
CatalogueService | createCouponCampaign | request | name | string | yes | (max length 200)
CatalogueService | createCouponCampaign | request | venueId | string (uuid) | yes
CatalogueService | createCouponCampaign | request | discount | Discount | yes
CatalogueService | createCouponCampaign | request | discount.kind | DiscountKind: enum (percentage, fixedAmount, fixedPrice, buyXGetY, freeItem, tieredPercentage) | yes
CatalogueService | createCouponCampaign | request | discount.percentage | number |  | (min 0; max 100)
CatalogueService | createCouponCampaign | request | discount.amount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createCouponCampaign | request | discount.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createCouponCampaign | request | discount.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createCouponCampaign | request | discount.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createCouponCampaign | request | discount.fixedPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createCouponCampaign | request | discount.fixedPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createCouponCampaign | request | discount.fixedPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createCouponCampaign | request | discount.fixedPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createCouponCampaign | request | discount.buyQuantity | integer |  | (min 1)
CatalogueService | createCouponCampaign | request | discount.getQuantity | integer |  | (min 1)
CatalogueService | createCouponCampaign | request | discount.getDiscountPercentage | number |  | 100 makes the free items actually free; lower values give a partial discount. (min 0; max 100)
CatalogueService | createCouponCampaign | request | discount.tiers | array of object |  | For tieredPercentage — more units, larger discount.
CatalogueService | createCouponCampaign | request | discount.tiers[].minQuantity | integer | yes | (min 1)
CatalogueService | createCouponCampaign | request | discount.tiers[].percentage | number | yes | (min 0; max 100)
CatalogueService | createCouponCampaign | request | discount.maxDiscountAmount | object |  | Cap on a percentage discount.
CatalogueService | createCouponCampaign | request | discount.maxDiscountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createCouponCampaign | request | discount.maxDiscountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createCouponCampaign | request | discount.maxDiscountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createCouponCampaign | request | discount.rewardVariantIds | array of string (uuid) |  | The reward products, where the reward is not the qualifying product: the free gift of freeItem, the "different product" of a buyXGetY (createPromotion; the builders setGiftFreeProduct and setBuyGetBo… (nullable)
CatalogueService | createCouponCampaign | request | discount.maxApplicationsPerBasket | integer |  | How many times the offer repeats in one basket: the "maximum repetitions" of an N-for-X offer (createPromotion; setFixedPriceOffer was retired in r2, CHG-CLN-001). (min 1; nullable)
CatalogueService | createCouponCampaign | request | conditions | PromotionConditions |  | All conditions must hold.
CatalogueService | createCouponCampaign | request | conditions.variantIds | array of string (uuid)
CatalogueService | createCouponCampaign | request | conditions.productKinds | array of string
CatalogueService | createCouponCampaign | request | conditions.categoryIds | array of string (uuid)
CatalogueService | createCouponCampaign | request | conditions.minQuantity | integer |  | (min 1)
CatalogueService | createCouponCampaign | request | conditions.minBasketValue | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createCouponCampaign | request | conditions.minBasketValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createCouponCampaign | request | conditions.minBasketValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createCouponCampaign | request | conditions.minBasketValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createCouponCampaign | request | conditions.channels | array of SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) |  | Empty or absent matches every channel.
CatalogueService | createCouponCampaign | request | conditions.purchaseGate | boolean |  | BL-037. (default False)
CatalogueService | createCouponCampaign | request | conditions.paymentMethod | array of string |  | BL-113. (nullable)
CatalogueService | createCouponCampaign | request | conditions.issuerBins | array of string |  | Card BIN ranges, where the campaign is issuer-specific rather than scheme-specific. (nullable)
CatalogueService | createCouponCampaign | request | conditions.componentRedemption | enum (allTogether, independently, sequenced) |  | BL-112. (nullable)
CatalogueService | createCouponCampaign | request | conditions.daysOfWeek | array of integer
CatalogueService | createCouponCampaign | request | conditions.startTime | string |  | (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
CatalogueService | createCouponCampaign | request | conditions.endTime | string |  | (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
CatalogueService | createCouponCampaign | request | conditions.membershipTierIds | array of string (uuid)
CatalogueService | createCouponCampaign | request | conditions.requiresCoupon | boolean |  | (default False)
CatalogueService | createCouponCampaign | request | conditions.firstPurchaseOnly | boolean |  | (default False)
CatalogueService | createCouponCampaign | request | conditions.performanceIds | array of string (uuid)
CatalogueService | createCouponCampaign | request | conditions.advanceDaysMin | integer |  | Early-bird — booked at least this many days ahead.
CatalogueService | createCouponCampaign | request | conditions.advanceDaysMax | integer |  | Last-minute — booked no more than this many days ahead.
CatalogueService | createCouponCampaign | request | conditions.eligibilityRuleIds | array of string (uuid) |  | Reusable eligibility rules (promotions.promotion_rule rows of ruleType: eligibility with no promotion of their own) that must also hold. (nullable)
CatalogueService | createCouponCampaign | request | isSingleUse | boolean |  | True generates individually redeemable codes. (default True)
CatalogueService | createCouponCampaign | request | maxRedemptionsPerCode | integer |  | (default 1)
CatalogueService | createCouponCampaign | request | validFrom | string (date-time) | yes
CatalogueService | createCouponCampaign | request | validTo | string (date-time)
CatalogueService | createCouponCampaign | request | campaignId | string (uuid) |  | The commercial campaign (promotions.campaign) the codes are issued under, as the Coupon & Promo Code Builder names it. (nullable)
CatalogueService | createCouponCampaign | response | code | string | yes | (max length 64)
CatalogueService | createCouponCampaign | response | name | string | yes | (max length 200)
CatalogueService | createCouponCampaign | response | venueId | string (uuid) | yes
CatalogueService | createCouponCampaign | response | discount | Discount | yes
CatalogueService | createCouponCampaign | response | discount.kind | DiscountKind: enum (percentage, fixedAmount, fixedPrice, buyXGetY, freeItem, tieredPercentage) | yes
CatalogueService | createCouponCampaign | response | discount.percentage | number |  | (min 0; max 100)
CatalogueService | createCouponCampaign | response | discount.amount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createCouponCampaign | response | discount.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createCouponCampaign | response | discount.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createCouponCampaign | response | discount.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createCouponCampaign | response | discount.fixedPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createCouponCampaign | response | discount.fixedPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createCouponCampaign | response | discount.fixedPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createCouponCampaign | response | discount.fixedPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createCouponCampaign | response | discount.buyQuantity | integer |  | (min 1)
CatalogueService | createCouponCampaign | response | discount.getQuantity | integer |  | (min 1)
CatalogueService | createCouponCampaign | response | discount.getDiscountPercentage | number |  | 100 makes the free items actually free; lower values give a partial discount. (min 0; max 100)
CatalogueService | createCouponCampaign | response | discount.tiers | array of object |  | For tieredPercentage — more units, larger discount.
CatalogueService | createCouponCampaign | response | discount.tiers[].minQuantity | integer | yes | (min 1)
CatalogueService | createCouponCampaign | response | discount.tiers[].percentage | number | yes | (min 0; max 100)
CatalogueService | createCouponCampaign | response | discount.maxDiscountAmount | object |  | Cap on a percentage discount.
CatalogueService | createCouponCampaign | response | discount.maxDiscountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createCouponCampaign | response | discount.maxDiscountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createCouponCampaign | response | discount.maxDiscountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createCouponCampaign | response | discount.rewardVariantIds | array of string (uuid) |  | The reward products, where the reward is not the qualifying product: the free gift of freeItem, the "different product" of a buyXGetY (createPromotion; the builders setGiftFreeProduct and setBuyGetBo… (nullable)
CatalogueService | createCouponCampaign | response | discount.maxApplicationsPerBasket | integer |  | How many times the offer repeats in one basket: the "maximum repetitions" of an N-for-X offer (createPromotion; setFixedPriceOffer was retired in r2, CHG-CLN-001). (min 1; nullable)
CatalogueService | createCouponCampaign | response | conditions | PromotionConditions |  | All conditions must hold.
CatalogueService | createCouponCampaign | response | conditions.variantIds | array of string (uuid)
CatalogueService | createCouponCampaign | response | conditions.productKinds | array of string
CatalogueService | createCouponCampaign | response | conditions.categoryIds | array of string (uuid)
CatalogueService | createCouponCampaign | response | conditions.minQuantity | integer |  | (min 1)
CatalogueService | createCouponCampaign | response | conditions.minBasketValue | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createCouponCampaign | response | conditions.minBasketValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createCouponCampaign | response | conditions.minBasketValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createCouponCampaign | response | conditions.minBasketValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createCouponCampaign | response | conditions.channels | array of SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) |  | Empty or absent matches every channel.
CatalogueService | createCouponCampaign | response | conditions.purchaseGate | boolean |  | BL-037. (default False)
CatalogueService | createCouponCampaign | response | conditions.paymentMethod | array of string |  | BL-113. (nullable)
CatalogueService | createCouponCampaign | response | conditions.issuerBins | array of string |  | Card BIN ranges, where the campaign is issuer-specific rather than scheme-specific. (nullable)
CatalogueService | createCouponCampaign | response | conditions.componentRedemption | enum (allTogether, independently, sequenced) |  | BL-112. (nullable)
CatalogueService | createCouponCampaign | response | conditions.daysOfWeek | array of integer
CatalogueService | createCouponCampaign | response | conditions.startTime | string |  | (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
CatalogueService | createCouponCampaign | response | conditions.endTime | string |  | (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
CatalogueService | createCouponCampaign | response | conditions.membershipTierIds | array of string (uuid)
CatalogueService | createCouponCampaign | response | conditions.requiresCoupon | boolean |  | (default False)
CatalogueService | createCouponCampaign | response | conditions.firstPurchaseOnly | boolean |  | (default False)
CatalogueService | createCouponCampaign | response | conditions.performanceIds | array of string (uuid)
CatalogueService | createCouponCampaign | response | conditions.advanceDaysMin | integer |  | Early-bird — booked at least this many days ahead.
CatalogueService | createCouponCampaign | response | conditions.advanceDaysMax | integer |  | Last-minute — booked no more than this many days ahead.
CatalogueService | createCouponCampaign | response | conditions.eligibilityRuleIds | array of string (uuid) |  | Reusable eligibility rules (promotions.promotion_rule rows of ruleType: eligibility with no promotion of their own) that must also hold. (nullable)
CatalogueService | createCouponCampaign | response | isSingleUse | boolean |  | True generates individually redeemable codes. (default True)
CatalogueService | createCouponCampaign | response | maxRedemptionsPerCode | integer |  | (default 1)
CatalogueService | createCouponCampaign | response | validFrom | string (date-time) | yes
CatalogueService | createCouponCampaign | response | validTo | string (date-time)
CatalogueService | createCouponCampaign | response | campaignId | string (uuid) |  | The commercial campaign (promotions.campaign) the codes are issued under, as the Coupon & Promo Code Builder names it. (nullable)
CatalogueService | createCouponCampaign | response | id | string (uuid) | yes
CatalogueService | createCouponCampaign | response | generatedCount | integer | yes
CatalogueService | createCouponCampaign | response | redeemedCount | integer | yes
CatalogueService | createCouponCampaign | response | isActive | boolean
CatalogueService | createCouponCampaign | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
ReportingService | createDashboard | request | name | string | yes | (max length 200)
ReportingService | createDashboard | request | module | ModuleKey: enum (core, ticketing, access, fnb, retail, inventory, seating, membership, …) | yes | What a tenant buys, and what a screen belongs to.
ReportingService | createDashboard | request | description | string |  | (max length 1000)
ReportingService | createDashboard | request | venueId | string (uuid) |  | Narrows every tile to one venue.
ReportingService | createDashboard | request | isShared | boolean |  | (default False)
ReportingService | createDashboard | request | tiles | array of DashboardTile | yes | (min items 1; max items 24)
ReportingService | createDashboard | request | tiles[].id | string (uuid) | yes
ReportingService | createDashboard | request | tiles[].title | string
ReportingService | createDashboard | request | tiles[].reportId | string (uuid) | yes
ReportingService | createDashboard | request | tiles[].visualisation | enum (number, line, area, bar, stackedBar, stackedBar100, combo, pie, …) | yes | Extended 22 September from eight marks to twenty against Ticketing_Platform_Native_Dashboard_Visualization_Requirements.pdf, which names eighteen components and marks every one MVP.
ReportingService | createDashboard | request | tiles[].parameters | object |  | Open on purpose, and not yet specified.
ReportingService | createDashboard | request | tiles[].refreshSeconds | integer |  | Minimum thirty seconds. (min 30)
ReportingService | createDashboard | request | tiles[].position | object | yes
ReportingService | createDashboard | request | tiles[].position.row | integer | yes
ReportingService | createDashboard | request | tiles[].position.column | integer | yes
ReportingService | createDashboard | request | tiles[].position.width | integer | yes
ReportingService | createDashboard | request | tiles[].position.height | integer | yes
ReportingService | createDashboard | response | name | string | yes | (max length 200)
ReportingService | createDashboard | response | module | ModuleKey: enum (core, ticketing, access, fnb, retail, inventory, seating, membership, …) | yes | What a tenant buys, and what a screen belongs to.
ReportingService | createDashboard | response | description | string |  | (max length 1000)
ReportingService | createDashboard | response | venueId | string (uuid) |  | Narrows every tile to one venue.
ReportingService | createDashboard | response | isShared | boolean |  | (default False)
ReportingService | createDashboard | response | tiles | array of DashboardTile | yes | (min items 1; max items 24)
ReportingService | createDashboard | response | tiles[].id | string (uuid) | yes
ReportingService | createDashboard | response | tiles[].title | string
ReportingService | createDashboard | response | tiles[].reportId | string (uuid) | yes
ReportingService | createDashboard | response | tiles[].visualisation | enum (number, line, area, bar, stackedBar, stackedBar100, combo, pie, …) | yes | Extended 22 September from eight marks to twenty against Ticketing_Platform_Native_Dashboard_Visualization_Requirements.pdf, which names eighteen components and marks every one MVP.
ReportingService | createDashboard | response | tiles[].parameters | object |  | Open on purpose, and not yet specified.
ReportingService | createDashboard | response | tiles[].refreshSeconds | integer |  | Minimum thirty seconds. (min 30)
ReportingService | createDashboard | response | tiles[].position | object | yes
ReportingService | createDashboard | response | tiles[].position.row | integer | yes
ReportingService | createDashboard | response | tiles[].position.column | integer | yes
ReportingService | createDashboard | response | tiles[].position.width | integer | yes
ReportingService | createDashboard | response | tiles[].position.height | integer | yes
ReportingService | createDashboard | response | id | string (uuid) | yes
ReportingService | createDashboard | response | ownerPrincipalId | string (uuid) | yes
ReportingService | createDashboard | response | aggregateCost | enum (low, medium, high) | yes | Combined refresh load of every tile.
ReportingService | createDashboard | response | archivedAt | string (date-time) |  | Set by deleteDashboard, which archives rather than removes. (read-only; nullable)
ReportingService | createDashboard | response | createdAt | string (date-time) | yes
ReportingService | createDashboard | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | createDeliveryLocation | request | venueId | string (uuid) | yes
FnbService | createDeliveryLocation | request | kind | DeliveryLocationKind: enum (table, seat, cabana, sunbed, poolside, box, suite, lawn, …) | yes | 4.6.26.
FnbService | createDeliveryLocation | request | label | string | yes | (max length 200)
FnbService | createDeliveryLocation | request | zone | string |  | (nullable)
FnbService | createDeliveryLocation | request | tableId | string (uuid) |  | (nullable)
FnbService | createDeliveryLocation | request | seatId | string |  | (nullable)
FnbService | createDeliveryLocation | request | servingOutletIds | array of string (uuid)
FnbService | createDeliveryLocation | request | walkTimeMinutes | integer |  | (min 0; nullable)
FnbService | createDeliveryLocation | response | id | string (uuid) | yes
FnbService | createDeliveryLocation | response | venueId | string (uuid) | yes
FnbService | createDeliveryLocation | response | kind | DeliveryLocationKind: enum (table, seat, cabana, sunbed, poolside, box, suite, lawn, …) | yes | 4.6.26.
FnbService | createDeliveryLocation | response | label | string | yes | What a runner is told.
FnbService | createDeliveryLocation | response | zone | string |  | (nullable)
FnbService | createDeliveryLocation | response | tableId | string (uuid) |  | Set where the location is a restaurant table, so it shares table state. (nullable)
FnbService | createDeliveryLocation | response | seatId | string |  | Set where the seat is the address. (nullable)
FnbService | createDeliveryLocation | response | servingOutletIds | array of string (uuid) |  | Which outlets deliver here.
FnbService | createDeliveryLocation | response | isServiceable | boolean | yes | False where the location exists but is not currently taking delivery — closed section, weather, no runner on shift.
FnbService | createDeliveryLocation | response | unserviceableReason | string |  | (nullable)
FnbService | createDeliveryLocation | response | walkTimeMinutes | integer |  | From the serving outlet. (nullable)
FnbService | createDeliveryLocation | response | codeGeneration | integer |  | Which printing of the location's ordering code is current (4 October 2026, CHG-FXC-009). (min 1; default 1)
FnbService | createDeliveryLocation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | createEntitlementTemplate | request | description | string |  | Validity, re-entry and transfer rules in prose.
CatalogueService | createEntitlementTemplate | request | id | string (uuid) | yes | Assigned by the server on create; createEntitlementTemplate does not take it. (read-only)
CatalogueService | createEntitlementTemplate | request | code | string | yes | (max length 64)
CatalogueService | createEntitlementTemplate | request | name | string | yes | (max length 200)
CatalogueService | createEntitlementTemplate | request | validityKind | enum (singleUse, dated, dateRange, rolling, unlimited, countLimited) | yes
CatalogueService | createEntitlementTemplate | request | validFromOffsetDays | integer |  | (nullable)
CatalogueService | createEntitlementTemplate | request | validForDays | integer |  | (nullable)
CatalogueService | createEntitlementTemplate | request | daysOfWeek | array of enum (mon, tue, wed, thu, fri, sat, sun) |  | 1.1.7 and 1.1.82. (nullable)
CatalogueService | createEntitlementTemplate | request | expiryAnchor | enum (offsetDays, endOfMonth, endOfQuarter, endOfYear, fixedDate, seasonEnd) |  | 1.1.90 to 1.1.92. (nullable)
CatalogueService | createEntitlementTemplate | request | expiryDate | string (date) |  | Where expiryAnchor is fixedDate. (nullable)
CatalogueService | createEntitlementTemplate | request | expiryNoticeDays | integer |  | How many days before validTo access raises entitlement.expiringSoon for an entitlement of this template still issued or partiallyConsumed (29 September, build pass, group G2; 5.5.30). (min 1; max 180; nullable)
CatalogueService | createEntitlementTemplate | request | carriesStoredValue | boolean |  | BL-033. (default False)
CatalogueService | createEntitlementTemplate | request | includedValue | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createEntitlementTemplate | request | includedValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createEntitlementTemplate | request | includedValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createEntitlementTemplate | request | includedValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createEntitlementTemplate | request | validTimeWindows | array of object |  | BL-036, 1.1.81 and 1.1.83. (nullable)
CatalogueService | createEntitlementTemplate | request | validTimeWindows[].from | string
CatalogueService | createEntitlementTemplate | request | validTimeWindows[].to | string
CatalogueService | createEntitlementTemplate | request | validTimeWindows[].daysOfWeek | array of string
CatalogueService | createEntitlementTemplate | request | blackoutDates | array of string (date) |  | Calendar exceptions on the entitlement. (nullable)
CatalogueService | createEntitlementTemplate | request | fastTrackTier | enum (none, priority, express, unlimited) |  | 19.2.20, BL-015. (nullable)
CatalogueService | createEntitlementTemplate | request | entriesAllowed | integer |  | Null means unlimited. (nullable)
CatalogueService | createEntitlementTemplate | request | transportRestriction | object |  | The journey a transport pass is good for (decided 29 September, rev 3 REV3-21). (nullable)
CatalogueService | createEntitlementTemplate | request | transportRestriction.fromStationId | string (uuid) | yes | A transport.Station.
CatalogueService | createEntitlementTemplate | request | transportRestriction.toStationId | string (uuid) | yes
CatalogueService | createEntitlementTemplate | request | transportRestriction.bothDirections | boolean |  | Valid from either station to the other, as the prototype sells it. (default True)
CatalogueService | createEntitlementTemplate | request | transportRestriction.routeIds | array of string (uuid) |  | The routes it may be used on.
CatalogueService | createEntitlementTemplate | request | reentryAllowed | boolean |  | (default False)
CatalogueService | createEntitlementTemplate | request | purchaseEligibility | object |  | 1.1.38, 1.1.121, 1.1.125, 1.1.126. (nullable)
CatalogueService | createEntitlementTemplate | request | purchaseEligibility.minAgeYears | integer |  | (nullable)
CatalogueService | createEntitlementTemplate | request | purchaseEligibility.maxAgeYears | integer |  | (nullable)
CatalogueService | createEntitlementTemplate | request | purchaseEligibility.minHeightCm | integer |  | Height gates a ride and can gate a sale. (nullable)
CatalogueService | createEntitlementTemplate | request | purchaseEligibility.residencyRequired | boolean |  | (default False)
CatalogueService | createEntitlementTemplate | request | purchaseEligibility.nationalities | array of string |  | (nullable)
CatalogueService | createEntitlementTemplate | request | purchaseEligibility.minLoyaltyTier | string |  | (nullable)
CatalogueService | createEntitlementTemplate | request | purchaseEligibility.requiresVerification | boolean |  | Whether the claim is checked or taken on trust. (default False)
CatalogueService | createEntitlementTemplate | request | personType | enum (adult, child, infant, senior, student, resident, staff) |  | 2.11.7. (nullable)
CatalogueService | createEntitlementTemplate | request | admissionRulesId | string (uuid) |  | (nullable)
CatalogueService | createEntitlementTemplate | request | isTransferable | boolean |  | (default True)
CatalogueService | createEntitlementTemplate | request | canShareMedia | boolean |  | Whether this entitlement may be appended to media a guest already holds (CF-58). (default True)
CatalogueService | createEntitlementTemplate | request | canClaimShopAndDrop | boolean |  | Whether this entitlement may be scanned to claim goods left under 4.4.7. (default False)
CatalogueService | createEntitlementTemplate | request | isNameBound | boolean |  | True requires a holder name at sale. (default False)
CatalogueService | createEntitlementTemplate | request | autoRenewDefault | boolean |  | Taken from their membership_plan, 20 September — the "take those" half of the TAKE BODY verdict. (default False)
CatalogueService | createEntitlementTemplate | request | renewalTermDays | integer |  | What a renewal extends the membership by. (nullable)
CatalogueService | createEntitlementTemplate | request | renewalGraceDays | integer |  | How long after expiry a membership can still be renewed rather than rejoined. (default 0)
CatalogueService | createEntitlementTemplate | request | renewalVariantId | string (uuid) |  | What a renewal sells, which is usually not what joining sold. (nullable)
CatalogueService | createEntitlementTemplate | request | crossesCells | boolean |  | True propagates a redemption right to other cells on issue (ADR-0010). (default False)
CatalogueService | createEntitlementTemplate | request | isActive | boolean
CatalogueService | createEntitlementTemplate | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
CatalogueService | createEntitlementTemplate | response | description | string |  | Validity, re-entry and transfer rules in prose.
CatalogueService | createEntitlementTemplate | response | id | string (uuid) | yes | Assigned by the server on create; createEntitlementTemplate does not take it. (read-only)
CatalogueService | createEntitlementTemplate | response | code | string | yes | (max length 64)
CatalogueService | createEntitlementTemplate | response | name | string | yes | (max length 200)
CatalogueService | createEntitlementTemplate | response | validityKind | enum (singleUse, dated, dateRange, rolling, unlimited, countLimited) | yes
CatalogueService | createEntitlementTemplate | response | validFromOffsetDays | integer |  | (nullable)
CatalogueService | createEntitlementTemplate | response | validForDays | integer |  | (nullable)
CatalogueService | createEntitlementTemplate | response | daysOfWeek | array of enum (mon, tue, wed, thu, fri, sat, sun) |  | 1.1.7 and 1.1.82. (nullable)
CatalogueService | createEntitlementTemplate | response | expiryAnchor | enum (offsetDays, endOfMonth, endOfQuarter, endOfYear, fixedDate, seasonEnd) |  | 1.1.90 to 1.1.92. (nullable)
CatalogueService | createEntitlementTemplate | response | expiryDate | string (date) |  | Where expiryAnchor is fixedDate. (nullable)
CatalogueService | createEntitlementTemplate | response | expiryNoticeDays | integer |  | How many days before validTo access raises entitlement.expiringSoon for an entitlement of this template still issued or partiallyConsumed (29 September, build pass, group G2; 5.5.30). (min 1; max 180; nullable)
CatalogueService | createEntitlementTemplate | response | carriesStoredValue | boolean |  | BL-033. (default False)
CatalogueService | createEntitlementTemplate | response | includedValue | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createEntitlementTemplate | response | includedValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createEntitlementTemplate | response | includedValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createEntitlementTemplate | response | includedValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createEntitlementTemplate | response | validTimeWindows | array of object |  | BL-036, 1.1.81 and 1.1.83. (nullable)
CatalogueService | createEntitlementTemplate | response | validTimeWindows[].from | string
CatalogueService | createEntitlementTemplate | response | validTimeWindows[].to | string
CatalogueService | createEntitlementTemplate | response | validTimeWindows[].daysOfWeek | array of string
CatalogueService | createEntitlementTemplate | response | blackoutDates | array of string (date) |  | Calendar exceptions on the entitlement. (nullable)
CatalogueService | createEntitlementTemplate | response | fastTrackTier | enum (none, priority, express, unlimited) |  | 19.2.20, BL-015. (nullable)
CatalogueService | createEntitlementTemplate | response | entriesAllowed | integer |  | Null means unlimited. (nullable)
CatalogueService | createEntitlementTemplate | response | transportRestriction | object |  | The journey a transport pass is good for (decided 29 September, rev 3 REV3-21). (nullable)
CatalogueService | createEntitlementTemplate | response | transportRestriction.fromStationId | string (uuid) | yes | A transport.Station.
CatalogueService | createEntitlementTemplate | response | transportRestriction.toStationId | string (uuid) | yes
CatalogueService | createEntitlementTemplate | response | transportRestriction.bothDirections | boolean |  | Valid from either station to the other, as the prototype sells it. (default True)
CatalogueService | createEntitlementTemplate | response | transportRestriction.routeIds | array of string (uuid) |  | The routes it may be used on.
CatalogueService | createEntitlementTemplate | response | reentryAllowed | boolean |  | (default False)
CatalogueService | createEntitlementTemplate | response | purchaseEligibility | object |  | 1.1.38, 1.1.121, 1.1.125, 1.1.126. (nullable)
CatalogueService | createEntitlementTemplate | response | purchaseEligibility.minAgeYears | integer |  | (nullable)
CatalogueService | createEntitlementTemplate | response | purchaseEligibility.maxAgeYears | integer |  | (nullable)
CatalogueService | createEntitlementTemplate | response | purchaseEligibility.minHeightCm | integer |  | Height gates a ride and can gate a sale. (nullable)
CatalogueService | createEntitlementTemplate | response | purchaseEligibility.residencyRequired | boolean |  | (default False)
CatalogueService | createEntitlementTemplate | response | purchaseEligibility.nationalities | array of string |  | (nullable)
CatalogueService | createEntitlementTemplate | response | purchaseEligibility.minLoyaltyTier | string |  | (nullable)
CatalogueService | createEntitlementTemplate | response | purchaseEligibility.requiresVerification | boolean |  | Whether the claim is checked or taken on trust. (default False)
CatalogueService | createEntitlementTemplate | response | personType | enum (adult, child, infant, senior, student, resident, staff) |  | 2.11.7. (nullable)
CatalogueService | createEntitlementTemplate | response | admissionRulesId | string (uuid) |  | (nullable)
CatalogueService | createEntitlementTemplate | response | isTransferable | boolean |  | (default True)
CatalogueService | createEntitlementTemplate | response | canShareMedia | boolean |  | Whether this entitlement may be appended to media a guest already holds (CF-58). (default True)
CatalogueService | createEntitlementTemplate | response | canClaimShopAndDrop | boolean |  | Whether this entitlement may be scanned to claim goods left under 4.4.7. (default False)
CatalogueService | createEntitlementTemplate | response | isNameBound | boolean |  | True requires a holder name at sale. (default False)
CatalogueService | createEntitlementTemplate | response | autoRenewDefault | boolean |  | Taken from their membership_plan, 20 September — the "take those" half of the TAKE BODY verdict. (default False)
CatalogueService | createEntitlementTemplate | response | renewalTermDays | integer |  | What a renewal extends the membership by. (nullable)
CatalogueService | createEntitlementTemplate | response | renewalGraceDays | integer |  | How long after expiry a membership can still be renewed rather than rejoined. (default 0)
CatalogueService | createEntitlementTemplate | response | renewalVariantId | string (uuid) |  | What a renewal sells, which is usually not what joining sold. (nullable)
CatalogueService | createEntitlementTemplate | response | crossesCells | boolean |  | True propagates a redemption right to other cells on issue (ADR-0010). (default False)
CatalogueService | createEntitlementTemplate | response | isActive | boolean
CatalogueService | createEntitlementTemplate | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
CatalogueService | createEntitlementTemplate | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | createEvent | request | code | string | yes | Unique per tenant (decided 28 September, audit R108). (max length 64)
CatalogueService | createEvent | request | name | string | yes | (max length 200)
CatalogueService | createEvent | request | venueId | string (uuid) | yes
CatalogueService | createEvent | request | parentEventId | string (uuid)
CatalogueService | createEvent | response | id | string (uuid) | yes
CatalogueService | createEvent | response | code | string | yes
CatalogueService | createEvent | response | name | string | yes
CatalogueService | createEvent | response | venueId | string (uuid) | yes
CatalogueService | createEvent | response | scopePath | string | yes
CatalogueService | createEvent | response | parentEventId | string (uuid) |  | For grouped events. (nullable)
CatalogueService | createEvent | response | performanceCount | integer |  | How many performances the event has. (read-only)
CatalogueService | createEvent | response | isActive | boolean
CatalogueService | createEvent | response | lifecycleState | enum (draft, planned, onSale, live, closed, cancelled, archived) |  | Where the event is in its lifecycle (4 October 2026, CHG-FXC-003; catalogue.event had nowhere to keep it). (read-only)
CatalogueService | createEvent | response | lifecycleStateChangedAt | string (date-time) |  | (read-only; nullable)
CatalogueService | createEvent | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | createFnbOrder | request | id | string (uuid) | yes
FnbService | createFnbOrder | request | outletId | string (uuid) | yes
FnbService | createFnbOrder | request | serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery) | yes
FnbService | createFnbOrder | request | tableVisitId | string (uuid) |  | Required for table service. (nullable)
FnbService | createFnbOrder | request | lines | array of CreateFnbOrderLine | yes | (min items 1)
FnbService | createFnbOrder | request | lines[].id | string (uuid) | yes
FnbService | createFnbOrder | request | lines[].menuItemId | string (uuid) | yes
FnbService | createFnbOrder | request | lines[].quantity | integer | yes | (min 1)
FnbService | createFnbOrder | request | lines[].modifierOptionIds | array of string (uuid)
FnbService | createFnbOrder | request | lines[].note | string |  | Free text to the kitchen. (max length 200)
FnbService | createFnbOrder | request | lines[].seatNumber | integer |  | Which cover ordered it. (nullable)
FnbService | createFnbOrder | request | lines[].course | integer |  | Course grouping, so the kitchen fires in sequence. (nullable)
FnbService | createFnbOrder | request | lines[].redeemEntitlementId | string |  | A meal combo redeemed at the till or by a scan (29 September, MOB-4; applied 30 September). (nullable)
FnbService | createFnbOrder | request | salesOrderId | string (uuid) |  | The orders.sales_order this F&B order fulfils (SD-046, 29 September). (nullable)
FnbService | createFnbOrder | request | recordedAt | string (date-time) | yes
FnbService | createFnbOrder | response | id | string (uuid) | yes
FnbService | createFnbOrder | response | orderNumber | string | yes
FnbService | createFnbOrder | response | outletId | string (uuid) | yes
FnbService | createFnbOrder | response | paymentTiming | object |  | The outlet's payment timing when the order was placed (CHG-CSA-010), kept as a snapshot. (read-only)
FnbService | createFnbOrder | response | sentToKitchenAt | string (date-time) |  | When the order's kitchen tickets were created. (read-only; nullable)
FnbService | createFnbOrder | response | serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery) | yes
FnbService | createFnbOrder | response | tableVisitId | string (uuid) |  | (nullable)
FnbService | createFnbOrder | response | status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) | yes | The full lifecycle from 4.6.35.
FnbService | createFnbOrder | response | lines | array of object | yes
FnbService | createFnbOrder | response | lines[].id | string (uuid) | yes
FnbService | createFnbOrder | response | lines[].menuItemId | string (uuid) | yes
FnbService | createFnbOrder | response | lines[].quantity | integer | yes | (min 1)
FnbService | createFnbOrder | response | lines[].modifierOptionIds | array of string (uuid)
FnbService | createFnbOrder | response | lines[].note | string |  | Free text to the kitchen. (max length 200)
FnbService | createFnbOrder | response | lines[].seatNumber | integer |  | Which cover ordered it. (nullable)
FnbService | createFnbOrder | response | lines[].course | integer |  | Course grouping, so the kitchen fires in sequence. (nullable)
FnbService | createFnbOrder | response | lines[].redeemEntitlementId | string |  | A meal combo redeemed at the till or by a scan (29 September, MOB-4; applied 30 September). (nullable)
FnbService | createFnbOrder | response | lines[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) |  | The full lifecycle from 4.6.35.
FnbService | createFnbOrder | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | createFnbOrder | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | createFnbOrder | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | createFnbOrder | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | createFnbOrder | response | lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | createFnbOrder | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | createFnbOrder | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | createFnbOrder | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | createFnbOrder | response | salesOrderId | string (uuid) |  | Retyped 29 September (SD-046), and format: uuid since ADR-0056 (30 September): every id is a uuid, so this joins orders.sales_order.id. (nullable)
FnbService | createFnbOrder | response | updatedAt | string (date-time) |  | Taken from their fnb.order. (nullable)
FnbService | createFnbOrder | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | createFnbOrder | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | createFnbOrder | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | createFnbOrder | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | createFnbOrder | response | taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | createFnbOrder | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | createFnbOrder | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | createFnbOrder | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | createFnbOrder | response | kitchenTicketId | string (uuid) |  | (nullable)
FnbService | createFnbOrder | response | kitchenTickets | array of KitchenTicket |  | The kitchen tickets this order created, one per station (SD-046). (read-only)
FnbService | createFnbOrder | response | kitchenTickets[].id | string (uuid) | yes
FnbService | createFnbOrder | response | kitchenTickets[].orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | createFnbOrder | response | kitchenTickets[].orderNumber | string
FnbService | createFnbOrder | response | kitchenTickets[].outletId | string (uuid) | yes
FnbService | createFnbOrder | response | kitchenTickets[].tableLabel | string |  | (nullable)
FnbService | createFnbOrder | response | kitchenTickets[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | createFnbOrder | response | kitchenTickets[].coursing | object |  | BL-131. (nullable)
FnbService | createFnbOrder | response | kitchenTickets[].buzzerCode | string |  | BL-128. (nullable)
FnbService | createFnbOrder | response | kitchenTickets[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | createFnbOrder | response | kitchenTickets[].priority | integer |  | Higher fires sooner.
FnbService | createFnbOrder | response | kitchenTickets[].prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | createFnbOrder | response | kitchenTickets[].prioritiseReason | string |  | (nullable)
FnbService | createFnbOrder | response | kitchenTickets[].lines | array of object | yes
FnbService | createFnbOrder | response | kitchenTickets[].lines[].lineId | string (uuid) | yes
FnbService | createFnbOrder | response | kitchenTickets[].lines[].name | string | yes
FnbService | createFnbOrder | response | kitchenTickets[].lines[].quantity | integer | yes
FnbService | createFnbOrder | response | kitchenTickets[].lines[].modifiers | array of string
FnbService | createFnbOrder | response | kitchenTickets[].lines[].note | string |  | (nullable)
FnbService | createFnbOrder | response | kitchenTickets[].lines[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | createFnbOrder | response | kitchenTickets[].lines[].refireOfLineId | string (uuid) |  | Set on a refire. (read-only; nullable)
FnbService | createFnbOrder | response | kitchenTickets[].lines[].refireReason | object |  | (read-only; nullable)
FnbService | createFnbOrder | response | kitchenTickets[].lines[].isChargeable | boolean |  | A refire's chargeable flag. (read-only; nullable)
FnbService | createFnbOrder | response | kitchenTickets[].lines[].course | integer |  | (nullable)
FnbService | createFnbOrder | response | kitchenTickets[].lines[].stationId | string (uuid) |  | (nullable)
FnbService | createFnbOrder | response | kitchenTickets[].lines[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | createFnbOrder | response | kitchenTickets[].createdAt | string (date-time) | yes
FnbService | createFnbOrder | response | kitchenTickets[].targetReadyAt | string (date-time) |  | (nullable)
FnbService | createFnbOrder | response | kitchenTickets[].elapsedSeconds | integer
FnbService | createFnbOrder | response | kitchenTickets[].visitId | string (uuid) |  | The table visit the ticket is for (4 October 2026, CHG-FXC-011; KIT-002): the {visitId} notifyServer takes. (read-only; nullable)
FnbService | createFnbOrder | response | estimatedReadyAt | string (date-time) |  | (nullable)
FnbService | createFnbOrder | response | createdAt | string (date-time) | yes
FnbService | createFnbOrder | response | recordedAt | string (date-time)
FnbService | createFnbOrder | response | syncedAt | string (date-time) |  | (nullable)
FnbService | createFnbOrder | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | createForecastScenario | request | id | string (uuid) |  | (read-only)
AiService | createForecastScenario | request | name | string
AiService | createForecastScenario | request | baseVersionId | string (uuid) | yes
AiService | createForecastScenario | request | changes | array of object | yes | (min items 1)
AiService | createForecastScenario | request | changes[].lever | enum (price, capacity, openingHours, weather, event, marketing, staffing, closure) | yes
AiService | createForecastScenario | request | changes[].target | string |  | (nullable)
AiService | createForecastScenario | request | changes[].value | object |  | (nullable)
AiService | createForecastScenario | request | status | enum (computing, ready, failed) |  | (read-only)
AiService | createForecastScenario | request | result | object |  | Deltas against the base version by subject and period. (read-only; nullable)
AiService | createForecastScenario | request | createdByPrincipalId | string (uuid) |  | (read-only)
AiService | createForecastScenario | request | createdAt | string (date-time) |  | (read-only)
AiService | createForecastScenario | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | createForecastScenario | response | id | string (uuid) |  | (read-only)
AiService | createForecastScenario | response | name | string
AiService | createForecastScenario | response | baseVersionId | string (uuid) | yes
AiService | createForecastScenario | response | changes | array of object | yes | (min items 1)
AiService | createForecastScenario | response | changes[].lever | enum (price, capacity, openingHours, weather, event, marketing, staffing, closure) | yes
AiService | createForecastScenario | response | changes[].target | string |  | (nullable)
AiService | createForecastScenario | response | changes[].value | object |  | (nullable)
AiService | createForecastScenario | response | status | enum (computing, ready, failed) |  | (read-only)
AiService | createForecastScenario | response | result | object |  | Deltas against the base version by subject and period. (read-only; nullable)
AiService | createForecastScenario | response | createdByPrincipalId | string (uuid) |  | (read-only)
AiService | createForecastScenario | response | createdAt | string (date-time) |  | (read-only)
AiService | createForecastScenario | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | createForecastScenario | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | createForm | request | id | string (uuid) | yes | (read-only)
MarketingService | createForm | request | name | string | yes
MarketingService | createForm | request | kind | enum (waiver, survey, dataCapture, consentForm, incidentReport, registration) | yes
MarketingService | createForm | request | consentPurposes | array of enum (facePass, faceTag, marketing, photography, waiver) |  | What a consentForm consents to (Chinmay, 2 October, batch 4; follows BO-188: biometric capture needs consent on the venue's own form; CHG-CSA-026).
MarketingService | createForm | request | version | integer | yes | Set by the server — 1 on createForm, the next number on every change. (read-only)
MarketingService | createForm | request | fields | array of FormField
MarketingService | createForm | request | fields[].key | string | yes
MarketingService | createForm | request | fields[].label | string | yes
MarketingService | createForm | request | fields[].labelLocalised | object
MarketingService | createForm | request | fields[].type | enum (text, longText, number, date, select, multiSelect, boolean, scale, …) | yes
MarketingService | createForm | request | fields[].options | array of string
MarketingService | createForm | request | fields[].isRequired | boolean |  | (default False)
MarketingService | createForm | request | fields[].isPersonalData | boolean |  | Marked at the field, because retention is decided at the field. (default False)
MarketingService | createForm | request | fields[].consentPurposeId | string (uuid) |  | (nullable)
MarketingService | createForm | request | fields[].showWhen | object |  | (nullable)
MarketingService | createForm | request | fields[].showWhen.field | string
MarketingService | createForm | request | fields[].showWhen.equals | string
MarketingService | createForm | request | requiresSignature | boolean |  | What makes it a waiver. (default False)
MarketingService | createForm | request | signatureKind | enum (drawn, typed, checkbox, none) |  | (default none)
MarketingService | createForm | request | scoreScale | enum (nps, csat, ces, likert5, likert7, stars) |  | What makes it a survey. (nullable)
MarketingService | createForm | request | appliesToProductIds | array of string (uuid)
MarketingService | createForm | request | validForMonths | integer |  | How long an acceptance lasts. (nullable)
MarketingService | createForm | request | minimumAge | integer |  | (nullable)
MarketingService | createForm | request | requiresGuardianForMinors | boolean |  | A minor cannot waive their own rights. (default True)
MarketingService | createForm | request | status | enum (draft, published, superseded, retired) | yes | (read-only)
MarketingService | createForm | request | legalReviewedBy | string |  | (nullable)
MarketingService | createForm | request | legalReviewedAt | string (date-time) |  | (nullable)
MarketingService | createForm | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | createForm | response | id | string (uuid) | yes | (read-only)
MarketingService | createForm | response | name | string | yes
MarketingService | createForm | response | kind | enum (waiver, survey, dataCapture, consentForm, incidentReport, registration) | yes
MarketingService | createForm | response | consentPurposes | array of enum (facePass, faceTag, marketing, photography, waiver) |  | What a consentForm consents to (Chinmay, 2 October, batch 4; follows BO-188: biometric capture needs consent on the venue's own form; CHG-CSA-026).
MarketingService | createForm | response | version | integer | yes | Set by the server — 1 on createForm, the next number on every change. (read-only)
MarketingService | createForm | response | fields | array of FormField
MarketingService | createForm | response | fields[].key | string | yes
MarketingService | createForm | response | fields[].label | string | yes
MarketingService | createForm | response | fields[].labelLocalised | object
MarketingService | createForm | response | fields[].type | enum (text, longText, number, date, select, multiSelect, boolean, scale, …) | yes
MarketingService | createForm | response | fields[].options | array of string
MarketingService | createForm | response | fields[].isRequired | boolean |  | (default False)
MarketingService | createForm | response | fields[].isPersonalData | boolean |  | Marked at the field, because retention is decided at the field. (default False)
MarketingService | createForm | response | fields[].consentPurposeId | string (uuid) |  | (nullable)
MarketingService | createForm | response | fields[].showWhen | object |  | (nullable)
MarketingService | createForm | response | fields[].showWhen.field | string
MarketingService | createForm | response | fields[].showWhen.equals | string
MarketingService | createForm | response | requiresSignature | boolean |  | What makes it a waiver. (default False)
MarketingService | createForm | response | signatureKind | enum (drawn, typed, checkbox, none) |  | (default none)
MarketingService | createForm | response | scoreScale | enum (nps, csat, ces, likert5, likert7, stars) |  | What makes it a survey. (nullable)
MarketingService | createForm | response | appliesToProductIds | array of string (uuid)
MarketingService | createForm | response | validForMonths | integer |  | How long an acceptance lasts. (nullable)
MarketingService | createForm | response | minimumAge | integer |  | (nullable)
MarketingService | createForm | response | requiresGuardianForMinors | boolean |  | A minor cannot waive their own rights. (default True)
MarketingService | createForm | response | status | enum (draft, published, superseded, retired) | yes | (read-only)
MarketingService | createForm | response | legalReviewedBy | string |  | (nullable)
MarketingService | createForm | response | legalReviewedAt | string (date-time) |  | (nullable)
MarketingService | createForm | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | createForm | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
InventoryService | createGoodsReceipt | request | id | string (uuid) | yes
InventoryService | createGoodsReceipt | request | purchaseOrderId | string (uuid) | yes
InventoryService | createGoodsReceipt | request | locationId | string (uuid) | yes
InventoryService | createGoodsReceipt | request | deliveryNoteReference | string |  | (max length 128)
InventoryService | createGoodsReceipt | request | lines | array of object | yes | (min items 1)
InventoryService | createGoodsReceipt | request | lines[].itemId | string (uuid) | yes
InventoryService | createGoodsReceipt | request | lines[].receivedQuantity | number | yes | (min 0)
InventoryService | createGoodsReceipt | request | lines[].unit | string
InventoryService | createGoodsReceipt | request | lines[].batchNumber | string |  | (max length 64)
InventoryService | createGoodsReceipt | request | lines[].expiryDate | string (date) |  | Required for perishable items.
InventoryService | createGoodsReceipt | request | lines[].note | string |  | (max length 200)
InventoryService | createGoodsReceipt | request | recordedAt | string (date-time) | yes
InventoryService | createGoodsReceipt | response | id | string (uuid) | yes
InventoryService | createGoodsReceipt | response | receiptNumber | string | yes | Server-assigned: the venue prefix plus a sequence per venue (decided 28 September, audit R152), e.g. (read-only)
InventoryService | createGoodsReceipt | response | purchaseOrderId | string (uuid) | yes
InventoryService | createGoodsReceipt | response | locationId | string (uuid) | yes
InventoryService | createGoodsReceipt | response | deliveryNoteReference | string |  | (nullable)
InventoryService | createGoodsReceipt | response | lines | array of object | yes
InventoryService | createGoodsReceipt | response | lines[].lineId | string (uuid) |  | One batch or expiry line of the receipt. (read-only)
InventoryService | createGoodsReceipt | response | lines[].itemId | string (uuid)
InventoryService | createGoodsReceipt | response | lines[].itemName | string
InventoryService | createGoodsReceipt | response | lines[].orderedQuantity | number
InventoryService | createGoodsReceipt | response | lines[].receivedQuantity | number
InventoryService | createGoodsReceipt | response | lines[].rejectedQuantity | number
InventoryService | createGoodsReceipt | response | lines[].batchNumber | string |  | (nullable)
InventoryService | createGoodsReceipt | response | lines[].expiryDate | string (date) |  | (nullable)
InventoryService | createGoodsReceipt | response | lines[].unitCost | Money |  | On the wire this is three fields; in the database it is one column.
InventoryService | createGoodsReceipt | response | lines[].unitCost.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
InventoryService | createGoodsReceipt | response | lines[].unitCost.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
InventoryService | createGoodsReceipt | response | lines[].unitCost.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
InventoryService | createGoodsReceipt | response | totalValue | Money |  | On the wire this is three fields; in the database it is one column.
InventoryService | createGoodsReceipt | response | totalValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
InventoryService | createGoodsReceipt | response | totalValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
InventoryService | createGoodsReceipt | response | totalValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
InventoryService | createGoodsReceipt | response | receivedByPrincipalId | string (uuid) | yes
InventoryService | createGoodsReceipt | response | journalEntryId | string |  | The accrual the supplier invoice will later match against. (nullable)
InventoryService | createGoodsReceipt | response | createdAt | string (date-time) | yes
InventoryService | createGoodsReceipt | response | recordedAt | string (date-time)
InventoryService | createGoodsReceipt | response | syncedAt | string (date-time) |  | (nullable)
InventoryService | createGoodsReceipt | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | createGuestFnbOrder | request | id | string (uuid) | yes
FnbService | createGuestFnbOrder | request | locationSessionId | string (uuid) |  | From claimLocationSession. (nullable)
FnbService | createGuestFnbOrder | request | outletId | string (uuid) |  | Required for collection. (nullable)
FnbService | createGuestFnbOrder | request | fulfilment | object |  | Required for takeaway and address delivery; refused with 422 when it breaks the outlet's FnbDeliveryPolicy. (nullable)
FnbService | createGuestFnbOrder | request | fulfilment.id | string (uuid) |  | (read-only)
FnbService | createGuestFnbOrder | request | fulfilment.orderId | string (uuid) |  | The guest order this fulfils (FnbOrder.id). (read-only)
FnbService | createGuestFnbOrder | request | fulfilment.mode | enum (collection, delivery, inVenue) | yes | collection from a counter, delivery to an address outside the venue, inVenue to a table, seat, cabana or named location (the location session).
FnbService | createGuestFnbOrder | request | fulfilment.collectionAt | string (date-time) |  | (nullable)
FnbService | createGuestFnbOrder | request | fulfilment.windowStart | string (date-time) |  | (nullable)
FnbService | createGuestFnbOrder | request | fulfilment.windowEnd | string (date-time) |  | (nullable)
FnbService | createGuestFnbOrder | request | fulfilment.deliveryAddress | object |  | (nullable)
FnbService | createGuestFnbOrder | request | fulfilment.deliveryAddress.building | string |  | (max length 200)
FnbService | createGuestFnbOrder | request | fulfilment.deliveryAddress.unit | string |  | (max length 60; nullable)
FnbService | createGuestFnbOrder | request | fulfilment.deliveryAddress.emirate | string |  | (max length 60)
FnbService | createGuestFnbOrder | request | fulfilment.deliveryAddress.directions | string |  | (max length 500; nullable)
FnbService | createGuestFnbOrder | request | fulfilment.deliveryFee | object |  | (read-only; nullable)
FnbService | createGuestFnbOrder | request | fulfilment.deliveryFee.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | createGuestFnbOrder | request | fulfilment.deliveryFee.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | createGuestFnbOrder | request | fulfilment.deliveryFee.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | createGuestFnbOrder | request | fulfilment.cutlery | boolean |  | (default False)
FnbService | createGuestFnbOrder | request | fulfilment.scopePath | string |  | The partition key (ADR-0005). (read-only)
FnbService | createGuestFnbOrder | request | lines | array of CreateGuestOrderLine | yes | (min items 1)
FnbService | createGuestFnbOrder | request | lines[].id | string (uuid) | yes
FnbService | createGuestFnbOrder | request | lines[].menuItemId | string (uuid) | yes
FnbService | createGuestFnbOrder | request | lines[].quantity | integer | yes | (min 1; max 20)
FnbService | createGuestFnbOrder | request | lines[].modifierOptionIds | array of string (uuid)
FnbService | createGuestFnbOrder | request | lines[].note | string |  | Free text to the kitchen. (max length 200)
FnbService | createGuestFnbOrder | request | quotedTotal | object | yes | What the guest was shown.
FnbService | createGuestFnbOrder | request | quotedTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | createGuestFnbOrder | request | quotedTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | createGuestFnbOrder | request | quotedTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | createGuestFnbOrder | request | paymentMethod | enum (card, wallet, roomCharge, addToTab)
FnbService | createGuestFnbOrder | request | recordedAt | string (date-time) | yes
FnbService | createGuestFnbOrder | response | orderId | string | yes
FnbService | createGuestFnbOrder | response | orderNumber | string | yes | Short and readable.
FnbService | createGuestFnbOrder | response | fulfilment | enum (collect, deliverToLocation, tableService, deliverToAddress) |  | How the order reaches the guest, in the request's terms: collect is GuestOrderFulfilment.mode collection; deliverToAddress is delivery; inVenue is tableService where the location session is a table a…
FnbService | createGuestFnbOrder | response | deliveryLabel | string |  | Where it is going, as a runner would read it. (nullable)
FnbService | createGuestFnbOrder | response | status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) | yes | The full lifecycle from 4.6.35.
FnbService | createGuestFnbOrder | response | total | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | createGuestFnbOrder | response | total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | createGuestFnbOrder | response | total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | createGuestFnbOrder | response | total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | createGuestFnbOrder | response | estimatedReadyAt | string (date-time) |  | (nullable)
FnbService | createGuestFnbOrder | response | collectionPoint | string |  | (nullable)
FnbService | createGuestFnbOrder | response | tableLabel | string |  | (nullable)
FnbService | createGuestFnbOrder | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | createGuidedChoice | request | id | string (uuid) | yes | UUIDv7. (read-only)
WhiteLabelService | createGuidedChoice | request | venueId | string (uuid) | yes | From the path of createGuidedChoice. (read-only)
WhiteLabelService | createGuidedChoice | request | name | string | yes | Staff-facing name, e.g. (max length 80)
WhiteLabelService | createGuidedChoice | request | mode | enum (button, popupOnArrival, off) | yes | How the guest reaches it (rev 3 REV3-11). (default button)
WhiteLabelService | createGuidedChoice | request | showBanner | boolean |  | The dark banner under the products ("Choose from the experiences above or let us help you decide") with a Help me choose button. (default True)
WhiteLabelService | createGuidedChoice | request | behaviour | enum (filter, recommend) |  | filter (default) narrows the list; recommend ends on one result card (decided 29 September, W4). (default filter)
WhiteLabelService | createGuidedChoice | request | showEverything | boolean |  | The "Show everything" link under a filtered list, which clears the answers (W4). (default True)
WhiteLabelService | createGuidedChoice | request | questions | array of object | yes | One to four questions (decided 29 September, W4: the Deep Dive reference asks three or four; rev 3 REV3-11 allowed two). (min items 1; max items 4)
WhiteLabelService | createGuidedChoice | request | questions[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | createGuidedChoice | request | questions[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | createGuidedChoice | request | questions[].kind | enum (choice, yesNo, age, level, certification) |  | What the question asks (decided 29 September, W4). (default choice)
WhiteLabelService | createGuidedChoice | request | questions[].sortOrder | integer | yes | (min 0)
WhiteLabelService | createGuidedChoice | request | questions[].answers | array of object | yes | Two to four answers; the prototype shows three (proposed, client to correct, rev 3 REV3-11). (min items 2; max items 4)
WhiteLabelService | createGuidedChoice | request | questions[].answers[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | createGuidedChoice | request | questions[].answers[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | createGuidedChoice | request | questions[].answers[].body | object |  | The one-liner under the title, at most 140 characters in each language.
WhiteLabelService | createGuidedChoice | request | questions[].answers[].icon | string |  | An icon name from the guest app's icon set. (max length 40; nullable)
WhiteLabelService | createGuidedChoice | request | questions[].answers[].badge | object |  | Optional, e.g. (nullable)
WhiteLabelService | createGuidedChoice | request | questions[].answers[].sortOrder | integer | yes | (min 0)
WhiteLabelService | createGuidedChoice | request | questions[].answers[].target | object |  | Required with behaviour recommend on the last question; optional with filter, where it is the card shown above the filtered list. (nullable)
WhiteLabelService | createGuidedChoice | request | questions[].answers[].filter | object |  | What this answer keeps in the list (decided 29 September, W4). (nullable)
WhiteLabelService | createGuidedChoice | request | questions[].answers[].consentPrefill | object |  | Pre-fills a REV3-26 consent question from this answer (decided 29 September, W4). (nullable)
WhiteLabelService | createGuidedChoice | request | questions[].answers[].result | object |  | The result card when this answer decides the result. (nullable)
WhiteLabelService | createGuidedChoice | request | status | object | yes | (read-only)
WhiteLabelService | createGuidedChoice | request | source | enum (manual, aiSuggested) | yes | manual when staff created it; aiSuggested when the ai service proposed it (a service caller). (read-only)
WhiteLabelService | createGuidedChoice | request | suggestionRef | string |  | For aiSuggested, the id of the ai job that proposed it. (read-only; nullable)
WhiteLabelService | createGuidedChoice | request | publishedAt | string (date-time) |  | (read-only; nullable)
WhiteLabelService | createGuidedChoice | request | publishedBy | string (uuid) |  | The person who published it. (read-only; nullable)
WhiteLabelService | createGuidedChoice | request | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | createGuidedChoice | response | id | string (uuid) | yes | UUIDv7. (read-only)
WhiteLabelService | createGuidedChoice | response | venueId | string (uuid) | yes | From the path of createGuidedChoice. (read-only)
WhiteLabelService | createGuidedChoice | response | name | string | yes | Staff-facing name, e.g. (max length 80)
WhiteLabelService | createGuidedChoice | response | mode | enum (button, popupOnArrival, off) | yes | How the guest reaches it (rev 3 REV3-11). (default button)
WhiteLabelService | createGuidedChoice | response | showBanner | boolean |  | The dark banner under the products ("Choose from the experiences above or let us help you decide") with a Help me choose button. (default True)
WhiteLabelService | createGuidedChoice | response | behaviour | enum (filter, recommend) |  | filter (default) narrows the list; recommend ends on one result card (decided 29 September, W4). (default filter)
WhiteLabelService | createGuidedChoice | response | showEverything | boolean |  | The "Show everything" link under a filtered list, which clears the answers (W4). (default True)
WhiteLabelService | createGuidedChoice | response | questions | array of object | yes | One to four questions (decided 29 September, W4: the Deep Dive reference asks three or four; rev 3 REV3-11 allowed two). (min items 1; max items 4)
WhiteLabelService | createGuidedChoice | response | questions[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | createGuidedChoice | response | questions[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | createGuidedChoice | response | questions[].kind | enum (choice, yesNo, age, level, certification) |  | What the question asks (decided 29 September, W4). (default choice)
WhiteLabelService | createGuidedChoice | response | questions[].sortOrder | integer | yes | (min 0)
WhiteLabelService | createGuidedChoice | response | questions[].answers | array of object | yes | Two to four answers; the prototype shows three (proposed, client to correct, rev 3 REV3-11). (min items 2; max items 4)
WhiteLabelService | createGuidedChoice | response | questions[].answers[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | createGuidedChoice | response | questions[].answers[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | createGuidedChoice | response | questions[].answers[].body | object |  | The one-liner under the title, at most 140 characters in each language.
WhiteLabelService | createGuidedChoice | response | questions[].answers[].icon | string |  | An icon name from the guest app's icon set. (max length 40; nullable)
WhiteLabelService | createGuidedChoice | response | questions[].answers[].badge | object |  | Optional, e.g. (nullable)
WhiteLabelService | createGuidedChoice | response | questions[].answers[].sortOrder | integer | yes | (min 0)
WhiteLabelService | createGuidedChoice | response | questions[].answers[].target | object |  | Required with behaviour recommend on the last question; optional with filter, where it is the card shown above the filtered list. (nullable)
WhiteLabelService | createGuidedChoice | response | questions[].answers[].filter | object |  | What this answer keeps in the list (decided 29 September, W4). (nullable)
WhiteLabelService | createGuidedChoice | response | questions[].answers[].consentPrefill | object |  | Pre-fills a REV3-26 consent question from this answer (decided 29 September, W4). (nullable)
WhiteLabelService | createGuidedChoice | response | questions[].answers[].result | object |  | The result card when this answer decides the result. (nullable)
WhiteLabelService | createGuidedChoice | response | status | object | yes | (read-only)
WhiteLabelService | createGuidedChoice | response | source | enum (manual, aiSuggested) | yes | manual when staff created it; aiSuggested when the ai service proposed it (a service caller). (read-only)
WhiteLabelService | createGuidedChoice | response | suggestionRef | string |  | For aiSuggested, the id of the ai job that proposed it. (read-only; nullable)
WhiteLabelService | createGuidedChoice | response | publishedAt | string (date-time) |  | (read-only; nullable)
WhiteLabelService | createGuidedChoice | response | publishedBy | string (uuid) |  | The person who published it. (read-only; nullable)
WhiteLabelService | createGuidedChoice | response | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | createGuidedChoice | param (path) | venueId | string (uuid) | yes
WhiteLabelService | createGuidedChoice | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | createInspectionTemplate | request | instructions | string |  | The procedure itself.
VenueOpsService | createInspectionTemplate | request | id | string (uuid) | yes
VenueOpsService | createInspectionTemplate | request | code | string | yes | (max length 64)
VenueOpsService | createInspectionTemplate | request | name | string | yes | (max length 200)
VenueOpsService | createInspectionTemplate | request | venueId | string (uuid) |  | (nullable)
VenueOpsService | createInspectionTemplate | request | appliesToAssetCategoryId | string (uuid) |  | (nullable)
VenueOpsService | createInspectionTemplate | request | frequency | enum (preOpening, postClosing, daily, weekly, monthly, annual, adHoc)
VenueOpsService | createInspectionTemplate | request | items | array of object | yes | (min items 1)
VenueOpsService | createInspectionTemplate | request | items[].key | string | yes
VenueOpsService | createInspectionTemplate | request | items[].label | string | yes
VenueOpsService | createInspectionTemplate | request | items[].kind | InspectionItemKind: enum (passFail, yesNo, numeric, text, photo, signature) | yes
VenueOpsService | createInspectionTemplate | request | items[].isRequired | boolean | yes
VenueOpsService | createInspectionTemplate | request | items[].isSafetyCritical | boolean |  | A failed safety-critical item blocks the inspection from passing and cannot be overridden by completing the rest. (default False)
VenueOpsService | createInspectionTemplate | request | items[].requiresPhotoOnFail | boolean |  | (default True)
VenueOpsService | createInspectionTemplate | request | items[].minValue | number |  | (nullable)
VenueOpsService | createInspectionTemplate | request | items[].maxValue | number |  | (nullable)
VenueOpsService | createInspectionTemplate | request | items[].guidance | string |  | (nullable)
VenueOpsService | createInspectionTemplate | request | retentionYears | integer |  | Compliance inspections are retained alongside the financial trail. (default 7)
VenueOpsService | createInspectionTemplate | request | isActive | boolean
VenueOpsService | createInspectionTemplate | response | instructions | string |  | The procedure itself.
VenueOpsService | createInspectionTemplate | response | id | string (uuid) | yes
VenueOpsService | createInspectionTemplate | response | code | string | yes | (max length 64)
VenueOpsService | createInspectionTemplate | response | name | string | yes | (max length 200)
VenueOpsService | createInspectionTemplate | response | venueId | string (uuid) |  | (nullable)
VenueOpsService | createInspectionTemplate | response | appliesToAssetCategoryId | string (uuid) |  | (nullable)
VenueOpsService | createInspectionTemplate | response | frequency | enum (preOpening, postClosing, daily, weekly, monthly, annual, adHoc)
VenueOpsService | createInspectionTemplate | response | items | array of object | yes | (min items 1)
VenueOpsService | createInspectionTemplate | response | items[].key | string | yes
VenueOpsService | createInspectionTemplate | response | items[].label | string | yes
VenueOpsService | createInspectionTemplate | response | items[].kind | InspectionItemKind: enum (passFail, yesNo, numeric, text, photo, signature) | yes
VenueOpsService | createInspectionTemplate | response | items[].isRequired | boolean | yes
VenueOpsService | createInspectionTemplate | response | items[].isSafetyCritical | boolean |  | A failed safety-critical item blocks the inspection from passing and cannot be overridden by completing the rest. (default False)
VenueOpsService | createInspectionTemplate | response | items[].requiresPhotoOnFail | boolean |  | (default True)
VenueOpsService | createInspectionTemplate | response | items[].minValue | number |  | (nullable)
VenueOpsService | createInspectionTemplate | response | items[].maxValue | number |  | (nullable)
VenueOpsService | createInspectionTemplate | response | items[].guidance | string |  | (nullable)
VenueOpsService | createInspectionTemplate | response | retentionYears | integer |  | Compliance inspections are retained alongside the financial trail. (default 7)
VenueOpsService | createInspectionTemplate | response | isActive | boolean
VenueOpsService | createInspectionTemplate | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createInstalmentPlan | request | orderId | string (uuid) | yes
OrderService | createInstalmentPlan | request | frequency | enum (monthly, quarterly, custom) | yes
OrderService | createInstalmentPlan | request | instalmentCount | integer | yes | (min 2)
OrderService | createInstalmentPlan | request | firstDueDate | string (date)
OrderService | createInstalmentPlan | request | customDueDates | array of string (date) |  | Required with custom; one per instalment after the first.
OrderService | createInstalmentPlan | request | paymentTokenId | string (uuid) | yes
OrderService | createInstalmentPlan | response | id | string (uuid) | yes
OrderService | createInstalmentPlan | response | orderId | string (uuid) | yes
OrderService | createInstalmentPlan | response | subjectId | string (uuid) |  | (nullable)
OrderService | createInstalmentPlan | response | frequency | enum (monthly, quarterly, custom) | yes
OrderService | createInstalmentPlan | response | paymentTokenId | string (uuid)
OrderService | createInstalmentPlan | response | status | enum (active, completed, inArrears, cancelled) | yes
OrderService | createInstalmentPlan | response | total | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createInstalmentPlan | response | total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createInstalmentPlan | response | total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createInstalmentPlan | response | total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createInstalmentPlan | response | paidToDate | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | createInstalmentPlan | response | paidToDate.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createInstalmentPlan | response | paidToDate.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createInstalmentPlan | response | paidToDate.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createInstalmentPlan | response | nextDueDate | string (date) |  | (nullable)
OrderService | createInstalmentPlan | response | instalments | array of PayInstalment | yes
OrderService | createInstalmentPlan | response | instalments[].sequence | integer | yes | (min 1)
OrderService | createInstalmentPlan | response | instalments[].dueDate | string (date) | yes
OrderService | createInstalmentPlan | response | instalments[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createInstalmentPlan | response | instalments[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createInstalmentPlan | response | instalments[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createInstalmentPlan | response | instalments[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createInstalmentPlan | response | instalments[].status | enum (scheduled, paid, failed, waived, cancelled) | yes
OrderService | createInstalmentPlan | response | instalments[].paymentId | string (uuid) |  | (nullable)
OrderService | createInstalmentPlan | response | instalments[].dunningCaseId | string (uuid) |  | (nullable)
OrderService | createInstalmentPlan | response | instalments[].attemptedAt | string (date-time) |  | (nullable)
OrderService | createInstalmentPlan | response | createdAt | string (date-time)
OrderService | createInstalmentPlan | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | createInstalmentPlan | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
InventoryService | createInventoryItem | request | sku | string | yes | (max length 64)
InventoryService | createInventoryItem | request | barcode | string |  | (max length 128)
InventoryService | createInventoryItem | request | name | string | yes | (max length 200)
InventoryService | createInventoryItem | request | venueId | string (uuid) | yes
InventoryService | createInventoryItem | request | categoryId | string (uuid)
InventoryService | createInventoryItem | request | baseUnit | string | yes | The unit stock is held in.
InventoryService | createInventoryItem | request | purchaseUnit | string |  | How the supplier sells it — a case of 24 against a base unit of one.
InventoryService | createInventoryItem | request | purchaseUnitFactor | number |  | (min 0; default 1)
InventoryService | createInventoryItem | request | costingMethod | CostingMethod: enum (weightedAverage, fifo, standardCost, lastPurchasePrice) | yes | Fixed at item creation.
InventoryService | createInventoryItem | request | reorderPoint | number |  | (min 0)
InventoryService | createInventoryItem | request | reorderQuantity | number |  | (min 0)
InventoryService | createInventoryItem | request | parLevel | number |  | (min 0)
InventoryService | createInventoryItem | request | preferredSupplierId | string (uuid)
InventoryService | createInventoryItem | request | allowNegativeStock | boolean |  | True permits issue beyond on-hand. (default False)
InventoryService | createInventoryItem | request | isPerishable | boolean |  | (default False)
InventoryService | createInventoryItem | request | shelfLifeDays | integer |  | (nullable)
InventoryService | createInventoryItem | response | sku | string | yes | (max length 64)
InventoryService | createInventoryItem | response | barcode | string |  | (max length 128)
InventoryService | createInventoryItem | response | name | string | yes | (max length 200)
InventoryService | createInventoryItem | response | venueId | string (uuid) | yes
InventoryService | createInventoryItem | response | categoryId | string (uuid)
InventoryService | createInventoryItem | response | baseUnit | string | yes | The unit stock is held in.
InventoryService | createInventoryItem | response | purchaseUnit | string |  | How the supplier sells it — a case of 24 against a base unit of one.
InventoryService | createInventoryItem | response | purchaseUnitFactor | number |  | (min 0; default 1)
InventoryService | createInventoryItem | response | costingMethod | CostingMethod: enum (weightedAverage, fifo, standardCost, lastPurchasePrice) | yes | Fixed at item creation.
InventoryService | createInventoryItem | response | reorderPoint | number |  | (min 0)
InventoryService | createInventoryItem | response | reorderQuantity | number |  | (min 0)
InventoryService | createInventoryItem | response | parLevel | number |  | (min 0)
InventoryService | createInventoryItem | response | preferredSupplierId | string (uuid)
InventoryService | createInventoryItem | response | allowNegativeStock | boolean |  | True permits issue beyond on-hand. (default False)
InventoryService | createInventoryItem | response | isPerishable | boolean |  | (default False)
InventoryService | createInventoryItem | response | shelfLifeDays | integer |  | (nullable)
InventoryService | createInventoryItem | response | id | string (uuid) | yes
InventoryService | createInventoryItem | response | onHand | number | yes | Derived from movements.
InventoryService | createInventoryItem | response | onOrder | number
InventoryService | createInventoryItem | response | inTransit | number
InventoryService | createInventoryItem | response | available | number |  | On-hand minus allocated, where allocated is stock reserved for orders (decided 28 September, audit R171).
InventoryService | createInventoryItem | response | averageCost | Money |  | On the wire this is three fields; in the database it is one column.
InventoryService | createInventoryItem | response | averageCost.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
InventoryService | createInventoryItem | response | averageCost.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
InventoryService | createInventoryItem | response | averageCost.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
InventoryService | createInventoryItem | response | lastPurchasePrice | Money |  | On the wire this is three fields; in the database it is one column.
InventoryService | createInventoryItem | response | lastPurchasePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
InventoryService | createInventoryItem | response | lastPurchasePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
InventoryService | createInventoryItem | response | lastPurchasePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
InventoryService | createInventoryItem | response | isBelowReorderPoint | boolean
InventoryService | createInventoryItem | response | hasMovements | boolean |  | True locks costing method and base unit.
InventoryService | createInventoryItem | response | isActive | boolean | yes
InventoryService | createInventoryItem | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | createInvitationCampaign | request | id | string (uuid) | yes | (read-only)
MarketingService | createInvitationCampaign | request | name | string | yes
MarketingService | createInvitationCampaign | request | eventId | string (uuid) |  | (nullable)
MarketingService | createInvitationCampaign | request | productId | string (uuid) |  | (nullable)
MarketingService | createInvitationCampaign | request | quota | integer | yes | Places held, not invitations sent.
MarketingService | createInvitationCampaign | request | overInvitePercent | number |  | How many more may be invited than there are places. (default 0)
MarketingService | createInvitationCampaign | request | issuedCount | integer |  | (read-only)
MarketingService | createInvitationCampaign | request | acceptedCount | integer |  | (read-only)
MarketingService | createInvitationCampaign | request | respondByAt | string (date-time) |  | (nullable)
MarketingService | createInvitationCampaign | request | status | enum (draft, open, closed, cancelled) | yes | (read-only)
MarketingService | createInvitationCampaign | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | createInvitationCampaign | response | id | string (uuid) | yes | (read-only)
MarketingService | createInvitationCampaign | response | name | string | yes
MarketingService | createInvitationCampaign | response | eventId | string (uuid) |  | (nullable)
MarketingService | createInvitationCampaign | response | productId | string (uuid) |  | (nullable)
MarketingService | createInvitationCampaign | response | quota | integer | yes | Places held, not invitations sent.
MarketingService | createInvitationCampaign | response | overInvitePercent | number |  | How many more may be invited than there are places. (default 0)
MarketingService | createInvitationCampaign | response | issuedCount | integer |  | (read-only)
MarketingService | createInvitationCampaign | response | acceptedCount | integer |  | (read-only)
MarketingService | createInvitationCampaign | response | respondByAt | string (date-time) |  | (nullable)
MarketingService | createInvitationCampaign | response | status | enum (draft, open, closed, cancelled) | yes | (read-only)
MarketingService | createInvitationCampaign | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | createInvitationCampaign | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | createKnowledgeCollection | request | id | string (uuid) |  | (read-only)
AiService | createKnowledgeCollection | request | name | string | yes
AiService | createKnowledgeCollection | request | description | string
AiService | createKnowledgeCollection | request | scopeLevel | enum (tenant, region, venue) | yes
AiService | createKnowledgeCollection | request | scopePath | string |  | (read-only)
AiService | createKnowledgeCollection | request | documentCount | integer |  | (read-only)
AiService | createKnowledgeCollection | request | shardKey | string |  | The tenant boundary on shared placement (ADR-0021). (read-only)
AiService | createKnowledgeCollection | request | retrieval | enum (dense, hybrid) |  | Set at creation and not changeable. (default hybrid)
AiService | createKnowledgeCollection | request | sparseModel | string |  | The sparse signal, where retrieval is hybrid. (nullable)
AiService | createKnowledgeCollection | request | idfScope | enum (shard, tenant, venue) |  | Which population the sparse score measures rarity against (ADR-0021). (default tenant)
AiService | createKnowledgeCollection | request | embeddingModel | string |  | This is what decides how many collections exist (ADR-0021). (read-only)
AiService | createKnowledgeCollection | request | isActive | boolean
AiService | createKnowledgeCollection | response | id | string (uuid) |  | (read-only)
AiService | createKnowledgeCollection | response | name | string | yes
AiService | createKnowledgeCollection | response | description | string
AiService | createKnowledgeCollection | response | scopeLevel | enum (tenant, region, venue) | yes
AiService | createKnowledgeCollection | response | scopePath | string |  | (read-only)
AiService | createKnowledgeCollection | response | documentCount | integer |  | (read-only)
AiService | createKnowledgeCollection | response | shardKey | string |  | The tenant boundary on shared placement (ADR-0021). (read-only)
AiService | createKnowledgeCollection | response | retrieval | enum (dense, hybrid) |  | Set at creation and not changeable. (default hybrid)
AiService | createKnowledgeCollection | response | sparseModel | string |  | The sparse signal, where retrieval is hybrid. (nullable)
AiService | createKnowledgeCollection | response | idfScope | enum (shard, tenant, venue) |  | Which population the sparse score measures rarity against (ADR-0021). (default tenant)
AiService | createKnowledgeCollection | response | embeddingModel | string |  | This is what decides how many collections exist (ADR-0021). (read-only)
AiService | createKnowledgeCollection | response | isActive | boolean
AiService | createKnowledgeCollection | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
ReportingService | createKpi | request | id | string (uuid)
ReportingService | createKpi | request | code | string | yes | takings and admissions are seeded for every tenant as system KPIs (decided 28 September, audit R283), and the five accreditation KPIs for every tenant with the accreditation module (29 September, bui…
ReportingService | createKpi | request | name | string | yes
ReportingService | createKpi | request | description | string |  | (nullable)
ReportingService | createKpi | request | domain | string |  | (nullable)
ReportingService | createKpi | request | formula | string |  | Expressed against the semantic model, not against tables.
ReportingService | createKpi | request | unit | enum (currency, count, percentage, duration, ratio, score)
ReportingService | createKpi | request | higherIsBetter | boolean |  | Refund rate and revenue both go up. (default True)
ReportingService | createKpi | request | defaultPeriod | string |  | (nullable)
ReportingService | createKpi | request | owner | string (uuid) |  | (nullable)
ReportingService | createKpi | request | scopePath | string
ReportingService | createKpi | request | isActive | boolean |  | (default True)
ReportingService | createKpi | response | id | string (uuid)
ReportingService | createKpi | response | code | string | yes | takings and admissions are seeded for every tenant as system KPIs (decided 28 September, audit R283), and the five accreditation KPIs for every tenant with the accreditation module (29 September, bui…
ReportingService | createKpi | response | name | string | yes
ReportingService | createKpi | response | description | string |  | (nullable)
ReportingService | createKpi | response | domain | string |  | (nullable)
ReportingService | createKpi | response | formula | string |  | Expressed against the semantic model, not against tables.
ReportingService | createKpi | response | unit | enum (currency, count, percentage, duration, ratio, score)
ReportingService | createKpi | response | higherIsBetter | boolean |  | Refund rate and revenue both go up. (default True)
ReportingService | createKpi | response | defaultPeriod | string |  | (nullable)
ReportingService | createKpi | response | owner | string (uuid) |  | (nullable)
ReportingService | createKpi | response | scopePath | string
ReportingService | createKpi | response | isActive | boolean |  | (default True)
ReportingService | createKpi | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
LedgerService | createLegalEntity | request | id | string (uuid) | yes | (read-only)
LedgerService | createLegalEntity | request | code | string | yes | (max length 64)
LedgerService | createLegalEntity | request | name | string | yes | (max length 200)
LedgerService | createLegalEntity | request | countryCode | string | yes | (pattern ^[A-Z]{2}$)
LedgerService | createLegalEntity | request | currency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | createLegalEntity | request | currencyScale | integer | yes | (min 0; max 4)
LedgerService | createLegalEntity | request | taxRegistrationNumber | string |  | (nullable)
LedgerService | createLegalEntity | request | fiscalYearStartMonth | integer | yes | (min 1; max 12)
LedgerService | createLegalEntity | request | regionIds | array of string (uuid)
LedgerService | createLegalEntity | request | isActive | boolean
LedgerService | createLegalEntity | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
LedgerService | createLegalEntity | response | id | string (uuid) | yes | (read-only)
LedgerService | createLegalEntity | response | code | string | yes | (max length 64)
LedgerService | createLegalEntity | response | name | string | yes | (max length 200)
LedgerService | createLegalEntity | response | countryCode | string | yes | (pattern ^[A-Z]{2}$)
LedgerService | createLegalEntity | response | currency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | createLegalEntity | response | currencyScale | integer | yes | (min 0; max 4)
LedgerService | createLegalEntity | response | taxRegistrationNumber | string |  | (nullable)
LedgerService | createLegalEntity | response | fiscalYearStartMonth | integer | yes | (min 1; max 12)
LedgerService | createLegalEntity | response | regionIds | array of string (uuid)
LedgerService | createLegalEntity | response | isActive | boolean
LedgerService | createLegalEntity | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
LedgerService | createLegalEntity | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | createLoyaltyProgramme | request | tiers | array of MarketingProgrammeTier | yes | Rows of marketing.programme_tier, the same shape MarketingProgrammeTier has — one definition of a tier, not a second copy that cannot round-trip.
MarketingService | createLoyaltyProgramme | request | tiers[].id | string (uuid) |  | (read-only)
MarketingService | createLoyaltyProgramme | request | tiers[].loyaltyProgrammeId | string (uuid) | yes | (read-only)
MarketingService | createLoyaltyProgramme | request | tiers[].code | string | yes | (max length 40)
MarketingService | createLoyaltyProgramme | request | tiers[].name | string | yes | (max length 120)
MarketingService | createLoyaltyProgramme | request | tiers[].rank | integer | yes | Order, not threshold.
MarketingService | createLoyaltyProgramme | request | tiers[].minLifetimePoints | integer |  | What reaching this tier requires. (nullable)
MarketingService | createLoyaltyProgramme | request | tiers[].retainLifetimePoints | integer |  | What keeping it requires, per review period. (nullable)
MarketingService | createLoyaltyProgramme | request | tiers[].validityMonths | integer |  | Null means the tier does not lapse on its own. (nullable)
MarketingService | createLoyaltyProgramme | request | tiers[].benefits | array of string |  | What the tier gives, as the guest reads it.
MarketingService | createLoyaltyProgramme | request | tiers[].earnMultiplier | number |  | Applied to every earn rule while the guest holds this tier. (nullable)
MarketingService | createLoyaltyProgramme | request | tiers[].isActive | boolean |  | (default True)
MarketingService | createLoyaltyProgramme | request | id | string (uuid) | yes | (read-only)
MarketingService | createLoyaltyProgramme | request | code | string | yes | Unique per tenant (decided 28 September, audit R108).
MarketingService | createLoyaltyProgramme | request | name | string | yes
MarketingService | createLoyaltyProgramme | request | venueId | string (uuid) |  | (nullable)
MarketingService | createLoyaltyProgramme | request | pointsLiabilityAccountId | string (uuid) |  | Points post here on accrual.
MarketingService | createLoyaltyProgramme | request | earnRules | array of object | yes
MarketingService | createLoyaltyProgramme | request | earnRules[].trigger | enum (perCurrencyUnit, perVisit, perProduct, onSignup, onBirthday, onReview) | yes
MarketingService | createLoyaltyProgramme | request | earnRules[].points | number | yes
MarketingService | createLoyaltyProgramme | request | earnRules[].productKinds | array of ProductKind: enum (admission, timedAdmission, datedAdmission, openDated, seated, membership, bundle, fnb, …) |  | Limits a perProduct or perCurrencyUnit rule to these kinds.
MarketingService | createLoyaltyProgramme | request | earnRules[].multiplier | number
MarketingService | createLoyaltyProgramme | request | pointsExpireAfterMonths | integer |  | (nullable)
MarketingService | createLoyaltyProgramme | request | isActive | boolean
MarketingService | createLoyaltyProgramme | response | tiers | array of MarketingProgrammeTier | yes | Rows of marketing.programme_tier, the same shape MarketingProgrammeTier has — one definition of a tier, not a second copy that cannot round-trip.
MarketingService | createLoyaltyProgramme | response | tiers[].id | string (uuid) |  | (read-only)
MarketingService | createLoyaltyProgramme | response | tiers[].loyaltyProgrammeId | string (uuid) | yes | (read-only)
MarketingService | createLoyaltyProgramme | response | tiers[].code | string | yes | (max length 40)
MarketingService | createLoyaltyProgramme | response | tiers[].name | string | yes | (max length 120)
MarketingService | createLoyaltyProgramme | response | tiers[].rank | integer | yes | Order, not threshold.
MarketingService | createLoyaltyProgramme | response | tiers[].minLifetimePoints | integer |  | What reaching this tier requires. (nullable)
MarketingService | createLoyaltyProgramme | response | tiers[].retainLifetimePoints | integer |  | What keeping it requires, per review period. (nullable)
MarketingService | createLoyaltyProgramme | response | tiers[].validityMonths | integer |  | Null means the tier does not lapse on its own. (nullable)
MarketingService | createLoyaltyProgramme | response | tiers[].benefits | array of string |  | What the tier gives, as the guest reads it.
MarketingService | createLoyaltyProgramme | response | tiers[].earnMultiplier | number |  | Applied to every earn rule while the guest holds this tier. (nullable)
MarketingService | createLoyaltyProgramme | response | tiers[].isActive | boolean |  | (default True)
MarketingService | createLoyaltyProgramme | response | id | string (uuid) | yes | (read-only)
MarketingService | createLoyaltyProgramme | response | code | string | yes | Unique per tenant (decided 28 September, audit R108).
MarketingService | createLoyaltyProgramme | response | name | string | yes
MarketingService | createLoyaltyProgramme | response | venueId | string (uuid) |  | (nullable)
MarketingService | createLoyaltyProgramme | response | pointsLiabilityAccountId | string (uuid) |  | Points post here on accrual.
MarketingService | createLoyaltyProgramme | response | earnRules | array of object | yes
MarketingService | createLoyaltyProgramme | response | earnRules[].trigger | enum (perCurrencyUnit, perVisit, perProduct, onSignup, onBirthday, onReview) | yes
MarketingService | createLoyaltyProgramme | response | earnRules[].points | number | yes
MarketingService | createLoyaltyProgramme | response | earnRules[].productKinds | array of ProductKind: enum (admission, timedAdmission, datedAdmission, openDated, seated, membership, bundle, fnb, …) |  | Limits a perProduct or perCurrencyUnit rule to these kinds.
MarketingService | createLoyaltyProgramme | response | earnRules[].multiplier | number
MarketingService | createLoyaltyProgramme | response | pointsExpireAfterMonths | integer |  | (nullable)
MarketingService | createLoyaltyProgramme | response | isActive | boolean
MarketingService | createLoyaltyProgramme | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | createMenu | request | code | string | yes | (max length 64)
FnbService | createMenu | request | name | string | yes | (max length 200)
FnbService | createMenu | request | outletId | string (uuid) | yes
FnbService | createMenu | request | availability | MenuAvailability |  | When this menu is in force.
FnbService | createMenu | request | availability.daysOfWeek | array of integer
FnbService | createMenu | request | availability.startTime | string |  | Wall-clock time, in the Region's time zone. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
FnbService | createMenu | request | availability.endTime | string |  | Wall-clock time, in the Region's time zone. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
FnbService | createMenu | request | availability.validFrom | string (date) |  | Calendar day, in the Region's time zone, not UTC. (nullable)
FnbService | createMenu | request | availability.validTo | string (date) |  | Calendar day, in the Region's time zone, not UTC. (nullable)
FnbService | createMenu | response | id | string (uuid) | yes
FnbService | createMenu | response | code | string | yes | (max length 64)
FnbService | createMenu | response | name | string | yes | (max length 200)
FnbService | createMenu | response | outletId | string (uuid) | yes
FnbService | createMenu | response | availability | MenuAvailability |  | When this menu is in force.
FnbService | createMenu | response | availability.daysOfWeek | array of integer
FnbService | createMenu | response | availability.startTime | string |  | Wall-clock time, in the Region's time zone. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
FnbService | createMenu | response | availability.endTime | string |  | Wall-clock time, in the Region's time zone. (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
FnbService | createMenu | response | availability.validFrom | string (date) |  | Calendar day, in the Region's time zone, not UTC. (nullable)
FnbService | createMenu | response | availability.validTo | string (date) |  | Calendar day, in the Region's time zone, not UTC. (nullable)
FnbService | createMenu | response | sections | array of MenuSection
FnbService | createMenu | response | sections[].id | string (uuid) |  | (read-only)
FnbService | createMenu | response | sections[].code | string | yes
FnbService | createMenu | response | sections[].name | string | yes
FnbService | createMenu | response | sections[].sortOrder | integer | yes
FnbService | createMenu | response | sections[].items | array of MenuItem |  | The section's items, in sale-board order.
FnbService | createMenu | response | sections[].items[].id | string (uuid) | yes
FnbService | createMenu | response | sections[].items[].productVariantId | string (uuid) | yes | The catalogue variant this item links to, for reporting, stock and tax class only.
FnbService | createMenu | response | sections[].items[].name | string | yes
FnbService | createMenu | response | sections[].items[].description | string |  | (nullable)
FnbService | createMenu | response | sections[].items[].price | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | createMenu | response | sections[].items[].dailyCount | integer |  | How many portions the kitchen set for today (setMenuItemDailyCount; Chinmay, 2 October, workbook Q194; CHG-CSA-017). (min 0; read-only; nullable)
FnbService | createMenu | response | sections[].items[].remainingCount | integer |  | What is left of dailyCount ("6 left" on the till and the guest menu). (min 0; read-only; nullable)
FnbService | createMenu | response | sections[].items[].sortOrder | integer
FnbService | createMenu | response | sections[].items[].modifierGroupIds | array of string (uuid)
FnbService | createMenu | response | sections[].items[].stationId | string (uuid) |  | (nullable)
FnbService | createMenu | response | sections[].items[].menuSectionId | string (uuid) |  | The section the item sits in, set by setMenuSections and applyMenuActions (moveSection). (read-only; nullable)
FnbService | createMenu | response | sections[].items[].isStockTracked | boolean |  | True where a recipe exists.
FnbService | createMenu | response | sections[].items[].isAvailable | boolean | yes
FnbService | createMenu | response | sections[].items[].unavailableReason | string |  | (nullable)
FnbService | createMenu | response | sections[].items[].restoreAt | string (date-time) |  | When an unavailable item comes back on its own (setItemAvailability). (nullable)
FnbService | createMenu | response | sections[].items[].preparationMinutes | integer |  | (nullable)
FnbService | createMenu | response | sections[].items[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | createMenu | response | isActive | boolean | yes
FnbService | createMenu | response | publishedVersion | integer |  | The MenuVersion.version live now. (read-only; nullable)
FnbService | createMenu | response | publishedAt | string (date-time) |  | (read-only; nullable)
FnbService | createMenu | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
RetailService | createMerchandise | request | sku | string | yes | (max length 64)
RetailService | createMerchandise | request | barcode | string |  | (max length 128)
RetailService | createMerchandise | request | name | string | yes | (max length 200)
RetailService | createMerchandise | request | description | string |  | What the item is, in the guest's words.
RetailService | createMerchandise | request | outletId | string (uuid) | yes
RetailService | createMerchandise | request | categoryId | string (uuid)
RetailService | createMerchandise | request | variantId | string (uuid) | yes
RetailService | createMerchandise | request | inventoryItemId | string (uuid)
RetailService | createMerchandise | request | isReturnable | boolean |  | (default True)
RetailService | createMerchandise | request | returnWindowDays | integer
RetailService | createMerchandise | request | requiresSerialNumber | boolean |  | (default False)
RetailService | createMerchandise | request | imageAssetRef | string
RetailService | createMerchandise | response | description | string |  | What the item is, in the guest's words.
RetailService | createMerchandise | response | id | string (uuid) | yes
RetailService | createMerchandise | response | sku | string | yes
RetailService | createMerchandise | response | barcode | string |  | (nullable)
RetailService | createMerchandise | response | name | string | yes
RetailService | createMerchandise | response | outletId | string (uuid) | yes
RetailService | createMerchandise | response | categoryId | string (uuid) |  | (nullable)
RetailService | createMerchandise | response | variantId | string (uuid) | yes | The catalogue variant sold.
RetailService | createMerchandise | response | inventoryItemId | string (uuid) |  | The stock item depleted on sale. (nullable)
RetailService | createMerchandise | response | price | Money | yes | On the wire this is three fields; in the database it is one column.
RetailService | createMerchandise | response | price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | createMerchandise | response | price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | createMerchandise | response | price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | createMerchandise | response | onHand | number | yes
RetailService | createMerchandise | response | isReturnable | boolean |  | (default True)
RetailService | createMerchandise | response | returnWindowDays | integer |  | (nullable)
RetailService | createMerchandise | response | requiresSerialNumber | boolean |  | (default False)
RetailService | createMerchandise | response | imageAssetRef | string |  | (nullable)
RetailService | createMerchandise | response | isActive | boolean | yes
RetailService | createMerchandise | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | createMessageTemplate | request | id | string (uuid) | yes | (read-only)
MarketingService | createMessageTemplate | request | code | string | yes | (max length 64)
MarketingService | createMessageTemplate | request | name | string | yes | (max length 200)
MarketingService | createMessageTemplate | request | channel | MessageChannel: enum (email, sms, whatsapp, push, inApp, post) | yes
MarketingService | createMessageTemplate | request | subjects | object |  | Per language.
MarketingService | createMessageTemplate | request | bodies | object | yes | Per language, keyed by ISO 639-1 code.
MarketingService | createMessageTemplate | request | mergeFields | array of string
MarketingService | createMessageTemplate | request | missingLanguages | array of string |  | Enabled languages without a body. (read-only)
MarketingService | createMessageTemplate | request | providerTemplateId | string |  | Required for WhatsApp, where templates are pre-approved by the provider. (nullable)
MarketingService | createMessageTemplate | request | brandId | string (uuid) |  | The brand whose identity the template carries; null for the tenant default. (nullable)
MarketingService | createMessageTemplate | request | ownership | enum (platform, crm) |  | platform = a transactional template owned by the communication service; crm = a marketing template owned by CRM (listSystemTransactionalTemplate). (default crm)
MarketingService | createMessageTemplate | response | id | string (uuid) | yes | (read-only)
MarketingService | createMessageTemplate | response | code | string | yes | (max length 64)
MarketingService | createMessageTemplate | response | name | string | yes | (max length 200)
MarketingService | createMessageTemplate | response | channel | MessageChannel: enum (email, sms, whatsapp, push, inApp, post) | yes
MarketingService | createMessageTemplate | response | subjects | object |  | Per language.
MarketingService | createMessageTemplate | response | bodies | object | yes | Per language, keyed by ISO 639-1 code.
MarketingService | createMessageTemplate | response | mergeFields | array of string
MarketingService | createMessageTemplate | response | missingLanguages | array of string |  | Enabled languages without a body. (read-only)
MarketingService | createMessageTemplate | response | providerTemplateId | string |  | Required for WhatsApp, where templates are pre-approved by the provider. (nullable)
MarketingService | createMessageTemplate | response | brandId | string (uuid) |  | The brand whose identity the template carries; null for the tenant default. (nullable)
MarketingService | createMessageTemplate | response | ownership | enum (platform, crm) |  | platform = a transactional template owned by the communication service; crm = a marketing template owned by CRM (listSystemTransactionalTemplate). (default crm)
MarketingService | createMessageTemplate | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | createMfaChallenge | request | action | string | yes | What the step-up is for.
IdentityService | createMfaChallenge | request | methodId | string (uuid)
IdentityService | createMfaChallenge | request | venueId | string (uuid) |  | For a guest, the venue whose VenueSettings.identity.guestTwoStep applies (sign-in venue, or the venue of the booking being acted on). (nullable)
IdentityService | createMfaChallenge | response | challengeId | string
IdentityService | createMfaChallenge | response | expiresAt | string (date-time)
IdentityService | createMfaChallenge | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | createModifierGroup | request | id | string (uuid) | yes
FnbService | createModifierGroup | request | code | string | yes
FnbService | createModifierGroup | request | name | string | yes
FnbService | createModifierGroup | request | minSelections | integer | yes | Greater than zero makes the group required. (min 0)
FnbService | createModifierGroup | request | maxSelections | integer | yes | (min 1)
FnbService | createModifierGroup | request | options | array of object | yes | (min items 1)
FnbService | createModifierGroup | request | options[].id | string (uuid) | yes
FnbService | createModifierGroup | request | options[].name | string | yes
FnbService | createModifierGroup | request | options[].priceDelta | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | createModifierGroup | request | options[].priceDelta.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | createModifierGroup | request | options[].priceDelta.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | createModifierGroup | request | options[].priceDelta.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | createModifierGroup | request | options[].isDefault | boolean
FnbService | createModifierGroup | request | options[].isAvailable | boolean
FnbService | createModifierGroup | request | options[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …) |  | What choosing this option adds to the dish.
FnbService | createModifierGroup | request | scopePath | string |  | The partition key (ADR-0005).
FnbService | createModifierGroup | response | id | string (uuid) | yes
FnbService | createModifierGroup | response | code | string | yes
FnbService | createModifierGroup | response | name | string | yes
FnbService | createModifierGroup | response | minSelections | integer | yes | Greater than zero makes the group required. (min 0)
FnbService | createModifierGroup | response | maxSelections | integer | yes | (min 1)
FnbService | createModifierGroup | response | options | array of object | yes | (min items 1)
FnbService | createModifierGroup | response | options[].id | string (uuid) | yes
FnbService | createModifierGroup | response | options[].name | string | yes
FnbService | createModifierGroup | response | options[].priceDelta | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | createModifierGroup | response | options[].priceDelta.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | createModifierGroup | response | options[].priceDelta.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | createModifierGroup | response | options[].priceDelta.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | createModifierGroup | response | options[].isDefault | boolean
FnbService | createModifierGroup | response | options[].isAvailable | boolean
FnbService | createModifierGroup | response | options[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …) |  | What choosing this option adds to the dish.
FnbService | createModifierGroup | response | scopePath | string |  | The partition key (ADR-0005).
FnbService | createModifierGroup | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createOrder | request | id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createOrder | request | venueId | string (uuid) | yes
OrderService | createOrder | request | channel | Channel: enum (pos, kiosk, web, mobile, b2b, ota, callCentre) | yes
OrderService | createOrder | request | shiftId | string (uuid)
OrderService | createOrder | request | subjectId | string (uuid) |  | Null for an anonymous sale. (nullable)
OrderService | createOrder | request | guestLinkId | string |  | Present where the guest is linked across cells. (nullable)
OrderService | createOrder | request | catalogueBundleVersion | string |  | The bundle the client priced from.
OrderService | createOrder | request | lines | array of CreateOrderLine | yes | (min items 1)
OrderService | createOrder | request | lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | createOrder | request | lines[].variantId | string (uuid) | yes
OrderService | createOrder | request | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | createOrder | request | lines[].performanceId | string (uuid)
OrderService | createOrder | request | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | createOrder | request | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | createOrder | request | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | createOrder | request | lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | createOrder | request | lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | createOrder | request | lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | createOrder | request | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | createOrder | request | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | createOrder | request | lines[].quantity | integer | yes | (min 1)
OrderService | createOrder | request | lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | createOrder | request | lines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | createOrder | request | lines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | createOrder | request | lines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | createOrder | request | lines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | createOrder | request | lines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | createOrder | request | lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | createOrder | request | lines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | request | lines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | request | lines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | request | lines[].holderName | string |  | (nullable)
OrderService | createOrder | request | lines[].dataMaskValues | object |  | Deliberately open.
OrderService | createOrder | request | recordedAt | string (date-time) | yes
OrderService | createOrder | response | id | string (uuid) | yes | The client UUIDv7 from CreateOrderRequest.id.
OrderService | createOrder | response | orderNumber | string |  | The number a guest reads and a cashier types. (read-only)
OrderService | createOrder | response | channel | object | yes | Where it came from.
OrderService | createOrder | response | channelProfileId | string (uuid) |  | The named sales channel the order came through (catalogue SalesChannelProfile.id), set by the server from the caller: a partner user's or reseller's channel, an API key's channel. (read-only; nullable)
OrderService | createOrder | response | venueId | string (uuid) | yes
OrderService | createOrder | response | scopePath | string | yes
OrderService | createOrder | response | status | OrderStatus: enum (pending, held, paid, partiallyPaid, completed, voided, refunded, partiallyRefunded, …) | yes | held is a parked sale — the cashier freed the till and the guest will return.
OrderService | createOrder | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | createOrder | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createOrder | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createOrder | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createOrder | response | netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | refundedAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | createOrder | response | refundedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | refundedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | refundedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | chargeCurrency | string |  | The currency the guest selected and is charged in (CHG-FIN-001, 2 October 2026). (pattern ^[A-Z]{3}$; read-only; nullable)
OrderService | createOrder | response | chargeFxRate | object |  | Units of chargeCurrency per one unit of the base currency, from the region's tender rate in force at checkout (finance.FxRate), stored on the order so the payment, the receipt, the tax invoice and an… (read-only; nullable)
OrderService | createOrder | response | chargeFxRateId | string (uuid) |  | The finance.FxRate row the rate was taken from, for audit. (read-only; nullable)
OrderService | createOrder | response | chargeTotal | object |  | grossAmount converted at chargeFxRate and rounded to the charge currency's scale: what the guest pays and what the payment request to the provider asks for (CHG-FIN-001). (read-only)
OrderService | createOrder | response | chargeTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | chargeTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | chargeTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | chargeRateLockedUntil | string (date-time) |  | The quote holds until then (the cart lease). (read-only; nullable)
OrderService | createOrder | response | droppedPromotions | array of object |  | Promotions left off this order at checkout because their budget cap would have been exceeded (decided 28 September, audit R101 (8)). (read-only)
OrderService | createOrder | response | droppedPromotions[].promotionId | string (uuid) | yes
OrderService | createOrder | response | droppedPromotions[].name | string
OrderService | createOrder | response | droppedPromotions[].reason | enum (budgetCapReached)
OrderService | createOrder | response | totalPriceVariance | object |  | Sum across lines.
OrderService | createOrder | response | totalPriceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | totalPriceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | totalPriceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | lines | array of OrderLine | yes
OrderService | createOrder | response | lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | createOrder | response | lines[].variantId | string (uuid) | yes
OrderService | createOrder | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | createOrder | response | lines[].performanceId | string (uuid)
OrderService | createOrder | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | createOrder | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | createOrder | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | createOrder | response | lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | createOrder | response | lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | createOrder | response | lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | createOrder | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | createOrder | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | createOrder | response | lines[].quantity | integer | yes | (min 1)
OrderService | createOrder | response | lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | createOrder | response | lines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | createOrder | response | lines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | createOrder | response | lines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | createOrder | response | lines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | createOrder | response | lines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | createOrder | response | lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | createOrder | response | lines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | lines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | lines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | lines[].holderName | string |  | (nullable)
OrderService | createOrder | response | lines[].dataMaskValues | object |  | Deliberately open.
OrderService | createOrder | response | lines[].serverUnitPrice | object | yes | What the server computed on ingest.
OrderService | createOrder | response | lines[].serverUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | lines[].serverUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | lines[].serverUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | lines[].priceVariance | object |  | Server minus quoted.
OrderService | createOrder | response | lines[].priceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | lines[].priceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | lines[].priceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createOrder | response | lines[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | lines[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | lines[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createOrder | response | lines[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | lines[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | lines[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createOrder | response | lines[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | lines[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | lines[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | lines[].entitlementIds | array of string (uuid) |  | The entitlements this line issued.
OrderService | createOrder | response | lines[].crossRegionRightIds | array of string |  | Redemption rights propagated to other cells for this line.
OrderService | createOrder | response | lines[].reprintCount | integer |  | How many times this line's tickets were reprinted or resent. (min 0; default 0; read-only)
OrderService | createOrder | response | lines[].venueId | string (uuid) |  | The order's venue, copied onto the line (ADR-0044's own example; system-design review SD-008, 29 September) so a line is scoped and partitionable without its order. (read-only)
OrderService | createOrder | response | lines[].discounts | array of OrderLineDiscount |  | The discounts applied to this line, one row each (system-design review SD-008, 29 September). (read-only)
OrderService | createOrder | response | lines[].discounts[].id | string (uuid) | yes
OrderService | createOrder | response | lines[].discounts[].promotionId | string (uuid) |  | The promotion that gave it. (nullable)
OrderService | createOrder | response | lines[].discounts[].source | enum (promotion, promoCode, manual, bundle, member) | yes
OrderService | createOrder | response | lines[].discounts[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createOrder | response | lines[].discounts[].reason | string |  | A cashier's reason for a manual discount. (max length 200; nullable)
OrderService | createOrder | response | payments | array of Payment
OrderService | createOrder | response | payments[].id | string (uuid) | yes
OrderService | createOrder | response | payments[].orderId | string (uuid) | yes
OrderService | createOrder | response | payments[].tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | createOrder | response | payments[].tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | payments[].tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale.
OrderService | createOrder | response | payments[].tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | payments[].tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | payments[].tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | payments[].fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | createOrder | response | payments[].fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | createOrder | response | payments[].changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | createOrder | response | payments[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createOrder | response | payments[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | payments[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | payments[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | payments[].changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | createOrder | response | payments[].changeAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createOrder | response | payments[].changeAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createOrder | response | payments[].changeAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createOrder | response | payments[].status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | createOrder | response | payments[].providerName | string |  | (nullable)
OrderService | createOrder | response | payments[].providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | createOrder | response | payments[].providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | createOrder | response | payments[].terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | createOrder | response | payments[].nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | createOrder | response | payments[].nextAction.kind | enum (redirect, terminal)
OrderService | createOrder | response | payments[].nextAction.url | string (uri) |  | (nullable)
OrderService | createOrder | response | payments[].nextAction.expiresAt | string (date-time) |  | (nullable)
OrderService | createOrder | response | payments[].lastInquiryAt | string (date-time) |  | (nullable)
OrderService | createOrder | response | payments[].recordedAt | string (date-time) | yes
OrderService | createOrder | response | payments[].syncedAt | string (date-time) |  | (nullable)
OrderService | createOrder | response | principalId | string (uuid)
OrderService | createOrder | response | workstationId | string (uuid)
OrderService | createOrder | response | shiftId | string (uuid) |  | (nullable)
OrderService | createOrder | response | subjectId | string (uuid) |  | (nullable)
OrderService | createOrder | response | holdLabel | string |  | The label a cashier gave when parking it with holdOrder — how they find it again. (max length 60; read-only; nullable)
OrderService | createOrder | response | heldUntil | string (date-time) |  | When a held order expires and is voided (states/order.yaml), from holdOrder's holdUntil. (read-only; nullable)
OrderService | createOrder | response | createdAt | string (date-time) | yes
OrderService | createOrder | response | recordedAt | string (date-time) | yes
OrderService | createOrder | response | syncedAt | string (date-time) |  | (nullable)
OrderService | createOrder | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | createOrgUnit | request | level | ScopeLevel: enum (tenant, brand, region, venue, department, subDepartment, workstation, outlet) | yes | Seven organisational levels, confirmed binding (ADR-0011), plus outlet.
TenancyService | createOrgUnit | request | parentId | string (uuid) | yes | Required for every level except tenant, which the cell creates at provisioning.
TenancyService | createOrgUnit | request | code | string | yes | Becomes the final ltree segment. (max length 64; pattern ^[a-z0-9_]+$)
TenancyService | createOrgUnit | request | name | string | yes | (max length 200)
TenancyService | createOrgUnit | response | id | string (uuid) | yes
TenancyService | createOrgUnit | response | level | ScopeLevel: enum (tenant, brand, region, venue, department, subDepartment, workstation, outlet) | yes | Seven organisational levels, confirmed binding (ADR-0011), plus outlet.
TenancyService | createOrgUnit | response | parentId | string (uuid) |  | (nullable)
TenancyService | createOrgUnit | response | path | string | yes | Materialised ltree path, e.g. (pattern ^[a-z0-9_]+(\.[a-z0-9_]+)*$)
TenancyService | createOrgUnit | response | code | string | yes | (max length 64)
TenancyService | createOrgUnit | response | name | string | yes | (max length 200)
TenancyService | createOrgUnit | response | isActive | boolean | yes | False causes every permission query at or beneath this node to resolve to DENY.
TenancyService | createOrgUnit | response | childCount | integer |  | (min 0)
TenancyService | createOrgUnit | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | createOutlet | request | id | string (uuid) | yes | (read-only)
TenancyService | createOutlet | request | code | string | yes | (max length 64)
TenancyService | createOutlet | request | name | string | yes | The outlet's name in English. (max length 200)
TenancyService | createOutlet | request | nameTranslations | OutletNameTranslations |  | The outlet's name in other languages, keyed by ISO 639-1 code (decided 2 October 2026, Chinmay, batch 2 #26, BO-044: "Yes, where a country needs it: the local language plus English"; DEC-031; CHG-CSP…
TenancyService | createOutlet | request | venueId | string (uuid) | yes
TenancyService | createOutlet | request | kind | OutletKind: enum (shop, restaurant, bar, cafe, kiosk, gameFloor, ticketOffice, mobile) | yes
TenancyService | createOutlet | request | outletType | object |  | The service model (DI-319; DEC-196; CHG-CSP-005). (nullable)
TenancyService | createOutlet | request | departmentId | string (uuid) |  | The department the outlet belongs to (DI-319: department, sub-department, cost centre and status; DEC-196; CHG-CSP-005): an OrgUnit of kind department, as Workstation.departmentId. (nullable)
TenancyService | createOutlet | request | zone | string |  | (nullable)
TenancyService | createOutlet | request | stockLocationId | string (uuid) |  | Where this outlet draws stock from. (nullable)
TenancyService | createOutlet | request | costCenterId | string (uuid) |  | Revenue and cost attribution. (nullable)
TenancyService | createOutlet | request | paymentTiming | object |  | Pay first, or send to the kitchen first then pay (DEC-064; CHG-CSP-004). (default sendFirst)
TenancyService | createOutlet | request | admissionContext | object |  | Inside the venue (needs an admission ticket) or standalone (no ticket) (DEC-070; CHG-CSP-004). (default insideVenue)
TenancyService | createOutlet | request | producesForOutletIds | array of string (uuid) |  | One kitchen serving several outlets is a producing outlet (decided 2 October 2026, Chinmay, batch 6 set 5, BO-134: "Yes: via a producing outlet (one kitchen outlet produces for several)"; DEC-188; CH… (default [])
TenancyService | createOutlet | request | saleBoardId | string (uuid) |  | The till layout every till in this outlet uses, unless a till overrides it (decided 2 October 2026, Chinmay, batch 6 set 4, BO-109: "Per outlet, with a till override"; DEC-183; CHG-CSP-006). (nullable)
TenancyService | createOutlet | request | openingHours | array of OpeningHoursWindow |  | The weekly pattern, one entry per window.
TenancyService | createOutlet | request | openingHours[].day | enum (mon, tue, wed, thu, fri, sat, sun) | yes
TenancyService | createOutlet | request | openingHours[].from | string | yes | Local time, 24-hour HH:MM, when the outlet opens. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
TenancyService | createOutlet | request | openingHours[].to | string | yes | Local time, 24-hour HH:MM, when the outlet closes. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
TenancyService | createOutlet | request | openingHours[].endsNextDay | boolean |  | A late-night window is one window past midnight (decided 2 October 2026, Chinmay, batch 6 set 6a, BO-731; DEC-197; CHG-CSP-007). (default False)
TenancyService | createOutlet | request | isActive | boolean
TenancyService | createOutlet | response | id | string (uuid) | yes | (read-only)
TenancyService | createOutlet | response | code | string | yes | (max length 64)
TenancyService | createOutlet | response | name | string | yes | The outlet's name in English. (max length 200)
TenancyService | createOutlet | response | nameTranslations | OutletNameTranslations |  | The outlet's name in other languages, keyed by ISO 639-1 code (decided 2 October 2026, Chinmay, batch 2 #26, BO-044: "Yes, where a country needs it: the local language plus English"; DEC-031; CHG-CSP…
TenancyService | createOutlet | response | venueId | string (uuid) | yes
TenancyService | createOutlet | response | kind | OutletKind: enum (shop, restaurant, bar, cafe, kiosk, gameFloor, ticketOffice, mobile) | yes
TenancyService | createOutlet | response | outletType | object |  | The service model (DI-319; DEC-196; CHG-CSP-005). (nullable)
TenancyService | createOutlet | response | departmentId | string (uuid) |  | The department the outlet belongs to (DI-319: department, sub-department, cost centre and status; DEC-196; CHG-CSP-005): an OrgUnit of kind department, as Workstation.departmentId. (nullable)
TenancyService | createOutlet | response | zone | string |  | (nullable)
TenancyService | createOutlet | response | stockLocationId | string (uuid) |  | Where this outlet draws stock from. (nullable)
TenancyService | createOutlet | response | costCenterId | string (uuid) |  | Revenue and cost attribution. (nullable)
TenancyService | createOutlet | response | paymentTiming | object |  | Pay first, or send to the kitchen first then pay (DEC-064; CHG-CSP-004). (default sendFirst)
TenancyService | createOutlet | response | admissionContext | object |  | Inside the venue (needs an admission ticket) or standalone (no ticket) (DEC-070; CHG-CSP-004). (default insideVenue)
TenancyService | createOutlet | response | producesForOutletIds | array of string (uuid) |  | One kitchen serving several outlets is a producing outlet (decided 2 October 2026, Chinmay, batch 6 set 5, BO-134: "Yes: via a producing outlet (one kitchen outlet produces for several)"; DEC-188; CH… (default [])
TenancyService | createOutlet | response | saleBoardId | string (uuid) |  | The till layout every till in this outlet uses, unless a till overrides it (decided 2 October 2026, Chinmay, batch 6 set 4, BO-109: "Per outlet, with a till override"; DEC-183; CHG-CSP-006). (nullable)
TenancyService | createOutlet | response | openingHours | array of OpeningHoursWindow |  | The weekly pattern, one entry per window.
TenancyService | createOutlet | response | openingHours[].day | enum (mon, tue, wed, thu, fri, sat, sun) | yes
TenancyService | createOutlet | response | openingHours[].from | string | yes | Local time, 24-hour HH:MM, when the outlet opens. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
TenancyService | createOutlet | response | openingHours[].to | string | yes | Local time, 24-hour HH:MM, when the outlet closes. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
TenancyService | createOutlet | response | openingHours[].endsNextDay | boolean |  | A late-night window is one window past midnight (decided 2 October 2026, Chinmay, batch 6 set 6a, BO-731; DEC-197; CHG-CSP-007). (default False)
TenancyService | createOutlet | response | isActive | boolean
TenancyService | createOutlet | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createPayment | request | id | string (uuid) | yes | Client-generated UUIDv7 of the payment, and its idempotency key — it must equal the Idempotency-Key header.
OrderService | createPayment | request | orderId | string (uuid) | yes
OrderService | createPayment | request | tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | createPayment | request | amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createPayment | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createPayment | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createPayment | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createPayment | request | tenderCurrency | string |  | The currency the guest handed over, where it is not the venue's — becomes Payment.tenderCurrency. (pattern ^[A-Z]{3}$; nullable)
OrderService | createPayment | request | tenderAmount | object |  | What the guest handed over, in tenderCurrency — becomes Payment.tenderAmount, one name for one concept (renamed from tenderedAmount on 26 September).
OrderService | createPayment | request | tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createPayment | request | tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createPayment | request | tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createPayment | request | walletAuthorisationId | string |  | Cross-cell wallet hold, where the guest's home cell is elsewhere. (nullable)
OrderService | createPayment | request | walletHoldId | string (uuid) |  | For a wallet tender, the hold wallet.holdWalletFunds placed (SD-027). (nullable)
OrderService | createPayment | request | returnUrl | string (uri) |  | Where the provider returns the guest after a 3-D Secure challenge or hosted page (SD-034). (nullable)
OrderService | createPayment | request | terminalId | string (uuid) |  | The card terminal to instruct, for a card payment at a till (ECR flow, SD-034). (nullable)
OrderService | createPayment | request | deviceId | string (uuid) |  | (nullable)
OrderService | createPayment | request | recordedAt | string (date-time) | yes
OrderService | createPayment | response | id | string (uuid) | yes
OrderService | createPayment | response | orderId | string (uuid) | yes
OrderService | createPayment | response | tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | createPayment | response | tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | createPayment | response | tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale.
OrderService | createPayment | response | tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createPayment | response | tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createPayment | response | tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createPayment | response | fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | createPayment | response | fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | createPayment | response | changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | createPayment | response | amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createPayment | response | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createPayment | response | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createPayment | response | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createPayment | response | changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | createPayment | response | changeAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createPayment | response | changeAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createPayment | response | changeAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createPayment | response | status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | createPayment | response | providerName | string |  | (nullable)
OrderService | createPayment | response | providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | createPayment | response | providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | createPayment | response | terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | createPayment | response | nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | createPayment | response | nextAction.kind | enum (redirect, terminal)
OrderService | createPayment | response | nextAction.url | string (uri) |  | (nullable)
OrderService | createPayment | response | nextAction.expiresAt | string (date-time) |  | (nullable)
OrderService | createPayment | response | lastInquiryAt | string (date-time) |  | (nullable)
OrderService | createPayment | response | recordedAt | string (date-time) | yes
OrderService | createPayment | response | syncedAt | string (date-time) |  | (nullable)
OrderService | createPayment | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createPaymentProviderConnection | request | id | string (uuid)
OrderService | createPaymentProviderConnection | request | code | string | yes
OrderService | createPaymentProviderConnection | request | name | string
OrderService | createPaymentProviderConnection | request | providerKind | enum (gateway, psp, acquirer, walletProvider, bnplProvider) | yes
OrderService | createPaymentProviderConnection | request | environment | enum (sandbox, production)
OrderService | createPaymentProviderConnection | request | credentialFingerprint | string |  | Written, never read back. (read-only)
OrderService | createPaymentProviderConnection | request | capabilities | object
OrderService | createPaymentProviderConnection | request | capabilities.methods | array of string
OrderService | createPaymentProviderConnection | request | capabilities.currencies | array of string
OrderService | createPaymentProviderConnection | request | capabilities.partialCapture | boolean |  | (default False)
OrderService | createPaymentProviderConnection | request | capabilities.multipleCapture | boolean |  | (default False)
OrderService | createPaymentProviderConnection | request | capabilities.refundWindowDays | integer |  | (nullable)
OrderService | createPaymentProviderConnection | request | capabilities.tokenisation | boolean |  | (default False)
OrderService | createPaymentProviderConnection | request | capabilities.threeDSecure | boolean |  | (default False)
OrderService | createPaymentProviderConnection | request | capabilities.cardPresent | boolean |  | (default False)
OrderService | createPaymentProviderConnection | request | merchantAccountId | string (uuid) |  | (nullable)
OrderService | createPaymentProviderConnection | request | status | enum (draft, testing, active, degraded, disabled)
OrderService | createPaymentProviderConnection | request | lastTestedAt | string (date-time) |  | (nullable)
OrderService | createPaymentProviderConnection | request | scopePath | string
OrderService | createPaymentProviderConnection | request | credentialRef | string |  | Where the provider credential is kept (4 October 2026, CHG-FXC-010; ADM-570): the vault reference the credential was stored under, as SetPaymentProviderRequest.credentialRef.
OrderService | createPaymentProviderConnection | response | id | string (uuid)
OrderService | createPaymentProviderConnection | response | code | string | yes
OrderService | createPaymentProviderConnection | response | name | string
OrderService | createPaymentProviderConnection | response | providerKind | enum (gateway, psp, acquirer, walletProvider, bnplProvider) | yes
OrderService | createPaymentProviderConnection | response | environment | enum (sandbox, production)
OrderService | createPaymentProviderConnection | response | credentialFingerprint | string |  | Written, never read back. (read-only)
OrderService | createPaymentProviderConnection | response | capabilities | object
OrderService | createPaymentProviderConnection | response | capabilities.methods | array of string
OrderService | createPaymentProviderConnection | response | capabilities.currencies | array of string
OrderService | createPaymentProviderConnection | response | capabilities.partialCapture | boolean |  | (default False)
OrderService | createPaymentProviderConnection | response | capabilities.multipleCapture | boolean |  | (default False)
OrderService | createPaymentProviderConnection | response | capabilities.refundWindowDays | integer |  | (nullable)
OrderService | createPaymentProviderConnection | response | capabilities.tokenisation | boolean |  | (default False)
OrderService | createPaymentProviderConnection | response | capabilities.threeDSecure | boolean |  | (default False)
OrderService | createPaymentProviderConnection | response | capabilities.cardPresent | boolean |  | (default False)
OrderService | createPaymentProviderConnection | response | merchantAccountId | string (uuid) |  | (nullable)
OrderService | createPaymentProviderConnection | response | status | enum (draft, testing, active, degraded, disabled)
OrderService | createPaymentProviderConnection | response | lastTestedAt | string (date-time) |  | (nullable)
OrderService | createPaymentProviderConnection | response | scopePath | string
OrderService | createPaymentProviderConnection | response | credentialRef | string |  | Where the provider credential is kept (4 October 2026, CHG-FXC-010; ADM-570): the vault reference the credential was stored under, as SetPaymentProviderRequest.credentialRef.
OrderService | createPaymentProviderConnection | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | createPerformances | request | startsAt | string (date-time) | yes
CatalogueService | createPerformances | request | endsAt | string (date-time) | yes
CatalogueService | createPerformances | request | admissionRulesId | string (uuid)
CatalogueService | createPerformances | request | seatMapId | string (uuid)
CatalogueService | createPerformances | request | language | string |  | As Performance.language; every performance of a generated series takes it (decided 29 September, rev 3 REV3-17). (max length 35; pattern ^[A-Za-z]{2,3}(-[A-Za-z0-9]{1,8})*$; nullable)
CatalogueService | createPerformances | request | format | string |  | As Performance.format (decided 29 September, rev 3 REV3-17). (max length 40; nullable)
CatalogueService | createPerformances | request | minutesOnScreen | integer |  | As Performance.minutesOnScreen; every performance of a generated series takes it (DI-167, DI-169; CHG-R4-014). (min 0; max 1440)
CatalogueService | createPerformances | request | slotLengthMinutes | integer |  | The slot length the form asks for (DI-167, DI-995; CHG-R4-014): every generated performance ends this many minutes after it starts. (min 1; max 1440)
CatalogueService | createPerformances | request | recurrence | object |  | Generate a series rather than a single performance.
CatalogueService | createPerformances | request | recurrence.intervalMinutes | integer |  | (min 1)
CatalogueService | createPerformances | request | recurrence.until | string (date-time)
CatalogueService | createPerformances | request | recurrence.daysOfWeek | array of integer
CatalogueService | createPerformances | request | recurrence.firstStartTime | string |  | The first start of each day, HH:MM on the region's clock (DI-995, 24 September minutes M24-01; CHG-R4-014). (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
CatalogueService | createPerformances | request | recurrence.lastStartTime | string |  | The last start of each day, HH:MM on the region's clock (DI-995; CHG-R4-014): no slot of the day starts after it, so a series every 30 minutes from 10:00 with a last start of 17:30 makes 16 slots a d… (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
CatalogueService | createPerformances | response | created | integer
CatalogueService | createPerformances | response | performances | array of Performance
CatalogueService | createPerformances | response | performances[].id | string (uuid) | yes
CatalogueService | createPerformances | response | performances[].eventId | string (uuid) | yes
CatalogueService | createPerformances | response | performances[].startsAt | string (date-time) | yes
CatalogueService | createPerformances | response | performances[].endsAt | string (date-time) | yes
CatalogueService | createPerformances | response | performances[].approvalRequestId | string (uuid) |  | BL-048. (nullable)
CatalogueService | createPerformances | response | performances[].requiresApprovalToCancel | boolean |  | Cancelling a sold performance is the one transition that needs a name against it. (default True)
CatalogueService | createPerformances | response | performances[].status | enum (scheduled, onSale, soldOut, suspended, cancelled, completed) | yes
CatalogueService | createPerformances | response | performances[].admissionRulesId | string (uuid) |  | (nullable)
CatalogueService | createPerformances | response | performances[].seatMapId | string (uuid) |  | (nullable)
CatalogueService | createPerformances | response | performances[].language | string |  | The language the performance is given in, as a BCP 47 tag (en, ar, fr, de, zh, ru, ar-AE). (max length 35; pattern ^[A-Za-z]{2,3}(-[A-Za-z0-9]{1,8})*$; nullable)
CatalogueService | createPerformances | response | performances[].format | string |  | How it is presented, free text the venue chooses, e.g. (max length 40; nullable)
CatalogueService | createPerformances | response | performances[].minutesOnScreen | integer |  | "Minutes on screen": how long after startsAt the slot is still sold (agreed 7 August, DI-167 and DI-169; added 6 October 2026, CHG-R4-014). (min 0; max 1440; default 0)
CatalogueService | createPerformances | param (path) | eventId | string (uuid) | yes
CatalogueService | createPerformances | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | createPerformances | param (header) | Prefer | enum (validate-only) |  | Validate, do not write (29 September, AI system design 2.3 and 2.2 D step 4).
PlatformService | createPlan | request | code | string | yes | (max length 64)
PlatformService | createPlan | request | name | string | yes | (max length 200)
PlatformService | createPlan | request | description | string |  | (max length 1000)
PlatformService | createPlan | request | cellTier | CellTier: enum (shared, dedicated, isolated, clientHosted) | yes
PlatformService | createPlan | request | licensedModules | array of ModuleKey: enum (core, ticketing, access, fnb, retail, inventory, seating, membership, …) | yes | A closed set as of 24 August. (min items 1)
PlatformService | createPlan | request | limits | array of EntitlementLimit | yes
PlatformService | createPlan | request | limits[].metric | UsageMetric: enum (venues, workstations, activeUsers, devices, brandedApps, aiTokens, apiCalls, storageGb, …) | yes
PlatformService | createPlan | request | limits[].limit | integer | yes | Null means unlimited. (nullable)
PlatformService | createPlan | request | limits[].overageAllowed | boolean |  | (default False)
PlatformService | createPlan | request | limits[].overageUnitPrice | Money |  | On the wire this is three fields; in the database it is one column.
PlatformService | createPlan | request | limits[].overageUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
PlatformService | createPlan | request | limits[].overageUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
PlatformService | createPlan | request | limits[].overageUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
PlatformService | createPlan | request | basePrice | Money | yes | On the wire this is three fields; in the database it is one column.
PlatformService | createPlan | request | basePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
PlatformService | createPlan | request | basePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
PlatformService | createPlan | request | basePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
PlatformService | createPlan | request | billingPeriod | enum (monthly, quarterly, annual)
PlatformService | createPlan | request | includesBrandedApp | boolean |  | Branded native publishing carries per-tenant operational cost and is priced, not absorbed.
PlatformService | createPlan | request | includedAiTokens | integer |  | AI tokens the package includes per billing period. (nullable)
PlatformService | createPlan | request | requestLimits | PlanRequestLimits |  | The limits section of a plan: every tenant has a request budget (ADR-0064, accepted 1 October; it decides the per-tenant limit ADR-0032 deferred). (nullable)
PlatformService | createPlan | request | requestLimits.guest | RequestBudget |  | One audience's bucket (ADR-0064).
PlatformService | createPlan | request | requestLimits.guest.sustainedPerSecond | integer | yes | Requests per second the bucket refills at. (min 1)
PlatformService | createPlan | request | requestLimits.guest.burstMultiplier | number |  | How far above the sustained rate a burst may go (2 is twice the rate). (min 1; default 2)
PlatformService | createPlan | request | requestLimits.guest.burstSeconds | integer |  | How long a burst may last. (min 1; default 10)
PlatformService | createPlan | request | requestLimits.staff | RequestBudget |  | One audience's bucket (ADR-0064).
PlatformService | createPlan | request | requestLimits.staff.sustainedPerSecond | integer | yes | Requests per second the bucket refills at. (min 1)
PlatformService | createPlan | request | requestLimits.staff.burstMultiplier | number |  | How far above the sustained rate a burst may go (2 is twice the rate). (min 1; default 2)
PlatformService | createPlan | request | requestLimits.staff.burstSeconds | integer |  | How long a burst may last. (min 1; default 10)
PlatformService | createPlan | request | requestLimits.service | RequestBudget |  | One audience's bucket (ADR-0064).
PlatformService | createPlan | request | requestLimits.service.sustainedPerSecond | integer | yes | Requests per second the bucket refills at. (min 1)
PlatformService | createPlan | request | requestLimits.service.burstMultiplier | number |  | How far above the sustained rate a burst may go (2 is twice the rate). (min 1; default 2)
PlatformService | createPlan | request | requestLimits.service.burstSeconds | integer |  | How long a burst may last. (min 1; default 10)
PlatformService | createPlan | request | requestLimits.partner | RequestBudget |  | One audience's bucket (ADR-0064).
PlatformService | createPlan | request | requestLimits.partner.sustainedPerSecond | integer | yes | Requests per second the bucket refills at. (min 1)
PlatformService | createPlan | request | requestLimits.partner.burstMultiplier | number |  | How far above the sustained rate a burst may go (2 is twice the rate). (min 1; default 2)
PlatformService | createPlan | request | requestLimits.partner.burstSeconds | integer |  | How long a burst may last. (min 1; default 10)
PlatformService | createPlan | request | requestLimits.replicaSharePercent | integer |  | The most of one replica's request slots one tenant may hold while the share is enforced. (min 1; max 100; default 25)
PlatformService | createPlan | request | requestLimits.shareEnforcedAbovePercent | integer |  | The replica load, as a percent of its limit, above which the share is enforced. (min 1; max 100; default 70)
PlatformService | createPlan | request | packageKind | enum (standard, custom) |  | Three standard packages, and custom ones allowed (decided 29 September, Chinmay). (default standard)
PlatformService | createPlan | request | offeredToTenantId | string (uuid) |  | Private to one tenant (decided 29 September, Chinmay): a custom package offered only to this tenant; listPlans shows it to no other tenant and setSubscription refuses it for any other (422 plan-not-o… (nullable)
PlatformService | createPlan | response | code | string | yes | (max length 64)
PlatformService | createPlan | response | name | string | yes | (max length 200)
PlatformService | createPlan | response | description | string |  | (max length 1000)
PlatformService | createPlan | response | cellTier | CellTier: enum (shared, dedicated, isolated, clientHosted) | yes
PlatformService | createPlan | response | licensedModules | array of ModuleKey: enum (core, ticketing, access, fnb, retail, inventory, seating, membership, …) | yes | A closed set as of 24 August. (min items 1)
PlatformService | createPlan | response | limits | array of EntitlementLimit | yes
PlatformService | createPlan | response | limits[].metric | UsageMetric: enum (venues, workstations, activeUsers, devices, brandedApps, aiTokens, apiCalls, storageGb, …) | yes
PlatformService | createPlan | response | limits[].limit | integer | yes | Null means unlimited. (nullable)
PlatformService | createPlan | response | limits[].overageAllowed | boolean |  | (default False)
PlatformService | createPlan | response | limits[].overageUnitPrice | Money |  | On the wire this is three fields; in the database it is one column.
PlatformService | createPlan | response | limits[].overageUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
PlatformService | createPlan | response | limits[].overageUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
PlatformService | createPlan | response | limits[].overageUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
PlatformService | createPlan | response | basePrice | Money | yes | On the wire this is three fields; in the database it is one column.
PlatformService | createPlan | response | basePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
PlatformService | createPlan | response | basePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
PlatformService | createPlan | response | basePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
PlatformService | createPlan | response | billingPeriod | enum (monthly, quarterly, annual)
PlatformService | createPlan | response | includesBrandedApp | boolean |  | Branded native publishing carries per-tenant operational cost and is priced, not absorbed.
PlatformService | createPlan | response | includedAiTokens | integer |  | AI tokens the package includes per billing period. (nullable)
PlatformService | createPlan | response | requestLimits | PlanRequestLimits |  | The limits section of a plan: every tenant has a request budget (ADR-0064, accepted 1 October; it decides the per-tenant limit ADR-0032 deferred). (nullable)
PlatformService | createPlan | response | requestLimits.guest | RequestBudget |  | One audience's bucket (ADR-0064).
PlatformService | createPlan | response | requestLimits.guest.sustainedPerSecond | integer | yes | Requests per second the bucket refills at. (min 1)
PlatformService | createPlan | response | requestLimits.guest.burstMultiplier | number |  | How far above the sustained rate a burst may go (2 is twice the rate). (min 1; default 2)
PlatformService | createPlan | response | requestLimits.guest.burstSeconds | integer |  | How long a burst may last. (min 1; default 10)
PlatformService | createPlan | response | requestLimits.staff | RequestBudget |  | One audience's bucket (ADR-0064).
PlatformService | createPlan | response | requestLimits.staff.sustainedPerSecond | integer | yes | Requests per second the bucket refills at. (min 1)
PlatformService | createPlan | response | requestLimits.staff.burstMultiplier | number |  | How far above the sustained rate a burst may go (2 is twice the rate). (min 1; default 2)
PlatformService | createPlan | response | requestLimits.staff.burstSeconds | integer |  | How long a burst may last. (min 1; default 10)
PlatformService | createPlan | response | requestLimits.service | RequestBudget |  | One audience's bucket (ADR-0064).
PlatformService | createPlan | response | requestLimits.service.sustainedPerSecond | integer | yes | Requests per second the bucket refills at. (min 1)
PlatformService | createPlan | response | requestLimits.service.burstMultiplier | number |  | How far above the sustained rate a burst may go (2 is twice the rate). (min 1; default 2)
PlatformService | createPlan | response | requestLimits.service.burstSeconds | integer |  | How long a burst may last. (min 1; default 10)
PlatformService | createPlan | response | requestLimits.partner | RequestBudget |  | One audience's bucket (ADR-0064).
PlatformService | createPlan | response | requestLimits.partner.sustainedPerSecond | integer | yes | Requests per second the bucket refills at. (min 1)
PlatformService | createPlan | response | requestLimits.partner.burstMultiplier | number |  | How far above the sustained rate a burst may go (2 is twice the rate). (min 1; default 2)
PlatformService | createPlan | response | requestLimits.partner.burstSeconds | integer |  | How long a burst may last. (min 1; default 10)
PlatformService | createPlan | response | requestLimits.replicaSharePercent | integer |  | The most of one replica's request slots one tenant may hold while the share is enforced. (min 1; max 100; default 25)
PlatformService | createPlan | response | requestLimits.shareEnforcedAbovePercent | integer |  | The replica load, as a percent of its limit, above which the share is enforced. (min 1; max 100; default 70)
PlatformService | createPlan | response | packageKind | enum (standard, custom) |  | Three standard packages, and custom ones allowed (decided 29 September, Chinmay). (default standard)
PlatformService | createPlan | response | offeredToTenantId | string (uuid) |  | Private to one tenant (decided 29 September, Chinmay): a custom package offered only to this tenant; listPlans shows it to no other tenant and setSubscription refuses it for any other (422 plan-not-o… (nullable)
PlatformService | createPlan | response | id | string (uuid) | yes
PlatformService | createPlan | response | version | string | yes | Existing subscribers stay on the version they were sold.
PlatformService | createPlan | response | isActive | boolean | yes
PlatformService | createPlan | response | subscriberCount | integer | yes
PlatformService | createPlan | response | publishedAt | string (date-time)
PlatformService | createPlan | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
PlatformService | createPlanVersion | request | code | string | yes | (max length 64)
PlatformService | createPlanVersion | request | name | string | yes | (max length 200)
PlatformService | createPlanVersion | request | description | string |  | (max length 1000)
PlatformService | createPlanVersion | request | cellTier | CellTier: enum (shared, dedicated, isolated, clientHosted) | yes
PlatformService | createPlanVersion | request | licensedModules | array of ModuleKey: enum (core, ticketing, access, fnb, retail, inventory, seating, membership, …) | yes | A closed set as of 24 August. (min items 1)
PlatformService | createPlanVersion | request | limits | array of EntitlementLimit | yes
PlatformService | createPlanVersion | request | limits[].metric | UsageMetric: enum (venues, workstations, activeUsers, devices, brandedApps, aiTokens, apiCalls, storageGb, …) | yes
PlatformService | createPlanVersion | request | limits[].limit | integer | yes | Null means unlimited. (nullable)
PlatformService | createPlanVersion | request | limits[].overageAllowed | boolean |  | (default False)
PlatformService | createPlanVersion | request | limits[].overageUnitPrice | Money |  | On the wire this is three fields; in the database it is one column.
PlatformService | createPlanVersion | request | limits[].overageUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
PlatformService | createPlanVersion | request | limits[].overageUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
PlatformService | createPlanVersion | request | limits[].overageUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
PlatformService | createPlanVersion | request | basePrice | Money | yes | On the wire this is three fields; in the database it is one column.
PlatformService | createPlanVersion | request | basePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
PlatformService | createPlanVersion | request | basePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
PlatformService | createPlanVersion | request | basePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
PlatformService | createPlanVersion | request | billingPeriod | enum (monthly, quarterly, annual)
PlatformService | createPlanVersion | request | includesBrandedApp | boolean |  | Branded native publishing carries per-tenant operational cost and is priced, not absorbed.
PlatformService | createPlanVersion | request | includedAiTokens | integer |  | AI tokens the package includes per billing period. (nullable)
PlatformService | createPlanVersion | request | requestLimits | PlanRequestLimits |  | The limits section of a plan: every tenant has a request budget (ADR-0064, accepted 1 October; it decides the per-tenant limit ADR-0032 deferred). (nullable)
PlatformService | createPlanVersion | request | requestLimits.guest | RequestBudget |  | One audience's bucket (ADR-0064).
PlatformService | createPlanVersion | request | requestLimits.guest.sustainedPerSecond | integer | yes | Requests per second the bucket refills at. (min 1)
PlatformService | createPlanVersion | request | requestLimits.guest.burstMultiplier | number |  | How far above the sustained rate a burst may go (2 is twice the rate). (min 1; default 2)
PlatformService | createPlanVersion | request | requestLimits.guest.burstSeconds | integer |  | How long a burst may last. (min 1; default 10)
PlatformService | createPlanVersion | request | requestLimits.staff | RequestBudget |  | One audience's bucket (ADR-0064).
PlatformService | createPlanVersion | request | requestLimits.staff.sustainedPerSecond | integer | yes | Requests per second the bucket refills at. (min 1)
PlatformService | createPlanVersion | request | requestLimits.staff.burstMultiplier | number |  | How far above the sustained rate a burst may go (2 is twice the rate). (min 1; default 2)
PlatformService | createPlanVersion | request | requestLimits.staff.burstSeconds | integer |  | How long a burst may last. (min 1; default 10)
PlatformService | createPlanVersion | request | requestLimits.service | RequestBudget |  | One audience's bucket (ADR-0064).
PlatformService | createPlanVersion | request | requestLimits.service.sustainedPerSecond | integer | yes | Requests per second the bucket refills at. (min 1)
PlatformService | createPlanVersion | request | requestLimits.service.burstMultiplier | number |  | How far above the sustained rate a burst may go (2 is twice the rate). (min 1; default 2)
PlatformService | createPlanVersion | request | requestLimits.service.burstSeconds | integer |  | How long a burst may last. (min 1; default 10)
PlatformService | createPlanVersion | request | requestLimits.partner | RequestBudget |  | One audience's bucket (ADR-0064).
PlatformService | createPlanVersion | request | requestLimits.partner.sustainedPerSecond | integer | yes | Requests per second the bucket refills at. (min 1)
PlatformService | createPlanVersion | request | requestLimits.partner.burstMultiplier | number |  | How far above the sustained rate a burst may go (2 is twice the rate). (min 1; default 2)
PlatformService | createPlanVersion | request | requestLimits.partner.burstSeconds | integer |  | How long a burst may last. (min 1; default 10)
PlatformService | createPlanVersion | request | requestLimits.replicaSharePercent | integer |  | The most of one replica's request slots one tenant may hold while the share is enforced. (min 1; max 100; default 25)
PlatformService | createPlanVersion | request | requestLimits.shareEnforcedAbovePercent | integer |  | The replica load, as a percent of its limit, above which the share is enforced. (min 1; max 100; default 70)
PlatformService | createPlanVersion | request | packageKind | enum (standard, custom) |  | Three standard packages, and custom ones allowed (decided 29 September, Chinmay). (default standard)
PlatformService | createPlanVersion | request | offeredToTenantId | string (uuid) |  | Private to one tenant (decided 29 September, Chinmay): a custom package offered only to this tenant; listPlans shows it to no other tenant and setSubscription refuses it for any other (422 plan-not-o… (nullable)
PlatformService | createPlanVersion | response | code | string | yes | (max length 64)
PlatformService | createPlanVersion | response | name | string | yes | (max length 200)
PlatformService | createPlanVersion | response | description | string |  | (max length 1000)
PlatformService | createPlanVersion | response | cellTier | CellTier: enum (shared, dedicated, isolated, clientHosted) | yes
PlatformService | createPlanVersion | response | licensedModules | array of ModuleKey: enum (core, ticketing, access, fnb, retail, inventory, seating, membership, …) | yes | A closed set as of 24 August. (min items 1)
PlatformService | createPlanVersion | response | limits | array of EntitlementLimit | yes
PlatformService | createPlanVersion | response | limits[].metric | UsageMetric: enum (venues, workstations, activeUsers, devices, brandedApps, aiTokens, apiCalls, storageGb, …) | yes
PlatformService | createPlanVersion | response | limits[].limit | integer | yes | Null means unlimited. (nullable)
PlatformService | createPlanVersion | response | limits[].overageAllowed | boolean |  | (default False)
PlatformService | createPlanVersion | response | limits[].overageUnitPrice | Money |  | On the wire this is three fields; in the database it is one column.
PlatformService | createPlanVersion | response | limits[].overageUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
PlatformService | createPlanVersion | response | limits[].overageUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
PlatformService | createPlanVersion | response | limits[].overageUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
PlatformService | createPlanVersion | response | basePrice | Money | yes | On the wire this is three fields; in the database it is one column.
PlatformService | createPlanVersion | response | basePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
PlatformService | createPlanVersion | response | basePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
PlatformService | createPlanVersion | response | basePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
PlatformService | createPlanVersion | response | billingPeriod | enum (monthly, quarterly, annual)
PlatformService | createPlanVersion | response | includesBrandedApp | boolean |  | Branded native publishing carries per-tenant operational cost and is priced, not absorbed.
PlatformService | createPlanVersion | response | includedAiTokens | integer |  | AI tokens the package includes per billing period. (nullable)
PlatformService | createPlanVersion | response | requestLimits | PlanRequestLimits |  | The limits section of a plan: every tenant has a request budget (ADR-0064, accepted 1 October; it decides the per-tenant limit ADR-0032 deferred). (nullable)
PlatformService | createPlanVersion | response | requestLimits.guest | RequestBudget |  | One audience's bucket (ADR-0064).
PlatformService | createPlanVersion | response | requestLimits.guest.sustainedPerSecond | integer | yes | Requests per second the bucket refills at. (min 1)
PlatformService | createPlanVersion | response | requestLimits.guest.burstMultiplier | number |  | How far above the sustained rate a burst may go (2 is twice the rate). (min 1; default 2)
PlatformService | createPlanVersion | response | requestLimits.guest.burstSeconds | integer |  | How long a burst may last. (min 1; default 10)
PlatformService | createPlanVersion | response | requestLimits.staff | RequestBudget |  | One audience's bucket (ADR-0064).
PlatformService | createPlanVersion | response | requestLimits.staff.sustainedPerSecond | integer | yes | Requests per second the bucket refills at. (min 1)
PlatformService | createPlanVersion | response | requestLimits.staff.burstMultiplier | number |  | How far above the sustained rate a burst may go (2 is twice the rate). (min 1; default 2)
PlatformService | createPlanVersion | response | requestLimits.staff.burstSeconds | integer |  | How long a burst may last. (min 1; default 10)
PlatformService | createPlanVersion | response | requestLimits.service | RequestBudget |  | One audience's bucket (ADR-0064).
PlatformService | createPlanVersion | response | requestLimits.service.sustainedPerSecond | integer | yes | Requests per second the bucket refills at. (min 1)
PlatformService | createPlanVersion | response | requestLimits.service.burstMultiplier | number |  | How far above the sustained rate a burst may go (2 is twice the rate). (min 1; default 2)
PlatformService | createPlanVersion | response | requestLimits.service.burstSeconds | integer |  | How long a burst may last. (min 1; default 10)
PlatformService | createPlanVersion | response | requestLimits.partner | RequestBudget |  | One audience's bucket (ADR-0064).
PlatformService | createPlanVersion | response | requestLimits.partner.sustainedPerSecond | integer | yes | Requests per second the bucket refills at. (min 1)
PlatformService | createPlanVersion | response | requestLimits.partner.burstMultiplier | number |  | How far above the sustained rate a burst may go (2 is twice the rate). (min 1; default 2)
PlatformService | createPlanVersion | response | requestLimits.partner.burstSeconds | integer |  | How long a burst may last. (min 1; default 10)
PlatformService | createPlanVersion | response | requestLimits.replicaSharePercent | integer |  | The most of one replica's request slots one tenant may hold while the share is enforced. (min 1; max 100; default 25)
PlatformService | createPlanVersion | response | requestLimits.shareEnforcedAbovePercent | integer |  | The replica load, as a percent of its limit, above which the share is enforced. (min 1; max 100; default 70)
PlatformService | createPlanVersion | response | packageKind | enum (standard, custom) |  | Three standard packages, and custom ones allowed (decided 29 September, Chinmay). (default standard)
PlatformService | createPlanVersion | response | offeredToTenantId | string (uuid) |  | Private to one tenant (decided 29 September, Chinmay): a custom package offered only to this tenant; listPlans shows it to no other tenant and setSubscription refuses it for any other (422 plan-not-o… (nullable)
PlatformService | createPlanVersion | response | id | string (uuid) | yes
PlatformService | createPlanVersion | response | version | string | yes | Existing subscribers stay on the version they were sold.
PlatformService | createPlanVersion | response | isActive | boolean | yes
PlatformService | createPlanVersion | response | subscriberCount | integer | yes
PlatformService | createPlanVersion | response | publishedAt | string (date-time)
PlatformService | createPlanVersion | param (path) | planId | string (uuid) | yes
PlatformService | createPlanVersion | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | createPreview | request | platform | enum (ios, android, web)
WhiteLabelService | createPreview | request | theme | enum (light, dark) |  | Deprecated with Theme.darkMode (CHG-CSA-035); ignored.
WhiteLabelService | createPreview | request | language | string |  | (pattern ^[a-z]{2}$)
WhiteLabelService | createPreview | request | outputs | array of enum (app, pdfTicket, appleWalletPass, googleWalletPass) |  | What to render besides the app (CHG-CSA-041).
WhiteLabelService | createPreview | request | productId | string (uuid) |  | The product whose ticket and passes to render; a sample ticket where absent. (nullable)
WhiteLabelService | createPreview | request | expiresInHours | integer |  | (min 1; max 168; default 24)
WhiteLabelService | createPreview | response | previewId | string (uuid) | yes
WhiteLabelService | createPreview | response | url | string | yes
WhiteLabelService | createPreview | response | platform | enum (ios, android, web)
WhiteLabelService | createPreview | response | theme | enum (light, dark) |  | Deprecated with Theme.darkMode (CHG-CSA-035); the preview always renders the venue's theme.
WhiteLabelService | createPreview | response | language | string |  | (pattern ^[a-z]{2}$)
WhiteLabelService | createPreview | response | outputPreviews | array of object |  | The PDF ticket and the Apple and Google Wallet passes, previewed with the app (Chinmay, 2 October, workbook Q151: in Block A; CHG-CSA-041). (read-only)
WhiteLabelService | createPreview | response | outputPreviews[].output | enum (app, pdfTicket, appleWalletPass, googleWalletPass) | yes
WhiteLabelService | createPreview | response | outputPreviews[].url | string | yes | A short-lived link to the rendered output (the PDF, the .pkpass, or the Google pass preview), expiring with the preview.
WhiteLabelService | createPreview | response | expiresAt | string (date-time) | yes
WhiteLabelService | createPreview | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | createPriceList | request | code | string | yes | (max length 64)
CatalogueService | createPriceList | request | name | string | yes | (max length 200)
CatalogueService | createPriceList | request | venueId | string (uuid) | yes
CatalogueService | createPriceList | request | channels | array of Channel: enum (pos, kiosk, web, mobile, b2b, ota, callCentre) | yes | (min items 1)
CatalogueService | createPriceList | request | validFrom | string (date-time)
CatalogueService | createPriceList | request | validTo | string (date-time)
CatalogueService | createPriceList | request | priority | integer |  | (default 0)
CatalogueService | createPriceList | request | description | string |  | The price list master fields (data model DM3) are written here since setPriceListMaster was retired in r2 (BC-008, CHG-CLN-001); each is optional and means what it means on PriceList. (nullable)
CatalogueService | createPriceList | request | priceListType | enum (standardRetail, venue, attraction, event, membership, group, corporate, b2b, …)
CatalogueService | createPriceList | request | ownerPrincipalId | string (uuid) |  | (nullable)
CatalogueService | createPriceList | request | tags | array of string
CatalogueService | createPriceList | request | legalEntityId | string (uuid) |  | (nullable)
CatalogueService | createPriceList | request | brand | string |  | (max length 100; nullable)
CatalogueService | createPriceList | request | businessUnit | string |  | (max length 100; nullable)
CatalogueService | createPriceList | request | countryCode | string |  | (max length 2; pattern ^[A-Z]{2}$; nullable)
CatalogueService | createPriceList | request | marketCode | string |  | (max length 40; nullable)
CatalogueService | createPriceList | request | scopeLevel | enum (global, country, market, brand, venue, event, businessUnit)
CatalogueService | createPriceList | request | defaultPriceCategoryId | string (uuid) |  | (nullable)
CatalogueService | createPriceList | request | roundingProfileId | string (uuid) |  | (nullable)
CatalogueService | createPriceList | request | priceResolutionPolicyId | string (uuid) |  | (nullable)
CatalogueService | createPriceList | request | allowOverrides | boolean
CatalogueService | createPriceList | request | allowInheritance | boolean
CatalogueService | createPriceList | request | allowMultipleCurrencies | boolean
CatalogueService | createPriceList | request | allowProductSpecificRates | boolean
CatalogueService | createPriceList | response | id | string (uuid) | yes
CatalogueService | createPriceList | response | code | string | yes
CatalogueService | createPriceList | response | name | string | yes
CatalogueService | createPriceList | response | venueId | string (uuid) | yes
CatalogueService | createPriceList | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
CatalogueService | createPriceList | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
CatalogueService | createPriceList | response | channels | array of Channel: enum (pos, kiosk, web, mobile, b2b, ota, callCentre) | yes
CatalogueService | createPriceList | response | validFrom | string (date-time) |  | (nullable)
CatalogueService | createPriceList | response | validTo | string (date-time) |  | (nullable)
CatalogueService | createPriceList | response | priority | integer |  | Where lists overlap, higher priority wins.
CatalogueService | createPriceList | response | description | string |  | Price list master fields (29 September, data model DM3), set with createPriceList and updatePriceList since setPriceListMaster was retired in r2 (BC-008, CHG-CLN-001). (nullable)
CatalogueService | createPriceList | response | priceListType | enum (standardRetail, venue, attraction, event, membership, group, corporate, b2b, …) |  | (default standardRetail)
CatalogueService | createPriceList | response | status | object |  | (default active)
CatalogueService | createPriceList | response | ownerPrincipalId | string (uuid) |  | (nullable)
CatalogueService | createPriceList | response | tags | array of string
CatalogueService | createPriceList | response | legalEntityId | string (uuid) |  | (nullable)
CatalogueService | createPriceList | response | brand | string |  | (max length 100; nullable)
CatalogueService | createPriceList | response | businessUnit | string |  | (max length 100; nullable)
CatalogueService | createPriceList | response | countryCode | string |  | (max length 2; pattern ^[A-Z]{2}$; nullable)
CatalogueService | createPriceList | response | marketCode | string |  | (max length 40; nullable)
CatalogueService | createPriceList | response | scopeLevel | enum (global, country, market, brand, venue, event, businessUnit) |  | (default venue)
CatalogueService | createPriceList | response | defaultPriceCategoryId | string (uuid) |  | (nullable)
CatalogueService | createPriceList | response | roundingProfileId | string (uuid) |  | (nullable)
CatalogueService | createPriceList | response | priceResolutionPolicyId | string (uuid) |  | (nullable)
CatalogueService | createPriceList | response | allowOverrides | boolean |  | (default False)
CatalogueService | createPriceList | response | allowInheritance | boolean |  | (default True)
CatalogueService | createPriceList | response | allowMultipleCurrencies | boolean |  | (default False)
CatalogueService | createPriceList | response | allowProductSpecificRates | boolean |  | (default True)
CatalogueService | createPriceList | response | clonedFromPriceListId | string (uuid) |  | (nullable)
CatalogueService | createPriceList | response | currentVersion | integer |  | The active catalogue.price_list_version. (read-only; nullable)
CatalogueService | createPriceList | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | createPriceList | param (header) | Prefer | enum (validate-only) |  | Validate, do not write (29 September, AI system design 2.3 and 2.2 D step 4).
WhiteLabelService | createPromoBlock | request | id | string (uuid) | yes | (read-only)
WhiteLabelService | createPromoBlock | request | title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | createPromoBlock | request | description | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | createPromoBlock | request | iconAssetRef | string (uuid) |  | (nullable)
WhiteLabelService | createPromoBlock | request | promotionId | string (uuid) |  | Presentation only. (nullable)
WhiteLabelService | createPromoBlock | request | linkTarget | LinkTarget
WhiteLabelService | createPromoBlock | request | linkTarget.kind | enum (module, contentPage, product, event, externalUrl, appSection, none) | yes | appSection points at a section of the guest mobile app (decided 29 September, MOB-1), so the bottom navigation can hold Home, Explore, Plan and Tickets.
WhiteLabelService | createPromoBlock | request | linkTarget.moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) |  | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | createPromoBlock | request | linkTarget.appSection | enum (home, explore, plan, tickets, map, account, buyTickets) |  | Required when kind is appSection.
WhiteLabelService | createPromoBlock | request | linkTarget.contentPageId | string (uuid)
WhiteLabelService | createPromoBlock | request | linkTarget.productId | string (uuid)
WhiteLabelService | createPromoBlock | request | linkTarget.eventId | string (uuid)
WhiteLabelService | createPromoBlock | request | linkTarget.url | string
WhiteLabelService | createPromoBlock | request | startsAt | string (date-time) |  | (nullable)
WhiteLabelService | createPromoBlock | request | endsAt | string (date-time) |  | Must follow startsAt when both are set (decided 28 September, audit R163). (nullable)
WhiteLabelService | createPromoBlock | request | state | object |  | Moved by the schedule timer at startsAt and endsAt, in the tenant's timezone, as for Banner.state. (read-only)
WhiteLabelService | createPromoBlock | request | sortOrder | integer
WhiteLabelService | createPromoBlock | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | createPromoBlock | response | id | string (uuid) | yes | (read-only)
WhiteLabelService | createPromoBlock | response | title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | createPromoBlock | response | description | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | createPromoBlock | response | iconAssetRef | string (uuid) |  | (nullable)
WhiteLabelService | createPromoBlock | response | promotionId | string (uuid) |  | Presentation only. (nullable)
WhiteLabelService | createPromoBlock | response | linkTarget | LinkTarget
WhiteLabelService | createPromoBlock | response | linkTarget.kind | enum (module, contentPage, product, event, externalUrl, appSection, none) | yes | appSection points at a section of the guest mobile app (decided 29 September, MOB-1), so the bottom navigation can hold Home, Explore, Plan and Tickets.
WhiteLabelService | createPromoBlock | response | linkTarget.moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) |  | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | createPromoBlock | response | linkTarget.appSection | enum (home, explore, plan, tickets, map, account, buyTickets) |  | Required when kind is appSection.
WhiteLabelService | createPromoBlock | response | linkTarget.contentPageId | string (uuid)
WhiteLabelService | createPromoBlock | response | linkTarget.productId | string (uuid)
WhiteLabelService | createPromoBlock | response | linkTarget.eventId | string (uuid)
WhiteLabelService | createPromoBlock | response | linkTarget.url | string
WhiteLabelService | createPromoBlock | response | startsAt | string (date-time) |  | (nullable)
WhiteLabelService | createPromoBlock | response | endsAt | string (date-time) |  | Must follow startsAt when both are set (decided 28 September, audit R163). (nullable)
WhiteLabelService | createPromoBlock | response | state | object |  | Moved by the schedule timer at startsAt and endsAt, in the tenant's timezone, as for Banner.state. (read-only)
WhiteLabelService | createPromoBlock | response | sortOrder | integer
WhiteLabelService | createPromoBlock | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | createPromoBlock | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | createPromotion | request | code | string | yes | Unique per tenant (6 October 2026, CHG-R4-015; the rule of audit R108 for configuration codes). (max length 64; pattern ^[A-Za-z0-9_-]+$)
CatalogueService | createPromotion | request | name | string | yes | (max length 200)
CatalogueService | createPromotion | request | description | string |  | (max length 1000)
CatalogueService | createPromotion | request | venueId | string (uuid) | yes
CatalogueService | createPromotion | request | discount | Discount | yes
CatalogueService | createPromotion | request | discount.kind | DiscountKind: enum (percentage, fixedAmount, fixedPrice, buyXGetY, freeItem, tieredPercentage) | yes
CatalogueService | createPromotion | request | discount.percentage | number |  | (min 0; max 100)
CatalogueService | createPromotion | request | discount.amount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createPromotion | request | discount.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createPromotion | request | discount.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createPromotion | request | discount.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createPromotion | request | discount.fixedPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createPromotion | request | discount.fixedPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createPromotion | request | discount.fixedPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createPromotion | request | discount.fixedPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createPromotion | request | discount.buyQuantity | integer |  | (min 1)
CatalogueService | createPromotion | request | discount.getQuantity | integer |  | (min 1)
CatalogueService | createPromotion | request | discount.getDiscountPercentage | number |  | 100 makes the free items actually free; lower values give a partial discount. (min 0; max 100)
CatalogueService | createPromotion | request | discount.tiers | array of object |  | For tieredPercentage — more units, larger discount.
CatalogueService | createPromotion | request | discount.tiers[].minQuantity | integer | yes | (min 1)
CatalogueService | createPromotion | request | discount.tiers[].percentage | number | yes | (min 0; max 100)
CatalogueService | createPromotion | request | discount.maxDiscountAmount | object |  | Cap on a percentage discount.
CatalogueService | createPromotion | request | discount.maxDiscountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createPromotion | request | discount.maxDiscountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createPromotion | request | discount.maxDiscountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createPromotion | request | discount.rewardVariantIds | array of string (uuid) |  | The reward products, where the reward is not the qualifying product: the free gift of freeItem, the "different product" of a buyXGetY (createPromotion; the builders setGiftFreeProduct and setBuyGetBo… (nullable)
CatalogueService | createPromotion | request | discount.maxApplicationsPerBasket | integer |  | How many times the offer repeats in one basket: the "maximum repetitions" of an N-for-X offer (createPromotion; setFixedPriceOffer was retired in r2, CHG-CLN-001). (min 1; nullable)
CatalogueService | createPromotion | request | conditions | PromotionConditions |  | All conditions must hold.
CatalogueService | createPromotion | request | conditions.variantIds | array of string (uuid)
CatalogueService | createPromotion | request | conditions.productKinds | array of string
CatalogueService | createPromotion | request | conditions.categoryIds | array of string (uuid)
CatalogueService | createPromotion | request | conditions.minQuantity | integer |  | (min 1)
CatalogueService | createPromotion | request | conditions.minBasketValue | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createPromotion | request | conditions.minBasketValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createPromotion | request | conditions.minBasketValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createPromotion | request | conditions.minBasketValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createPromotion | request | conditions.channels | array of SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) |  | Empty or absent matches every channel.
CatalogueService | createPromotion | request | conditions.purchaseGate | boolean |  | BL-037. (default False)
CatalogueService | createPromotion | request | conditions.paymentMethod | array of string |  | BL-113. (nullable)
CatalogueService | createPromotion | request | conditions.issuerBins | array of string |  | Card BIN ranges, where the campaign is issuer-specific rather than scheme-specific. (nullable)
CatalogueService | createPromotion | request | conditions.componentRedemption | enum (allTogether, independently, sequenced) |  | BL-112. (nullable)
CatalogueService | createPromotion | request | conditions.daysOfWeek | array of integer
CatalogueService | createPromotion | request | conditions.startTime | string |  | (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
CatalogueService | createPromotion | request | conditions.endTime | string |  | (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
CatalogueService | createPromotion | request | conditions.membershipTierIds | array of string (uuid)
CatalogueService | createPromotion | request | conditions.requiresCoupon | boolean |  | (default False)
CatalogueService | createPromotion | request | conditions.firstPurchaseOnly | boolean |  | (default False)
CatalogueService | createPromotion | request | conditions.performanceIds | array of string (uuid)
CatalogueService | createPromotion | request | conditions.advanceDaysMin | integer |  | Early-bird — booked at least this many days ahead.
CatalogueService | createPromotion | request | conditions.advanceDaysMax | integer |  | Last-minute — booked no more than this many days ahead.
CatalogueService | createPromotion | request | conditions.eligibilityRuleIds | array of string (uuid) |  | Reusable eligibility rules (promotions.promotion_rule rows of ruleType: eligibility with no promotion of their own) that must also hold. (nullable)
CatalogueService | createPromotion | request | stackingMode | object |  | (default bestOnly)
CatalogueService | createPromotion | request | stackingGroup | string |  | (max length 64)
CatalogueService | createPromotion | request | precedence | integer |  | Higher evaluates first where several could apply. (default 0)
CatalogueService | createPromotion | request | validFrom | string (date-time) | yes
CatalogueService | createPromotion | request | validTo | string (date-time)
CatalogueService | createPromotion | request | maxRedemptions | integer |  | (nullable)
CatalogueService | createPromotion | request | maxRedemptionsPerGuest | integer |  | (nullable)
CatalogueService | createPromotion | request | budgetCap | object |  | Total discount value after which the promotion stops automatically.
CatalogueService | createPromotion | request | budgetCap.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createPromotion | request | budgetCap.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createPromotion | request | budgetCap.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createPromotion | request | campaignId | string (uuid) |  | The commercial campaign (promotions.campaign) this promotion belongs to; null for a promotion run on its own. (nullable)
CatalogueService | createPromotion | request | recommendable | boolean |  | May the recommendation engine show this offer to a guest (8.6.30 to 8.6.36; 29 September, build pass, group G2, from group G1's handoff). (default False)
CatalogueService | createPromotion | request | recommendableSegmentIds | array of string (uuid) |  | The marketing-crm segments the offer may be recommended to; null means every guest its own conditions admit. (nullable)
CatalogueService | createPromotion | response | code | string | yes | Unique per tenant (6 October 2026, CHG-R4-015; the rule of audit R108 for configuration codes). (max length 64; pattern ^[A-Za-z0-9_-]+$)
CatalogueService | createPromotion | response | name | string | yes | (max length 200)
CatalogueService | createPromotion | response | description | string |  | (max length 1000)
CatalogueService | createPromotion | response | venueId | string (uuid) | yes
CatalogueService | createPromotion | response | discount | Discount | yes
CatalogueService | createPromotion | response | discount.kind | DiscountKind: enum (percentage, fixedAmount, fixedPrice, buyXGetY, freeItem, tieredPercentage) | yes
CatalogueService | createPromotion | response | discount.percentage | number |  | (min 0; max 100)
CatalogueService | createPromotion | response | discount.amount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createPromotion | response | discount.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createPromotion | response | discount.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createPromotion | response | discount.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createPromotion | response | discount.fixedPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createPromotion | response | discount.fixedPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createPromotion | response | discount.fixedPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createPromotion | response | discount.fixedPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createPromotion | response | discount.buyQuantity | integer |  | (min 1)
CatalogueService | createPromotion | response | discount.getQuantity | integer |  | (min 1)
CatalogueService | createPromotion | response | discount.getDiscountPercentage | number |  | 100 makes the free items actually free; lower values give a partial discount. (min 0; max 100)
CatalogueService | createPromotion | response | discount.tiers | array of object |  | For tieredPercentage — more units, larger discount.
CatalogueService | createPromotion | response | discount.tiers[].minQuantity | integer | yes | (min 1)
CatalogueService | createPromotion | response | discount.tiers[].percentage | number | yes | (min 0; max 100)
CatalogueService | createPromotion | response | discount.maxDiscountAmount | object |  | Cap on a percentage discount.
CatalogueService | createPromotion | response | discount.maxDiscountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createPromotion | response | discount.maxDiscountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createPromotion | response | discount.maxDiscountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createPromotion | response | discount.rewardVariantIds | array of string (uuid) |  | The reward products, where the reward is not the qualifying product: the free gift of freeItem, the "different product" of a buyXGetY (createPromotion; the builders setGiftFreeProduct and setBuyGetBo… (nullable)
CatalogueService | createPromotion | response | discount.maxApplicationsPerBasket | integer |  | How many times the offer repeats in one basket: the "maximum repetitions" of an N-for-X offer (createPromotion; setFixedPriceOffer was retired in r2, CHG-CLN-001). (min 1; nullable)
CatalogueService | createPromotion | response | conditions | PromotionConditions |  | All conditions must hold.
CatalogueService | createPromotion | response | conditions.variantIds | array of string (uuid)
CatalogueService | createPromotion | response | conditions.productKinds | array of string
CatalogueService | createPromotion | response | conditions.categoryIds | array of string (uuid)
CatalogueService | createPromotion | response | conditions.minQuantity | integer |  | (min 1)
CatalogueService | createPromotion | response | conditions.minBasketValue | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createPromotion | response | conditions.minBasketValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createPromotion | response | conditions.minBasketValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createPromotion | response | conditions.minBasketValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createPromotion | response | conditions.channels | array of SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) |  | Empty or absent matches every channel.
CatalogueService | createPromotion | response | conditions.purchaseGate | boolean |  | BL-037. (default False)
CatalogueService | createPromotion | response | conditions.paymentMethod | array of string |  | BL-113. (nullable)
CatalogueService | createPromotion | response | conditions.issuerBins | array of string |  | Card BIN ranges, where the campaign is issuer-specific rather than scheme-specific. (nullable)
CatalogueService | createPromotion | response | conditions.componentRedemption | enum (allTogether, independently, sequenced) |  | BL-112. (nullable)
CatalogueService | createPromotion | response | conditions.daysOfWeek | array of integer
CatalogueService | createPromotion | response | conditions.startTime | string |  | (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
CatalogueService | createPromotion | response | conditions.endTime | string |  | (pattern ^([01]\d¦2[0-3]):[0-5]\d$)
CatalogueService | createPromotion | response | conditions.membershipTierIds | array of string (uuid)
CatalogueService | createPromotion | response | conditions.requiresCoupon | boolean |  | (default False)
CatalogueService | createPromotion | response | conditions.firstPurchaseOnly | boolean |  | (default False)
CatalogueService | createPromotion | response | conditions.performanceIds | array of string (uuid)
CatalogueService | createPromotion | response | conditions.advanceDaysMin | integer |  | Early-bird — booked at least this many days ahead.
CatalogueService | createPromotion | response | conditions.advanceDaysMax | integer |  | Last-minute — booked no more than this many days ahead.
CatalogueService | createPromotion | response | conditions.eligibilityRuleIds | array of string (uuid) |  | Reusable eligibility rules (promotions.promotion_rule rows of ruleType: eligibility with no promotion of their own) that must also hold. (nullable)
CatalogueService | createPromotion | response | stackingMode | object |  | (default bestOnly)
CatalogueService | createPromotion | response | stackingGroup | string |  | (max length 64)
CatalogueService | createPromotion | response | precedence | integer |  | Higher evaluates first where several could apply. (default 0)
CatalogueService | createPromotion | response | validFrom | string (date-time) | yes
CatalogueService | createPromotion | response | validTo | string (date-time)
CatalogueService | createPromotion | response | maxRedemptions | integer |  | (nullable)
CatalogueService | createPromotion | response | maxRedemptionsPerGuest | integer |  | (nullable)
CatalogueService | createPromotion | response | budgetCap | object |  | Total discount value after which the promotion stops automatically.
CatalogueService | createPromotion | response | budgetCap.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createPromotion | response | budgetCap.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createPromotion | response | budgetCap.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createPromotion | response | campaignId | string (uuid) |  | The commercial campaign (promotions.campaign) this promotion belongs to; null for a promotion run on its own. (nullable)
CatalogueService | createPromotion | response | recommendable | boolean |  | May the recommendation engine show this offer to a guest (8.6.30 to 8.6.36; 29 September, build pass, group G2, from group G1's handoff). (default False)
CatalogueService | createPromotion | response | recommendableSegmentIds | array of string (uuid) |  | The marketing-crm segments the offer may be recommended to; null means every guest its own conditions admit. (nullable)
CatalogueService | createPromotion | response | id | string (uuid) | yes
CatalogueService | createPromotion | response | status | PromotionStatus: enum (draft, scheduled, live, paused, expired, ended) | yes
CatalogueService | createPromotion | response | isPaused | boolean
CatalogueService | createPromotion | response | redemptionCount | integer
CatalogueService | createPromotion | response | discountGiven | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createPromotion | response | discountGiven.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createPromotion | response | discountGiven.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createPromotion | response | discountGiven.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createPromotion | response | publishedAt | string (date-time) |  | (nullable)
CatalogueService | createPromotion | response | version | integer |  | Starts at 1 and goes up by one on every saved change. (min 1; read-only)
CatalogueService | createPromotion | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | createQueue | request | code | string | yes | (max length 64)
VenueOpsService | createQueue | request | name | LocalisedText | yes
VenueOpsService | createQueue | request | venueId | string (uuid) | yes
VenueOpsService | createQueue | request | attractionProductId | string (uuid)
VenueOpsService | createQueue | request | assetId | string (uuid) |  | The ride. (nullable)
VenueOpsService | createQueue | request | accessPointId | string (uuid) |  | (nullable)
VenueOpsService | createQueue | request | kind | enum (standby, singleRider, fastPass, virtual, accessible, groupOnly, staffOnly) |  | 5.6.x. (default standby)
VenueOpsService | createQueue | request | operatingWindows | array of object |  | When the queue runs, which is not when the venue is open.
VenueOpsService | createQueue | request | operatingWindows[].day | enum (mon, tue, wed, thu, fri, sat, sun) | yes
VenueOpsService | createQueue | request | operatingWindows[].from | string | yes | Venue local time, 24-hour HH:MM, when the queue starts running. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
VenueOpsService | createQueue | request | operatingWindows[].to | string | yes | Venue local time, 24-hour HH:MM, when the queue stops running. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
VenueOpsService | createQueue | request | operatingWindows[].lastEntryMinutesBefore | integer |  | When the queue stops accepting, which is before it stops running. (default 0)
VenueOpsService | createQueue | request | parentQueueId | string (uuid) |  | Where several queues share one capacity. (nullable)
VenueOpsService | createQueue | request | loadBalanceWithQueueIds | array of string (uuid) |  | BL-137.
VenueOpsService | createQueue | request | inQueueOfferEnabled | boolean |  | A guest with twenty minutes to wait is a guest with twenty minutes to buy something. (default False)
VenueOpsService | createQueue | request | notifyBeforeCallMinutes | integer |  | BL-017, 19.2.61. (default 5)
VenueOpsService | createQueue | request | capacityPerCycle | integer | yes | (min 1)
VenueOpsService | createQueue | request | cycleMinutes | number | yes | (min 0)
VenueOpsService | createQueue | request | maxPartySize | integer |  | (default 6)
VenueOpsService | createQueue | request | returnWindowMinutes | integer |  | How long a called party has to arrive before the entry expires. (default 15)
VenueOpsService | createQueue | request | heightRequirementCm | integer |  | (nullable)
VenueOpsService | createQueue | request | fastPassAllocationPercent | number |  | Share of each cycle reserved for Fast Pass holders. (min 0; max 100; default 0)
VenueOpsService | createQueue | request | zone | string |  | (nullable)
VenueOpsService | createQueue | request | fastPass | object |  | The lane's Fast Pass block (decided 29 September, VM close-out). (nullable)
VenueOpsService | createQueue | request | fastPass.entitlementProductIds | array of string (uuid) | yes | Catalogue products whose entitlement admits to this lane.
VenueOpsService | createQueue | request | fastPass.loyaltyTierIds | array of string (uuid) |  | 5.6.7 and 5.6.34 (decided 29 September, build pass).
VenueOpsService | createQueue | request | fastPass.promotionIds | array of string (uuid) |  | 5.6.34 (decided 29 September, build pass).
VenueOpsService | createQueue | request | fastPass.accessibilityPriority | boolean |  | 5.6.7 (decided 29 September, build pass). (default False)
VenueOpsService | createQueue | request | fastPass.returnWindowMinutes | integer |  | How long after the booked return time a Fast Pass holder may still enter. (min 1; max 240; default 60)
VenueOpsService | createQueue | request | fastPass.maxPerGuestPerDay | integer |  | Fast Pass redemptions one guest may make on this lane per day; null is no cap. (min 1; nullable)
VenueOpsService | createQueue | request | fastPass.allowedAccessPointIds | array of string (uuid) |  | Access points that redeem Fast Pass for this lane; empty is the queue's own.
VenueOpsService | createQueue | response | code | string | yes | (max length 64)
VenueOpsService | createQueue | response | name | LocalisedText | yes
VenueOpsService | createQueue | response | venueId | string (uuid) | yes
VenueOpsService | createQueue | response | attractionProductId | string (uuid)
VenueOpsService | createQueue | response | assetId | string (uuid) |  | The ride. (nullable)
VenueOpsService | createQueue | response | accessPointId | string (uuid) |  | (nullable)
VenueOpsService | createQueue | response | kind | enum (standby, singleRider, fastPass, virtual, accessible, groupOnly, staffOnly) |  | 5.6.x. (default standby)
VenueOpsService | createQueue | response | operatingWindows | array of object |  | When the queue runs, which is not when the venue is open.
VenueOpsService | createQueue | response | operatingWindows[].day | enum (mon, tue, wed, thu, fri, sat, sun) | yes
VenueOpsService | createQueue | response | operatingWindows[].from | string | yes | Venue local time, 24-hour HH:MM, when the queue starts running. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
VenueOpsService | createQueue | response | operatingWindows[].to | string | yes | Venue local time, 24-hour HH:MM, when the queue stops running. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
VenueOpsService | createQueue | response | operatingWindows[].lastEntryMinutesBefore | integer |  | When the queue stops accepting, which is before it stops running. (default 0)
VenueOpsService | createQueue | response | parentQueueId | string (uuid) |  | Where several queues share one capacity. (nullable)
VenueOpsService | createQueue | response | loadBalanceWithQueueIds | array of string (uuid) |  | BL-137.
VenueOpsService | createQueue | response | inQueueOfferEnabled | boolean |  | A guest with twenty minutes to wait is a guest with twenty minutes to buy something. (default False)
VenueOpsService | createQueue | response | notifyBeforeCallMinutes | integer |  | BL-017, 19.2.61. (default 5)
VenueOpsService | createQueue | response | capacityPerCycle | integer | yes | (min 1)
VenueOpsService | createQueue | response | cycleMinutes | number | yes | (min 0)
VenueOpsService | createQueue | response | maxPartySize | integer |  | (default 6)
VenueOpsService | createQueue | response | returnWindowMinutes | integer |  | How long a called party has to arrive before the entry expires. (default 15)
VenueOpsService | createQueue | response | heightRequirementCm | integer |  | (nullable)
VenueOpsService | createQueue | response | fastPassAllocationPercent | number |  | Share of each cycle reserved for Fast Pass holders. (min 0; max 100; default 0)
VenueOpsService | createQueue | response | zone | string |  | (nullable)
VenueOpsService | createQueue | response | fastPass | object |  | The lane's Fast Pass block (decided 29 September, VM close-out). (nullable)
VenueOpsService | createQueue | response | fastPass.entitlementProductIds | array of string (uuid) | yes | Catalogue products whose entitlement admits to this lane.
VenueOpsService | createQueue | response | fastPass.loyaltyTierIds | array of string (uuid) |  | 5.6.7 and 5.6.34 (decided 29 September, build pass).
VenueOpsService | createQueue | response | fastPass.promotionIds | array of string (uuid) |  | 5.6.34 (decided 29 September, build pass).
VenueOpsService | createQueue | response | fastPass.accessibilityPriority | boolean |  | 5.6.7 (decided 29 September, build pass). (default False)
VenueOpsService | createQueue | response | fastPass.returnWindowMinutes | integer |  | How long after the booked return time a Fast Pass holder may still enter. (min 1; max 240; default 60)
VenueOpsService | createQueue | response | fastPass.maxPerGuestPerDay | integer |  | Fast Pass redemptions one guest may make on this lane per day; null is no cap. (min 1; nullable)
VenueOpsService | createQueue | response | fastPass.allowedAccessPointIds | array of string (uuid) |  | Access points that redeem Fast Pass for this lane; empty is the queue's own.
VenueOpsService | createQueue | response | id | string (uuid) | yes
VenueOpsService | createQueue | response | status | QueueStatus: enum (open, paused, closed, atCapacity) | yes
VenueOpsService | createQueue | response | statusReason | string |  | (nullable)
VenueOpsService | createQueue | response | waitingPartyCount | integer | yes
VenueOpsService | createQueue | response | waitingGuestCount | integer
VenueOpsService | createQueue | response | currentWaitMinutes | integer |  | (nullable)
VenueOpsService | createQueue | response | waitTimeSource | WaitTimeSource: enum (sensor, throughput, manual, unavailable) |  | Where the estimate came from.
VenueOpsService | createQueue | response | waitTimeAsOf | string (date-time) |  | When currentWaitMinutes was last set, by whichever source set it. (read-only; nullable)
VenueOpsService | createQueue | response | manualWaitExpiresAt | string (date-time) |  | Set by setWaitTime as now plus expiresInMinutes. (read-only; nullable)
VenueOpsService | createQueue | response | manualWaitNote | string |  | The note given with the current manual figure. (max length 200; read-only; nullable)
VenueOpsService | createQueue | response | expectedReopenAt | string (date-time) |  | (nullable)
VenueOpsService | createQueue | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | createReferral | request | id | string (uuid) | yes | (read-only)
MarketingService | createReferral | request | referrerSubjectId | string (uuid) | yes
MarketingService | createReferral | request | refereeSubjectId | string (uuid) |  | (read-only; nullable)
MarketingService | createReferral | request | code | string | yes | (read-only)
MarketingService | createReferral | request | status | enum (issued, registered, qualified, rewarded, expired, void) | yes | (read-only)
MarketingService | createReferral | request | qualifyingAction | enum (firstPurchase, firstVisit, membershipPurchase)
MarketingService | createReferral | request | referrerRewardId | string (uuid) |  | (read-only; nullable)
MarketingService | createReferral | request | refereeRewardId | string (uuid) |  | (read-only; nullable)
MarketingService | createReferral | request | expiresAt | string (date-time) |  | (nullable)
MarketingService | createReferral | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | createReferral | response | id | string (uuid) | yes | (read-only)
MarketingService | createReferral | response | referrerSubjectId | string (uuid) | yes
MarketingService | createReferral | response | refereeSubjectId | string (uuid) |  | (read-only; nullable)
MarketingService | createReferral | response | code | string | yes | (read-only)
MarketingService | createReferral | response | status | enum (issued, registered, qualified, rewarded, expired, void) | yes | (read-only)
MarketingService | createReferral | response | qualifyingAction | enum (firstPurchase, firstVisit, membershipPurchase)
MarketingService | createReferral | response | referrerRewardId | string (uuid) |  | (read-only; nullable)
MarketingService | createReferral | response | refereeRewardId | string (uuid) |  | (read-only; nullable)
MarketingService | createReferral | response | expiresAt | string (date-time) |  | (nullable)
MarketingService | createReferral | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | createReferral | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createRefund | request | id | string (uuid) | yes | Client-generated UUIDv7 of the refund, and its idempotency key — it must equal the Idempotency-Key header.
OrderService | createRefund | request | lineIds | array of string (uuid) |  | Omit to refund the whole order.
OrderService | createRefund | request | amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createRefund | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createRefund | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createRefund | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createRefund | request | reason | string | yes | (min length 3; max length 500)
OrderService | createRefund | request | secondaryAuthorisation | object |  | Required above the venue's requiresSecondUserAbove.
OrderService | createRefund | request | secondaryAuthorisation.principalId | string (uuid) | yes
OrderService | createRefund | request | secondaryAuthorisation.credential | string | yes | The second person's staff PIN, as they sign in at a till with it. (max length 512)
OrderService | createRefund | request | refundToOriginalTender | boolean |  | (default True)
OrderService | createRefund | request | alternateTender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) |  | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | createRefund | request | recordedAt | string (date-time) | yes
OrderService | createRefund | response | id | string (uuid) | yes
OrderService | createRefund | response | orderId | string (uuid) | yes
OrderService | createRefund | response | batchId | string (uuid) |  | The RefundBatch that raised this refund, where createBulkRefund did. (read-only; nullable)
OrderService | createRefund | response | fxRate | object |  | The rate on the original payment, not today's (BL-087, CF-118). (read-only; nullable)
OrderService | createRefund | response | taxReversalEntryId | string (uuid) |  | A refund reverses the tax entry it created, and this is where that is stated rather than implied. (read-only; nullable)
OrderService | createRefund | response | settleTo | enum (originalTender, advanceBalance, wireTransfer, storeCredit) |  | BL-086. (default originalTender)
OrderService | createRefund | response | fxVariance | object |  | Where the sale rate and the current rate differ, the difference is booked as an FX variance rather than hidden in the refund.
OrderService | createRefund | response | fxVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createRefund | response | fxVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createRefund | response | fxVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createRefund | response | tenderCurrency | string |  | A refund goes back in the currency the guest paid (decided 2 October 2026, Chinmay; CHG-FIN-001). (pattern ^[A-Z]{3}$; read-only; nullable)
OrderService | createRefund | response | tenderAmount | object |  | The refund in tenderCurrency, at that currency's own scale (CHG-FIN-001). (read-only)
OrderService | createRefund | response | tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createRefund | response | tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createRefund | response | tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createRefund | response | amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createRefund | response | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createRefund | response | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createRefund | response | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createRefund | response | appliedPercentage | number |  | From the venue's time bands, or an approver override.
OrderService | createRefund | response | status | enum (pendingApproval, pendingGateway, completed, declined, failed) | yes
OrderService | createRefund | response | reason | string
OrderService | createRefund | response | requestedByPrincipalId | string (uuid)
OrderService | createRefund | response | secondaryPrincipalId | string (uuid) |  | (nullable)
OrderService | createRefund | response | approvedByPrincipalId | string (uuid) |  | (nullable)
OrderService | createRefund | response | ledgerEntryId | string (uuid) |  | Written before the gateway is called. (nullable)
OrderService | createRefund | response | gatewayReference | string |  | (nullable)
OrderService | createRefund | response | createdAt | string (date-time) | yes
OrderService | createRefund | response | completedAt | string (date-time) |  | (nullable)
OrderService | createRefund | param (path) | orderId | string (uuid) | yes
OrderService | createRefund | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createRefundRequest | request | orderId | string (uuid) | yes
OrderService | createRefundRequest | request | lineIds | array of string (uuid)
OrderService | createRefundRequest | request | reason | string | yes | (min length 3; max length 1000)
OrderService | createRefundRequest | response | requestId | string
OrderService | createRefundRequest | response | status | enum (submitted, moreInfoRequested, approved, declined)
OrderService | createRefundRequest | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
ReportingService | createReport | request | name | string | yes | (max length 200)
ReportingService | createReport | request | description | string |  | (max length 1000)
ReportingService | createReport | request | category | ReportCategory: enum (sales, admission, financial, inventory, guest, operations, marketing, workforce, …) | yes
ReportingService | createReport | request | dataSource | DataSource: enum (orders, orderLines, payments, refunds, shifts, scanEvents, entitlements, products, …) | yes | What a report may be built over.
ReportingService | createReport | request | columns | array of ReportColumn | yes | (min items 1)
ReportingService | createReport | request | columns[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | createReport | request | columns[].field | string | yes
ReportingService | createReport | request | columns[].label | string
ReportingService | createReport | request | columns[].aggregation | object |  | (default none)
ReportingService | createReport | request | columns[].sortOrder | integer
ReportingService | createReport | request | columns[].sortDirection | enum (asc, desc)
ReportingService | createReport | request | columns[].format | string |  | (nullable)
ReportingService | createReport | request | columns[].role | enum (dimension, measure) |  | What the column is to a chart (decided 2 October 2026, Chinmay; CHG-FIN-007). (nullable)
ReportingService | createReport | request | columns[].encoding | enum (category, x, y, series, value, size, colour, location, …) |  | Which field well the column fills (CHG-FIN-007), the binding the twenty marks of DashboardTile.visualisation need. (nullable)
ReportingService | createReport | request | columns[].axis | enum (primary, secondary) |  | For a measure on a combo, the axis it is drawn against. (nullable)
ReportingService | createReport | request | columns[].seriesType | enum (bar, line, area) |  | For a measure on a combo, how that series is drawn (CHG-FIN-007). (nullable)
ReportingService | createReport | request | columns[].hierarchyLevel | integer |  | For matrix rows and columns, treemap nesting and decompositionTree levels, the depth of this dimension, 1 outermost. (min 1; nullable)
ReportingService | createReport | request | columns[].unitLabel | string |  | The unit an axis states, for example "AED" or "Admissions". (max length 40; nullable)
ReportingService | createReport | request | filters | array of ReportFilter
ReportingService | createReport | request | filters[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | createReport | request | filters[].field | string | yes
ReportingService | createReport | request | filters[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, contains, …) | yes
ReportingService | createReport | request | filters[].value | object |  | Open on purpose; its type is the field's.
ReportingService | createReport | request | filters[].values | array of object |  | The values for in and notIn, or exactly two (from, to) for between.
ReportingService | createReport | request | filters[].isParameter | boolean |  | Prompted at run time rather than fixed. (default False)
ReportingService | createReport | request | groupBy | array of string
ReportingService | createReport | request | parameters | array of ReportParameter
ReportingService | createReport | request | parameters[].key | string | yes
ReportingService | createReport | request | parameters[].label | string | yes
ReportingService | createReport | request | parameters[].type | FieldType: enum (string, integer, decimal, money, boolean, date, dateTime, uuid, …) | yes
ReportingService | createReport | request | parameters[].isRequired | boolean | yes
ReportingService | createReport | request | parameters[].defaultValue | object |  | Open on purpose.
ReportingService | createReport | request | requiredPermission | Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) | yes | Permission needed to run this report, from the shared Permission vocabulary.
ReportingService | createReport | request | maxDateRangeDays | integer |  | Guards against a query spanning years of scan events. (min 1; default 366; nullable)
ReportingService | createReport | response | name | string | yes | (max length 200)
ReportingService | createReport | response | description | string |  | (max length 1000)
ReportingService | createReport | response | category | ReportCategory: enum (sales, admission, financial, inventory, guest, operations, marketing, workforce, …) | yes
ReportingService | createReport | response | dataSource | DataSource: enum (orders, orderLines, payments, refunds, shifts, scanEvents, entitlements, products, …) | yes | What a report may be built over.
ReportingService | createReport | response | columns | array of ReportColumn | yes | (min items 1)
ReportingService | createReport | response | columns[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | createReport | response | columns[].field | string | yes
ReportingService | createReport | response | columns[].label | string
ReportingService | createReport | response | columns[].aggregation | object |  | (default none)
ReportingService | createReport | response | columns[].sortOrder | integer
ReportingService | createReport | response | columns[].sortDirection | enum (asc, desc)
ReportingService | createReport | response | columns[].format | string |  | (nullable)
ReportingService | createReport | response | columns[].role | enum (dimension, measure) |  | What the column is to a chart (decided 2 October 2026, Chinmay; CHG-FIN-007). (nullable)
ReportingService | createReport | response | columns[].encoding | enum (category, x, y, series, value, size, colour, location, …) |  | Which field well the column fills (CHG-FIN-007), the binding the twenty marks of DashboardTile.visualisation need. (nullable)
ReportingService | createReport | response | columns[].axis | enum (primary, secondary) |  | For a measure on a combo, the axis it is drawn against. (nullable)
ReportingService | createReport | response | columns[].seriesType | enum (bar, line, area) |  | For a measure on a combo, how that series is drawn (CHG-FIN-007). (nullable)
ReportingService | createReport | response | columns[].hierarchyLevel | integer |  | For matrix rows and columns, treemap nesting and decompositionTree levels, the depth of this dimension, 1 outermost. (min 1; nullable)
ReportingService | createReport | response | columns[].unitLabel | string |  | The unit an axis states, for example "AED" or "Admissions". (max length 40; nullable)
ReportingService | createReport | response | filters | array of ReportFilter
ReportingService | createReport | response | filters[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | createReport | response | filters[].field | string | yes
ReportingService | createReport | response | filters[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, contains, …) | yes
ReportingService | createReport | response | filters[].value | object |  | Open on purpose; its type is the field's.
ReportingService | createReport | response | filters[].values | array of object |  | The values for in and notIn, or exactly two (from, to) for between.
ReportingService | createReport | response | filters[].isParameter | boolean |  | Prompted at run time rather than fixed. (default False)
ReportingService | createReport | response | groupBy | array of string
ReportingService | createReport | response | parameters | array of ReportParameter
ReportingService | createReport | response | parameters[].key | string | yes
ReportingService | createReport | response | parameters[].label | string | yes
ReportingService | createReport | response | parameters[].type | FieldType: enum (string, integer, decimal, money, boolean, date, dateTime, uuid, …) | yes
ReportingService | createReport | response | parameters[].isRequired | boolean | yes
ReportingService | createReport | response | parameters[].defaultValue | object |  | Open on purpose.
ReportingService | createReport | response | requiredPermission | Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) | yes | Permission needed to run this report, from the shared Permission vocabulary.
ReportingService | createReport | response | maxDateRangeDays | integer |  | Guards against a query spanning years of scan events. (min 1; default 366; nullable)
ReportingService | createReport | response | id | string (uuid) | yes
ReportingService | createReport | response | version | string | yes | The current version.
ReportingService | createReport | response | isSystem | boolean | yes | Shipped with the platform — seeded at provisioning (BL-053, SeededReport).
ReportingService | createReport | response | isRetired | boolean | yes
ReportingService | createReport | response | estimatedCost | enum (low, medium, high) |  | Informs whether it may run inline or must be queued.
ReportingService | createReport | response | createdByPrincipalId | string (uuid) |  | (nullable)
ReportingService | createReport | response | createdAt | string (date-time) | yes
ReportingService | createReport | response | lastRunAt | string (date-time) |  | (nullable)
ReportingService | createReport | response | scopePath | string |  | The partition key (ADR-0005).
ReportingService | createReport | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createResaleListing | request | entitlementId | string (uuid) | yes
OrderService | createResaleListing | request | askPrice | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createResaleListing | request | askPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createResaleListing | request | askPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createResaleListing | request | askPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createResaleListing | request | sellerSubjectId | string (uuid) |  | The holder listing it. (nullable)
OrderService | createResaleListing | response | id | string (uuid) | yes | (read-only)
OrderService | createResaleListing | response | entitlementId | string (uuid) | yes
OrderService | createResaleListing | response | sellerSubjectId | string (uuid) | yes
OrderService | createResaleListing | response | askPrice | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | createResaleListing | response | askPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createResaleListing | response | askPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createResaleListing | response | askPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createResaleListing | response | priceCapPercent | number |  | A ceiling as a percentage of face value, because uncapped resale is a venue watching its own tickets sold at four times the price with its name on them. (read-only; nullable)
OrderService | createResaleListing | response | sellerFeePercent | number |  | Snapshotted from ResaleFeePolicy at listing. (read-only)
OrderService | createResaleListing | response | buyerFeePercent | number |  | Snapshotted from ResaleFeePolicy at listing. (read-only)
OrderService | createResaleListing | response | status | enum (pendingReview, listed, reserved, sold, withdrawn, expired, rejected) | yes | pendingReview and rejected added 29 September (DM5): a listing the marketplace's moderationMode sends to review waits there until approveListingModeration lists or rejects it. (read-only)
OrderService | createResaleListing | response | listedAt | string (date-time) |  | (read-only)
OrderService | createResaleListing | response | soldToSubjectId | string (uuid) |  | (read-only; nullable)
OrderService | createResaleListing | response | reviewReasons | array of enum (highResalePrice, unusualDiscount, highValueTicket, vipTicket, sellerRisk, newSeller, multipleListings, identityIssue, …) |  | Why the listing was sent to review (DM5, 29 September). (read-only)
OrderService | createResaleListing | response | moderatedByPrincipalId | string (uuid) |  | (read-only; nullable)
OrderService | createResaleListing | response | moderatedAt | string (date-time) |  | (read-only; nullable)
OrderService | createResaleListing | response | moderationReason | string |  | (max length 1000; read-only; nullable)
OrderService | createResaleListing | response | payoutStatus | enum (pending, held, paid, failed) |  | The seller is paid after the buyer is admitted, not after they pay. (read-only)
OrderService | createResaleListing | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | createResaleListing | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createReservation | request | id | string (uuid) | yes | Client-generated UUIDv7 of the reservation, and its idempotency key — it must equal the Idempotency-Key header.
OrderService | createReservation | request | venueId | string (uuid) | yes
OrderService | createReservation | request | subjectId | string (uuid) |  | The guest the reservation is held for.
OrderService | createReservation | request | lines | array of CreateOrderLine | yes | (min items 1)
OrderService | createReservation | request | lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | createReservation | request | lines[].variantId | string (uuid) | yes
OrderService | createReservation | request | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | createReservation | request | lines[].performanceId | string (uuid)
OrderService | createReservation | request | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | createReservation | request | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | createReservation | request | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | createReservation | request | lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | createReservation | request | lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | createReservation | request | lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | createReservation | request | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | createReservation | request | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | createReservation | request | lines[].quantity | integer | yes | (min 1)
OrderService | createReservation | request | lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | createReservation | request | lines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | createReservation | request | lines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | createReservation | request | lines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | createReservation | request | lines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | createReservation | request | lines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | createReservation | request | lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | createReservation | request | lines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createReservation | request | lines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createReservation | request | lines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createReservation | request | lines[].holderName | string |  | (nullable)
OrderService | createReservation | request | lines[].dataMaskValues | object |  | Deliberately open.
OrderService | createReservation | request | expiresAt | string (date-time) | yes
OrderService | createReservation | response | id | string (uuid) | yes
OrderService | createReservation | response | venueId | string (uuid) | yes
OrderService | createReservation | response | subjectId | string (uuid) |  | The guest it is held for, from CreateReservationRequest.subjectId. (nullable)
OrderService | createReservation | response | status | enum (held, converted, expired, cancelled) | yes
OrderService | createReservation | response | lines | array of CreateOrderLine
OrderService | createReservation | response | lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | createReservation | response | lines[].variantId | string (uuid) | yes
OrderService | createReservation | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | createReservation | response | lines[].performanceId | string (uuid)
OrderService | createReservation | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | createReservation | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | createReservation | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | createReservation | response | lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | createReservation | response | lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | createReservation | response | lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | createReservation | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | createReservation | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | createReservation | response | lines[].quantity | integer | yes | (min 1)
OrderService | createReservation | response | lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | createReservation | response | lines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | createReservation | response | lines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | createReservation | response | lines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | createReservation | response | lines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | createReservation | response | lines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | createReservation | response | lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | createReservation | response | lines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | createReservation | response | lines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | createReservation | response | lines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | createReservation | response | lines[].holderName | string |  | (nullable)
OrderService | createReservation | response | lines[].dataMaskValues | object |  | Deliberately open.
OrderService | createReservation | response | expiresAt | string (date-time) | yes
OrderService | createReservation | response | createdAt | string (date-time) | yes
OrderService | createReservation | response | convertedOrderId | string (uuid) |  | (nullable)
OrderService | createReservation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | createResource | request | id | string (uuid) | yes
VenueOpsService | createResource | request | code | string | yes
VenueOpsService | createResource | request | name | string | yes
VenueOpsService | createResource | request | kind | ResourceKind: enum (cabana, lounger, locker, wheelchair, stroller, equipment, room, auditorium, …) | yes | BL-135.
VenueOpsService | createResource | request | venueId | string (uuid) | yes
VenueOpsService | createResource | request | scopePath | string
VenueOpsService | createResource | request | parentResourceId | string (uuid) |  | A pool cabana belongs to the pool area; a seat belongs to an auditorium. (nullable)
VenueOpsService | createResource | request | principalId | string (uuid) |  | For a resource of kind instructor or staff. (nullable)
VenueOpsService | createResource | request | attributes | object |  | Configurable per kind — capacity, size, shade, power, poolside.
VenueOpsService | createResource | request | setupMinutes | integer |  | Before the booking, not inside it. (default 0)
VenueOpsService | createResource | request | teardownMinutes | integer |  | After the booking. (default 0)
VenueOpsService | createResource | request | cleaningPolicy | object |  | How the resource is cleaned between uses (decided 29 September, W10). (nullable)
VenueOpsService | createResource | request | cleaningPolicy.mode | enum (afterEveryBooking, timesPerDay) | yes
VenueOpsService | createResource | request | cleaningPolicy.bufferMinutes | integer | yes | Minutes one cleaning takes. (min 5; max 240)
VenueOpsService | createResource | request | cleaningPolicy.cleaningsPerDay | integer |  | Required for timesPerDay; ignored for afterEveryBooking. (min 1; max 24; nullable)
VenueOpsService | createResource | request | cleaningPolicy.windowStart | string |  | Venue-local time the cleaning window opens. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
VenueOpsService | createResource | request | cleaningPolicy.windowEnd | string |  | Venue-local time the cleaning window closes. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
VenueOpsService | createResource | request | requiresQualification | array of string |  | Qualification codes a person must hold to be assigned to this.
VenueOpsService | createResource | request | depositAmount | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | createResource | request | depositAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | createResource | request | depositAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | createResource | request | depositAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | createResource | request | status | enum (available, booked, checkedOut, maintenance, retired)
VenueOpsService | createResource | request | isActive | boolean |  | (default True)
VenueOpsService | createResource | request | resourceTypeId | string (uuid) |  | The configurable resource type (resources.resource_type, 4 October 2026, CHG-FXC-003). (nullable)
VenueOpsService | createResource | response | id | string (uuid) | yes
VenueOpsService | createResource | response | code | string | yes
VenueOpsService | createResource | response | name | string | yes
VenueOpsService | createResource | response | kind | ResourceKind: enum (cabana, lounger, locker, wheelchair, stroller, equipment, room, auditorium, …) | yes | BL-135.
VenueOpsService | createResource | response | venueId | string (uuid) | yes
VenueOpsService | createResource | response | scopePath | string
VenueOpsService | createResource | response | parentResourceId | string (uuid) |  | A pool cabana belongs to the pool area; a seat belongs to an auditorium. (nullable)
VenueOpsService | createResource | response | principalId | string (uuid) |  | For a resource of kind instructor or staff. (nullable)
VenueOpsService | createResource | response | attributes | object |  | Configurable per kind — capacity, size, shade, power, poolside.
VenueOpsService | createResource | response | setupMinutes | integer |  | Before the booking, not inside it. (default 0)
VenueOpsService | createResource | response | teardownMinutes | integer |  | After the booking. (default 0)
VenueOpsService | createResource | response | cleaningPolicy | object |  | How the resource is cleaned between uses (decided 29 September, W10). (nullable)
VenueOpsService | createResource | response | cleaningPolicy.mode | enum (afterEveryBooking, timesPerDay) | yes
VenueOpsService | createResource | response | cleaningPolicy.bufferMinutes | integer | yes | Minutes one cleaning takes. (min 5; max 240)
VenueOpsService | createResource | response | cleaningPolicy.cleaningsPerDay | integer |  | Required for timesPerDay; ignored for afterEveryBooking. (min 1; max 24; nullable)
VenueOpsService | createResource | response | cleaningPolicy.windowStart | string |  | Venue-local time the cleaning window opens. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
VenueOpsService | createResource | response | cleaningPolicy.windowEnd | string |  | Venue-local time the cleaning window closes. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
VenueOpsService | createResource | response | requiresQualification | array of string |  | Qualification codes a person must hold to be assigned to this.
VenueOpsService | createResource | response | depositAmount | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | createResource | response | depositAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | createResource | response | depositAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | createResource | response | depositAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | createResource | response | status | enum (available, booked, checkedOut, maintenance, retired)
VenueOpsService | createResource | response | isActive | boolean |  | (default True)
VenueOpsService | createResource | response | resourceTypeId | string (uuid) |  | The configurable resource type (resources.resource_type, 4 October 2026, CHG-FXC-003). (nullable)
VenueOpsService | createResource | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | createResourceBlock | request | id | string (uuid)
VenueOpsService | createResourceBlock | request | resourceId | string (uuid) | yes
VenueOpsService | createResourceBlock | request | from | string (date-time) | yes
VenueOpsService | createResourceBlock | request | to | string (date-time) | yes
VenueOpsService | createResourceBlock | request | reason | enum (setup, teardown, maintenance, blackout, closed, operational, training) | yes
VenueOpsService | createResourceBlock | request | note | string |  | (nullable)
VenueOpsService | createResourceBlock | request | createdBy | string (uuid) |  | (nullable)
VenueOpsService | createResourceBlock | request | scopePath | string
VenueOpsService | createResourceBlock | response | id | string (uuid)
VenueOpsService | createResourceBlock | response | resourceId | string (uuid) | yes
VenueOpsService | createResourceBlock | response | from | string (date-time) | yes
VenueOpsService | createResourceBlock | response | to | string (date-time) | yes
VenueOpsService | createResourceBlock | response | reason | enum (setup, teardown, maintenance, blackout, closed, operational, training) | yes
VenueOpsService | createResourceBlock | response | note | string |  | (nullable)
VenueOpsService | createResourceBlock | response | createdBy | string (uuid) |  | (nullable)
VenueOpsService | createResourceBlock | response | scopePath | string
VenueOpsService | createResourceBlock | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | createResourceHold | request | id | string (uuid) | yes | Client-generated UUIDv7, as a seat hold's.
VenueOpsService | createResourceHold | request | mapId | string (uuid) | yes | The published venue map the guest picked from.
VenueOpsService | createResourceHold | request | resourceIds | array of string (uuid) | yes | Placed resources on that map, e.g. (min items 1; max items 10)
VenueOpsService | createResourceHold | request | from | string (date-time) | yes
VenueOpsService | createResourceHold | request | to | string (date-time) | yes
VenueOpsService | createResourceHold | request | partySize | integer |  | Checked against each resource's capacity; above it the hold is refused 422. (min 1; nullable)
VenueOpsService | createResourceHold | request | ttlSeconds | integer |  | 8 minutes by default, 30 in all with extensions (audit R169), as a seat hold. (min 60; max 1800; default 480)
VenueOpsService | createResourceHold | request | subjectId | string (uuid) |  | (nullable)
VenueOpsService | createResourceHold | response | id | string (uuid) | yes
VenueOpsService | createResourceHold | response | mapId | string (uuid) | yes
VenueOpsService | createResourceHold | response | resourceIds | array of string (uuid) | yes
VenueOpsService | createResourceHold | response | from | string (date-time) | yes
VenueOpsService | createResourceHold | response | to | string (date-time) | yes
VenueOpsService | createResourceHold | response | partySize | integer |  | (nullable)
VenueOpsService | createResourceHold | response | status | enum (held, converted, released, expired) | yes
VenueOpsService | createResourceHold | response | totalPrice | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | createResourceHold | response | totalPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | createResourceHold | response | totalPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | createResourceHold | response | totalPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | createResourceHold | response | heldByPrincipalId | string (uuid) |  | (nullable)
VenueOpsService | createResourceHold | response | subjectId | string (uuid) |  | (nullable)
VenueOpsService | createResourceHold | response | orderId | string (uuid) |  | Set when the order converts it. (nullable)
VenueOpsService | createResourceHold | response | extensionCount | integer |  | (default 0)
VenueOpsService | createResourceHold | response | createdAt | string (date-time) | yes
VenueOpsService | createResourceHold | response | expiresAt | string (date-time) | yes
VenueOpsService | createResourceHold | response | scopePath | string |  | The partition key (ADR-0005), written at venue scope.
VenueOpsService | createResourceHold | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | createResourcePackage | request | id | string (uuid)
VenueOpsService | createResourcePackage | request | code | string | yes
VenueOpsService | createResourcePackage | request | name | string | yes
VenueOpsService | createResourcePackage | request | description | string |  | (nullable)
VenueOpsService | createResourcePackage | request | applicableVenueIds | array of string (uuid)
VenueOpsService | createResourcePackage | request | components | array of ResourceRequirement
VenueOpsService | createResourcePackage | request | components[].id | string (uuid)
VenueOpsService | createResourcePackage | request | components[].resourceTypeId | string (uuid) |  | (nullable)
VenueOpsService | createResourcePackage | request | components[].categoryId | string (uuid) |  | (nullable)
VenueOpsService | createResourcePackage | request | components[].resourceId | string (uuid) |  | A fixed component, and the exception rather than the rule. (nullable)
VenueOpsService | createResourcePackage | request | components[].quantity | integer | yes | (default 1)
VenueOpsService | createResourcePackage | request | components[].mandatory | boolean |  | (default True)
VenueOpsService | createResourcePackage | request | components[].requiredQualifications | array of string
VenueOpsService | createResourcePackage | request | components[].requiredAttributes | object
VenueOpsService | createResourcePackage | request | components[].substituteResourceIds | array of string (uuid)
VenueOpsService | createResourcePackage | request | components[].scopePath | string
VenueOpsService | createResourcePackage | request | components[].packageId | string (uuid) |  | The package this requirement is a component of (4 October 2026, CHG-FXC-003). (read-only; nullable)
VenueOpsService | createResourcePackage | request | components[].productId | string (uuid) |  | The experience product this requirement belongs to (setExperienceResourceRequirements). (read-only; nullable)
VenueOpsService | createResourcePackage | request | allocationPriority | integer |  | (default 0)
VenueOpsService | createResourcePackage | request | effectiveFrom | string (date) |  | (nullable)
VenueOpsService | createResourcePackage | request | effectiveTo | string (date) |  | (nullable)
VenueOpsService | createResourcePackage | request | minimumMinutes | integer |  | (nullable)
VenueOpsService | createResourcePackage | request | maximumMinutes | integer |  | (nullable)
VenueOpsService | createResourcePackage | request | requiresApproval | boolean |  | (default False)
VenueOpsService | createResourcePackage | request | internalCost | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | createResourcePackage | request | internalCost.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | createResourcePackage | request | internalCost.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | createResourcePackage | request | internalCost.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | createResourcePackage | request | scopePath | string
VenueOpsService | createResourcePackage | response | id | string (uuid)
VenueOpsService | createResourcePackage | response | code | string | yes
VenueOpsService | createResourcePackage | response | name | string | yes
VenueOpsService | createResourcePackage | response | description | string |  | (nullable)
VenueOpsService | createResourcePackage | response | applicableVenueIds | array of string (uuid)
VenueOpsService | createResourcePackage | response | components | array of ResourceRequirement
VenueOpsService | createResourcePackage | response | components[].id | string (uuid)
VenueOpsService | createResourcePackage | response | components[].resourceTypeId | string (uuid) |  | (nullable)
VenueOpsService | createResourcePackage | response | components[].categoryId | string (uuid) |  | (nullable)
VenueOpsService | createResourcePackage | response | components[].resourceId | string (uuid) |  | A fixed component, and the exception rather than the rule. (nullable)
VenueOpsService | createResourcePackage | response | components[].quantity | integer | yes | (default 1)
VenueOpsService | createResourcePackage | response | components[].mandatory | boolean |  | (default True)
VenueOpsService | createResourcePackage | response | components[].requiredQualifications | array of string
VenueOpsService | createResourcePackage | response | components[].requiredAttributes | object
VenueOpsService | createResourcePackage | response | components[].substituteResourceIds | array of string (uuid)
VenueOpsService | createResourcePackage | response | components[].scopePath | string
VenueOpsService | createResourcePackage | response | components[].packageId | string (uuid) |  | The package this requirement is a component of (4 October 2026, CHG-FXC-003). (read-only; nullable)
VenueOpsService | createResourcePackage | response | components[].productId | string (uuid) |  | The experience product this requirement belongs to (setExperienceResourceRequirements). (read-only; nullable)
VenueOpsService | createResourcePackage | response | allocationPriority | integer |  | (default 0)
VenueOpsService | createResourcePackage | response | effectiveFrom | string (date) |  | (nullable)
VenueOpsService | createResourcePackage | response | effectiveTo | string (date) |  | (nullable)
VenueOpsService | createResourcePackage | response | minimumMinutes | integer |  | (nullable)
VenueOpsService | createResourcePackage | response | maximumMinutes | integer |  | (nullable)
VenueOpsService | createResourcePackage | response | requiresApproval | boolean |  | (default False)
VenueOpsService | createResourcePackage | response | internalCost | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | createResourcePackage | response | internalCost.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | createResourcePackage | response | internalCost.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | createResourcePackage | response | internalCost.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | createResourcePackage | response | scopePath | string
VenueOpsService | createResourcePackage | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
RetailService | createRetailReturn | request | id | string (uuid) | yes
RetailService | createRetailReturn | request | saleId | string | yes
RetailService | createRetailReturn | request | lines | array of object | yes | (min items 1)
RetailService | createRetailReturn | request | lines[].lineId | string | yes
RetailService | createRetailReturn | request | lines[].quantity | integer | yes | (min 1)
RetailService | createRetailReturn | request | lines[].condition | ReturnCondition: enum (resaleable, opened, damaged, faulty, missingParts) | yes | Determines whether stock is restored or written off.
RetailService | createRetailReturn | request | lines[].serialNumbers | array of string
RetailService | createRetailReturn | request | lines[].note | string |  | (max length 200)
RetailService | createRetailReturn | request | reason | ReturnReason: enum (changedMind, wrongSize, wrongItem, faulty, damagedInTransit, duplicatePurchase, giftReturn, other) | yes
RetailService | createRetailReturn | request | refundTender | string |  | Defaults to the original tender.
RetailService | createRetailReturn | request | secondaryAuthorisation | object |  | Required above the outlet's self-authorise limit.
RetailService | createRetailReturn | request | secondaryAuthorisation.principalId | string (uuid) | yes | The supervisor signing.
RetailService | createRetailReturn | request | secondaryAuthorisation.credential | string | yes | The supervisor's staff PIN, as they sign in at a till with it. (max length 512)
RetailService | createRetailReturn | request | recordedAt | string (date-time) | yes
RetailService | createRetailReturn | response | id | string | yes
RetailService | createRetailReturn | response | returnNumber | string
RetailService | createRetailReturn | response | saleId | string | yes
RetailService | createRetailReturn | response | refundId | string |  | The refund raised in the Order & Payment context. (nullable)
RetailService | createRetailReturn | response | lines | array of object | yes
RetailService | createRetailReturn | response | lines[].lineId | string
RetailService | createRetailReturn | response | lines[].merchandiseId | string (uuid)
RetailService | createRetailReturn | response | lines[].name | string
RetailService | createRetailReturn | response | lines[].quantity | integer
RetailService | createRetailReturn | response | lines[].condition | ReturnCondition: enum (resaleable, opened, damaged, faulty, missingParts) |  | Determines whether stock is restored or written off.
RetailService | createRetailReturn | response | lines[].wasRestocked | boolean |  | False for opened, damaged or faulty goods, which are written off with a reason rather than silently absent.
RetailService | createRetailReturn | response | lines[].refundAmount | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | createRetailReturn | response | lines[].refundAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | createRetailReturn | response | lines[].refundAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | createRetailReturn | response | lines[].refundAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | createRetailReturn | response | reason | ReturnReason: enum (changedMind, wrongSize, wrongItem, faulty, damagedInTransit, duplicatePurchase, giftReturn, other)
RetailService | createRetailReturn | response | refundAmount | Money | yes | On the wire this is three fields; in the database it is one column.
RetailService | createRetailReturn | response | refundAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | createRetailReturn | response | refundAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | createRetailReturn | response | refundAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | createRetailReturn | response | refundTender | string
RetailService | createRetailReturn | response | restockedQuantity | integer | yes
RetailService | createRetailReturn | response | writtenOffQuantity | integer | yes
RetailService | createRetailReturn | response | status | object | yes | (read-only)
RetailService | createRetailReturn | response | refusedReason | object |  | Set when status is refused, null otherwise. (read-only; nullable)
RetailService | createRetailReturn | response | acceptedByPrincipalId | string (uuid) |  | Who took the return at the desk.
RetailService | createRetailReturn | response | secondaryPrincipalId | string (uuid) |  | (nullable)
RetailService | createRetailReturn | response | createdAt | string (date-time) | yes
RetailService | createRetailReturn | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
RetailService | createRetailSale | request | id | string (uuid) | yes
RetailService | createRetailSale | request | outletId | string (uuid) | yes
RetailService | createRetailSale | request | shiftId | string
RetailService | createRetailSale | request | subjectId | string (uuid)
RetailService | createRetailSale | request | lines | array of CreateRetailSaleLine | yes | (min items 1)
RetailService | createRetailSale | request | lines[].id | string (uuid) | yes
RetailService | createRetailSale | request | lines[].merchandiseId | string (uuid) | yes
RetailService | createRetailSale | request | lines[].quantity | integer | yes | (min 1)
RetailService | createRetailSale | request | lines[].serialNumbers | array of string |  | Required where the item is serialised.
RetailService | createRetailSale | request | lines[].overridePrice | object |  | Manual price override.
RetailService | createRetailSale | request | lines[].overridePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | createRetailSale | request | lines[].overridePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | createRetailSale | request | lines[].overridePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | createRetailSale | request | lines[].overrideReason | string |  | (max length 200)
RetailService | createRetailSale | request | couponCodes | array of string
RetailService | createRetailSale | request | recordedAt | string (date-time) | yes
RetailService | createRetailSale | response | id | string | yes
RetailService | createRetailSale | response | receiptNumber | string | yes | Server-assigned: the venue prefix plus a sequence per venue (decided 28 September, audit R152). (read-only)
RetailService | createRetailSale | response | orderId | string | yes | The order in the Order & Payment context.
RetailService | createRetailSale | response | outletId | string (uuid) | yes
RetailService | createRetailSale | response | shiftId | string |  | (nullable)
RetailService | createRetailSale | response | subjectId | string (uuid) |  | (nullable)
RetailService | createRetailSale | response | lines | array of object | yes
RetailService | createRetailSale | response | lines[].lineId | string
RetailService | createRetailSale | response | lines[].merchandiseId | string (uuid)
RetailService | createRetailSale | response | lines[].name | string
RetailService | createRetailSale | response | lines[].quantity | integer
RetailService | createRetailSale | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | createRetailSale | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | createRetailSale | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | createRetailSale | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | createRetailSale | response | lines[].discount | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | createRetailSale | response | lines[].discount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | createRetailSale | response | lines[].discount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | createRetailSale | response | lines[].discount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | createRetailSale | response | lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | createRetailSale | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | createRetailSale | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | createRetailSale | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | createRetailSale | response | lines[].serialNumbers | array of string
RetailService | createRetailSale | response | lines[].returnedQuantity | integer
RetailService | createRetailSale | response | lines[].isReturnable | boolean |  | False once the window has passed or the line is fully returned.
RetailService | createRetailSale | response | lines[].notReturnableReason | string |  | (nullable)
RetailService | createRetailSale | response | subtotal | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | createRetailSale | response | subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | createRetailSale | response | subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | createRetailSale | response | subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | createRetailSale | response | discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | createRetailSale | response | discountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | createRetailSale | response | discountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | createRetailSale | response | discountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | createRetailSale | response | taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | createRetailSale | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | createRetailSale | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | createRetailSale | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | createRetailSale | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
RetailService | createRetailSale | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | createRetailSale | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | createRetailSale | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | createRetailSale | response | reprintCount | integer
RetailService | createRetailSale | response | createdAt | string (date-time) | yes
RetailService | createRetailSale | response | recordedAt | string (date-time)
RetailService | createRetailSale | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | createRole | request | code | string | yes | Unique within the tenant, compared case-insensitively (decided 28 September, audit R108). (max length 64; pattern ^[A-Za-z0-9_-]+$)
IdentityService | createRole | request | name | string | yes | (max length 200)
IdentityService | createRole | request | description | string |  | (max length 500)
IdentityService | createRole | request | presetCodes | array of string |  | Presets (CapabilityTemplate.code) whose permissions fill the new role's checklist; copied, never bound (CHG-CSP-003).
IdentityService | createRole | request | permissions | array of Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) |  | Permissions ticked on the checklist beyond the presets.
IdentityService | createRole | response | id | string (uuid) | yes
IdentityService | createRole | response | code | string | yes | Unique within the tenant (decided 28 September, audit R108).
IdentityService | createRole | response | name | string | yes
IdentityService | createRole | response | description | string
IdentityService | createRole | response | permissions | array of Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) |  | A role that grants no permissions is not a role.
IdentityService | createRole | response | inheritsFromRoleId | string (uuid) |  | Role composition, one level deep and no deeper. (nullable)
IdentityService | createRole | response | isSystem | boolean |  | Seeded roles ship and are editable; deleting one is refused. (default False)
IdentityService | createRole | response | presetCode | string |  | The preset this role was started from, for the record only (decided 2 October 2026, Chinmay; DEC-007; CHG-CSP-003): the first of createRole.presetCodes, or null for a role ticked by hand. (max length 64; read-only; nullable)
IdentityService | createRole | response | principalCount | integer
IdentityService | createRole | response | grantCount | integer
IdentityService | createRole | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | createRotaAssignment | request | overtimeMinutes | integer |  | BL-044, 1.2.83. (read-only; nullable)
TenancyService | createRotaAssignment | request | restPeriodBefore | integer |  | Minutes since the previous shift ended. (nullable)
TenancyService | createRotaAssignment | request | breachesWorkingHourLimit | boolean |  | Flagged at assignment, not discovered at payroll. (default False; read-only)
TenancyService | createRotaAssignment | request | labourCost | object |  | Cost at the point of scheduling.
TenancyService | createRotaAssignment | request | labourCost.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | createRotaAssignment | request | labourCost.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | createRotaAssignment | request | labourCost.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | createRotaAssignment | request | id | string (uuid) |  | (read-only)
TenancyService | createRotaAssignment | request | principalId | string (uuid) | yes
TenancyService | createRotaAssignment | request | displayName | string |  | (read-only)
TenancyService | createRotaAssignment | request | venueId | string (uuid) | yes
TenancyService | createRotaAssignment | request | departmentId | string (uuid) |  | (nullable)
TenancyService | createRotaAssignment | request | position | string | yes | What they are rostered to do — gate steward, cashier, lifeguard, technician.
TenancyService | createRotaAssignment | request | requiredRoleId | string (uuid) |  | Checked on assignment. (nullable)
TenancyService | createRotaAssignment | request | workstationId | string (uuid) |  | Where the position needs a till. (nullable)
TenancyService | createRotaAssignment | request | startsAt | string (date-time) | yes
TenancyService | createRotaAssignment | request | endsAt | string (date-time) | yes
TenancyService | createRotaAssignment | request | status | RotaStatus: enum (planned, published, confirmed, swapPending, cancelled, completed, noShow)
TenancyService | createRotaAssignment | request | breakMinutes | integer |  | (nullable)
TenancyService | createRotaAssignment | request | note | string |  | (nullable)
TenancyService | createRotaAssignment | response | overtimeMinutes | integer |  | BL-044, 1.2.83. (read-only; nullable)
TenancyService | createRotaAssignment | response | restPeriodBefore | integer |  | Minutes since the previous shift ended. (nullable)
TenancyService | createRotaAssignment | response | breachesWorkingHourLimit | boolean |  | Flagged at assignment, not discovered at payroll. (default False; read-only)
TenancyService | createRotaAssignment | response | labourCost | object |  | Cost at the point of scheduling.
TenancyService | createRotaAssignment | response | labourCost.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | createRotaAssignment | response | labourCost.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | createRotaAssignment | response | labourCost.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | createRotaAssignment | response | id | string (uuid) |  | (read-only)
TenancyService | createRotaAssignment | response | principalId | string (uuid) | yes
TenancyService | createRotaAssignment | response | displayName | string |  | (read-only)
TenancyService | createRotaAssignment | response | venueId | string (uuid) | yes
TenancyService | createRotaAssignment | response | departmentId | string (uuid) |  | (nullable)
TenancyService | createRotaAssignment | response | position | string | yes | What they are rostered to do — gate steward, cashier, lifeguard, technician.
TenancyService | createRotaAssignment | response | requiredRoleId | string (uuid) |  | Checked on assignment. (nullable)
TenancyService | createRotaAssignment | response | workstationId | string (uuid) |  | Where the position needs a till. (nullable)
TenancyService | createRotaAssignment | response | startsAt | string (date-time) | yes
TenancyService | createRotaAssignment | response | endsAt | string (date-time) | yes
TenancyService | createRotaAssignment | response | status | RotaStatus: enum (planned, published, confirmed, swapPending, cancelled, completed, noShow)
TenancyService | createRotaAssignment | response | breakMinutes | integer |  | (nullable)
TenancyService | createRotaAssignment | response | note | string |  | (nullable)
TenancyService | createRotaAssignment | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | createSaleBoard | request | id | string (uuid) | yes | (read-only)
TenancyService | createSaleBoard | request | code | string | yes | (max length 64)
TenancyService | createSaleBoard | request | name | string | yes | (max length 200)
TenancyService | createSaleBoard | request | venueId | string (uuid) | yes
TenancyService | createSaleBoard | request | kind | SaleBoardKind: enum (ticketing, fnb, retail, mixed) | yes
TenancyService | createSaleBoard | request | pages | array of object | yes | (min items 1)
TenancyService | createSaleBoard | request | pages[].name | string | yes
TenancyService | createSaleBoard | request | pages[].sortOrder | integer | yes
TenancyService | createSaleBoard | request | pages[].tiles | array of object | yes
TenancyService | createSaleBoard | request | pages[].tiles[].position | integer | yes
TenancyService | createSaleBoard | request | pages[].tiles[].kind | enum (product, category, action, spacer) | yes
TenancyService | createSaleBoard | request | pages[].tiles[].variantId | string (uuid) |  | (nullable)
TenancyService | createSaleBoard | request | pages[].tiles[].label | string
TenancyService | createSaleBoard | request | pages[].tiles[].colour | string |  | (nullable)
TenancyService | createSaleBoard | request | pages[].tiles[].imageAssetRef | string |  | (nullable)
TenancyService | createSaleBoard | request | isActive | boolean
TenancyService | createSaleBoard | response | id | string (uuid) | yes | (read-only)
TenancyService | createSaleBoard | response | code | string | yes | (max length 64)
TenancyService | createSaleBoard | response | name | string | yes | (max length 200)
TenancyService | createSaleBoard | response | venueId | string (uuid) | yes
TenancyService | createSaleBoard | response | kind | SaleBoardKind: enum (ticketing, fnb, retail, mixed) | yes
TenancyService | createSaleBoard | response | pages | array of object | yes | (min items 1)
TenancyService | createSaleBoard | response | pages[].name | string | yes
TenancyService | createSaleBoard | response | pages[].sortOrder | integer | yes
TenancyService | createSaleBoard | response | pages[].tiles | array of object | yes
TenancyService | createSaleBoard | response | pages[].tiles[].position | integer | yes
TenancyService | createSaleBoard | response | pages[].tiles[].kind | enum (product, category, action, spacer) | yes
TenancyService | createSaleBoard | response | pages[].tiles[].variantId | string (uuid) |  | (nullable)
TenancyService | createSaleBoard | response | pages[].tiles[].label | string
TenancyService | createSaleBoard | response | pages[].tiles[].colour | string |  | (nullable)
TenancyService | createSaleBoard | response | pages[].tiles[].imageAssetRef | string |  | (nullable)
TenancyService | createSaleBoard | response | isActive | boolean
TenancyService | createSaleBoard | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | createSeatCategory | request | code | string | yes | (max length 64)
CatalogueService | createSeatCategory | request | name | string | yes | (max length 200)
CatalogueService | createSeatCategory | request | venueId | string (uuid) | yes
CatalogueService | createSeatCategory | request | displayColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
CatalogueService | createSeatCategory | request | rank | integer |  | Ordering for best-seat assignment.
CatalogueService | createSeatCategory | request | priceBands | array of SeatPriceBand |  | The category's price bands (decided 28 September, audit R275 (d)).
CatalogueService | createSeatCategory | request | priceBands[].id | string (uuid) |  | (read-only)
CatalogueService | createSeatCategory | request | priceBands[].seatCategoryId | string (uuid) |  | (read-only)
CatalogueService | createSeatCategory | request | priceBands[].code | string | yes | Unique within the category. (max length 64)
CatalogueService | createSeatCategory | request | priceBands[].displayLabel | string | yes | (max length 200)
CatalogueService | createSeatCategory | request | priceBands[].displayColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$; nullable)
CatalogueService | createSeatCategory | request | priceBands[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | createSeatCategory | request | priceBands[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createSeatCategory | request | priceBands[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createSeatCategory | request | priceBands[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createSeatCategory | request | priceBands[].channel | object |  | Null means every channel. (nullable)
CatalogueService | createSeatCategory | request | priceBands[].customerSegmentId | string (uuid) |  | A marketing-crm customer segment; null means everyone. (nullable)
CatalogueService | createSeatCategory | request | priceBands[].effectiveFrom | string (date-time) | yes
CatalogueService | createSeatCategory | request | priceBands[].effectiveTo | string (date-time) |  | Null means open-ended. (nullable)
CatalogueService | createSeatCategory | response | id | string (uuid) | yes
CatalogueService | createSeatCategory | response | code | string | yes
CatalogueService | createSeatCategory | response | name | string | yes
CatalogueService | createSeatCategory | response | venueId | string (uuid) | yes
CatalogueService | createSeatCategory | response | displayColour | string |  | (nullable)
CatalogueService | createSeatCategory | response | rank | integer | yes | Ordering for best-seat assignment.
CatalogueService | createSeatCategory | response | seatCount | integer
CatalogueService | createSeatCategory | response | priceBands | array of SeatPriceBand |  | What a seat in this category costs, by band (decided 28 September, audit R275 (d), from the BO-1045 pack).
CatalogueService | createSeatCategory | response | priceBands[].id | string (uuid) |  | (read-only)
CatalogueService | createSeatCategory | response | priceBands[].seatCategoryId | string (uuid) |  | (read-only)
CatalogueService | createSeatCategory | response | priceBands[].code | string | yes | Unique within the category. (max length 64)
CatalogueService | createSeatCategory | response | priceBands[].displayLabel | string | yes | (max length 200)
CatalogueService | createSeatCategory | response | priceBands[].displayColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$; nullable)
CatalogueService | createSeatCategory | response | priceBands[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | createSeatCategory | response | priceBands[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createSeatCategory | response | priceBands[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createSeatCategory | response | priceBands[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createSeatCategory | response | priceBands[].channel | object |  | Null means every channel. (nullable)
CatalogueService | createSeatCategory | response | priceBands[].customerSegmentId | string (uuid) |  | A marketing-crm customer segment; null means everyone. (nullable)
CatalogueService | createSeatCategory | response | priceBands[].effectiveFrom | string (date-time) | yes
CatalogueService | createSeatCategory | response | priceBands[].effectiveTo | string (date-time) |  | Null means open-ended. (nullable)
CatalogueService | createSeatCategory | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | createSeatCategory | param (header) | Prefer | enum (validate-only) |  | Validate, do not write (29 September, AI system design 2.3 and 2.2 D step 4).
CatalogueService | createSeatHold | request | id | string (uuid) | yes
CatalogueService | createSeatHold | request | performanceId | string (uuid) | yes
CatalogueService | createSeatHold | request | seatIds | array of string | yes | 50 is the ceiling of the venue setting, not the limit a caller gets. (min items 1; max items 50)
CatalogueService | createSeatHold | request | ttlSeconds | integer |  | 8 minutes by default, extendable to 30 in all (decided 28 September, audit R169). (min 60; max 1800; default 480)
CatalogueService | createSeatHold | request | subjectId | string (uuid)
CatalogueService | createSeatHold | response | id | string | yes
CatalogueService | createSeatHold | response | performanceId | string (uuid) | yes
CatalogueService | createSeatHold | response | seatIds | array of string | yes
CatalogueService | createSeatHold | response | bufferedSeatIds | array of string |  | Neighbours implicitly held by a seating rule.
CatalogueService | createSeatHold | response | status | enum (held, converted, released, expired) | yes
CatalogueService | createSeatHold | response | totalPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | createSeatHold | response | totalPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | createSeatHold | response | totalPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | createSeatHold | response | totalPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | createSeatHold | response | heldByPrincipalId | string (uuid) |  | (nullable)
CatalogueService | createSeatHold | response | subjectId | string (uuid) |  | (nullable)
CatalogueService | createSeatHold | response | extensionCount | integer
CatalogueService | createSeatHold | response | createdAt | string (date-time) | yes
CatalogueService | createSeatHold | response | expiresAt | string (date-time) | yes
CatalogueService | createSeatHold | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | createSegment | request | name | string | yes | (max length 200)
MarketingService | createSegment | request | description | string |  | (max length 1000)
MarketingService | createSegment | request | venueId | string (uuid)
MarketingService | createSegment | request | match | enum (all, any) |  | (default all)
MarketingService | createSegment | request | criteria | array of SegmentCriterion | yes | (min items 1)
MarketingService | createSegment | request | criteria[].attribute | string | yes | Behavioural or profile attribute — visit count, last visit, lifetime value, product purchased, membership tier, venue visited, language.
MarketingService | createSegment | request | criteria[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, exists, …) | yes
MarketingService | createSegment | request | criteria[].value | object
MarketingService | createSegment | request | criteria[].values | array of object
MarketingService | createSegment | request | excludeSegmentIds | array of string (uuid)
MarketingService | createSegment | request | ruleGroups | array of SegmentRuleGroup |  | Nested AND / OR / NOT groups (contract gap CHG-WIR-007, BO-755; CHG-CSA-045).
MarketingService | createSegment | request | ruleGroups[].operator | enum (and, or, not)
MarketingService | createSegment | request | ruleGroups[].criteria | array of object |  | Each entry has the shape of SegmentCriterion (attribute, operator, value).
MarketingService | createSegment | request | ruleGroups[].groups | array of SegmentRuleGroup
MarketingService | createSegment | request | effectiveFrom | string (date-time) |  | The segment is evaluated for sends only from this time. (nullable)
MarketingService | createSegment | request | effectiveTo | string (date-time) |  | (nullable)
MarketingService | createSegment | request | ownerPrincipalId | string (uuid) |  | Who answers for the segment; defaults to its creator. (nullable)
MarketingService | createSegment | request | requiresApproval | boolean |  | Where true, a campaign may use the segment only after an approvals request on it is approved. (default False)
MarketingService | createSegment | response | name | string | yes | (max length 200)
MarketingService | createSegment | response | description | string |  | (max length 1000)
MarketingService | createSegment | response | venueId | string (uuid)
MarketingService | createSegment | response | match | enum (all, any) |  | (default all)
MarketingService | createSegment | response | criteria | array of SegmentCriterion | yes | (min items 1)
MarketingService | createSegment | response | criteria[].attribute | string | yes | Behavioural or profile attribute — visit count, last visit, lifetime value, product purchased, membership tier, venue visited, language.
MarketingService | createSegment | response | criteria[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, exists, …) | yes
MarketingService | createSegment | response | criteria[].value | object
MarketingService | createSegment | response | criteria[].values | array of object
MarketingService | createSegment | response | excludeSegmentIds | array of string (uuid)
MarketingService | createSegment | response | ruleGroups | array of SegmentRuleGroup |  | Nested AND / OR / NOT groups (contract gap CHG-WIR-007, BO-755; CHG-CSA-045).
MarketingService | createSegment | response | ruleGroups[].operator | enum (and, or, not)
MarketingService | createSegment | response | ruleGroups[].criteria | array of object |  | Each entry has the shape of SegmentCriterion (attribute, operator, value).
MarketingService | createSegment | response | ruleGroups[].groups | array of SegmentRuleGroup
MarketingService | createSegment | response | effectiveFrom | string (date-time) |  | The segment is evaluated for sends only from this time. (nullable)
MarketingService | createSegment | response | effectiveTo | string (date-time) |  | (nullable)
MarketingService | createSegment | response | ownerPrincipalId | string (uuid) |  | Who answers for the segment; defaults to its creator. (nullable)
MarketingService | createSegment | response | requiresApproval | boolean |  | Where true, a campaign may use the segment only after an approvals request on it is approved. (default False)
MarketingService | createSegment | response | id | string (uuid) | yes
MarketingService | createSegment | response | lastEvaluatedSize | integer |  | (nullable)
MarketingService | createSegment | response | lastEvaluatedAt | string (date-time) |  | (nullable)
MarketingService | createSegment | response | createdAt | string (date-time) | yes
MarketingService | createSegment | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
RetailService | createShopAndDrop | request | id | string (uuid) | yes
RetailService | createShopAndDrop | request | saleId | string |  | The retail sale, from a till. (nullable)
RetailService | createShopAndDrop | request | orderId | string |  | The paid online order, when the order service calls on payment (audit R236). (nullable)
RetailService | createShopAndDrop | request | entitlementId | string |  | The guest's ticket. (nullable)
RetailService | createShopAndDrop | request | collectionPointId | string (uuid) | yes
RetailService | createShopAndDrop | request | lineIds | array of string |  | Omit to drop the whole sale.
RetailService | createShopAndDrop | request | collectBy | string (date-time) |  | Usually venue close.
RetailService | createShopAndDrop | request | recordedAt | string (date-time) | yes
RetailService | createShopAndDrop | response | id | string | yes
RetailService | createShopAndDrop | response | dropReference | string | yes | Short and readable.
RetailService | createShopAndDrop | response | saleId | string |  | The till sale. (nullable)
RetailService | createShopAndDrop | response | orderId | string (uuid) |  | The paid online order that created this collection (audit R236). (nullable)
RetailService | createShopAndDrop | response | entitlementId | string |  | The ticket that claims these goods. (nullable)
RetailService | createShopAndDrop | response | subjectId | string (uuid) |  | (nullable)
RetailService | createShopAndDrop | response | collectionPointId | string (uuid) | yes
RetailService | createShopAndDrop | response | collectionPointName | string
RetailService | createShopAndDrop | response | status | enum (awaitingCollection, partiallyCollected, collected, uncollected, disposed) | yes
RetailService | createShopAndDrop | response | lines | array of object
RetailService | createShopAndDrop | response | lines[].lineId | string
RetailService | createShopAndDrop | response | lines[].merchandiseId | string (uuid)
RetailService | createShopAndDrop | response | lines[].name | string
RetailService | createShopAndDrop | response | lines[].quantity | integer
RetailService | createShopAndDrop | response | lines[].collectedQuantity | integer
RetailService | createShopAndDrop | response | droppedAt | string (date-time)
RetailService | createShopAndDrop | response | collectBy | string (date-time) | yes
RetailService | createShopAndDrop | response | collectedAt | string (date-time) |  | (nullable)
RetailService | createShopAndDrop | response | collectedByPrincipalId | string (uuid) |  | (nullable)
RetailService | createShopAndDrop | response | verifiedBy | string |  | (nullable)
RetailService | createShopAndDrop | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | createTableReservation | request | id | string (uuid) |  | (read-only)
FnbService | createTableReservation | request | outletId | string (uuid) | yes
FnbService | createTableReservation | request | subjectId | string (uuid) |  | (nullable)
FnbService | createTableReservation | request | guestName | string
FnbService | createTableReservation | request | contactPoint | string
FnbService | createTableReservation | request | partySize | integer | yes | (min 1)
FnbService | createTableReservation | request | startsAt | string (date-time) | yes
FnbService | createTableReservation | request | durationMinutes | integer |  | How long the cover is held.
FnbService | createTableReservation | request | tables | array of FnbReservationTable |  | The dining tables assigned to this reservation, one row each.
FnbService | createTableReservation | request | tables[].reservationId | string (uuid) | yes
FnbService | createTableReservation | request | tables[].tableId | string (uuid) | yes
FnbService | createTableReservation | request | tables[].createdAt | string (date-time) | yes
FnbService | createTableReservation | request | status | TableReservationStatus: enum (awaitingDeposit, booked, confirmed, seated, completed, cancelled, noShow) |  | awaitingDeposit only where the venue's dining deposit applies (decided 29 September, rev 3 REV3-8b); a booking with no deposit starts booked.
FnbService | createTableReservation | request | groupId | string (uuid) |  | 5.1.2. (nullable)
FnbService | createTableReservation | request | notes | string |  | Allergies, accessibility needs and other requests, as the guest wrote them.
FnbService | createTableReservation | request | seatingPreference | string |  | The seating area the guest asked for, e.g. (max length 64; nullable)
FnbService | createTableReservation | request | occasion | enum (birthday, anniversary, business, celebration, other) |  | The occasion the guest named (workbook Q204, DI-337; CHG-CSA-018). (nullable)
FnbService | createTableReservation | request | takenByPrincipalId | string (uuid) |  | The staff member who took the booking (createTableReservationForGuest); null for a guest's own booking (CHG-CSA-045). (read-only; nullable)
FnbService | createTableReservation | request | actualPartySize | integer |  | (read-only; nullable)
FnbService | createTableReservation | request | tableVisitId | string (uuid) |  | (read-only; nullable)
FnbService | createTableReservation | request | deposit | TableReservationDeposit |  | The deposit this booking holds, snapshotted from orders.DepositPolicy.dining when it was made (decided 29 September, rev 3 REV3-8b). (read-only; nullable)
FnbService | createTableReservation | request | deposit.amount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | createTableReservation | request | deposit.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | createTableReservation | request | deposit.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | createTableReservation | request | deposit.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | createTableReservation | request | deposit.basis | enum (fixedPerGuest, fixedPerTable, percentOfMinimumSpend) | yes
FnbService | createTableReservation | request | deposit.holdExpiresAt | string (date-time) |  | While awaitingDeposit, when the held cover is released if the deposit has not been authorised. (nullable)
FnbService | createTableReservation | request | deposit.refundableUntil | string (date-time) |  | startsAt less dining.refundableUntilHours. (nullable)
FnbService | createTableReservation | request | deposit.variantId | string (uuid) |  | The venue's table-deposit variant, DepositPolicy.dining.depositVariantId, which the client sends to addCartLine with this booking's id.
FnbService | createTableReservation | request | deposit.cartLineId | string (uuid) |  | The orders.CartLine carrying the deposit, once added. (nullable)
FnbService | createTableReservation | request | deposit.depositId | string (uuid) |  | The orders.deposit row, once the payment is authorised. (nullable)
FnbService | createTableReservation | request | createdAt | string (date-time) |  | (read-only)
FnbService | createTableReservation | response | id | string (uuid) |  | (read-only)
FnbService | createTableReservation | response | outletId | string (uuid) | yes
FnbService | createTableReservation | response | subjectId | string (uuid) |  | (nullable)
FnbService | createTableReservation | response | guestName | string
FnbService | createTableReservation | response | contactPoint | string
FnbService | createTableReservation | response | partySize | integer | yes | (min 1)
FnbService | createTableReservation | response | startsAt | string (date-time) | yes
FnbService | createTableReservation | response | durationMinutes | integer |  | How long the cover is held.
FnbService | createTableReservation | response | tables | array of FnbReservationTable |  | The dining tables assigned to this reservation, one row each.
FnbService | createTableReservation | response | tables[].reservationId | string (uuid) | yes
FnbService | createTableReservation | response | tables[].tableId | string (uuid) | yes
FnbService | createTableReservation | response | tables[].createdAt | string (date-time) | yes
FnbService | createTableReservation | response | status | TableReservationStatus: enum (awaitingDeposit, booked, confirmed, seated, completed, cancelled, noShow) |  | awaitingDeposit only where the venue's dining deposit applies (decided 29 September, rev 3 REV3-8b); a booking with no deposit starts booked.
FnbService | createTableReservation | response | groupId | string (uuid) |  | 5.1.2. (nullable)
FnbService | createTableReservation | response | notes | string |  | Allergies, accessibility needs and other requests, as the guest wrote them.
FnbService | createTableReservation | response | seatingPreference | string |  | The seating area the guest asked for, e.g. (max length 64; nullable)
FnbService | createTableReservation | response | occasion | enum (birthday, anniversary, business, celebration, other) |  | The occasion the guest named (workbook Q204, DI-337; CHG-CSA-018). (nullable)
FnbService | createTableReservation | response | takenByPrincipalId | string (uuid) |  | The staff member who took the booking (createTableReservationForGuest); null for a guest's own booking (CHG-CSA-045). (read-only; nullable)
FnbService | createTableReservation | response | actualPartySize | integer |  | (read-only; nullable)
FnbService | createTableReservation | response | tableVisitId | string (uuid) |  | (read-only; nullable)
FnbService | createTableReservation | response | deposit | TableReservationDeposit |  | The deposit this booking holds, snapshotted from orders.DepositPolicy.dining when it was made (decided 29 September, rev 3 REV3-8b). (read-only; nullable)
FnbService | createTableReservation | response | deposit.amount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | createTableReservation | response | deposit.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | createTableReservation | response | deposit.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | createTableReservation | response | deposit.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | createTableReservation | response | deposit.basis | enum (fixedPerGuest, fixedPerTable, percentOfMinimumSpend) | yes
FnbService | createTableReservation | response | deposit.holdExpiresAt | string (date-time) |  | While awaitingDeposit, when the held cover is released if the deposit has not been authorised. (nullable)
FnbService | createTableReservation | response | deposit.refundableUntil | string (date-time) |  | startsAt less dining.refundableUntilHours. (nullable)
FnbService | createTableReservation | response | deposit.variantId | string (uuid) |  | The venue's table-deposit variant, DepositPolicy.dining.depositVariantId, which the client sends to addCartLine with this booking's id.
FnbService | createTableReservation | response | deposit.cartLineId | string (uuid) |  | The orders.CartLine carrying the deposit, once added. (nullable)
FnbService | createTableReservation | response | deposit.depositId | string (uuid) |  | The orders.deposit row, once the payment is authorised. (nullable)
FnbService | createTableReservation | response | createdAt | string (date-time) |  | (read-only)
FnbService | createTableReservation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | createTableReservationForGuest | request | id | string (uuid) |  | (read-only)
FnbService | createTableReservationForGuest | request | outletId | string (uuid) | yes
FnbService | createTableReservationForGuest | request | subjectId | string (uuid) |  | (nullable)
FnbService | createTableReservationForGuest | request | guestName | string
FnbService | createTableReservationForGuest | request | contactPoint | string
FnbService | createTableReservationForGuest | request | partySize | integer | yes | (min 1)
FnbService | createTableReservationForGuest | request | startsAt | string (date-time) | yes
FnbService | createTableReservationForGuest | request | durationMinutes | integer |  | How long the cover is held.
FnbService | createTableReservationForGuest | request | tables | array of FnbReservationTable |  | The dining tables assigned to this reservation, one row each.
FnbService | createTableReservationForGuest | request | tables[].reservationId | string (uuid) | yes
FnbService | createTableReservationForGuest | request | tables[].tableId | string (uuid) | yes
FnbService | createTableReservationForGuest | request | tables[].createdAt | string (date-time) | yes
FnbService | createTableReservationForGuest | request | status | TableReservationStatus: enum (awaitingDeposit, booked, confirmed, seated, completed, cancelled, noShow) |  | awaitingDeposit only where the venue's dining deposit applies (decided 29 September, rev 3 REV3-8b); a booking with no deposit starts booked.
FnbService | createTableReservationForGuest | request | groupId | string (uuid) |  | 5.1.2. (nullable)
FnbService | createTableReservationForGuest | request | notes | string |  | Allergies, accessibility needs and other requests, as the guest wrote them.
FnbService | createTableReservationForGuest | request | seatingPreference | string |  | The seating area the guest asked for, e.g. (max length 64; nullable)
FnbService | createTableReservationForGuest | request | occasion | enum (birthday, anniversary, business, celebration, other) |  | The occasion the guest named (workbook Q204, DI-337; CHG-CSA-018). (nullable)
FnbService | createTableReservationForGuest | request | takenByPrincipalId | string (uuid) |  | The staff member who took the booking (createTableReservationForGuest); null for a guest's own booking (CHG-CSA-045). (read-only; nullable)
FnbService | createTableReservationForGuest | request | actualPartySize | integer |  | (read-only; nullable)
FnbService | createTableReservationForGuest | request | tableVisitId | string (uuid) |  | (read-only; nullable)
FnbService | createTableReservationForGuest | request | deposit | TableReservationDeposit |  | The deposit this booking holds, snapshotted from orders.DepositPolicy.dining when it was made (decided 29 September, rev 3 REV3-8b). (read-only; nullable)
FnbService | createTableReservationForGuest | request | deposit.amount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | createTableReservationForGuest | request | deposit.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | createTableReservationForGuest | request | deposit.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | createTableReservationForGuest | request | deposit.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | createTableReservationForGuest | request | deposit.basis | enum (fixedPerGuest, fixedPerTable, percentOfMinimumSpend) | yes
FnbService | createTableReservationForGuest | request | deposit.holdExpiresAt | string (date-time) |  | While awaitingDeposit, when the held cover is released if the deposit has not been authorised. (nullable)
FnbService | createTableReservationForGuest | request | deposit.refundableUntil | string (date-time) |  | startsAt less dining.refundableUntilHours. (nullable)
FnbService | createTableReservationForGuest | request | deposit.variantId | string (uuid) |  | The venue's table-deposit variant, DepositPolicy.dining.depositVariantId, which the client sends to addCartLine with this booking's id.
FnbService | createTableReservationForGuest | request | deposit.cartLineId | string (uuid) |  | The orders.CartLine carrying the deposit, once added. (nullable)
FnbService | createTableReservationForGuest | request | deposit.depositId | string (uuid) |  | The orders.deposit row, once the payment is authorised. (nullable)
FnbService | createTableReservationForGuest | request | createdAt | string (date-time) |  | (read-only)
FnbService | createTableReservationForGuest | response | id | string (uuid) |  | (read-only)
FnbService | createTableReservationForGuest | response | outletId | string (uuid) | yes
FnbService | createTableReservationForGuest | response | subjectId | string (uuid) |  | (nullable)
FnbService | createTableReservationForGuest | response | guestName | string
FnbService | createTableReservationForGuest | response | contactPoint | string
FnbService | createTableReservationForGuest | response | partySize | integer | yes | (min 1)
FnbService | createTableReservationForGuest | response | startsAt | string (date-time) | yes
FnbService | createTableReservationForGuest | response | durationMinutes | integer |  | How long the cover is held.
FnbService | createTableReservationForGuest | response | tables | array of FnbReservationTable |  | The dining tables assigned to this reservation, one row each.
FnbService | createTableReservationForGuest | response | tables[].reservationId | string (uuid) | yes
FnbService | createTableReservationForGuest | response | tables[].tableId | string (uuid) | yes
FnbService | createTableReservationForGuest | response | tables[].createdAt | string (date-time) | yes
FnbService | createTableReservationForGuest | response | status | TableReservationStatus: enum (awaitingDeposit, booked, confirmed, seated, completed, cancelled, noShow) |  | awaitingDeposit only where the venue's dining deposit applies (decided 29 September, rev 3 REV3-8b); a booking with no deposit starts booked.
FnbService | createTableReservationForGuest | response | groupId | string (uuid) |  | 5.1.2. (nullable)
FnbService | createTableReservationForGuest | response | notes | string |  | Allergies, accessibility needs and other requests, as the guest wrote them.
FnbService | createTableReservationForGuest | response | seatingPreference | string |  | The seating area the guest asked for, e.g. (max length 64; nullable)
FnbService | createTableReservationForGuest | response | occasion | enum (birthday, anniversary, business, celebration, other) |  | The occasion the guest named (workbook Q204, DI-337; CHG-CSA-018). (nullable)
FnbService | createTableReservationForGuest | response | takenByPrincipalId | string (uuid) |  | The staff member who took the booking (createTableReservationForGuest); null for a guest's own booking (CHG-CSA-045). (read-only; nullable)
FnbService | createTableReservationForGuest | response | actualPartySize | integer |  | (read-only; nullable)
FnbService | createTableReservationForGuest | response | tableVisitId | string (uuid) |  | (read-only; nullable)
FnbService | createTableReservationForGuest | response | deposit | TableReservationDeposit |  | The deposit this booking holds, snapshotted from orders.DepositPolicy.dining when it was made (decided 29 September, rev 3 REV3-8b). (read-only; nullable)
FnbService | createTableReservationForGuest | response | deposit.amount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | createTableReservationForGuest | response | deposit.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | createTableReservationForGuest | response | deposit.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | createTableReservationForGuest | response | deposit.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | createTableReservationForGuest | response | deposit.basis | enum (fixedPerGuest, fixedPerTable, percentOfMinimumSpend) | yes
FnbService | createTableReservationForGuest | response | deposit.holdExpiresAt | string (date-time) |  | While awaitingDeposit, when the held cover is released if the deposit has not been authorised. (nullable)
FnbService | createTableReservationForGuest | response | deposit.refundableUntil | string (date-time) |  | startsAt less dining.refundableUntilHours. (nullable)
FnbService | createTableReservationForGuest | response | deposit.variantId | string (uuid) |  | The venue's table-deposit variant, DepositPolicy.dining.depositVariantId, which the client sends to addCartLine with this booking's id.
FnbService | createTableReservationForGuest | response | deposit.cartLineId | string (uuid) |  | The orders.CartLine carrying the deposit, once added. (nullable)
FnbService | createTableReservationForGuest | response | deposit.depositId | string (uuid) |  | The orders.deposit row, once the payment is authorised. (nullable)
FnbService | createTableReservationForGuest | response | createdAt | string (date-time) |  | (read-only)
FnbService | createTableReservationForGuest | param (path) | outletId | string (uuid) | yes
FnbService | createTableReservationForGuest | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
LedgerService | createTaxCode | request | code | string | yes | (max length 64)
LedgerService | createTaxCode | request | name | string | yes | (max length 200)
LedgerService | createTaxCode | request | countryCode | string | yes | (pattern ^[A-Z]{2}$)
LedgerService | createTaxCode | request | rate | number | yes | (min 0; max 100)
LedgerService | createTaxCode | request | compoundOnTaxCodeId | string (uuid)
LedgerService | createTaxCode | request | isInclusive | boolean |  | (default False)
LedgerService | createTaxCode | request | accountId | string (uuid) | yes
LedgerService | createTaxCode | request | effectiveFrom | string (date) | yes | A day in the region's time zone, local midnight to local midnight.
LedgerService | createTaxCode | response | id | string (uuid) | yes
LedgerService | createTaxCode | response | code | string | yes | (max length 64)
LedgerService | createTaxCode | response | name | string | yes | (max length 200)
LedgerService | createTaxCode | response | countryCode | string | yes | (pattern ^[A-Z]{2}$)
LedgerService | createTaxCode | response | appliesTo | array of enum (goods, services, admission, food, accommodation, donation, gratuity, fee) |  | What this code covers, and donation is why the field exists (CF-84).
LedgerService | createTaxCode | response | rate | number | yes | (min 0; max 100)
LedgerService | createTaxCode | response | compoundOnTaxCodeId | string (uuid) |  | When set, this tax applies to the base plus the referenced tax, not to the base alone. (nullable)
LedgerService | createTaxCode | response | isInclusive | boolean |  | True when the displayed price already contains this tax.
LedgerService | createTaxCode | response | accountId | string (uuid)
LedgerService | createTaxCode | response | effectiveFrom | string (date) | yes | A day in the region's time zone, local midnight to local midnight.
LedgerService | createTaxCode | response | effectiveTo | string (date) |  | A day in the region's time zone, local midnight to local midnight. (nullable)
LedgerService | createTaxCode | response | isActive | boolean | yes
LedgerService | createTaxCode | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
PlatformService | createTenant | request | code | string | yes | (max length 64; pattern ^[a-z0-9-]+$)
PlatformService | createTenant | request | name | string | yes | (max length 200)
PlatformService | createTenant | request | billingEmail | string | yes
PlatformService | createTenant | request | billingAddress | string |  | (max length 500)
PlatformService | createTenant | request | accountManagerPrincipalId | string (uuid)
PlatformService | createTenant | request | planId | string (uuid)
PlatformService | createTenant | response | id | string (uuid) | yes
PlatformService | createTenant | response | code | string | yes
PlatformService | createTenant | response | name | string | yes
PlatformService | createTenant | response | status | TenantStatus: enum (onboarding, active, suspended, terminating, terminated) | yes
PlatformService | createTenant | response | suspensionMode | SuspensionMode: enum (readOnly, noNewSales, fullLockout) |  | Access validation continues under every mode.
PlatformService | createTenant | response | suspensionReason | string |  | (nullable)
PlatformService | createTenant | response | suspensionEffectiveAt | string (date-time) |  | When the suspension takes, or took, effect — suspendTenant.effectiveAt. (nullable)
PlatformService | createTenant | response | suspensionNoticeMessage | LocalisedText |  | The notice shown to the tenant's users about the suspension — suspendTenant.noticeMessage.
PlatformService | createTenant | response | terminationScheduledAt | string (date-time) |  | When terminateTenant started the retention window. (nullable)
PlatformService | createTenant | response | terminationRetentionUntil | string (date-time) |  | terminationScheduledAt plus the request's retentionDays. (nullable)
PlatformService | createTenant | response | terminationReason | string |  | (max length 1000; nullable)
PlatformService | createTenant | response | terminationRequestedByPrincipalId | string (uuid) |  | (nullable)
PlatformService | createTenant | response | planId | string (uuid) |  | (nullable)
PlatformService | createTenant | response | planName | string |  | (nullable)
PlatformService | createTenant | response | cellCount | integer
PlatformService | createTenant | response | venueCount | integer
PlatformService | createTenant | response | regionId | string (uuid) |  | The tenant's home region: the tenancy region node whose RegionSettings govern tenant-wide gates, today allowedAiResidencies (decided 28 September, audit R203). (read-only; nullable)
PlatformService | createTenant | response | billingEmail | string
PlatformService | createTenant | response | billingAddress | string |  | Accepted by createTenant and updateTenant; stored here so the response can return what was sent. (max length 500; nullable)
PlatformService | createTenant | response | accountManagerPrincipalId | string (uuid) |  | (nullable)
PlatformService | createTenant | response | createdAt | string (date-time) | yes
PlatformService | createTenant | response | activatedAt | string (date-time) |  | (nullable)
PlatformService | createTenant | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | createTicketTemplate | request | name | string |  | (max length 200)
OrderService | createTicketTemplate | request | mediaType | enum (thermalTicket, a4Pdf, wristband, rfidCard, walletPass, qrOnly, sms)
OrderService | createTicketTemplate | request | isRecyclable | boolean
OrderService | createTicketTemplate | request | recycleAfterDays | integer |  | (min 0; nullable)
OrderService | createTicketTemplate | request | appliesToProductKinds | array of string
OrderService | createTicketTemplate | request | appliesToChannels | array of SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …)
OrderService | createTicketTemplate | request | selectionPriority | integer
OrderService | createTicketTemplate | request | layoutRef | string |  | The artwork, as a media-asset reference.
OrderService | createTicketTemplate | request | localeVariants | object
OrderService | createTicketTemplate | request | isActive | boolean
OrderService | createTicketTemplate | response | id | string (uuid) | yes
OrderService | createTicketTemplate | response | name | string | yes
OrderService | createTicketTemplate | response | isRecyclable | boolean |  | BL-103. (default False)
OrderService | createTicketTemplate | response | recycleAfterDays | integer |  | A quarantine before reissue. (nullable)
OrderService | createTicketTemplate | response | mediaType | enum (thermalTicket, a4Pdf, wristband, rfidCard, walletPass, qrOnly, sms) | yes
OrderService | createTicketTemplate | response | appliesToProductKinds | array of string
OrderService | createTicketTemplate | response | appliesToChannels | array of SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …)
OrderService | createTicketTemplate | response | selectionPriority | integer |  | 2.16.x. (default 100)
OrderService | createTicketTemplate | response | layoutRef | string
OrderService | createTicketTemplate | response | localeVariants | object
OrderService | createTicketTemplate | response | isActive | boolean | yes
OrderService | createTicketTemplate | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | createTransportPassType | request | venueId | string (uuid) | yes
VenueOpsService | createTransportPassType | request | code | string | yes | (max length 32)
VenueOpsService | createTransportPassType | request | name | LocalisedText | yes
VenueOpsService | createTransportPassType | request | description | LocalisedText
VenueOpsService | createTransportPassType | request | kind | enum (multiTrip, unlimited) | yes
VenueOpsService | createTransportPassType | request | trips | integer |  | Journeys included. (min 2; max 100; nullable)
VenueOpsService | createTransportPassType | request | fareMultiplier | number | yes | The pass price as a multiple of the single adult fare between its two stations. (min 0; max 1000)
VenueOpsService | createTransportPassType | request | referenceTrips | integer | yes | The single trips the saving is measured against — trips for a multi-trip card, an number the venue sets for unlimited (14 a week, 60 a month in the demo seed data). (min 1; max 1000)
VenueOpsService | createTransportPassType | request | validityDays | integer | yes | (min 1; max 366)
VenueOpsService | createTransportPassType | request | routeIds | array of string (uuid) |  | Routes it is sold on.
VenueOpsService | createTransportPassType | request | sortOrder | integer |  | (min 0; default 0)
VenueOpsService | createTransportPassType | response | venueId | string (uuid) | yes
VenueOpsService | createTransportPassType | response | code | string | yes | (max length 32)
VenueOpsService | createTransportPassType | response | name | LocalisedText | yes
VenueOpsService | createTransportPassType | response | description | LocalisedText
VenueOpsService | createTransportPassType | response | kind | enum (multiTrip, unlimited) | yes
VenueOpsService | createTransportPassType | response | trips | integer |  | Journeys included. (min 2; max 100; nullable)
VenueOpsService | createTransportPassType | response | fareMultiplier | number | yes | The pass price as a multiple of the single adult fare between its two stations. (min 0; max 1000)
VenueOpsService | createTransportPassType | response | referenceTrips | integer | yes | The single trips the saving is measured against — trips for a multi-trip card, an number the venue sets for unlimited (14 a week, 60 a month in the demo seed data). (min 1; max 1000)
VenueOpsService | createTransportPassType | response | validityDays | integer | yes | (min 1; max 366)
VenueOpsService | createTransportPassType | response | routeIds | array of string (uuid) |  | Routes it is sold on.
VenueOpsService | createTransportPassType | response | sortOrder | integer |  | (min 0; default 0)
VenueOpsService | createTransportPassType | response | id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | createTransportPassType | response | active | boolean | yes | (default True)
VenueOpsService | createTransportPassType | response | catalogueProductId | string (uuid) |  | The catalogue openDated product this pass is sold as. (read-only)
VenueOpsService | createTransportPassType | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | createTransportRoute | request | venueId | string (uuid) | yes
VenueOpsService | createTransportRoute | request | code | string | yes | The line and direction, e.g. (max length 32)
VenueOpsService | createTransportRoute | request | lineCode | string |  | The public line number shared by both directions, e.g. (max length 16)
VenueOpsService | createTransportRoute | request | name | LocalisedText | yes
VenueOpsService | createTransportRoute | request | colour | string |  | (pattern ^#[0-9a-fA-F]{6}$)
VenueOpsService | createTransportRoute | request | pairedRouteId | string (uuid) |  | The same line run the other way. (nullable)
VenueOpsService | createTransportRoute | request | bookingCutoffMinutes | integer |  | How long before a departure leaves the boarding stop that online sale stops. (min 0; max 1440; default 5)
VenueOpsService | createTransportRoute | request | stops | array of RouteStopInput | yes | (min items 2; max items 100)
VenueOpsService | createTransportRoute | request | stops[].stationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | createTransportRoute | request | stops[].offsetMinutes | integer | yes | Minutes after the departure from the first stop that the coach leaves this one. (min 0; max 1440)
VenueOpsService | createTransportRoute | request | stops[].boardingAllowed | boolean |  | (default True)
VenueOpsService | createTransportRoute | request | stops[].alightingAllowed | boolean |  | (default True)
VenueOpsService | createTransportRoute | response | venueId | string (uuid) | yes
VenueOpsService | createTransportRoute | response | code | string | yes | The line and direction, e.g. (max length 32)
VenueOpsService | createTransportRoute | response | lineCode | string |  | The public line number shared by both directions, e.g. (max length 16)
VenueOpsService | createTransportRoute | response | name | LocalisedText | yes
VenueOpsService | createTransportRoute | response | colour | string |  | (pattern ^#[0-9a-fA-F]{6}$)
VenueOpsService | createTransportRoute | response | pairedRouteId | string (uuid) |  | The same line run the other way. (nullable)
VenueOpsService | createTransportRoute | response | bookingCutoffMinutes | integer |  | How long before a departure leaves the boarding stop that online sale stops. (min 0; max 1440; default 5)
VenueOpsService | createTransportRoute | response | stops | array of RouteStop | yes
VenueOpsService | createTransportRoute | response | stops[].stationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | createTransportRoute | response | stops[].offsetMinutes | integer | yes | Minutes after the departure from the first stop that the coach leaves this one. (min 0; max 1440)
VenueOpsService | createTransportRoute | response | stops[].boardingAllowed | boolean |  | (default True)
VenueOpsService | createTransportRoute | response | stops[].alightingAllowed | boolean |  | (default True)
VenueOpsService | createTransportRoute | response | stops[].id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | createTransportRoute | response | stops[].sequence | integer | yes | 1 for the origin. (min 1)
VenueOpsService | createTransportRoute | response | stops[].station | Station
VenueOpsService | createTransportRoute | response | stops[].station.venueId | string (uuid) | yes
VenueOpsService | createTransportRoute | response | stops[].station.code | string | yes | Short operator code, e.g. (max length 32)
VenueOpsService | createTransportRoute | response | stops[].station.name | LocalisedText | yes
VenueOpsService | createTransportRoute | response | stops[].station.shortName | LocalisedText |  | The label on the route diagram and the map pin (Union Sq, MoE).
VenueOpsService | createTransportRoute | response | stops[].station.latitude | number |  | (min -90; max 90; nullable)
VenueOpsService | createTransportRoute | response | stops[].station.longitude | number |  | (min -180; max 180; nullable)
VenueOpsService | createTransportRoute | response | stops[].station.id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | createTransportRoute | response | stops[].station.active | boolean | yes | (default True)
VenueOpsService | createTransportRoute | response | id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | createTransportRoute | response | status | TransportRouteStatus: enum (draft, active, suspended, retired) | yes
VenueOpsService | createTransportRoute | response | totalMinutes | integer |  | The last stop's offset. (read-only)
VenueOpsService | createTransportRoute | response | catalogueEventId | string (uuid) |  | The catalogue event its departures are performances of. (read-only)
VenueOpsService | createTransportRoute | response | catalogueProductId | string (uuid) |  | The one-way trip product (kind timedAdmission); one variant per passenger type. (read-only)
VenueOpsService | createTransportRoute | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | createTransportStation | request | venueId | string (uuid) | yes
VenueOpsService | createTransportStation | request | code | string | yes | Short operator code, e.g. (max length 32)
VenueOpsService | createTransportStation | request | name | LocalisedText | yes
VenueOpsService | createTransportStation | request | shortName | LocalisedText |  | The label on the route diagram and the map pin (Union Sq, MoE).
VenueOpsService | createTransportStation | request | latitude | number |  | (min -90; max 90; nullable)
VenueOpsService | createTransportStation | request | longitude | number |  | (min -180; max 180; nullable)
VenueOpsService | createTransportStation | response | venueId | string (uuid) | yes
VenueOpsService | createTransportStation | response | code | string | yes | Short operator code, e.g. (max length 32)
VenueOpsService | createTransportStation | response | name | LocalisedText | yes
VenueOpsService | createTransportStation | response | shortName | LocalisedText |  | The label on the route diagram and the map pin (Union Sq, MoE).
VenueOpsService | createTransportStation | response | latitude | number |  | (min -90; max 90; nullable)
VenueOpsService | createTransportStation | response | longitude | number |  | (min -180; max 180; nullable)
VenueOpsService | createTransportStation | response | id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | createTransportStation | response | active | boolean | yes | (default True)
VenueOpsService | createTransportStation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | createTransportTimetable | request | name | string | yes | (max length 120)
VenueOpsService | createTransportTimetable | request | validFrom | string (date) | yes
VenueOpsService | createTransportTimetable | request | validTo | string (date) |  | (nullable)
VenueOpsService | createTransportTimetable | request | releaseHorizonDays | integer |  | How many days ahead departures go on sale. (min 1; max 365; default 30)
VenueOpsService | createTransportTimetable | request | seatCapacity | integer | yes | Seats per departure, unless a departure overrides it. (min 1; max 200)
VenueOpsService | createTransportTimetable | request | seatMapId | string (uuid) |  | The coach seat map for Seat Selection (seating). (nullable)
VenueOpsService | createTransportTimetable | request | runs | array of TimetableRun | yes | (min items 1; max items 500)
VenueOpsService | createTransportTimetable | request | runs[].departsAt | string | yes | Venue local time, 24-hour HH:MM, at the route's first stop. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
VenueOpsService | createTransportTimetable | request | runs[].days | array of enum (mon, tue, wed, thu, fri, sat, sun) | yes | (min items 1)
VenueOpsService | createTransportTimetable | response | name | string | yes | (max length 120)
VenueOpsService | createTransportTimetable | response | validFrom | string (date) | yes
VenueOpsService | createTransportTimetable | response | validTo | string (date) |  | (nullable)
VenueOpsService | createTransportTimetable | response | releaseHorizonDays | integer |  | How many days ahead departures go on sale. (min 1; max 365; default 30)
VenueOpsService | createTransportTimetable | response | seatCapacity | integer | yes | Seats per departure, unless a departure overrides it. (min 1; max 200)
VenueOpsService | createTransportTimetable | response | seatMapId | string (uuid) |  | The coach seat map for Seat Selection (seating). (nullable)
VenueOpsService | createTransportTimetable | response | runs | array of TimetableRun | yes | (min items 1; max items 500)
VenueOpsService | createTransportTimetable | response | runs[].departsAt | string | yes | Venue local time, 24-hour HH:MM, at the route's first stop. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
VenueOpsService | createTransportTimetable | response | runs[].days | array of enum (mon, tue, wed, thu, fri, sat, sun) | yes | (min items 1)
VenueOpsService | createTransportTimetable | response | id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | createTransportTimetable | response | routeId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | createTransportTimetable | response | status | TransportTimetableStatus: enum (draft, published, superseded, withdrawn) | yes
VenueOpsService | createTransportTimetable | response | publishedAt | string (date-time) |  | (read-only; nullable)
VenueOpsService | createTransportTimetable | response | releasedThrough | string (date) |  | The last date whose departures have been generated. (read-only; nullable)
VenueOpsService | createTransportTimetable | response | supersededById | string (uuid) |  | (read-only; nullable)
VenueOpsService | createTransportTimetable | param (path) | routeId | string (uuid) | yes
VenueOpsService | createTransportTimetable | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | createUpload | request | filename | string | yes | (max length 256)
VenueOpsService | createUpload | request | contentType | string | yes
VenueOpsService | createUpload | request | sizeBytes | integer | yes | (min 1)
VenueOpsService | createUpload | request | venueId | string (uuid)
VenueOpsService | createUpload | response | id | string (uuid) |  | Added 20 August. (read-only)
VenueOpsService | createUpload | response | uploadId | string (uuid) | yes
VenueOpsService | createUpload | response | uploadUrl | string | yes | Signed.
VenueOpsService | createUpload | response | method | enum (PUT, POST) | yes
VenueOpsService | createUpload | response | headers | object
VenueOpsService | createUpload | response | maxSizeBytes | integer
VenueOpsService | createUpload | response | expiresAt | string (date-time) | yes
VenueOpsService | createUpload | response | filename | string
VenueOpsService | createUpload | response | contentType | string
VenueOpsService | createUpload | response | sizeBytes | integer
VenueOpsService | createUpload | response | venueId | string (uuid) |  | (nullable)
VenueOpsService | createUpload | response | assetId | string (uuid) |  | The asset this upload became — created by completeUpload, or the asset whose file replaceMediaAsset swapped. (read-only; nullable)
VenueOpsService | createUpload | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | createUrlRedirect | request | id | string (uuid) | yes | (read-only)
MarketingService | createUrlRedirect | request | fromPath | string | yes
MarketingService | createUrlRedirect | request | toPath | string | yes
MarketingService | createUrlRedirect | request | statusCode | enum (301, 302, 307, 308) | yes
MarketingService | createUrlRedirect | request | reason | enum (contentMigrated, pageRetired, campaignExpired, restructure, slugChanged)
MarketingService | createUrlRedirect | request | createdAt | string (date-time) |  | Taken from their whitelabel.redirect, 20 September. (read-only; nullable)
MarketingService | createUrlRedirect | request | hitCount | integer |  | (read-only)
MarketingService | createUrlRedirect | request | isActive | boolean |  | (default True)
MarketingService | createUrlRedirect | request | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | createUrlRedirect | response | id | string (uuid) | yes | (read-only)
MarketingService | createUrlRedirect | response | fromPath | string | yes
MarketingService | createUrlRedirect | response | toPath | string | yes
MarketingService | createUrlRedirect | response | statusCode | enum (301, 302, 307, 308) | yes
MarketingService | createUrlRedirect | response | reason | enum (contentMigrated, pageRetired, campaignExpired, restructure, slugChanged)
MarketingService | createUrlRedirect | response | createdAt | string (date-time) |  | Taken from their whitelabel.redirect, 20 September. (read-only; nullable)
MarketingService | createUrlRedirect | response | hitCount | integer |  | (read-only)
MarketingService | createUrlRedirect | response | isActive | boolean |  | (default True)
MarketingService | createUrlRedirect | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | createUrlRedirect | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | createVenueMap | request | id | string (uuid) | yes | (read-only)
VenueOpsService | createVenueMap | request | name | string | yes
VenueOpsService | createVenueMap | request | venueId | string (uuid) | yes
VenueOpsService | createVenueMap | request | scopePath | string |  | Derived from venueId. (read-only)
VenueOpsService | createVenueMap | request | kind | enum (park, floor, zone, parking)
VenueOpsService | createVenueMap | request | floorLevel | integer |  | (nullable)
VenueOpsService | createVenueMap | request | status | enum (draft, published, archived) | yes | draft on create. (read-only)
VenueOpsService | createVenueMap | request | publishedVersion | integer |  | The VenueMapVersion.version guests are served. (read-only; nullable)
VenueOpsService | createVenueMap | request | graphVersion | integer |  | Bumped by a publish or a closure, and returned as VenueMapGraph.version. (read-only)
VenueOpsService | createVenueMap | request | isGeoreferenced | boolean |  | Whether a guest can be located on it. (read-only)
VenueOpsService | createVenueMap | request | baseAssetId | string (uuid) |  | The illustrated map a guest actually sees, held in assets like any other media. (nullable)
VenueOpsService | createVenueMap | request | baseImageAlignment | object |  | How the illustration lines up with the geometry. (nullable)
VenueOpsService | createVenueMap | request | baseImageAlignment.imageWidthPx | integer
VenueOpsService | createVenueMap | request | baseImageAlignment.imageHeightPx | integer
VenueOpsService | createVenueMap | request | baseImageAlignment.anchors | array of object |  | (min items 2; max items 4)
VenueOpsService | createVenueMap | request | baseImageAlignment.anchors[].planX | number
VenueOpsService | createVenueMap | request | baseImageAlignment.anchors[].planY | number
VenueOpsService | createVenueMap | request | baseImageAlignment.anchors[].imageX | number
VenueOpsService | createVenueMap | request | baseImageAlignment.anchors[].imageY | number
VenueOpsService | createVenueMap | request | tileSetRef | string |  | Where a base image is large enough to need zoom levels. (read-only; nullable)
VenueOpsService | createVenueMap | request | boundsGeoJson | string |  | (nullable)
VenueOpsService | createVenueMap | request | graphStatus | enum (notBuilt, connected, disconnected, partial) |  | Whether every public point can actually be reached. (read-only)
VenueOpsService | createVenueMap | request | modelAssetId | string (uuid) |  | The 3D layer of the working draft (ADR-0069, contract item closed 3 October 2026): the GLB (model3d asset) the last glbModel import brought in. (read-only; nullable)
VenueOpsService | createVenueMap | request | navigationFileAssetId | string (uuid) |  | The navigation file imported with the model, kept so the import can be re-run and audited. (read-only; nullable)
VenueOpsService | createVenueMap | request | modelTransform | object |  | How the model's local frame sits on the earth (ADR-0069 section 3): the navigation file's anchor, stored once and used both ways. (read-only)
VenueOpsService | createVenueMap | request | modelTransform.originLat | number | yes | (min -90; max 90)
VenueOpsService | createVenueMap | request | modelTransform.originLng | number | yes | (min -180; max 180)
VenueOpsService | createVenueMap | request | modelTransform.originAltitudeMetres | number |  | (default 0)
VenueOpsService | createVenueMap | request | modelTransform.headingDegrees | number | yes | True-north bearing of the model's -Z axis, clockwise. (min 0)
VenueOpsService | createVenueMap | request | modelTransform.scale | number |  | Metres per model unit; 1 for a model in metres. (default 1)
VenueOpsService | createVenueMap | request | modelTransform.controlPoints | array of object |  | Surveyed checks, far apart. (min items 2; max items 8)
VenueOpsService | createVenueMap | request | modelTransform.controlPoints[].label | string | yes
VenueOpsService | createVenueMap | request | modelTransform.controlPoints[].x | number | yes
VenueOpsService | createVenueMap | request | modelTransform.controlPoints[].z | number | yes
VenueOpsService | createVenueMap | request | modelTransform.controlPoints[].lat | number | yes
VenueOpsService | createVenueMap | request | modelTransform.controlPoints[].lng | number | yes
VenueOpsService | createVenueMap | request | modelTransform.controlPoints[].residualMetres | number |  | Measured at import. (read-only; nullable)
VenueOpsService | createVenueMap | request | model3dStatus | enum (none, publishable, blocked) |  | Whether the next publish carries the 3D layer. (read-only)
VenueOpsService | createVenueMap | response | id | string (uuid) | yes | (read-only)
VenueOpsService | createVenueMap | response | name | string | yes
VenueOpsService | createVenueMap | response | venueId | string (uuid) | yes
VenueOpsService | createVenueMap | response | scopePath | string |  | Derived from venueId. (read-only)
VenueOpsService | createVenueMap | response | kind | enum (park, floor, zone, parking)
VenueOpsService | createVenueMap | response | floorLevel | integer |  | (nullable)
VenueOpsService | createVenueMap | response | status | enum (draft, published, archived) | yes | draft on create. (read-only)
VenueOpsService | createVenueMap | response | publishedVersion | integer |  | The VenueMapVersion.version guests are served. (read-only; nullable)
VenueOpsService | createVenueMap | response | graphVersion | integer |  | Bumped by a publish or a closure, and returned as VenueMapGraph.version. (read-only)
VenueOpsService | createVenueMap | response | isGeoreferenced | boolean |  | Whether a guest can be located on it. (read-only)
VenueOpsService | createVenueMap | response | baseAssetId | string (uuid) |  | The illustrated map a guest actually sees, held in assets like any other media. (nullable)
VenueOpsService | createVenueMap | response | baseImageAlignment | object |  | How the illustration lines up with the geometry. (nullable)
VenueOpsService | createVenueMap | response | baseImageAlignment.imageWidthPx | integer
VenueOpsService | createVenueMap | response | baseImageAlignment.imageHeightPx | integer
VenueOpsService | createVenueMap | response | baseImageAlignment.anchors | array of object |  | (min items 2; max items 4)
VenueOpsService | createVenueMap | response | baseImageAlignment.anchors[].planX | number
VenueOpsService | createVenueMap | response | baseImageAlignment.anchors[].planY | number
VenueOpsService | createVenueMap | response | baseImageAlignment.anchors[].imageX | number
VenueOpsService | createVenueMap | response | baseImageAlignment.anchors[].imageY | number
VenueOpsService | createVenueMap | response | tileSetRef | string |  | Where a base image is large enough to need zoom levels. (read-only; nullable)
VenueOpsService | createVenueMap | response | boundsGeoJson | string |  | (nullable)
VenueOpsService | createVenueMap | response | graphStatus | enum (notBuilt, connected, disconnected, partial) |  | Whether every public point can actually be reached. (read-only)
VenueOpsService | createVenueMap | response | modelAssetId | string (uuid) |  | The 3D layer of the working draft (ADR-0069, contract item closed 3 October 2026): the GLB (model3d asset) the last glbModel import brought in. (read-only; nullable)
VenueOpsService | createVenueMap | response | navigationFileAssetId | string (uuid) |  | The navigation file imported with the model, kept so the import can be re-run and audited. (read-only; nullable)
VenueOpsService | createVenueMap | response | modelTransform | object |  | How the model's local frame sits on the earth (ADR-0069 section 3): the navigation file's anchor, stored once and used both ways. (read-only)
VenueOpsService | createVenueMap | response | modelTransform.originLat | number | yes | (min -90; max 90)
VenueOpsService | createVenueMap | response | modelTransform.originLng | number | yes | (min -180; max 180)
VenueOpsService | createVenueMap | response | modelTransform.originAltitudeMetres | number |  | (default 0)
VenueOpsService | createVenueMap | response | modelTransform.headingDegrees | number | yes | True-north bearing of the model's -Z axis, clockwise. (min 0)
VenueOpsService | createVenueMap | response | modelTransform.scale | number |  | Metres per model unit; 1 for a model in metres. (default 1)
VenueOpsService | createVenueMap | response | modelTransform.controlPoints | array of object |  | Surveyed checks, far apart. (min items 2; max items 8)
VenueOpsService | createVenueMap | response | modelTransform.controlPoints[].label | string | yes
VenueOpsService | createVenueMap | response | modelTransform.controlPoints[].x | number | yes
VenueOpsService | createVenueMap | response | modelTransform.controlPoints[].z | number | yes
VenueOpsService | createVenueMap | response | modelTransform.controlPoints[].lat | number | yes
VenueOpsService | createVenueMap | response | modelTransform.controlPoints[].lng | number | yes
VenueOpsService | createVenueMap | response | modelTransform.controlPoints[].residualMetres | number |  | Measured at import. (read-only; nullable)
VenueOpsService | createVenueMap | response | model3dStatus | enum (none, publishable, blocked) |  | Whether the next publish carries the 3D layer. (read-only)
VenueOpsService | createVenueMap | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | decideAiInsight | request | decision | enum (review, accept, reject, actioned) | yes
AiService | decideAiInsight | request | reason | string |  | (max length 1000; nullable)
AiService | decideAiInsight | request | actionRef | string |  | (nullable)
AiService | decideAiInsight | response | id | string (uuid) |  | (read-only)
AiService | decideAiInsight | response | kind | enum (anomaly, forecastDeviation, trend, opportunity, executiveSummary, rootCause, forecastThreshold, marketingRecommendation) | yes
AiService | decideAiInsight | response | detectorId | string (uuid) |  | (nullable)
AiService | decideAiInsight | response | metricKey | string |  | (nullable)
AiService | decideAiInsight | response | subjectKind | enum (campaign, journey, forecastDefinition, venue) |  | What the insight is about where it is not a KPI (29 September, build): a marketing-crm campaign or journey for marketingRecommendation, a forecast definition for forecastThreshold. (nullable)
AiService | decideAiInsight | response | subjectRef | string |  | (nullable)
AiService | decideAiInsight | response | recommendedAction | object |  | For marketingRecommendation: {recommendation, parameters} as AiMarketingRecommendation. (nullable)
AiService | decideAiInsight | response | expectedImpact | object |  | A range on a named metric (metric, low, high), never a single number (design 5.6). (nullable)
AiService | decideAiInsight | response | title | string | yes
AiService | decideAiInsight | response | narrative | string |  | (nullable)
AiService | decideAiInsight | response | evidence | array of AiEvidenceItem |  | The evidence of one decision record, stored with it.
AiService | decideAiInsight | response | evidence[].label | enum (source, derived, modelInferred) | yes
AiService | decideAiInsight | response | evidence[].kind | string | yes | What it is: feature, rule, document, metric, transaction, candidateSet.
AiService | decideAiInsight | response | evidence[].ref | string |  | Where it came from: a table and id, a document chunk, a metric key. (nullable)
AiService | decideAiInsight | response | evidence[].name | string
AiService | decideAiInsight | response | evidence[].value | object |  | (nullable)
AiService | decideAiInsight | response | evidence[].observedAt | string (date-time) |  | (nullable)
AiService | decideAiInsight | response | magnitude | number |  | (nullable)
AiService | decideAiInsight | response | priority | enum (low, medium, high, critical)
AiService | decideAiInsight | response | correlationKey | string |  | (nullable)
AiService | decideAiInsight | response | status | enum (new, reviewed, accepted, rejected, actioned, measured) | yes | (read-only)
AiService | decideAiInsight | response | decidedByPrincipalId | string (uuid) |  | (read-only; nullable)
AiService | decideAiInsight | response | decidedAt | string (date-time) |  | (read-only; nullable)
AiService | decideAiInsight | response | actionRef | string |  | (nullable)
AiService | decideAiInsight | response | measuredImpact | object |  | (read-only; nullable)
AiService | decideAiInsight | response | decisionRecordId | string (uuid) |  | (read-only; nullable)
AiService | decideAiInsight | response | detectedAt | string (date-time) |  | (read-only)
AiService | decideAiInsight | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | decideAiInsight | param (path) | insightId | string (uuid) | yes
AiService | decideAiInsight | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | decideApprovalRequest | request | decision | enum (approve, reject, return, requestInformation) | yes
TenancyService | decideApprovalRequest | request | comment | string |  | (max length 1000)
TenancyService | decideApprovalRequest | request | reason | string |  | Required on rejection. (max length 500)
TenancyService | decideApprovalRequest | request | stepUpToken | string |  | Where the rule demands MFA (11.1.60).
TenancyService | decideApprovalRequest | request | signature | string |  | 11.1.57.
TenancyService | decideApprovalRequest | response | id | string | yes
TenancyService | decideApprovalRequest | response | kind | ApprovalKind: enum (refund, priceOverride, discountOverride, complimentaryTicket, membershipCancellation, accessPermissionChange, configurationChange, aiRecommendation, …) | yes | 11.1.7 and 11.1.30–11.1.37.
TenancyService | decideApprovalRequest | response | rerouteOnNoApprover | boolean |  | BL-154. (default True)
TenancyService | decideApprovalRequest | response | outOfOfficeDelegateId | string (uuid) |  | (nullable)
TenancyService | decideApprovalRequest | response | allowEmailApproval | boolean |  | Approving from an email link with no second factor is the weakest path in the system, so it is off by default and available only below a configured value. (default False)
TenancyService | decideApprovalRequest | response | reopenedFrom | string (uuid) |  | Reopening a decided approval creates a new one that points back. (nullable)
TenancyService | decideApprovalRequest | response | status | ApprovalStatus: enum (draft, pending, escalated, returned, informationRequested, approved, rejected, withdrawn, …) | yes
TenancyService | decideApprovalRequest | response | subjectContract | string
TenancyService | decideApprovalRequest | response | subjectType | string
TenancyService | decideApprovalRequest | response | subjectId | string
TenancyService | decideApprovalRequest | response | scopePath | string
TenancyService | decideApprovalRequest | response | summary | string
TenancyService | decideApprovalRequest | response | amount | Money |  | On the wire this is three fields; in the database it is one column.
TenancyService | decideApprovalRequest | response | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | decideApprovalRequest | response | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | decideApprovalRequest | response | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | decideApprovalRequest | response | justification | string |  | (nullable)
TenancyService | decideApprovalRequest | response | requestedByPrincipalId | string (uuid) | yes
TenancyService | decideApprovalRequest | response | matrixVersion | integer
TenancyService | decideApprovalRequest | response | mode | ApprovalMode: enum (sequential, parallel, consensus, majority) |  | 11.1.43–11.1.46.
TenancyService | decideApprovalRequest | response | currentLevel | integer
TenancyService | decideApprovalRequest | response | totalLevels | integer
TenancyService | decideApprovalRequest | response | pendingApprovers | array of object
TenancyService | decideApprovalRequest | response | pendingApprovers[].principalId | string (uuid)
TenancyService | decideApprovalRequest | response | pendingApprovers[].displayName | string
TenancyService | decideApprovalRequest | response | pendingApprovers[].isDelegate | boolean
TenancyService | decideApprovalRequest | response | decisions | array of ApprovalDecision |  | Every decision at every level, in order.
TenancyService | decideApprovalRequest | response | decisions[].id | string (uuid) |  | Added 20 August. (read-only)
TenancyService | decideApprovalRequest | response | decisions[].level | integer | yes
TenancyService | decideApprovalRequest | response | decisions[].principalId | string (uuid) | yes
TenancyService | decideApprovalRequest | response | decisions[].displayName | string
TenancyService | decideApprovalRequest | response | decisions[].isDelegate | boolean
TenancyService | decideApprovalRequest | response | decisions[].delegatedFrom | string (uuid) |  | (nullable)
TenancyService | decideApprovalRequest | response | decisions[].decision | enum (approve, reject) | yes
TenancyService | decideApprovalRequest | response | decisions[].comment | string |  | (nullable)
TenancyService | decideApprovalRequest | response | decisions[].reason | string |  | (nullable)
TenancyService | decideApprovalRequest | response | decisions[].usedMfa | boolean
TenancyService | decideApprovalRequest | response | decisions[].signatureRef | string |  | (nullable)
TenancyService | decideApprovalRequest | response | decisions[].decidedAt | string (date-time) | yes
TenancyService | decideApprovalRequest | response | escalations | array of object |  | 11.1.48.
TenancyService | decideApprovalRequest | response | escalations[].at | string (date-time)
TenancyService | decideApprovalRequest | response | escalations[].reason | string
TenancyService | decideApprovalRequest | response | escalations[].fromLevel | integer
TenancyService | decideApprovalRequest | response | escalations[].toLevel | integer
TenancyService | decideApprovalRequest | response | escalations[].wasAutomatic | boolean
TenancyService | decideApprovalRequest | response | resubmittedFromId | string |  | (nullable)
TenancyService | decideApprovalRequest | response | reopenedFromId | string |  | (nullable)
TenancyService | decideApprovalRequest | response | slaDueAt | string (date-time) |  | (nullable)
TenancyService | decideApprovalRequest | response | slaBreached | boolean
TenancyService | decideApprovalRequest | response | expiresAt | string (date-time) |  | (nullable)
TenancyService | decideApprovalRequest | response | assignedToPrincipalId | string (uuid) |  | Who claimed or was assigned the request in a shared queue (assignApprovalRequest; DI-723; CHG-CSP-042). (read-only; nullable)
TenancyService | decideApprovalRequest | response | assignedToDepartmentId | string (uuid) |  | The department queue it was assigned to, where it went to a department rather than a person (CHG-CSP-042). (read-only; nullable)
TenancyService | decideApprovalRequest | response | assignedAt | string (date-time) |  | (read-only; nullable)
TenancyService | decideApprovalRequest | response | requestedAt | string (date-time) | yes
TenancyService | decideApprovalRequest | response | completedAt | string (date-time) |  | (nullable)
TenancyService | decideApprovalRequest | response | aiAssessment | object |  | AI context for the reviewer, never an input to the decision (11.1.73 to 11.1.75; MoM 8 September; 29 September, build pass, group G2). (read-only; nullable)
TenancyService | decideApprovalRequest | response | aiAssessment.riskScore | integer |  | (min 0; max 100)
TenancyService | decideApprovalRequest | response | aiAssessment.riskBand | enum (low, medium, high, critical)
TenancyService | decideApprovalRequest | response | aiAssessment.priorityScore | integer |  | (min 0; max 100)
TenancyService | decideApprovalRequest | response | aiAssessment.escalationSuggestion | object |  | A suggestion a person may act on through escalateApprovalRequest, or the tenant's own SLA policy may; nothing escalates because of it.
TenancyService | decideApprovalRequest | response | aiAssessment.escalationSuggestion.action | enum (escalate, addBackupApprover, none)
TenancyService | decideApprovalRequest | response | aiAssessment.escalationSuggestion.reason | string |  | (nullable)
TenancyService | decideApprovalRequest | response | aiAssessment.signals | array of object |  | The signals behind the scores, largest first, as ai.AiApprovalRequestScore.signals. (max items 10)
TenancyService | decideApprovalRequest | response | aiAssessment.signals[].code | string
TenancyService | decideApprovalRequest | response | aiAssessment.signals[].contribution | number
TenancyService | decideApprovalRequest | response | aiAssessment.signals[].detail | string |  | (nullable)
TenancyService | decideApprovalRequest | response | aiAssessment.scoreId | string (uuid) |  | The ai.approval_request_score row it was copied from; ai.getApprovalRequestScore gives the full context.
TenancyService | decideApprovalRequest | response | aiAssessment.decisionRecordId | string |  | The ai decision record, for the audit of what the AI said and why.
TenancyService | decideApprovalRequest | response | aiAssessment.assessedAt | string (date-time)
TenancyService | decideApprovalRequest | param (path) | requestId | string (uuid) | yes
TenancyService | decideApprovalRequest | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | decideOperationalRequirement | request | decision | enum (accept, modify, reject) | yes
AiService | decideOperationalRequirement | request | quantity | number |  | (nullable)
AiService | decideOperationalRequirement | request | note | string |  | (max length 1000; nullable)
AiService | decideOperationalRequirement | response | id | string (uuid) |  | (read-only)
AiService | decideOperationalRequirement | response | versionId | string (uuid) | yes
AiService | decideOperationalRequirement | response | kind | enum (staff, pos, kiosk, gates, fnb, retail, stock, resource, …) | yes
AiService | decideOperationalRequirement | response | targetContract | string |  | The owning module that applies it: workforce, fnb, inventory, resources, access.
AiService | decideOperationalRequirement | response | subjectRef | string |  | A role, outlet, gate, item or resource type. (nullable)
AiService | decideOperationalRequirement | response | periodStart | string (date-time) | yes
AiService | decideOperationalRequirement | response | periodEnd | string (date-time)
AiService | decideOperationalRequirement | response | quantity | number | yes
AiService | decideOperationalRequirement | response | quantityP90 | number |  | The requirement at the forecast's 90th percentile, for planning to the busy case. (nullable)
AiService | decideOperationalRequirement | response | unit | string
AiService | decideOperationalRequirement | response | productivityStandard | object |  | The standard used, e.g. (nullable)
AiService | decideOperationalRequirement | response | status | enum (issued, accepted, modified, rejected, handedOver, expired) |  | (read-only)
AiService | decideOperationalRequirement | response | decidedByPrincipalId | string (uuid) |  | (read-only; nullable)
AiService | decideOperationalRequirement | response | decidedAt | string (date-time) |  | (read-only; nullable)
AiService | decideOperationalRequirement | response | decisionNote | string |  | (nullable)
AiService | decideOperationalRequirement | response | handoverRef | string |  | The owning module's record once handed over. (read-only; nullable)
AiService | decideOperationalRequirement | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | decideOperationalRequirement | param (path) | requirementId | string (uuid) | yes
AiService | decideOperationalRequirement | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
PlatformService | decideProductionAccess | request | decision | enum (approve, reject) | yes
PlatformService | decideProductionAccess | request | reason | string |  | (max length 1000; nullable)
PlatformService | decideProductionAccess | request | scopes | array of string |  | Narrow the requested scopes.
PlatformService | decideProductionAccess | request | credentialTtlDays | integer |  | (min 1; max 730; default 365)
PlatformService | decideProductionAccess | response | id | string (uuid) | yes | (read-only)
PlatformService | decideProductionAccess | response | developerId | string (uuid) | yes | (read-only)
PlatformService | decideProductionAccess | response | sandboxClientId | string (uuid) | yes | (read-only)
PlatformService | decideProductionAccess | response | listingId | string (uuid) | yes
PlatformService | decideProductionAccess | response | scopes | array of string
PlatformService | decideProductionAccess | response | allowedTenantIds | array of string (uuid)
PlatformService | decideProductionAccess | response | ipAllowList | array of string
PlatformService | decideProductionAccess | response | note | string |  | (nullable)
PlatformService | decideProductionAccess | response | status | enum (pending, approved, rejected, withdrawn) | yes | (read-only)
PlatformService | decideProductionAccess | response | decidedByPrincipalId | string (uuid) |  | (read-only; nullable)
PlatformService | decideProductionAccess | response | decidedAt | string (date-time) |  | (read-only; nullable)
PlatformService | decideProductionAccess | response | reason | string |  | (read-only; nullable)
PlatformService | decideProductionAccess | response | productionClientId | string (uuid) |  | (read-only; nullable)
PlatformService | decideProductionAccess | response | requestedAt | string (date-time) |  | (read-only)
PlatformService | decideProductionAccess | param (path) | requestId | string (uuid) | yes
PlatformService | decideProductionAccess | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | decideProposedAction | request | decision | enum (approve, reject) | yes
AiService | decideProposedAction | request | reason | string |  | (max length 500)
AiService | decideProposedAction | response | id | string (uuid) | yes
AiService | decideProposedAction | response | interactionId | string (uuid)
AiService | decideProposedAction | response | translationJobId | string (uuid) |  | The proposeTranslations job that drafted this proposal; getTranslationProposals reads a job's rows by it. (read-only; nullable)
AiService | decideProposedAction | response | kind | enum (pricing, promotion, operational, financial, configuration, content, audience) | yes | content (a marketing or storefront draft from proposeMarketingContent) and audience (a lookalike segment from proposeLookalikeSegment) added 29 September (build); both are applied by a person in the…
AiService | decideProposedAction | response | targetContract | string | yes | Which contract would perform it.
AiService | decideProposedAction | response | targetOperation | string | yes
AiService | decideProposedAction | response | payload | object | yes | The request body a person would submit, ready to review.
AiService | decideProposedAction | response | summary | string
AiService | decideProposedAction | response | status | enum (proposed, approved, rejected, applied, expired) | yes | Expiry (decided 28 September, audit R213): a proposed action expires 7 days after proposedAt; an approved action not applied expires 24 hours after decidedAt.
AiService | decideProposedAction | response | expiresAt | string (date-time) |  | When the expiry timer moves this action to expired — proposedAt plus 7 days while proposed, decidedAt plus 24 hours once approved, null once rejected, applied or expired (audit R213). (read-only; nullable)
AiService | decideProposedAction | response | approvalLevel | integer |  | 8.3.65. (min 1; max 2)
AiService | decideProposedAction | response | decidedByPrincipalId | string (uuid) |  | (nullable)
AiService | decideProposedAction | response | decisionReason | string |  | Required on rejection. (nullable)
AiService | decideProposedAction | response | proposedAt | string (date-time)
AiService | decideProposedAction | response | decidedAt | string (date-time) |  | (nullable)
AiService | decideProposedAction | response | scopePath | string |  | Added 29 September (AI design 3.1): ai.proposed_action had no policy — its only references were nullable. (read-only)
AiService | decideProposedAction | response | planId | string (uuid) |  | The plan this action presents for a decision (AI design 2.2 D, 3.8). (read-only; nullable)
AiService | decideProposedAction | response | approvalRequestId | string (uuid) |  | The approvals request deciding a tier 2 or matrix-caught action (AI design 2.3). (read-only; nullable)
AiService | decideProposedAction | response | changeSetHash | string |  | Hash of the change set approved; execution refuses a plan whose hash differs (AIC-181). (read-only; nullable)
AiService | decideProposedAction | param (path) | actionId | string (uuid) | yes
AiService | decideProposedAction | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | decideRecommendations | request | placement | enum (productPage, cart, checkout, postPurchase, preVisit, inVenue, posBasket, kioskBasket, …) | yes
AiService | decideRecommendations | request | channel | string | yes
AiService | decideRecommendations | request | cartId | string (uuid) |  | (nullable)
AiService | decideRecommendations | request | productId | string (uuid) |  | The product in view, for a product-page placement. (nullable)
AiService | decideRecommendations | request | subjectId | string (uuid) |  | Known customer, where signed in. (nullable)
AiService | decideRecommendations | request | sessionRef | string |  | (nullable)
AiService | decideRecommendations | request | previewOnly | boolean |  | A staff preview that records nothing (contract gap CHG-WIR-014, BO-102; CHG-CSA-045): the slot is filled as a guest would see it, but no impression, tracking id or decision record is written. (default False)
AiService | decideRecommendations | request | maxItems | integer |  | (min 1; max 12; default 4)
AiService | decideRecommendations | request | locale | string |  | (nullable)
AiService | decideRecommendations | request | itemKinds | array of enum (upsell, crossSell, upgrade, bundle, addOn, membership, nextBestOffer, offer, …) |  | Only these kinds may fill the slot (29 September, build).
AiService | decideRecommendations | request | portfolioScope | boolean |  | Also consider the entitlements of the people the guest may act for under a delegated access (CF-132 household), not only their own (5.5.30). (default False)
AiService | decideRecommendations | response | decisionId | string (uuid) | yes
AiService | decideRecommendations | response | placement | enum (productPage, cart, checkout, postPurchase, preVisit, inVenue, posBasket, kioskBasket, …)
AiService | decideRecommendations | response | mode | enum (personalised, contextual, rulesOnly, fallback) | yes
AiService | decideRecommendations | response | items | array of AiRecommendationItem | yes
AiService | decideRecommendations | response | items[].trackingId | string (uuid) | yes | Echoed on every recordRecommendationEvents event and as orders.addCartLine.recommendationId, so attribution never guesses.
AiService | decideRecommendations | response | items[].productId | string (uuid) |  | The product recommended. (nullable)
AiService | decideRecommendations | response | items[].promotionId | string (uuid) |  | For offer, a published promotion the guest is eligible for. (nullable)
AiService | decideRecommendations | response | items[].couponRef | string |  | For offer, a coupon campaign; a code is assigned only when the guest takes it (promotions.assignCoupon). (nullable)
AiService | decideRecommendations | response | items[].rewardId | string (uuid) |  | For reward, a marketing-crm loyalty reward the guest can redeem. (nullable)
AiService | decideRecommendations | response | items[].challengeId | string (uuid) |  | For challenge, a marketing-crm challenge the guest can join. (nullable)
AiService | decideRecommendations | response | items[].kind | enum (upsell, crossSell, upgrade, bundle, addOn, membership, nextBestOffer, offer, …)
AiService | decideRecommendations | response | items[].rank | integer | yes | (min 1)
AiService | decideRecommendations | response | items[].priceRef | string |  | The Pricing reference the channel resolves to a price. (nullable)
AiService | decideRecommendations | response | items[].reasonTemplateKey | string |  | The template reason (decided 29 September, decision 9): no model writes guest-visible reasons. (nullable)
AiService | decideRecommendations | response | items[].reasonText | string |  | The rendered template in the session locale, where the channel shows reasons. (nullable)
AiService | decideRecommendations | response | items[].confidenceBand | enum (high, medium, low) |  | Design 5.6: a band, never a bare percentage.
AiService | decideRecommendations | response | items[].score | number |  | Normalised score. (nullable)
AiService | decideRecommendations | response | expiresAt | string (date-time) | yes
AiService | decideRecommendations | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | deleteAccessPointGroup | param (path) | groupId | string (uuid) | yes
AccessService | deleteAccessPointGroup | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | deleteBanner | param (path) | bannerId | string (uuid) | yes
WhiteLabelService | deleteBanner | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | deleteBookingFlow | param (path) | bookingFlowId | string (uuid) | yes
WhiteLabelService | deleteBookingFlow | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | deleteContentPage | param (path) | pageId | string (uuid) | yes
WhiteLabelService | deleteContentPage | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
ReportingService | deleteDashboard | param (path) | dashboardId | string (uuid) | yes
ReportingService | deleteDashboard | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | deleteFavouriteRoute | param (path) | favouriteId | string (uuid) | yes
VenueOpsService | deleteFavouriteRoute | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | deleteGuestAccount | response | requestId | string
IdentityService | deleteGuestAccount | response | estimatedCompletionAt | string (date-time)
IdentityService | deleteGuestAccount | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | deleteGuidedChoice | param (path) | guidedChoiceId | string (uuid) | yes
WhiteLabelService | deleteGuidedChoice | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | deleteMediaAsset | param (path) | mediaId | string (uuid) | yes
VenueOpsService | deleteMediaAsset | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | deletePromoBlock | param (path) | promoBlockId | string (uuid) | yes
WhiteLabelService | deletePromoBlock | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
ReportingService | deleteReport | param (path) | reportId | string (uuid) | yes
ReportingService | deleteReport | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
PlatformService | deprecateApiVersion | request | sunsetAt | string (date-time) | yes
PlatformService | deprecateApiVersion | request | reason | string | yes
PlatformService | deprecateApiVersion | request | migrationGuideUrl | string |  | (nullable)
PlatformService | deprecateApiVersion | response | version | string | yes
PlatformService | deprecateApiVersion | response | status | enum (preview, current, deprecated, sunset) | yes
PlatformService | deprecateApiVersion | response | releasedAt | string (date-time)
PlatformService | deprecateApiVersion | response | deprecatedAt | string (date-time) |  | (nullable)
PlatformService | deprecateApiVersion | response | sunsetAt | string (date-time) |  | (nullable)
PlatformService | deprecateApiVersion | response | minimumNoticeMonths | integer |  | The commitment, not the intention. (default 12)
PlatformService | deprecateApiVersion | response | migrationGuideUrl | string |  | (nullable)
PlatformService | deprecateApiVersion | response | activeClientCount | integer |  | (read-only)
PlatformService | deprecateApiVersion | response | changes | array of object |  | The developer changelog for this version (17 September minutes, M17-14): every operation added, changed, deprecated or removed, and whether the change is breaking under ADR-0026.
PlatformService | deprecateApiVersion | response | changes[].operationId | string | yes
PlatformService | deprecateApiVersion | response | changes[].contract | string
PlatformService | deprecateApiVersion | response | changes[].kind | enum (added, changed, deprecated, removed) | yes
PlatformService | deprecateApiVersion | response | changes[].breaking | boolean |  | (default False)
PlatformService | deprecateApiVersion | response | changes[].summary | string
PlatformService | deprecateApiVersion | param (path) | version | string | yes
PlatformService | deprecateApiVersion | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | diffConfigVersion | response | fromVersion | string | yes
WhiteLabelService | diffConfigVersion | response | toVersion | string | yes
WhiteLabelService | diffConfigVersion | response | changes | array of object | yes
WhiteLabelService | diffConfigVersion | response | changes[].area | string | yes
WhiteLabelService | diffConfigVersion | response | changes[].path | string | yes
WhiteLabelService | diffConfigVersion | response | changes[].changeKind | enum (added, removed, modified) | yes
WhiteLabelService | diffConfigVersion | response | changes[].before | string |  | (nullable)
WhiteLabelService | diffConfigVersion | response | changes[].after | string |  | (nullable)
WhiteLabelService | diffConfigVersion | response | changes[].changeScope | ChangeScope: enum (runtime, buildTime) |  | Whether a change reaches guests on publish or needs a store release.
WhiteLabelService | diffConfigVersion | param (path) | version | string | yes
WhiteLabelService | diffConfigVersion | param (query) | against | string |  | Another version.
CatalogueService | editSeatMapStructure | request | addSections | array of object
CatalogueService | editSeatMapStructure | request | addSections[].code | string | yes | (max length 20)
CatalogueService | editSeatMapStructure | request | addSections[].name | string | yes | (max length 100)
CatalogueService | editSeatMapStructure | request | addSections[].boundary | array of Point
CatalogueService | editSeatMapStructure | request | addSections[].boundary[].x | number | yes
CatalogueService | editSeatMapStructure | request | addSections[].boundary[].y | number | yes
CatalogueService | editSeatMapStructure | request | addRows | array of object
CatalogueService | editSeatMapStructure | request | addRows[].sectionCode | string | yes
CatalogueService | editSeatMapStructure | request | addRows[].label | string | yes | (max length 10)
CatalogueService | editSeatMapStructure | request | addRows[].seatCount | integer | yes | (min 1; max 500)
CatalogueService | editSeatMapStructure | request | addRows[].firstSeatNumber | integer |  | (min 0; default 1)
CatalogueService | editSeatMapStructure | request | addRows[].numberingDirection | enum (leftToRight, rightToLeft) |  | (default leftToRight)
CatalogueService | editSeatMapStructure | request | addRows[].start | Point
CatalogueService | editSeatMapStructure | request | addRows[].start.x | number | yes
CatalogueService | editSeatMapStructure | request | addRows[].start.y | number | yes
CatalogueService | editSeatMapStructure | request | addRows[].end | Point
CatalogueService | editSeatMapStructure | request | addRows[].end.x | number | yes
CatalogueService | editSeatMapStructure | request | addRows[].end.y | number | yes
CatalogueService | editSeatMapStructure | request | addRows[].curveRadius | number |  | Null or absent for a straight row. (nullable)
CatalogueService | editSeatMapStructure | request | addRows[].categoryId | string (uuid) |  | (nullable)
CatalogueService | editSeatMapStructure | request | addSeats | array of object
CatalogueService | editSeatMapStructure | request | addSeats[].sectionCode | string | yes
CatalogueService | editSeatMapStructure | request | addSeats[].rowLabel | string | yes
CatalogueService | editSeatMapStructure | request | addSeats[].seatNumber | string | yes
CatalogueService | editSeatMapStructure | request | addSeats[].position | Point
CatalogueService | editSeatMapStructure | request | addSeats[].position.x | number | yes
CatalogueService | editSeatMapStructure | request | addSeats[].position.y | number | yes
CatalogueService | editSeatMapStructure | request | addSeats[].categoryId | string (uuid) |  | (nullable)
CatalogueService | editSeatMapStructure | request | addSeats[].attribute | SeatAttribute: enum (standard, accessible, companion, obstructedView, restrictedLegroom, premium, houseSeat, buffer, …) |  | BL-168.
CatalogueService | editSeatMapStructure | request | removeSeatIds | array of string (uuid)
CatalogueService | editSeatMapStructure | request | relabel | array of object
CatalogueService | editSeatMapStructure | request | relabel[].seatId | string (uuid) | yes
CatalogueService | editSeatMapStructure | request | relabel[].sectionCode | string
CatalogueService | editSeatMapStructure | request | relabel[].rowLabel | string
CatalogueService | editSeatMapStructure | request | relabel[].seatNumber | string
CatalogueService | editSeatMapStructure | response | sectionsAdded | integer
CatalogueService | editSeatMapStructure | response | seatsAdded | integer
CatalogueService | editSeatMapStructure | response | seatsRemoved | integer
CatalogueService | editSeatMapStructure | response | seatsRelabelled | integer
CatalogueService | editSeatMapStructure | param (path) | seatMapId | string (uuid) | yes
CatalogueService | editSeatMapStructure | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | editSeatMapStructure | param (header) | Prefer | enum (validate-only) |  | Validate, do not write (29 September, AI system design 2.3 and 2.2 D step 4).
AccessService | enrolFacePass | request | subjectId | string (uuid) | yes
AccessService | enrolFacePass | request | entitlementId | string (uuid) | yes | An Entitlement.id, which is a UUIDv7.
AccessService | enrolFacePass | request | template | string (password) | yes | Write-only, never returned.
AccessService | enrolFacePass | request | capturedAt | string (date-time) | yes
AccessService | enrolFacePass | request | source | enum (guestApp, ticketCounter, annualPassCounter, selfServiceKiosk) | yes | The three surfaces 3.2.43 allows, and the self-service kiosk since 2 October 2026 (Chinmay, BO-186; DEC-236; CHG-CSP-021): a kiosk shows the venue's consent form on its screen and enrols only where t…
AccessService | enrolFacePass | request | consent | object | yes
AccessService | enrolFacePass | request | consent.purposeId | string (uuid) | yes
AccessService | enrolFacePass | request | consent.givenAt | string (date-time) | yes
AccessService | enrolFacePass | request | consent.consentFormId | string (uuid) |  | The venue's consent form accepted (DEC-128; CHG-CSP-018). (nullable)
AccessService | enrolFacePass | request | consent.consentFormVersion | integer |  | The version of that form shown (CHG-CSP-018). (min 1; nullable)
AccessService | enrolFacePass | request | consent.guardianSubjectId | string (uuid) |  | Required where the subject is a minor. (nullable)
AccessService | enrolFacePass | request | consent.guardianRelationship | string |  | (nullable)
AccessService | enrolFacePass | request | reasonForReEnrollment | enum (appearanceChange, poorOriginalCapture, technicalIssue, guestRequest, recovery, other) |  | Required when the subject already has a Face Pass: why the face is being enrolled again (decided 29 September, writers pass) (nullable)
AccessService | enrolFacePass | response | id | string (uuid) | yes | (read-only)
AccessService | enrolFacePass | response | subjectId | string (uuid) | yes
AccessService | enrolFacePass | response | entitlementId | string (uuid) | yes | The Entitlement.id, a UUIDv7 (pii.subject_biometric.entitlement_id).
AccessService | enrolFacePass | response | kind | BiometricKind: enum (facePass, faceTag) | yes | BL-106, CF-35.
AccessService | enrolFacePass | response | retentionAnchor | object |  | BL-106.
AccessService | enrolFacePass | response | source | enum (guestApp, ticketCounter, annualPassCounter, entryGate) | yes | entryGate is valid for faceTag only, and 3.2.43's omission of it from Face Pass is deliberate: an enduring enrolment is a considered act with consent attached, not something done in a queue.
AccessService | enrolFacePass | response | enrolmentChannel | enum (guestApp, ticketCounter, annualPassCounter, selfServiceKiosk, entryGate) |  | Where the face was actually captured (decided 2 October 2026, Chinmay, BO-186; DEC-236; CHG-CSP-021): source with selfServiceKiosk told apart. (read-only)
AccessService | enrolFacePass | response | consentFormId | string (uuid) |  | The venue's consent form the capture was consented on, and its version below (DEC-128; CHG-CSP-018). (read-only; nullable)
AccessService | enrolFacePass | response | consentFormVersion | integer |  | (read-only; nullable)
AccessService | enrolFacePass | response | capturedAt | string (date-time) | yes
AccessService | enrolFacePass | response | consentPurposeId | string (uuid)
AccessService | enrolFacePass | response | consentGivenAt | string (date-time)
AccessService | enrolFacePass | response | guardianSubjectId | string (uuid) |  | Where the subject is a minor (3.2.12). (nullable)
AccessService | enrolFacePass | response | isActive | boolean |  | (read-only)
AccessService | enrolFacePass | response | expiresAt | string (date-time) |  | Bounded by whatever retentionAnchor names, and a face outliving it is a biometric held for no stated purpose. (nullable)
AccessService | enrolFacePass | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AccessService | enrolFaceTag | request | subjectId | string (uuid) | yes
AccessService | enrolFaceTag | request | entitlementId | string (uuid) | yes | An Entitlement.id, which is a UUIDv7.
AccessService | enrolFaceTag | request | template | string (password) | yes | Write-only, never returned.
AccessService | enrolFaceTag | request | capturedAt | string (date-time) | yes
AccessService | enrolFaceTag | request | source | enum (ticketCounter, entryGate) | yes | The two surfaces 3.2.44 allows, and a gate is present here exactly where it is absent from Face Pass: this one does not outlive the visit.
AccessService | enrolFaceTag | request | consent | object | yes | Per-visit rather than enduring, and still explicit.
AccessService | enrolFaceTag | request | consent.purposeId | string (uuid) | yes
AccessService | enrolFaceTag | request | consent.method | enum (onScreenAcknowledgement, signedForm) |  | How the guest consented (added 29 September, build pass, 3.2.44). (default onScreenAcknowledgement)
AccessService | enrolFaceTag | request | consent.givenAt | string (date-time) | yes
AccessService | enrolFaceTag | request | consent.consentFormId | string (uuid) |  | The venue's consent form the guest accepted (VenueSettings.biometrics.consentFormId; DEC-128; CHG-CSP-018). (nullable)
AccessService | enrolFaceTag | request | consent.consentFormVersion | integer |  | The version of that form shown (CHG-CSP-018). (min 1; nullable)
AccessService | enrolFaceTag | request | consent.guardianSubjectId | string (uuid) |  | Required where the subject is a minor (3.2.12). (nullable)
AccessService | enrolFaceTag | request | consent.guardianRelationship | string |  | (nullable)
AccessService | enrolFaceTag | response | id | string (uuid) | yes | (read-only)
AccessService | enrolFaceTag | response | subjectId | string (uuid) | yes
AccessService | enrolFaceTag | response | entitlementId | string (uuid) | yes | The Entitlement.id, a UUIDv7 (pii.subject_biometric.entitlement_id).
AccessService | enrolFaceTag | response | kind | BiometricKind: enum (facePass, faceTag) | yes | BL-106, CF-35.
AccessService | enrolFaceTag | response | retentionAnchor | object |  | BL-106.
AccessService | enrolFaceTag | response | source | enum (guestApp, ticketCounter, annualPassCounter, entryGate) | yes | entryGate is valid for faceTag only, and 3.2.43's omission of it from Face Pass is deliberate: an enduring enrolment is a considered act with consent attached, not something done in a queue.
AccessService | enrolFaceTag | response | enrolmentChannel | enum (guestApp, ticketCounter, annualPassCounter, selfServiceKiosk, entryGate) |  | Where the face was actually captured (decided 2 October 2026, Chinmay, BO-186; DEC-236; CHG-CSP-021): source with selfServiceKiosk told apart. (read-only)
AccessService | enrolFaceTag | response | consentFormId | string (uuid) |  | The venue's consent form the capture was consented on, and its version below (DEC-128; CHG-CSP-018). (read-only; nullable)
AccessService | enrolFaceTag | response | consentFormVersion | integer |  | (read-only; nullable)
AccessService | enrolFaceTag | response | capturedAt | string (date-time) | yes
AccessService | enrolFaceTag | response | consentPurposeId | string (uuid)
AccessService | enrolFaceTag | response | consentGivenAt | string (date-time)
AccessService | enrolFaceTag | response | guardianSubjectId | string (uuid) |  | Where the subject is a minor (3.2.12). (nullable)
AccessService | enrolFaceTag | response | isActive | boolean |  | (read-only)
AccessService | enrolFaceTag | response | expiresAt | string (date-time) |  | Bounded by whatever retentionAnchor names, and a face outliving it is a biometric held for no stated purpose. (nullable)
AccessService | enrolFaceTag | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | enrolMfaMethod | request | kind | MfaKind: enum (totp, smsOtp, emailOtp, biometric, hardwareToken) | yes
IdentityService | enrolMfaMethod | request | target | string |  | Phone or email for OTP methods.
IdentityService | enrolMfaMethod | response | id | string (uuid) |  | Added 20 August. (read-only)
IdentityService | enrolMfaMethod | response | methodId | string (uuid) | yes
IdentityService | enrolMfaMethod | response | kind | MfaKind: enum (totp, smsOtp, emailOtp, biometric, hardwareToken) | yes
IdentityService | enrolMfaMethod | response | secret | string |  | TOTP shared secret. (nullable)
IdentityService | enrolMfaMethod | response | qrCodeUri | string |  | (nullable)
IdentityService | enrolMfaMethod | response | recoveryCodes | array of string |  | Returned once, in this enrolment response (enrolMfaMethod writes them, hashed, to identity.mfa_recovery_code).
IdentityService | enrolMfaMethod | response | expiresAt | string (date-time)
IdentityService | enrolMfaMethod | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | enterWaitingRoom | response | waitingEntryId | string (uuid) | yes | A UUIDv7 minted on arrival; what the waiting page polls with.
CatalogueService | enterWaitingRoom | response | performanceId | string (uuid) | yes
CatalogueService | enterWaitingRoom | response | state | enum (notRequired, waiting, admitted, expired, closed) | yes | notRequired: the room is off, go to the sale.
CatalogueService | enterWaitingRoom | response | position | integer |  | Place in the room; null unless waiting. (min 1; nullable)
CatalogueService | enterWaitingRoom | response | aheadOfYou | integer |  | (min 0; nullable)
CatalogueService | enterWaitingRoom | response | estimatedWaitSeconds | integer |  | At the current release rate. (min 0; nullable)
CatalogueService | enterWaitingRoom | response | pollAfterSeconds | integer |  | (min 1; default 5)
CatalogueService | enterWaitingRoom | response | admission | object |  | Set when state is admitted. (nullable)
CatalogueService | enterWaitingRoom | response | admission.token | string | yes | The signed token, opaque to the client.
CatalogueService | enterWaitingRoom | response | admission.tokenId | string (uuid) |  | The token's unique id.
CatalogueService | enterWaitingRoom | response | admission.performanceId | string (uuid) | yes
CatalogueService | enterWaitingRoom | response | admission.expiresAt | string (date-time) | yes
CatalogueService | enterWaitingRoom | param (path) | performanceId | string (uuid) | yes
CatalogueService | enterWaitingRoom | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | escalateCorrectiveAction | response | id | string (uuid) | yes
FnbService | escalateCorrectiveAction | response | raisedAt | string (date-time) | yes
FnbService | escalateCorrectiveAction | response | raisedByPrincipalId | string (uuid) |  | Who raised it, which is who may not sign it when it is critical (signCorrectiveAction). (read-only; nullable)
FnbService | escalateCorrectiveAction | response | source | enum (temperatureExcursion, coldChainBreach, expiredStock, contamination, pestSighting, equipmentFailure, missedCheck, manual) | yes | missedCheck is raised by the server when a checkpoint goes past its checkFrequencyMinutes with no reading (audit R125 (5)).
FnbService | escalateCorrectiveAction | response | sourceRef | string (uuid) |  | (nullable)
FnbService | escalateCorrectiveAction | response | severity | enum (observation, minor, major, critical) |  | Set by the source when the platform opens it (decided 28 September, audit R125 (5)): an out-of-range reading or a cold-chain breach opens at major, a missed check at minor.
FnbService | escalateCorrectiveAction | response | actionTaken | string |  | (nullable)
FnbService | escalateCorrectiveAction | response | disposal | enum (none, discarded, reworked, quarantined, returned) |  | (nullable)
FnbService | escalateCorrectiveAction | response | status | enum (open, actioned, signed, escalated, closed) | yes
FnbService | escalateCorrectiveAction | response | signedByPrincipalId | string (uuid) |  | (nullable)
FnbService | escalateCorrectiveAction | response | signedAt | string (date-time) |  | (nullable)
FnbService | escalateCorrectiveAction | response | escalatedToPrincipalId | string (uuid) |  | A critical finding a shift cannot close. (nullable)
FnbService | escalateCorrectiveAction | response | scopePath | string |  | The partition key (ADR-0005).
FnbService | escalateCorrectiveAction | param (path) | actionId | string (uuid) | yes
FnbService | escalateCorrectiveAction | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | evaluateAiGovernance | request | capabilityKey | string | yes
AiService | evaluateAiGovernance | request | action | enum (read, analyze, recommend, generate, prepare, create, modify, publish, …) | yes
AiService | evaluateAiGovernance | request | scopePath | string |  | (nullable)
AiService | evaluateAiGovernance | request | principalId | string (uuid) |  | (nullable)
AiService | evaluateAiGovernance | request | dataCategories | array of string
AiService | evaluateAiGovernance | request | amount | object |  | (nullable)
AiService | evaluateAiGovernance | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
AiService | evaluateAiGovernance | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
AiService | evaluateAiGovernance | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
AiService | evaluateAiGovernance | request | toolKey | string |  | (nullable)
AiService | evaluateAiGovernance | response | outcome | AiGovernanceOutcome: enum (allow, allowWithConditions, prepareOnly, approvalRequired, escalate, block) | yes | What the governance decision point returns (design 3.8, AIC-166).
AiService | evaluateAiGovernance | response | policyVersion | string | yes
AiService | evaluateAiGovernance | response | autonomyLevel | integer |  | One autonomy scale for every capability (design 3.8 and 5.5, GOV 0 to 4; ADR-0050). (min 0; max 4)
AiService | evaluateAiGovernance | response | conditions | object |  | (nullable)
AiService | evaluateAiGovernance | response | requiredApprovalTier | integer |  | (min 1; max 2; nullable)
AiService | evaluateAiGovernance | response | explanation | string
AiService | evaluateAiGovernance | response | decisionRecordId | string (uuid) |  | (nullable)
AiService | evaluateAiGovernance | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
TenancyService | evaluateApprovalRequirement | request | kind | ApprovalKind: enum (refund, priceOverride, discountOverride, complimentaryTicket, membershipCancellation, accessPermissionChange, configurationChange, aiRecommendation, …) | yes | 11.1.7 and 11.1.30–11.1.37.
TenancyService | evaluateApprovalRequirement | request | scopePath | string | yes
TenancyService | evaluateApprovalRequirement | request | amount | Money |  | On the wire this is three fields; in the database it is one column.
TenancyService | evaluateApprovalRequirement | request | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | evaluateApprovalRequirement | request | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | evaluateApprovalRequirement | request | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | evaluateApprovalRequirement | request | attributes | object |  | Whatever the conditional rules match on (11.1.13).
TenancyService | evaluateApprovalRequirement | response | isRequired | boolean | yes
TenancyService | evaluateApprovalRequirement | response | matchedRule | object |  | (nullable)
TenancyService | evaluateApprovalRequirement | response | matchedRule.id | string (uuid) |  | Added 20 August. (read-only)
TenancyService | evaluateApprovalRequirement | response | matchedRule.order | integer | yes | First match wins.
TenancyService | evaluateApprovalRequirement | response | matchedRule.minAmount | Money |  | On the wire this is three fields; in the database it is one column.
TenancyService | evaluateApprovalRequirement | response | matchedRule.minAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | evaluateApprovalRequirement | response | matchedRule.minAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | evaluateApprovalRequirement | response | matchedRule.minAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | evaluateApprovalRequirement | response | matchedRule.maxAmount | Money |  | On the wire this is three fields; in the database it is one column.
TenancyService | evaluateApprovalRequirement | response | matchedRule.maxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | evaluateApprovalRequirement | response | matchedRule.maxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | evaluateApprovalRequirement | response | matchedRule.maxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | evaluateApprovalRequirement | response | matchedRule.riskScoreAbove | number |  | 11.1.12. (nullable)
TenancyService | evaluateApprovalRequirement | response | matchedRule.condition | string |  | 11.1.13. (nullable)
TenancyService | evaluateApprovalRequirement | response | matchedRule.approverRoleIds | array of string (uuid) | yes | Role ids from identity.listRoles (Role.id), which is where an editor gets the names to show and pick from. (min items 1)
TenancyService | evaluateApprovalRequirement | response | matchedRule.approverScopeLevel | enum (venue, department, region, tenant) |  | 11.1.39.
TenancyService | evaluateApprovalRequirement | response | matchedRule.mode | ApprovalMode: enum (sequential, parallel, consensus, majority) | yes | 11.1.43–11.1.46.
TenancyService | evaluateApprovalRequirement | response | matchedRule.levels | integer |  | 11.1.3. (default 1)
TenancyService | evaluateApprovalRequirement | response | matchedRule.requiresMfa | boolean |  | (default False)
TenancyService | evaluateApprovalRequirement | response | matchedRule.requiresSignature | boolean |  | (default False)
TenancyService | evaluateApprovalRequirement | response | matchedRule.slaMinutes | integer |  | 11.1.14. (nullable)
TenancyService | evaluateApprovalRequirement | response | matchedRule.escalateAfterMinutes | integer |  | (nullable)
TenancyService | evaluateApprovalRequirement | response | matchedRule.escalateToRoleIds | array of string (uuid) |  | Role ids from identity.listRoles, as approverRoleIds.
TenancyService | evaluateApprovalRequirement | response | matchedRule.expiresAfterMinutes | integer |  | 11.1.53. (nullable)
TenancyService | evaluateApprovalRequirement | response | matchedRule.subjectTypes | array of string |  | Which subjects of the kind this rule matches (decided 2 October 2026, Chinmay; CHG-CSP-028, CHG-CSP-036, CHG-CSP-031): the CreateApprovalRequest.subjectType values, for example topologyPublication or…
TenancyService | evaluateApprovalRequirement | response | matchedRule.signatureMethods | array of enum (platformKey, uaePass, externalCertificate, drawnSignature) |  | The signature methods this level accepts, where requiresSignature is true (design-notes correction on ADM-344, Block B: "Configuring which stages need a signature is a policy write"; CHG-CSP-045).
TenancyService | evaluateApprovalRequirement | response | matchedRule.externalProviderId | string (uuid) |  | 11.1.65 (29 September). (nullable)
TenancyService | evaluateApprovalRequirement | response | matchedRule.code | string |  | A stable code for the rule, unique within its matrix (4 October 2026, CHG-FXC-005). (max length 64; nullable)
TenancyService | evaluateApprovalRequirement | response | matchedRule.minimumApprovals | integer |  | N in N-of-M (CHG-FXC-005). (min 1; nullable)
TenancyService | evaluateApprovalRequirement | response | matchedRule.requiredApproverRoleId | string (uuid) |  | A role that must be among the approvals whatever N is (the CFO in an N-of-M group); it is also one of approverRoleIds (CHG-FXC-005). (nullable)
TenancyService | evaluateApprovalRequirement | response | matchedRule.rejectionBehavior | enum (rejectRequest, returnToPreviousLevel, returnToRequester) |  | What a rejection at this rule does; null is rejectRequest (CHG-FXC-005). (nullable)
TenancyService | evaluateApprovalRequirement | response | matchedRule.allowRequestChanges | boolean |  | (default False)
TenancyService | evaluateApprovalRequirement | response | matchedRule.allowDelegate | boolean |  | (default True)
TenancyService | evaluateApprovalRequirement | response | matchedRule.allowReassign | boolean |  | (default False)
TenancyService | evaluateApprovalRequirement | response | matchedRule.minPercentage | number |  | A percentage threshold (a discount or a margin impact) at or above which the rule applies, beside minAmount (CHG-FXC-005). (nullable)
TenancyService | evaluateApprovalRequirement | response | matchedRule.matchAttributes | object |  | The request attributes a rule matches on (CHG-FXC-005): keys module, product, department, customerType, risk, exceptionType, legalEntity, each an exact value the request's attributes must carry. (nullable)
TenancyService | evaluateApprovalRequirement | response | matchedRule.compositeMode | enum (single, sequential, parallel, anyOne, allMustApprove, conditional, multiLevel) |  | The approvalMode the composite screen sent, kept so it reads back what it saved; mode, levels and minimumApprovals are what the engine runs (CHG-FXC-005). (nullable)
TenancyService | evaluateApprovalRequirement | response | matrixVersion | integer |  | (nullable)
TenancyService | evaluateApprovalRequirement | response | approvers | array of object |  | Resolved, with delegations applied.
TenancyService | evaluateApprovalRequirement | response | approvers[].principalId | string (uuid)
TenancyService | evaluateApprovalRequirement | response | approvers[].displayName | string
TenancyService | evaluateApprovalRequirement | response | approvers[].level | integer
TenancyService | evaluateApprovalRequirement | response | approvers[].isDelegate | boolean
TenancyService | evaluateApprovalRequirement | response | approvers[].delegatedFrom | string (uuid) |  | (nullable)
TenancyService | evaluateApprovalRequirement | response | slaMinutes | integer |  | (nullable)
TenancyService | evaluateApprovalRequirement | response | noApproverAvailable | boolean |  | The case that must not fail silently.
TenancyService | evaluateApprovalRequirement | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | evaluatePromotions | request | venueId | string (uuid) | yes
CatalogueService | evaluatePromotions | request | channel | object | yes | Where the sale is being made.
CatalogueService | evaluatePromotions | request | subjectId | string (uuid)
CatalogueService | evaluatePromotions | request | membershipTierId | string (uuid)
CatalogueService | evaluatePromotions | request | couponCodes | array of string
CatalogueService | evaluatePromotions | request | evaluateAt | string (date-time) |  | For back-office testing of a rule before publishing.
CatalogueService | evaluatePromotions | request | orderId | string (uuid) |  | The order (orders.sales_order) being priced for payment. (nullable)
CatalogueService | evaluatePromotions | request | lines | array of object | yes | (min items 1)
CatalogueService | evaluatePromotions | request | lines[].lineId | string | yes
CatalogueService | evaluatePromotions | request | lines[].variantId | string (uuid) | yes
CatalogueService | evaluatePromotions | request | lines[].performanceId | string (uuid)
CatalogueService | evaluatePromotions | request | lines[].quantity | integer | yes | (min 1)
CatalogueService | evaluatePromotions | request | lines[].unitPrice | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | evaluatePromotions | request | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | evaluatePromotions | request | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | evaluatePromotions | request | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | evaluatePromotions | response | totalDiscount | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | evaluatePromotions | response | totalDiscount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | evaluatePromotions | response | totalDiscount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | evaluatePromotions | response | totalDiscount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | evaluatePromotions | response | lines | array of object | yes
CatalogueService | evaluatePromotions | response | lines[].lineId | string | yes
CatalogueService | evaluatePromotions | response | lines[].originalPrice | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | evaluatePromotions | response | lines[].originalPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | evaluatePromotions | response | lines[].originalPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | evaluatePromotions | response | lines[].originalPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | evaluatePromotions | response | lines[].discountedPrice | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | evaluatePromotions | response | lines[].discountedPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | evaluatePromotions | response | lines[].discountedPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | evaluatePromotions | response | lines[].discountedPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | evaluatePromotions | response | lines[].discount | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | evaluatePromotions | response | lines[].discount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | evaluatePromotions | response | lines[].discount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | evaluatePromotions | response | lines[].discount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | evaluatePromotions | response | lines[].appliedPromotionIds | array of string (uuid)
CatalogueService | evaluatePromotions | response | applied | array of object | yes
CatalogueService | evaluatePromotions | response | applied[].promotionId | string (uuid) | yes
CatalogueService | evaluatePromotions | response | applied[].promotionCode | string | yes
CatalogueService | evaluatePromotions | response | applied[].promotionName | string
CatalogueService | evaluatePromotions | response | applied[].discount | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | evaluatePromotions | response | applied[].discount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | evaluatePromotions | response | applied[].discount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | evaluatePromotions | response | applied[].discount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | evaluatePromotions | response | applied[].couponCode | string |  | (nullable)
CatalogueService | evaluatePromotions | response | rejected | array of object | yes | Promotions that matched the products but did not apply, with the reason.
CatalogueService | evaluatePromotions | response | rejected[].promotionCode | string | yes
CatalogueService | evaluatePromotions | response | rejected[].promotionName | string
CatalogueService | evaluatePromotions | response | rejected[].reason | enum (conditionsNotMet, supersededByBetterOffer, exclusivePromotionApplied, redemptionLimitReached, budgetExhausted, outsideValidPeriod, wrongChannel, membershipRequired, …) | yes
CatalogueService | evaluatePromotions | response | rejected[].detail | string
CatalogueService | evaluatePromotions | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | exchangeOrderLines | request | id | string (uuid) | yes | Client-generated UUIDv7 of this exchange, and its idempotency key — it must equal the Idempotency-Key header.
OrderService | exchangeOrderLines | request | outgoingLineIds | array of string (uuid) | yes | (min items 1)
OrderService | exchangeOrderLines | request | incomingLines | array of CreateOrderLine | yes | (min items 1)
OrderService | exchangeOrderLines | request | incomingLines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | exchangeOrderLines | request | incomingLines[].variantId | string (uuid) | yes
OrderService | exchangeOrderLines | request | incomingLines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | exchangeOrderLines | request | incomingLines[].performanceId | string (uuid)
OrderService | exchangeOrderLines | request | incomingLines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | exchangeOrderLines | request | incomingLines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | exchangeOrderLines | request | incomingLines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | exchangeOrderLines | request | incomingLines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | exchangeOrderLines | request | incomingLines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | exchangeOrderLines | request | incomingLines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | exchangeOrderLines | request | incomingLines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | exchangeOrderLines | request | incomingLines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | exchangeOrderLines | request | incomingLines[].quantity | integer | yes | (min 1)
OrderService | exchangeOrderLines | request | incomingLines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | exchangeOrderLines | request | incomingLines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | exchangeOrderLines | request | incomingLines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | exchangeOrderLines | request | incomingLines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | exchangeOrderLines | request | incomingLines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | exchangeOrderLines | request | incomingLines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | exchangeOrderLines | request | incomingLines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | exchangeOrderLines | request | incomingLines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | exchangeOrderLines | request | incomingLines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | exchangeOrderLines | request | incomingLines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | exchangeOrderLines | request | incomingLines[].holderName | string |  | (nullable)
OrderService | exchangeOrderLines | request | incomingLines[].dataMaskValues | object |  | Deliberately open.
OrderService | exchangeOrderLines | request | waiveFee | boolean |  | (default False)
OrderService | exchangeOrderLines | request | reason | string |  | (max length 500)
OrderService | exchangeOrderLines | request | recordedAt | string (date-time) | yes
OrderService | exchangeOrderLines | response | orderId | string (uuid) | yes
OrderService | exchangeOrderLines | response | outgoingValue | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | exchangeOrderLines | response | outgoingValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | exchangeOrderLines | response | outgoingValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | exchangeOrderLines | response | outgoingValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | exchangeOrderLines | response | incomingValue | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | exchangeOrderLines | response | incomingValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | exchangeOrderLines | response | incomingValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | exchangeOrderLines | response | incomingValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | exchangeOrderLines | response | exchangeFee | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | exchangeOrderLines | response | exchangeFee.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | exchangeOrderLines | response | exchangeFee.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | exchangeOrderLines | response | exchangeFee.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | exchangeOrderLines | response | difference | object | yes | Only the difference settles.
OrderService | exchangeOrderLines | response | difference.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | exchangeOrderLines | response | difference.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | exchangeOrderLines | response | difference.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | exchangeOrderLines | response | newLineIds | array of string (uuid)
OrderService | exchangeOrderLines | response | revokedEntitlementIds | array of string (uuid)
OrderService | exchangeOrderLines | response | issuedEntitlementIds | array of string (uuid)
OrderService | exchangeOrderLines | param (path) | orderId | string (uuid) | yes
OrderService | exchangeOrderLines | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | explainMetricChange | request | metricKey | string | yes
AiService | explainMetricChange | request | period | string | yes | ISO period, e.g.
AiService | explainMetricChange | request | comparison | enum (previousPeriod, samePeriodLastYear, forecast) |  | (default previousPeriod)
AiService | explainMetricChange | request | dimensions | array of string
AiService | explainMetricChange | request | keep | boolean |  | (default False)
AiService | explainMetricChange | response | metricKey | string | yes
AiService | explainMetricChange | response | period | string
AiService | explainMetricChange | response | comparison | string
AiService | explainMetricChange | response | change | number | yes
AiService | explainMetricChange | response | changePercent | number |  | (nullable)
AiService | explainMetricChange | response | drivers | array of object | yes
AiService | explainMetricChange | response | drivers[].dimension | string
AiService | explainMetricChange | response | drivers[].member | string
AiService | explainMetricChange | response | drivers[].contribution | number
AiService | explainMetricChange | response | drivers[].evidence | AiEvidenceItem |  | One piece of evidence behind a decision, labelled by origin (AIC-197): read from a source system, derived by a rule or feature, or inferred by a model.
AiService | explainMetricChange | response | drivers[].evidence.label | enum (source, derived, modelInferred) | yes
AiService | explainMetricChange | response | drivers[].evidence.kind | string | yes | What it is: feature, rule, document, metric, transaction, candidateSet.
AiService | explainMetricChange | response | drivers[].evidence.ref | string |  | Where it came from: a table and id, a document chunk, a metric key. (nullable)
AiService | explainMetricChange | response | drivers[].evidence.name | string
AiService | explainMetricChange | response | drivers[].evidence.value | object |  | (nullable)
AiService | explainMetricChange | response | drivers[].evidence.observedAt | string (date-time) |  | (nullable)
AiService | explainMetricChange | response | narrative | string |  | (nullable)
AiService | explainMetricChange | response | reliability | enum (grounded, partial, conflictingSources, insufficientEvidence)
AiService | explainMetricChange | response | dataAsOf | string (date-time)
AiService | explainMetricChange | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
WhiteLabelService | exportSitePackage | request | version | string |  | The published version to package; the current one where absent. (nullable)
WhiteLabelService | exportSitePackage | response | id | string (uuid) | yes | (read-only)
WhiteLabelService | exportSitePackage | response | version | string
WhiteLabelService | exportSitePackage | response | status | enum (building, ready, failed) | yes
WhiteLabelService | exportSitePackage | response | downloadUrl | string |  | Short-lived; present when ready. (nullable)
WhiteLabelService | exportSitePackage | response | expiresAt | string (date-time) |  | (nullable)
WhiteLabelService | exportSitePackage | response | requestedByPrincipalId | string (uuid) |  | (read-only)
WhiteLabelService | exportSitePackage | response | platformStaffGrantId | string (uuid) |  | The platform-staff grant it was made under, where platform staff made it (R098). (read-only; nullable)
WhiteLabelService | exportSitePackage | response | createdAt | string (date-time) |  | (read-only)
WhiteLabelService | exportSitePackage | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | exportSitePackage | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | exportSubjectData | request | format | enum (json, csv, pdf) |  | (default json)
IdentityService | exportSubjectData | response | requestId | string | yes | The data-subject request raised for this export.
IdentityService | exportSubjectData | response | format | enum (json, csv, pdf) | yes | The format asked for, or json when the request named none.
IdentityService | exportSubjectData | response | estimatedCompletionAt | string (date-time) |  | (nullable)
IdentityService | exportSubjectData | param (path) | subjectId | string (uuid) | yes
IdentityService | exportSubjectData | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | extendCart | response | id | string (uuid) | yes
OrderService | extendCart | response | token | string |  | How an anonymous guest returns to their cart, including from a recovery email. (read-only)
OrderService | extendCart | response | venueId | string (uuid) | yes
OrderService | extendCart | response | channel | SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) | yes | Where a sale came from.
OrderService | extendCart | response | subjectId | string (uuid) |  | Null while anonymous. (nullable)
OrderService | extendCart | response | status | CartStatus: enum (active, expiring, expired, abandoned, checkedOut) | yes
OrderService | extendCart | response | lines | array of CartLine | yes
OrderService | extendCart | response | lines[].id | string (uuid) | yes
OrderService | extendCart | response | lines[].variantId | string (uuid) | yes
OrderService | extendCart | response | lines[].productName | string |  | (read-only)
OrderService | extendCart | response | lines[].quantity | integer | yes | (min 1)
OrderService | extendCart | response | lines[].performanceId | string (uuid) |  | (nullable)
OrderService | extendCart | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | extendCart | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | extendCart | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | extendCart | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | extendCart | response | lines[].tableReservationId | string (uuid) |  | Set on a table deposit line only (decided 29 September, rev 3 REV3-8b): the fnb.TableReservation this line secures. (nullable)
OrderService | extendCart | response | lines[].seatIds | array of string (uuid) |  | (max items 50)
OrderService | extendCart | response | lines[].resourceHoldId | string (uuid) |  | The resources.ResourceHold this line buys (decided 29 September, rev 3 REV3-15). (nullable)
OrderService | extendCart | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | extendCart | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | extendCart | response | lines[].parentLineId | string (uuid) |  | The line this add-on is attached to, from AddCartLineRequest.parentLineId. (nullable)
OrderService | extendCart | response | lines[].overridePrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | extendCart | response | lines[].overridePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | extendCart | response | lines[].overridePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | extendCart | response | lines[].overridePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | extendCart | response | lines[].overrideReason | enum (priceMatch, serviceRecovery, negotiated, damagedGoods, staffSale, error) |  | BL-085. (nullable)
OrderService | extendCart | response | lines[].feeKind | enum (booking, transaction, service, delivery, convenience, cancellation) |  | A fee is a line, not an adjustment. (nullable)
OrderService | extendCart | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | extendCart | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | extendCart | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | extendCart | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | extendCart | response | lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | extendCart | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | extendCart | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | extendCart | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | extendCart | response | lines[].inventoryHoldId | string |  | The capacity held for this line — a catalogue.InventoryHold.id, typed as that id is. (nullable)
OrderService | extendCart | response | lines[].leaseExpiresAt | string (date-time) |  | Shown to the guest. (nullable)
OrderService | extendCart | response | lines[].isAvailable | boolean |  | Re-checked on every read. (read-only)
OrderService | extendCart | response | conflicts | array of CartConflict
OrderService | extendCart | response | conflicts[].kind | enum (overlappingTime, sameSessionDifferentVenue, exceedsPartySize, requiresPrerequisite, consentBlocksBooking)
OrderService | extendCart | response | conflicts[].lineIds | array of string (uuid)
OrderService | extendCart | response | conflicts[].message | string
OrderService | extendCart | response | conflicts[].isBlocking | boolean |  | Most are not.
OrderService | extendCart | response | consentQuestions | array of object |  | The consent questions this cart's products and flow ask (decided 29 September, rev 3 REV3-26), computed on read at their current version as the union of each line's published booking flow's white-lab… (read-only)
OrderService | extendCart | response | consentQuestions[].id | string (uuid) | yes | (read-only)
OrderService | extendCart | response | consentQuestions[].kind | ConsentQuestionKind: enum (swim, scuba, risk, custom) | yes | What the question is about (decided 29 September, rev 3 REV3-26).
OrderService | extendCart | response | consentQuestions[].text | object | yes | The question as the guest reads it, per locale.
OrderService | extendCart | response | consentQuestions[].helpText | object |  | (nullable)
OrderService | extendCart | response | consentQuestions[].version | integer | yes | Raised by one each time the question changes (updateConsentQuestion). (min 1; read-only)
OrderService | extendCart | response | consentQuestions[].scope | enum (perPerson, perBooking) | yes | Asked for each declared person, or once for the whole booking. (default perPerson)
OrderService | extendCart | response | consentQuestions[].required | boolean | yes | Checkout waits until it is answered (orders.checkoutCart 422 consentRequired). (default True)
OrderService | extendCart | response | consentQuestions[].blockingAnswer | enum (yes, no, none) | yes | The answer that stops the booking, for the person or the booking it covers. (default none)
OrderService | extendCart | response | consentQuestions[].status | enum (active, retired) | yes | (default active)
OrderService | extendCart | response | consentQuestions[].scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | extendCart | response | consentQuestions[].updatedAt | string (date-time) |  | (read-only)
OrderService | extendCart | response | consentQuestions[].lineIds | array of string (uuid) |  | The cart lines that ask it.
OrderService | extendCart | response | consentQuestions[].answered | boolean |  | Every person (for perPerson) or the booking (for perBooking) has an answer.
OrderService | extendCart | response | subtotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | extendCart | response | subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | extendCart | response | subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | extendCart | response | subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | extendCart | response | discountTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | extendCart | response | discountTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | extendCart | response | discountTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | extendCart | response | discountTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | extendCart | response | taxTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | extendCart | response | taxTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | extendCart | response | taxTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | extendCart | response | taxTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | extendCart | response | total | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | extendCart | response | total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | extendCart | response | total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | extendCart | response | total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | extendCart | response | appliedPromotionIds | array of string (uuid) |  | Re-evaluated on every read.
OrderService | extendCart | response | couponCodes | array of string |  | The promo codes the guest entered through applyCartPromoCode (decided 28 September, audit R073 (e)). (read-only)
OrderService | extendCart | response | expiresAt | string (date-time) |  | The earliest lease expiry in the cart, or the cart's own window where it holds none.
OrderService | extendCart | response | extensionsUsed | integer |  | (read-only)
OrderService | extendCart | response | maxExtensions | integer |  | (read-only)
OrderService | extendCart | response | locale | string
OrderService | extendCart | response | createdAt | string (date-time)
OrderService | extendCart | response | updatedAt | string (date-time)
OrderService | extendCart | param (path) | cartId | string (uuid) | yes
OrderService | extendCart | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | extendReservation | response | id | string (uuid) | yes
OrderService | extendReservation | response | venueId | string (uuid) | yes
OrderService | extendReservation | response | subjectId | string (uuid) |  | The guest it is held for, from CreateReservationRequest.subjectId. (nullable)
OrderService | extendReservation | response | status | enum (held, converted, expired, cancelled) | yes
OrderService | extendReservation | response | lines | array of CreateOrderLine
OrderService | extendReservation | response | lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | extendReservation | response | lines[].variantId | string (uuid) | yes
OrderService | extendReservation | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | extendReservation | response | lines[].performanceId | string (uuid)
OrderService | extendReservation | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | extendReservation | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | extendReservation | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | extendReservation | response | lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | extendReservation | response | lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | extendReservation | response | lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | extendReservation | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | extendReservation | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | extendReservation | response | lines[].quantity | integer | yes | (min 1)
OrderService | extendReservation | response | lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | extendReservation | response | lines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | extendReservation | response | lines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | extendReservation | response | lines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | extendReservation | response | lines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | extendReservation | response | lines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | extendReservation | response | lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | extendReservation | response | lines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | extendReservation | response | lines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | extendReservation | response | lines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | extendReservation | response | lines[].holderName | string |  | (nullable)
OrderService | extendReservation | response | lines[].dataMaskValues | object |  | Deliberately open.
OrderService | extendReservation | response | expiresAt | string (date-time) | yes
OrderService | extendReservation | response | createdAt | string (date-time) | yes
OrderService | extendReservation | response | convertedOrderId | string (uuid) |  | (nullable)
OrderService | extendReservation | param (path) | reservationId | string (uuid) | yes
OrderService | extendReservation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | extendResourceHold | response | id | string (uuid) | yes
VenueOpsService | extendResourceHold | response | mapId | string (uuid) | yes
VenueOpsService | extendResourceHold | response | resourceIds | array of string (uuid) | yes
VenueOpsService | extendResourceHold | response | from | string (date-time) | yes
VenueOpsService | extendResourceHold | response | to | string (date-time) | yes
VenueOpsService | extendResourceHold | response | partySize | integer |  | (nullable)
VenueOpsService | extendResourceHold | response | status | enum (held, converted, released, expired) | yes
VenueOpsService | extendResourceHold | response | totalPrice | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | extendResourceHold | response | totalPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | extendResourceHold | response | totalPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | extendResourceHold | response | totalPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | extendResourceHold | response | heldByPrincipalId | string (uuid) |  | (nullable)
VenueOpsService | extendResourceHold | response | subjectId | string (uuid) |  | (nullable)
VenueOpsService | extendResourceHold | response | orderId | string (uuid) |  | Set when the order converts it. (nullable)
VenueOpsService | extendResourceHold | response | extensionCount | integer |  | (default 0)
VenueOpsService | extendResourceHold | response | createdAt | string (date-time) | yes
VenueOpsService | extendResourceHold | response | expiresAt | string (date-time) | yes
VenueOpsService | extendResourceHold | response | scopePath | string |  | The partition key (ADR-0005), written at venue scope.
VenueOpsService | extendResourceHold | param (path) | holdId | string (uuid) | yes
VenueOpsService | extendResourceHold | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | extendSeatHold | response | id | string | yes
CatalogueService | extendSeatHold | response | performanceId | string (uuid) | yes
CatalogueService | extendSeatHold | response | seatIds | array of string | yes
CatalogueService | extendSeatHold | response | bufferedSeatIds | array of string |  | Neighbours implicitly held by a seating rule.
CatalogueService | extendSeatHold | response | status | enum (held, converted, released, expired) | yes
CatalogueService | extendSeatHold | response | totalPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | extendSeatHold | response | totalPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | extendSeatHold | response | totalPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | extendSeatHold | response | totalPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | extendSeatHold | response | heldByPrincipalId | string (uuid) |  | (nullable)
CatalogueService | extendSeatHold | response | subjectId | string (uuid) |  | (nullable)
CatalogueService | extendSeatHold | response | extensionCount | integer
CatalogueService | extendSeatHold | response | createdAt | string (date-time) | yes
CatalogueService | extendSeatHold | response | expiresAt | string (date-time) | yes
CatalogueService | extendSeatHold | param (path) | holdId | string (uuid) | yes
CatalogueService | extendSeatHold | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | fireCourse | request | recordedAt | string (date-time) | yes | Device time of the act (offline-capable; replayed in this order).
FnbService | fireCourse | request | course | integer | yes | (min 1)
FnbService | fireCourse | request | fireAt | string (date-time) |  | For timed coursing. (nullable)
FnbService | fireCourse | response | id | string (uuid) | yes
FnbService | fireCourse | response | orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | fireCourse | response | orderNumber | string
FnbService | fireCourse | response | outletId | string (uuid) | yes
FnbService | fireCourse | response | tableLabel | string |  | (nullable)
FnbService | fireCourse | response | serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | fireCourse | response | coursing | object |  | BL-131. (nullable)
FnbService | fireCourse | response | buzzerCode | string |  | BL-128. (nullable)
FnbService | fireCourse | response | status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | fireCourse | response | priority | integer |  | Higher fires sooner.
FnbService | fireCourse | response | prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | fireCourse | response | prioritiseReason | string |  | (nullable)
FnbService | fireCourse | response | lines | array of object | yes
FnbService | fireCourse | response | lines[].lineId | string (uuid) | yes
FnbService | fireCourse | response | lines[].name | string | yes
FnbService | fireCourse | response | lines[].quantity | integer | yes
FnbService | fireCourse | response | lines[].modifiers | array of string
FnbService | fireCourse | response | lines[].note | string |  | (nullable)
FnbService | fireCourse | response | lines[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | fireCourse | response | lines[].refireOfLineId | string (uuid) |  | Set on a refire. (read-only; nullable)
FnbService | fireCourse | response | lines[].refireReason | object |  | (read-only; nullable)
FnbService | fireCourse | response | lines[].isChargeable | boolean |  | A refire's chargeable flag. (read-only; nullable)
FnbService | fireCourse | response | lines[].course | integer |  | (nullable)
FnbService | fireCourse | response | lines[].stationId | string (uuid) |  | (nullable)
FnbService | fireCourse | response | lines[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | fireCourse | response | createdAt | string (date-time) | yes
FnbService | fireCourse | response | targetReadyAt | string (date-time) |  | (nullable)
FnbService | fireCourse | response | elapsedSeconds | integer
FnbService | fireCourse | response | visitId | string (uuid) |  | The table visit the ticket is for (4 October 2026, CHG-FXC-011; KIT-002): the {visitId} notifyServer takes. (read-only; nullable)
FnbService | fireCourse | param (path) | ticketId | string (uuid) | yes
FnbService | fireCourse | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | forceLogout | request | reason | string | yes | (min length 3; max length 500)
IdentityService | forceLogout | request | workstationId | string (uuid) |  | The till making the call. (nullable)
IdentityService | forceLogout | request | supervisorStepUp | object |  | The supervisor ending the session, signing on this device.
IdentityService | forceLogout | request | supervisorStepUp.principalId | string (uuid) | yes | The supervisor signing.
IdentityService | forceLogout | request | supervisorStepUp.credential | string | yes | The supervisor's staff PIN, as they sign in at a till with it. (max length 512)
IdentityService | forceLogout | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | forceLogout | param (path) | sessionId | string (uuid) | yes
CatalogueService | generateCouponCodes | request | quantity | integer | yes | (min 1; max 50000)
CatalogueService | generateCouponCodes | request | prefix | string |  | (max length 16)
CatalogueService | generateCouponCodes | request | length | integer |  | (min 6; max 32; default 12)
CatalogueService | generateCouponCodes | request | assignToSubjectIds | array of string (uuid) |  | Personalised codes bound to named guests. (max items 50000)
CatalogueService | generateCouponCodes | response | batchId | string (uuid)
CatalogueService | generateCouponCodes | response | quantity | integer
CatalogueService | generateCouponCodes | response | status | enum (queued, generating, complete, failed)
CatalogueService | generateCouponCodes | param (path) | campaignId | string (uuid) | yes
CatalogueService | generateCouponCodes | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | generateVisitPlan | request | venueId | string (uuid) | yes | The venue the guest picked in the app (GST-001 / WEB-001), which scopes the plan.
VenueOpsService | generateVisitPlan | request | dayVenues | array of object |  | Which venue on which date, in a multi-venue tenant (30 September client meeting, MoM 4.7, Allam's requirement). (max items 7)
VenueOpsService | generateVisitPlan | request | dayVenues[].date | string (date) | yes
VenueOpsService | generateVisitPlan | request | dayVenues[].venueId | string (uuid) | yes
VenueOpsService | generateVisitPlan | request | dates | array of string (date) | yes | (min items 1; max items 7)
VenueOpsService | generateVisitPlan | request | party | array of object | yes | One entry per person. (min items 1; max items 20)
VenueOpsService | generateVisitPlan | request | party[].heightCm | integer |  | (min 40; max 230; nullable)
VenueOpsService | generateVisitPlan | request | party[].ageYears | integer |  | (min 0; max 120; nullable)
VenueOpsService | generateVisitPlan | request | pace | enum (packed, relaxed) |  | (default relaxed)
VenueOpsService | generateVisitPlan | request | interestTags | array of string |  | The same closed list as VenuePoint.interestTags. (max items 12)
VenueOpsService | generateVisitPlan | request | cuisineTags | array of string |  | Matched per day against the cuisineTags of that day's venue's dining points only (30 September, MoM 4.7). (max items 8)
VenueOpsService | generateVisitPlan | request | retailTags | array of string |  | Shops the party would like to visit (30 September client meeting, MoM 4.7: retail and kiosk shops join F&B as venue-linked planner options), e.g. (max items 8)
VenueOpsService | generateVisitPlan | request | mustIncludePointIds | array of string (uuid) |  | Placed on a day whose venue has the point. (max items 10)
VenueOpsService | generateVisitPlan | request | preset | enum (highlights, family, thrillSeeker, waterDay, relaxed, showsAndDining) |  | A ready-made day plan (GST-052 Suggested Itineraries): the preset fixes the interests and the pace, and the party still decides eligibility. (nullable)
VenueOpsService | generateVisitPlan | request | presetKey | string |  | The ready-made plan the guest took on GST-052 (30 September, second wave of the 29 September pass, MOB-6): one of the built-in preset keys above, or a key of a ready-made plan the venue defines. (max length 64; pattern ^[a-z][a-zA-Z0-9]*$; nullable)
VenueOpsService | generateVisitPlan | request | startTime | string |  | When the party arrives. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
VenueOpsService | generateVisitPlan | request | locale | string |  | (nullable)
VenueOpsService | generateVisitPlan | response | id | string (uuid) | yes | (read-only)
VenueOpsService | generateVisitPlan | response | venueId | string (uuid) | yes
VenueOpsService | generateVisitPlan | response | scopePath | string |  | Derived from venueId. (read-only)
VenueOpsService | generateVisitPlan | response | subjectId | string (uuid) |  | The signed-in guest. (read-only; nullable)
VenueOpsService | generateVisitPlan | response | sessionRef | string |  | The anonymous device session that owns the plan until sign-in. (read-only; nullable)
VenueOpsService | generateVisitPlan | response | ownership | enum (anonymous, account) |  | anonymous while the plan belongs to a device session (built and changed only; it lapses with the session), account once the guest signed in and the plan moved to their account, where it is saved and… (read-only)
VenueOpsService | generateVisitPlan | response | status | enum (draft, booked, archived) | yes | booked after bookVisitPlan; a booked plan is read-only. (read-only)
VenueOpsService | generateVisitPlan | response | version | integer | yes | The current version. (min 1; read-only)
VenueOpsService | generateVisitPlan | response | source | enum (rules, preset, aiAgent) |  | What produced the current version: the rules planner, a preset, or the AI planner agent acting for the guest. (read-only)
VenueOpsService | generateVisitPlan | response | inputs | VisitPlanRequest |  | What generateVisitPlan takes (29 September, MOB-6): the Plan tab's form on GST-051 and WEB-050.
VenueOpsService | generateVisitPlan | response | inputs.venueId | string (uuid) | yes | The venue the guest picked in the app (GST-001 / WEB-001), which scopes the plan.
VenueOpsService | generateVisitPlan | response | inputs.dayVenues | array of object |  | Which venue on which date, in a multi-venue tenant (30 September client meeting, MoM 4.7, Allam's requirement). (max items 7)
VenueOpsService | generateVisitPlan | response | inputs.dayVenues[].date | string (date) | yes
VenueOpsService | generateVisitPlan | response | inputs.dayVenues[].venueId | string (uuid) | yes
VenueOpsService | generateVisitPlan | response | inputs.dates | array of string (date) | yes | (min items 1; max items 7)
VenueOpsService | generateVisitPlan | response | inputs.party | array of object | yes | One entry per person. (min items 1; max items 20)
VenueOpsService | generateVisitPlan | response | inputs.party[].heightCm | integer |  | (min 40; max 230; nullable)
VenueOpsService | generateVisitPlan | response | inputs.party[].ageYears | integer |  | (min 0; max 120; nullable)
VenueOpsService | generateVisitPlan | response | inputs.pace | enum (packed, relaxed) |  | (default relaxed)
VenueOpsService | generateVisitPlan | response | inputs.interestTags | array of string |  | The same closed list as VenuePoint.interestTags. (max items 12)
VenueOpsService | generateVisitPlan | response | inputs.cuisineTags | array of string |  | Matched per day against the cuisineTags of that day's venue's dining points only (30 September, MoM 4.7). (max items 8)
VenueOpsService | generateVisitPlan | response | inputs.retailTags | array of string |  | Shops the party would like to visit (30 September client meeting, MoM 4.7: retail and kiosk shops join F&B as venue-linked planner options), e.g. (max items 8)
VenueOpsService | generateVisitPlan | response | inputs.mustIncludePointIds | array of string (uuid) |  | Placed on a day whose venue has the point. (max items 10)
VenueOpsService | generateVisitPlan | response | inputs.preset | enum (highlights, family, thrillSeeker, waterDay, relaxed, showsAndDining) |  | A ready-made day plan (GST-052 Suggested Itineraries): the preset fixes the interests and the pace, and the party still decides eligibility. (nullable)
VenueOpsService | generateVisitPlan | response | inputs.presetKey | string |  | The ready-made plan the guest took on GST-052 (30 September, second wave of the 29 September pass, MOB-6): one of the built-in preset keys above, or a key of a ready-made plan the venue defines. (max length 64; pattern ^[a-z][a-zA-Z0-9]*$; nullable)
VenueOpsService | generateVisitPlan | response | inputs.startTime | string |  | When the party arrives. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
VenueOpsService | generateVisitPlan | response | inputs.locale | string |  | (nullable)
VenueOpsService | generateVisitPlan | response | mapVersion | integer |  | The published map version the plan was laid out on. (read-only)
VenueOpsService | generateVisitPlan | response | cartId | string (uuid) |  | The cart bookVisitPlan filled. (read-only; nullable)
VenueOpsService | generateVisitPlan | response | excluded | array of object |  | What was left out and why, e.g. (read-only)
VenueOpsService | generateVisitPlan | response | excluded[].pointId | string (uuid)
VenueOpsService | generateVisitPlan | response | excluded[].productId | string (uuid) |  | (nullable)
VenueOpsService | generateVisitPlan | response | excluded[].reason | enum (heightRule, ageRule, closedOnDate, notInInterests, noTime, notAtVenue) |  | notAtVenue (30 September, MoM 4.7): a must-include point that is at none of the plan's venues, so no day could hold it.
VenueOpsService | generateVisitPlan | response | unmatchedPreferences | array of object |  | A preference a day's venue cannot meet is said, never faked (30 September client meeting, MoM 4.7, Allam's requirement). (read-only)
VenueOpsService | generateVisitPlan | response | unmatchedPreferences[].date | string (date) | yes
VenueOpsService | generateVisitPlan | response | unmatchedPreferences[].venueId | string (uuid) | yes | The day's venue, which has no match.
VenueOpsService | generateVisitPlan | response | unmatchedPreferences[].preference | enum (cuisine, retail, interest) | yes
VenueOpsService | generateVisitPlan | response | unmatchedPreferences[].tag | string | yes | (max length 30)
VenueOpsService | generateVisitPlan | response | unmatchedPreferences[].availableAtVenueIds | array of string (uuid) |  | Other active venues of the tenant where the tag is matched.
VenueOpsService | generateVisitPlan | response | days | array of object | yes | One per date, in order. (read-only)
VenueOpsService | generateVisitPlan | response | days[].date | string (date) | yes
VenueOpsService | generateVisitPlan | response | days[].venueId | string (uuid) | yes | The venue this day is planned at (30 September, MoM 4.7): VisitPlanRequest.dayVenues for the date, else venueId.
VenueOpsService | generateVisitPlan | response | days[].opensAt | string |  | (nullable)
VenueOpsService | generateVisitPlan | response | days[].closesAt | string |  | (nullable)
VenueOpsService | generateVisitPlan | response | days[].items | array of VisitPlanItem | yes
VenueOpsService | generateVisitPlan | response | days[].items[].id | string (uuid) | yes | (read-only)
VenueOpsService | generateVisitPlan | response | days[].items[].planId | string (uuid) | yes | (read-only)
VenueOpsService | generateVisitPlan | response | days[].items[].planVersion | integer | yes | (min 1; read-only)
VenueOpsService | generateVisitPlan | response | days[].items[].date | string (date) | yes
VenueOpsService | generateVisitPlan | response | days[].items[].sequence | integer | yes | (min 1)
VenueOpsService | generateVisitPlan | response | days[].items[].kind | enum (attraction, show, meal, shop, rest, travel) | yes | meal is a stop at a dining point (restaurant, cafe or food kiosk); shop is a retail stop at a shop or a retail kiosk (30 September client meeting, MoM 4.7: retail is placed from the day venue's own p…
VenueOpsService | generateVisitPlan | response | days[].items[].venueId | string (uuid) |  | The venue of this stop (30 September client meeting, MoM 4.7): always the day's venue, and the venue whose map pointId is on. (read-only)
VenueOpsService | generateVisitPlan | response | days[].items[].pointId | string (uuid) |  | (nullable)
VenueOpsService | generateVisitPlan | response | days[].items[].productId | string (uuid) |  | What is bought for this stop, where it is bought. (nullable)
VenueOpsService | generateVisitPlan | response | days[].items[].bundleId | string (uuid) |  | A meal combo or package, from the point's featuredOffer. (nullable)
VenueOpsService | generateVisitPlan | response | days[].items[].performanceId | string (uuid) |  | (nullable)
VenueOpsService | generateVisitPlan | response | days[].items[].startsAt | string (date-time) | yes
VenueOpsService | generateVisitPlan | response | days[].items[].endsAt | string (date-time) | yes
VenueOpsService | generateVisitPlan | response | days[].items[].walkMinutesBefore | integer |  | (min 0; nullable)
VenueOpsService | generateVisitPlan | response | days[].items[].expectedWaitMinutes | integer |  | The typical wait at that hour when the plan was laid out; GST-059 replaces it with the live one. (min 0; nullable)
VenueOpsService | generateVisitPlan | response | days[].items[].addOnSuggestion | object |  | A suggested add-on for this stop, e.g. (nullable)
VenueOpsService | generateVisitPlan | response | days[].items[].addOnAccepted | boolean |  | (default False)
VenueOpsService | generateVisitPlan | response | days[].items[].addOnProductIds | array of string (uuid) |  | Add-ons the guest put on this stop with addAddOn (CHG-RUL-009), beside an accepted suggestion, as catalogue product ids. (read-only)
VenueOpsService | generateVisitPlan | response | days[].items[].pinned | boolean |  | The guest fixed this stop; a re-lay moves other stops around it. (default False)
VenueOpsService | generateVisitPlan | response | days[].items[].note | string |  | (max length 200; nullable)
VenueOpsService | generateVisitPlan | response | createdAt | string (date-time) |  | (read-only)
VenueOpsService | generateVisitPlan | response | updatedAt | string (date-time) |  | (read-only)
VenueOpsService | generateVisitPlan | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | getAiByokEnablement | response | id | string (uuid) |  | (read-only)
AiService | getAiByokEnablement | response | tenantId | string (uuid) | yes
AiService | getAiByokEnablement | response | enabled | boolean | yes
AiService | getAiByokEnablement | response | coverage | enum (perTask, allTasks) |  | Whether the tenant may supply a key per task or one key for everything. (default perTask)
AiService | getAiByokEnablement | response | allowedTasks | array of string |  | Where coverage is perTask: the gateway tasks a tenant key may serve.
AiService | getAiByokEnablement | response | taskModelMap | array of object |  | The provider's equivalent model for each task, chosen by TICVAI (Chinmay, 2 October, workbook Q1; closes AI-D20; CHG-CSA-001). (read-only)
AiService | getAiByokEnablement | response | taskModelMap[].taskKey | string
AiService | getAiByokEnablement | response | taskModelMap[].tier | string
AiService | getAiByokEnablement | response | taskModelMap[].modelId | string (uuid) |  | (nullable)
AiService | getAiByokEnablement | response | taskModelMap[].compatibilityPassed | boolean |  | Whether the provider's compatibility test passed for this task (AiProviderCompatibility, CHG-FUP-008); a task that has not passed stays on the TICVAI-managed model. (nullable)
AiService | getAiByokEnablement | response | reason | string |  | (max length 1000)
AiService | getAiByokEnablement | response | platformStaffGrantId | string (uuid) |  | The open platform-staff grant the change was made under (audit R098). (read-only)
AiService | getAiByokEnablement | response | decidedByPrincipalId | string (uuid) |  | (read-only)
AiService | getAiByokEnablement | response | decidedAt | string (date-time) |  | (read-only)
AiService | getAiByokEnablement | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | getAiByokEnablement | param (path) | tenantId | string (uuid) | yes
AiService | getAiPolicy | response | id | string (uuid) |  | Added 20 August. (read-only)
AiService | getAiPolicy | response | scopeLevel | enum (tenant, venue) | yes | Tenant sets the default; a venue may narrow it and never widen it.
AiService | getAiPolicy | response | scopePath | string | yes | The node this row belongs to, and the key it is written under — the tenant's node where scopeLevel is tenant, a venue's where it is venue.
AiService | getAiPolicy | response | enabledCapabilities | array of enum (assist, search, generateConfiguration, generateLayout, summarise, explain, gatewayAndModels, governance, …) | yes | Extended on 29 September to the fourteen capabilities of the AI design (section 1.1, AiCapabilityFamily).
AiService | getAiPolicy | response | allowedRoleIds | array of string (uuid)
AiService | getAiPolicy | response | maskedFields | array of string |  | Redacted before a prompt leaves the platform (8.3.73).
AiService | getAiPolicy | response | requiresApprovalFor | array of enum (pricing, promotion, operational, financial, configuration) |  | 8.3.61–8.3.64.
AiService | getAiPolicy | response | scrubbing | object |  | Mandatory offline PII scrubbing and moderation on every LLM call (Chinmay, 2 October: "we may need to scrub personal info no matter what"; ADR-0020 amended; CHG-CSA-003). (read-only)
AiService | getAiPolicy | response | scrubbing.mode | enum (mandatory)
AiService | getAiPolicy | response | scrubbing.scrubberVersion | string |  | The pinned Presidio release (and recogniser set) in force, e.g. (read-only)
AiService | getAiPolicy | response | scrubbing.residualPatternCheck | array of enum (emiratesId, uaePhone, cardPan, iban, email) |  | The deterministic patterns run after Presidio; a match blocks the call (fail closed, 503 scrubber-unavailable). (read-only)
AiService | getAiPolicy | response | scrubbing.recognisers | array of string |  | The recogniser set in force, e.g.
AiService | getAiPolicy | response | scrubbing.reversibleTokens | boolean |  | Always true; the placeholder map stays in the cell.
AiService | getAiPolicy | response | scrubbing.guardModel | string |  | The input and output guard in force, e.g.
AiService | getAiPolicy | response | globalEndpointExclusions | object |  | What never goes to a global endpoint (3 October 2026, CHG-R1S-016; the legal research docs/active/research/openai-key-uae-3-october.md, item 6). (read-only)
AiService | getAiPolicy | response | globalEndpointExclusions.fieldCategories | array of enum (allergy, accessibility, familyAndChildren, health, biometric, religion, payment) |  | Allergy, accessibility and family or children data in F&B and booking prompts, and health, biometric, religion and payment data anywhere.
AiService | getAiPolicy | response | globalEndpointExclusions.fields | array of string |  | The schema fields held under those categories, e.g.
AiService | getAiPolicy | response | globalEndpointExclusions.blockedMedia | array of enum (image, audio, file) |  | Images, audio and files are never sent to a global endpoint.
AiService | getAiPolicy | response | monthlyTokenCeiling | integer |  | (nullable)
AiService | getAiPolicy | response | ceilingBehaviour | enum (warn, warnThenDisable, block) |  | Decided 17 August: warn, and let the venue manager choose. (default warn)
AiService | getAiPolicy | response | ceilingBehaviourByCapability | array of object |  | Ceiling behaviour per capability (AI design 5.9, AIC-227), so a budget never silently disables fraud scoring, which spends no tokens, or a critical capability.
AiService | getAiPolicy | response | ceilingBehaviourByCapability[].capability | string | yes | An AiCapabilityFamily value, or a registered capability key.
AiService | getAiPolicy | response | ceilingBehaviourByCapability[].behaviour | enum (warn, warnThenDisable, block, neverRestrict) | yes
AiService | getAiPolicy | response | autonomyOverrides | array of object |  | Tighten only (AI design 3.8, AIC-151).
AiService | getAiPolicy | response | autonomyOverrides[].capabilityKey | string | yes
AiService | getAiPolicy | response | autonomyOverrides[].autonomyLevel | integer | yes | One autonomy scale for every capability (design 3.8 and 5.5, GOV 0 to 4; ADR-0050). (min 0; max 4)
AiService | getAiPolicy | response | ceilingWarningPercent | integer |  | Warn before the ceiling, not at it. (default 80)
AiService | getAiPolicy | response | guestCapabilityScope | array of enum (ticketSelection, promotions, faq, recommendations, checkout, waitTimes, wayfinding, visitPlanning) |  | What a guest-facing assistant may help with, and nothing else (2.1.28).
AiService | getAiPolicy | response | retrieveTopK | integer |  | How many chunks retrieval returns before reranking. (default 30)
AiService | getAiPolicy | response | rerankTopK | integer |  | How many survive the rerank and reach the model. (default 5; nullable)
AiService | getAiPolicy | response | cacheAnswers | boolean |  | The largest cost lever available at a kiosk. (default True)
AiService | getAiPolicy | response | cacheTtlMinutes | integer |  | An upper bound on top of event invalidation, not instead of it. (default 60)
AiService | getAiPolicy | response | retainInteractionsDays | integer |  | How long prompts and responses are kept.
AiService | getAiPolicy | response | semanticCacheThreshold | number |  | Similarity above which a cached answer serves a new question. (min 0; max 1; default 0.95)
AiService | getAiPolicy | response | negativeCacheTtlSeconds | integer |  | How long *no answer found* is remembered. (default 300)
AiService | getAiPolicy | response | cascade | object |  | A small model answers and escalates only below a confidence threshold. (nullable)
AiService | getAiPolicy | response | cascade.smallModel | string
AiService | getAiPolicy | response | cascade.largeModel | string
AiService | getAiPolicy | response | cascade.escalateBelow | number |  | (default 0.7)
AiService | getAiPolicy | response | chunking | object |  | The single biggest lever on retrieval quality, and currently nowhere.
AiService | getAiPolicy | response | chunking.sizeTokens | integer |  | (default 512)
AiService | getAiPolicy | response | chunking.overlapTokens | integer |  | (default 64)
AiService | getAiPolicy | response | chunking.strategy | enum (fixed, sentence, semantic) |  | (default sentence)
AiService | getAiPolicy | response | quantisation | enum (none, scalar, binary) |  | A decision, never a default. (default none)
AiService | getAiPolicy | response | hnsw | object |  | Defaults are tuned for neither our recall nor our latency. (nullable)
AiService | getAiPolicy | response | hnsw.m | integer |  | (default 16)
AiService | getAiPolicy | response | hnsw.efConstruct | integer |  | (default 128)
AiService | getAiPolicy | response | hnsw.efSearch | integer |  | (default 64)
AiService | getAiPolicy | response | perRequestTokenCeiling | integer |  | One runaway conversation can spend a tenant's month. (nullable)
AiService | getAiPolicy | response | streamsByCapability | array of string |  | Time to first token and total latency are separate targets.
AiService | getAiPolicy | response | fallbackProviderId | string (uuid) |  | BL-151: a provider outage with no fallback is every AI surface going dark at once. (nullable)
AiService | getAiPolicy | response | guardrailShortCircuit | boolean |  | A refusal a rule can decide never reaches a model. (default True)
AiService | getAiPolicy | response | suggestionProviders | object |  | Which producer answers each SuggestionKind, and what requestSuggestion routes by. (read-only)
AiService | getAiPolicy | param (query) | scopePath | string |  | The tenant or venue node to read the policy for.
AiService | getAiUsage | response | currency | string |  | The tenant's selected currency, by default its billing currency (AED for a UAE tenant), not USD (CHG-RUL-017; Chinmay, 2 October, workbook Q8; CHG-CSA-004). (min length 3; max length 3; read-only)
AiService | getAiUsage | response | ceiling | object |  | The spend ceiling in force (getAiSpendCeiling), with the tokens it equals at the current blended rate and what is used so far (CHG-CSA-004). (read-only; nullable)
AiService | getAiUsage | response | ceiling.spend | Money |  | On the wire this is three fields; in the database it is one column.
AiService | getAiUsage | response | ceiling.spend.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
AiService | getAiUsage | response | ceiling.spend.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
AiService | getAiUsage | response | ceiling.spend.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
AiService | getAiUsage | response | ceiling.tokens | integer |  | (nullable)
AiService | getAiUsage | response | ceiling.usedSpend | Money |  | On the wire this is three fields; in the database it is one column.
AiService | getAiUsage | response | ceiling.usedSpend.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
AiService | getAiUsage | response | ceiling.usedSpend.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
AiService | getAiUsage | response | ceiling.usedSpend.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
AiService | getAiUsage | response | ceiling.usedTokens | integer
AiService | getAiUsage | response | from | string (date)
AiService | getAiUsage | response | to | string (date)
AiService | getAiUsage | response | groupBy | string
AiService | getAiUsage | response | rows | array of object
AiService | getAiUsage | response | rows[].key | string
AiService | getAiUsage | response | rows[].interactions | integer
AiService | getAiUsage | response | rows[].promptTokens | integer
AiService | getAiUsage | response | rows[].completionTokens | integer
AiService | getAiUsage | response | rows[].cost | Money |  | On the wire this is three fields; in the database it is one column.
AiService | getAiUsage | response | rows[].cost.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
AiService | getAiUsage | response | rows[].cost.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
AiService | getAiUsage | response | rows[].cost.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
AiService | getAiUsage | response | rows[].p95LatencyMs | integer
AiService | getAiUsage | response | rows[].refusalRate | number
AiService | getAiUsage | response | rows[].rejectionRate | number |  | Proposals a person refused.
AiService | getAiUsage | response | forecast | object |  | A month-end projection, labelled a forecast (AI design 2.3, 4.5). (nullable)
AiService | getAiUsage | response | forecast.label | enum (forecast)
AiService | getAiUsage | response | forecast.periodEnd | string (date)
AiService | getAiUsage | response | forecast.projectedTokens | integer
AiService | getAiUsage | response | forecast.projectedCost | Money |  | On the wire this is three fields; in the database it is one column.
AiService | getAiUsage | response | forecast.projectedCost.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
AiService | getAiUsage | response | forecast.projectedCost.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
AiService | getAiUsage | response | forecast.projectedCost.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
AiService | getAiUsage | response | forecast.basis | string |  | How it was projected, e.g.
AiService | getAiUsage | param (query) | from | string (date)
AiService | getAiUsage | param (query) | groupBy | enum (tenant, venue, principal, provider, capability, day, agent, model, …)
AiService | getAiVenueSettings | response | id | string (uuid) |  | (read-only)
AiService | getAiVenueSettings | response | venueId | string (uuid) | yes
AiService | getAiVenueSettings | response | venueType | enum (waterPark, themePark, familyEntertainmentCentre, museum, arena, zooAquarium, other) | yes
AiService | getAiVenueSettings | response | isOutdoor | boolean |  | Outdoor venues take the summer-heat and weather effects. (default True)
AiService | getAiVenueSettings | response | capacity | integer |  | (min 1; nullable)
AiService | getAiVenueSettings | response | openingHours | array of object |  | The usual week.
AiService | getAiVenueSettings | response | openingHours[].dayOfWeek | integer |  | (min 1; max 7)
AiService | getAiVenueSettings | response | openingHours[].opensAt | string
AiService | getAiVenueSettings | response | openingHours[].closesAt | string
AiService | getAiVenueSettings | response | typicalWeekdayAttendance | integer |  | (min 0; nullable)
AiService | getAiVenueSettings | response | typicalWeekendAttendance | integer |  | (min 0; nullable)
AiService | getAiVenueSettings | response | peakMonths | array of integer
AiService | getAiVenueSettings | response | averageSpend | object |  | (nullable)
AiService | getAiVenueSettings | response | averageSpend.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
AiService | getAiVenueSettings | response | averageSpend.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
AiService | getAiVenueSettings | response | averageSpend.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
AiService | getAiVenueSettings | response | fnbAttachRate | number |  | (min 0; max 1; nullable)
AiService | getAiVenueSettings | response | staffProductivity | object |  | Per role, units per staff hour, e.g.
AiService | getAiVenueSettings | response | startingPatternKey | string |  | The pattern and version in use, e.g. (read-only)
AiService | getAiVenueSettings | response | updatedAt | string (date-time) |  | (read-only)
AiService | getAiVenueSettings | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | getAiVenueSettings | param (path) | venueId | string (uuid) | yes
WhiteLabelService | getAppBuild | response | id | string (uuid) | yes | (read-only)
WhiteLabelService | getAppBuild | response | platform | enum (ios, android) | yes
WhiteLabelService | getAppBuild | response | configVersion | string | yes | The ConfigVersion.version built.
WhiteLabelService | getAppBuild | response | storeAccountId | string (uuid) |  | (read-only)
WhiteLabelService | getAppBuild | response | versionName | string |  | The marketing version, e.g. (read-only)
WhiteLabelService | getAppBuild | response | buildNumber | integer |  | (read-only)
WhiteLabelService | getAppBuild | response | status | enum (queued, building, built, failed, submitted, inReview, approved, rejected, …) | yes | queued to built or failed is the build service's; from submitted on it is read from the store with the client's credential, or stays built when the client uploads by hand. (read-only)
WhiteLabelService | getAppBuild | response | failureReason | string |  | (read-only; nullable)
WhiteLabelService | getAppBuild | response | packageAssetRef | string (uuid) |  | The signed .ipa or .aab in the assets library, for the client to download and upload. (read-only; nullable)
WhiteLabelService | getAppBuild | response | releaseNotes | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | getAppBuild | response | submitToStore | boolean |  | (default False)
WhiteLabelService | getAppBuild | response | requestedAt | string (date-time) | yes | (read-only)
WhiteLabelService | getAppBuild | response | requestedByPrincipalId | string (uuid) |  | (read-only)
WhiteLabelService | getAppBuild | response | finishedAt | string (date-time) |  | (read-only; nullable)
WhiteLabelService | getAppBuild | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | getAppBuild | param (path) | appBuildId | string (uuid) | yes
WhiteLabelService | getAppIcons | response | sourceAssetRef | string (uuid) | yes | The MediaAsset id of the 1024×1024 source.
WhiteLabelService | getAppIcons | response | derived | array of object |  | Generated by setAppIcons from the source, one entry per platform and size — the iOS and Android store sets and the web favicons listed on setAppIcons (audit R163). (read-only)
WhiteLabelService | getAppIcons | response | derived[].platform | enum (ios, android, web)
WhiteLabelService | getAppIcons | response | derived[].size | string
WhiteLabelService | getAppIcons | response | derived[].assetRef | string (uuid)
WhiteLabelService | getAppIcons | response | changeScope | object | yes | Always buildTime — icons are baked into the binary. (read-only)
WhiteLabelService | getAppIcons | response | liveVersion | string |  | Icon currently shipped. (read-only; nullable)
WhiteLabelService | getAppIcons | response | requiresRebuild | boolean |  | True while the draft's source differs from the icon in liveVersion. (read-only)
CatalogueService | getAvailability | response | items | array of PerformanceAvailability | yes
CatalogueService | getAvailability | response | items[].channelCapacityId | string (uuid) | yes
CatalogueService | getAvailability | response | items[].performanceId | string (uuid) | yes | The performance this channel capacity belongs to (ChannelCapacity.performanceId), so rows for several performances can be told apart.
CatalogueService | getAvailability | response | items[].startsAt | string (date-time) |  | The performance's start, so a time tile and its day part (morning, afternoon, evening, split at the venue's BookingFlowConfig.dayPartBoundaries) come from this one call (rev 3 REV3-1). (read-only)
CatalogueService | getAvailability | response | items[].capacity | integer | yes
CatalogueService | getAvailability | response | items[].sold | integer | yes
CatalogueService | getAvailability | response | items[].leased | integer | yes | Held by terminals but not yet sold.
CatalogueService | getAvailability | response | items[].remaining | integer | yes
CatalogueService | getAvailability | response | items[].byChannel | array of object |  | Per-channel position.
CatalogueService | getAvailability | response | items[].byChannel[].channel | Channel: enum (pos, kiosk, web, mobile, b2b, ota, callCentre)
CatalogueService | getAvailability | response | items[].byChannel[].allocated | integer
CatalogueService | getAvailability | response | items[].byChannel[].sold | integer
CatalogueService | getAvailability | response | items[].byChannel[].remaining | integer
CatalogueService | getAvailability | response | nextCursor | string
CatalogueService | getAvailability | response | hasMore | boolean | yes
CatalogueService | getAvailability | param (query) | performanceId | string (uuid)
CatalogueService | getAvailability | param (query) | channelCapacityId | string (uuid)
CatalogueService | getAvailability | param (query) | eventId | string (uuid) |  | Every performance of this event starting between from and to (rev 3 REV3-1).
CatalogueService | getAvailability | param (query) | from | string (date-time) |  | Required with eventId.
CatalogueService | getAvailability | param (query) | to | string (date-time) |  | Required with eventId.
CatalogueService | getAvailability | param (query) | pageSize | integer
CatalogueService | getAvailability | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
FnbService | getBill | response | visitId | string | yes
FnbService | getBill | response | covers | integer
FnbService | getBill | response | lines | array of object | yes
FnbService | getBill | response | lines[].lineId | string | yes
FnbService | getBill | response | lines[].orderId | string
FnbService | getBill | response | lines[].name | string | yes
FnbService | getBill | response | lines[].quantity | integer | yes
FnbService | getBill | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | getBill | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getBill | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getBill | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getBill | response | lines[].lineTotal | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | getBill | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getBill | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getBill | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getBill | response | lines[].categoryCode | string |  | (nullable)
FnbService | getBill | response | lines[].seatNumber | integer |  | (nullable)
FnbService | getBill | response | subtotal | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | getBill | response | subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getBill | response | subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getBill | response | subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getBill | response | serviceCharge | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | getBill | response | serviceCharge.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getBill | response | serviceCharge.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getBill | response | serviceCharge.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getBill | response | taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | getBill | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getBill | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getBill | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getBill | response | discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | getBill | response | discountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getBill | response | discountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getBill | response | discountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getBill | response | total | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | getBill | response | total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getBill | response | total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getBill | response | total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getBill | param (path) | visitId | string (uuid) | yes
OrderService | getBillingStatement | response | id | string (uuid) | yes
OrderService | getBillingStatement | response | subjectId | string (uuid) |  | (read-only)
OrderService | getBillingStatement | response | periodStart | string (date) | yes
OrderService | getBillingStatement | response | periodEnd | string (date) | yes
OrderService | getBillingStatement | response | lines | array of BillingStatementLine
OrderService | getBillingStatement | response | lines[].occurredAt | string (date-time) | yes
OrderService | getBillingStatement | response | lines[].kind | enum (charge, refund, failedAttempt, adjustment) | yes
OrderService | getBillingStatement | response | lines[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getBillingStatement | response | lines[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getBillingStatement | response | lines[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getBillingStatement | response | lines[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getBillingStatement | response | lines[].description | string
OrderService | getBillingStatement | response | lines[].netAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getBillingStatement | response | lines[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getBillingStatement | response | lines[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getBillingStatement | response | lines[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getBillingStatement | response | lines[].discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getBillingStatement | response | lines[].discountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getBillingStatement | response | lines[].discountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getBillingStatement | response | lines[].discountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getBillingStatement | response | lines[].taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getBillingStatement | response | lines[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getBillingStatement | response | lines[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getBillingStatement | response | lines[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getBillingStatement | response | lines[].taxRate | number |  | 2.14.23. (nullable)
OrderService | getBillingStatement | response | lines[].taxInvoiceId | string (uuid) |  | The finance tax invoice issued for this charge, where one was (issueTaxInvoice); the guest downloads it with getTaxDocumentRendition. (nullable)
OrderService | getBillingStatement | response | lines[].declineClass | string |  | Present on failedAttempt only, and it is what turns *"your payment failed"* into something a guest can act on: a soft decline means try again, a hard one means the card needs replacing. (nullable)
OrderService | getBillingStatement | response | total | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getBillingStatement | response | total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getBillingStatement | response | total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getBillingStatement | response | total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getBillingStatement | response | taxTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getBillingStatement | response | taxTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getBillingStatement | response | taxTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getBillingStatement | response | taxTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getBillingStatement | response | discountTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getBillingStatement | response | discountTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getBillingStatement | response | discountTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getBillingStatement | response | discountTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getBillingStatement | response | pdfUrl | string (uri) |  | Set when getBillingStatement is called with format=pdf; a short-lived link. (read-only; nullable)
OrderService | getBillingStatement | response | isTaxInvoice | boolean | yes | Always false, and stated rather than assumed. (default False; read-only)
OrderService | getBillingStatement | param (path) | statementId | string (uuid) | yes
OrderService | getBillingStatement | param (query) | format | enum (json, pdf) |  | 2.14.23.
OrderService | getBillingStatement | param (query) | language | string
WhiteLabelService | getBookingFlow | response | id | string (uuid) |  | (read-only)
WhiteLabelService | getBookingFlow | response | venueId | string (uuid) |  | From the path of createBookingFlowDefinition. (read-only)
WhiteLabelService | getBookingFlow | response | flowTypeKey | BookingFlowTypeKey: enum (datedDayPass, timedEntry, openDated, seatedFixedPerformance, seatedDateTimeSeatMap, experienceWorkshop, surfSession, meetingRoomHourly, …) | yes | The flow types the system catalogue offers (decided 29 September, W12; impact.md b).
WhiteLabelService | getBookingFlow | response | name | string | yes | Staff-facing, e.g. (max length 80)
WhiteLabelService | getBookingFlow | response | isDefaultForType | boolean |  | At most one per venue and type; setting it takes it from the previous default. (default False)
WhiteLabelService | getBookingFlow | response | isEnabled | boolean |  | A disabled flow is kept and not published; products naming it fall back to the default. (default True)
WhiteLabelService | getBookingFlow | response | steps | array of BookingFlowStep |  | Every step of the type, in the venue's order. (max items 30)
WhiteLabelService | getBookingFlow | response | steps[].id | string (uuid) |  | (read-only)
WhiteLabelService | getBookingFlow | response | steps[].bookingFlowId | string (uuid) |  | (read-only)
WhiteLabelService | getBookingFlow | response | steps[].stepKey | BookingFlowStepKey: enum (location, helpMeChoose, product, date, time, performance, level, language, …) | yes | Every step a guest booking flow can hold (decided 29 September, W12).
WhiteLabelService | getBookingFlow | response | steps[].enabled | boolean | yes | A required step cannot be off; the flow saves and isValid turns false.
WhiteLabelService | getBookingFlow | response | steps[].sortOrder | integer | yes | (min 0)
WhiteLabelService | getBookingFlow | response | steps[].requirement | enum (required, optional, conditional) |  | From the flow type, so the CMS can mark the step without a second read. (read-only)
WhiteLabelService | getBookingFlow | response | steps[].settings | object |  | The step's own settings, by the names the type's stepSettings gives for this step (e.g. (default {})
WhiteLabelService | getBookingFlow | response | settings | BookingFlowLevelSettings |  | The settings that belong to one flow, not to the venue (decided 29 September, W12).
WhiteLabelService | getBookingFlow | response | settings.performanceReveal | enum (dateTimeTicket, allAtOnce) |  | Performance reveal (rev 3 REV3-2). (default dateTimeTicket)
WhiteLabelService | getBookingFlow | response | settings.signInAt | enum (afterAddOns, atPayment) |  | Where the guest is asked to sign in, or for a guest-checkout code (rev 3 REV3-3). (default afterAddOns)
WhiteLabelService | getBookingFlow | response | settings.seatEventDateMode | enum (inlineStep, popupOnSeatMap) |  | Date and time on a seated event (rev 3 REV3-4). (default inlineStep)
WhiteLabelService | getBookingFlow | response | settings.extrasStep | enum (auto, always, never) |  | auto shows the extras step only when the cart's products have add-ons; never is the same as turning the optional extras step off. (default auto)
WhiteLabelService | getBookingFlow | response | settings.quickTour | boolean |  | Quick tour (rev 3 REV3-20). (default False)
WhiteLabelService | getBookingFlow | response | settings.consentQuestionIds | array of string (uuid) |  | The flow's own consent questions (rev 3 REV3-26). (max items 10; default [])
WhiteLabelService | getBookingFlow | response | isValid | boolean |  | Whether the flow passes validateBookingFlow; worked out in the same transaction as each write. (read-only)
WhiteLabelService | getBookingFlow | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | getBookingFlow | response | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | getBookingFlow | param (path) | bookingFlowId | string (uuid) | yes
WhiteLabelService | getBookingFlowConfig | response | preset | enum (auto, ticketBox, playCentre, venueSite, marketplace, singleEvent, season, custom) |  | L1 Ticket box … L6 Season. (default auto)
WhiteLabelService | getBookingFlowConfig | response | stepIndicator | enum (bar, numbered, dots, segmented, breadcrumb, pills, ticks, none) |  | (default bar)
WhiteLabelService | getBookingFlowConfig | response | cartLayout | enum (sidebarRight, sidebarLeft, slideInRight, slideUpBottom, singleColumn, floatingIcon) |  | floatingIcon is a round basket button with the item count that opens the cart (decided 29 September, rev 3 REV3-10). (default sidebarRight)
WhiteLabelService | getBookingFlowConfig | response | cartSideInRtl | enum (keepRight, mirror) |  | The cart side when the guest reads Arabic or another right-to-left language (decided 29 September, rev 3 REV3-10). (default keepRight)
WhiteLabelService | getBookingFlowConfig | response | cardLayout | enum (stackedRows, splitRows, cardsAcross, posterCards) |  | How ticket and product cards are laid out (decided 29 September, rev 3 DG-6). (default stackedRows)
WhiteLabelService | getBookingFlowConfig | response | cardSize | enum (compact, standard, large, extraLarge) |  | Labels Compact, Standard, Large, Extra large (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | getBookingFlowConfig | response | seatPicker | enum (bowl, zonesThenSeats, zonesOnly, seatsOnly) |  | Default bowl, as the prototype has it (decided 29 September, rev 3 CFG-6). (default bowl)
WhiteLabelService | getBookingFlowConfig | response | mapView | enum (2d, 3d) |  | (default 3d)
WhiteLabelService | getBookingFlowConfig | response | density | enum (compact, standard, roomy) |  | Labels Compact, Standard, Roomy, default Compact as the design has it (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | getBookingFlowConfig | response | embedMode | enum (fullPage, embedded) |  | embedded hides the hero banner, event page and venue header, for a flow placed inside the venue's own site. (default fullPage)
WhiteLabelService | getBookingFlowConfig | response | heroBanner | boolean |  | (default True)
WhiteLabelService | getBookingFlowConfig | response | searchInBanner | boolean |  | Off by default, as the prototype has it (decided 29 September, rev 3 CFG-6). (default False)
WhiteLabelService | getBookingFlowConfig | response | eventBannerDates | boolean |  | Dates in event banner (decided 29 September, rev 3 23SEP-19). (default False)
WhiteLabelService | getBookingFlowConfig | response | singleEventPage | boolean |  | (default False)
WhiteLabelService | getBookingFlowConfig | response | quantitiesOnAddOns | boolean |  | (default True)
WhiteLabelService | getBookingFlowConfig | response | timesPerPage | enum (8, 12, 24, all) |  | Times per page (decided 29 September, rev 3 REV3-1). (default 24)
WhiteLabelService | getBookingFlowConfig | response | dayPartFilter | boolean |  | Morning, afternoon and evening chips with counts above the times (decided 29 September, rev 3 REV3-1). (default True)
WhiteLabelService | getBookingFlowConfig | response | dayPartBoundaries | object |  | Where the day parts divide, in the venue's time zone (decided 29 September, rev 3 REV3-1).
WhiteLabelService | getBookingFlowConfig | response | dayPartBoundaries.afternoonStartsAt | string |  | (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; default 12:00)
WhiteLabelService | getBookingFlowConfig | response | dayPartBoundaries.eveningStartsAt | string |  | (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; default 17:00)
WhiteLabelService | getBookingFlowConfig | response | seatViewPosition | enum (bottom, right, left, top) |  | Where the view-from-your-seat box sits around the seat map (decided 29 September, rev 3 REV3-5). (default bottom)
WhiteLabelService | getBookingFlowConfig | response | seatTimeBar | boolean |  | Time bar above the seat map (decided 29 September, rev 3 REV3-6). (default True)
WhiteLabelService | getBookingFlowConfig | response | ticketCategories | enum (categoryThenSubcategory, flatList) |  | How tickets are grouped (decided 29 September, rev 3 REV3-16). (default categoryThenSubcategory)
WhiteLabelService | getBookingFlowConfig | response | ticketTags | boolean |  | Tags on tickets (decided 29 September, rev 3 23SEP-3). (default True)
WhiteLabelService | getBookingFlowConfig | response | cardInfo | boolean |  | Extra info on cards (decided 29 September, rev 3 23SEP-6). (default True)
WhiteLabelService | getBookingFlowConfig | response | conciergeMascot | boolean |  | The concierge as mascot art or a plain button (decided 29 September, rev 3 CFG-5). (default True)
WhiteLabelService | getBookingFlowConfig | response | showInfoOnly | boolean |  | Show info-only products (decided 29 September, rev 3 REV3-14). (default True)
WhiteLabelService | getBookingFlowConfig | response | locationSwitcher | boolean |  | Location switcher (decided 29 September, rev 3 REV3-18). (default False)
WhiteLabelService | getBookingFlowConfig | response | guestContactFields | array of enum (email, mobile, name) |  | What the guest-checkout pop-up asks, and nothing else (decided 29 September, W1). (min items 1; max items 3; default ['email'])
WhiteLabelService | getBookingFlowConfig | response | dateStripDays | integer |  | The date strip (decided 17 September, M17-08). (min 3; max 31; default 7)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides | array of BookingFlowVenueOverride |  | Per-venue overrides, at most one per venue. (max items 200; default [])
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].venueId | string (uuid) | yes | One of the tenant's active venues.
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings | BookingFlowSettings | yes | Every guest booking-flow setting, once.
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.preset | enum (auto, ticketBox, playCentre, venueSite, marketplace, singleEvent, season, custom) |  | L1 Ticket box … L6 Season. (default auto)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.stepIndicator | enum (bar, numbered, dots, segmented, breadcrumb, pills, ticks, none) |  | (default bar)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.cartLayout | enum (sidebarRight, sidebarLeft, slideInRight, slideUpBottom, singleColumn, floatingIcon) |  | floatingIcon is a round basket button with the item count that opens the cart (decided 29 September, rev 3 REV3-10). (default sidebarRight)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.cartSideInRtl | enum (keepRight, mirror) |  | The cart side when the guest reads Arabic or another right-to-left language (decided 29 September, rev 3 REV3-10). (default keepRight)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.cardLayout | enum (stackedRows, splitRows, cardsAcross, posterCards) |  | How ticket and product cards are laid out (decided 29 September, rev 3 DG-6). (default stackedRows)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.cardSize | enum (compact, standard, large, extraLarge) |  | Labels Compact, Standard, Large, Extra large (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.seatPicker | enum (bowl, zonesThenSeats, zonesOnly, seatsOnly) |  | Default bowl, as the prototype has it (decided 29 September, rev 3 CFG-6). (default bowl)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.mapView | enum (2d, 3d) |  | (default 3d)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.density | enum (compact, standard, roomy) |  | Labels Compact, Standard, Roomy, default Compact as the design has it (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.embedMode | enum (fullPage, embedded) |  | embedded hides the hero banner, event page and venue header, for a flow placed inside the venue's own site. (default fullPage)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.heroBanner | boolean |  | (default True)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.searchInBanner | boolean |  | Off by default, as the prototype has it (decided 29 September, rev 3 CFG-6). (default False)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.eventBannerDates | boolean |  | Dates in event banner (decided 29 September, rev 3 23SEP-19). (default False)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.singleEventPage | boolean |  | (default False)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.quantitiesOnAddOns | boolean |  | (default True)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.timesPerPage | enum (8, 12, 24, all) |  | Times per page (decided 29 September, rev 3 REV3-1). (default 24)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.dayPartFilter | boolean |  | Morning, afternoon and evening chips with counts above the times (decided 29 September, rev 3 REV3-1). (default True)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.dayPartBoundaries | object |  | Where the day parts divide, in the venue's time zone (decided 29 September, rev 3 REV3-1).
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.seatViewPosition | enum (bottom, right, left, top) |  | Where the view-from-your-seat box sits around the seat map (decided 29 September, rev 3 REV3-5). (default bottom)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.seatTimeBar | boolean |  | Time bar above the seat map (decided 29 September, rev 3 REV3-6). (default True)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.ticketCategories | enum (categoryThenSubcategory, flatList) |  | How tickets are grouped (decided 29 September, rev 3 REV3-16). (default categoryThenSubcategory)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.ticketTags | boolean |  | Tags on tickets (decided 29 September, rev 3 23SEP-3). (default True)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.cardInfo | boolean |  | Extra info on cards (decided 29 September, rev 3 23SEP-6). (default True)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.conciergeMascot | boolean |  | The concierge as mascot art or a plain button (decided 29 September, rev 3 CFG-5). (default True)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.showInfoOnly | boolean |  | Show info-only products (decided 29 September, rev 3 REV3-14). (default True)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.locationSwitcher | boolean |  | Location switcher (decided 29 September, rev 3 REV3-18). (default False)
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.guestContactFields | array of enum (email, mobile, name) |  | What the guest-checkout pop-up asks, and nothing else (decided 29 September, W1). (min items 1; max items 3; default ['email'])
WhiteLabelService | getBookingFlowConfig | response | venueOverrides[].settings.dateStripDays | integer |  | The date strip (decided 17 September, M17-08). (min 3; max 31; default 7)
WhiteLabelService | getBookingFlowConfig | param (query) | effectiveForVenueId | string (uuid) |  | Return the settings in force at this venue, the tenant's with the venue's override laid over them, and no venueOverrides (decided 29 September, rev 3 CFG-11).
WhiteLabelService | getBrandIdentity | response | logoAssetRef | string (uuid) | yes | The primary logo.
WhiteLabelService | getBrandIdentity | response | logoDarkAssetRef | string (uuid) |  | Used on dark backgrounds. (nullable)
WhiteLabelService | getBrandIdentity | response | logoVariant | enum (light, dark, duotone) |  | Which lockup sits in the nav bar, and whose colours drive the theme (decided 29 September, rev 3 CFG-4). (default light)
WhiteLabelService | getBrandIdentity | response | faviconAssetRef | string (uuid) |  | The browser tab icon for the guest web app. (nullable)
WhiteLabelService | getBrandIdentity | response | splashImageAssetRefs | array of string (uuid) |  | Splash images, shown in order.
WhiteLabelService | getBrandIdentity | response | splashDurationSeconds | integer |  | (min 0; max 10; default 3)
WhiteLabelService | getBrandIdentity | response | splashBackgroundColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getBrandIdentity | response | showLoadingIndicator | boolean |  | (default True)
WhiteLabelService | getBrandIdentity | response | splashChangeScope | object |  | Always buildTime for native apps. (read-only)
WhiteLabelService | getBrandIdentity | response | introVideoAssetRef | string (uuid) |  | The optional intro video (decided 29 September, MOB-5). (nullable)
WhiteLabelService | getBrandIdentity | response | introVideoMode | enum (off, firstLaunch, everyLaunch) |  | When GST-001 plays it full screen. (default off)
WhiteLabelService | getBrandIdentity | response | showPoweredBy | boolean |  | "Powered by TICVAI", a configuration toggle, on by default (Chinmay, 2 October, workbook Q160 and the pre-apply round; consistent with DI-297; CHG-CSA-036). (default True)
CatalogueService | getBundle | response | code | string | yes | (max length 64)
CatalogueService | getBundle | response | name | string | yes | (max length 200)
CatalogueService | getBundle | response | description | string |  | (max length 1000)
CatalogueService | getBundle | response | venueId | string (uuid) | yes
CatalogueService | getBundle | response | kind | BundleKind: enum (fixed, dynamic, mandatory, optional, promotional) | yes
CatalogueService | getBundle | response | price | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | getBundle | response | price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | getBundle | response | price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | getBundle | response | price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | getBundle | response | components | array of BundleComponent | yes | (min items 0)
CatalogueService | getBundle | response | components[].id | string (uuid) |  | Added 20 August. (read-only)
CatalogueService | getBundle | response | components[].variantId | string (uuid) | yes
CatalogueService | getBundle | response | components[].componentKind | BundleComponentKind: enum (admission, fnbMenuItem, retail, addOn, other) |  | What a bundle component entitles the guest to (decided 29 September, MOB-4). (default admission)
CatalogueService | getBundle | response | components[].menuItemId | string (uuid) |  | The F&B menu item a fnbMenuItem component entitles the guest to (decided 29 September, MOB-4): the meal of a *meal combo with admission*. (nullable)
CatalogueService | getBundle | response | components[].redeemAtOutletIds | array of string (uuid) |  | Outlets that redeem an fnbMenuItem component; empty means any outlet of the component's venue that has the menu item on a live menu (MOB-4). (max items 20)
CatalogueService | getBundle | response | components[].quantity | integer | yes | (min 1)
CatalogueService | getBundle | response | components[].isOptional | boolean |  | (default False)
CatalogueService | getBundle | response | components[].substituteVariantIds | array of string (uuid) |  | For dynamic bundles — guest chooses among these.
CatalogueService | getBundle | response | components[].substitutionTriggers | array of enum (soldOut, capacityExhausted, productSuspended, venueClosed, externalApiUnavailable, inventoryBelowThreshold) |  | When a substitute from substituteVariantIds may replace this component (Dynamic Component Substitution Engine). (nullable)
CatalogueService | getBundle | response | components[].substitutionPriceEffect | enum (samePrice, surcharge, reducedPrice) |  | What a substitution does to the bundle price. (default samePrice)
CatalogueService | getBundle | response | components[].substitutionApproval | enum (none, customer, operator) |  | Who must accept a substitution before it stands. (default customer)
CatalogueService | getBundle | response | components[].venueId | string (uuid) |  | Where this component is redeemed. (nullable)
CatalogueService | getBundle | response | choiceGroups | array of BundleChoiceGroup |  | Dynamic bundles (3.5.10).
CatalogueService | getBundle | response | choiceGroups[].id | string (uuid) |  | (read-only)
CatalogueService | getBundle | response | choiceGroups[].label | string | yes | What the guest is asked.
CatalogueService | getBundle | response | choiceGroups[].choose | integer | yes | How many options the guest picks. (min 1)
CatalogueService | getBundle | response | choiceGroups[].allowDuplicates | boolean |  | Whether the same option may be picked twice. (default False)
CatalogueService | getBundle | response | choiceGroups[].options | array of object | yes | The rows of promotions.bundle_choice_option, one per option, each keyed to its group. (min items 2)
CatalogueService | getBundle | response | choiceGroups[].options[].id | string (uuid) |  | (read-only)
CatalogueService | getBundle | response | choiceGroups[].options[].variantId | string (uuid) | yes
CatalogueService | getBundle | response | choiceGroups[].options[].quantity | integer |  | (default 1)
CatalogueService | getBundle | response | choiceGroups[].options[].isDefault | boolean |  | (default False)
CatalogueService | getBundle | response | choiceGroups[].unavailableBehaviour | enum (hideOption, hideBundle) |  | An option that has sold out for the chosen date is not offered. (default hideOption)
CatalogueService | getBundle | response | allocation | object | yes
CatalogueService | getBundle | response | allocation.method | object | yes | Proportional to list price by default. (default proRataListPrice)
CatalogueService | getBundle | response | allocation.components | array of AllocationComponent | yes
CatalogueService | getBundle | response | allocation.components[].id | string (uuid) |  | Added 20 August. (read-only)
CatalogueService | getBundle | response | allocation.components[].variantId | string (uuid) | yes
CatalogueService | getBundle | response | allocation.components[].percentage | number |  | (min 0; max 100)
CatalogueService | getBundle | response | allocation.components[].fixedAmount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | getBundle | response | allocation.components[].listPrice | object |  | For proRataListPrice — weights derived from list prices.
CatalogueService | getBundle | response | allocation.components[].revenueAccountId | string (uuid)
CatalogueService | getBundle | response | allocation.components[].legalEntityId | string (uuid) |  | Set where the component is earned by a different legal entity. (nullable)
CatalogueService | getBundle | response | allocation.components[].venueId | string (uuid) |  | (nullable)
CatalogueService | getBundle | response | validFrom | string (date-time)
CatalogueService | getBundle | response | validTo | string (date-time)
CatalogueService | getBundle | response | campaignId | string (uuid) |  | The commercial campaign (promotions.campaign) the bundle is sold under. (nullable)
CatalogueService | getBundle | response | ownerPrincipalId | string (uuid) |  | The bundle owner (Bundle Definition & Setup). (nullable)
CatalogueService | getBundle | response | category | string |  | The bundle category the setup screen files it under. (max length 100; nullable)
CatalogueService | getBundle | response | isStandaloneProduct | boolean |  | Whether the bundle appears as a product in its own right, or only as an offer on another product. (default True)
CatalogueService | getBundle | response | isRecommendedAtCheckout | boolean |  | Whether checkout recommends the bundle. (default False)
CatalogueService | getBundle | response | requiredVariantIds | array of string (uuid) |  | Products that must already be in the basket for the bundle to be sold (the setup screen's "requires another product"). (nullable)
CatalogueService | getBundle | response | id | string (uuid) | yes
CatalogueService | getBundle | response | savingsAmount | object | yes | Sum of component list prices less the bundle price.
CatalogueService | getBundle | response | savingsAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | getBundle | response | savingsAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | getBundle | response | savingsAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | getBundle | response | savingsPercentage | number
CatalogueService | getBundle | response | hasBeenSold | boolean | yes | True locks components and allocation against amendment.
CatalogueService | getBundle | response | isActive | boolean | yes
CatalogueService | getBundle | param (path) | bundleId | string (uuid) | yes
OrderService | getCart | response | id | string (uuid) | yes
OrderService | getCart | response | token | string |  | How an anonymous guest returns to their cart, including from a recovery email. (read-only)
OrderService | getCart | response | venueId | string (uuid) | yes
OrderService | getCart | response | channel | SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) | yes | Where a sale came from.
OrderService | getCart | response | subjectId | string (uuid) |  | Null while anonymous. (nullable)
OrderService | getCart | response | status | CartStatus: enum (active, expiring, expired, abandoned, checkedOut) | yes
OrderService | getCart | response | lines | array of CartLine | yes
OrderService | getCart | response | lines[].id | string (uuid) | yes
OrderService | getCart | response | lines[].variantId | string (uuid) | yes
OrderService | getCart | response | lines[].productName | string |  | (read-only)
OrderService | getCart | response | lines[].quantity | integer | yes | (min 1)
OrderService | getCart | response | lines[].performanceId | string (uuid) |  | (nullable)
OrderService | getCart | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | getCart | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | getCart | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | getCart | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | getCart | response | lines[].tableReservationId | string (uuid) |  | Set on a table deposit line only (decided 29 September, rev 3 REV3-8b): the fnb.TableReservation this line secures. (nullable)
OrderService | getCart | response | lines[].seatIds | array of string (uuid) |  | (max items 50)
OrderService | getCart | response | lines[].resourceHoldId | string (uuid) |  | The resources.ResourceHold this line buys (decided 29 September, rev 3 REV3-15). (nullable)
OrderService | getCart | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | getCart | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | getCart | response | lines[].parentLineId | string (uuid) |  | The line this add-on is attached to, from AddCartLineRequest.parentLineId. (nullable)
OrderService | getCart | response | lines[].overridePrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getCart | response | lines[].overridePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCart | response | lines[].overridePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCart | response | lines[].overridePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCart | response | lines[].overrideReason | enum (priceMatch, serviceRecovery, negotiated, damagedGoods, staffSale, error) |  | BL-085. (nullable)
OrderService | getCart | response | lines[].feeKind | enum (booking, transaction, service, delivery, convenience, cancellation) |  | A fee is a line, not an adjustment. (nullable)
OrderService | getCart | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getCart | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCart | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCart | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCart | response | lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getCart | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCart | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCart | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCart | response | lines[].inventoryHoldId | string |  | The capacity held for this line — a catalogue.InventoryHold.id, typed as that id is. (nullable)
OrderService | getCart | response | lines[].leaseExpiresAt | string (date-time) |  | Shown to the guest. (nullable)
OrderService | getCart | response | lines[].isAvailable | boolean |  | Re-checked on every read. (read-only)
OrderService | getCart | response | conflicts | array of CartConflict
OrderService | getCart | response | conflicts[].kind | enum (overlappingTime, sameSessionDifferentVenue, exceedsPartySize, requiresPrerequisite, consentBlocksBooking)
OrderService | getCart | response | conflicts[].lineIds | array of string (uuid)
OrderService | getCart | response | conflicts[].message | string
OrderService | getCart | response | conflicts[].isBlocking | boolean |  | Most are not.
OrderService | getCart | response | consentQuestions | array of object |  | The consent questions this cart's products and flow ask (decided 29 September, rev 3 REV3-26), computed on read at their current version as the union of each line's published booking flow's white-lab… (read-only)
OrderService | getCart | response | consentQuestions[].id | string (uuid) | yes | (read-only)
OrderService | getCart | response | consentQuestions[].kind | ConsentQuestionKind: enum (swim, scuba, risk, custom) | yes | What the question is about (decided 29 September, rev 3 REV3-26).
OrderService | getCart | response | consentQuestions[].text | object | yes | The question as the guest reads it, per locale.
OrderService | getCart | response | consentQuestions[].helpText | object |  | (nullable)
OrderService | getCart | response | consentQuestions[].version | integer | yes | Raised by one each time the question changes (updateConsentQuestion). (min 1; read-only)
OrderService | getCart | response | consentQuestions[].scope | enum (perPerson, perBooking) | yes | Asked for each declared person, or once for the whole booking. (default perPerson)
OrderService | getCart | response | consentQuestions[].required | boolean | yes | Checkout waits until it is answered (orders.checkoutCart 422 consentRequired). (default True)
OrderService | getCart | response | consentQuestions[].blockingAnswer | enum (yes, no, none) | yes | The answer that stops the booking, for the person or the booking it covers. (default none)
OrderService | getCart | response | consentQuestions[].status | enum (active, retired) | yes | (default active)
OrderService | getCart | response | consentQuestions[].scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | getCart | response | consentQuestions[].updatedAt | string (date-time) |  | (read-only)
OrderService | getCart | response | consentQuestions[].lineIds | array of string (uuid) |  | The cart lines that ask it.
OrderService | getCart | response | consentQuestions[].answered | boolean |  | Every person (for perPerson) or the booking (for perBooking) has an answer.
OrderService | getCart | response | subtotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getCart | response | subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCart | response | subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCart | response | subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCart | response | discountTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getCart | response | discountTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCart | response | discountTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCart | response | discountTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCart | response | taxTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getCart | response | taxTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCart | response | taxTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCart | response | taxTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCart | response | total | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getCart | response | total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCart | response | total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCart | response | total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCart | response | appliedPromotionIds | array of string (uuid) |  | Re-evaluated on every read.
OrderService | getCart | response | couponCodes | array of string |  | The promo codes the guest entered through applyCartPromoCode (decided 28 September, audit R073 (e)). (read-only)
OrderService | getCart | response | expiresAt | string (date-time) |  | The earliest lease expiry in the cart, or the cart's own window where it holds none.
OrderService | getCart | response | extensionsUsed | integer |  | (read-only)
OrderService | getCart | response | maxExtensions | integer |  | (read-only)
OrderService | getCart | response | locale | string
OrderService | getCart | response | createdAt | string (date-time)
OrderService | getCart | response | updatedAt | string (date-time)
OrderService | getCart | param (path) | cartId | string (uuid) | yes
OrderService | getCart | param (header) | X-Consistency-Token | string |  | Opaque token returned by a prior write: the database instance and its WAL LSN (SD-025, 29 September; ADR-0040 allows several instances per region, so an LSN alone is ambiguous).
MarketingService | getCookieConsentRuntime | response | banner | CookieBannerPreferenceCenterDesignerView | yes | One version of a cookie banner and preference-centre design (pack 17.1.6).
MarketingService | getCookieConsentRuntime | response | banner.id | string (uuid) |  | (read-only)
MarketingService | getCookieConsentRuntime | response | banner.brandId | string (uuid) |  | Null for the corporate design every brand inherits. (nullable)
MarketingService | getCookieConsentRuntime | response | banner.inheritsFromId | string (uuid) |  | (nullable)
MarketingService | getCookieConsentRuntime | response | banner.channel | enum (b2cWebsite, customerPortal, mobileApp, embeddedCheckout, whiteLabelSite, partnerMicrosite) | yes
MarketingService | getCookieConsentRuntime | response | banner.logoAssetId | string (uuid) |  | (nullable)
MarketingService | getCookieConsentRuntime | response | banner.title | LocalisedText |  | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | getCookieConsentRuntime | response | banner.body | LocalisedText |  | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | getCookieConsentRuntime | response | banner.position | enum (top, bottom, popup, modal) | yes
MarketingService | getCookieConsentRuntime | response | banner.themeId | string |  | The white-label theme it takes colours and fonts from. (nullable)
MarketingService | getCookieConsentRuntime | response | banner.buttons | array of object
MarketingService | getCookieConsentRuntime | response | banner.buttons[].action | enum (acceptAll, rejectNonEssential, managePreferences, savePreferences, doNotSellOrShare) | yes
MarketingService | getCookieConsentRuntime | response | banner.buttons[].label | LocalisedText |  | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | getCookieConsentRuntime | response | banner.rejectIsOneClick | boolean | yes | Must be true. (default True)
MarketingService | getCookieConsentRuntime | response | banner.links | array of object
MarketingService | getCookieConsentRuntime | response | banner.links[].label | LocalisedText | yes | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | getCookieConsentRuntime | response | banner.links[].policyKind | enum (privacy, cookie, termsAndConditions) | yes
MarketingService | getCookieConsentRuntime | response | banner.categories | array of object | yes | (min items 1)
MarketingService | getCookieConsentRuntime | response | banner.categories[].category | enum (strictlyNecessary, functional, analytics, personalisation, marketing) | yes
MarketingService | getCookieConsentRuntime | response | banner.categories[].description | LocalisedText |  | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | getCookieConsentRuntime | response | banner.categories[].defaultOn | boolean | yes | True only for strictlyNecessary, which is always active.
MarketingService | getCookieConsentRuntime | response | banner.languages | array of string | yes | Every language the storefront serves; Arabic renders right to left. (min items 1)
MarketingService | getCookieConsentRuntime | response | banner.regulatoryRegimes | array of enum (gdpr, ePrivacy, ccpaCpra, lgpd, uaePdpl, saudiPdpl) |  | 2.6.60 (29 September, build).
MarketingService | getCookieConsentRuntime | response | banner.recordIpAddress | boolean |  | 2.6.55, "if legally permitted" (29 September, build). (default False)
MarketingService | getCookieConsentRuntime | response | banner.noticeVersion | string |  | Moves with the cookie policy (white-label setPolicy, kind cookie). (read-only)
MarketingService | getCookieConsentRuntime | response | banner.version | integer |  | (min 1; read-only)
MarketingService | getCookieConsentRuntime | response | banner.status | enum (draft, published, superseded) |  | (read-only)
MarketingService | getCookieConsentRuntime | response | banner.scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | getCookieConsentRuntime | response | banner.updatedAt | string (date-time) |  | (read-only)
MarketingService | getCookieConsentRuntime | response | noticeVersion | string | yes
MarketingService | getCookieConsentRuntime | response | requiresDecision | boolean | yes | True with no decision, an expired one, or one given against a superseded notice.
MarketingService | getCookieConsentRuntime | response | decision | object |  | The latest decision for the presented key; null without a key. (nullable)
MarketingService | getCookieConsentRuntime | response | decision.id | string (uuid) |  | (read-only)
MarketingService | getCookieConsentRuntime | response | decision.consentKey | string | yes | Opaque, minted by us, not a device fingerprint. (max length 64; read-only)
MarketingService | getCookieConsentRuntime | response | decision.channel | CookieConsentChannel: enum (b2cWebsite, customerPortal, mobileApp, embeddedCheckout, whiteLabelSite, partnerMicrosite) | yes | The six governed surfaces, as the registry and the banner design name them (pack 17.1.5-17.1.6).
MarketingService | getCookieConsentRuntime | response | decision.brandId | string (uuid) |  | (nullable)
MarketingService | getCookieConsentRuntime | response | decision.bannerDesignId | string (uuid) |  | The published CookieBannerPreferenceCenterDesignerView version the visitor was shown. (nullable)
MarketingService | getCookieConsentRuntime | response | decision.action | DeviceConsentAction: enum (acceptAll, rejectNonEssential, savePreferences, withdraw, doNotSellOrShare) | yes | What the visitor pressed.
MarketingService | getCookieConsentRuntime | response | decision.categories | array of object | yes | Every category of the design, with the decision this row gives it. (min items 1)
MarketingService | getCookieConsentRuntime | response | decision.categories[].category | CookieCategory: enum (strictlyNecessary, functional, analytics, personalisation, marketing) | yes | 2.6.53.
MarketingService | getCookieConsentRuntime | response | decision.categories[].decision | enum (granted, declined) | yes
MarketingService | getCookieConsentRuntime | response | decision.noticeVersion | string | yes | The cookie notice version decided against (white-label setPolicy, kind cookie).
MarketingService | getCookieConsentRuntime | response | decision.language | string |  | (max length 10; nullable)
MarketingService | getCookieConsentRuntime | response | decision.globalPrivacyControl | boolean |  | The browser sent a Global Privacy Control signal; honoured as a CCPA/CPRA opt-out of sale and sharing. (default False)
MarketingService | getCookieConsentRuntime | response | decision.source | ConsentSource: enum (guestApp, website, kiosk, pos, callCentre, import, agentRecorded, cookieBanner, …) |  | checkout (30 September, M18-15): an opt-in ticked beside the terms at checkout, carried on orders checkoutCart marketingConsents[] and recorded by recordCheckoutConsents, bound to the order and the v…
MarketingService | getCookieConsentRuntime | response | decision.country | string |  | The edge's geolocation of the request, for the geographic statistics (2.6.63). (pattern ^[A-Z]{2}$; read-only; nullable)
MarketingService | getCookieConsentRuntime | response | decision.decidedAt | string (date-time) | yes
MarketingService | getCookieConsentRuntime | response | decision.expiresAt | string (date-time) |  | A device consent expires and a subject consent does not. (read-only; nullable)
MarketingService | getCookieConsentRuntime | response | decision.claimedBySubjectId | string (uuid) |  | Set once, by claimDeviceConsent. (read-only; nullable)
MarketingService | getCookieConsentRuntime | response | decision.claimedAt | string (date-time) |  | (read-only; nullable)
MarketingService | getCookieConsentRuntime | response | decision.scopePath | string |  | The partition key (ADR-0005), tenant-scoped: a decision with no subject still belongs to one tenant. (read-only)
MarketingService | getCookieConsentRuntime | response | allowedTechnologies | array of object | yes | Per category, the approved technologies it unlocks.
MarketingService | getCookieConsentRuntime | response | allowedTechnologies[].category | CookieCategory: enum (strictlyNecessary, functional, analytics, personalisation, marketing) | yes | 2.6.53.
MarketingService | getCookieConsentRuntime | response | allowedTechnologies[].granted | boolean |  | Whether the presented decision grants it; always true for strictlyNecessary.
MarketingService | getCookieConsentRuntime | response | allowedTechnologies[].technologies | array of object | yes
MarketingService | getCookieConsentRuntime | response | allowedTechnologies[].technologies[].name | string | yes
MarketingService | getCookieConsentRuntime | response | allowedTechnologies[].technologies[].provider | string | yes
MarketingService | getCookieConsentRuntime | response | allowedTechnologies[].technologies[].technologyType | string
MarketingService | getCookieConsentRuntime | response | consentModeSignals | object | yes | The decision in Google consent-mode terms (2.6.65), so Analytics and Tag Manager are told, not left to guess.
MarketingService | getCookieConsentRuntime | response | consentModeSignals.adStorage | enum (granted, denied)
MarketingService | getCookieConsentRuntime | response | consentModeSignals.adUserData | enum (granted, denied)
MarketingService | getCookieConsentRuntime | response | consentModeSignals.adPersonalization | enum (granted, denied)
MarketingService | getCookieConsentRuntime | response | consentModeSignals.analyticsStorage | enum (granted, denied)
MarketingService | getCookieConsentRuntime | response | consentModeSignals.functionalityStorage | enum (granted, denied)
MarketingService | getCookieConsentRuntime | response | consentModeSignals.personalizationStorage | enum (granted, denied)
MarketingService | getCookieConsentRuntime | response | consentModeSignals.securityStorage | enum (granted)
MarketingService | getCookieConsentRuntime | param (query) | channel | CookieConsentChannel: enum (b2cWebsite, customerPortal, mobileApp, embeddedCheckout, whiteLabelSite, partnerMicrosite) | yes
MarketingService | getCookieConsentRuntime | param (query) | brandId | string (uuid)
MarketingService | getCookieConsentRuntime | param (query) | language | string |  | One of the design's languages; the tenant's default where omitted
MarketingService | getCookieConsentRuntime | param (header) | X-Consent-Key | string |  | The key the visitor's browser or app holds, if any
CatalogueService | getCouponCode | response | code | string | yes
CatalogueService | getCouponCode | response | campaignId | string (uuid) | yes
CatalogueService | getCouponCode | response | batchId | string (uuid) |  | The generateCouponCodes batch that issued this code. (nullable)
CatalogueService | getCouponCode | response | status | CouponStatus: enum (issued, assigned, redeemed, expired, voided) | yes
CatalogueService | getCouponCode | response | assignedSubjectId | string (uuid) |  | (nullable)
CatalogueService | getCouponCode | response | redemptionCount | integer
CatalogueService | getCouponCode | response | maxRedemptions | integer
CatalogueService | getCouponCode | response | discount | Discount
CatalogueService | getCouponCode | response | discount.kind | DiscountKind: enum (percentage, fixedAmount, fixedPrice, buyXGetY, freeItem, tieredPercentage) | yes
CatalogueService | getCouponCode | response | discount.percentage | number |  | (min 0; max 100)
CatalogueService | getCouponCode | response | discount.amount | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | getCouponCode | response | discount.amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | getCouponCode | response | discount.amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | getCouponCode | response | discount.amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | getCouponCode | response | discount.fixedPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | getCouponCode | response | discount.fixedPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | getCouponCode | response | discount.fixedPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | getCouponCode | response | discount.fixedPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | getCouponCode | response | discount.buyQuantity | integer |  | (min 1)
CatalogueService | getCouponCode | response | discount.getQuantity | integer |  | (min 1)
CatalogueService | getCouponCode | response | discount.getDiscountPercentage | number |  | 100 makes the free items actually free; lower values give a partial discount. (min 0; max 100)
CatalogueService | getCouponCode | response | discount.tiers | array of object |  | For tieredPercentage — more units, larger discount.
CatalogueService | getCouponCode | response | discount.tiers[].minQuantity | integer | yes | (min 1)
CatalogueService | getCouponCode | response | discount.tiers[].percentage | number | yes | (min 0; max 100)
CatalogueService | getCouponCode | response | discount.maxDiscountAmount | object |  | Cap on a percentage discount.
CatalogueService | getCouponCode | response | discount.maxDiscountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | getCouponCode | response | discount.maxDiscountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | getCouponCode | response | discount.maxDiscountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | getCouponCode | response | discount.rewardVariantIds | array of string (uuid) |  | The reward products, where the reward is not the qualifying product: the free gift of freeItem, the "different product" of a buyXGetY (createPromotion; the builders setGiftFreeProduct and setBuyGetBo… (nullable)
CatalogueService | getCouponCode | response | discount.maxApplicationsPerBasket | integer |  | How many times the offer repeats in one basket: the "maximum repetitions" of an N-for-X offer (createPromotion; setFixedPriceOffer was retired in r2, CHG-CLN-001). (min 1; nullable)
CatalogueService | getCouponCode | response | invalidReason | enum (expired, alreadyRedeemed, voided, notYetValid, wrongVenue, conditionsNotMet, notAssignedToGuest) |  | Why the code cannot be applied. (nullable)
CatalogueService | getCouponCode | response | validFrom | string (date-time) |  | (nullable)
CatalogueService | getCouponCode | response | validTo | string (date-time) |  | (nullable)
CatalogueService | getCouponCode | response | redeemedAt | string (date-time) |  | (nullable)
CatalogueService | getCouponCode | response | redeemedOrderId | string |  | (nullable)
CatalogueService | getCouponCode | response | scopePath | string |  | The partition key (ADR-0005).
CatalogueService | getCouponCode | response | assignmentId | string (uuid) |  | The CouponCodeAssignment that assigned this code (4 October 2026, CHG-FXC-005). (read-only; nullable)
CatalogueService | getCouponCode | response | distributionStatus | enum (pending, sent, delivered, viewed, cancelled) |  | How far the code got to its holder (4 October 2026, CHG-FXC-005). (read-only; nullable)
CatalogueService | getCouponCode | param (path) | code | string | yes
FnbService | getCourseRules | response | outletId | string (uuid) |  | The outlet in the path. (read-only)
FnbService | getCourseRules | response | defaultCoursing | CoursingPolicy: enum (fireAndForget, holdAndFire, phased, timed, delayed) |  | How a ticket's courses are fired.
FnbService | getCourseRules | response | courseNames | array of string
FnbService | getCourseRules | response | autoFireMinutes | integer |  | (nullable)
FnbService | getCourseRules | response | serviceModeOverrides | object |  | A different default per service mode.
FnbService | getCourseRules | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
FnbService | getCourseRules | param (path) | outletId | string (uuid) | yes
IdentityService | getCurrentSession | response | sessionId | string (uuid) | yes
IdentityService | getCurrentSession | response | principalId | string (uuid) | yes
IdentityService | getCurrentSession | response | roleId | string (uuid) | yes
IdentityService | getCurrentSession | response | displayName | string
IdentityService | getCurrentSession | response | scope | array of ScopeRef | yes | Scope nodes this session may act within, resolved once at login from the ltree hierarchy with deny-overrides-allow.
IdentityService | getCurrentSession | response | scope[].id | string (uuid) | yes
IdentityService | getCurrentSession | response | scope[].level | ScopeLevel: enum (tenant, brand, region, venue, department, subDepartment, workstation, outlet, …) | yes | The eight organisational levels, plus subject.
IdentityService | getCurrentSession | response | scope[].path | string | yes | Materialised ltree path.
IdentityService | getCurrentSession | response | scope[].code | string |  | (nullable)
IdentityService | getCurrentSession | response | scope[].name | string |  | (nullable)
IdentityService | getCurrentSession | response | effectivePermissions | object | yes | Flattened set across all granted scopes, after deny resolution.
IdentityService | getCurrentSession | response | permissionsByScope | array of ScopedPermissions |  | Permissions effective at each granted scope path.
IdentityService | getCurrentSession | response | permissionsByScope[].scopePath | string | yes | (pattern ^[a-z0-9_]+(\.[a-z0-9_]+)*$)
IdentityService | getCurrentSession | response | permissionsByScope[].permissions | array of Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) | yes
IdentityService | getCurrentSession | response | saleBoardId | string (uuid) |  | Landing surface, derived from the WORKSTATION, not the role (12 Aug 2026 §3).
IdentityService | getCurrentSession | response | workstation | WorkstationContext
IdentityService | getCurrentSession | response | workstation.id | string (uuid) | yes
IdentityService | getCurrentSession | response | workstation.code | string | yes
IdentityService | getCurrentSession | response | workstation.venueId | string (uuid) | yes
IdentityService | getCurrentSession | response | workstation.regionId | string (uuid) | yes
IdentityService | getCurrentSession | response | workstation.accessPointId | string (uuid) |  | Inherited from the workstation, never selected by the operator.
IdentityService | getCurrentSession | response | workstation.devices | array of object
IdentityService | getCurrentSession | response | workstation.devices[].kind | enum (receiptPrinter, ticketPrinter, cashDrawer, barcodeScanner, rfidReader, paymentTerminal, customerDisplay) | yes
IdentityService | getCurrentSession | response | workstation.devices[].driver | string | yes
IdentityService | getCurrentSession | response | workstation.devices[].identifier | string
IdentityService | getCurrentSession | response | workstation.currency | string |  | (pattern ^[A-Z]{3}$)
IdentityService | getCurrentSession | response | workstation.currencyScale | integer |  | (min 0; max 4)
IdentityService | getCurrentSession | response | workstation.timezone | string
IdentityService | getCurrentSession | response | workstation.cellName | string |  | The cell serving this workstation's region.
IdentityService | getCurrentSession | response | workstation.deploymentProfile | enum (terminalLocal, venueEdge, thin) |  | Whether this surface reads catalogue locally (ADR-0013).
IdentityService | getCurrentSession | response | openedAt | string (date-time)
IdentityService | getCurrentSession | response | expiresAt | string (date-time)
OrderService | getCurrentShift | response | id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | getCurrentShift | response | workstationId | string (uuid) | yes
OrderService | getCurrentShift | response | venueId | string (uuid) | yes
OrderService | getCurrentShift | response | scopePath | string | yes
OrderService | getCurrentShift | response | principalId | string (uuid) | yes | Who opened it.
OrderService | getCurrentShift | response | principalDisplayName | string
OrderService | getCurrentShift | response | incidents | array of object |  | BL-097.
OrderService | getCurrentShift | response | incidents[].kind | enum (noSale, drawerOpen, override, voidAfterPayment, guestDispute, tillJam, priceQuery, other)
OrderService | getCurrentShift | response | incidents[].at | string (date-time)
OrderService | getCurrentShift | response | incidents[].principalId | string (uuid)
OrderService | getCurrentShift | response | incidents[].note | string |  | (nullable)
OrderService | getCurrentShift | response | status | ShiftStatus: enum (pendingApproval, open, suspended, pendingVariance, pendingClosure, closed, autoClosed) | yes
OrderService | getCurrentShift | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | getCurrentShift | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | getCurrentShift | response | depositBoxCode | string |  | (nullable)
OrderService | getCurrentShift | response | bagNumber | string |  | (nullable)
OrderService | getCurrentShift | response | openingFloat | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getCurrentShift | response | openingFloat.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCurrentShift | response | openingFloat.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCurrentShift | response | openingFloat.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCurrentShift | response | salesTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getCurrentShift | response | salesTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCurrentShift | response | salesTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCurrentShift | response | salesTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCurrentShift | response | refundsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getCurrentShift | response | refundsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCurrentShift | response | refundsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCurrentShift | response | refundsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCurrentShift | response | liftsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getCurrentShift | response | liftsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCurrentShift | response | liftsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCurrentShift | response | liftsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCurrentShift | response | expectedCash | object |  | 26 September, pull audit R207. (read-only; nullable)
OrderService | getCurrentShift | response | expectedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCurrentShift | response | expectedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCurrentShift | response | expectedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCurrentShift | response | countedCash | object |  | What the close count found. (read-only; nullable)
OrderService | getCurrentShift | response | countedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCurrentShift | response | countedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCurrentShift | response | countedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCurrentShift | response | variance | object |  | Counted minus expected, as ShiftCloseResult.variance. (read-only; nullable)
OrderService | getCurrentShift | response | variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getCurrentShift | response | variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getCurrentShift | response | variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getCurrentShift | response | cashierReason | enum (tillError, unrecordedRefund, miscount, other) |  | What the cashier said went wrong, given with the blind count (CloseShiftRequest.cashierReason, DI-803) without seeing the variance; the supervisor reads it beside the variance on BO-040 (CHG-FIN-003). (read-only; nullable)
OrderService | getCurrentShift | response | cashierNote | string |  | The cashier's note with the count (CloseShiftRequest.notes; CHG-FIN-003). (max length 1000; read-only; nullable)
OrderService | getCurrentShift | response | varianceReasonRequired | boolean |  | Computed, not stored (CHG-R4-019): true while the shift is pendingClosure because its count differs from the expected figure within the threshold and no cashierReason is recorded. (read-only)
OrderService | getCurrentShift | response | heldLeaseCount | integer |  | Inventory leases currently held by this workstation.
OrderService | getCurrentShift | response | openedAt | string (date-time) | yes
OrderService | getCurrentShift | response | businessDate | string (date) |  | The business day the shift belongs to (12 October 2026, CHG-R6-032): the venue-local date of openedAt taken against the venue's businessDayCutoff (tenancy VenueSettings, inheriting the tenant default… (read-only)
OrderService | getCurrentShift | response | recordedAt | string (date-time) |  | When the device recorded the open.
OrderService | getCurrentShift | response | suspendedAt | string (date-time) |  | (nullable)
OrderService | getCurrentShift | response | suspendReason | string |  | The reason given to suspendShift. (max length 200; nullable)
OrderService | getCurrentShift | response | closedAt | string (date-time) |  | (nullable)
OrderService | getCurrentShift | response | closedByPrincipalId | string (uuid) |  | Who submitted the close count. (nullable)
OrderService | getCurrentShift | response | recountRequestedAt | string (date-time) |  | Set by rejectShiftVariance, cleared by the cashier's recount (decided 2 October 2026, Chinmay; DEC-175; CHG-CSP-013; DI-804). (read-only; nullable)
OrderService | getCurrentShift | response | recountRequestedByPrincipalId | string (uuid) |  | The supervisor who sent the count back (CHG-CSP-013). (read-only; nullable)
OrderService | getCurrentShift | response | recountReason | string |  | The supervisor's reason, shown to the cashier; never an amount (CHG-CSP-013, CHG-FIN-003). (max length 500; read-only; nullable)
OrderService | getCurrentShift | response | countNumber | integer |  | How many close counts the shift has had: 0 before the first, 1 after it, 2 after a recount (CHG-CSP-013). (min 0; read-only)
OrderService | getCurrentShift | response | syncedAt | string (date-time) |  | Null while the shift has unsynced operations. (nullable)
OrderService | getCurrentShift | response | approvals | array of object
OrderService | getCurrentShift | response | approvals[].kind | enum (open, close, variance) | yes | open from approveShiftOpen, close from approveShiftClose, variance from acceptShiftVariance.
OrderService | getCurrentShift | response | approvals[].principalId | string (uuid) | yes
OrderService | getCurrentShift | response | approvals[].at | string (date-time) | yes
OrderService | getCurrentShift | response | approvals[].reason | string
ReportingService | getDashboard | response | name | string | yes | (max length 200)
ReportingService | getDashboard | response | module | ModuleKey: enum (core, ticketing, access, fnb, retail, inventory, seating, membership, …) | yes | What a tenant buys, and what a screen belongs to.
ReportingService | getDashboard | response | description | string |  | (max length 1000)
ReportingService | getDashboard | response | venueId | string (uuid) |  | Narrows every tile to one venue.
ReportingService | getDashboard | response | isShared | boolean |  | (default False)
ReportingService | getDashboard | response | tiles | array of DashboardTile | yes | (min items 1; max items 24)
ReportingService | getDashboard | response | tiles[].id | string (uuid) | yes
ReportingService | getDashboard | response | tiles[].title | string
ReportingService | getDashboard | response | tiles[].reportId | string (uuid) | yes
ReportingService | getDashboard | response | tiles[].visualisation | enum (number, line, area, bar, stackedBar, stackedBar100, combo, pie, …) | yes | Extended 22 September from eight marks to twenty against Ticketing_Platform_Native_Dashboard_Visualization_Requirements.pdf, which names eighteen components and marks every one MVP.
ReportingService | getDashboard | response | tiles[].parameters | object |  | Open on purpose, and not yet specified.
ReportingService | getDashboard | response | tiles[].refreshSeconds | integer |  | Minimum thirty seconds. (min 30)
ReportingService | getDashboard | response | tiles[].position | object | yes
ReportingService | getDashboard | response | tiles[].position.row | integer | yes
ReportingService | getDashboard | response | tiles[].position.column | integer | yes
ReportingService | getDashboard | response | tiles[].position.width | integer | yes
ReportingService | getDashboard | response | tiles[].position.height | integer | yes
ReportingService | getDashboard | response | id | string (uuid) | yes
ReportingService | getDashboard | response | ownerPrincipalId | string (uuid) | yes
ReportingService | getDashboard | response | aggregateCost | enum (low, medium, high) | yes | Combined refresh load of every tile.
ReportingService | getDashboard | response | archivedAt | string (date-time) |  | Set by deleteDashboard, which archives rather than removes. (read-only; nullable)
ReportingService | getDashboard | response | createdAt | string (date-time) | yes
ReportingService | getDashboard | response | tileData | array of object
ReportingService | getDashboard | response | tileData[].tileId | string (uuid)
ReportingService | getDashboard | response | tileData[].result | ReportResult
ReportingService | getDashboard | response | tileData[].result.executionId | string | yes
ReportingService | getDashboard | response | tileData[].result.columns | array of object | yes
ReportingService | getDashboard | response | tileData[].result.rows | array of object | yes | Open on purpose; the shape is columns.
ReportingService | getDashboard | response | tileData[].result.totals | object |  | Aggregated columns only, keyed and typed as a row is.
ReportingService | getDashboard | response | tileData[].result.rowCount | integer
ReportingService | getDashboard | response | tileData[].result.nextCursor | string |  | (nullable)
ReportingService | getDashboard | response | tileData[].result.generatedAt | string (date-time)
ReportingService | getDashboard | response | tileData[].result.dataAsOf | string (date-time) |  | Replica position the result was read at.
ReportingService | getDashboard | response | tileData[].isCached | boolean
ReportingService | getDashboard | response | tileData[].error | string |  | (nullable)
ReportingService | getDashboard | param (path) | dashboardId | string (uuid) | yes
ReportingService | getDashboard | param (query) | refresh | boolean |  | Bypass cached tile data.
WhiteLabelService | getDeepLinkScheme | response | baseUrl | string | yes | The primary domain, or the platform subdomain where none is primary.
WhiteLabelService | getDeepLinkScheme | response | patterns | array of object | yes | The patterns, fixed (4 October 2026, CHG-FXC-009).
WhiteLabelService | getDeepLinkScheme | response | patterns[].kind | string | yes | A LinkTarget.kind, or bookingFlow.
WhiteLabelService | getDeepLinkScheme | response | patterns[].pattern | string | yes | e.g.
WhiteLabelService | getDeepLinkScheme | response | appLinksEnabled | boolean
TenancyService | getDeviceAssignment | response | deviceId | string (uuid) |  | From the path of setDeviceAssignment. (read-only)
TenancyService | getDeviceAssignment | response | ownerOrgUnitId | string (uuid) |  | Who the device belongs to — the cost centre that replaces it when it breaks. (nullable)
TenancyService | getDeviceAssignment | response | custodianPrincipalId | string (uuid) |  | Who is holding it right now. (nullable)
TenancyService | getDeviceAssignment | response | assignedWorkstationId | string (uuid) |  | (nullable)
TenancyService | getDeviceAssignment | response | locationScopePath | string |  | (nullable)
TenancyService | getDeviceAssignment | response | lastSeenLocation | string |  | Reported by the heartbeat; distinct from where it is supposed to be. (read-only; nullable)
TenancyService | getDeviceAssignment | response | assetTag | string |  | (nullable)
TenancyService | getDeviceAssignment | response | acquiredAt | string (date) |  | A calendar date in the region's time zone. (nullable)
TenancyService | getDeviceAssignment | response | warrantyExpiresAt | string (date) |  | A calendar date in the region's time zone. (nullable)
TenancyService | getDeviceAssignment | response | assignedAt | string (date-time) |  | (read-only)
TenancyService | getDeviceAssignment | response | scopePath | string |  | (read-only)
TenancyService | getDeviceAssignment | param (path) | deviceId | string (uuid) | yes
MarketingService | getDeviceConsentHistory | response | items | array of DeviceConsent | yes
MarketingService | getDeviceConsentHistory | response | items[].id | string (uuid) |  | (read-only)
MarketingService | getDeviceConsentHistory | response | items[].consentKey | string | yes | Opaque, minted by us, not a device fingerprint. (max length 64; read-only)
MarketingService | getDeviceConsentHistory | response | items[].channel | CookieConsentChannel: enum (b2cWebsite, customerPortal, mobileApp, embeddedCheckout, whiteLabelSite, partnerMicrosite) | yes | The six governed surfaces, as the registry and the banner design name them (pack 17.1.5-17.1.6).
MarketingService | getDeviceConsentHistory | response | items[].brandId | string (uuid) |  | (nullable)
MarketingService | getDeviceConsentHistory | response | items[].bannerDesignId | string (uuid) |  | The published CookieBannerPreferenceCenterDesignerView version the visitor was shown. (nullable)
MarketingService | getDeviceConsentHistory | response | items[].action | DeviceConsentAction: enum (acceptAll, rejectNonEssential, savePreferences, withdraw, doNotSellOrShare) | yes | What the visitor pressed.
MarketingService | getDeviceConsentHistory | response | items[].categories | array of object | yes | Every category of the design, with the decision this row gives it. (min items 1)
MarketingService | getDeviceConsentHistory | response | items[].categories[].category | CookieCategory: enum (strictlyNecessary, functional, analytics, personalisation, marketing) | yes | 2.6.53.
MarketingService | getDeviceConsentHistory | response | items[].categories[].decision | enum (granted, declined) | yes
MarketingService | getDeviceConsentHistory | response | items[].noticeVersion | string | yes | The cookie notice version decided against (white-label setPolicy, kind cookie).
MarketingService | getDeviceConsentHistory | response | items[].language | string |  | (max length 10; nullable)
MarketingService | getDeviceConsentHistory | response | items[].globalPrivacyControl | boolean |  | The browser sent a Global Privacy Control signal; honoured as a CCPA/CPRA opt-out of sale and sharing. (default False)
MarketingService | getDeviceConsentHistory | response | items[].source | ConsentSource: enum (guestApp, website, kiosk, pos, callCentre, import, agentRecorded, cookieBanner, …) |  | checkout (30 September, M18-15): an opt-in ticked beside the terms at checkout, carried on orders checkoutCart marketingConsents[] and recorded by recordCheckoutConsents, bound to the order and the v…
MarketingService | getDeviceConsentHistory | response | items[].country | string |  | The edge's geolocation of the request, for the geographic statistics (2.6.63). (pattern ^[A-Z]{2}$; read-only; nullable)
MarketingService | getDeviceConsentHistory | response | items[].decidedAt | string (date-time) | yes
MarketingService | getDeviceConsentHistory | response | items[].expiresAt | string (date-time) |  | A device consent expires and a subject consent does not. (read-only; nullable)
MarketingService | getDeviceConsentHistory | response | items[].claimedBySubjectId | string (uuid) |  | Set once, by claimDeviceConsent. (read-only; nullable)
MarketingService | getDeviceConsentHistory | response | items[].claimedAt | string (date-time) |  | (read-only; nullable)
MarketingService | getDeviceConsentHistory | response | items[].scopePath | string |  | The partition key (ADR-0005), tenant-scoped: a decision with no subject still belongs to one tenant. (read-only)
MarketingService | getDeviceConsentHistory | response | nextCursor | string
MarketingService | getDeviceConsentHistory | response | hasMore | boolean | yes
MarketingService | getDeviceConsentHistory | param (header) | X-Consent-Key | string | yes | The key the visitor's browser or app holds
MarketingService | getDeviceConsentHistory | param (query) | pageSize | integer
MarketingService | getDeviceConsentHistory | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
AiService | getEffectiveAiPolicy | response | capabilityKey | string | yes
AiService | getEffectiveAiPolicy | response | scopePath | string
AiService | getEffectiveAiPolicy | response | autonomyLevel | integer | yes | One autonomy scale for every capability (design 3.8 and 5.5, GOV 0 to 4; ADR-0050). (min 0; max 4)
AiService | getEffectiveAiPolicy | response | autonomyCeiling | integer |  | One autonomy scale for every capability (design 3.8 and 5.5, GOV 0 to 4; ADR-0050). (min 0; max 4)
AiService | getEffectiveAiPolicy | response | rules | array of object | yes
AiService | getEffectiveAiPolicy | response | rules[].rule | AiGovernanceRule |  | One rule of a governance policy version: which actions on which data, under which conditions, get which outcome (AIC-147..160).
AiService | getEffectiveAiPolicy | response | rules[].rule.effect | AiGovernanceOutcome: enum (allow, allowWithConditions, prepareOnly, approvalRequired, escalate, block) | yes | What the governance decision point returns (design 3.8, AIC-166).
AiService | getEffectiveAiPolicy | response | rules[].rule.capabilityKeys | array of string |  | Registered capabilities it applies to.
AiService | getEffectiveAiPolicy | response | rules[].rule.actions | array of enum (read, analyze, recommend, generate, prepare, create, modify, publish, …) |  | ADM-523: what AI may do, from reading to executing.
AiService | getEffectiveAiPolicy | response | rules[].rule.dataCategories | array of string |  | Data categories (ADM-524), e.g.
AiService | getEffectiveAiPolicy | response | rules[].rule.purposes | array of string |  | Permitted purposes for those categories (AIC-156, AIR-182).
AiService | getEffectiveAiPolicy | response | rules[].rule.maxAmount | object |  | Above this value the effect escalates one step (for example to approvalRequired). (nullable)
AiService | getEffectiveAiPolicy | response | rules[].rule.roleIds | array of string (uuid) |  | Roles the rule applies to; empty means every role.
AiService | getEffectiveAiPolicy | response | rules[].rule.environments | array of enum (development, sandbox, staging, production) |  | ADM-525.
AiService | getEffectiveAiPolicy | response | rules[].rule.conditions | object |  | Conditions attached to an allowWithConditions effect, for example maskFields or requireCitation. (nullable)
AiService | getEffectiveAiPolicy | response | rules[].policyKey | string
AiService | getEffectiveAiPolicy | response | rules[].version | integer
AiService | getEffectiveAiPolicy | response | rules[].scopePath | string
AiService | getEffectiveAiPolicy | response | exceptions | array of AiPolicyException
AiService | getEffectiveAiPolicy | response | exceptions[].id | string (uuid) |  | (read-only)
AiService | getEffectiveAiPolicy | response | exceptions[].policyId | string (uuid) | yes
AiService | getEffectiveAiPolicy | response | exceptions[].capabilityKey | string |  | (nullable)
AiService | getEffectiveAiPolicy | response | exceptions[].reason | string | yes | (max length 2000)
AiService | getEffectiveAiPolicy | response | exceptions[].compensatingControls | array of string
AiService | getEffectiveAiPolicy | response | exceptions[].startsAt | string (date-time) |  | (nullable)
AiService | getEffectiveAiPolicy | response | exceptions[].expiresAt | string (date-time) | yes | Required.
AiService | getEffectiveAiPolicy | response | exceptions[].status | enum (active, expired, revoked) |  | (read-only)
AiService | getEffectiveAiPolicy | response | exceptions[].approvedByPrincipalId | string (uuid) |  | (read-only)
AiService | getEffectiveAiPolicy | response | exceptions[].revokedByPrincipalId | string (uuid) |  | (read-only; nullable)
AiService | getEffectiveAiPolicy | response | exceptions[].revokedAt | string (date-time) |  | (read-only; nullable)
AiService | getEffectiveAiPolicy | response | exceptions[].revokeReason | string |  | (read-only; nullable)
AiService | getEffectiveAiPolicy | response | exceptions[].scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | getEffectiveAiPolicy | response | conflicts | array of object |  | Conflicting rules and the more restrictive result they resolved to (AIC-161).
AiService | getEffectiveAiPolicy | response | conflicts[].description | string
AiService | getEffectiveAiPolicy | response | conflicts[].resolvedTo | AiGovernanceOutcome: enum (allow, allowWithConditions, prepareOnly, approvalRequired, escalate, block) |  | What the governance decision point returns (design 3.8, AIC-166).
AiService | getEffectiveAiPolicy | response | resolvedAt | string (date-time)
AiService | getEffectiveAiPolicy | param (query) | capabilityKey | string | yes
AiService | getEffectiveAiPolicy | param (query) | scopePath | string
AiService | getEffectiveAiPolicy | param (query) | environment | enum (development, sandbox, staging, production)
AccessService | getEntitlement | response | id | string (uuid) | yes | A UUIDv7, matching TicketStatus.ticketId — stable for the life of the ticket and independent of the media carrying it.
AccessService | getEntitlement | response | templateId | string (uuid) | yes | The definition it was issued against.
AccessService | getEntitlement | response | productId | string (uuid) | yes
AccessService | getEntitlement | response | orderId | string (uuid) | yes | The order's id, a UUIDv7 as in /orders/{orderId} (orders.sales_order.id). (nullable)
AccessService | getEntitlement | response | orderLineId | string (uuid)
AccessService | getEntitlement | response | subjectId | string (uuid) | yes | Who holds it. (nullable)
AccessService | getEntitlement | response | venueId | string (uuid)
AccessService | getEntitlement | response | scopePath | string
AccessService | getEntitlement | response | mediaCode | string |  | What is scanned — a QR payload, a wristband serial, a card number.
AccessService | getEntitlement | response | credentialFormat | object |  | The credential this entitlement was issued with, resolved once at issue by issueOrderEntitlements: the product's credentialFormatOverride, else the sales channel's ticketCredentialFormat, else platfo… (nullable)
AccessService | getEntitlement | response | status | EntitlementStatus: enum (issued, partiallyConsumed, fullyConsumed, expired, cancelled, surrendered) | yes | What the storage layer holds, and what a guest is shown.
AccessService | getEntitlement | response | statusNote | string |  | Not TicketStatus — that is a validation result with a misleading name, computed at scan time and carrying isValid and isInsideVenue. (nullable)
AccessService | getEntitlement | response | validFrom | string (date-time) | yes
AccessService | getEntitlement | response | validTo | string (date-time) | yes | Resolved at issue from the template, then owned here.
AccessService | getEntitlement | response | entriesUsed | integer |  | The number validateAccess decrements and nothing was decrementing. (default 0; read-only)
AccessService | getEntitlement | response | entriesAllowed | integer |  | (nullable)
AccessService | getEntitlement | response | lastEntryAt | string (date-time) |  | recordedAt of the latest admission counted in entriesUsed, written by the same writes. (read-only; nullable)
AccessService | getEntitlement | response | firstEntryAt | string (date-time) |  | recordedAt of the first admission, written by the same writes as lastEntryAt; it starts a time-bound entitlement's window (DEC-232; CHG-CSP-030). (read-only; nullable)
AccessService | getEntitlement | response | timeBoundUntil | string (date-time) |  | Where the template is time-bound, when its window closes: firstEntryAt plus the validity rule's minutesAfterFirstScan (decided 2 October 2026, Chinmay, BO-159; DEC-232; CHG-CSP-030). (read-only; nullable)
AccessService | getEntitlement | response | lifecycleLabel | enum (created, pendingFulfillment, active, partiallyUsed, used, expired, suspended, cancelled, …) |  | The Virtual Ticket status in the client's 13 names, mapped onto the entitlement model (decided 2 October 2026, Chinmay, critical set 2, BO-336: "Map the pack's 13 names onto the model; add any missin… (read-only)
AccessService | getEntitlement | response | cancellationKind | enum (voided, refunded, performanceCancelled, superseded) |  | Which act cancelled the entitlement, so the pack's Voided, Refunded and Reissued / superseded are told apart while status keeps the one r1 value cancelled (DEC-266; CHG-CSP-033). (read-only; nullable)
AccessService | getEntitlement | response | frozenDays | integer |  | Days added by a freeze. (default 0; read-only)
AccessService | getEntitlement | response | suspendedReason | string |  | (nullable)
AccessService | getEntitlement | response | freezeReason | enum (travelling, injury, personal, seasonal, other) |  | The reason of the latest freezeEntitlement (audit R222). (nullable)
AccessService | getEntitlement | response | freezeNote | string |  | The note the latest freezeEntitlement took, required there when reason is other (decided 28 September, audit R222). (max length 500; nullable)
AccessService | getEntitlement | response | isNameBound | boolean |  | (default False)
AccessService | getEntitlement | response | holderName | string |  | (nullable)
AccessService | getEntitlement | response | sharedWithSubjectIds | array of string (uuid) |  | shareEntitlement.
AccessService | getEntitlement | response | issuedVia | enum (sale, invitation, reissue, transfer, resale, membership, groupBooking) |  | How it came to exist, and it matters to finance.
AccessService | getEntitlement | response | supersedesEntitlementId | string (uuid) |  | For a reissue or a resale. (nullable)
AccessService | getEntitlement | response | walletValueId | string (uuid) |  | Where the template carries stored value. (nullable)
AccessService | getEntitlement | response | facePassEnrolmentId | string (uuid) |  | The active facePass enrolment on this entitlement (FacePassEnrolment.id), or null when none is. (read-only; nullable)
AccessService | getEntitlement | response | invitationId | string (uuid) |  | The invitation that issued it (4 October 2026, CHG-FXC-007): orders.issueInvitation issues the entitlement without an order, because an invitation never enters the order path. (nullable)
AccessService | getEntitlement | param (path) | entitlementId | string (uuid) | yes
AccessService | getEntitlementCredential | response | mediaCode | string
AccessService | getEntitlementCredential | response | credentialFormat | object |  | The entitlement's credentialFormat; platformSignedQr where it is null (CHG-R6-031).
AccessService | getEntitlementCredential | response | payload | string
AccessService | getEntitlementCredential | response | expiresAt | string (date-time) |  | (nullable)
AccessService | getEntitlementCredential | response | rotation | object |  | The time-based seed the rotating code is derived from (audit R230). (nullable)
AccessService | getEntitlementCredential | response | rotation.secret | string | yes | Base32 shared secret.
AccessService | getEntitlementCredential | response | rotation.timeStepSeconds | integer | yes | 30 seconds for an admission QR (Chinmay, 3 October 2026, Block A business rules: GST-055's admission QR rotates every 30 seconds; CHG-RUL-018). (min 10; max 60; default 30)
AccessService | getEntitlementCredential | response | rotation.digits | integer | yes | (min 6; max 10; default 8)
AccessService | getEntitlementCredential | response | rotation.algorithm | enum (SHA1, SHA256, SHA512) | yes | (default SHA256)
AccessService | getEntitlementCredential | response | rotation.validFrom | string (date-time) | yes
AccessService | getEntitlementCredential | response | rotation.validTo | string (date-time) | yes | The seed stops verifying after this.
AccessService | getEntitlementCredential | param (path) | entitlementId | string (uuid) | yes
AccessService | getEntitlementCredential | param (query) | rotate | boolean
AccessService | getEntitlementHistory | param (path) | entitlementId | string (uuid) | yes
VenueOpsService | getExpiringRights | param (query) | withinDays | integer
AccessService | getFacePassEnrolment | response | id | string (uuid) | yes | (read-only)
AccessService | getFacePassEnrolment | response | subjectId | string (uuid) | yes
AccessService | getFacePassEnrolment | response | entitlementId | string (uuid) | yes | The Entitlement.id, a UUIDv7 (pii.subject_biometric.entitlement_id).
AccessService | getFacePassEnrolment | response | kind | BiometricKind: enum (facePass, faceTag) | yes | BL-106, CF-35.
AccessService | getFacePassEnrolment | response | retentionAnchor | object |  | BL-106.
AccessService | getFacePassEnrolment | response | source | enum (guestApp, ticketCounter, annualPassCounter, entryGate) | yes | entryGate is valid for faceTag only, and 3.2.43's omission of it from Face Pass is deliberate: an enduring enrolment is a considered act with consent attached, not something done in a queue.
AccessService | getFacePassEnrolment | response | enrolmentChannel | enum (guestApp, ticketCounter, annualPassCounter, selfServiceKiosk, entryGate) |  | Where the face was actually captured (decided 2 October 2026, Chinmay, BO-186; DEC-236; CHG-CSP-021): source with selfServiceKiosk told apart. (read-only)
AccessService | getFacePassEnrolment | response | consentFormId | string (uuid) |  | The venue's consent form the capture was consented on, and its version below (DEC-128; CHG-CSP-018). (read-only; nullable)
AccessService | getFacePassEnrolment | response | consentFormVersion | integer |  | (read-only; nullable)
AccessService | getFacePassEnrolment | response | capturedAt | string (date-time) | yes
AccessService | getFacePassEnrolment | response | consentPurposeId | string (uuid)
AccessService | getFacePassEnrolment | response | consentGivenAt | string (date-time)
AccessService | getFacePassEnrolment | response | guardianSubjectId | string (uuid) |  | Where the subject is a minor (3.2.12). (nullable)
AccessService | getFacePassEnrolment | response | isActive | boolean |  | (read-only)
AccessService | getFacePassEnrolment | response | expiresAt | string (date-time) |  | Bounded by whatever retentionAnchor names, and a face outliving it is a biometric held for no stated purpose. (nullable)
AccessService | getFacePassEnrolment | param (path) | enrolmentId | string (uuid) | yes
FnbService | getFnbDeliveryPolicy | response | id | string (uuid) |  | (read-only)
FnbService | getFnbDeliveryPolicy | response | outletId | string (uuid) | yes
FnbService | getFnbDeliveryPolicy | response | collectionEnabled | boolean |  | (default True)
FnbService | getFnbDeliveryPolicy | response | deliveryEnabled | boolean |  | (default False)
FnbService | getFnbDeliveryPolicy | response | collectionPoint | string |  | (max length 200; nullable)
FnbService | getFnbDeliveryPolicy | response | collectionHoldMinutes | integer |  | (default 20)
FnbService | getFnbDeliveryPolicy | response | asapCollectionMinutes | integer |  | (default 25)
FnbService | getFnbDeliveryPolicy | response | asapDeliveryMinutes | integer |  | (default 45)
FnbService | getFnbDeliveryPolicy | response | slotMinutes | integer |  | (default 30)
FnbService | getFnbDeliveryPolicy | response | minimumOrder | object |  | (nullable)
FnbService | getFnbDeliveryPolicy | response | minimumOrder.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getFnbDeliveryPolicy | response | minimumOrder.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getFnbDeliveryPolicy | response | minimumOrder.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getFnbDeliveryPolicy | response | deliveryFee | object |  | (nullable)
FnbService | getFnbDeliveryPolicy | response | deliveryFee.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getFnbDeliveryPolicy | response | deliveryFee.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getFnbDeliveryPolicy | response | deliveryFee.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getFnbDeliveryPolicy | response | freeDeliveryAbove | object |  | (nullable)
FnbService | getFnbDeliveryPolicy | response | freeDeliveryAbove.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getFnbDeliveryPolicy | response | freeDeliveryAbove.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getFnbDeliveryPolicy | response | freeDeliveryAbove.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getFnbDeliveryPolicy | response | radiusKm | number |  | (min 0; nullable)
FnbService | getFnbDeliveryPolicy | response | emiratesServed | array of string
FnbService | getFnbDeliveryPolicy | response | cutleryOptIn | boolean |  | Cutlery only when asked for, as in the design. (default True)
FnbService | getFnbDeliveryPolicy | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
FnbService | getFnbDeliveryPolicy | param (query) | outletId | string (uuid) | yes
FnbService | getFnbOrder | response | id | string (uuid) | yes
FnbService | getFnbOrder | response | orderNumber | string | yes
FnbService | getFnbOrder | response | outletId | string (uuid) | yes
FnbService | getFnbOrder | response | paymentTiming | object |  | The outlet's payment timing when the order was placed (CHG-CSA-010), kept as a snapshot. (read-only)
FnbService | getFnbOrder | response | sentToKitchenAt | string (date-time) |  | When the order's kitchen tickets were created. (read-only; nullable)
FnbService | getFnbOrder | response | serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery) | yes
FnbService | getFnbOrder | response | tableVisitId | string (uuid) |  | (nullable)
FnbService | getFnbOrder | response | status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) | yes | The full lifecycle from 4.6.35.
FnbService | getFnbOrder | response | lines | array of object | yes
FnbService | getFnbOrder | response | lines[].id | string (uuid) | yes
FnbService | getFnbOrder | response | lines[].menuItemId | string (uuid) | yes
FnbService | getFnbOrder | response | lines[].quantity | integer | yes | (min 1)
FnbService | getFnbOrder | response | lines[].modifierOptionIds | array of string (uuid)
FnbService | getFnbOrder | response | lines[].note | string |  | Free text to the kitchen. (max length 200)
FnbService | getFnbOrder | response | lines[].seatNumber | integer |  | Which cover ordered it. (nullable)
FnbService | getFnbOrder | response | lines[].course | integer |  | Course grouping, so the kitchen fires in sequence. (nullable)
FnbService | getFnbOrder | response | lines[].redeemEntitlementId | string |  | A meal combo redeemed at the till or by a scan (29 September, MOB-4; applied 30 September). (nullable)
FnbService | getFnbOrder | response | lines[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) |  | The full lifecycle from 4.6.35.
FnbService | getFnbOrder | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | getFnbOrder | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getFnbOrder | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getFnbOrder | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getFnbOrder | response | lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | getFnbOrder | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getFnbOrder | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getFnbOrder | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getFnbOrder | response | salesOrderId | string (uuid) |  | Retyped 29 September (SD-046), and format: uuid since ADR-0056 (30 September): every id is a uuid, so this joins orders.sales_order.id. (nullable)
FnbService | getFnbOrder | response | updatedAt | string (date-time) |  | Taken from their fnb.order. (nullable)
FnbService | getFnbOrder | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | getFnbOrder | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getFnbOrder | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getFnbOrder | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getFnbOrder | response | taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | getFnbOrder | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getFnbOrder | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getFnbOrder | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getFnbOrder | response | kitchenTicketId | string (uuid) |  | (nullable)
FnbService | getFnbOrder | response | kitchenTickets | array of KitchenTicket |  | The kitchen tickets this order created, one per station (SD-046). (read-only)
FnbService | getFnbOrder | response | kitchenTickets[].id | string (uuid) | yes
FnbService | getFnbOrder | response | kitchenTickets[].orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | getFnbOrder | response | kitchenTickets[].orderNumber | string
FnbService | getFnbOrder | response | kitchenTickets[].outletId | string (uuid) | yes
FnbService | getFnbOrder | response | kitchenTickets[].tableLabel | string |  | (nullable)
FnbService | getFnbOrder | response | kitchenTickets[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | getFnbOrder | response | kitchenTickets[].coursing | object |  | BL-131. (nullable)
FnbService | getFnbOrder | response | kitchenTickets[].buzzerCode | string |  | BL-128. (nullable)
FnbService | getFnbOrder | response | kitchenTickets[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | getFnbOrder | response | kitchenTickets[].priority | integer |  | Higher fires sooner.
FnbService | getFnbOrder | response | kitchenTickets[].prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | getFnbOrder | response | kitchenTickets[].prioritiseReason | string |  | (nullable)
FnbService | getFnbOrder | response | kitchenTickets[].lines | array of object | yes
FnbService | getFnbOrder | response | kitchenTickets[].lines[].lineId | string (uuid) | yes
FnbService | getFnbOrder | response | kitchenTickets[].lines[].name | string | yes
FnbService | getFnbOrder | response | kitchenTickets[].lines[].quantity | integer | yes
FnbService | getFnbOrder | response | kitchenTickets[].lines[].modifiers | array of string
FnbService | getFnbOrder | response | kitchenTickets[].lines[].note | string |  | (nullable)
FnbService | getFnbOrder | response | kitchenTickets[].lines[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | getFnbOrder | response | kitchenTickets[].lines[].refireOfLineId | string (uuid) |  | Set on a refire. (read-only; nullable)
FnbService | getFnbOrder | response | kitchenTickets[].lines[].refireReason | object |  | (read-only; nullable)
FnbService | getFnbOrder | response | kitchenTickets[].lines[].isChargeable | boolean |  | A refire's chargeable flag. (read-only; nullable)
FnbService | getFnbOrder | response | kitchenTickets[].lines[].course | integer |  | (nullable)
FnbService | getFnbOrder | response | kitchenTickets[].lines[].stationId | string (uuid) |  | (nullable)
FnbService | getFnbOrder | response | kitchenTickets[].lines[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | getFnbOrder | response | kitchenTickets[].createdAt | string (date-time) | yes
FnbService | getFnbOrder | response | kitchenTickets[].targetReadyAt | string (date-time) |  | (nullable)
FnbService | getFnbOrder | response | kitchenTickets[].elapsedSeconds | integer
FnbService | getFnbOrder | response | kitchenTickets[].visitId | string (uuid) |  | The table visit the ticket is for (4 October 2026, CHG-FXC-011; KIT-002): the {visitId} notifyServer takes. (read-only; nullable)
FnbService | getFnbOrder | response | estimatedReadyAt | string (date-time) |  | (nullable)
FnbService | getFnbOrder | response | createdAt | string (date-time) | yes
FnbService | getFnbOrder | response | recordedAt | string (date-time)
FnbService | getFnbOrder | response | syncedAt | string (date-time) |  | (nullable)
FnbService | getFnbOrder | param (path) | orderId | string (uuid) | yes
WhiteLabelService | getFonts | response | primaryLatin | string | yes
WhiteLabelService | getFonts | response | primaryArabic | string |  | Required when ar is among the tenant's languages (audit R163). (nullable)
WhiteLabelService | getFonts | response | secondaryLatin | string |  | (nullable)
WhiteLabelService | getFonts | response | secondaryArabic | string |  | Required whenever secondaryLatin is set and ar is among the tenant's languages (decided 28 September, audit R163). (nullable)
WhiteLabelService | getFonts | response | customFontAssetRefs | array of string (uuid) |  | Uploaded font files, as MediaAsset ids.
WhiteLabelService | getFonts | response | changeScope | object |  | Custom font files are buildTime; selecting a bundled face is runtime. (read-only)
AiService | getForecast | response | items | array of AiForecastPoint | yes
AiService | getForecast | response | items[].id | string (uuid) |  | (read-only)
AiService | getForecast | response | items[].versionId | string (uuid) | yes
AiService | getForecast | response | items[].scenarioId | string (uuid) |  | Set where the point belongs to a what-if scenario rather than the version itself. (nullable)
AiService | getForecast | response | items[].targetStart | string (date-time) | yes
AiService | getForecast | response | items[].targetEnd | string (date-time)
AiService | getForecast | response | items[].dimensionKey | string |  | Canonical key of the breakdown, e.g. (nullable)
AiService | getForecast | response | items[].p10 | number |  | (nullable)
AiService | getForecast | response | items[].p50 | number | yes
AiService | getForecast | response | items[].p90 | number |  | (nullable)
AiService | getForecast | response | items[].unit | string
AiService | getForecast | response | items[].drivers | object |  | Component decomposition or SHAP contributions, largest first (ADM-506). (nullable)
AiService | getForecast | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | getForecast | response | nextCursor | string
AiService | getForecast | response | hasMore | boolean | yes
AiService | getForecast | response | version | AiForecastVersion |  | An immutable forecast version (AIP-032): producer, model version, data cut-off, horizon and status.
AiService | getForecast | response | version.id | string (uuid) |  | (read-only)
AiService | getForecast | response | version.definitionId | string (uuid) | yes
AiService | getForecast | response | version.versionNumber | integer | yes | (min 1)
AiService | getForecast | response | version.module | object |  | The module of the version's definition (AiForecastDefinition.module), copied when the version is produced; the module whose AI publish permission publishForecastVersion requires (CHG-FUP-004). (read-only)
AiService | getForecast | response | version.status | enum (running, draft, awaitingApproval, published, superseded, rejected, failed) | yes | (read-only)
AiService | getForecast | response | version.basis | SuggestionBasis: enum (heuristic, statistical, model, hybrid, manual) | yes | How the answer was reached, and this is the field the whole design exists for.
AiService | getForecast | response | version.maturity | AiMaturity |  | Where an answer stands, on every answer (29 September, AI functions review; baseline then learn).
AiService | getForecast | response | version.maturity.stage | enum (starting, learning, established, learned) | yes | starting: the baseline (venue AI settings, the starting pattern for the venue type, the UAE calendar, weather).
AiService | getForecast | response | version.maturity.basedOn | string | yes | The "Based on" line, in words, e.g.
AiService | getForecast | response | version.maturity.sources | array of object
AiService | getForecast | response | version.maturity.ownDataShare | number |  | The weight own data carries, n / (k + n). (min 0; max 1)
AiService | getForecast | response | version.maturity.limitedHistory | boolean
AiService | getForecast | response | version.maturity.nextStage | object |  | What the next stage needs, e.g. (nullable)
AiService | getForecast | response | version.producerRef | string
AiService | getForecast | response | version.modelVersion | string |  | (nullable)
AiService | getForecast | response | version.dataCutoffAt | string (date-time) |  | The analytical replica watermark the snapshot was taken at.
AiService | getForecast | response | version.horizonStart | string (date-time)
AiService | getForecast | response | version.horizonEnd | string (date-time)
AiService | getForecast | response | version.qualityChecks | object |  | Each gate and whether it passed. (read-only)
AiService | getForecast | response | version.publishedByPrincipalId | string (uuid) |  | Null where the definition auto-published. (read-only; nullable)
AiService | getForecast | response | version.publishedAt | string (date-time) |  | (read-only; nullable)
AiService | getForecast | response | version.decisionRecordId | string (uuid) |  | (read-only; nullable)
AiService | getForecast | response | version.createdAt | string (date-time) |  | (read-only)
AiService | getForecast | response | version.scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | getForecast | response | stale | boolean
AiService | getForecast | param (query) | definitionKey | string | yes
AiService | getForecast | param (query) | versionId | string (uuid)
AiService | getForecast | param (query) | from | string (date-time)
AiService | getForecast | param (query) | to | string (date-time)
AiService | getForecast | param (query) | dimensionKey | string |  | A canonical breakdown key, e.g.
AiService | getForecast | param (query) | scenarioId | string (uuid)
AiService | getForecast | param (query) | pageSize | integer
AiService | getForecast | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
AiService | getForecastAccuracy | response | items | array of AiForecastAccuracy | yes
AiService | getForecastAccuracy | response | items[].id | string (uuid) |  | (read-only)
AiService | getForecastAccuracy | response | items[].definitionId | string (uuid) | yes
AiService | getForecastAccuracy | response | items[].versionId | string (uuid) |  | (nullable)
AiService | getForecastAccuracy | response | items[].producerRef | string
AiService | getForecastAccuracy | response | items[].horizonDays | integer | yes | (min 0)
AiService | getForecastAccuracy | response | items[].periodStart | string (date-time) | yes
AiService | getForecastAccuracy | response | items[].periodEnd | string (date-time)
AiService | getForecastAccuracy | response | items[].wape | number |  | (nullable)
AiService | getForecastAccuracy | response | items[].bias | number |  | (nullable)
AiService | getForecastAccuracy | response | items[].intervalCoverage | number |  | Share of actuals inside the 10th-90th percentile band. (min 0; max 1; nullable)
AiService | getForecastAccuracy | response | items[].baselineWape | number |  | (nullable)
AiService | getForecastAccuracy | response | items[].measuredAt | string (date-time) |  | (read-only)
AiService | getForecastAccuracy | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | getForecastAccuracy | response | nextCursor | string
AiService | getForecastAccuracy | response | hasMore | boolean | yes
AiService | getForecastAccuracy | param (query) | definitionKey | string | yes
AiService | getForecastAccuracy | param (query) | horizonDays | integer
AiService | getForecastAccuracy | param (query) | from | string (date-time)
AiService | getForecastAccuracy | param (query) | pageSize | integer
AiService | getForecastAccuracy | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
MarketingService | getForm | response | id | string (uuid) | yes | (read-only)
MarketingService | getForm | response | name | string | yes
MarketingService | getForm | response | kind | enum (waiver, survey, dataCapture, consentForm, incidentReport, registration) | yes
MarketingService | getForm | response | consentPurposes | array of enum (facePass, faceTag, marketing, photography, waiver) |  | What a consentForm consents to (Chinmay, 2 October, batch 4; follows BO-188: biometric capture needs consent on the venue's own form; CHG-CSA-026).
MarketingService | getForm | response | version | integer | yes | Set by the server — 1 on createForm, the next number on every change. (read-only)
MarketingService | getForm | response | fields | array of FormField
MarketingService | getForm | response | fields[].key | string | yes
MarketingService | getForm | response | fields[].label | string | yes
MarketingService | getForm | response | fields[].labelLocalised | object
MarketingService | getForm | response | fields[].type | enum (text, longText, number, date, select, multiSelect, boolean, scale, …) | yes
MarketingService | getForm | response | fields[].options | array of string
MarketingService | getForm | response | fields[].isRequired | boolean |  | (default False)
MarketingService | getForm | response | fields[].isPersonalData | boolean |  | Marked at the field, because retention is decided at the field. (default False)
MarketingService | getForm | response | fields[].consentPurposeId | string (uuid) |  | (nullable)
MarketingService | getForm | response | fields[].showWhen | object |  | (nullable)
MarketingService | getForm | response | fields[].showWhen.field | string
MarketingService | getForm | response | fields[].showWhen.equals | string
MarketingService | getForm | response | requiresSignature | boolean |  | What makes it a waiver. (default False)
MarketingService | getForm | response | signatureKind | enum (drawn, typed, checkbox, none) |  | (default none)
MarketingService | getForm | response | scoreScale | enum (nps, csat, ces, likert5, likert7, stars) |  | What makes it a survey. (nullable)
MarketingService | getForm | response | appliesToProductIds | array of string (uuid)
MarketingService | getForm | response | validForMonths | integer |  | How long an acceptance lasts. (nullable)
MarketingService | getForm | response | minimumAge | integer |  | (nullable)
MarketingService | getForm | response | requiresGuardianForMinors | boolean |  | A minor cannot waive their own rights. (default True)
MarketingService | getForm | response | status | enum (draft, published, superseded, retired) | yes | (read-only)
MarketingService | getForm | response | legalReviewedBy | string |  | (nullable)
MarketingService | getForm | response | legalReviewedAt | string (date-time) |  | (nullable)
MarketingService | getForm | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | getForm | param (path) | formId | string (uuid) | yes
MarketingService | getForm | param (query) | version | integer
VenueOpsService | getGameCard | response | cardCode | string | yes | A pre-printed card keeps the code printed on it.
VenueOpsService | getGameCard | response | kind | string
VenueOpsService | getGameCard | response | venueId | string (uuid) | yes
VenueOpsService | getGameCard | response | subjectId | string (uuid) |  | (nullable)
VenueOpsService | getGameCard | response | credits | integer | yes | Bought with money.
VenueOpsService | getGameCard | response | bonusCredits | integer | yes | From a promotion.
VenueOpsService | getGameCard | response | points | integer | yes | Won by playing.
VenueOpsService | getGameCard | response | status | enum (active, blocked, expired, transferred) | yes
VenueOpsService | getGameCard | response | blockedReason | string |  | (nullable)
VenueOpsService | getGameCard | response | transferredToCardCode | string |  | (nullable)
VenueOpsService | getGameCard | response | lastPlayedAt | string (date-time) |  | (nullable)
VenueOpsService | getGameCard | response | issuedAt | string (date-time) | yes
VenueOpsService | getGameCard | response | expiresAt | string (date-time) |  | (nullable)
VenueOpsService | getGameCard | response | id | string (uuid) |  | The card's own id (4 October 2026, CHG-FXC-006): the {cardId} of setGameCardLifecycle, which had no column to match, and the id of the Wallet view wallet.loadGameCredits and wallet.adjustGameCard ret… (read-only)
VenueOpsService | getGameCard | response | walletId | string (uuid) |  | Where the card's credits are held (4 October 2026, CHG-FXC-006). (read-only; nullable)
VenueOpsService | getGameCard | param (path) | cardCode | string | yes
WalletService | getGiftCard | response | cardCode | string | yes
WalletService | getGiftCard | response | kind | string
WalletService | getGiftCard | response | faceValue | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | getGiftCard | response | faceValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | getGiftCard | response | faceValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | getGiftCard | response | faceValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | getGiftCard | response | balance | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | getGiftCard | response | balance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | getGiftCard | response | balance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | getGiftCard | response | balance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | getGiftCard | response | status | enum (issued, active, partiallyRedeemed, redeemed, expired, blocked) | yes
WalletService | getGiftCard | response | blockedReason | string |  | (nullable)
WalletService | getGiftCard | response | issuedAt | string (date-time) | yes
WalletService | getGiftCard | response | activatedAt | string (date-time) |  | (nullable)
WalletService | getGiftCard | response | expiresAt | string (date-time) |  | (nullable)
WalletService | getGiftCard | param (path) | cardCode | string | yes
OrderService | getGroupBooking | response | id | string (uuid) | yes
OrderService | getGroupBooking | response | kind | enum (general, school, corporate, party) |  | (default general)
OrderService | getGroupBooking | response | packageProductId | string |  | The school-trip format or party package. (nullable)
OrderService | getGroupBooking | response | yearGroup | string |  | (max length 40; nullable)
OrderService | getGroupBooking | response | accessAndDietaryNeeds | string |  | (max length 1000; nullable)
OrderService | getGroupBooking | response | celebrantName | string |  | The birthday child. (max length 120; nullable)
OrderService | getGroupBooking | response | celebrantTurningAge | integer |  | (min 1; max 18; nullable)
OrderService | getGroupBooking | response | allergiesAndRequests | string |  | (max length 1000; nullable)
OrderService | getGroupBooking | response | finalHeadcountDueBy | string (date-time) |  | (nullable)
OrderService | getGroupBooking | response | quoteSentAt | string (date-time) |  | (read-only; nullable)
OrderService | getGroupBooking | response | riskAssessmentSentAt | string (date-time) |  | (read-only; nullable)
OrderService | getGroupBooking | response | preferredDate | string (date) |  | The date the guest asked for on requestGroupBooking — what its 409 dateUnavailable is checked against. (nullable)
OrderService | getGroupBooking | response | orderId | string (uuid) | yes
OrderService | getGroupBooking | response | leaderSubjectId | string (uuid) | yes
OrderService | getGroupBooking | response | organisationName | string |  | (nullable)
OrderService | getGroupBooking | response | expectedSize | integer | yes
OrderService | getGroupBooking | response | confirmedSize | integer |  | (nullable)
OrderService | getGroupBooking | response | minimumSize | integer |  | Below which the group rate does not apply. (nullable)
OrderService | getGroupBooking | response | attendeeCaptureRequired | boolean |  | Whether names are needed before admission. (default False)
OrderService | getGroupBooking | response | attendeeCaptureDueBy | string (date-time) |  | (nullable)
OrderService | getGroupBooking | response | status | enum (provisional, confirmed, namesPending, complete, cancelled) | yes
OrderService | getGroupBooking | param (path) | groupBookingId | string (uuid) | yes
CatalogueService | getGroupPackageDefinition | response | id | string (uuid) |  | (read-only)
CatalogueService | getGroupPackageDefinition | response | productId | string |  | (read-only)
CatalogueService | getGroupPackageDefinition | response | kind | enum (school, party) | yes
CatalogueService | getGroupPackageDefinition | response | maxParticipants | integer | yes | Pupils or children, e.g. (min 1)
CatalogueService | getGroupPackageDefinition | response | durationMinutes | integer | yes | (min 15)
CatalogueService | getGroupPackageDefinition | response | hostCount | integer |  | Party hosts included. (min 0; default 1)
CatalogueService | getGroupPackageDefinition | response | pricingBasis | enum (perParticipant, perPackage)
CatalogueService | getGroupPackageDefinition | response | freeLeaderRatio | integer |  | Schools: one teacher or assistant enters free per this many pupils. (default 10; nullable)
CatalogueService | getGroupPackageDefinition | response | paymentMode | enum (invoice, deposit, full) |  | Schools are invoiced; parties take a deposit (see DepositPolicy).
CatalogueService | getGroupPackageDefinition | response | includes | array of string
CatalogueService | getGroupPackageDefinition | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
CatalogueService | getGroupPackageDefinition | param (path) | productId | string | yes
FnbService | getGuestBill | response | visitId | string | yes
FnbService | getGuestBill | response | covers | integer
FnbService | getGuestBill | response | lines | array of object | yes
FnbService | getGuestBill | response | lines[].lineId | string | yes
FnbService | getGuestBill | response | lines[].orderId | string
FnbService | getGuestBill | response | lines[].name | string | yes
FnbService | getGuestBill | response | lines[].quantity | integer | yes
FnbService | getGuestBill | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | getGuestBill | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getGuestBill | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getGuestBill | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getGuestBill | response | lines[].lineTotal | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | getGuestBill | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getGuestBill | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getGuestBill | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getGuestBill | response | lines[].categoryCode | string |  | (nullable)
FnbService | getGuestBill | response | lines[].seatNumber | integer |  | (nullable)
FnbService | getGuestBill | response | subtotal | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | getGuestBill | response | subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getGuestBill | response | subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getGuestBill | response | subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getGuestBill | response | serviceCharge | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | getGuestBill | response | serviceCharge.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getGuestBill | response | serviceCharge.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getGuestBill | response | serviceCharge.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getGuestBill | response | taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | getGuestBill | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getGuestBill | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getGuestBill | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getGuestBill | response | discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | getGuestBill | response | discountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getGuestBill | response | discountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getGuestBill | response | discountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getGuestBill | response | total | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | getGuestBill | response | total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getGuestBill | response | total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getGuestBill | response | total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getGuestBill | param (path) | sessionId | string (uuid) | yes
MarketingService | getGuestConsents | response | subjectId | string (uuid) | yes
MarketingService | getGuestConsents | response | purposes | array of object | yes
MarketingService | getGuestConsents | response | purposes[].purpose | ConsentPurpose: enum (marketing, personalisation, profiling, thirdPartySharing, aiProcessing, transactional) | yes
MarketingService | getGuestConsents | response | purposes[].decision | ConsentDecision: enum (granted, withdrawn, notAsked) | yes
MarketingService | getGuestConsents | response | purposes[].channels | array of MessageChannel: enum (email, sms, whatsapp, push, inApp, post)
MarketingService | getGuestConsents | response | purposes[].noticeVersion | string |  | (nullable)
MarketingService | getGuestConsents | response | purposes[].requiresRenewal | boolean | yes | True where the notice has been superseded since consent was given.
MarketingService | getGuestConsents | response | purposes[].decidedAt | string (date-time) |  | (nullable)
MarketingService | getGuestConsents | param (path) | subjectId | string (uuid) | yes
MarketingService | getGuestConversation | response | id | string (uuid) | yes
MarketingService | getGuestConversation | response | state | ConversationState: enum (withAssistant, queued, withAgent, waitingOnGuest, resolved, abandoned, timedOut) | yes | withAssistant and queued are different, and the second has a person waiting.
MarketingService | getGuestConversation | response | queuePosition | integer |  | Place among the unclaimed conversations in its queue, from the live agent queue (audit R149). (read-only; nullable)
MarketingService | getGuestConversation | response | estimatedWaitSeconds | integer |  | From the live agent queue, the conversations ahead divided across that queue's agents online now (audit R149). (read-only; nullable)
MarketingService | getGuestConversation | response | messages | array of GuestConversationMessage | yes | Oldest first; after afterMessageId when it was sent
MarketingService | getGuestConversation | response | messages[].id | string (uuid) | yes
MarketingService | getGuestConversation | response | messages[].sender | enum (guest, agent, assistant, system) | yes
MarketingService | getGuestConversation | response | messages[].body | string | yes
MarketingService | getGuestConversation | response | messages[].attachments | array of object
MarketingService | getGuestConversation | response | messages[].attachments[].assetId | string (uuid)
MarketingService | getGuestConversation | response | messages[].attachments[].kind | enum (image, video, document, ticket, qr, paymentLink)
MarketingService | getGuestConversation | response | messages[].sentAt | string (date-time) | yes
MarketingService | getGuestConversation | param (path) | conversationId | string (uuid) | yes
MarketingService | getGuestConversation | param (query) | afterMessageId | string (uuid) |  | Only the messages sent after this one, oldest first, so a polling chat fetches what is new
MarketingService | getGuestLoyalty | response | leaderboardNickname | string |  | BL-173. (max length 24; nullable)
MarketingService | getGuestLoyalty | response | subjectId | string (uuid) | yes
MarketingService | getGuestLoyalty | response | programmeId | string (uuid) | yes
MarketingService | getGuestLoyalty | response | pointsBalance | integer | yes
MarketingService | getGuestLoyalty | response | lifetimePoints | integer
MarketingService | getGuestLoyalty | response | tierId | string (uuid) |  | The tier this row's tierCode and tierName are a copy of. (nullable)
MarketingService | getGuestLoyalty | response | tierCode | string | yes
MarketingService | getGuestLoyalty | response | tierName | string
MarketingService | getGuestLoyalty | response | pointsToNextTier | integer |  | (nullable)
MarketingService | getGuestLoyalty | response | nextExpiryPoints | integer |  | (nullable)
MarketingService | getGuestLoyalty | response | nextExpiryAt | string (date-time) |  | (nullable)
MarketingService | getGuestLoyalty | param (path) | subjectId | string (uuid) | yes
MarketingService | getGuestLoyalty | param (query) | programmeId | string (uuid) | yes | Which programme.
FnbService | getGuestMenu | response | outletId | string (uuid) | yes
FnbService | getGuestMenu | response | menuId | string (uuid) | yes
FnbService | getGuestMenu | response | name | string | yes
FnbService | getGuestMenu | response | inForceUntil | string (date-time) | yes | When this menu stops applying. (nullable)
FnbService | getGuestMenu | response | currency | string |  | (pattern ^[A-Z]{3}$)
FnbService | getGuestMenu | response | currencyScale | integer
FnbService | getGuestMenu | response | sections | array of object | yes
FnbService | getGuestMenu | response | sections[].name | string
FnbService | getGuestMenu | response | sections[].sortOrder | integer
FnbService | getGuestMenu | response | sections[].items | array of object
FnbService | getGuestMenu | response | sections[].items[].menuItemId | string (uuid) | yes
FnbService | getGuestMenu | response | sections[].items[].name | string | yes
FnbService | getGuestMenu | response | sections[].items[].description | string |  | (nullable)
FnbService | getGuestMenu | response | sections[].items[].price | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | getGuestMenu | response | sections[].items[].imageAssetRef | string |  | (nullable)
FnbService | getGuestMenu | response | sections[].items[].isAvailable | boolean | yes | Marked, not removed.
FnbService | getGuestMenu | response | sections[].items[].unavailableReason | string |  | (nullable)
FnbService | getGuestMenu | response | sections[].items[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …) | yes | Always present.
FnbService | getGuestMenu | response | sections[].items[].allergenDetail | object |  | What the dish contains and what it may contain, told apart (3 October 2026, CHG-R1S-022: the kiosk and guest menus promise the difference and the flat list cannot carry it).
FnbService | getGuestMenu | response | sections[].items[].preparationMinutes | integer |  | (nullable)
FnbService | getGuestMenu | response | sections[].items[].modifierGroups | array of ModifierGroup
FnbService | getGuestMenu | param (path) | outletId | string (uuid) | yes
FnbService | getGuestMenu | param (query) | at | string (date-time) |  | Evaluate menu availability at this time rather than now.
FnbService | getGuestMenu | param (query) | language | string
FnbService | getGuestOrderStatus | response | orderId | string | yes
FnbService | getGuestOrderStatus | response | orderNumber | string
FnbService | getGuestOrderStatus | response | status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) | yes | The full lifecycle from 4.6.35.
FnbService | getGuestOrderStatus | response | estimatedReadyAt | string (date-time) |  | (nullable)
FnbService | getGuestOrderStatus | response | isReadyForCollection | boolean
FnbService | getGuestOrderStatus | response | lines | array of object | yes | Per-line status.
FnbService | getGuestOrderStatus | response | lines[].name | string
FnbService | getGuestOrderStatus | response | lines[].quantity | integer
FnbService | getGuestOrderStatus | response | lines[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled)
FnbService | getGuestOrderStatus | param (path) | orderId | string (uuid) | yes
IdentityService | getGuestSession | response | subjectId | string (uuid) | yes
IdentityService | getGuestSession | response | displayName | string |  | (nullable)
IdentityService | getGuestSession | response | tokens | TokenPair | yes
IdentityService | getGuestSession | response | tokens.accessToken | string | yes | JWT carrying sid, validated per request against the session registry.
IdentityService | getGuestSession | response | tokens.refreshToken | string | yes
IdentityService | getGuestSession | response | tokens.expiresIn | integer | yes | Seconds
IdentityService | getGuestSession | response | isVerified | boolean | yes | False until an OTP or a verified provider identity confirms ownership.
IdentityService | getGuestSession | response | identityProviders | array of enum (password, otp, apple, google, uaePass) |  | Linked providers.
IdentityService | getGuestSession | response | guestLinkId | string |  | Present where the guest is linked across cells (ADR-0010). (nullable)
IdentityService | getGuestSession | response | requiresMfa | boolean |  | True only where the sign-in venue enabled guest two-step verification (VenueSettings.identity.guestTwoStep, in tenancy) and this guest has an active method (decided 29 September, rev 3 GAP-B1, per ve… (default False)
IdentityService | getGuestSession | response | mfaMethods | array of MfaMethod |  | The guest's active methods, so the client can offer the right one.
IdentityService | getGuestSession | response | mfaMethods[].id | string (uuid) | yes
IdentityService | getGuestSession | response | mfaMethods[].kind | MfaKind: enum (totp, smsOtp, emailOtp, biometric, hardwareToken) | yes
IdentityService | getGuestSession | response | mfaMethods[].label | string |  | (nullable)
IdentityService | getGuestSession | response | mfaMethods[].maskedTarget | string |  | Partially masked destination, so a person can tell two methods apart. (nullable)
IdentityService | getGuestSession | response | mfaMethods[].isActive | boolean | yes
IdentityService | getGuestSession | response | mfaMethods[].isPrimary | boolean
IdentityService | getGuestSession | response | mfaMethods[].enrolledAt | string (date-time) | yes
IdentityService | getGuestSession | response | mfaMethods[].lastUsedAt | string (date-time) |  | (nullable)
IdentityService | getGuestSession | response | homeCellName | string |  | (nullable)
IdentityService | getGuestSession | response | preferredLanguage | string |  | (nullable)
IdentityService | getGuestSession | response | expiresAt | string (date-time) | yes | 30 days, sliding (decided 28 September, audit R126 (2)): each use of the session moves this to 30 days from now, and 30 days unused ends it.
AiService | getGuidedChoiceSuggestion | response | id | string (uuid) |  | (read-only)
AiService | getGuidedChoiceSuggestion | response | venueId | string (uuid) | yes
AiService | getGuidedChoiceSuggestion | response | trigger | enum (productsUploaded, mappedProductWithdrawn, productsUncovered, manual) | yes
AiService | getGuidedChoiceSuggestion | response | status | enum (running, proposed, noSuggestion, failed, superseded) | yes | (read-only)
AiService | getGuidedChoiceSuggestion | response | productCount | integer |  | (min 0; read-only)
AiService | getGuidedChoiceSuggestion | response | questions | array of object |  | The questions chosen, in the order asked. (read-only)
AiService | getGuidedChoiceSuggestion | response | questions[].attribute | string |  | The catalogue attribute asked about: audience, level, minimum height or age, duration, price band, format, language.
AiService | getGuidedChoiceSuggestion | response | questions[].order | integer |  | (min 1)
AiService | getGuidedChoiceSuggestion | response | questions[].split | object |  | How evenly it divides the bookable products: products per answer.
AiService | getGuidedChoiceSuggestion | response | questions[].droppedBecause | string |  | Set where an attribute was considered and dropped (an answer would leave nothing bookable). (nullable)
AiService | getGuidedChoiceSuggestion | response | questions[].answers | array of object
AiService | getGuidedChoiceSuggestion | response | questions[].answers[].value | string
AiService | getGuidedChoiceSuggestion | response | questions[].answers[].leadsTo | enum (product, category, flow)
AiService | getGuidedChoiceSuggestion | response | questions[].answers[].targetRef | string
AiService | getGuidedChoiceSuggestion | response | wordingSource | enum (model, attributeNames) |  | Where the text came from. (read-only)
AiService | getGuidedChoiceSuggestion | response | modelVersion | string |  | (read-only; nullable)
AiService | getGuidedChoiceSuggestion | response | promptTemplateVersion | string |  | (read-only; nullable)
AiService | getGuidedChoiceSuggestion | response | guidedChoiceId | string (uuid) |  | The white-label draft GuidedChoice it produced. (read-only; nullable)
AiService | getGuidedChoiceSuggestion | response | decisionRecordId | string (uuid) |  | (read-only; nullable)
AiService | getGuidedChoiceSuggestion | response | createdAt | string (date-time) |  | (read-only)
AiService | getGuidedChoiceSuggestion | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | getGuidedChoiceSuggestion | param (path) | suggestionId | string (uuid) | yes
FnbService | getHaccpStatus | response | checksDue | integer
FnbService | getHaccpStatus | response | checksMissed | integer
FnbService | getHaccpStatus | response | openActions | integer
FnbService | getHaccpStatus | response | unsignedActions | integer
FnbService | getHaccpStatus | response | oldestOpenActionAgeHours | integer |  | (nullable)
FnbService | getHaccpStatus | response | lastInspectionAt | string (date-time) |  | (nullable)
WhiteLabelService | getHomepageLayout | response | templateKey | string |  | The landing-page template this layout started from (listLandingPageTemplates), or null for a layout composed from scratch (CHG-CSA-037). (nullable)
WhiteLabelService | getHomepageLayout | response | landingSource | enum (storefront, ownSite) |  | storefront: this home is the tenant's landing page. (default storefront)
WhiteLabelService | getHomepageLayout | response | id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | getHomepageLayout | response | sections | array of object | yes
WhiteLabelService | getHomepageLayout | response | sections[].id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | getHomepageLayout | response | sections[].kind | HomepageSectionKind: enum (heroBanner, quickActions, tickets, whatsOn, attractions, membership, dining, shop, …) | yes | Which module each section needs, proposed, client to correct (decided 28 September, audit R163).
WhiteLabelService | getHomepageLayout | response | sections[].title | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | getHomepageLayout | response | sections[].sortOrder | integer | yes
WhiteLabelService | getHomepageLayout | response | sections[].isVisible | boolean | yes
WhiteLabelService | getHomepageLayout | response | sections[].contentPageId | string (uuid) |  | (nullable)
WhiteLabelService | getHomepageLayout | response | sections[].maxItems | integer |  | How many cards the section shows, the venue's choice (Chinmay, 2 October, workbook Q152: every customisation option of the approved wireframe, including the card count per section; CHG-CSA-040). (nullable)
WhiteLabelService | getHomepageLayout | response | sections[].scrollAnimation | enum (rise, scale, slide, blur, none) |  | How the section enters as the guest scrolls (Chinmay, 2 October, workbook Q153: "must be there"; DI-1088; CHG-CSA-040). (default rise)
WhiteLabelService | getHomepageLayout | response | sections[].heroStyle | enum (carousel, video, poster, split, None) |  | For heroBanner only (decided 29 September, MOB-3). (nullable)
FnbService | getKitchenSla | response | outletId | string (uuid) |  | The outlet, from the path. (read-only)
FnbService | getKitchenSla | response | targets | array of object
FnbService | getKitchenSla | response | targets[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery) | yes
FnbService | getKitchenSla | response | targets[].targetMinutes | integer | yes | (min 1)
FnbService | getKitchenSla | response | targets[].warnAtPercent | integer |  | (default 80)
FnbService | getKitchenSla | response | priorityWeights | object |  | The weight of each signal the board names — age, promise time, table stage, a VIP marker.
FnbService | getKitchenSla | response | priorityWeights.age | integer |  | (min 0)
FnbService | getKitchenSla | response | priorityWeights.targetReadyAt | integer |  | Promise time. (min 0)
FnbService | getKitchenSla | response | priorityWeights.tableStage | integer |  | (min 0)
FnbService | getKitchenSla | response | priorityWeights.vip | integer |  | (min 0)
FnbService | getKitchenSla | param (path) | outletId | string (uuid) | yes
CatalogueService | getLatestBundle | response | version | string | yes
CatalogueService | getLatestBundle | response | venueId | string (uuid) | yes
CatalogueService | getLatestBundle | response | isDelta | boolean | yes
CatalogueService | getLatestBundle | response | baseVersion | string |  | Present when isDelta. (nullable)
CatalogueService | getLatestBundle | response | signature | string | yes | Detached signature over contentHash.
CatalogueService | getLatestBundle | response | signatureKeyId | string | yes
CatalogueService | getLatestBundle | response | contentHash | string | yes
CatalogueService | getLatestBundle | response | staleAfter | string (date-time) | yes
CatalogueService | getLatestBundle | response | payload | object | yes | Products, variants, price lists, prices, tax codes, events, performances, envelope definitions, data mask field definitions and the venue's sale boards.
CatalogueService | getLatestBundle | response | payload.saleBoards | array of object |  | The venue's sale boards as tenancy.listSaleBoards returns them, read from platform.sale_board when the bundle is snapshotted (decided 28 September, audit R129 (4)).
CatalogueService | getLatestBundle | param (query) | since | string |  | Applied bundle version.
CatalogueService | getLatestBundle | param (header) | If-None-Match | string
MarketingService | getLoyaltyPosition | response | subjectId | string (uuid)
MarketingService | getLoyaltyPosition | response | programmeId | string (uuid)
MarketingService | getLoyaltyPosition | response | pointsBalance | integer
MarketingService | getLoyaltyPosition | response | pointsPending | integer |  | Earned and not yet cleared — a purchase inside the refund window.
MarketingService | getLoyaltyPosition | response | tier | string
MarketingService | getLoyaltyPosition | response | nextTier | string |  | The name of the next MarketingProgrammeTier by rank above the guest's current tier, resolved at read. (nullable)
MarketingService | getLoyaltyPosition | response | pointsToNextTier | integer |  | (nullable)
MarketingService | getLoyaltyPosition | response | expiringPoints | integer
MarketingService | getLoyaltyPosition | response | expiringAt | string (date-time) |  | Points that lapse unannounced are a complaint. (nullable)
MarketingService | getLoyaltyPosition | param (query) | programmeId | string (uuid) | yes | Which programme.
VenueOpsService | getMapResourceAvailability | response | mapId | string (uuid) | yes
VenueOpsService | getMapResourceAvailability | response | mapVersion | integer | yes | The published venue-map version the placements were read from; the client checks it against the map it cached.
VenueOpsService | getMapResourceAvailability | response | from | string (date-time) | yes
VenueOpsService | getMapResourceAvailability | response | to | string (date-time) | yes
VenueOpsService | getMapResourceAvailability | response | totals | object
VenueOpsService | getMapResourceAvailability | response | totals.total | integer
VenueOpsService | getMapResourceAvailability | response | totals.available | integer
VenueOpsService | getMapResourceAvailability | response | totals.held | integer
VenueOpsService | getMapResourceAvailability | response | totals.booked | integer
VenueOpsService | getMapResourceAvailability | response | totals.unavailable | integer
VenueOpsService | getMapResourceAvailability | response | resources | array of object | yes
VenueOpsService | getMapResourceAvailability | response | resources[].resourceId | string (uuid) | yes
VenueOpsService | getMapResourceAvailability | response | resources[].placedResourceId | string (uuid) |  | The venue-map.PlacedResource it was read from.
VenueOpsService | getMapResourceAvailability | response | resources[].label | string | yes | As on the map, e.g.
VenueOpsService | getMapResourceAvailability | response | resources[].kind | ResourceKind: enum (cabana, lounger, locker, wheelchair, stroller, equipment, room, auditorium, …) |  | BL-135.
VenueOpsService | getMapResourceAvailability | response | resources[].zone | string
VenueOpsService | getMapResourceAvailability | response | resources[].capacity | integer
VenueOpsService | getMapResourceAvailability | response | resources[].priceBandCode | string
VenueOpsService | getMapResourceAvailability | response | resources[].variantId | string (uuid) |  | What the cart line names to buy it.
VenueOpsService | getMapResourceAvailability | response | resources[].price | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | getMapResourceAvailability | response | resources[].price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | getMapResourceAvailability | response | resources[].price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | getMapResourceAvailability | response | resources[].price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | getMapResourceAvailability | response | resources[].status | enum (available, held, booked, unavailable) | yes | unavailable covers maintenance, a blackout, a block and a placement marked not bookable; the map greys all of them the same way.
VenueOpsService | getMapResourceAvailability | param (query) | mapId | string (uuid) | yes | The venue-map.VenueMap whose placed resources to report.
VenueOpsService | getMapResourceAvailability | param (query) | from | string (date-time) | yes | Start of the window.
VenueOpsService | getMapResourceAvailability | param (query) | to | string (date-time) | yes
VenueOpsService | getMapResourceAvailability | param (query) | kind | ResourceKind: enum (cabana, lounger, locker, wheelchair, stroller, equipment, room, auditorium, …) |  | Only resources of this kind, e.g.
VenueOpsService | getMediaAsset | response | id | string (uuid) | yes
VenueOpsService | getMediaAsset | response | kind | MediaKind: enum (image, video, audio, document, vector, font, archive, model3d) | yes | model3d added 3 October 2026 (r1 additions; ADR-0069 action item 4): a glTF binary (model/gltf-binary, .glb) venue model, at most 40 MB.
VenueOpsService | getMediaAsset | response | status | MediaStatus: enum (processing, ready, quarantined, failed, archived) | yes
VenueOpsService | getMediaAsset | response | filename | string | yes
VenueOpsService | getMediaAsset | response | contentType | string | yes
VenueOpsService | getMediaAsset | response | sizeBytes | integer | yes
VenueOpsService | getMediaAsset | response | title | LocalisedText
VenueOpsService | getMediaAsset | response | description | object |  | Set by updateMediaAsset and matched by searchMedia's search.
VenueOpsService | getMediaAsset | response | altText | object |  | Required before use in a guest-facing surface.
VenueOpsService | getMediaAsset | response | width | integer |  | (nullable)
VenueOpsService | getMediaAsset | response | height | integer |  | (nullable)
VenueOpsService | getMediaAsset | response | durationSeconds | number |  | (nullable)
VenueOpsService | getMediaAsset | response | customMetadata | object |  | BL-178. (nullable)
VenueOpsService | getMediaAsset | response | sharedWithTenantIds | array of string (uuid) |  | BL-178.
VenueOpsService | getMediaAsset | response | tags | array of string
VenueOpsService | getMediaAsset | response | categoryId | string (uuid) |  | The asset's category, one of MediaTaxonomy.categories[].id; null while unclassified. (nullable)
VenueOpsService | getMediaAsset | response | venueId | string (uuid) |  | (nullable)
VenueOpsService | getMediaAsset | response | url | string |  | Signed and expiring for private assets; stable CDN URL for public ones.
VenueOpsService | getMediaAsset | response | thumbnailUrl | string |  | (nullable)
VenueOpsService | getMediaAsset | response | referenceCount | integer | yes | How many surfaces reference this asset.
VenueOpsService | getMediaAsset | response | rights | MediaRights |  | Licensing terms.
VenueOpsService | getMediaAsset | response | rights.licenceKind | enum (owned, royaltyFree, rightsManaged, creativeCommons, editorialOnly, unknown)
VenueOpsService | getMediaAsset | response | rights.licensor | string |  | (nullable)
VenueOpsService | getMediaAsset | response | rights.licenceReference | string |  | (nullable)
VenueOpsService | getMediaAsset | response | rights.validFrom | string (date) |  | (nullable)
VenueOpsService | getMediaAsset | response | rights.validTo | string (date) |  | (nullable)
VenueOpsService | getMediaAsset | response | rights.permittedUses | array of enum (web, print, socialMedia, inVenue, advertising, internal)
VenueOpsService | getMediaAsset | response | rights.attributionRequired | boolean |  | (default False)
VenueOpsService | getMediaAsset | response | rights.attributionText | string |  | (nullable)
VenueOpsService | getMediaAsset | response | rights.permittedTerritories | array of string |  | ISO country or region codes.
VenueOpsService | getMediaAsset | response | rights.permittedChannels | array of string |  | Distribution channel codes, checked by setMediaDistributionChannels.
VenueOpsService | getMediaAsset | response | rights.modelReleaseHeld | boolean |  | (default False)
VenueOpsService | getMediaAsset | response | rights.renewalOwner | string (uuid) |  | (nullable)
VenueOpsService | getMediaAsset | response | isRightsExpired | boolean
VenueOpsService | getMediaAsset | response | version | integer
VenueOpsService | getMediaAsset | response | uploadedByPrincipalId | string (uuid)
VenueOpsService | getMediaAsset | response | createdAt | string (date-time) | yes
VenueOpsService | getMediaAsset | response | derivatives | array of object |  | Generated from the original, never uploaded separately.
VenueOpsService | getMediaAsset | response | derivatives[].label | string
VenueOpsService | getMediaAsset | response | derivatives[].width | integer
VenueOpsService | getMediaAsset | response | derivatives[].height | integer
VenueOpsService | getMediaAsset | response | derivatives[].sizeBytes | integer
VenueOpsService | getMediaAsset | response | derivatives[].url | string
VenueOpsService | getMediaAsset | response | usage | array of MediaUsage |  | Every place this asset is referenced.
VenueOpsService | getMediaAsset | response | usage[].extractedText | string |  | Text pulled out of an uploaded document, after extraction.
VenueOpsService | getMediaAsset | response | usage[].id | string (uuid) |  | Added 20 August. (read-only)
VenueOpsService | getMediaAsset | response | usage[].surface | enum (tenantBranding, homepageBanner, promoBlock, contentPage, product, event, menuItem, merchandise, …) | yes
VenueOpsService | getMediaAsset | response | usage[].referenceId | string | yes
VenueOpsService | getMediaAsset | response | usage[].label | string
VenueOpsService | getMediaAsset | response | usage[].isLive | boolean |  | True where the referencing surface is published to guests.
VenueOpsService | getMediaAsset | response | collections | array of object
VenueOpsService | getMediaAsset | response | collections[].id | string (uuid)
VenueOpsService | getMediaAsset | response | collections[].name | string
VenueOpsService | getMediaAsset | response | previousVersions | array of object
VenueOpsService | getMediaAsset | response | previousVersions[].version | integer
VenueOpsService | getMediaAsset | response | previousVersions[].replacedAt | string (date-time)
VenueOpsService | getMediaAsset | response | previousVersions[].replacedByPrincipalId | string (uuid)
VenueOpsService | getMediaAsset | param (path) | mediaId | string (uuid) | yes
OrderService | getMediaEntitlements | response | mediaCode | string | yes
OrderService | getMediaEntitlements | response | mediaKind | enum (qr, wristband, card, nfc, mobilePass)
OrderService | getMediaEntitlements | response | subjectId | string (uuid) |  | (nullable)
OrderService | getMediaEntitlements | response | isValid | boolean | yes
OrderService | getMediaEntitlements | response | invalidReason | string |  | (nullable)
OrderService | getMediaEntitlements | response | canAcceptMore | boolean |  | False where the media has been surrendered, expired or blocked.
OrderService | getMediaEntitlements | response | entitlements | array of object | yes
OrderService | getMediaEntitlements | response | entitlements[].entitlementId | string (uuid)
OrderService | getMediaEntitlements | response | entitlements[].name | string
OrderService | getMediaEntitlements | response | entitlements[].kind | enum (admission, locker, fnb, retail, parking, rental, experience, membership)
OrderService | getMediaEntitlements | response | entitlements[].orderId | string (uuid)
OrderService | getMediaEntitlements | response | entitlements[].addedAt | string (date-time)
OrderService | getMediaEntitlements | response | entitlements[].status | object |  | Replaced isRedeemed on 17 August.
OrderService | getMediaEntitlements | response | entitlements[].entriesUsed | integer
OrderService | getMediaEntitlements | response | entitlements[].entriesAllowed | integer |  | (nullable)
OrderService | getMediaEntitlements | response | entitlements[].redeemedAt | string (date-time) |  | (nullable)
OrderService | getMediaEntitlements | response | entitlements[].transferredToSubjectId | string (uuid) |  | (nullable)
OrderService | getMediaEntitlements | response | entitlements[].validTo | string (date-time) |  | (nullable)
OrderService | getMediaEntitlements | param (path) | mediaCode | string | yes | The QR, wristband or card the guest is already carrying.
IdentityService | getMyIdentityVerification | response | id | string (uuid) | yes | (read-only)
IdentityService | getMyIdentityVerification | response | subjectId | string (uuid) | yes
IdentityService | getMyIdentityVerification | response | subjectDocumentId | string (uuid) |  | The pii.subject_document row submitted.
IdentityService | getMyIdentityVerification | response | documentKind | enum (passport, emiratesId, nationalId, drivingLicence, residencePermit, other)
IdentityService | getMyIdentityVerification | response | documentNumberLast4 | string |  | (max length 4; read-only; nullable)
IdentityService | getMyIdentityVerification | response | reason | enum (policyRequired, ageRestrictedPurchase, residentPricing, accountRecovery)
IdentityService | getMyIdentityVerification | response | status | enum (pending, verified, rejected, resubmissionRequested) | yes | (read-only)
IdentityService | getMyIdentityVerification | response | method | enum (manualReview, documentScanner, provider) |  | (read-only; nullable)
IdentityService | getMyIdentityVerification | response | decisionReason | string |  | (max length 300; read-only; nullable)
IdentityService | getMyIdentityVerification | response | decidedByPrincipalId | string (uuid) |  | (read-only; nullable)
IdentityService | getMyIdentityVerification | response | submittedAt | string (date-time) | yes | (read-only)
IdentityService | getMyIdentityVerification | response | decidedAt | string (date-time) |  | (read-only; nullable)
IdentityService | getMyIdentityVerification | response | documentImageDeletedAt | string (date-time) |  | When the scan (and any selfie) was deleted under the policy's retention. (read-only; nullable)
CatalogueService | getMyMemberships | param (query) | includeLapsed | boolean
MarketingService | getMyProfile | response | profile | GuestProfile | yes
MarketingService | getMyProfile | response | profile.id | string (uuid) |  | Added 20 August. (read-only)
MarketingService | getMyProfile | response | profile.subjectId | string (uuid) | yes | Opaque reference.
MarketingService | getMyProfile | response | profile.displayName | string |  | (nullable)
MarketingService | getMyProfile | response | profile.email | string |  | (nullable)
MarketingService | getMyProfile | response | profile.phone | string |  | (nullable)
MarketingService | getMyProfile | response | profile.preferredLanguage | string |  | (nullable)
MarketingService | getMyProfile | response | profile.preferredChannel | MessageChannel: enum (email, sms, whatsapp, push, inApp, post)
MarketingService | getMyProfile | response | profile.guestLinkId | string |  | Present where the guest is linked across cells. (nullable)
MarketingService | getMyProfile | response | profile.tags | array of string
MarketingService | getMyProfile | response | profile.engagementScore | integer |  | 22.2.20 and 22.2.21. (min 0; max 100; nullable)
MarketingService | getMyProfile | response | profile.engagementTier | enum (new, active, occasional, lapsing, lapsed, dormant) |  | 5.3.19. (nullable)
MarketingService | getMyProfile | response | profile.lifetimeValue | Money |  | On the wire this is three fields; in the database it is one column.
MarketingService | getMyProfile | response | profile.lifetimeValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
MarketingService | getMyProfile | response | profile.lifetimeValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
MarketingService | getMyProfile | response | profile.lifetimeValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
MarketingService | getMyProfile | response | profile.visitCount | integer
MarketingService | getMyProfile | response | profile.lastVisitAt | string (date-time) |  | (nullable)
MarketingService | getMyProfile | response | profile.isActive | boolean | yes
MarketingService | getMyProfile | response | profile.mergedIntoSubjectId | string (uuid) |  | Set on the absorbed profile by mergeGuestProfiles and mergeGuests, which retain it as a redirect rather than deleting it. (read-only; nullable)
MarketingService | getMyProfile | response | profile.mergedAt | string (date-time) |  | (read-only; nullable)
MarketingService | getMyProfile | response | preferences | GuestPreferences |  | What the guest likes, kept apart from what they permit (consent) and from who they are (the profile).
MarketingService | getMyProfile | response | preferences.id | string (uuid) |  | (read-only)
MarketingService | getMyProfile | response | preferences.subjectId | string (uuid) |  | (read-only)
MarketingService | getMyProfile | response | preferences.seatingPreference | string |  | (max length 200; nullable)
MarketingService | getMyProfile | response | preferences.drinkPreferences | array of string
MarketingService | getMyProfile | response | preferences.dietary | array of string |  | Also written by updateMyProfile.
MarketingService | getMyProfile | response | preferences.accessibility | array of string |  | Also written by updateMyProfile.
MarketingService | getMyProfile | response | preferences.preferredChannel | object |  | Stored on the profile (GuestProfile.preferredChannel) — carried here because the preference screen edits it beside the rest.
MarketingService | getMyProfile | response | preferences.updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | getNavigation | response | id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | getNavigation | response | kind | enum (bottomNavigation, drawer, tabs) | yes
WhiteLabelService | getNavigation | response | items | array of object | yes | (max items 12)
WhiteLabelService | getNavigation | response | items[].id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | getNavigation | response | items[].label | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | getNavigation | response | items[].icon | string
WhiteLabelService | getNavigation | response | items[].target | LinkTarget | yes
WhiteLabelService | getNavigation | response | items[].target.kind | enum (module, contentPage, product, event, externalUrl, appSection, none) | yes | appSection points at a section of the guest mobile app (decided 29 September, MOB-1), so the bottom navigation can hold Home, Explore, Plan and Tickets.
WhiteLabelService | getNavigation | response | items[].target.moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) |  | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | getNavigation | response | items[].target.appSection | enum (home, explore, plan, tickets, map, account, buyTickets) |  | Required when kind is appSection.
WhiteLabelService | getNavigation | response | items[].target.contentPageId | string (uuid)
WhiteLabelService | getNavigation | response | items[].target.productId | string (uuid)
WhiteLabelService | getNavigation | response | items[].target.eventId | string (uuid)
WhiteLabelService | getNavigation | response | items[].target.url | string
WhiteLabelService | getNavigation | response | items[].isVisible | boolean | yes | At most five may be visible in bottom navigation; the rest overflow.
WhiteLabelService | getNavigation | response | items[].sortOrder | integer | yes
WhiteLabelService | getNavigation | response | buyButton | object |  | The persistent Buy tickets button (decided 29 September, MOB-2). (nullable)
WhiteLabelService | getNavigation | response | buyButton.style | enum (raised, floating, flat, hidden) |  | raised sits in the centre of the tab bar, as the v4 prototype shows; hidden turns it off. (default raised)
WhiteLabelService | getNavigation | response | buyButton.label | LocalisedText |  | Keyed by ISO 639-1 code.
VenueOpsService | getNextTransportDeparture | response | departureId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | getNextTransportDeparture | response | performanceId | string (uuid) | yes
VenueOpsService | getNextTransportDeparture | response | routeId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | getNextTransportDeparture | response | routeCode | string |  | The price card's label, e.g.
VenueOpsService | getNextTransportDeparture | response | departsAt | string (date-time) | yes | At the boarding stop.
VenueOpsService | getNextTransportDeparture | response | arrivesAt | string (date-time) | yes | At the alighting stop.
VenueOpsService | getNextTransportDeparture | response | durationMinutes | integer | yes | (min 0)
VenueOpsService | getNextTransportDeparture | response | period | TimePeriod: enum (morning, afternoon, evening, night) | yes | Proposed, client to correct (rev 3 REV3-21): morning 05:00–11:59, afternoon 12:00–16:59, evening 17:00–20:59, night 21:00–04:59.
VenueOpsService | getNextTransportDeparture | response | seatsLeft | integer | yes | Catalogue availability for the performance. (min 0)
VenueOpsService | getNextTransportDeparture | response | fitsParty | boolean
VenueOpsService | getNextTransportDeparture | response | fare | Money | yes | On the wire this is three fields; in the database it is one column.
VenueOpsService | getNextTransportDeparture | response | fare.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | getNextTransportDeparture | response | fare.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | getNextTransportDeparture | response | fare.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | getNextTransportDeparture | response | partyTotal | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | getNextTransportDeparture | response | partyTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | getNextTransportDeparture | response | partyTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | getNextTransportDeparture | response | partyTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | getNextTransportDeparture | param (query) | fromStationId | string (uuid) | yes
VenueOpsService | getNextTransportDeparture | param (query) | toStationId | string (uuid) | yes
VenueOpsService | getNextTransportDeparture | param (query) | after | string (date-time)
VenueOpsService | getNextTransportDeparture | param (query) | passengers | array of string |  | As on searchTransportDepartures.
OrderService | getOrder | response | id | string (uuid) | yes | The client UUIDv7 from CreateOrderRequest.id.
OrderService | getOrder | response | orderNumber | string |  | The number a guest reads and a cashier types. (read-only)
OrderService | getOrder | response | channel | object | yes | Where it came from.
OrderService | getOrder | response | channelProfileId | string (uuid) |  | The named sales channel the order came through (catalogue SalesChannelProfile.id), set by the server from the caller: a partner user's or reseller's channel, an API key's channel. (read-only; nullable)
OrderService | getOrder | response | venueId | string (uuid) | yes
OrderService | getOrder | response | scopePath | string | yes
OrderService | getOrder | response | status | OrderStatus: enum (pending, held, paid, partiallyPaid, completed, voided, refunded, partiallyRefunded, …) | yes | held is a parked sale — the cashier freed the till and the guest will return.
OrderService | getOrder | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | getOrder | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getOrder | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getOrder | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getOrder | response | netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | refundedAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getOrder | response | refundedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | refundedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | refundedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | chargeCurrency | string |  | The currency the guest selected and is charged in (CHG-FIN-001, 2 October 2026). (pattern ^[A-Z]{3}$; read-only; nullable)
OrderService | getOrder | response | chargeFxRate | object |  | Units of chargeCurrency per one unit of the base currency, from the region's tender rate in force at checkout (finance.FxRate), stored on the order so the payment, the receipt, the tax invoice and an… (read-only; nullable)
OrderService | getOrder | response | chargeFxRateId | string (uuid) |  | The finance.FxRate row the rate was taken from, for audit. (read-only; nullable)
OrderService | getOrder | response | chargeTotal | object |  | grossAmount converted at chargeFxRate and rounded to the charge currency's scale: what the guest pays and what the payment request to the provider asks for (CHG-FIN-001). (read-only)
OrderService | getOrder | response | chargeTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | chargeTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | chargeTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | chargeRateLockedUntil | string (date-time) |  | The quote holds until then (the cart lease). (read-only; nullable)
OrderService | getOrder | response | droppedPromotions | array of object |  | Promotions left off this order at checkout because their budget cap would have been exceeded (decided 28 September, audit R101 (8)). (read-only)
OrderService | getOrder | response | droppedPromotions[].promotionId | string (uuid) | yes
OrderService | getOrder | response | droppedPromotions[].name | string
OrderService | getOrder | response | droppedPromotions[].reason | enum (budgetCapReached)
OrderService | getOrder | response | totalPriceVariance | object |  | Sum across lines.
OrderService | getOrder | response | totalPriceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | totalPriceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | totalPriceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | lines | array of OrderLine | yes
OrderService | getOrder | response | lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | getOrder | response | lines[].variantId | string (uuid) | yes
OrderService | getOrder | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | getOrder | response | lines[].performanceId | string (uuid)
OrderService | getOrder | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | getOrder | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | getOrder | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | getOrder | response | lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | getOrder | response | lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | getOrder | response | lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | getOrder | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | getOrder | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | getOrder | response | lines[].quantity | integer | yes | (min 1)
OrderService | getOrder | response | lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | getOrder | response | lines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | getOrder | response | lines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | getOrder | response | lines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | getOrder | response | lines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | getOrder | response | lines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | getOrder | response | lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | getOrder | response | lines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | lines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | lines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | lines[].holderName | string |  | (nullable)
OrderService | getOrder | response | lines[].dataMaskValues | object |  | Deliberately open.
OrderService | getOrder | response | lines[].serverUnitPrice | object | yes | What the server computed on ingest.
OrderService | getOrder | response | lines[].serverUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | lines[].serverUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | lines[].serverUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | lines[].priceVariance | object |  | Server minus quoted.
OrderService | getOrder | response | lines[].priceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | lines[].priceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | lines[].priceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getOrder | response | lines[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | lines[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | lines[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getOrder | response | lines[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | lines[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | lines[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getOrder | response | lines[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | lines[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | lines[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | lines[].entitlementIds | array of string (uuid) |  | The entitlements this line issued.
OrderService | getOrder | response | lines[].crossRegionRightIds | array of string |  | Redemption rights propagated to other cells for this line.
OrderService | getOrder | response | lines[].reprintCount | integer |  | How many times this line's tickets were reprinted or resent. (min 0; default 0; read-only)
OrderService | getOrder | response | lines[].venueId | string (uuid) |  | The order's venue, copied onto the line (ADR-0044's own example; system-design review SD-008, 29 September) so a line is scoped and partitionable without its order. (read-only)
OrderService | getOrder | response | lines[].discounts | array of OrderLineDiscount |  | The discounts applied to this line, one row each (system-design review SD-008, 29 September). (read-only)
OrderService | getOrder | response | lines[].discounts[].id | string (uuid) | yes
OrderService | getOrder | response | lines[].discounts[].promotionId | string (uuid) |  | The promotion that gave it. (nullable)
OrderService | getOrder | response | lines[].discounts[].source | enum (promotion, promoCode, manual, bundle, member) | yes
OrderService | getOrder | response | lines[].discounts[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getOrder | response | lines[].discounts[].reason | string |  | A cashier's reason for a manual discount. (max length 200; nullable)
OrderService | getOrder | response | payments | array of Payment
OrderService | getOrder | response | payments[].id | string (uuid) | yes
OrderService | getOrder | response | payments[].orderId | string (uuid) | yes
OrderService | getOrder | response | payments[].tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | getOrder | response | payments[].tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | payments[].tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale.
OrderService | getOrder | response | payments[].tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | payments[].tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | payments[].tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | payments[].fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | getOrder | response | payments[].fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | getOrder | response | payments[].changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | getOrder | response | payments[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getOrder | response | payments[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | payments[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | payments[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | payments[].changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getOrder | response | payments[].changeAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrder | response | payments[].changeAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrder | response | payments[].changeAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrder | response | payments[].status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | getOrder | response | payments[].providerName | string |  | (nullable)
OrderService | getOrder | response | payments[].providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | getOrder | response | payments[].providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | getOrder | response | payments[].terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | getOrder | response | payments[].nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | getOrder | response | payments[].nextAction.kind | enum (redirect, terminal)
OrderService | getOrder | response | payments[].nextAction.url | string (uri) |  | (nullable)
OrderService | getOrder | response | payments[].nextAction.expiresAt | string (date-time) |  | (nullable)
OrderService | getOrder | response | payments[].lastInquiryAt | string (date-time) |  | (nullable)
OrderService | getOrder | response | payments[].recordedAt | string (date-time) | yes
OrderService | getOrder | response | payments[].syncedAt | string (date-time) |  | (nullable)
OrderService | getOrder | response | principalId | string (uuid)
OrderService | getOrder | response | workstationId | string (uuid)
OrderService | getOrder | response | shiftId | string (uuid) |  | (nullable)
OrderService | getOrder | response | subjectId | string (uuid) |  | (nullable)
OrderService | getOrder | response | holdLabel | string |  | The label a cashier gave when parking it with holdOrder — how they find it again. (max length 60; read-only; nullable)
OrderService | getOrder | response | heldUntil | string (date-time) |  | When a held order expires and is voided (states/order.yaml), from holdOrder's holdUntil. (read-only; nullable)
OrderService | getOrder | response | createdAt | string (date-time) | yes
OrderService | getOrder | response | recordedAt | string (date-time) | yes
OrderService | getOrder | response | syncedAt | string (date-time) |  | (nullable)
OrderService | getOrder | param (path) | orderId | string (uuid) | yes
OrderService | getOrder | param (header) | X-Consistency-Token | string |  | Opaque token returned by a prior write: the database instance and its WAL LSN (SD-025, 29 September; ADR-0040 allows several instances per region, so an LSN alone is ambiguous).
OrderService | getOrderCalendarEvent | param (path) | orderId | string (uuid) | yes
OrderService | getOrderStatement | response | orderId | string (uuid) | yes
OrderService | getOrderStatement | response | orderNumber | string | yes
OrderService | getOrderStatement | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | getOrderStatement | response | currencyScale | integer |  | Resolved from the region, not stored (ADR-0018, 24 August).
OrderService | getOrderStatement | response | entries | array of object | yes | Sequential.
OrderService | getOrderStatement | response | entries[].kind | enum (sale, payment, refund, void, modification, exchange, fee, variance, …) | yes
OrderService | getOrderStatement | response | entries[].description | string
OrderService | getOrderStatement | response | entries[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getOrderStatement | response | entries[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrderStatement | response | entries[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrderStatement | response | entries[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrderStatement | response | entries[].runningBalance | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getOrderStatement | response | entries[].runningBalance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrderStatement | response | entries[].runningBalance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrderStatement | response | entries[].runningBalance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrderStatement | response | entries[].referenceId | string |  | (nullable)
OrderService | getOrderStatement | response | entries[].principalId | string (uuid) |  | (nullable)
OrderService | getOrderStatement | response | entries[].occurredAt | string (date-time) | yes
OrderService | getOrderStatement | response | totalPaid | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getOrderStatement | response | totalPaid.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrderStatement | response | totalPaid.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrderStatement | response | totalPaid.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrderStatement | response | totalRefunded | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getOrderStatement | response | totalRefunded.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrderStatement | response | totalRefunded.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrderStatement | response | totalRefunded.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrderStatement | response | currentBalance | object | yes | Positive means the guest owes; negative means a refund is outstanding.
OrderService | getOrderStatement | response | currentBalance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getOrderStatement | response | currentBalance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getOrderStatement | response | currentBalance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getOrderStatement | param (path) | orderId | string (uuid) | yes
TenancyService | getOutlet | response | id | string (uuid) | yes | (read-only)
TenancyService | getOutlet | response | code | string | yes | (max length 64)
TenancyService | getOutlet | response | name | string | yes | The outlet's name in English. (max length 200)
TenancyService | getOutlet | response | nameTranslations | OutletNameTranslations |  | The outlet's name in other languages, keyed by ISO 639-1 code (decided 2 October 2026, Chinmay, batch 2 #26, BO-044: "Yes, where a country needs it: the local language plus English"; DEC-031; CHG-CSP…
TenancyService | getOutlet | response | venueId | string (uuid) | yes
TenancyService | getOutlet | response | kind | OutletKind: enum (shop, restaurant, bar, cafe, kiosk, gameFloor, ticketOffice, mobile) | yes
TenancyService | getOutlet | response | outletType | object |  | The service model (DI-319; DEC-196; CHG-CSP-005). (nullable)
TenancyService | getOutlet | response | departmentId | string (uuid) |  | The department the outlet belongs to (DI-319: department, sub-department, cost centre and status; DEC-196; CHG-CSP-005): an OrgUnit of kind department, as Workstation.departmentId. (nullable)
TenancyService | getOutlet | response | zone | string |  | (nullable)
TenancyService | getOutlet | response | stockLocationId | string (uuid) |  | Where this outlet draws stock from. (nullable)
TenancyService | getOutlet | response | costCenterId | string (uuid) |  | Revenue and cost attribution. (nullable)
TenancyService | getOutlet | response | paymentTiming | object |  | Pay first, or send to the kitchen first then pay (DEC-064; CHG-CSP-004). (default sendFirst)
TenancyService | getOutlet | response | admissionContext | object |  | Inside the venue (needs an admission ticket) or standalone (no ticket) (DEC-070; CHG-CSP-004). (default insideVenue)
TenancyService | getOutlet | response | producesForOutletIds | array of string (uuid) |  | One kitchen serving several outlets is a producing outlet (decided 2 October 2026, Chinmay, batch 6 set 5, BO-134: "Yes: via a producing outlet (one kitchen outlet produces for several)"; DEC-188; CH… (default [])
TenancyService | getOutlet | response | saleBoardId | string (uuid) |  | The till layout every till in this outlet uses, unless a till overrides it (decided 2 October 2026, Chinmay, batch 6 set 4, BO-109: "Per outlet, with a till override"; DEC-183; CHG-CSP-006). (nullable)
TenancyService | getOutlet | response | openingHours | array of OpeningHoursWindow |  | The weekly pattern, one entry per window.
TenancyService | getOutlet | response | openingHours[].day | enum (mon, tue, wed, thu, fri, sat, sun) | yes
TenancyService | getOutlet | response | openingHours[].from | string | yes | Local time, 24-hour HH:MM, when the outlet opens. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
TenancyService | getOutlet | response | openingHours[].to | string | yes | Local time, 24-hour HH:MM, when the outlet closes. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
TenancyService | getOutlet | response | openingHours[].endsNextDay | boolean |  | A late-night window is one window past midnight (decided 2 October 2026, Chinmay, batch 6 set 6a, BO-731; DEC-197; CHG-CSP-007). (default False)
TenancyService | getOutlet | response | isActive | boolean
TenancyService | getOutlet | param (path) | outletId | string (uuid) | yes
AccessService | getParkingEntitlement | response | id | string (uuid) |  | (read-only)
AccessService | getParkingEntitlement | response | facilityId | string (uuid) | yes
AccessService | getParkingEntitlement | response | orderId | string (uuid) | yes | The order's id, a UUIDv7 as in /orders/{orderId} (orders.sales_order.id).
AccessService | getParkingEntitlement | response | subjectId | string (uuid) |  | (nullable)
AccessService | getParkingEntitlement | response | plateNumber | string |  | Required in plateWhitelist mode, meaningless in the others. (nullable)
AccessService | getParkingEntitlement | response | plateCountry | string |  | (nullable)
AccessService | getParkingEntitlement | response | mediaCode | string |  | The code presented in none and qrHandoff modes. (nullable)
AccessService | getParkingEntitlement | response | status | object |  | Server-owned. (read-only)
AccessService | getParkingEntitlement | response | pushedAt | string (date-time) |  | (read-only; nullable)
AccessService | getParkingEntitlement | response | pushFailureReason | string |  | (read-only; nullable)
AccessService | getParkingEntitlement | response | validFrom | string (date-time) | yes
AccessService | getParkingEntitlement | response | validTo | string (date-time) | yes
AccessService | getParkingEntitlement | param (path) | entitlementId | string (uuid) | yes
OrderService | getPaymentLink | response | link | object |  | The link as its holder may see it, not the staff record.
OrderService | getPaymentLink | response | link.status | enum (issued, viewed, paid, expired, cancelled, superseded) | yes
OrderService | getPaymentLink | response | link.expiresAt | string (date-time) | yes
OrderService | getPaymentLink | response | link.releaseHoldOnExpiry | boolean
OrderService | getPaymentLink | response | lines | array of OrderLine
OrderService | getPaymentLink | response | lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | getPaymentLink | response | lines[].variantId | string (uuid) | yes
OrderService | getPaymentLink | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | getPaymentLink | response | lines[].performanceId | string (uuid)
OrderService | getPaymentLink | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | getPaymentLink | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | getPaymentLink | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | getPaymentLink | response | lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | getPaymentLink | response | lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | getPaymentLink | response | lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | getPaymentLink | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | getPaymentLink | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | getPaymentLink | response | lines[].quantity | integer | yes | (min 1)
OrderService | getPaymentLink | response | lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | getPaymentLink | response | lines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | getPaymentLink | response | lines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | getPaymentLink | response | lines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | getPaymentLink | response | lines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | getPaymentLink | response | lines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | getPaymentLink | response | lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | getPaymentLink | response | lines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getPaymentLink | response | lines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getPaymentLink | response | lines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getPaymentLink | response | lines[].holderName | string |  | (nullable)
OrderService | getPaymentLink | response | lines[].dataMaskValues | object |  | Deliberately open.
OrderService | getPaymentLink | response | lines[].serverUnitPrice | object | yes | What the server computed on ingest.
OrderService | getPaymentLink | response | lines[].serverUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getPaymentLink | response | lines[].serverUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getPaymentLink | response | lines[].serverUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getPaymentLink | response | lines[].priceVariance | object |  | Server minus quoted.
OrderService | getPaymentLink | response | lines[].priceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getPaymentLink | response | lines[].priceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getPaymentLink | response | lines[].priceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getPaymentLink | response | lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getPaymentLink | response | lines[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getPaymentLink | response | lines[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getPaymentLink | response | lines[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getPaymentLink | response | lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getPaymentLink | response | lines[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getPaymentLink | response | lines[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getPaymentLink | response | lines[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getPaymentLink | response | lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getPaymentLink | response | lines[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getPaymentLink | response | lines[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getPaymentLink | response | lines[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getPaymentLink | response | lines[].entitlementIds | array of string (uuid) |  | The entitlements this line issued.
OrderService | getPaymentLink | response | lines[].crossRegionRightIds | array of string |  | Redemption rights propagated to other cells for this line.
OrderService | getPaymentLink | response | lines[].reprintCount | integer |  | How many times this line's tickets were reprinted or resent. (min 0; default 0; read-only)
OrderService | getPaymentLink | response | lines[].venueId | string (uuid) |  | The order's venue, copied onto the line (ADR-0044's own example; system-design review SD-008, 29 September) so a line is scoped and partitionable without its order. (read-only)
OrderService | getPaymentLink | response | lines[].discounts | array of OrderLineDiscount |  | The discounts applied to this line, one row each (system-design review SD-008, 29 September). (read-only)
OrderService | getPaymentLink | response | lines[].discounts[].id | string (uuid) | yes
OrderService | getPaymentLink | response | lines[].discounts[].promotionId | string (uuid) |  | The promotion that gave it. (nullable)
OrderService | getPaymentLink | response | lines[].discounts[].source | enum (promotion, promoCode, manual, bundle, member) | yes
OrderService | getPaymentLink | response | lines[].discounts[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | getPaymentLink | response | lines[].discounts[].reason | string |  | A cashier's reason for a manual discount. (max length 200; nullable)
OrderService | getPaymentLink | response | amountDue | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getPaymentLink | response | amountDue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getPaymentLink | response | amountDue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getPaymentLink | response | amountDue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getPaymentLink | response | venueName | string
OrderService | getPaymentLink | response | expiresInSeconds | integer
OrderService | getPaymentLink | param (path) | token | string | yes
CatalogueService | getPerformance | response | id | string (uuid) | yes
CatalogueService | getPerformance | response | eventId | string (uuid) | yes
CatalogueService | getPerformance | response | startsAt | string (date-time) | yes
CatalogueService | getPerformance | response | endsAt | string (date-time) | yes
CatalogueService | getPerformance | response | approvalRequestId | string (uuid) |  | BL-048. (nullable)
CatalogueService | getPerformance | response | requiresApprovalToCancel | boolean |  | Cancelling a sold performance is the one transition that needs a name against it. (default True)
CatalogueService | getPerformance | response | status | enum (scheduled, onSale, soldOut, suspended, cancelled, completed) | yes
CatalogueService | getPerformance | response | admissionRulesId | string (uuid) |  | (nullable)
CatalogueService | getPerformance | response | seatMapId | string (uuid) |  | (nullable)
CatalogueService | getPerformance | response | language | string |  | The language the performance is given in, as a BCP 47 tag (en, ar, fr, de, zh, ru, ar-AE). (max length 35; pattern ^[A-Za-z]{2,3}(-[A-Za-z0-9]{1,8})*$; nullable)
CatalogueService | getPerformance | response | format | string |  | How it is presented, free text the venue chooses, e.g. (max length 40; nullable)
CatalogueService | getPerformance | response | minutesOnScreen | integer |  | "Minutes on screen": how long after startsAt the slot is still sold (agreed 7 August, DI-167 and DI-169; added 6 October 2026, CHG-R4-014). (min 0; max 1440; default 0)
CatalogueService | getPerformance | param (path) | performanceId | string (uuid) | yes
WhiteLabelService | getPlatformSubdomain | response | hostname | string | yes | e.g.
WhiteLabelService | getPlatformSubdomain | response | cell | string | yes
WhiteLabelService | getPlatformSubdomain | response | certificate | enum (wildcard)
WhiteLabelService | getPlatformSubdomain | response | isPrimary | boolean |  | True while no custom domain is primary.
CatalogueService | getProduct | response | id | string (uuid) | yes
CatalogueService | getProduct | response | code | string | yes | (max length 64)
CatalogueService | getProduct | response | familyKey | string |  | The same product at another location (decided 29 September, rev 3 REV3-18). (max length 64; pattern ^[A-Za-z0-9_-]+$; nullable)
CatalogueService | getProduct | response | name | string | yes | (max length 200)
CatalogueService | getProduct | response | description | string
CatalogueService | getProduct | response | nameLocalised | object |  | The product's name in each language the venue sells in (6 October 2026, CHG-R4-011), keyed by ISO 639-1 code, e.g. (nullable)
CatalogueService | getProduct | response | descriptionLocalised | object |  | The product's description in each language, as nameLocalised; falls back to description (6 October 2026, CHG-R4-011). (nullable)
CatalogueService | getProduct | response | kind | ProductKind: enum (admission, timedAdmission, datedAdmission, openDated, seated, membership, bundle, fnb, …) | yes | openDated added 24 August from the client's *Create Ticket Flow* board, which names six main ticket types and this was the one with no kind: valid on any date within an eligible range, rather than fo…
CatalogueService | getProduct | response | venueId | string (uuid) | yes
CatalogueService | getProduct | response | scopePath | string | yes
CatalogueService | getProduct | response | createdByPrincipalId | string (uuid) |  | 1.4.18. (read-only)
CatalogueService | getProduct | response | approvedByPrincipalId | string (uuid) |  | (read-only; nullable)
CatalogueService | getProduct | response | responsibleDepartmentId | string (uuid) |  | Who owns this product commercially. (nullable)
CatalogueService | getProduct | response | onSaleFrom | string (date-time) |  | 1.4.8. (nullable)
CatalogueService | getProduct | response | onSaleTo | string (date-time) |  | Retires the product automatically. (nullable)
CatalogueService | getProduct | response | categoryId | string (uuid) |  | Taken from their fnb.product and retail.product, 20 September. (nullable)
CatalogueService | getProduct | response | lifecycleState | ProductLifecycleState: enum (draft, inReview, approved, live, withdrawn, archived)
CatalogueService | getProduct | response | isSellable | boolean | yes | True only when live and carried by a published bundle. (read-only)
CatalogueService | getProduct | response | isStockTracked | boolean |  | Taken from their fnb.product, 20 September. (default False)
CatalogueService | getProduct | response | hasVariants | boolean | yes
CatalogueService | getProduct | response | variantCount | integer
CatalogueService | getProduct | response | segmentTags | array of string |  | 7.3.5.
CatalogueService | getProduct | response | codeSchema | string |  | 7.3.4 specifies [ParkCode]-[ProductType]-[Variant]. (read-only)
CatalogueService | getProduct | response | channels | array of Channel: enum (pos, kiosk, web, mobile, b2b, ota, callCentre)
CatalogueService | getProduct | response | entitlementTemplateId | string (uuid) |  | What the buyer receives. (nullable)
CatalogueService | getProduct | response | blockedOffline | boolean |  | True for seated and retail.
CatalogueService | getProduct | response | dataMaskValues | object |  | Custom fields.
CatalogueService | getProduct | response | guestListing | GuestListing: enum (bookable, infoOnly, hidden) |  | How a product appears to a guest (decided 29 September, rev 3 REV3-14). (default bookable)
CatalogueService | getProduct | response | notBookableLabel | object |  | The label a guest reads on an infoOnly product, e.g. (nullable)
CatalogueService | getProduct | response | salesContact | object |  | Who a guest contacts to book a view-only product (decided 29 September, W3), e.g. (nullable)
CatalogueService | getProduct | response | salesContact.phone | string |  | (max length 32; nullable)
CatalogueService | getProduct | response | salesContact.email | string (email) |  | (max length 254; nullable)
CatalogueService | getProduct | response | salesContact.note | object |  | A line shown under the contact, e.g. (nullable)
CatalogueService | getProduct | response | bookingFlowId | string (uuid) |  | The booking flow this product is sold through (decided 29 September, W8 and W12): a white-label BookingFlow of the venue, which orders the guest's steps (for a workshop, the product first and then th… (nullable)
CatalogueService | getProduct | response | displayTags | array of ProductDisplayTag |  | Short facts a guest reads on the ticket card and under *Read more*: *2 Hours*, *Min 1.10 m*, *Free adult entry*, *Valid 90 days*, *Emirates ID* (decided 29 September, 23SEP-3). (max items 6)
CatalogueService | getProduct | response | displayTags[].kind | enum (clock, height, free, calendar, id) | yes | clock a duration, height a height rule, free something included free, calendar a validity, id a document the guest must bring.
CatalogueService | getProduct | response | displayTags[].label | object | yes | What the guest reads, e.g.
CatalogueService | getProduct | response | displayTags[].derived | boolean |  | True on a tag the server derived on read because the venue set none. (default False; read-only)
CatalogueService | getProduct | response | media | array of ProductMedia |  | The product's own photos and video (decided 29 September, 23SEP-4). (max items 20)
CatalogueService | getProduct | response | media[].assetId | string (uuid) | yes | A MediaAsset of assets.yaml, in status ready.
CatalogueService | getProduct | response | media[].kind | enum (image, video) | yes
CatalogueService | getProduct | response | media[].isPrimary | boolean | yes | The item *Read more* opens on and a listing shows. (default False)
CatalogueService | getProduct | response | media[].displayOrder | integer |  | (default 100)
CatalogueService | getProduct | response | media[].altText | object |  | (nullable)
CatalogueService | getProduct | response | consentQuestionIds | array of string (uuid) |  | The consent questions a guest answers when booking this product, in the order they are asked (decided 29 September, rev 3 REV3-26): *Are you able to swim?*, *Do you hold a scuba certification?*, *I a… (max items 10)
CatalogueService | getProduct | response | requiresTimeWindow | boolean |  | True for a space sold by the hour, e.g. (default False)
CatalogueService | getProduct | response | productOwnerPrincipalId | string (uuid) |  | The product owner (29 September, data model DM3), set with setProductContextOwnership. (nullable)
CatalogueService | getProduct | response | operationalContact | string |  | A principal id or a name, as the context screen takes it. (max length 200; nullable)
CatalogueService | getProduct | response | businessUnitId | string (uuid) |  | (nullable)
CatalogueService | getProduct | response | legalEntityId | string (uuid) |  | A ledger.legal_entity, read through finance. (nullable)
CatalogueService | getProduct | response | attractionId | string (uuid) |  | (nullable)
CatalogueService | getProduct | response | siteId | string (uuid) |  | (nullable)
CatalogueService | getProduct | response | locationId | string (uuid) |  | (nullable)
CatalogueService | getProduct | response | brandId | string (uuid) |  | The brand, as the context screen names it (a catalogue brand category). (nullable)
CatalogueService | getProduct | response | marketCode | string |  | (max length 40; nullable)
CatalogueService | getProduct | response | salesTerritory | string |  | (max length 100; nullable)
CatalogueService | getProduct | response | eventId | string (uuid) |  | The event this product sells admission to (4 October 2026, CHG-FXC-011; WEB-002, WEB-004): a product page finds its event and the event's performances (Performance.eventId) give it dates. (nullable)
CatalogueService | getProduct | param (path) | productId | string (uuid) | yes
CatalogueService | getProductEligibilityRule | response | id | string (uuid) |  | (read-only)
CatalogueService | getProductEligibilityRule | response | productId | string |  | (read-only)
CatalogueService | getProductEligibilityRule | response | minAgeYears | integer |  | (min 0; nullable)
CatalogueService | getProductEligibilityRule | response | maxAgeYears | integer |  | (min 0; nullable)
CatalogueService | getProductEligibilityRule | response | minHeightCm | integer |  | (min 50; max 250; nullable)
CatalogueService | getProductEligibilityRule | response | maxHeightCm | integer |  | (min 50; max 250; nullable)
CatalogueService | getProductEligibilityRule | response | heightBandsCm | array of integer |  | Band edges the guest chooses between, e.g. (default [120, 140])
CatalogueService | getProductEligibilityRule | response | accompaniedBelowAge | integer |  | Under this age an adult must be present, e.g. (nullable)
CatalogueService | getProductEligibilityRule | response | guardianSignatureAgeFrom | integer |  | (nullable)
CatalogueService | getProductEligibilityRule | response | guardianSignatureAgeTo | integer |  | Ages needing a guardian's signature, e.g. (nullable)
CatalogueService | getProductEligibilityRule | response | waiverRequired | boolean |  | (default False)
CatalogueService | getProductEligibilityRule | response | swimAbility | enum (notRequired, confident) |  | Superseded for the guest's answer (decided 29 September, rev 3 REV3-26): the swim question is a consent, not a data field. (default notRequired)
CatalogueService | getProductEligibilityRule | response | refundableIfIneligibleAtGate | boolean |  | (default False)
CatalogueService | getProductEligibilityRule | response | requiredCertificationCode | string |  | A certification the participant must hold (decided 29 September, W4; added 30 September), e.g. (max length 60; nullable)
CatalogueService | getProductEligibilityRule | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
CatalogueService | getProductEligibilityRule | param (path) | productId | string | yes
CatalogueService | getPromotion | param (path) | promotionId | string (uuid) | yes
CatalogueService | getPromotionUsage | response | promotionId | string (uuid) | yes
CatalogueService | getPromotionUsage | response | redemptionCount | integer | yes
CatalogueService | getPromotionUsage | response | discountGiven | Money | yes | On the wire this is three fields; in the database it is one column.
CatalogueService | getPromotionUsage | response | discountGiven.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | getPromotionUsage | response | discountGiven.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | getPromotionUsage | response | discountGiven.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | getPromotionUsage | response | budgetCap | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | getPromotionUsage | response | budgetCap.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | getPromotionUsage | response | budgetCap.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | getPromotionUsage | response | budgetCap.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | getPromotionUsage | response | budgetRemaining | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | getPromotionUsage | response | budgetRemaining.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | getPromotionUsage | response | budgetRemaining.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | getPromotionUsage | response | budgetRemaining.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | getPromotionUsage | response | isBudgetExhausted | boolean
CatalogueService | getPromotionUsage | response | byChannel | array of object
CatalogueService | getPromotionUsage | response | byChannel[].channel | SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …) |  | Where a sale came from.
CatalogueService | getPromotionUsage | response | byChannel[].redemptionCount | integer
CatalogueService | getPromotionUsage | response | byChannel[].discountGiven | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | getPromotionUsage | response | byChannel[].discountGiven.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | getPromotionUsage | response | byChannel[].discountGiven.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | getPromotionUsage | response | byChannel[].discountGiven.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | getPromotionUsage | param (path) | promotionId | string (uuid) | yes
WhiteLabelService | getPublishReviewPolicy | response | enabled | boolean | yes | (default False)
WhiteLabelService | getPublishReviewPolicy | response | requiresReviewerOtherThanAuthor | boolean |  | (default True)
WhiteLabelService | getPublishReviewPolicy | response | appliesTo | array of enum (tenantConfig, contentBlocks) |  | What the review covers.
WhiteLabelService | getPublishReviewPolicy | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | getPublishedBookingFlow | response | id | string (uuid) |  | (read-only)
WhiteLabelService | getPublishedBookingFlow | response | venueId | string (uuid) |  | From the path of createBookingFlowDefinition. (read-only)
WhiteLabelService | getPublishedBookingFlow | response | flowTypeKey | BookingFlowTypeKey: enum (datedDayPass, timedEntry, openDated, seatedFixedPerformance, seatedDateTimeSeatMap, experienceWorkshop, surfSession, meetingRoomHourly, …) | yes | The flow types the system catalogue offers (decided 29 September, W12; impact.md b).
WhiteLabelService | getPublishedBookingFlow | response | name | string | yes | Staff-facing, e.g. (max length 80)
WhiteLabelService | getPublishedBookingFlow | response | isDefaultForType | boolean |  | At most one per venue and type; setting it takes it from the previous default. (default False)
WhiteLabelService | getPublishedBookingFlow | response | isEnabled | boolean |  | A disabled flow is kept and not published; products naming it fall back to the default. (default True)
WhiteLabelService | getPublishedBookingFlow | response | steps | array of BookingFlowStep |  | Every step of the type, in the venue's order. (max items 30)
WhiteLabelService | getPublishedBookingFlow | response | steps[].id | string (uuid) |  | (read-only)
WhiteLabelService | getPublishedBookingFlow | response | steps[].bookingFlowId | string (uuid) |  | (read-only)
WhiteLabelService | getPublishedBookingFlow | response | steps[].stepKey | BookingFlowStepKey: enum (location, helpMeChoose, product, date, time, performance, level, language, …) | yes | Every step a guest booking flow can hold (decided 29 September, W12).
WhiteLabelService | getPublishedBookingFlow | response | steps[].enabled | boolean | yes | A required step cannot be off; the flow saves and isValid turns false.
WhiteLabelService | getPublishedBookingFlow | response | steps[].sortOrder | integer | yes | (min 0)
WhiteLabelService | getPublishedBookingFlow | response | steps[].requirement | enum (required, optional, conditional) |  | From the flow type, so the CMS can mark the step without a second read. (read-only)
WhiteLabelService | getPublishedBookingFlow | response | steps[].settings | object |  | The step's own settings, by the names the type's stepSettings gives for this step (e.g. (default {})
WhiteLabelService | getPublishedBookingFlow | response | settings | BookingFlowLevelSettings |  | The settings that belong to one flow, not to the venue (decided 29 September, W12).
WhiteLabelService | getPublishedBookingFlow | response | settings.performanceReveal | enum (dateTimeTicket, allAtOnce) |  | Performance reveal (rev 3 REV3-2). (default dateTimeTicket)
WhiteLabelService | getPublishedBookingFlow | response | settings.signInAt | enum (afterAddOns, atPayment) |  | Where the guest is asked to sign in, or for a guest-checkout code (rev 3 REV3-3). (default afterAddOns)
WhiteLabelService | getPublishedBookingFlow | response | settings.seatEventDateMode | enum (inlineStep, popupOnSeatMap) |  | Date and time on a seated event (rev 3 REV3-4). (default inlineStep)
WhiteLabelService | getPublishedBookingFlow | response | settings.extrasStep | enum (auto, always, never) |  | auto shows the extras step only when the cart's products have add-ons; never is the same as turning the optional extras step off. (default auto)
WhiteLabelService | getPublishedBookingFlow | response | settings.quickTour | boolean |  | Quick tour (rev 3 REV3-20). (default False)
WhiteLabelService | getPublishedBookingFlow | response | settings.consentQuestionIds | array of string (uuid) |  | The flow's own consent questions (rev 3 REV3-26). (max items 10; default [])
WhiteLabelService | getPublishedBookingFlow | response | isValid | boolean |  | Whether the flow passes validateBookingFlow; worked out in the same transaction as each write. (read-only)
WhiteLabelService | getPublishedBookingFlow | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | getPublishedBookingFlow | response | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | getPublishedBookingFlow | param (path) | venueId | string (uuid) | yes
WhiteLabelService | getPublishedBookingFlow | param (query) | productId | string (uuid)
WhiteLabelService | getPublishedBookingFlow | param (query) | productCategoryId | string (uuid)
WhiteLabelService | getPublishedBookingFlow | param (query) | flowTypeKey | BookingFlowTypeKey: enum (datedDayPass, timedEntry, openDated, seatedFixedPerformance, seatedDateTimeSeatMap, experienceWorkshop, surfSession, meetingRoomHourly, …)
WhiteLabelService | getPublishedGuidedChoice | response | id | string (uuid) | yes | UUIDv7. (read-only)
WhiteLabelService | getPublishedGuidedChoice | response | venueId | string (uuid) | yes | From the path of createGuidedChoice. (read-only)
WhiteLabelService | getPublishedGuidedChoice | response | name | string | yes | Staff-facing name, e.g. (max length 80)
WhiteLabelService | getPublishedGuidedChoice | response | mode | enum (button, popupOnArrival, off) | yes | How the guest reaches it (rev 3 REV3-11). (default button)
WhiteLabelService | getPublishedGuidedChoice | response | showBanner | boolean |  | The dark banner under the products ("Choose from the experiences above or let us help you decide") with a Help me choose button. (default True)
WhiteLabelService | getPublishedGuidedChoice | response | behaviour | enum (filter, recommend) |  | filter (default) narrows the list; recommend ends on one result card (decided 29 September, W4). (default filter)
WhiteLabelService | getPublishedGuidedChoice | response | showEverything | boolean |  | The "Show everything" link under a filtered list, which clears the answers (W4). (default True)
WhiteLabelService | getPublishedGuidedChoice | response | questions | array of object | yes | One to four questions (decided 29 September, W4: the Deep Dive reference asks three or four; rev 3 REV3-11 allowed two). (min items 1; max items 4)
WhiteLabelService | getPublishedGuidedChoice | response | questions[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | getPublishedGuidedChoice | response | questions[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | getPublishedGuidedChoice | response | questions[].kind | enum (choice, yesNo, age, level, certification) |  | What the question asks (decided 29 September, W4). (default choice)
WhiteLabelService | getPublishedGuidedChoice | response | questions[].sortOrder | integer | yes | (min 0)
WhiteLabelService | getPublishedGuidedChoice | response | questions[].answers | array of object | yes | Two to four answers; the prototype shows three (proposed, client to correct, rev 3 REV3-11). (min items 2; max items 4)
WhiteLabelService | getPublishedGuidedChoice | response | questions[].answers[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | getPublishedGuidedChoice | response | questions[].answers[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | getPublishedGuidedChoice | response | questions[].answers[].body | object |  | The one-liner under the title, at most 140 characters in each language.
WhiteLabelService | getPublishedGuidedChoice | response | questions[].answers[].icon | string |  | An icon name from the guest app's icon set. (max length 40; nullable)
WhiteLabelService | getPublishedGuidedChoice | response | questions[].answers[].badge | object |  | Optional, e.g. (nullable)
WhiteLabelService | getPublishedGuidedChoice | response | questions[].answers[].sortOrder | integer | yes | (min 0)
WhiteLabelService | getPublishedGuidedChoice | response | questions[].answers[].target | object |  | Required with behaviour recommend on the last question; optional with filter, where it is the card shown above the filtered list. (nullable)
WhiteLabelService | getPublishedGuidedChoice | response | questions[].answers[].filter | object |  | What this answer keeps in the list (decided 29 September, W4). (nullable)
WhiteLabelService | getPublishedGuidedChoice | response | questions[].answers[].consentPrefill | object |  | Pre-fills a REV3-26 consent question from this answer (decided 29 September, W4). (nullable)
WhiteLabelService | getPublishedGuidedChoice | response | questions[].answers[].result | object |  | The result card when this answer decides the result. (nullable)
WhiteLabelService | getPublishedGuidedChoice | response | status | object | yes | (read-only)
WhiteLabelService | getPublishedGuidedChoice | response | source | enum (manual, aiSuggested) | yes | manual when staff created it; aiSuggested when the ai service proposed it (a service caller). (read-only)
WhiteLabelService | getPublishedGuidedChoice | response | suggestionRef | string |  | For aiSuggested, the id of the ai job that proposed it. (read-only; nullable)
WhiteLabelService | getPublishedGuidedChoice | response | publishedAt | string (date-time) |  | (read-only; nullable)
WhiteLabelService | getPublishedGuidedChoice | response | publishedBy | string (uuid) |  | The person who published it. (read-only; nullable)
WhiteLabelService | getPublishedGuidedChoice | response | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | getPublishedGuidedChoice | param (path) | venueId | string (uuid) | yes
WhiteLabelService | getPublishedTenantConfig | response | tenantId | string (uuid) | yes
WhiteLabelService | getPublishedTenantConfig | response | publishedVersion | string | yes | The ConfigVersion.version this answer was read from; a client holding the same version keeps its copy.
WhiteLabelService | getPublishedTenantConfig | response | publishedAt | string (date-time) | yes
WhiteLabelService | getPublishedTenantConfig | response | brand | BrandIdentity |  | Every *AssetRef here is a MediaAsset id from the assets library (createUpload then completeUpload), PNG or SVG and at most 2 MB (decided 28 September, audit R270).
WhiteLabelService | getPublishedTenantConfig | response | brand.logoAssetRef | string (uuid) | yes | The primary logo.
WhiteLabelService | getPublishedTenantConfig | response | brand.logoDarkAssetRef | string (uuid) |  | Used on dark backgrounds. (nullable)
WhiteLabelService | getPublishedTenantConfig | response | brand.logoVariant | enum (light, dark, duotone) |  | Which lockup sits in the nav bar, and whose colours drive the theme (decided 29 September, rev 3 CFG-4). (default light)
WhiteLabelService | getPublishedTenantConfig | response | brand.faviconAssetRef | string (uuid) |  | The browser tab icon for the guest web app. (nullable)
WhiteLabelService | getPublishedTenantConfig | response | brand.splashImageAssetRefs | array of string (uuid) |  | Splash images, shown in order.
WhiteLabelService | getPublishedTenantConfig | response | brand.splashDurationSeconds | integer |  | (min 0; max 10; default 3)
WhiteLabelService | getPublishedTenantConfig | response | brand.splashBackgroundColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getPublishedTenantConfig | response | brand.showLoadingIndicator | boolean |  | (default True)
WhiteLabelService | getPublishedTenantConfig | response | brand.splashChangeScope | object |  | Always buildTime for native apps. (read-only)
WhiteLabelService | getPublishedTenantConfig | response | brand.introVideoAssetRef | string (uuid) |  | The optional intro video (decided 29 September, MOB-5). (nullable)
WhiteLabelService | getPublishedTenantConfig | response | brand.introVideoMode | enum (off, firstLaunch, everyLaunch) |  | When GST-001 plays it full screen. (default off)
WhiteLabelService | getPublishedTenantConfig | response | brand.showPoweredBy | boolean |  | "Powered by TICVAI", a configuration toggle, on by default (Chinmay, 2 October, workbook Q160 and the pre-apply round; consistent with DI-297; CHG-CSA-036). (default True)
WhiteLabelService | getPublishedTenantConfig | response | appIcons | AppIcons
WhiteLabelService | getPublishedTenantConfig | response | appIcons.sourceAssetRef | string (uuid) | yes | The MediaAsset id of the 1024×1024 source.
WhiteLabelService | getPublishedTenantConfig | response | appIcons.derived | array of object |  | Generated by setAppIcons from the source, one entry per platform and size — the iOS and Android store sets and the web favicons listed on setAppIcons (audit R163). (read-only)
WhiteLabelService | getPublishedTenantConfig | response | appIcons.derived[].platform | enum (ios, android, web)
WhiteLabelService | getPublishedTenantConfig | response | appIcons.derived[].size | string
WhiteLabelService | getPublishedTenantConfig | response | appIcons.derived[].assetRef | string (uuid)
WhiteLabelService | getPublishedTenantConfig | response | appIcons.changeScope | object | yes | Always buildTime — icons are baked into the binary. (read-only)
WhiteLabelService | getPublishedTenantConfig | response | appIcons.liveVersion | string |  | Icon currently shipped. (read-only; nullable)
WhiteLabelService | getPublishedTenantConfig | response | appIcons.requiresRebuild | boolean |  | True while the draft's source differs from the icon in liveVersion. (read-only)
WhiteLabelService | getPublishedTenantConfig | response | theme | Theme
WhiteLabelService | getPublishedTenantConfig | response | theme.primaryColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getPublishedTenantConfig | response | theme.secondaryColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getPublishedTenantConfig | response | theme.accentColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getPublishedTenantConfig | response | theme.backgroundColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getPublishedTenantConfig | response | theme.textColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getPublishedTenantConfig | response | theme.darkMode | object |  | Deprecated and ignored (Chinmay, 2 October, workbook Q150 and the pre-apply round; CHG-CSA-035).
WhiteLabelService | getPublishedTenantConfig | response | theme.darkMode.primaryColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getPublishedTenantConfig | response | theme.darkMode.backgroundColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getPublishedTenantConfig | response | theme.darkMode.textColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getPublishedTenantConfig | response | theme.cornerRadius | integer |  | The prototype's 0 to 22 px slider sits inside these bounds (rev 3 CFG-2, no change). (min 0; max 32)
WhiteLabelService | getPublishedTenantConfig | response | theme.surfaceStyle | enum (glass, solid) |  | Cards and panels as frosted glass or opaque (decided 29 September, rev 3 CFG-3). (default glass)
WhiteLabelService | getPublishedTenantConfig | response | theme.buttonStyle | enum (solid, outline, pill) |  | Button shape (decided 29 September, rev 3 CFG-3). (default solid)
WhiteLabelService | getPublishedTenantConfig | response | theme.componentColours | object |  | Colours for single interactive elements (decided 17 September, M17-11).
WhiteLabelService | getPublishedTenantConfig | response | theme.componentColours.primaryCta | ThemeComponentColour
WhiteLabelService | getPublishedTenantConfig | response | theme.componentColours.payButton | ThemeComponentColour
WhiteLabelService | getPublishedTenantConfig | response | theme.componentColours.addToCart | ThemeComponentColour
WhiteLabelService | getPublishedTenantConfig | response | theme.componentColours.buyTicketsButton | ThemeComponentColour
WhiteLabelService | getPublishedTenantConfig | response | theme.componentColours.link | ThemeComponentColour
WhiteLabelService | getPublishedTenantConfig | response | theme.componentColours.badge | ThemeComponentColour
WhiteLabelService | getPublishedTenantConfig | response | fonts | FontConfig
WhiteLabelService | getPublishedTenantConfig | response | fonts.primaryLatin | string | yes
WhiteLabelService | getPublishedTenantConfig | response | fonts.primaryArabic | string |  | Required when ar is among the tenant's languages (audit R163). (nullable)
WhiteLabelService | getPublishedTenantConfig | response | fonts.secondaryLatin | string |  | (nullable)
WhiteLabelService | getPublishedTenantConfig | response | fonts.secondaryArabic | string |  | Required whenever secondaryLatin is set and ar is among the tenant's languages (decided 28 September, audit R163). (nullable)
WhiteLabelService | getPublishedTenantConfig | response | fonts.customFontAssetRefs | array of string (uuid) |  | Uploaded font files, as MediaAsset ids.
WhiteLabelService | getPublishedTenantConfig | response | fonts.changeScope | object |  | Custom font files are buildTime; selecting a bundled face is runtime. (read-only)
WhiteLabelService | getPublishedTenantConfig | response | header | HeaderConfig
WhiteLabelService | getPublishedTenantConfig | response | header.layout | enum (logoLeft, logoCentre, logoWithMenu) | yes
WhiteLabelService | getPublishedTenantConfig | response | header.showLogo | boolean |  | (default True)
WhiteLabelService | getPublishedTenantConfig | response | header.showMenu | boolean |  | (default True)
WhiteLabelService | getPublishedTenantConfig | response | header.showNotifications | boolean |  | (default True)
WhiteLabelService | getPublishedTenantConfig | response | header.backgroundColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getPublishedTenantConfig | response | footer | FooterConfig |  | BL-002.
WhiteLabelService | getPublishedTenantConfig | response | footer.id | string (uuid) | yes | (read-only)
WhiteLabelService | getPublishedTenantConfig | response | footer.scopePath | string | yes | The partition key (ADR-0005), written at tenant scope by the server. (read-only)
WhiteLabelService | getPublishedTenantConfig | response | footer.columns | array of object
WhiteLabelService | getPublishedTenantConfig | response | footer.columns[].heading | string
WhiteLabelService | getPublishedTenantConfig | response | footer.columns[].links | array of object
WhiteLabelService | getPublishedTenantConfig | response | footer.legalLinks | object |  | Required links, held separately from the free-form columns — a tenant reorganising their footer must not be able to remove the privacy notice by accident.
WhiteLabelService | getPublishedTenantConfig | response | footer.legalLinks.termsUrl | string
WhiteLabelService | getPublishedTenantConfig | response | footer.legalLinks.privacyUrl | string
WhiteLabelService | getPublishedTenantConfig | response | footer.legalLinks.accessibilityUrl | string |  | (nullable)
WhiteLabelService | getPublishedTenantConfig | response | footer.legalLinks.cookiePolicyUrl | string |  | (nullable)
WhiteLabelService | getPublishedTenantConfig | response | footer.copyrightText | string
WhiteLabelService | getPublishedTenantConfig | response | footer.socialLinks | array of object
WhiteLabelService | getPublishedTenantConfig | response | footer.socialLinks[].platform | string
WhiteLabelService | getPublishedTenantConfig | response | footer.socialLinks[].url | string
WhiteLabelService | getPublishedTenantConfig | response | navigation | NavigationConfig |  | The mobile tab set is venue configuration (decided 29 September, MOB-1; 29 September brief decision 6).
WhiteLabelService | getPublishedTenantConfig | response | navigation.id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | getPublishedTenantConfig | response | navigation.kind | enum (bottomNavigation, drawer, tabs) | yes
WhiteLabelService | getPublishedTenantConfig | response | navigation.items | array of object | yes | (max items 12)
WhiteLabelService | getPublishedTenantConfig | response | navigation.items[].id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | getPublishedTenantConfig | response | navigation.items[].label | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | getPublishedTenantConfig | response | navigation.items[].icon | string
WhiteLabelService | getPublishedTenantConfig | response | navigation.items[].target | LinkTarget | yes
WhiteLabelService | getPublishedTenantConfig | response | navigation.items[].isVisible | boolean | yes | At most five may be visible in bottom navigation; the rest overflow.
WhiteLabelService | getPublishedTenantConfig | response | navigation.items[].sortOrder | integer | yes
WhiteLabelService | getPublishedTenantConfig | response | navigation.buyButton | object |  | The persistent Buy tickets button (decided 29 September, MOB-2). (nullable)
WhiteLabelService | getPublishedTenantConfig | response | navigation.buyButton.style | enum (raised, floating, flat, hidden) |  | raised sits in the centre of the tab bar, as the v4 prototype shows; hidden turns it off. (default raised)
WhiteLabelService | getPublishedTenantConfig | response | navigation.buyButton.label | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | getPublishedTenantConfig | response | homepage | HomepageLayout |  | The client-approved web and app wireframes are the layout (Chinmay, 2 October, workbook Q163; CHG-CSA-040): sections, their order and their options follow the approved wireframes and change only wher…
WhiteLabelService | getPublishedTenantConfig | response | homepage.templateKey | string |  | The landing-page template this layout started from (listLandingPageTemplates), or null for a layout composed from scratch (CHG-CSA-037). (nullable)
WhiteLabelService | getPublishedTenantConfig | response | homepage.landingSource | enum (storefront, ownSite) |  | storefront: this home is the tenant's landing page. (default storefront)
WhiteLabelService | getPublishedTenantConfig | response | homepage.id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | getPublishedTenantConfig | response | homepage.sections | array of object | yes
WhiteLabelService | getPublishedTenantConfig | response | homepage.sections[].id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | getPublishedTenantConfig | response | homepage.sections[].kind | HomepageSectionKind: enum (heroBanner, quickActions, tickets, whatsOn, attractions, membership, dining, shop, …) | yes | Which module each section needs, proposed, client to correct (decided 28 September, audit R163).
WhiteLabelService | getPublishedTenantConfig | response | homepage.sections[].title | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | getPublishedTenantConfig | response | homepage.sections[].sortOrder | integer | yes
WhiteLabelService | getPublishedTenantConfig | response | homepage.sections[].isVisible | boolean | yes
WhiteLabelService | getPublishedTenantConfig | response | homepage.sections[].contentPageId | string (uuid) |  | (nullable)
WhiteLabelService | getPublishedTenantConfig | response | homepage.sections[].maxItems | integer |  | How many cards the section shows, the venue's choice (Chinmay, 2 October, workbook Q152: every customisation option of the approved wireframe, including the card count per section; CHG-CSA-040). (nullable)
WhiteLabelService | getPublishedTenantConfig | response | homepage.sections[].scrollAnimation | enum (rise, scale, slide, blur, none) |  | How the section enters as the guest scrolls (Chinmay, 2 October, workbook Q153: "must be there"; DI-1088; CHG-CSA-040). (default rise)
WhiteLabelService | getPublishedTenantConfig | response | homepage.sections[].heroStyle | enum (carousel, video, poster, split, None) |  | For heroBanner only (decided 29 September, MOB-3). (nullable)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow | object |  | The booking-flow display settings, resolved for venueId when one was sent (the tenant's values with that venue's venueOverrides entry laid over, rev 3 CFG-11).
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.preset | enum (auto, ticketBox, playCentre, venueSite, marketplace, singleEvent, season, custom) |  | L1 Ticket box … L6 Season. (default auto)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.stepIndicator | enum (bar, numbered, dots, segmented, breadcrumb, pills, ticks, none) |  | (default bar)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.cartLayout | enum (sidebarRight, sidebarLeft, slideInRight, slideUpBottom, singleColumn, floatingIcon) |  | floatingIcon is a round basket button with the item count that opens the cart (decided 29 September, rev 3 REV3-10). (default sidebarRight)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.cartSideInRtl | enum (keepRight, mirror) |  | The cart side when the guest reads Arabic or another right-to-left language (decided 29 September, rev 3 REV3-10). (default keepRight)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.cardLayout | enum (stackedRows, splitRows, cardsAcross, posterCards) |  | How ticket and product cards are laid out (decided 29 September, rev 3 DG-6). (default stackedRows)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.cardSize | enum (compact, standard, large, extraLarge) |  | Labels Compact, Standard, Large, Extra large (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.seatPicker | enum (bowl, zonesThenSeats, zonesOnly, seatsOnly) |  | Default bowl, as the prototype has it (decided 29 September, rev 3 CFG-6). (default bowl)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.mapView | enum (2d, 3d) |  | (default 3d)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.density | enum (compact, standard, roomy) |  | Labels Compact, Standard, Roomy, default Compact as the design has it (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.embedMode | enum (fullPage, embedded) |  | embedded hides the hero banner, event page and venue header, for a flow placed inside the venue's own site. (default fullPage)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.heroBanner | boolean |  | (default True)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.searchInBanner | boolean |  | Off by default, as the prototype has it (decided 29 September, rev 3 CFG-6). (default False)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.eventBannerDates | boolean |  | Dates in event banner (decided 29 September, rev 3 23SEP-19). (default False)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.singleEventPage | boolean |  | (default False)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.quantitiesOnAddOns | boolean |  | (default True)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.timesPerPage | enum (8, 12, 24, all) |  | Times per page (decided 29 September, rev 3 REV3-1). (default 24)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.dayPartFilter | boolean |  | Morning, afternoon and evening chips with counts above the times (decided 29 September, rev 3 REV3-1). (default True)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.dayPartBoundaries | object |  | Where the day parts divide, in the venue's time zone (decided 29 September, rev 3 REV3-1).
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.dayPartBoundaries.afternoonStartsAt | string |  | (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; default 12:00)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.dayPartBoundaries.eveningStartsAt | string |  | (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; default 17:00)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.seatViewPosition | enum (bottom, right, left, top) |  | Where the view-from-your-seat box sits around the seat map (decided 29 September, rev 3 REV3-5). (default bottom)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.seatTimeBar | boolean |  | Time bar above the seat map (decided 29 September, rev 3 REV3-6). (default True)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.ticketCategories | enum (categoryThenSubcategory, flatList) |  | How tickets are grouped (decided 29 September, rev 3 REV3-16). (default categoryThenSubcategory)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.ticketTags | boolean |  | Tags on tickets (decided 29 September, rev 3 23SEP-3). (default True)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.cardInfo | boolean |  | Extra info on cards (decided 29 September, rev 3 23SEP-6). (default True)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.conciergeMascot | boolean |  | The concierge as mascot art or a plain button (decided 29 September, rev 3 CFG-5). (default True)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.showInfoOnly | boolean |  | Show info-only products (decided 29 September, rev 3 REV3-14). (default True)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.locationSwitcher | boolean |  | Location switcher (decided 29 September, rev 3 REV3-18). (default False)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.guestContactFields | array of enum (email, mobile, name) |  | What the guest-checkout pop-up asks, and nothing else (decided 29 September, W1). (min items 1; max items 3; default ['email'])
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.dateStripDays | integer |  | The date strip (decided 17 September, M17-08). (min 3; max 31; default 7)
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.venueOverrides | array of BookingFlowVenueOverride |  | Per-venue overrides, at most one per venue. (max items 200; default [])
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.venueOverrides[].venueId | string (uuid) | yes | One of the tenant's active venues.
WhiteLabelService | getPublishedTenantConfig | response | bookingFlow.venueOverrides[].settings | BookingFlowSettings | yes | Every guest booking-flow setting, once.
WhiteLabelService | getPublishedTenantConfig | response | languages | LanguageConfig
WhiteLabelService | getPublishedTenantConfig | response | languages.languages | array of string | yes | A tenant may add or select interface languages beyond English and Arabic (Chinmay, 2 October, workbook Q145; CHG-CSA-039).
WhiteLabelService | getPublishedTenantConfig | response | languages.defaultLanguage | string | yes | (pattern ^[a-z]{2}$)
WhiteLabelService | getPublishedTenantConfig | response | languages.uiStringCoverage | array of object |  | How complete the interface strings are in each enabled language (CHG-CSA-039). (read-only)
WhiteLabelService | getPublishedTenantConfig | response | languages.uiStringCoverage[].language | string
WhiteLabelService | getPublishedTenantConfig | response | languages.uiStringCoverage[].coveragePercent | number |  | (min 0; max 100)
WhiteLabelService | getPublishedTenantConfig | response | languages.uiStringCoverage[].status | enum (complete, draft, missing)
WhiteLabelService | getPublishedTenantConfig | response | languages.rtlLanguages | array of string |  | The enabled languages written right to left — those whose Unicode CLDR character order is right-to-left (Arabic, ar, among them). (read-only)
WhiteLabelService | getPublishedTenantConfig | response | languages.translationGaps | array of object |  | Content lacking a version in an enabled language. (read-only)
WhiteLabelService | getPublishedTenantConfig | response | languages.translationGaps[].language | string
WhiteLabelService | getPublishedTenantConfig | response | languages.translationGaps[].missingCount | integer
WhiteLabelService | getPublishedTenantConfig | response | languages.translationGaps[].areas | array of string
WhiteLabelService | getPublishedTenantConfig | response | accessibility | AccessibilitySettings |  | BL-065, 2.1.27.
WhiteLabelService | getPublishedTenantConfig | response | accessibility.largeTextAvailable | boolean |  | (default True)
WhiteLabelService | getPublishedTenantConfig | response | accessibility.highContrastAvailable | boolean |  | (default True)
WhiteLabelService | getPublishedTenantConfig | response | accessibility.simplifiedNavigationAvailable | boolean |  | (default True)
WhiteLabelService | getPublishedTenantConfig | response | accessibility.screenReaderSupported | boolean |  | (default True)
WhiteLabelService | getPublishedTenantConfig | response | accessibility.reachableHeightModeAvailable | boolean |  | Moves the interface to the lower half of the screen for a guest using a wheelchair. (default False)
WhiteLabelService | getPublishedTenantConfig | response | accessibility.sessionTimeoutMultiplier | number |  | Timeouts are an accessibility barrier nobody counts. (default 1)
WhiteLabelService | getPublishedTenantConfig | response | enabledModules | array of ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) |  | The modules the tenant has enabled and published, so a guest surface hides a tab or a homepage section for a module that is off.
WhiteLabelService | getPublishedTenantConfig | response | enabledFeatures | array of string |  | The featureKey of every feature toggle that is on in the published version.
WhiteLabelService | getPublishedTenantConfig | response | isInMaintenance | boolean | yes | Live state (setMaintenanceMode), as on getTenantAppStatus.
WhiteLabelService | getPublishedTenantConfig | response | maintenanceMessage | object |  | (nullable)
WhiteLabelService | getPublishedTenantConfig | response | expectedBackAt | string (date-time) |  | (nullable)
WhiteLabelService | getPublishedTenantConfig | response | minimumAppVersion | MinimumAppVersion |  | The oldest guest app build still allowed to run (decided 28 September, audit R073). (nullable)
WhiteLabelService | getPublishedTenantConfig | response | minimumAppVersion.ios | string |  | (pattern ^\d+\.\d+\.\d+$; nullable)
WhiteLabelService | getPublishedTenantConfig | response | minimumAppVersion.android | string |  | (pattern ^\d+\.\d+\.\d+$; nullable)
WhiteLabelService | getPublishedTenantConfig | response | availability | AppAvailability: enum (open, soldOut, closed) |  | The sold-out or closed signal (decided 28 September, audit R073). (default open)
WhiteLabelService | getPublishedTenantConfig | response | availabilityMessage | object |  | (nullable)
WhiteLabelService | getPublishedTenantConfig | response | contact | VenueContact |  | How a guest reaches the venue: WEB-028 Contact & Venue Information, and the screen shown on an error or when the app cannot help (decided 28 September, audit R073). (nullable)
WhiteLabelService | getPublishedTenantConfig | response | contact.phone | string |  | (nullable)
WhiteLabelService | getPublishedTenantConfig | response | contact.email | string (email) |  | (nullable)
WhiteLabelService | getPublishedTenantConfig | response | contact.whatsapp | string |  | (nullable)
WhiteLabelService | getPublishedTenantConfig | response | contact.address | object |  | (nullable)
WhiteLabelService | getPublishedTenantConfig | response | contact.openingHours | object |  | Prose, as the guest reads it. (nullable)
WhiteLabelService | getPublishedTenantConfig | response | analyticsProviders | array of PublishedAnalyticsProvider |  | The analytics platforms the storefront and app load (Chinmay, 3 October 2026, Pattern 4; CHG-GCF-005): a guest reads them here instead of listAnalyticsProviders, which needs TENANT_CONFIGURE.
WhiteLabelService | getPublishedTenantConfig | response | analyticsProviders[].provider | enum (googleAnalytics4, googleTagManager, adobeAnalytics, metaPixel, matomo, other) | yes
WhiteLabelService | getPublishedTenantConfig | response | analyticsProviders[].otherProviderName | string |  | The provider's name, when provider is other (StorefrontAnalyticsProvider.providerLabel). (max length 100; nullable)
WhiteLabelService | getPublishedTenantConfig | response | analyticsProviders[].measurementId | string | yes | What the tag or SDK reports to (GA4 G-..., Tag Manager GTM-..., a pixel id). (max length 100)
WhiteLabelService | getPublishedTenantConfig | response | analyticsProviders[].surfaces | array of enum (guestWeb, guestApp) | yes | (min items 1)
WhiteLabelService | getPublishedTenantConfig | response | analyticsProviders[].consentCategory | enum (functional, analytics, personalisation, marketing) | yes | The cookie category the visitor must grant before this provider loads (marketing-crm CookieCategory).
WhiteLabelService | getPublishedTenantConfig | response | paymentTokenisation | object |  | The provider the guest app tokenises cards with (4 October 2026, CHG-FXC-010; GST-071): the providerId storePaymentToken requires, its kind and the publishable key the client SDK needs. (nullable)
WhiteLabelService | getPublishedTenantConfig | response | paymentTokenisation.providerId | string (uuid) | yes
WhiteLabelService | getPublishedTenantConfig | response | paymentTokenisation.providerKind | string | yes
WhiteLabelService | getPublishedTenantConfig | response | paymentTokenisation.publishableKey | string |  | (nullable)
WhiteLabelService | getPublishedTenantConfig | param (query) | venueId | string (uuid) |  | The venue the guest picked (WEB-001, GST-001).
TenancyService | getRegionSettings | response | countryCode | string | yes | ISO 3166-1 alpha-2. (pattern ^[A-Z]{2}$)
TenancyService | getRegionSettings | response | currencyCode | string | yes | (pattern ^[A-Z]{3}$)
TenancyService | getRegionSettings | response | currencyScale | integer | yes | Decimal places for this region's currency. (min 0; max 4)
TenancyService | getRegionSettings | response | timeZone | string | yes | IANA zone, e.g.
TenancyService | getRegionSettings | response | dateFormat | string |  | (default dd/MM/yyyy)
TenancyService | getRegionSettings | response | numberFormat | string |  | (default #,##0.00)
TenancyService | getRegionSettings | response | fiscalYearStartMonth | integer | yes | Varies by country. (min 1; max 12)
TenancyService | getRegionSettings | response | allowedAiResidencies | array of string |  | The region's compliance gate on AI providers (decided 28 September, audit R203; ADR-0009). (default [])
TenancyService | getRegionSettings | response | aiResidencyClass | enum (uaeOnly, globalAllowed, onPrem) |  | The tenant's AI residency class (decided 2 October 2026, Chinmay, "AI residency: per-tenant residency class"; DEC-539; CHG-CSP-009; amends AI-D02 and ADR-0009 section 1). (default uaeOnly)
TenancyService | getRegionSettings | response | aiResidencyClassLocked | boolean |  | Set by TICVAI at onboarding for a government, bank or health tenant (DEC-539), which must stay uaeOnly. (default False; read-only)
TenancyService | getRegionSettings | response | tenantCategory | enum (private, semiGovernment, government, banking, payments, health, difc, adgm) |  | What kind of organisation the tenant is, for AI residency (3 October 2026, CHG-R1S-016; the legal research docs/active/research/openai-key-uae-3-october.md, item 2, and Chinmay's per-tenant residency… (default private; read-only)
TenancyService | getRegionSettings | response | aiResidencyOptIn | object |  | The evidence a globalAllowed opt-in needs under PDPL Article 23 (DEC-539; CHG-CSP-009): the tenant's references to its vendor contract, its DPIA and the notice guests see. (nullable)
TenancyService | getRegionSettings | response | aiResidencyOptIn.vendorContractReference | string |  | (max length 200)
TenancyService | getRegionSettings | response | aiResidencyOptIn.dpiaReference | string |  | (max length 200)
TenancyService | getRegionSettings | response | aiResidencyOptIn.guestNoticeReference | string |  | (max length 200)
TenancyService | getRegionSettings | response | aiResidencyOptIn.confirmedByPrincipalId | string (uuid) |  | (read-only)
TenancyService | getRegionSettings | response | aiResidencyOptIn.confirmedAt | string (date-time) |  | (read-only)
TenancyService | getRegionSettings | response | localLanguageNameLocales | array of string |  | The languages an outlet name must also be given in, in this country (decided 2 October 2026, Chinmay, batch 2 #26: "English plus the local language where the country needs it"; DEC-031; CHG-CSP-005). (default [])
TenancyService | getRegionSettings | response | requiredBillingDocuments | array of object |  | Which documents a TICVAI customer's billing entity must upload, in this country (decided 2 October 2026, Chinmay, batch 6 set 7, ADM-411: "Trade licence always; VAT certificate when a TRN is entered;… (default [{'documentType': 'tradeLicence', 'requiredWhen': 'always'}, {'documentType': 'vatCertificate', 'requiredWhen': 'trnEntered'}])
TenancyService | getRegionSettings | response | requiredBillingDocuments[].documentType | string |  | The document kind, as the subscription contract's PartnerDocument names it (tradeLicence, vatCertificate, ...). (max length 64)
TenancyService | getRegionSettings | response | requiredBillingDocuments[].requiredWhen | enum (always, trnEntered)
TenancyService | getRegionSettings | response | minorAgeThreshold | integer |  | The age below which a guest is a minor here, set per country (decided 2 October 2026, Chinmay, critical set 1, BO-187: "Guardian consent on the venue's form; minor age per country"; DEC-237; CHG-CSP-… (min 0; max 21; default 18)
TenancyService | getRegionSettings | response | placement | Placement |  | Read-only here. (read-only)
TenancyService | getRegionSettings | response | placement.mode | enum (shared, dedicated, isolated, clientHosted) | yes
TenancyService | getRegionSettings | response | placement.cellName | string
TenancyService | getRegionSettings | response | placement.cloudRegion | string
TenancyService | getRegionSettings | response | cellName | string |  | The cell serving this region. (read-only)
TenancyService | getRegionSettings | param (path) | regionId | string (uuid) | yes
ReportingService | getReport | response | name | string | yes | (max length 200)
ReportingService | getReport | response | description | string |  | (max length 1000)
ReportingService | getReport | response | category | ReportCategory: enum (sales, admission, financial, inventory, guest, operations, marketing, workforce, …) | yes
ReportingService | getReport | response | dataSource | DataSource: enum (orders, orderLines, payments, refunds, shifts, scanEvents, entitlements, products, …) | yes | What a report may be built over.
ReportingService | getReport | response | columns | array of ReportColumn | yes | (min items 1)
ReportingService | getReport | response | columns[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | getReport | response | columns[].field | string | yes
ReportingService | getReport | response | columns[].label | string
ReportingService | getReport | response | columns[].aggregation | object |  | (default none)
ReportingService | getReport | response | columns[].sortOrder | integer
ReportingService | getReport | response | columns[].sortDirection | enum (asc, desc)
ReportingService | getReport | response | columns[].format | string |  | (nullable)
ReportingService | getReport | response | columns[].role | enum (dimension, measure) |  | What the column is to a chart (decided 2 October 2026, Chinmay; CHG-FIN-007). (nullable)
ReportingService | getReport | response | columns[].encoding | enum (category, x, y, series, value, size, colour, location, …) |  | Which field well the column fills (CHG-FIN-007), the binding the twenty marks of DashboardTile.visualisation need. (nullable)
ReportingService | getReport | response | columns[].axis | enum (primary, secondary) |  | For a measure on a combo, the axis it is drawn against. (nullable)
ReportingService | getReport | response | columns[].seriesType | enum (bar, line, area) |  | For a measure on a combo, how that series is drawn (CHG-FIN-007). (nullable)
ReportingService | getReport | response | columns[].hierarchyLevel | integer |  | For matrix rows and columns, treemap nesting and decompositionTree levels, the depth of this dimension, 1 outermost. (min 1; nullable)
ReportingService | getReport | response | columns[].unitLabel | string |  | The unit an axis states, for example "AED" or "Admissions". (max length 40; nullable)
ReportingService | getReport | response | filters | array of ReportFilter
ReportingService | getReport | response | filters[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | getReport | response | filters[].field | string | yes
ReportingService | getReport | response | filters[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, contains, …) | yes
ReportingService | getReport | response | filters[].value | object |  | Open on purpose; its type is the field's.
ReportingService | getReport | response | filters[].values | array of object |  | The values for in and notIn, or exactly two (from, to) for between.
ReportingService | getReport | response | filters[].isParameter | boolean |  | Prompted at run time rather than fixed. (default False)
ReportingService | getReport | response | groupBy | array of string
ReportingService | getReport | response | parameters | array of ReportParameter
ReportingService | getReport | response | parameters[].key | string | yes
ReportingService | getReport | response | parameters[].label | string | yes
ReportingService | getReport | response | parameters[].type | FieldType: enum (string, integer, decimal, money, boolean, date, dateTime, uuid, …) | yes
ReportingService | getReport | response | parameters[].isRequired | boolean | yes
ReportingService | getReport | response | parameters[].defaultValue | object |  | Open on purpose.
ReportingService | getReport | response | requiredPermission | Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) | yes | Permission needed to run this report, from the shared Permission vocabulary.
ReportingService | getReport | response | maxDateRangeDays | integer |  | Guards against a query spanning years of scan events. (min 1; default 366; nullable)
ReportingService | getReport | response | id | string (uuid) | yes
ReportingService | getReport | response | version | string | yes | The current version.
ReportingService | getReport | response | isSystem | boolean | yes | Shipped with the platform — seeded at provisioning (BL-053, SeededReport).
ReportingService | getReport | response | isRetired | boolean | yes
ReportingService | getReport | response | estimatedCost | enum (low, medium, high) |  | Informs whether it may run inline or must be queued.
ReportingService | getReport | response | createdByPrincipalId | string (uuid) |  | (nullable)
ReportingService | getReport | response | createdAt | string (date-time) | yes
ReportingService | getReport | response | lastRunAt | string (date-time) |  | (nullable)
ReportingService | getReport | response | scopePath | string |  | The partition key (ADR-0005).
ReportingService | getReport | param (path) | reportId | string (uuid) | yes
OrderService | getReservation | response | id | string (uuid) | yes
OrderService | getReservation | response | venueId | string (uuid) | yes
OrderService | getReservation | response | subjectId | string (uuid) |  | The guest it is held for, from CreateReservationRequest.subjectId. (nullable)
OrderService | getReservation | response | status | enum (held, converted, expired, cancelled) | yes
OrderService | getReservation | response | lines | array of CreateOrderLine
OrderService | getReservation | response | lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | getReservation | response | lines[].variantId | string (uuid) | yes
OrderService | getReservation | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | getReservation | response | lines[].performanceId | string (uuid)
OrderService | getReservation | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | getReservation | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | getReservation | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | getReservation | response | lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | getReservation | response | lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | getReservation | response | lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | getReservation | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | getReservation | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | getReservation | response | lines[].quantity | integer | yes | (min 1)
OrderService | getReservation | response | lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | getReservation | response | lines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | getReservation | response | lines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | getReservation | response | lines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | getReservation | response | lines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | getReservation | response | lines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | getReservation | response | lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | getReservation | response | lines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getReservation | response | lines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getReservation | response | lines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getReservation | response | lines[].holderName | string |  | (nullable)
OrderService | getReservation | response | lines[].dataMaskValues | object |  | Deliberately open.
OrderService | getReservation | response | expiresAt | string (date-time) | yes
OrderService | getReservation | response | createdAt | string (date-time) | yes
OrderService | getReservation | response | convertedOrderId | string (uuid) |  | (nullable)
OrderService | getReservation | param (path) | reservationId | string (uuid) | yes
VenueOpsService | getResourceAvailability | response | resourceId | string (uuid)
VenueOpsService | getResourceAvailability | response | freeWindows | array of object
VenueOpsService | getResourceAvailability | response | freeWindows[].from | string (date-time)
VenueOpsService | getResourceAvailability | response | freeWindows[].to | string (date-time)
VenueOpsService | getResourceAvailability | response | blockedWindows | array of object |  | With a reason, because they are not the same.
VenueOpsService | getResourceAvailability | response | blockedWindows[].from | string (date-time)
VenueOpsService | getResourceAvailability | response | blockedWindows[].to | string (date-time)
VenueOpsService | getResourceAvailability | response | blockedWindows[].reason | enum (booked, held, setup, teardown, maintenance, blackout, closed, cleaning) |  | held is a live ResourceHold (rev 3 REV3-15): taken now, free again if it expires.
VenueOpsService | getResourceAvailability | param (path) | resourceId | string (uuid) | yes
VenueOpsService | getResourceAvailability | param (query) | from | string (date-time) | yes
VenueOpsService | getResourceAvailability | param (query) | to | string (date-time) | yes
VenueOpsService | getResourceHold | response | id | string (uuid) | yes
VenueOpsService | getResourceHold | response | mapId | string (uuid) | yes
VenueOpsService | getResourceHold | response | resourceIds | array of string (uuid) | yes
VenueOpsService | getResourceHold | response | from | string (date-time) | yes
VenueOpsService | getResourceHold | response | to | string (date-time) | yes
VenueOpsService | getResourceHold | response | partySize | integer |  | (nullable)
VenueOpsService | getResourceHold | response | status | enum (held, converted, released, expired) | yes
VenueOpsService | getResourceHold | response | totalPrice | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | getResourceHold | response | totalPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | getResourceHold | response | totalPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | getResourceHold | response | totalPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | getResourceHold | response | heldByPrincipalId | string (uuid) |  | (nullable)
VenueOpsService | getResourceHold | response | subjectId | string (uuid) |  | (nullable)
VenueOpsService | getResourceHold | response | orderId | string (uuid) |  | Set when the order converts it. (nullable)
VenueOpsService | getResourceHold | response | extensionCount | integer |  | (default 0)
VenueOpsService | getResourceHold | response | createdAt | string (date-time) | yes
VenueOpsService | getResourceHold | response | expiresAt | string (date-time) | yes
VenueOpsService | getResourceHold | response | scopePath | string |  | The partition key (ADR-0005), written at venue scope.
VenueOpsService | getResourceHold | param (path) | holdId | string (uuid) | yes
RetailService | getRetailSale | response | id | string | yes
RetailService | getRetailSale | response | receiptNumber | string | yes | Server-assigned: the venue prefix plus a sequence per venue (decided 28 September, audit R152). (read-only)
RetailService | getRetailSale | response | orderId | string | yes | The order in the Order & Payment context.
RetailService | getRetailSale | response | outletId | string (uuid) | yes
RetailService | getRetailSale | response | shiftId | string |  | (nullable)
RetailService | getRetailSale | response | subjectId | string (uuid) |  | (nullable)
RetailService | getRetailSale | response | lines | array of object | yes
RetailService | getRetailSale | response | lines[].lineId | string
RetailService | getRetailSale | response | lines[].merchandiseId | string (uuid)
RetailService | getRetailSale | response | lines[].name | string
RetailService | getRetailSale | response | lines[].quantity | integer
RetailService | getRetailSale | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | getRetailSale | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | getRetailSale | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | getRetailSale | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | getRetailSale | response | lines[].discount | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | getRetailSale | response | lines[].discount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | getRetailSale | response | lines[].discount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | getRetailSale | response | lines[].discount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | getRetailSale | response | lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | getRetailSale | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | getRetailSale | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | getRetailSale | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | getRetailSale | response | lines[].serialNumbers | array of string
RetailService | getRetailSale | response | lines[].returnedQuantity | integer
RetailService | getRetailSale | response | lines[].isReturnable | boolean |  | False once the window has passed or the line is fully returned.
RetailService | getRetailSale | response | lines[].notReturnableReason | string |  | (nullable)
RetailService | getRetailSale | response | subtotal | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | getRetailSale | response | subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | getRetailSale | response | subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | getRetailSale | response | subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | getRetailSale | response | discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | getRetailSale | response | discountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | getRetailSale | response | discountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | getRetailSale | response | discountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | getRetailSale | response | taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | getRetailSale | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | getRetailSale | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | getRetailSale | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | getRetailSale | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
RetailService | getRetailSale | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | getRetailSale | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | getRetailSale | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | getRetailSale | response | reprintCount | integer
RetailService | getRetailSale | response | createdAt | string (date-time) | yes
RetailService | getRetailSale | response | recordedAt | string (date-time)
RetailService | getRetailSale | param (path) | saleId | string (uuid) | yes
RetailService | getReturnPolicy | response | id | string (uuid) |  | Added 20 August. (read-only)
RetailService | getReturnPolicy | response | outletId | string (uuid) | yes
RetailService | getReturnPolicy | response | defaultWindowDays | integer | yes | (min 0)
RetailService | getReturnPolicy | response | requiresReceipt | boolean | yes | (default True)
RetailService | getReturnPolicy | response | allowCashRefundOnCardSale | boolean |  | (default False)
RetailService | getReturnPolicy | response | selfAuthoriseLimit | object |  | Up to this, one cashier may accept a return alone.
RetailService | getReturnPolicy | response | selfAuthoriseLimit.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | getReturnPolicy | response | selfAuthoriseLimit.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | getReturnPolicy | response | selfAuthoriseLimit.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | getReturnPolicy | response | requiresSecondUserAbove | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | getReturnPolicy | response | requiresSecondUserAbove.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | getReturnPolicy | response | requiresSecondUserAbove.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | getReturnPolicy | response | requiresSecondUserAbove.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | getReturnPolicy | response | requiresApprovalAbove | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | getReturnPolicy | response | requiresApprovalAbove.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | getReturnPolicy | response | requiresApprovalAbove.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | getReturnPolicy | response | requiresApprovalAbove.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | getReturnPolicy | response | restockableConditions | array of object |  | Conditions that return stock to sale.
RetailService | getReturnPolicy | response | nonReturnableCategoryIds | array of string (uuid)
RetailService | getReturnPolicy | param (path) | outletId | string (uuid) | yes
CatalogueService | getSeatAvailability | response | performanceId | string (uuid) | yes
CatalogueService | getSeatAvailability | response | seatMapId | string (uuid) | yes
CatalogueService | getSeatAvailability | response | renderMode | enum (graphical, list) | yes | The mode the server actually used.
CatalogueService | getSeatAvailability | response | totals | object | yes
CatalogueService | getSeatAvailability | response | totals.total | integer
CatalogueService | getSeatAvailability | response | totals.available | integer
CatalogueService | getSeatAvailability | response | totals.held | integer
CatalogueService | getSeatAvailability | response | totals.sold | integer
CatalogueService | getSeatAvailability | response | totals.blocked | integer
CatalogueService | getSeatAvailability | response | totals.buffered | integer
CatalogueService | getSeatAvailability | response | byCategory | array of object
CatalogueService | getSeatAvailability | response | byCategory[].categoryId | string (uuid)
CatalogueService | getSeatAvailability | response | byCategory[].available | integer
CatalogueService | getSeatAvailability | response | byCategory[].sold | integer
CatalogueService | getSeatAvailability | response | byCategory[].price | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | getSeatAvailability | response | byCategory[].price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | getSeatAvailability | response | byCategory[].price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | getSeatAvailability | response | byCategory[].price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | getSeatAvailability | response | sections | array of object |  | The map's sections with what a guest screen needs to show the view from each (decided 29 September, rev 3 23SEP-14): the photo where the venue supplied one, otherwise null and the client renders the…
CatalogueService | getSeatAvailability | response | sections[].code | string | yes
CatalogueService | getSeatAvailability | response | sections[].name | string | yes
CatalogueService | getSeatAvailability | response | sections[].viewAssetId | string (uuid) |  | As Section.viewAssetId. (nullable)
CatalogueService | getSeatAvailability | response | sections[].boundary | array of Point |  | As Section.boundary. (nullable)
CatalogueService | getSeatAvailability | response | sections[].boundary[].x | number | yes
CatalogueService | getSeatAvailability | response | sections[].boundary[].y | number | yes
CatalogueService | getSeatAvailability | response | seats | array of object | yes
CatalogueService | getSeatAvailability | response | seats[].seatId | string | yes
CatalogueService | getSeatAvailability | response | seats[].status | SeatStatus: enum (available, held, sold, blocked, buffered, unavailable) | yes
CatalogueService | getSeatAvailability | response | seats[].categoryId | string (uuid) |  | (nullable)
CatalogueService | getSeatAvailability | response | seats[].displayLabel | string |  | What the guest sees, e.g.
CatalogueService | getSeatAvailability | response | seats[].position | object |  | The seat's coordinates on the map, as on Seat. (nullable)
CatalogueService | getSeatAvailability | response | seats[].position.x | number | yes
CatalogueService | getSeatAvailability | response | seats[].position.y | number | yes
CatalogueService | getSeatAvailability | param (path) | performanceId | string (uuid) | yes
CatalogueService | getSeatAvailability | param (query) | sectionCode | string
CatalogueService | getSeatAvailability | param (query) | categoryId | string (uuid)
CatalogueService | getSeatAvailability | param (query) | availableOnly | boolean
CatalogueService | getSeatAvailability | param (query) | mode | enum (auto, graphical, list) |  | graphical requires geometry and returns coordinates.
CatalogueService | getSeatHold | response | id | string | yes
CatalogueService | getSeatHold | response | performanceId | string (uuid) | yes
CatalogueService | getSeatHold | response | seatIds | array of string | yes
CatalogueService | getSeatHold | response | bufferedSeatIds | array of string |  | Neighbours implicitly held by a seating rule.
CatalogueService | getSeatHold | response | status | enum (held, converted, released, expired) | yes
CatalogueService | getSeatHold | response | totalPrice | Money |  | On the wire this is three fields; in the database it is one column.
CatalogueService | getSeatHold | response | totalPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
CatalogueService | getSeatHold | response | totalPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
CatalogueService | getSeatHold | response | totalPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
CatalogueService | getSeatHold | response | heldByPrincipalId | string (uuid) |  | (nullable)
CatalogueService | getSeatHold | response | subjectId | string (uuid) |  | (nullable)
CatalogueService | getSeatHold | response | extensionCount | integer
CatalogueService | getSeatHold | response | createdAt | string (date-time) | yes
CatalogueService | getSeatHold | response | expiresAt | string (date-time) | yes
CatalogueService | getSeatHold | param (path) | holdId | string (uuid) | yes
MarketingService | getSeoMetadata | response | id | string (uuid) | yes | (read-only)
MarketingService | getSeoMetadata | response | entityKind | enum (contentPage, product, event, performance, membership, promotion, venue) | yes
MarketingService | getSeoMetadata | response | entityId | string (uuid) | yes
MarketingService | getSeoMetadata | response | locale | string
MarketingService | getSeoMetadata | response | title | string |  | (nullable)
MarketingService | getSeoMetadata | response | metaDescription | string |  | (nullable)
MarketingService | getSeoMetadata | response | keywords | array of string
MarketingService | getSeoMetadata | response | canonicalUrl | string |  | (nullable)
MarketingService | getSeoMetadata | response | slug | string |  | 22.11.6. (nullable)
MarketingService | getSeoMetadata | response | hreflang | object |  | 22.11.11.
MarketingService | getSeoMetadata | response | schemaOrgType | string |  | (nullable)
MarketingService | getSeoMetadata | response | openGraph | object
MarketingService | getSeoMetadata | response | isAutoGenerated | boolean |  | 22.11.2. (default True)
MarketingService | getSeoMetadata | response | noIndex | boolean |  | (default False)
MarketingService | getSeoMetadata | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | getSeoMetadata | param (query) | entityKind | enum (contentPage, product, event, performance, membership, promotion, venue) | yes
MarketingService | getSeoMetadata | param (query) | entityId | string (uuid) | yes
MarketingService | getSeoMetadata | param (query) | locale | string |  | Absent means the tenant's default language.
OrderService | getShiftCountLines | response | items | array of CashCountLine | yes
OrderService | getShiftCountLines | response | items[].id | string (uuid)
OrderService | getShiftCountLines | response | items[].shiftId | string (uuid) | yes | A UUIDv7, as Shift.id and orders.pos_shift.id are.
OrderService | getShiftCountLines | response | items[].depositBoxId | string (uuid) |  | (nullable)
OrderService | getShiftCountLines | response | items[].countKind | enum (openingFloat, close, movement) |  | Which count this line belongs to — the opening float (openShift), the close (closeShift) or a lift or add (createCashMovement).
OrderService | getShiftCountLines | response | items[].cashMovementId | string (uuid) |  | The movement this line counts, where countKind is movement. (nullable)
OrderService | getShiftCountLines | response | items[].denominationId | string (uuid) | yes | References platform.denomination — face value, kind and sort order live there.
OrderService | getShiftCountLines | response | items[].countedQuantity | integer | yes | How many of this note or coin were in the drawer. (min 0)
OrderService | getShiftCountLines | response | items[].countedValue | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getShiftCountLines | response | items[].countedValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getShiftCountLines | response | items[].countedValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getShiftCountLines | response | items[].countedValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getShiftCountLines | response | items[].countedBy | string (uuid) |  | (nullable)
OrderService | getShiftCountLines | response | items[].countedAt | string (date-time)
OrderService | getShiftCountLines | response | items[].recountOf | string (uuid) |  | A recount points at what it replaces rather than overwriting it. (nullable)
OrderService | getShiftCountLines | response | nextCursor | string
OrderService | getShiftCountLines | response | hasMore | boolean | yes
OrderService | getShiftCountLines | param (path) | shiftId | string (uuid) | yes
OrderService | getShiftCountLines | param (query) | countKind | enum (openingFloat, close, movement)
OrderService | getShiftCountLines | param (query) | pageSize | integer
OrderService | getShiftCountLines | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
WhiteLabelService | getSitePackage | response | id | string (uuid) | yes | (read-only)
WhiteLabelService | getSitePackage | response | version | string
WhiteLabelService | getSitePackage | response | status | enum (building, ready, failed) | yes
WhiteLabelService | getSitePackage | response | downloadUrl | string |  | Short-lived; present when ready. (nullable)
WhiteLabelService | getSitePackage | response | expiresAt | string (date-time) |  | (nullable)
WhiteLabelService | getSitePackage | response | requestedByPrincipalId | string (uuid) |  | (read-only)
WhiteLabelService | getSitePackage | response | platformStaffGrantId | string (uuid) |  | The platform-staff grant it was made under, where platform staff made it (R098). (read-only; nullable)
WhiteLabelService | getSitePackage | response | createdAt | string (date-time) |  | (read-only)
WhiteLabelService | getSitePackage | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | getSitePackage | param (path) | packageId | string (uuid) | yes
WhiteLabelService | getSiteSetupProgress | response | id | string (uuid) |  | (read-only)
WhiteLabelService | getSiteSetupProgress | response | presetKey | enum (themePark, waterPark, museum, theatreAndArena, singleAttraction, playCentre, multiVenue, None) |  | The starting point. (nullable)
WhiteLabelService | getSiteSetupProgress | response | currentStep | object |  | (nullable)
WhiteLabelService | getSiteSetupProgress | response | steps | object |  | One entry per SiteSetupStepKey.
WhiteLabelService | getSiteSetupProgress | response | minimumPathDone | boolean |  | True once the minimum path is done: a logo, the four theme colours, at least one enabled valid booking flow and a published version. (read-only)
WhiteLabelService | getSiteSetupProgress | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | getSiteSetupProgress | response | updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | getStoreAccounts | response | accounts | array of StoreAccount | yes
WhiteLabelService | getStoreAccounts | response | accounts[].id | string (uuid) |  | (read-only)
WhiteLabelService | getStoreAccounts | response | accounts[].store | enum (appleAppStore, googlePlay) | yes
WhiteLabelService | getStoreAccounts | response | accounts[].accountHolderName | string | yes | The client's legal entity as the store knows it. (max length 200)
WhiteLabelService | getStoreAccounts | response | accounts[].dunsNumber | string |  | Required for appleAppStore; Apple enrols an organisation only with its D-U-N-S number. (pattern ^[0-9]{9}$; nullable)
WhiteLabelService | getStoreAccounts | response | accounts[].developerAccountId | string | yes | Apple Team ID, or the Google Play developer account id. (max length 64)
WhiteLabelService | getStoreAccounts | response | accounts[].appIdentifier | string | yes | The bundle id (Apple) or application id (Google) the app is signed with. (max length 155; pattern ^[A-Za-z][A-Za-z0-9_]*(\.[A-Za-z0-9_]+)+$)
WhiteLabelService | getStoreAccounts | response | accounts[].apiCredentialSecretRef | string |  | App Store Connect API key or Play service-account key, sent once and kept in the secret store; this is its reference. (nullable)
WhiteLabelService | getStoreAccounts | response | accounts[].hasApiCredential | boolean |  | (read-only)
WhiteLabelService | getStoreAccounts | response | accounts[].passTypeIdentifier | string |  | The Apple Wallet Pass Type ID (pass.<reverse-domain>), registered in the client's own Apple Developer account, one per brand (Chinmay, 12 October 2026: the client owns the certificate; CHG-R6-033). (pattern ^pass\.[A-Za-z0-9.-]+$; nullable)
WhiteLabelService | getStoreAccounts | response | accounts[].passCertificateSecretRef | string |  | The Pass Type ID certificate (its .p12 and password), from the client's Apple Developer account, sent once and kept in Key Vault; this is its reference, as apiCredentialSecretRef is. (nullable)
WhiteLabelService | getStoreAccounts | response | accounts[].hasPassCertificate | boolean |  | (read-only)
WhiteLabelService | getStoreAccounts | response | accounts[].passCertificateExpiresAt | string (date-time) |  | When the pass certificate expires, read from the certificate when it is stored (CHG-R6-033). (read-only; nullable)
WhiteLabelService | getStoreAccounts | response | accounts[].listing | object |  | The store listing.
WhiteLabelService | getStoreAccounts | response | accounts[].listing.appName | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | getStoreAccounts | response | accounts[].listing.subtitle | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | getStoreAccounts | response | accounts[].listing.description | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | getStoreAccounts | response | accounts[].listing.keywords | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | getStoreAccounts | response | accounts[].listing.category | string
WhiteLabelService | getStoreAccounts | response | accounts[].listing.supportUrl | string (uri)
WhiteLabelService | getStoreAccounts | response | accounts[].listing.privacyPolicyUrl | string (uri)
WhiteLabelService | getStoreAccounts | response | accounts[].listing.screenshotAssetRefs | array of string (uuid)
WhiteLabelService | getStoreAccounts | response | accounts[].scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | getStoreAccounts | response | accounts[].updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | getStoreAccounts | response | items | array of object | yes
WhiteLabelService | getStoreAccounts | response | items[].item | enum (appleDunsNumber, appleDeveloperAccount, googlePlayDeveloperAccount, storeListing, appIcons, publishedConfiguration) | yes
WhiteLabelService | getStoreAccounts | response | items[].done | boolean | yes
WhiteLabelService | getStoreAccounts | response | items[].clientOwned | boolean |  | True for the three accounts, which only the client can open.
WhiteLabelService | getStoreAccounts | response | items[].guidance | string |  | What to do next, in the operator's language.
FnbService | getTableMap | response | outletId | string (uuid) | yes
FnbService | getTableMap | response | zones | array of string
FnbService | getTableMap | response | tables | array of TableState | yes
FnbService | getTableMap | response | tables[].id | string (uuid) | yes
FnbService | getTableMap | response | tables[].label | string | yes | The table code, unique per venue (decided 28 September, audit R108). (max length 32)
FnbService | getTableMap | response | tables[].capacity | integer | yes | (min 1)
FnbService | getTableMap | response | tables[].zone | string |  | (nullable)
FnbService | getTableMap | response | tables[].position | object
FnbService | getTableMap | response | tables[].position.x | number
FnbService | getTableMap | response | tables[].position.y | number
FnbService | getTableMap | response | tables[].shape | enum (round, square, rectangle, booth, bar)
FnbService | getTableMap | response | tables[].isOutOfService | boolean |  | Damaged, or its section closed. (default False)
FnbService | getTableMap | response | tables[].codeGeneration | integer |  | Which printing of the location's ordering code is current (4 October 2026, CHG-FXC-009). (min 1; default 1)
FnbService | getTableMap | response | tables[].status | TableStatus: enum (free, seated, ordered, billRequested, needsClearing, reserved, outOfService) | yes
FnbService | getTableMap | response | tables[].visitId | string (uuid) |  | (nullable)
FnbService | getTableMap | response | tables[].covers | integer |  | (nullable)
FnbService | getTableMap | response | tables[].seatedAt | string (date-time) |  | (nullable)
FnbService | getTableMap | response | tables[].serverPrincipalId | string (uuid) |  | (nullable)
FnbService | getTableMap | response | tables[].billTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | getTableMap | response | tables[].billTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getTableMap | response | tables[].billTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getTableMap | response | tables[].billTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getTableMap | param (path) | outletId | string (uuid) | yes
FnbService | getTableVisit | response | id | string (uuid) | yes
FnbService | getTableVisit | response | tableId | string (uuid) | yes
FnbService | getTableVisit | response | tableLabel | string
FnbService | getTableVisit | response | outletId | string (uuid) | yes
FnbService | getTableVisit | response | covers | integer | yes
FnbService | getTableVisit | response | status | enum (open, billRequested, settled, merged, cancelled) | yes
FnbService | getTableVisit | response | serverPrincipalId | string (uuid) |  | (nullable)
FnbService | getTableVisit | response | subjectId | string (uuid) |  | (nullable)
FnbService | getTableVisit | response | orders | array of FnbOrder | yes
FnbService | getTableVisit | response | orders[].id | string (uuid) | yes
FnbService | getTableVisit | response | orders[].orderNumber | string | yes
FnbService | getTableVisit | response | orders[].outletId | string (uuid) | yes
FnbService | getTableVisit | response | orders[].paymentTiming | object |  | The outlet's payment timing when the order was placed (CHG-CSA-010), kept as a snapshot. (read-only)
FnbService | getTableVisit | response | orders[].sentToKitchenAt | string (date-time) |  | When the order's kitchen tickets were created. (read-only; nullable)
FnbService | getTableVisit | response | orders[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery) | yes
FnbService | getTableVisit | response | orders[].tableVisitId | string (uuid) |  | (nullable)
FnbService | getTableVisit | response | orders[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) | yes | The full lifecycle from 4.6.35.
FnbService | getTableVisit | response | orders[].lines | array of object | yes
FnbService | getTableVisit | response | orders[].lines[].id | string (uuid) | yes
FnbService | getTableVisit | response | orders[].lines[].menuItemId | string (uuid) | yes
FnbService | getTableVisit | response | orders[].lines[].quantity | integer | yes | (min 1)
FnbService | getTableVisit | response | orders[].lines[].modifierOptionIds | array of string (uuid)
FnbService | getTableVisit | response | orders[].lines[].note | string |  | Free text to the kitchen. (max length 200)
FnbService | getTableVisit | response | orders[].lines[].seatNumber | integer |  | Which cover ordered it. (nullable)
FnbService | getTableVisit | response | orders[].lines[].course | integer |  | Course grouping, so the kitchen fires in sequence. (nullable)
FnbService | getTableVisit | response | orders[].lines[].redeemEntitlementId | string |  | A meal combo redeemed at the till or by a scan (29 September, MOB-4; applied 30 September). (nullable)
FnbService | getTableVisit | response | orders[].lines[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) |  | The full lifecycle from 4.6.35.
FnbService | getTableVisit | response | orders[].lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | getTableVisit | response | orders[].lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | getTableVisit | response | orders[].salesOrderId | string (uuid) |  | Retyped 29 September (SD-046), and format: uuid since ADR-0056 (30 September): every id is a uuid, so this joins orders.sales_order.id. (nullable)
FnbService | getTableVisit | response | orders[].updatedAt | string (date-time) |  | Taken from their fnb.order. (nullable)
FnbService | getTableVisit | response | orders[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | getTableVisit | response | orders[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getTableVisit | response | orders[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getTableVisit | response | orders[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getTableVisit | response | orders[].taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | getTableVisit | response | orders[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getTableVisit | response | orders[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getTableVisit | response | orders[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getTableVisit | response | orders[].kitchenTicketId | string (uuid) |  | (nullable)
FnbService | getTableVisit | response | orders[].kitchenTickets | array of KitchenTicket |  | The kitchen tickets this order created, one per station (SD-046). (read-only)
FnbService | getTableVisit | response | orders[].kitchenTickets[].id | string (uuid) | yes
FnbService | getTableVisit | response | orders[].kitchenTickets[].orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | getTableVisit | response | orders[].kitchenTickets[].orderNumber | string
FnbService | getTableVisit | response | orders[].kitchenTickets[].outletId | string (uuid) | yes
FnbService | getTableVisit | response | orders[].kitchenTickets[].tableLabel | string |  | (nullable)
FnbService | getTableVisit | response | orders[].kitchenTickets[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | getTableVisit | response | orders[].kitchenTickets[].coursing | object |  | BL-131. (nullable)
FnbService | getTableVisit | response | orders[].kitchenTickets[].buzzerCode | string |  | BL-128. (nullable)
FnbService | getTableVisit | response | orders[].kitchenTickets[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | getTableVisit | response | orders[].kitchenTickets[].priority | integer |  | Higher fires sooner.
FnbService | getTableVisit | response | orders[].kitchenTickets[].prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | getTableVisit | response | orders[].kitchenTickets[].prioritiseReason | string |  | (nullable)
FnbService | getTableVisit | response | orders[].kitchenTickets[].lines | array of object | yes
FnbService | getTableVisit | response | orders[].kitchenTickets[].createdAt | string (date-time) | yes
FnbService | getTableVisit | response | orders[].kitchenTickets[].targetReadyAt | string (date-time) |  | (nullable)
FnbService | getTableVisit | response | orders[].kitchenTickets[].elapsedSeconds | integer
FnbService | getTableVisit | response | orders[].kitchenTickets[].visitId | string (uuid) |  | The table visit the ticket is for (4 October 2026, CHG-FXC-011; KIT-002): the {visitId} notifyServer takes. (read-only; nullable)
FnbService | getTableVisit | response | orders[].estimatedReadyAt | string (date-time) |  | (nullable)
FnbService | getTableVisit | response | orders[].createdAt | string (date-time) | yes
FnbService | getTableVisit | response | orders[].recordedAt | string (date-time)
FnbService | getTableVisit | response | orders[].syncedAt | string (date-time) |  | (nullable)
FnbService | getTableVisit | response | mergedIntoVisitId | string (uuid) |  | (nullable)
FnbService | getTableVisit | response | mergedFromVisitIds | array of string (uuid)
FnbService | getTableVisit | response | runningTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | getTableVisit | response | runningTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getTableVisit | response | runningTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getTableVisit | response | runningTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getTableVisit | response | gratuity | object |  | The gratuity taken at closeTableVisit. (read-only; nullable)
FnbService | getTableVisit | response | gratuity.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | getTableVisit | response | gratuity.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | getTableVisit | response | gratuity.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | getTableVisit | response | openedAt | string (date-time) | yes
FnbService | getTableVisit | response | closedAt | string (date-time) |  | (nullable)
FnbService | getTableVisit | response | serviceStage | string |  | Where the table is in its service (4 October 2026, CHG-FXC-003): the last stage setServiceStage recorded (its stage value), null before the first. (read-only; nullable)
FnbService | getTableVisit | response | serviceStageRecordedAt | string (date-time) |  | (read-only; nullable)
FnbService | getTableVisit | param (path) | visitId | string (uuid) | yes
LedgerService | getTaxDocumentRendition | response | documentId | string (uuid) | yes
LedgerService | getTaxDocumentRendition | response | documentKind | enum (taxInvoice, creditMemo) | yes
LedgerService | getTaxDocumentRendition | response | documentNumber | string
LedgerService | getTaxDocumentRendition | response | language | string |  | (nullable)
LedgerService | getTaxDocumentRendition | response | contentType | string |  | (default application/pdf)
LedgerService | getTaxDocumentRendition | response | url | string (uri) | yes
LedgerService | getTaxDocumentRendition | response | expiresAt | string (date-time) | yes
LedgerService | getTaxDocumentRendition | param (path) | documentId | string (uuid) | yes | A tax invoice id or a credit memo id.
LedgerService | getTaxDocumentRendition | param (query) | language | string
LedgerService | getTaxInvoice | response | id | string (uuid) | yes | (read-only)
LedgerService | getTaxInvoice | response | invoiceNumber | string | yes | Server-assigned from the legal entity's series for the document kind, in sequence and without gaps, e.g. (read-only)
LedgerService | getTaxInvoice | response | invoiceType | FinTaxInvoiceType: enum (simplified, full, consolidated) | yes | 5.7.93.
LedgerService | getTaxInvoice | response | status | FinTaxInvoiceStatus: enum (issued, partiallyCredited, fullyCredited, superseded) | yes | issued until a credit memo is issued against it; superseded where a full invoice replaced a simplified one for the same supply (only if the law allows it; see issueTaxInvoice).
LedgerService | getTaxInvoice | response | legalEntityId | string (uuid) | yes
LedgerService | getTaxInvoice | response | templateId | string (uuid) |  | (nullable)
LedgerService | getTaxInvoice | response | venueId | string (uuid) |  | (nullable)
LedgerService | getTaxInvoice | response | orderIds | array of string (uuid)
LedgerService | getTaxInvoice | response | supplierName | string
LedgerService | getTaxInvoice | response | supplierAddress | string |  | (nullable)
LedgerService | getTaxInvoice | response | supplierTaxRegistrationNumber | string |  | (nullable)
LedgerService | getTaxInvoice | response | buyerSubjectId | string (uuid) |  | The guest the orders belong to; the key a guest's own reads filter on. (nullable)
LedgerService | getTaxInvoice | response | buyerName | string |  | (nullable)
LedgerService | getTaxInvoice | response | buyerAddress | string |  | (nullable)
LedgerService | getTaxInvoice | response | buyerCountryCode | string |  | (pattern ^[A-Z]{2}$; nullable)
LedgerService | getTaxInvoice | response | buyerTaxRegistrationNumber | string |  | (nullable)
LedgerService | getTaxInvoice | response | customerAccountId | string (uuid) |  | (nullable)
LedgerService | getTaxInvoice | response | issuedAt | string (date-time) | yes
LedgerService | getTaxInvoice | response | supplyDate | string (date) | yes | The date of supply where it differs from the issue date (the latest order's payment date on a consolidated invoice).
LedgerService | getTaxInvoice | response | currency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | discountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | discountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | discountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | taxAmountInLegalCurrency | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | taxAmountInLegalCurrency.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | taxAmountInLegalCurrency.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | taxAmountInLegalCurrency.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | legalCurrency | string |  | The legal entity's currency (AED in the UAE), in which the law requires the tax and the gross amount (CHG-FIN-011). (pattern ^[A-Z]{3}$; read-only)
LedgerService | getTaxInvoice | response | grossAmountInLegalCurrency | object |  | The gross amount payable in the legal currency (Executive Regulation Art. (read-only)
LedgerService | getTaxInvoice | response | grossAmountInLegalCurrency.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | grossAmountInLegalCurrency.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | grossAmountInLegalCurrency.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | legalFxRate | object |  | Units of the legal currency per one unit of currency, printed with the tax where the invoice is not in the legal currency (Art. (read-only; nullable)
LedgerService | getTaxInvoice | response | legalFxRateSource | object |  | uaeCentralBank for a UAE legal entity (Decree-Law Art. (read-only; nullable)
LedgerService | getTaxInvoice | response | paidCurrency | string |  | Where the guest paid in a currency they selected (orders.Order.chargeCurrency, CHG-FIN-001), printed as payment information with paidAmount and the charge rate. (pattern ^[A-Z]{3}$; read-only; nullable)
LedgerService | getTaxInvoice | response | paidAmount | object |  | What the guest paid in paidCurrency (orders.Order.chargeTotal). (read-only)
LedgerService | getTaxInvoice | response | paidAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | paidAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | paidAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | reverseChargeStatement | string |  | Where the recipient must account for the tax, the statement saying so and the Decree-Law provision (Art. (read-only; nullable)
LedgerService | getTaxInvoice | response | creditedAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | creditedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | creditedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | creditedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | languages | array of string
LedgerService | getTaxInvoice | response | supersedesInvoiceId | string (uuid) |  | (nullable)
LedgerService | getTaxInvoice | response | renditionAssetId | string (uuid) |  | The PDF rendered at issue; read through getTaxDocumentRendition. (read-only; nullable)
LedgerService | getTaxInvoice | response | eInvoiceStatus | FinEInvoiceTransmissionStatus: enum (notRequired, queued, sent, accepted, rejected, failed) |  | 6.1.1.
LedgerService | getTaxInvoice | response | issuedByPrincipalId | string (uuid) |  | Null where the platform issued it. (read-only; nullable)
LedgerService | getTaxInvoice | response | lines | array of FinTaxInvoiceLine | yes
LedgerService | getTaxInvoice | response | lines[].lineNumber | integer | yes | (min 1)
LedgerService | getTaxInvoice | response | lines[].orderId | string (uuid)
LedgerService | getTaxInvoice | response | lines[].orderLineId | string (uuid) |  | (nullable)
LedgerService | getTaxInvoice | response | lines[].description | string | yes | (max length 500)
LedgerService | getTaxInvoice | response | lines[].quantity | number | yes
LedgerService | getTaxInvoice | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | lines[].discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | lines[].discountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | lines[].discountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | lines[].discountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | lines[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | lines[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | lines[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | lines[].taxCodeId | string (uuid) |  | (nullable)
LedgerService | getTaxInvoice | response | lines[].taxRate | number |  | (min 0; max 100)
LedgerService | getTaxInvoice | response | lines[].taxCategory | FinTaxCategory: enum (standardRated, zeroRated, exempt, outOfScope, reverseCharge) | yes | How a line is treated for VAT.
LedgerService | getTaxInvoice | response | lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | lines[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | lines[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | lines[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | lines[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | lines[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | lines[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | lines[].creditedAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | lines[].creditedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | lines[].creditedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | lines[].creditedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | lines[].grossAmountInLegalCurrency | object |  | The amount payable for the line in the legal currency (AED), Executive Regulation Art. (read-only)
LedgerService | getTaxInvoice | response | lines[].grossAmountInLegalCurrency.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | lines[].grossAmountInLegalCurrency.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | lines[].grossAmountInLegalCurrency.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | taxSummary | array of object |  | VAT per rate and category, summed from the lines for the response.
LedgerService | getTaxInvoice | response | taxSummary[].taxCategory | FinTaxCategory: enum (standardRated, zeroRated, exempt, outOfScope, reverseCharge) |  | How a line is treated for VAT.
LedgerService | getTaxInvoice | response | taxSummary[].taxRate | number
LedgerService | getTaxInvoice | response | taxSummary[].taxableAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | taxSummary[].taxableAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | taxSummary[].taxableAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | taxSummary[].taxableAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | taxSummary[].taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | getTaxInvoice | response | taxSummary[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | getTaxInvoice | response | taxSummary[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | getTaxInvoice | response | taxSummary[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | getTaxInvoice | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
LedgerService | getTaxInvoice | param (path) | invoiceId | string (uuid) | yes
WhiteLabelService | getTenantAppStatus | response | tenantId | string (uuid) | yes
WhiteLabelService | getTenantAppStatus | response | isPublished | boolean | yes | True once any version has been published.
WhiteLabelService | getTenantAppStatus | response | publishedVersion | string |  | (nullable)
WhiteLabelService | getTenantAppStatus | response | publishedAt | string (date-time) |  | (nullable)
WhiteLabelService | getTenantAppStatus | response | draftVersion | string |  | Staff only.
WhiteLabelService | getTenantAppStatus | response | hasUnpublishedChanges | boolean |  | Staff only.
WhiteLabelService | getTenantAppStatus | response | activeModuleCount | integer |  | Staff only.
WhiteLabelService | getTenantAppStatus | response | licensedModuleCount | integer |  | Staff only.
WhiteLabelService | getTenantAppStatus | response | activePageCount | integer |  | Staff only.
WhiteLabelService | getTenantAppStatus | response | isInMaintenance | boolean | yes
WhiteLabelService | getTenantAppStatus | response | maintenanceMessage | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | getTenantAppStatus | response | expectedBackAt | string (date-time) |  | (nullable)
WhiteLabelService | getTenantAppStatus | response | minimumAppVersion | MinimumAppVersion |  | The oldest guest app build still allowed to run (decided 28 September, audit R073). (nullable)
WhiteLabelService | getTenantAppStatus | response | minimumAppVersion.ios | string |  | (pattern ^\d+\.\d+\.\d+$; nullable)
WhiteLabelService | getTenantAppStatus | response | minimumAppVersion.android | string |  | (pattern ^\d+\.\d+\.\d+$; nullable)
WhiteLabelService | getTenantAppStatus | response | contact | VenueContact |  | How a guest reaches the venue: WEB-028 Contact & Venue Information, and the screen shown on an error or when the app cannot help (decided 28 September, audit R073). (nullable)
WhiteLabelService | getTenantAppStatus | response | contact.phone | string |  | (nullable)
WhiteLabelService | getTenantAppStatus | response | contact.email | string (email) |  | (nullable)
WhiteLabelService | getTenantAppStatus | response | contact.whatsapp | string |  | (nullable)
WhiteLabelService | getTenantAppStatus | response | contact.address | object |  | (nullable)
WhiteLabelService | getTenantAppStatus | response | contact.openingHours | object |  | Prose, as the guest reads it. (nullable)
WhiteLabelService | getTenantAppStatus | response | availability | AppAvailability: enum (open, soldOut, closed) |  | The sold-out or closed signal (decided 28 September, audit R073). (default open)
WhiteLabelService | getTenantAppStatus | response | availabilityMessage | object |  | What the sold-out or closed screen says (WEB-029). (nullable)
WhiteLabelService | getTenantAppStatus | response | venues | array of object |  | Public: the venues a guest can pick (decided 28 September, audit R267; schema named 29 September, readiness close-out, our build plan). (max items 200)
WhiteLabelService | getTenantAppStatus | response | venues[].venueId | string (uuid) | yes | The venue's scope node (tenancy.OrgUnit.id, level venue): what every guest screen that declares venueId from: session reads once the guest picks it.
WhiteLabelService | getTenantAppStatus | response | venues[].name | string | yes | The venue's name (tenancy.OrgUnit.name). (max length 200)
WhiteLabelService | getTenantAppStatus | response | venues[].city | string |  | Shown under the name so two venues with similar names can be told apart. (max length 120; nullable)
WhiteLabelService | getTenantAppStatus | response | venues[].openingHoursToday | object |  | Today's opening hours in the venue's time zone, from tenancy.VenueSettings opening hours. (nullable)
WhiteLabelService | getTenantAppStatus | response | venues[].openingHoursToday.opens | string |  | (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
WhiteLabelService | getTenantAppStatus | response | venues[].openingHoursToday.closes | string |  | (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
WhiteLabelService | getTenantAppStatus | response | whatsNew | array of object |  | Public: the guest "what's new" (decided 29 September, rev 3 GAP-B2). (max items 10)
WhiteLabelService | getTenantAppStatus | response | whatsNew[].version | string | yes | The release version.
WhiteLabelService | getTenantAppStatus | response | whatsNew[].publishedAt | string (date-time) | yes | When the release reached the tenant's cell.
WhiteLabelService | getTenantAppStatus | response | whatsNew[].notes | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | getTenantAppStatus | response | recentChanges | array of object |  | Staff only.
WhiteLabelService | getTenantAppStatus | response | recentChanges[].area | string
WhiteLabelService | getTenantAppStatus | response | recentChanges[].description | string
WhiteLabelService | getTenantAppStatus | response | recentChanges[].principalId | string (uuid)
WhiteLabelService | getTenantAppStatus | response | recentChanges[].at | string (date-time)
WhiteLabelService | getTenantConfig | response | tenantId | string (uuid) | yes
WhiteLabelService | getTenantConfig | response | version | string | yes | The draft's working version label; the published one is ConfigVersion.version.
WhiteLabelService | getTenantConfig | response | isDraft | boolean |  | True for the working draft, which is the only row. (read-only)
WhiteLabelService | getTenantConfig | response | brand | BrandIdentity |  | Every *AssetRef here is a MediaAsset id from the assets library (createUpload then completeUpload), PNG or SVG and at most 2 MB (decided 28 September, audit R270).
WhiteLabelService | getTenantConfig | response | brand.logoAssetRef | string (uuid) | yes | The primary logo.
WhiteLabelService | getTenantConfig | response | brand.logoDarkAssetRef | string (uuid) |  | Used on dark backgrounds. (nullable)
WhiteLabelService | getTenantConfig | response | brand.logoVariant | enum (light, dark, duotone) |  | Which lockup sits in the nav bar, and whose colours drive the theme (decided 29 September, rev 3 CFG-4). (default light)
WhiteLabelService | getTenantConfig | response | brand.faviconAssetRef | string (uuid) |  | The browser tab icon for the guest web app. (nullable)
WhiteLabelService | getTenantConfig | response | brand.splashImageAssetRefs | array of string (uuid) |  | Splash images, shown in order.
WhiteLabelService | getTenantConfig | response | brand.splashDurationSeconds | integer |  | (min 0; max 10; default 3)
WhiteLabelService | getTenantConfig | response | brand.splashBackgroundColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTenantConfig | response | brand.showLoadingIndicator | boolean |  | (default True)
WhiteLabelService | getTenantConfig | response | brand.splashChangeScope | object |  | Always buildTime for native apps. (read-only)
WhiteLabelService | getTenantConfig | response | brand.introVideoAssetRef | string (uuid) |  | The optional intro video (decided 29 September, MOB-5). (nullable)
WhiteLabelService | getTenantConfig | response | brand.introVideoMode | enum (off, firstLaunch, everyLaunch) |  | When GST-001 plays it full screen. (default off)
WhiteLabelService | getTenantConfig | response | brand.showPoweredBy | boolean |  | "Powered by TICVAI", a configuration toggle, on by default (Chinmay, 2 October, workbook Q160 and the pre-apply round; consistent with DI-297; CHG-CSA-036). (default True)
WhiteLabelService | getTenantConfig | response | appIcons | AppIcons
WhiteLabelService | getTenantConfig | response | appIcons.sourceAssetRef | string (uuid) | yes | The MediaAsset id of the 1024×1024 source.
WhiteLabelService | getTenantConfig | response | appIcons.derived | array of object |  | Generated by setAppIcons from the source, one entry per platform and size — the iOS and Android store sets and the web favicons listed on setAppIcons (audit R163). (read-only)
WhiteLabelService | getTenantConfig | response | appIcons.derived[].platform | enum (ios, android, web)
WhiteLabelService | getTenantConfig | response | appIcons.derived[].size | string
WhiteLabelService | getTenantConfig | response | appIcons.derived[].assetRef | string (uuid)
WhiteLabelService | getTenantConfig | response | appIcons.changeScope | object | yes | Always buildTime — icons are baked into the binary. (read-only)
WhiteLabelService | getTenantConfig | response | appIcons.liveVersion | string |  | Icon currently shipped. (read-only; nullable)
WhiteLabelService | getTenantConfig | response | appIcons.requiresRebuild | boolean |  | True while the draft's source differs from the icon in liveVersion. (read-only)
WhiteLabelService | getTenantConfig | response | bookingFlow | BookingFlowConfig |  | Set per tenant, with a per-venue override (decided 29 September, rev 3 CFG-11).
WhiteLabelService | getTenantConfig | response | bookingFlow.preset | enum (auto, ticketBox, playCentre, venueSite, marketplace, singleEvent, season, custom) |  | L1 Ticket box … L6 Season. (default auto)
WhiteLabelService | getTenantConfig | response | bookingFlow.stepIndicator | enum (bar, numbered, dots, segmented, breadcrumb, pills, ticks, none) |  | (default bar)
WhiteLabelService | getTenantConfig | response | bookingFlow.cartLayout | enum (sidebarRight, sidebarLeft, slideInRight, slideUpBottom, singleColumn, floatingIcon) |  | floatingIcon is a round basket button with the item count that opens the cart (decided 29 September, rev 3 REV3-10). (default sidebarRight)
WhiteLabelService | getTenantConfig | response | bookingFlow.cartSideInRtl | enum (keepRight, mirror) |  | The cart side when the guest reads Arabic or another right-to-left language (decided 29 September, rev 3 REV3-10). (default keepRight)
WhiteLabelService | getTenantConfig | response | bookingFlow.cardLayout | enum (stackedRows, splitRows, cardsAcross, posterCards) |  | How ticket and product cards are laid out (decided 29 September, rev 3 DG-6). (default stackedRows)
WhiteLabelService | getTenantConfig | response | bookingFlow.cardSize | enum (compact, standard, large, extraLarge) |  | Labels Compact, Standard, Large, Extra large (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | getTenantConfig | response | bookingFlow.seatPicker | enum (bowl, zonesThenSeats, zonesOnly, seatsOnly) |  | Default bowl, as the prototype has it (decided 29 September, rev 3 CFG-6). (default bowl)
WhiteLabelService | getTenantConfig | response | bookingFlow.mapView | enum (2d, 3d) |  | (default 3d)
WhiteLabelService | getTenantConfig | response | bookingFlow.density | enum (compact, standard, roomy) |  | Labels Compact, Standard, Roomy, default Compact as the design has it (decided 29 September, rev 3 DG-6). (default compact)
WhiteLabelService | getTenantConfig | response | bookingFlow.embedMode | enum (fullPage, embedded) |  | embedded hides the hero banner, event page and venue header, for a flow placed inside the venue's own site. (default fullPage)
WhiteLabelService | getTenantConfig | response | bookingFlow.heroBanner | boolean |  | (default True)
WhiteLabelService | getTenantConfig | response | bookingFlow.searchInBanner | boolean |  | Off by default, as the prototype has it (decided 29 September, rev 3 CFG-6). (default False)
WhiteLabelService | getTenantConfig | response | bookingFlow.eventBannerDates | boolean |  | Dates in event banner (decided 29 September, rev 3 23SEP-19). (default False)
WhiteLabelService | getTenantConfig | response | bookingFlow.singleEventPage | boolean |  | (default False)
WhiteLabelService | getTenantConfig | response | bookingFlow.quantitiesOnAddOns | boolean |  | (default True)
WhiteLabelService | getTenantConfig | response | bookingFlow.timesPerPage | enum (8, 12, 24, all) |  | Times per page (decided 29 September, rev 3 REV3-1). (default 24)
WhiteLabelService | getTenantConfig | response | bookingFlow.dayPartFilter | boolean |  | Morning, afternoon and evening chips with counts above the times (decided 29 September, rev 3 REV3-1). (default True)
WhiteLabelService | getTenantConfig | response | bookingFlow.dayPartBoundaries | object |  | Where the day parts divide, in the venue's time zone (decided 29 September, rev 3 REV3-1).
WhiteLabelService | getTenantConfig | response | bookingFlow.dayPartBoundaries.afternoonStartsAt | string |  | (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; default 12:00)
WhiteLabelService | getTenantConfig | response | bookingFlow.dayPartBoundaries.eveningStartsAt | string |  | (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; default 17:00)
WhiteLabelService | getTenantConfig | response | bookingFlow.seatViewPosition | enum (bottom, right, left, top) |  | Where the view-from-your-seat box sits around the seat map (decided 29 September, rev 3 REV3-5). (default bottom)
WhiteLabelService | getTenantConfig | response | bookingFlow.seatTimeBar | boolean |  | Time bar above the seat map (decided 29 September, rev 3 REV3-6). (default True)
WhiteLabelService | getTenantConfig | response | bookingFlow.ticketCategories | enum (categoryThenSubcategory, flatList) |  | How tickets are grouped (decided 29 September, rev 3 REV3-16). (default categoryThenSubcategory)
WhiteLabelService | getTenantConfig | response | bookingFlow.ticketTags | boolean |  | Tags on tickets (decided 29 September, rev 3 23SEP-3). (default True)
WhiteLabelService | getTenantConfig | response | bookingFlow.cardInfo | boolean |  | Extra info on cards (decided 29 September, rev 3 23SEP-6). (default True)
WhiteLabelService | getTenantConfig | response | bookingFlow.conciergeMascot | boolean |  | The concierge as mascot art or a plain button (decided 29 September, rev 3 CFG-5). (default True)
WhiteLabelService | getTenantConfig | response | bookingFlow.showInfoOnly | boolean |  | Show info-only products (decided 29 September, rev 3 REV3-14). (default True)
WhiteLabelService | getTenantConfig | response | bookingFlow.locationSwitcher | boolean |  | Location switcher (decided 29 September, rev 3 REV3-18). (default False)
WhiteLabelService | getTenantConfig | response | bookingFlow.guestContactFields | array of enum (email, mobile, name) |  | What the guest-checkout pop-up asks, and nothing else (decided 29 September, W1). (min items 1; max items 3; default ['email'])
WhiteLabelService | getTenantConfig | response | bookingFlow.dateStripDays | integer |  | The date strip (decided 17 September, M17-08). (min 3; max 31; default 7)
WhiteLabelService | getTenantConfig | response | bookingFlow.venueOverrides | array of BookingFlowVenueOverride |  | Per-venue overrides, at most one per venue. (max items 200; default [])
WhiteLabelService | getTenantConfig | response | bookingFlow.venueOverrides[].venueId | string (uuid) | yes | One of the tenant's active venues.
WhiteLabelService | getTenantConfig | response | bookingFlow.venueOverrides[].settings | BookingFlowSettings | yes | Every guest booking-flow setting, once.
WhiteLabelService | getTenantConfig | response | bookingFlows | array of BookingFlow |  | Every venue's booking flows in the draft (whitelabel.booking_flow), so a publish snapshots them with the rest (decided 29 September, W12). (read-only)
WhiteLabelService | getTenantConfig | response | bookingFlows[].id | string (uuid) |  | (read-only)
WhiteLabelService | getTenantConfig | response | bookingFlows[].venueId | string (uuid) |  | From the path of createBookingFlowDefinition. (read-only)
WhiteLabelService | getTenantConfig | response | bookingFlows[].flowTypeKey | BookingFlowTypeKey: enum (datedDayPass, timedEntry, openDated, seatedFixedPerformance, seatedDateTimeSeatMap, experienceWorkshop, surfSession, meetingRoomHourly, …) | yes | The flow types the system catalogue offers (decided 29 September, W12; impact.md b).
WhiteLabelService | getTenantConfig | response | bookingFlows[].name | string | yes | Staff-facing, e.g. (max length 80)
WhiteLabelService | getTenantConfig | response | bookingFlows[].isDefaultForType | boolean |  | At most one per venue and type; setting it takes it from the previous default. (default False)
WhiteLabelService | getTenantConfig | response | bookingFlows[].isEnabled | boolean |  | A disabled flow is kept and not published; products naming it fall back to the default. (default True)
WhiteLabelService | getTenantConfig | response | bookingFlows[].steps | array of BookingFlowStep |  | Every step of the type, in the venue's order. (max items 30)
WhiteLabelService | getTenantConfig | response | bookingFlows[].steps[].id | string (uuid) |  | (read-only)
WhiteLabelService | getTenantConfig | response | bookingFlows[].steps[].bookingFlowId | string (uuid) |  | (read-only)
WhiteLabelService | getTenantConfig | response | bookingFlows[].steps[].stepKey | BookingFlowStepKey: enum (location, helpMeChoose, product, date, time, performance, level, language, …) | yes | Every step a guest booking flow can hold (decided 29 September, W12).
WhiteLabelService | getTenantConfig | response | bookingFlows[].steps[].enabled | boolean | yes | A required step cannot be off; the flow saves and isValid turns false.
WhiteLabelService | getTenantConfig | response | bookingFlows[].steps[].sortOrder | integer | yes | (min 0)
WhiteLabelService | getTenantConfig | response | bookingFlows[].steps[].requirement | enum (required, optional, conditional) |  | From the flow type, so the CMS can mark the step without a second read. (read-only)
WhiteLabelService | getTenantConfig | response | bookingFlows[].steps[].settings | object |  | The step's own settings, by the names the type's stepSettings gives for this step (e.g. (default {})
WhiteLabelService | getTenantConfig | response | bookingFlows[].settings | BookingFlowLevelSettings |  | The settings that belong to one flow, not to the venue (decided 29 September, W12).
WhiteLabelService | getTenantConfig | response | bookingFlows[].settings.performanceReveal | enum (dateTimeTicket, allAtOnce) |  | Performance reveal (rev 3 REV3-2). (default dateTimeTicket)
WhiteLabelService | getTenantConfig | response | bookingFlows[].settings.signInAt | enum (afterAddOns, atPayment) |  | Where the guest is asked to sign in, or for a guest-checkout code (rev 3 REV3-3). (default afterAddOns)
WhiteLabelService | getTenantConfig | response | bookingFlows[].settings.seatEventDateMode | enum (inlineStep, popupOnSeatMap) |  | Date and time on a seated event (rev 3 REV3-4). (default inlineStep)
WhiteLabelService | getTenantConfig | response | bookingFlows[].settings.extrasStep | enum (auto, always, never) |  | auto shows the extras step only when the cart's products have add-ons; never is the same as turning the optional extras step off. (default auto)
WhiteLabelService | getTenantConfig | response | bookingFlows[].settings.quickTour | boolean |  | Quick tour (rev 3 REV3-20). (default False)
WhiteLabelService | getTenantConfig | response | bookingFlows[].settings.consentQuestionIds | array of string (uuid) |  | The flow's own consent questions (rev 3 REV3-26). (max items 10; default [])
WhiteLabelService | getTenantConfig | response | bookingFlows[].isValid | boolean |  | Whether the flow passes validateBookingFlow; worked out in the same transaction as each write. (read-only)
WhiteLabelService | getTenantConfig | response | bookingFlows[].scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | getTenantConfig | response | bookingFlows[].updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | getTenantConfig | response | theme | Theme
WhiteLabelService | getTenantConfig | response | theme.primaryColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTenantConfig | response | theme.secondaryColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTenantConfig | response | theme.accentColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTenantConfig | response | theme.backgroundColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTenantConfig | response | theme.textColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTenantConfig | response | theme.darkMode | object |  | Deprecated and ignored (Chinmay, 2 October, workbook Q150 and the pre-apply round; CHG-CSA-035).
WhiteLabelService | getTenantConfig | response | theme.darkMode.primaryColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTenantConfig | response | theme.darkMode.backgroundColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTenantConfig | response | theme.darkMode.textColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTenantConfig | response | theme.cornerRadius | integer |  | The prototype's 0 to 22 px slider sits inside these bounds (rev 3 CFG-2, no change). (min 0; max 32)
WhiteLabelService | getTenantConfig | response | theme.surfaceStyle | enum (glass, solid) |  | Cards and panels as frosted glass or opaque (decided 29 September, rev 3 CFG-3). (default glass)
WhiteLabelService | getTenantConfig | response | theme.buttonStyle | enum (solid, outline, pill) |  | Button shape (decided 29 September, rev 3 CFG-3). (default solid)
WhiteLabelService | getTenantConfig | response | theme.componentColours | object |  | Colours for single interactive elements (decided 17 September, M17-11).
WhiteLabelService | getTenantConfig | response | theme.componentColours.primaryCta | ThemeComponentColour
WhiteLabelService | getTenantConfig | response | theme.componentColours.payButton | ThemeComponentColour
WhiteLabelService | getTenantConfig | response | theme.componentColours.addToCart | ThemeComponentColour
WhiteLabelService | getTenantConfig | response | theme.componentColours.buyTicketsButton | ThemeComponentColour
WhiteLabelService | getTenantConfig | response | theme.componentColours.link | ThemeComponentColour
WhiteLabelService | getTenantConfig | response | theme.componentColours.badge | ThemeComponentColour
WhiteLabelService | getTenantConfig | response | fonts | FontConfig
WhiteLabelService | getTenantConfig | response | fonts.primaryLatin | string | yes
WhiteLabelService | getTenantConfig | response | fonts.primaryArabic | string |  | Required when ar is among the tenant's languages (audit R163). (nullable)
WhiteLabelService | getTenantConfig | response | fonts.secondaryLatin | string |  | (nullable)
WhiteLabelService | getTenantConfig | response | fonts.secondaryArabic | string |  | Required whenever secondaryLatin is set and ar is among the tenant's languages (decided 28 September, audit R163). (nullable)
WhiteLabelService | getTenantConfig | response | fonts.customFontAssetRefs | array of string (uuid) |  | Uploaded font files, as MediaAsset ids.
WhiteLabelService | getTenantConfig | response | fonts.changeScope | object |  | Custom font files are buildTime; selecting a bundled face is runtime. (read-only)
WhiteLabelService | getTenantConfig | response | footer | FooterConfig |  | BL-002.
WhiteLabelService | getTenantConfig | response | footer.id | string (uuid) | yes | (read-only)
WhiteLabelService | getTenantConfig | response | footer.scopePath | string | yes | The partition key (ADR-0005), written at tenant scope by the server. (read-only)
WhiteLabelService | getTenantConfig | response | footer.columns | array of object
WhiteLabelService | getTenantConfig | response | footer.columns[].heading | string
WhiteLabelService | getTenantConfig | response | footer.columns[].links | array of object
WhiteLabelService | getTenantConfig | response | footer.legalLinks | object |  | Required links, held separately from the free-form columns — a tenant reorganising their footer must not be able to remove the privacy notice by accident.
WhiteLabelService | getTenantConfig | response | footer.legalLinks.termsUrl | string
WhiteLabelService | getTenantConfig | response | footer.legalLinks.privacyUrl | string
WhiteLabelService | getTenantConfig | response | footer.legalLinks.accessibilityUrl | string |  | (nullable)
WhiteLabelService | getTenantConfig | response | footer.legalLinks.cookiePolicyUrl | string |  | (nullable)
WhiteLabelService | getTenantConfig | response | footer.copyrightText | string
WhiteLabelService | getTenantConfig | response | footer.socialLinks | array of object
WhiteLabelService | getTenantConfig | response | footer.socialLinks[].platform | string
WhiteLabelService | getTenantConfig | response | footer.socialLinks[].url | string
WhiteLabelService | getTenantConfig | response | notificationBranding | object |  | BL-003. (nullable)
WhiteLabelService | getTenantConfig | response | notificationBranding.senderName | string
WhiteLabelService | getTenantConfig | response | notificationBranding.replyToEmail | string (email)
WhiteLabelService | getTenantConfig | response | notificationBranding.smsSenderId | string |  | (nullable)
WhiteLabelService | getTenantConfig | response | notificationBranding.whatsappBusinessId | string |  | (nullable)
WhiteLabelService | getTenantConfig | response | notificationBranding.logoAssetId | string (uuid) |  | (nullable)
WhiteLabelService | getTenantConfig | response | enabledPaymentMethods | array of string |  | BL-004. (nullable)
WhiteLabelService | getTenantConfig | response | accessibility | AccessibilitySettings |  | BL-065, 2.1.27.
WhiteLabelService | getTenantConfig | response | accessibility.largeTextAvailable | boolean |  | (default True)
WhiteLabelService | getTenantConfig | response | accessibility.highContrastAvailable | boolean |  | (default True)
WhiteLabelService | getTenantConfig | response | accessibility.simplifiedNavigationAvailable | boolean |  | (default True)
WhiteLabelService | getTenantConfig | response | accessibility.screenReaderSupported | boolean |  | (default True)
WhiteLabelService | getTenantConfig | response | accessibility.reachableHeightModeAvailable | boolean |  | Moves the interface to the lower half of the screen for a guest using a wheelchair. (default False)
WhiteLabelService | getTenantConfig | response | accessibility.sessionTimeoutMultiplier | number |  | Timeouts are an accessibility barrier nobody counts. (default 1)
WhiteLabelService | getTenantConfig | response | header | HeaderConfig
WhiteLabelService | getTenantConfig | response | header.layout | enum (logoLeft, logoCentre, logoWithMenu) | yes
WhiteLabelService | getTenantConfig | response | header.showLogo | boolean |  | (default True)
WhiteLabelService | getTenantConfig | response | header.showMenu | boolean |  | (default True)
WhiteLabelService | getTenantConfig | response | header.showNotifications | boolean |  | (default True)
WhiteLabelService | getTenantConfig | response | header.backgroundColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTenantConfig | response | navigation | NavigationConfig |  | The mobile tab set is venue configuration (decided 29 September, MOB-1; 29 September brief decision 6).
WhiteLabelService | getTenantConfig | response | navigation.id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | getTenantConfig | response | navigation.kind | enum (bottomNavigation, drawer, tabs) | yes
WhiteLabelService | getTenantConfig | response | navigation.items | array of object | yes | (max items 12)
WhiteLabelService | getTenantConfig | response | navigation.items[].id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | getTenantConfig | response | navigation.items[].label | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | getTenantConfig | response | navigation.items[].icon | string
WhiteLabelService | getTenantConfig | response | navigation.items[].target | LinkTarget | yes
WhiteLabelService | getTenantConfig | response | navigation.items[].isVisible | boolean | yes | At most five may be visible in bottom navigation; the rest overflow.
WhiteLabelService | getTenantConfig | response | navigation.items[].sortOrder | integer | yes
WhiteLabelService | getTenantConfig | response | navigation.buyButton | object |  | The persistent Buy tickets button (decided 29 September, MOB-2). (nullable)
WhiteLabelService | getTenantConfig | response | navigation.buyButton.style | enum (raised, floating, flat, hidden) |  | raised sits in the centre of the tab bar, as the v4 prototype shows; hidden turns it off. (default raised)
WhiteLabelService | getTenantConfig | response | navigation.buyButton.label | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | getTenantConfig | response | homepage | HomepageLayout |  | The client-approved web and app wireframes are the layout (Chinmay, 2 October, workbook Q163; CHG-CSA-040): sections, their order and their options follow the approved wireframes and change only wher…
WhiteLabelService | getTenantConfig | response | homepage.templateKey | string |  | The landing-page template this layout started from (listLandingPageTemplates), or null for a layout composed from scratch (CHG-CSA-037). (nullable)
WhiteLabelService | getTenantConfig | response | homepage.landingSource | enum (storefront, ownSite) |  | storefront: this home is the tenant's landing page. (default storefront)
WhiteLabelService | getTenantConfig | response | homepage.id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | getTenantConfig | response | homepage.sections | array of object | yes
WhiteLabelService | getTenantConfig | response | homepage.sections[].id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | getTenantConfig | response | homepage.sections[].kind | HomepageSectionKind: enum (heroBanner, quickActions, tickets, whatsOn, attractions, membership, dining, shop, …) | yes | Which module each section needs, proposed, client to correct (decided 28 September, audit R163).
WhiteLabelService | getTenantConfig | response | homepage.sections[].title | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | getTenantConfig | response | homepage.sections[].sortOrder | integer | yes
WhiteLabelService | getTenantConfig | response | homepage.sections[].isVisible | boolean | yes
WhiteLabelService | getTenantConfig | response | homepage.sections[].contentPageId | string (uuid) |  | (nullable)
WhiteLabelService | getTenantConfig | response | homepage.sections[].maxItems | integer |  | How many cards the section shows, the venue's choice (Chinmay, 2 October, workbook Q152: every customisation option of the approved wireframe, including the card count per section; CHG-CSA-040). (nullable)
WhiteLabelService | getTenantConfig | response | homepage.sections[].scrollAnimation | enum (rise, scale, slide, blur, none) |  | How the section enters as the guest scrolls (Chinmay, 2 October, workbook Q153: "must be there"; DI-1088; CHG-CSA-040). (default rise)
WhiteLabelService | getTenantConfig | response | homepage.sections[].heroStyle | enum (carousel, video, poster, split, None) |  | For heroBanner only (decided 29 September, MOB-3). (nullable)
WhiteLabelService | getTenantConfig | response | modules | array of ModuleEnablement
WhiteLabelService | getTenantConfig | response | modules[].moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) | yes | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | getTenantConfig | response | modules[].displayName | string
WhiteLabelService | getTenantConfig | response | modules[].isLicensed | boolean | yes | From the tenant's subscription.
WhiteLabelService | getTenantConfig | response | modules[].isEnabled | boolean | yes
WhiteLabelService | getTenantConfig | response | modules[].referencedBy | array of string |  | Navigation items and homepage sections pointing at this module. (read-only)
WhiteLabelService | getTenantConfig | response | features | array of FeatureToggle
WhiteLabelService | getTenantConfig | response | features[].featureKey | object | yes | guestCheckout is off by default (decided 17 September 2026, matrix 2.6.28, placement settled by [ADR-0045](../../docs/adr/0045-every-order-carries-a-proven-contact.md) 18 September): the venue sets t…
WhiteLabelService | getTenantConfig | response | features[].displayName | string
WhiteLabelService | getTenantConfig | response | features[].isEnabled | boolean | yes
WhiteLabelService | getTenantConfig | response | features[].changeScope | object | yes | Wallet and payment integrations are buildTime on native apps — enabling one needs a release, not a publish. (read-only)
WhiteLabelService | getTenantConfig | response | features[].requiresConfiguration | boolean |  | True where the feature needs credentials or setup elsewhere first.
WhiteLabelService | getTenantConfig | response | languages | LanguageConfig
WhiteLabelService | getTenantConfig | response | languages.languages | array of string | yes | A tenant may add or select interface languages beyond English and Arabic (Chinmay, 2 October, workbook Q145; CHG-CSA-039).
WhiteLabelService | getTenantConfig | response | languages.defaultLanguage | string | yes | (pattern ^[a-z]{2}$)
WhiteLabelService | getTenantConfig | response | languages.uiStringCoverage | array of object |  | How complete the interface strings are in each enabled language (CHG-CSA-039). (read-only)
WhiteLabelService | getTenantConfig | response | languages.uiStringCoverage[].language | string
WhiteLabelService | getTenantConfig | response | languages.uiStringCoverage[].coveragePercent | number |  | (min 0; max 100)
WhiteLabelService | getTenantConfig | response | languages.uiStringCoverage[].status | enum (complete, draft, missing)
WhiteLabelService | getTenantConfig | response | languages.rtlLanguages | array of string |  | The enabled languages written right to left — those whose Unicode CLDR character order is right-to-left (Arabic, ar, among them). (read-only)
WhiteLabelService | getTenantConfig | response | languages.translationGaps | array of object |  | Content lacking a version in an enabled language. (read-only)
WhiteLabelService | getTenantConfig | response | languages.translationGaps[].language | string
WhiteLabelService | getTenantConfig | response | languages.translationGaps[].missingCount | integer
WhiteLabelService | getTenantConfig | response | languages.translationGaps[].areas | array of string
WhiteLabelService | getTenantConfig | response | updatedAt | string (date-time)
WhiteLabelService | getTenantConfig | response | isInMaintenance | boolean |  | Written by setMaintenanceMode; read by getTenantAppStatus. (default False)
WhiteLabelService | getTenantConfig | response | maintenanceMessage | object |  | The message on the branded maintenance screen. (nullable)
WhiteLabelService | getTenantConfig | response | expectedBackAt | string (date-time) |  | (nullable)
WhiteLabelService | getTenantConfig | response | minimumAppVersion | object |  | Live state, written by setMaintenanceMode (audit R073).
WhiteLabelService | getTenantConfig | response | minimumAppVersion.ios | string |  | (pattern ^\d+\.\d+\.\d+$; nullable)
WhiteLabelService | getTenantConfig | response | minimumAppVersion.android | string |  | (pattern ^\d+\.\d+\.\d+$; nullable)
WhiteLabelService | getTenantConfig | response | contact | object |  | Live state, written by setMaintenanceMode (audit R073).
WhiteLabelService | getTenantConfig | response | contact.phone | string |  | (nullable)
WhiteLabelService | getTenantConfig | response | contact.email | string (email) |  | (nullable)
WhiteLabelService | getTenantConfig | response | contact.whatsapp | string |  | (nullable)
WhiteLabelService | getTenantConfig | response | contact.address | object |  | (nullable)
WhiteLabelService | getTenantConfig | response | contact.openingHours | object |  | Prose, as the guest reads it. (nullable)
WhiteLabelService | getTenantConfig | response | availability | object |  | Live state, written by setMaintenanceMode (audit R073).
WhiteLabelService | getTenantConfig | response | availabilityMessage | object |  | Live state, written by setMaintenanceMode (audit R073). (nullable)
WhiteLabelService | getTenantConfig | response | venues | array of object |  | The tenant's active venues, for the guest venue picker on WEB-001 and GST-001 (decided 28 September, audit R267).
WhiteLabelService | getTenantConfig | response | venues[].venueId | string (uuid) | yes
WhiteLabelService | getTenantConfig | response | venues[].name | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | getTenantConfig | response | venues[].city | string |  | (nullable)
WhiteLabelService | getTenantConfig | response | venues[].openingHours | object |  | Today's hours as shown to a guest, e.g. (nullable)
WhiteLabelService | getTenantConfig | param (query) | version | string |  | Read a published version's snapshot instead of the working draft.
PlatformService | getTenantLicences | response | poweredByRemovable | boolean |  | Whether the tenant's licence lets it switch "Powered by TICVAI" off (Chinmay, 2 October, workbook Q160 and the pre-apply round; CHG-CSA-036). (default False; read-only)
PlatformService | getTenantLicences | response | tenantId | string (uuid) | yes
PlatformService | getTenantLicences | response | planId | string (uuid) |  | (nullable)
PlatformService | getTenantLicences | response | licensedModules | array of object | yes | Union of plan modules and add-ons.
PlatformService | getTenantLicences | response | licensedModules[].moduleKey | string | yes
PlatformService | getTenantLicences | response | licensedModules[].displayName | string
PlatformService | getTenantLicences | response | licensedModules[].source | enum (plan, addOn) | yes
PlatformService | getTenantLicences | response | licensedModules[].validTo | string (date) |  | (nullable)
PlatformService | getTenantLicences | response | limits | array of EntitlementLimit | yes
PlatformService | getTenantLicences | response | limits[].metric | UsageMetric: enum (venues, workstations, activeUsers, devices, brandedApps, aiTokens, apiCalls, storageGb, …) | yes
PlatformService | getTenantLicences | response | limits[].limit | integer | yes | Null means unlimited. (nullable)
PlatformService | getTenantLicences | response | limits[].overageAllowed | boolean |  | (default False)
PlatformService | getTenantLicences | response | limits[].overageUnitPrice | Money |  | On the wire this is three fields; in the database it is one column.
PlatformService | getTenantLicences | response | limits[].overageUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
PlatformService | getTenantLicences | response | limits[].overageUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
PlatformService | getTenantLicences | response | limits[].overageUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
PlatformService | getTenantLicences | param (path) | tenantId | string (uuid) | yes
WhiteLabelService | getTheme | response | primaryColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | secondaryColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | accentColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | backgroundColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | textColour | string | yes | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | darkMode | object |  | Deprecated and ignored (Chinmay, 2 October, workbook Q150 and the pre-apply round; CHG-CSA-035).
WhiteLabelService | getTheme | response | darkMode.primaryColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | darkMode.backgroundColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | darkMode.textColour | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | cornerRadius | integer |  | The prototype's 0 to 22 px slider sits inside these bounds (rev 3 CFG-2, no change). (min 0; max 32)
WhiteLabelService | getTheme | response | surfaceStyle | enum (glass, solid) |  | Cards and panels as frosted glass or opaque (decided 29 September, rev 3 CFG-3). (default glass)
WhiteLabelService | getTheme | response | buttonStyle | enum (solid, outline, pill) |  | Button shape (decided 29 September, rev 3 CFG-3). (default solid)
WhiteLabelService | getTheme | response | componentColours | object |  | Colours for single interactive elements (decided 17 September, M17-11).
WhiteLabelService | getTheme | response | componentColours.primaryCta | ThemeComponentColour
WhiteLabelService | getTheme | response | componentColours.primaryCta.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | componentColours.primaryCta.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | componentColours.payButton | ThemeComponentColour
WhiteLabelService | getTheme | response | componentColours.payButton.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | componentColours.payButton.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | componentColours.addToCart | ThemeComponentColour
WhiteLabelService | getTheme | response | componentColours.addToCart.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | componentColours.addToCart.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | componentColours.buyTicketsButton | ThemeComponentColour
WhiteLabelService | getTheme | response | componentColours.buyTicketsButton.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | componentColours.buyTicketsButton.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | componentColours.link | ThemeComponentColour
WhiteLabelService | getTheme | response | componentColours.link.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | componentColours.link.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | componentColours.badge | ThemeComponentColour
WhiteLabelService | getTheme | response | componentColours.badge.background | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
WhiteLabelService | getTheme | response | componentColours.badge.text | string |  | (pattern ^#[0-9A-Fa-f]{6}$)
OrderService | getTillShiftPolicy | response | id | string (uuid) |  | (read-only)
OrderService | getTillShiftPolicy | response | venueId | string (uuid) | yes
OrderService | getTillShiftPolicy | response | scopePath | string |  | (read-only)
OrderService | getTillShiftPolicy | response | requireOpenApproval | boolean |  | Every shift opens pendingApproval and waits for approveShiftOpen (SHIFT_APPROVE_OPEN). (default False)
OrderService | getTillShiftPolicy | response | openingFloatTolerance | object |  | How far a declared opening float may differ from the box's allocated float before the shift waits for approval (states/shift.yaml, pendingApproval). (nullable)
OrderService | getTillShiftPolicy | response | openingFloatTolerance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getTillShiftPolicy | response | openingFloatTolerance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getTillShiftPolicy | response | openingFloatTolerance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getTillShiftPolicy | response | depositBoxRequired | boolean |  | A shift cannot open without a deposit box (OpenShiftRequest.depositBoxCode); refused 400 otherwise. (default True)
OrderService | getTillShiftPolicy | response | bagNumberRequired | boolean |  | A shift cannot open without a bag number (OpenShiftRequest.bagNumber). (default False)
OrderService | getTillShiftPolicy | response | requireCloseApproval | boolean |  | Every counted shift waits in pendingClosure for approveShiftClose (SHIFT_APPROVE_CLOSE), even within the variance threshold. (default False)
OrderService | getTillShiftPolicy | response | autoCloseAfterHours | integer |  | Hours after which an open or suspended shift nobody closed is closed by the inactivity job as autoClosed and the supervisors are told (states/shift.yaml). (min 1; max 48; default 14; nullable)
OrderService | getTillShiftPolicy | response | noSaleAlertCount | integer |  | No-sales in one shift (recordNoSale) at which the supervisors are alerted on the venue's alerting channel; the count is on POS-020. (min 1; default 10; nullable)
OrderService | getTillShiftPolicy | response | updatedAt | string (date-time) |  | (read-only)
OrderService | getTillShiftPolicy | param (path) | venueId | string (uuid) | yes
AiService | getTranslationProposals | response | targetLocale | string | yes
AiService | getTranslationProposals | response | translationJobId | string (uuid) |  | The job to follow with getTranslationProposals (contract gap CHG-WIR-017, CMS-011; CHG-CSA-045). (read-only)
AiService | getTranslationProposals | response | status | enum (running, completed, failed) |  | running while drafts are still being written; drafts then holds those done so far. (read-only)
AiService | getTranslationProposals | response | drafts | array of object | yes
AiService | getTranslationProposals | response | drafts[].targetKind | enum (contentBlock, productName, emailTemplate, messageTemplate) | yes
AiService | getTranslationProposals | response | drafts[].targetRef | string | yes | The id of the block, product or template the draft sits on.
AiService | getTranslationProposals | response | drafts[].draftText | string | yes | The first-pass translation, as saved on the draft.
AiService | getTranslationProposals | param (path) | translationJobId | string (uuid) | yes
VenueOpsService | getTransportDeparture | response | departureId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | getTransportDeparture | response | performanceId | string (uuid) | yes
VenueOpsService | getTransportDeparture | response | routeId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | getTransportDeparture | response | routeCode | string |  | The price card's label, e.g.
VenueOpsService | getTransportDeparture | response | departsAt | string (date-time) | yes | At the boarding stop.
VenueOpsService | getTransportDeparture | response | arrivesAt | string (date-time) | yes | At the alighting stop.
VenueOpsService | getTransportDeparture | response | durationMinutes | integer | yes | (min 0)
VenueOpsService | getTransportDeparture | response | period | TimePeriod: enum (morning, afternoon, evening, night) | yes | Proposed, client to correct (rev 3 REV3-21): morning 05:00–11:59, afternoon 12:00–16:59, evening 17:00–20:59, night 21:00–04:59.
VenueOpsService | getTransportDeparture | response | seatsLeft | integer | yes | Catalogue availability for the performance. (min 0)
VenueOpsService | getTransportDeparture | response | fitsParty | boolean
VenueOpsService | getTransportDeparture | response | fare | Money | yes | On the wire this is three fields; in the database it is one column.
VenueOpsService | getTransportDeparture | response | fare.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | getTransportDeparture | response | fare.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | getTransportDeparture | response | fare.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | getTransportDeparture | response | partyTotal | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | getTransportDeparture | response | partyTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | getTransportDeparture | response | partyTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | getTransportDeparture | response | partyTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | getTransportDeparture | param (path) | departureId | string (uuid) | yes
VenueOpsService | getTransportFareTable | response | model | FareModel: enum (stopCount, matrix) | yes | stopCount: base plus an amount per stop travelled — the prototype's rule.
VenueOpsService | getTransportFareTable | response | baseFare | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | getTransportFareTable | response | baseFare.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | getTransportFareTable | response | baseFare.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | getTransportFareTable | response | baseFare.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | getTransportFareTable | response | perStopFare | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | getTransportFareTable | response | perStopFare.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | getTransportFareTable | response | perStopFare.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | getTransportFareTable | response | perStopFare.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | getTransportFareTable | response | matrix | array of object |  | matrix only.
VenueOpsService | getTransportFareTable | response | matrix[].fromStationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | getTransportFareTable | response | matrix[].toStationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | getTransportFareTable | response | matrix[].fare | Money | yes | On the wire this is three fields; in the database it is one column.
VenueOpsService | getTransportFareTable | response | matrix[].fare.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | getTransportFareTable | response | matrix[].fare.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | getTransportFareTable | response | matrix[].fare.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | getTransportFareTable | response | passengerTypes | array of PassengerType | yes | (min items 1; max items 10)
VenueOpsService | getTransportFareTable | response | passengerTypes[].code | string | yes | adult, child, student, determination. (pattern ^[a-z][a-zA-Z0-9]{0,31}$)
VenueOpsService | getTransportFareTable | response | passengerTypes[].name | LocalisedText | yes
VenueOpsService | getTransportFareTable | response | passengerTypes[].description | LocalisedText |  | What the picker shows under the name ("Age 5–11 · half fare").
VenueOpsService | getTransportFareTable | response | passengerTypes[].fareMultiplier | number | yes | Share of the adult fare, set by the venue. (min 0; max 1)
VenueOpsService | getTransportFareTable | response | passengerTypes[].minAge | integer |  | (min 0; nullable)
VenueOpsService | getTransportFareTable | response | passengerTypes[].maxAge | integer |  | (min 0; nullable)
VenueOpsService | getTransportFareTable | response | passengerTypes[].proofRequired | LocalisedText |  | Checked by the driver at boarding ("Valid student card", "Sanad card").
VenueOpsService | getTransportFareTable | response | passengerTypes[].isDefault | boolean |  | The type a new search starts with, one of it. (default False)
VenueOpsService | getTransportFareTable | response | passengerTypes[].catalogueVariantId | string (uuid) |  | The variant of the route's trip product this type is sold as. (read-only)
VenueOpsService | getTransportFareTable | response | effectiveFrom | string (date-time) | yes
VenueOpsService | getTransportFareTable | response | id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | getTransportFareTable | response | routeId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | getTransportFareTable | response | effectiveTo | string (date-time) |  | When the next version takes over; null when none is set (CHG-RUL-012). (read-only; nullable)
VenueOpsService | getTransportFareTable | response | upcoming | object |  | The next version, set and not yet in force (CHG-RUL-012); null when none. (read-only; nullable)
VenueOpsService | getTransportFareTable | response | upcoming.id | string (uuid) |  | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | getTransportFareTable | response | upcoming.effectiveFrom | string (date-time)
VenueOpsService | getTransportFareTable | param (path) | routeId | string (uuid) | yes
VenueOpsService | getTransportFareTable | param (query) | at | string (date-time) |  | The instant whose table is returned (the travel time for a guest).
VenueOpsService | getTransportRoute | response | venueId | string (uuid) | yes
VenueOpsService | getTransportRoute | response | code | string | yes | The line and direction, e.g. (max length 32)
VenueOpsService | getTransportRoute | response | lineCode | string |  | The public line number shared by both directions, e.g. (max length 16)
VenueOpsService | getTransportRoute | response | name | LocalisedText | yes
VenueOpsService | getTransportRoute | response | colour | string |  | (pattern ^#[0-9a-fA-F]{6}$)
VenueOpsService | getTransportRoute | response | pairedRouteId | string (uuid) |  | The same line run the other way. (nullable)
VenueOpsService | getTransportRoute | response | bookingCutoffMinutes | integer |  | How long before a departure leaves the boarding stop that online sale stops. (min 0; max 1440; default 5)
VenueOpsService | getTransportRoute | response | stops | array of RouteStop | yes
VenueOpsService | getTransportRoute | response | stops[].stationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | getTransportRoute | response | stops[].offsetMinutes | integer | yes | Minutes after the departure from the first stop that the coach leaves this one. (min 0; max 1440)
VenueOpsService | getTransportRoute | response | stops[].boardingAllowed | boolean |  | (default True)
VenueOpsService | getTransportRoute | response | stops[].alightingAllowed | boolean |  | (default True)
VenueOpsService | getTransportRoute | response | stops[].id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | getTransportRoute | response | stops[].sequence | integer | yes | 1 for the origin. (min 1)
VenueOpsService | getTransportRoute | response | stops[].station | Station
VenueOpsService | getTransportRoute | response | stops[].station.venueId | string (uuid) | yes
VenueOpsService | getTransportRoute | response | stops[].station.code | string | yes | Short operator code, e.g. (max length 32)
VenueOpsService | getTransportRoute | response | stops[].station.name | LocalisedText | yes
VenueOpsService | getTransportRoute | response | stops[].station.shortName | LocalisedText |  | The label on the route diagram and the map pin (Union Sq, MoE).
VenueOpsService | getTransportRoute | response | stops[].station.latitude | number |  | (min -90; max 90; nullable)
VenueOpsService | getTransportRoute | response | stops[].station.longitude | number |  | (min -180; max 180; nullable)
VenueOpsService | getTransportRoute | response | stops[].station.id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | getTransportRoute | response | stops[].station.active | boolean | yes | (default True)
VenueOpsService | getTransportRoute | response | id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | getTransportRoute | response | status | TransportRouteStatus: enum (draft, active, suspended, retired) | yes
VenueOpsService | getTransportRoute | response | totalMinutes | integer |  | The last stop's offset. (read-only)
VenueOpsService | getTransportRoute | response | catalogueEventId | string (uuid) |  | The catalogue event its departures are performances of. (read-only)
VenueOpsService | getTransportRoute | response | catalogueProductId | string (uuid) |  | The one-way trip product (kind timedAdmission); one variant per passenger type. (read-only)
VenueOpsService | getTransportRoute | param (path) | routeId | string (uuid) | yes
VenueOpsService | getTransportRouteMap | response | routeId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | getTransportRouteMap | response | lineCode | string
VenueOpsService | getTransportRouteMap | response | colour | string
VenueOpsService | getTransportRouteMap | response | stops | array of object | yes | Every stop in route order.
VenueOpsService | getTransportRouteMap | response | stops[].stationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | getTransportRouteMap | response | stops[].sequence | integer | yes
VenueOpsService | getTransportRouteMap | response | stops[].name | string | yes | Localised to the caller.
VenueOpsService | getTransportRouteMap | response | stops[].shortName | string
VenueOpsService | getTransportRouteMap | response | stops[].latitude | number |  | (nullable)
VenueOpsService | getTransportRouteMap | response | stops[].longitude | number |  | (nullable)
VenueOpsService | getTransportRouteMap | response | stops[].offsetMinutes | integer
VenueOpsService | getTransportRouteMap | response | stops[].onJourney | boolean | yes | Between the boarding and alighting stops
VenueOpsService | getTransportRouteMap | response | stops[].isBoarding | boolean
VenueOpsService | getTransportRouteMap | response | stops[].isAlighting | boolean
VenueOpsService | getTransportRouteMap | response | intermediateStopCount | integer |  | Stops between boarding and alighting — the number behind "Show full route (n stops)".
VenueOpsService | getTransportRouteMap | response | bounds | object |  | The box around the stops with coordinates, for the map's initial view. (nullable)
VenueOpsService | getTransportRouteMap | response | bounds.south | number
VenueOpsService | getTransportRouteMap | response | bounds.west | number
VenueOpsService | getTransportRouteMap | response | bounds.north | number
VenueOpsService | getTransportRouteMap | response | bounds.east | number
VenueOpsService | getTransportRouteMap | param (path) | routeId | string (uuid) | yes
VenueOpsService | getTransportRouteMap | param (query) | fromStationId | string (uuid)
VenueOpsService | getTransportRouteMap | param (query) | toStationId | string (uuid)
AiService | getVenueHistoryImport | response | id | string (uuid) | yes | (read-only)
AiService | getVenueHistoryImport | response | venueId | string (uuid) | yes
AiService | getVenueHistoryImport | response | dataKind | enum (attendance, admissions, ticketSales, fnbSales, retailSales, queueReadings, staffShifts) | yes
AiService | getVenueHistoryImport | response | assetId | string (uuid)
AiService | getVenueHistoryImport | response | sourceSystem | string |  | (nullable)
AiService | getVenueHistoryImport | response | columnMapping | object
AiService | getVenueHistoryImport | response | dryRun | boolean |  | (default False)
AiService | getVenueHistoryImport | response | status | enum (queued, validating, loading, completed, completedWithRejections, failed) | yes | (read-only)
AiService | getVenueHistoryImport | response | periodFrom | string (date) |  | (read-only; nullable)
AiService | getVenueHistoryImport | response | periodTo | string (date) |  | (read-only; nullable)
AiService | getVenueHistoryImport | response | monthsCovered | integer |  | (read-only)
AiService | getVenueHistoryImport | response | rowsRead | integer |  | (read-only)
AiService | getVenueHistoryImport | response | rowsLoaded | integer |  | (read-only)
AiService | getVenueHistoryImport | response | rowsRejected | integer |  | (read-only)
AiService | getVenueHistoryImport | response | findings | array of object |  | (read-only)
AiService | getVenueHistoryImport | response | findings[].row | integer
AiService | getVenueHistoryImport | response | findings[].code | enum (badDate, badNumber, negativeValue, duplicateDay, unmappedColumn, outOfRange)
AiService | getVenueHistoryImport | response | findings[].detail | string
AiService | getVenueHistoryImport | response | requestedByPrincipalId | string (uuid) |  | (read-only)
AiService | getVenueHistoryImport | response | createdAt | string (date-time) |  | (read-only)
AiService | getVenueHistoryImport | response | completedAt | string (date-time) |  | (read-only; nullable)
AiService | getVenueHistoryImport | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | getVenueHistoryImport | param (path) | importId | string (uuid) | yes
VenueOpsService | getVenueMap | response | version | integer |  | The published version these points and paths belong to, which is the number a client caches and sends back as version. (read-only; nullable)
VenueOpsService | getVenueMap | response | map | VenueMap |  | A park map, or a floor plan.
VenueOpsService | getVenueMap | response | map.id | string (uuid) | yes | (read-only)
VenueOpsService | getVenueMap | response | map.name | string | yes
VenueOpsService | getVenueMap | response | map.venueId | string (uuid) | yes
VenueOpsService | getVenueMap | response | map.scopePath | string |  | Derived from venueId. (read-only)
VenueOpsService | getVenueMap | response | map.kind | enum (park, floor, zone, parking)
VenueOpsService | getVenueMap | response | map.floorLevel | integer |  | (nullable)
VenueOpsService | getVenueMap | response | map.status | enum (draft, published, archived) | yes | draft on create. (read-only)
VenueOpsService | getVenueMap | response | map.publishedVersion | integer |  | The VenueMapVersion.version guests are served. (read-only; nullable)
VenueOpsService | getVenueMap | response | map.graphVersion | integer |  | Bumped by a publish or a closure, and returned as VenueMapGraph.version. (read-only)
VenueOpsService | getVenueMap | response | map.isGeoreferenced | boolean |  | Whether a guest can be located on it. (read-only)
VenueOpsService | getVenueMap | response | map.baseAssetId | string (uuid) |  | The illustrated map a guest actually sees, held in assets like any other media. (nullable)
VenueOpsService | getVenueMap | response | map.baseImageAlignment | object |  | How the illustration lines up with the geometry. (nullable)
VenueOpsService | getVenueMap | response | map.baseImageAlignment.imageWidthPx | integer
VenueOpsService | getVenueMap | response | map.baseImageAlignment.imageHeightPx | integer
VenueOpsService | getVenueMap | response | map.baseImageAlignment.anchors | array of object |  | (min items 2; max items 4)
VenueOpsService | getVenueMap | response | map.tileSetRef | string |  | Where a base image is large enough to need zoom levels. (read-only; nullable)
VenueOpsService | getVenueMap | response | map.boundsGeoJson | string |  | (nullable)
VenueOpsService | getVenueMap | response | map.graphStatus | enum (notBuilt, connected, disconnected, partial) |  | Whether every public point can actually be reached. (read-only)
VenueOpsService | getVenueMap | response | map.modelAssetId | string (uuid) |  | The 3D layer of the working draft (ADR-0069, contract item closed 3 October 2026): the GLB (model3d asset) the last glbModel import brought in. (read-only; nullable)
VenueOpsService | getVenueMap | response | map.navigationFileAssetId | string (uuid) |  | The navigation file imported with the model, kept so the import can be re-run and audited. (read-only; nullable)
VenueOpsService | getVenueMap | response | map.modelTransform | object |  | How the model's local frame sits on the earth (ADR-0069 section 3): the navigation file's anchor, stored once and used both ways. (read-only)
VenueOpsService | getVenueMap | response | map.modelTransform.originLat | number | yes | (min -90; max 90)
VenueOpsService | getVenueMap | response | map.modelTransform.originLng | number | yes | (min -180; max 180)
VenueOpsService | getVenueMap | response | map.modelTransform.originAltitudeMetres | number |  | (default 0)
VenueOpsService | getVenueMap | response | map.modelTransform.headingDegrees | number | yes | True-north bearing of the model's -Z axis, clockwise. (min 0)
VenueOpsService | getVenueMap | response | map.modelTransform.scale | number |  | Metres per model unit; 1 for a model in metres. (default 1)
VenueOpsService | getVenueMap | response | map.modelTransform.controlPoints | array of object |  | Surveyed checks, far apart. (min items 2; max items 8)
VenueOpsService | getVenueMap | response | map.model3dStatus | enum (none, publishable, blocked) |  | Whether the next publish carries the 3D layer. (read-only)
VenueOpsService | getVenueMap | response | points | array of VenuePoint
VenueOpsService | getVenueMap | response | points[].id | string (uuid) | yes | (read-only)
VenueOpsService | getVenueMap | response | points[].mapId | string (uuid) | yes | From the path of the operation that writes the point. (read-only)
VenueOpsService | getVenueMap | response | points[].kind | enum (ride, attraction, show, restaurant, cafe, shop, kiosk, toilet, …) | yes | A closed set, and emergencyExit is separate from exit on purpose.
VenueOpsService | getVenueMap | response | points[].name | string | yes | Unique per venue (decided 28 September, audit R108).
VenueOpsService | getVenueMap | response | points[].nameLocalised | object |  | (nullable)
VenueOpsService | getVenueMap | response | points[].position | object | yes | Drawing coordinates.
VenueOpsService | getVenueMap | response | points[].position.x | number | yes
VenueOpsService | getVenueMap | response | points[].position.y | number | yes
VenueOpsService | getVenueMap | response | points[].outletId | string (uuid) |  | For a restaurant, cafe, shop or kiosk. (nullable)
VenueOpsService | getVenueMap | response | points[].productId | string (uuid) |  | For a ride or show — links to wait times and to booking. (nullable)
VenueOpsService | getVenueMap | response | points[].accessPointId | string (uuid) |  | For an entrance or exit. (nullable)
VenueOpsService | getVenueMap | response | points[].isStepFree | boolean |  | Whether the point itself can be reached without steps. (default True)
VenueOpsService | getVenueMap | response | points[].openingHours | string |  | (nullable)
VenueOpsService | getVenueMap | response | points[].iconRef | string |  | (nullable)
VenueOpsService | getVenueMap | response | points[].isActive | boolean |  | (default True)
VenueOpsService | getVenueMap | response | points[].isNavigable | boolean |  | Whether a route may pass through it. (default True)
VenueOpsService | getVenueMap | response | points[].isDestination | boolean |  | Whether a guest may be routed *to* it, and whether it appears in a list of places. (default True)
VenueOpsService | getVenueMap | response | points[].description | object |  | What the guest reads on Item Detail (29 September, MOB-4). (nullable)
VenueOpsService | getVenueMap | response | points[].media | array of object |  | The gallery on Item Detail (29 September, MOB-4): images and short clips from the asset library, first isPrimary shown on the map card. (max items 12)
VenueOpsService | getVenueMap | response | points[].media[].assetId | string (uuid) | yes
VenueOpsService | getVenueMap | response | points[].media[].kind | enum (image, video) | yes
VenueOpsService | getVenueMap | response | points[].media[].isPrimary | boolean |  | (default False)
VenueOpsService | getVenueMap | response | points[].media[].altText | string |  | (max length 200; nullable)
VenueOpsService | getVenueMap | response | points[].featuredOffer | object |  | The product card on Item Detail, for every kind of point (29 September, MOB-4). (nullable)
VenueOpsService | getVenueMap | response | points[].featuredOffer.kind | enum (product, bundle) | yes
VenueOpsService | getVenueMap | response | points[].featuredOffer.id | string (uuid) | yes | The catalogue.product id or the promotions.bundle id, by kind.
VenueOpsService | getVenueMap | response | points[].featuredOffer.label | string |  | The button text, e.g. (max length 40; nullable)
VenueOpsService | getVenueMap | response | points[].typicalDurationMinutes | integer |  | How long a visit to this point usually takes, ride time and queue excluded (29 September, MOB-6). (min 1; max 600; nullable)
VenueOpsService | getVenueMap | response | points[].interestTags | array of enum (thrill, family, kids, water, animals, shows, culture, shopping, …) |  | What a guest who says they like this would like here (29 September, MOB-6): the planner matches the guest's interests against these. (max items 12)
VenueOpsService | getVenueMap | response | points[].cuisineTags | array of string |  | For dining points (restaurant, cafe, kiosk; 29 September, MOB-6). (max items 8)
VenueOpsService | getVenueMap | response | points[].retailTags | array of string |  | For retail points (shop, and a kiosk that sells goods rather than food; 30 September client meeting, MoM 4.7: retail and kiosk shops join F&B as venue-linked planner options). (max items 8)
VenueOpsService | getVenueMap | response | paths | array of VenuePath
VenueOpsService | getVenueMap | response | paths[].id | string (uuid) | yes | (read-only)
VenueOpsService | getVenueMap | response | paths[].mapId | string (uuid) | yes | From the path of the operation that writes the path. (read-only)
VenueOpsService | getVenueMap | response | paths[].fromPointId | string (uuid) | yes
VenueOpsService | getVenueMap | response | paths[].toPointId | string (uuid) | yes
VenueOpsService | getVenueMap | response | paths[].geometry | string |  | The centreline this edge follows, as an encoded polyline. (nullable)
VenueOpsService | getVenueMap | response | paths[].distanceMetres | number |  | Computed by the server from geometry and the georeference. (read-only; nullable)
VenueOpsService | getVenueMap | response | paths[].isStepFree | boolean |  | The single most important attribute on this object. (default True)
VenueOpsService | getVenueMap | response | paths[].isIndoor | boolean |  | (default False)
VenueOpsService | getVenueMap | response | paths[].restrictedByPointId | string (uuid) |  | Where a path is one-way, it is because of a thing on it — not because of the path. (nullable)
VenueOpsService | getVenueMap | response | paths[].closedReason | string |  | Set by setPathClosure during works or an incident, never by sending it here. (read-only; nullable)
VenueOpsService | getVenueMap | response | resources | array of PlacedResource |  | The bookable resources placed on this version of the map (rev 3 REV3-15).
VenueOpsService | getVenueMap | response | resources[].id | string (uuid) | yes | (read-only)
VenueOpsService | getVenueMap | response | resources[].mapId | string (uuid) | yes | From the path of the operation that writes it. (read-only)
VenueOpsService | getVenueMap | response | resources[].resourceId | string (uuid) | yes | The resources.Resource this is.
VenueOpsService | getVenueMap | response | resources[].label | string | yes | What the guest sees and taps, e.g. (max length 40)
VenueOpsService | getVenueMap | response | resources[].kind | enum (cabana, lounger, table, pitch, other) | yes | A subset of resources.ResourceKind, the kinds a guest books from a map.
VenueOpsService | getVenueMap | response | resources[].zone | string | yes | The area the guest reads it by, e.g. (max length 80)
VenueOpsService | getVenueMap | response | resources[].capacity | integer | yes | Guests it takes, e.g. (min 1; max 500)
VenueOpsService | getVenueMap | response | resources[].priceBandCode | string | yes | The band it sells in, e.g. (max length 40)
VenueOpsService | getVenueMap | response | resources[].variantId | string (uuid) |  | Resolved from the price band. (read-only; nullable)
VenueOpsService | getVenueMap | response | resources[].position | object | yes | Drawing coordinates of its label anchor, as on VenuePoint.
VenueOpsService | getVenueMap | response | resources[].position.x | number | yes
VenueOpsService | getVenueMap | response | resources[].position.y | number | yes
VenueOpsService | getVenueMap | response | resources[].boundary | array of object |  | The shape drawn, as a polygon in drawing coordinates. (nullable)
VenueOpsService | getVenueMap | response | resources[].boundary[].x | number
VenueOpsService | getVenueMap | response | resources[].boundary[].y | number
VenueOpsService | getVenueMap | response | resources[].isBookable | boolean |  | False keeps it on the map and off sale, e.g. (default True)
VenueOpsService | getVenueMap | response | model3d | object |  | The 3D layer of the version read (ADR-0069; 3 October 2026, r1 additions). (nullable)
VenueOpsService | getVenueMap | response | model3d.modelAssetId | string (uuid) | yes
VenueOpsService | getVenueMap | response | model3d.sizeBytes | integer |  | (nullable)
VenueOpsService | getVenueMap | response | model3d.transform | VenueModelTransform | yes | ADR-0069 section 3: the navigation file's anchor.
VenueOpsService | getVenueMap | response | model3d.transform.originLat | number | yes | (min -90; max 90)
VenueOpsService | getVenueMap | response | model3d.transform.originLng | number | yes | (min -180; max 180)
VenueOpsService | getVenueMap | response | model3d.transform.originAltitudeMetres | number |  | (default 0)
VenueOpsService | getVenueMap | response | model3d.transform.headingDegrees | number | yes | True-north bearing of the model's -Z axis, clockwise. (min 0)
VenueOpsService | getVenueMap | response | model3d.transform.scale | number |  | Metres per model unit; 1 for a model in metres. (default 1)
VenueOpsService | getVenueMap | response | model3d.transform.controlPoints | array of object |  | Surveyed checks, far apart. (min items 2; max items 8)
VenueOpsService | getVenueMap | param (path) | mapId | string (uuid) | yes
VenueOpsService | getVenueMap | param (query) | version | integer |  | Absent means the published version.
VenueOpsService | getVenueMap | param (query) | draft | boolean |  | Read the working draft instead of a published version.
VenueOpsService | getVenueMapGraph | response | mapId | string (uuid) | yes
VenueOpsService | getVenueMapGraph | response | version | integer | yes | Bumped by a publish or a closure, and stored as VenueMap.graphVersion.
VenueOpsService | getVenueMapGraph | response | generatedAt | string (date-time)
VenueOpsService | getVenueMapGraph | response | nodes | array of object | yes
VenueOpsService | getVenueMapGraph | response | nodes[].pointId | string (uuid)
VenueOpsService | getVenueMapGraph | response | nodes[].x | number
VenueOpsService | getVenueMapGraph | response | nodes[].y | number
VenueOpsService | getVenueMapGraph | response | nodes[].kind | string
VenueOpsService | getVenueMapGraph | response | nodes[].isStepFree | boolean
VenueOpsService | getVenueMapGraph | response | edges | array of object | yes
VenueOpsService | getVenueMapGraph | response | edges[].from | string (uuid)
VenueOpsService | getVenueMapGraph | response | edges[].to | string (uuid)
VenueOpsService | getVenueMapGraph | response | edges[].distanceMetres | number
VenueOpsService | getVenueMapGraph | response | edges[].isStepFree | boolean
VenueOpsService | getVenueMapGraph | response | edges[].throughPointId | string |  | Where an access point restricts this edge. (nullable)
VenueOpsService | getVenueMapGraph | response | edges[].isClosed | boolean
VenueOpsService | getVenueMapGraph | response | components | integer |  | How many disconnected parts.
VenueOpsService | getVenueMapGraph | param (path) | mapId | string (uuid) | yes
VenueOpsService | getVenueMapGraph | param (query) | draft | boolean |  | The working draft's graph instead of the published one.
VenueOpsService | getVenueMapGraph | param (query) | stepFreeOnly | boolean |  | Returns the step-free subgraph, not a filtered copy of the whole one.
VenueOpsService | getVisitPlan | response | id | string (uuid) | yes | (read-only)
VenueOpsService | getVisitPlan | response | venueId | string (uuid) | yes
VenueOpsService | getVisitPlan | response | scopePath | string |  | Derived from venueId. (read-only)
VenueOpsService | getVisitPlan | response | subjectId | string (uuid) |  | The signed-in guest. (read-only; nullable)
VenueOpsService | getVisitPlan | response | sessionRef | string |  | The anonymous device session that owns the plan until sign-in. (read-only; nullable)
VenueOpsService | getVisitPlan | response | ownership | enum (anonymous, account) |  | anonymous while the plan belongs to a device session (built and changed only; it lapses with the session), account once the guest signed in and the plan moved to their account, where it is saved and… (read-only)
VenueOpsService | getVisitPlan | response | status | enum (draft, booked, archived) | yes | booked after bookVisitPlan; a booked plan is read-only. (read-only)
VenueOpsService | getVisitPlan | response | version | integer | yes | The current version. (min 1; read-only)
VenueOpsService | getVisitPlan | response | source | enum (rules, preset, aiAgent) |  | What produced the current version: the rules planner, a preset, or the AI planner agent acting for the guest. (read-only)
VenueOpsService | getVisitPlan | response | inputs | VisitPlanRequest |  | What generateVisitPlan takes (29 September, MOB-6): the Plan tab's form on GST-051 and WEB-050.
VenueOpsService | getVisitPlan | response | inputs.venueId | string (uuid) | yes | The venue the guest picked in the app (GST-001 / WEB-001), which scopes the plan.
VenueOpsService | getVisitPlan | response | inputs.dayVenues | array of object |  | Which venue on which date, in a multi-venue tenant (30 September client meeting, MoM 4.7, Allam's requirement). (max items 7)
VenueOpsService | getVisitPlan | response | inputs.dayVenues[].date | string (date) | yes
VenueOpsService | getVisitPlan | response | inputs.dayVenues[].venueId | string (uuid) | yes
VenueOpsService | getVisitPlan | response | inputs.dates | array of string (date) | yes | (min items 1; max items 7)
VenueOpsService | getVisitPlan | response | inputs.party | array of object | yes | One entry per person. (min items 1; max items 20)
VenueOpsService | getVisitPlan | response | inputs.party[].heightCm | integer |  | (min 40; max 230; nullable)
VenueOpsService | getVisitPlan | response | inputs.party[].ageYears | integer |  | (min 0; max 120; nullable)
VenueOpsService | getVisitPlan | response | inputs.pace | enum (packed, relaxed) |  | (default relaxed)
VenueOpsService | getVisitPlan | response | inputs.interestTags | array of string |  | The same closed list as VenuePoint.interestTags. (max items 12)
VenueOpsService | getVisitPlan | response | inputs.cuisineTags | array of string |  | Matched per day against the cuisineTags of that day's venue's dining points only (30 September, MoM 4.7). (max items 8)
VenueOpsService | getVisitPlan | response | inputs.retailTags | array of string |  | Shops the party would like to visit (30 September client meeting, MoM 4.7: retail and kiosk shops join F&B as venue-linked planner options), e.g. (max items 8)
VenueOpsService | getVisitPlan | response | inputs.mustIncludePointIds | array of string (uuid) |  | Placed on a day whose venue has the point. (max items 10)
VenueOpsService | getVisitPlan | response | inputs.preset | enum (highlights, family, thrillSeeker, waterDay, relaxed, showsAndDining) |  | A ready-made day plan (GST-052 Suggested Itineraries): the preset fixes the interests and the pace, and the party still decides eligibility. (nullable)
VenueOpsService | getVisitPlan | response | inputs.presetKey | string |  | The ready-made plan the guest took on GST-052 (30 September, second wave of the 29 September pass, MOB-6): one of the built-in preset keys above, or a key of a ready-made plan the venue defines. (max length 64; pattern ^[a-z][a-zA-Z0-9]*$; nullable)
VenueOpsService | getVisitPlan | response | inputs.startTime | string |  | When the party arrives. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$; nullable)
VenueOpsService | getVisitPlan | response | inputs.locale | string |  | (nullable)
VenueOpsService | getVisitPlan | response | mapVersion | integer |  | The published map version the plan was laid out on. (read-only)
VenueOpsService | getVisitPlan | response | cartId | string (uuid) |  | The cart bookVisitPlan filled. (read-only; nullable)
VenueOpsService | getVisitPlan | response | excluded | array of object |  | What was left out and why, e.g. (read-only)
VenueOpsService | getVisitPlan | response | excluded[].pointId | string (uuid)
VenueOpsService | getVisitPlan | response | excluded[].productId | string (uuid) |  | (nullable)
VenueOpsService | getVisitPlan | response | excluded[].reason | enum (heightRule, ageRule, closedOnDate, notInInterests, noTime, notAtVenue) |  | notAtVenue (30 September, MoM 4.7): a must-include point that is at none of the plan's venues, so no day could hold it.
VenueOpsService | getVisitPlan | response | unmatchedPreferences | array of object |  | A preference a day's venue cannot meet is said, never faked (30 September client meeting, MoM 4.7, Allam's requirement). (read-only)
VenueOpsService | getVisitPlan | response | unmatchedPreferences[].date | string (date) | yes
VenueOpsService | getVisitPlan | response | unmatchedPreferences[].venueId | string (uuid) | yes | The day's venue, which has no match.
VenueOpsService | getVisitPlan | response | unmatchedPreferences[].preference | enum (cuisine, retail, interest) | yes
VenueOpsService | getVisitPlan | response | unmatchedPreferences[].tag | string | yes | (max length 30)
VenueOpsService | getVisitPlan | response | unmatchedPreferences[].availableAtVenueIds | array of string (uuid) |  | Other active venues of the tenant where the tag is matched.
VenueOpsService | getVisitPlan | response | days | array of object | yes | One per date, in order. (read-only)
VenueOpsService | getVisitPlan | response | days[].date | string (date) | yes
VenueOpsService | getVisitPlan | response | days[].venueId | string (uuid) | yes | The venue this day is planned at (30 September, MoM 4.7): VisitPlanRequest.dayVenues for the date, else venueId.
VenueOpsService | getVisitPlan | response | days[].opensAt | string |  | (nullable)
VenueOpsService | getVisitPlan | response | days[].closesAt | string |  | (nullable)
VenueOpsService | getVisitPlan | response | days[].items | array of VisitPlanItem | yes
VenueOpsService | getVisitPlan | response | days[].items[].id | string (uuid) | yes | (read-only)
VenueOpsService | getVisitPlan | response | days[].items[].planId | string (uuid) | yes | (read-only)
VenueOpsService | getVisitPlan | response | days[].items[].planVersion | integer | yes | (min 1; read-only)
VenueOpsService | getVisitPlan | response | days[].items[].date | string (date) | yes
VenueOpsService | getVisitPlan | response | days[].items[].sequence | integer | yes | (min 1)
VenueOpsService | getVisitPlan | response | days[].items[].kind | enum (attraction, show, meal, shop, rest, travel) | yes | meal is a stop at a dining point (restaurant, cafe or food kiosk); shop is a retail stop at a shop or a retail kiosk (30 September client meeting, MoM 4.7: retail is placed from the day venue's own p…
VenueOpsService | getVisitPlan | response | days[].items[].venueId | string (uuid) |  | The venue of this stop (30 September client meeting, MoM 4.7): always the day's venue, and the venue whose map pointId is on. (read-only)
VenueOpsService | getVisitPlan | response | days[].items[].pointId | string (uuid) |  | (nullable)
VenueOpsService | getVisitPlan | response | days[].items[].productId | string (uuid) |  | What is bought for this stop, where it is bought. (nullable)
VenueOpsService | getVisitPlan | response | days[].items[].bundleId | string (uuid) |  | A meal combo or package, from the point's featuredOffer. (nullable)
VenueOpsService | getVisitPlan | response | days[].items[].performanceId | string (uuid) |  | (nullable)
VenueOpsService | getVisitPlan | response | days[].items[].startsAt | string (date-time) | yes
VenueOpsService | getVisitPlan | response | days[].items[].endsAt | string (date-time) | yes
VenueOpsService | getVisitPlan | response | days[].items[].walkMinutesBefore | integer |  | (min 0; nullable)
VenueOpsService | getVisitPlan | response | days[].items[].expectedWaitMinutes | integer |  | The typical wait at that hour when the plan was laid out; GST-059 replaces it with the live one. (min 0; nullable)
VenueOpsService | getVisitPlan | response | days[].items[].addOnSuggestion | object |  | A suggested add-on for this stop, e.g. (nullable)
VenueOpsService | getVisitPlan | response | days[].items[].addOnAccepted | boolean |  | (default False)
VenueOpsService | getVisitPlan | response | days[].items[].addOnProductIds | array of string (uuid) |  | Add-ons the guest put on this stop with addAddOn (CHG-RUL-009), beside an accepted suggestion, as catalogue product ids. (read-only)
VenueOpsService | getVisitPlan | response | days[].items[].pinned | boolean |  | The guest fixed this stop; a re-lay moves other stops around it. (default False)
VenueOpsService | getVisitPlan | response | days[].items[].note | string |  | (max length 200; nullable)
VenueOpsService | getVisitPlan | response | createdAt | string (date-time) |  | (read-only)
VenueOpsService | getVisitPlan | response | updatedAt | string (date-time) |  | (read-only)
VenueOpsService | getVisitPlan | param (path) | planId | string (uuid) | yes
VenueOpsService | getVisitPlan | param (query) | version | integer |  | Absent means the current version.
OrderService | getVisitReminder | response | id | string (uuid) |  | (read-only)
OrderService | getVisitReminder | response | orderId | string (uuid) |  | (read-only)
OrderService | getVisitReminder | response | subjectId | string (uuid) |  | The guest who set it. (read-only)
OrderService | getVisitReminder | response | enabled | boolean | yes
OrderService | getVisitReminder | response | leadTimeMinutes | integer |  | How long before each session starts. (min 15; max 10080; default 1440)
OrderService | getVisitReminder | response | channels | array of enum (push, email, sms) |  | (default ['push'])
OrderService | getVisitReminder | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | getVisitReminder | param (path) | orderId | string (uuid) | yes
VenueOpsService | getWaitTimes | param (query) | venueId | string (uuid) | yes
VenueOpsService | getWaitTimes | param (query) | category | string (uuid) |  | A catalogue product category id (ProductCategory, catalogue contract).
VenueOpsService | getWaitingGuest | response | id | string (uuid) | yes | The client-generated UUIDv7 from JoinQueueRequest.id, and the entryId every entry path takes.
VenueOpsService | getWaitingGuest | response | queueId | string (uuid) | yes
VenueOpsService | getWaitingGuest | response | queueName | LocalisedText
VenueOpsService | getWaitingGuest | response | subjectId | string (uuid) |  | (nullable)
VenueOpsService | getWaitingGuest | response | partyNumber | integer | yes | What the guest sees and what appears on signage.
VenueOpsService | getWaitingGuest | response | partySize | integer | yes
VenueOpsService | getWaitingGuest | response | status | QueueEntryStatus: enum (waiting, called, redeemed, expired, noShow, cancelled, released) | yes
VenueOpsService | getWaitingGuest | response | positionInQueue | integer |  | (nullable)
VenueOpsService | getWaitingGuest | response | partiesAhead | integer |  | (nullable)
VenueOpsService | getWaitingGuest | response | estimatedCallAt | string (date-time) |  | (nullable)
VenueOpsService | getWaitingGuest | response | isFastPass | boolean
VenueOpsService | getWaitingGuest | response | priorityBasis | enum (none, entitlement, loyaltyTier, promotion, accessibility) |  | Why this party is priority, when it is (decided 29 September, build pass; 5.6.7, 5.6.34): the first QueueFastPass criterion met at join, in the order entitlement, loyalty tier, promotion, accessibili… (default none)
VenueOpsService | getWaitingGuest | response | priorityTierId | string (uuid) |  | The loyalty tier that granted priority, where priorityBasis is loyaltyTier. (nullable)
VenueOpsService | getWaitingGuest | response | priorityPromotionId | string (uuid) |  | The promotion that granted priority, where priorityBasis is promotion. (nullable)
VenueOpsService | getWaitingGuest | response | accessibilityNeedDeclared | boolean |  | What the party declared at join, shown to the operator at the front. (default False)
VenueOpsService | getWaitingGuest | response | entitlementId | string |  | (nullable)
VenueOpsService | getWaitingGuest | response | calledAt | string (date-time) |  | (nullable)
VenueOpsService | getWaitingGuest | response | returnWindowEndsAt | string (date-time) |  | (nullable)
VenueOpsService | getWaitingGuest | response | redeemedAt | string (date-time) |  | (nullable)
VenueOpsService | getWaitingGuest | response | admittedCount | integer |  | (nullable)
VenueOpsService | getWaitingGuest | response | joinedAt | string (date-time) | yes
VenueOpsService | getWaitingGuest | response | syncedAt | string (date-time) |  | (nullable)
VenueOpsService | getWaitingGuest | response | overriddenByPrincipalId | string (uuid) |  | Who let the party past the queue (overrideWaitingGuest, 4 October 2026, CHG-FXC-003), with overrideReason and overriddenAt. (read-only; nullable)
VenueOpsService | getWaitingGuest | response | overrideReason | string |  | (read-only; nullable)
VenueOpsService | getWaitingGuest | response | overriddenAt | string (date-time) |  | (read-only; nullable)
VenueOpsService | getWaitingGuest | param (path) | entryId | string (uuid) | yes
CatalogueService | getWaitingRoomPosition | response | waitingEntryId | string (uuid) | yes | A UUIDv7 minted on arrival; what the waiting page polls with.
CatalogueService | getWaitingRoomPosition | response | performanceId | string (uuid) | yes
CatalogueService | getWaitingRoomPosition | response | state | enum (notRequired, waiting, admitted, expired, closed) | yes | notRequired: the room is off, go to the sale.
CatalogueService | getWaitingRoomPosition | response | position | integer |  | Place in the room; null unless waiting. (min 1; nullable)
CatalogueService | getWaitingRoomPosition | response | aheadOfYou | integer |  | (min 0; nullable)
CatalogueService | getWaitingRoomPosition | response | estimatedWaitSeconds | integer |  | At the current release rate. (min 0; nullable)
CatalogueService | getWaitingRoomPosition | response | pollAfterSeconds | integer |  | (min 1; default 5)
CatalogueService | getWaitingRoomPosition | response | admission | object |  | Set when state is admitted. (nullable)
CatalogueService | getWaitingRoomPosition | response | admission.token | string | yes | The signed token, opaque to the client.
CatalogueService | getWaitingRoomPosition | response | admission.tokenId | string (uuid) |  | The token's unique id.
CatalogueService | getWaitingRoomPosition | response | admission.performanceId | string (uuid) | yes
CatalogueService | getWaitingRoomPosition | response | admission.expiresAt | string (date-time) | yes
CatalogueService | getWaitingRoomPosition | param (path) | performanceId | string (uuid) | yes
CatalogueService | getWaitingRoomPosition | param (path) | waitingEntryId | string (uuid) | yes
MarketingService | getWaiverStatus | response | isSatisfied | boolean
MarketingService | getWaiverStatus | response | missingFormIds | array of string (uuid)
MarketingService | getWaiverStatus | response | expiringWithinDays | integer |  | (nullable)
MarketingService | getWaiverStatus | param (path) | subjectId | string (uuid) | yes
MarketingService | getWaiverStatus | param (query) | productId | string (uuid)
WalletService | getWallet | response | id | string (uuid) |  | Added 20 August. (read-only)
WalletService | getWallet | response | subjectId | string (uuid) | yes
WalletService | getWallet | response | balance | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | getWallet | response | balance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | getWallet | response | balance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | getWallet | response | balance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | getWallet | response | credits | array of object |  | 4.3.5 and 4.3.19.
WalletService | getWallet | response | credits[].kind | enum (cash, bonus, redemption, refund, goodwill) | yes | cash is money the guest paid and the others are not.
WalletService | getWallet | response | credits[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | getWallet | response | credits[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | getWallet | response | credits[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | getWallet | response | credits[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | getWallet | response | credits[].expiresAt | string (date-time) |  | (nullable)
WalletService | getWallet | response | credits[].sourceRef | string |  | (nullable)
WalletService | getWallet | response | credits[].isRefundable | boolean |  | True only for cash. (default False)
WalletService | getWallet | response | bonusBalance | object |  | Promotional value.
WalletService | getWallet | response | bonusBalance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | getWallet | response | bonusBalance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | getWallet | response | bonusBalance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | getWallet | response | currency | string | yes | (pattern ^[A-Z]{3}$)
WalletService | getWallet | response | status | enum (active, suspended, closed) | yes
WalletService | getWallet | response | homeCellName | string |  | Where the authoritative balance lives. (nullable)
WalletService | getWallet | response | expiresAt | string (date-time) |  | (nullable)
WalletService | getWallet | response | lastActivityAt | string (date-time) |  | (nullable)
WalletService | getWallet | param (path) | subjectId | string (uuid) | yes
WalletService | getWallet | param (header) | X-Consistency-Token | string |  | Opaque token returned by a prior write: the database instance and its WAL LSN (SD-025, 29 September; ADR-0040 allows several instances per region, so an LSN alone is ambiguous).
WalletService | getWalletAutoReloadSetting | response | walletId | string (uuid) |  | (read-only)
WalletService | getWalletAutoReloadSetting | response | subjectId | string (uuid) |  | (read-only)
WalletService | getWalletAutoReloadSetting | response | enabled | boolean | yes
WalletService | getWalletAutoReloadSetting | response | thresholdAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | getWalletAutoReloadSetting | response | thresholdAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | getWalletAutoReloadSetting | response | thresholdAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | getWalletAutoReloadSetting | response | thresholdAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | getWalletAutoReloadSetting | response | reloadAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | getWalletAutoReloadSetting | response | reloadAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | getWalletAutoReloadSetting | response | reloadAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | getWalletAutoReloadSetting | response | reloadAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | getWalletAutoReloadSetting | response | paymentTokenId | string (uuid) |  | (nullable)
WalletService | getWalletAutoReloadSetting | response | maximumPerDay | integer |  | (min 1; nullable)
WalletService | getWalletAutoReloadSetting | response | status | enum (active, suspendedAfterDecline, disabledByVenue) |  | (read-only)
WalletService | getWalletAutoReloadSetting | response | lastReloadAt | string (date-time) |  | (read-only; nullable)
WalletService | getWalletAutoReloadSetting | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
WalletService | getWalletAutoReloadSetting | param (path) | walletId | string (uuid) | yes
WalletService | getWalletExitBalance | response | walletId | string (uuid) | yes
WalletService | getWalletExitBalance | response | balance | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | getWalletExitBalance | response | balance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | getWalletExitBalance | response | balance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | getWalletExitBalance | response | balance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | getWalletExitBalance | response | pendingOfflineAmount | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | getWalletExitBalance | response | pendingOfflineAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | getWalletExitBalance | response | pendingOfflineAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | getWalletExitBalance | response | pendingOfflineAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | getWalletExitBalance | response | amountDue | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | getWalletExitBalance | response | amountDue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | getWalletExitBalance | response | amountDue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | getWalletExitBalance | response | amountDue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | getWalletExitBalance | response | refundable | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | getWalletExitBalance | response | refundable.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | getWalletExitBalance | response | refundable.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | getWalletExitBalance | response | refundable.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | getWalletExitBalance | response | nonRefundableCredit | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | getWalletExitBalance | response | nonRefundableCredit.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | getWalletExitBalance | response | nonRefundableCredit.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | getWalletExitBalance | response | nonRefundableCredit.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | getWalletExitBalance | response | waiveAllowedUpTo | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | getWalletExitBalance | response | waiveAllowedUpTo.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | getWalletExitBalance | response | waiveAllowedUpTo.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | getWalletExitBalance | response | waiveAllowedUpTo.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | getWalletExitBalance | response | asAt | string (date-time)
WalletService | getWalletExitBalance | param (path) | walletId | string (uuid) | yes
MarketingService | getWishlist | response | subjectId | string (uuid) | yes
MarketingService | getWishlist | response | items | array of object | yes
MarketingService | getWishlist | response | items[].id | string (uuid) | yes
MarketingService | getWishlist | response | items[].variantId | string (uuid) | yes
MarketingService | getWishlist | response | items[].productName | string
MarketingService | getWishlist | response | items[].performanceId | string (uuid) |  | (nullable)
MarketingService | getWishlist | response | items[].performanceStartsAt | string (date-time) |  | (nullable)
MarketingService | getWishlist | response | items[].price | Money |  | On the wire this is three fields; in the database it is one column.
MarketingService | getWishlist | response | items[].price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
MarketingService | getWishlist | response | items[].price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
MarketingService | getWishlist | response | items[].price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
MarketingService | getWishlist | response | items[].imageAssetRef | string |  | (nullable)
MarketingService | getWishlist | response | items[].isAvailable | boolean | yes | False where the product has been withdrawn or the performance has passed.
MarketingService | getWishlist | response | items[].unavailableReason | string |  | (nullable)
MarketingService | getWishlist | response | items[].note | string |  | (nullable)
MarketingService | getWishlist | response | items[].addedAt | string (date-time) | yes
MarketingService | getWishlist | param (path) | subjectId | string (uuid) | yes
TenancyService | getWorkstationHealth | response | score | integer
TenancyService | getWorkstationHealth | response | status | enum (healthy, warning, degraded, offline)
TenancyService | getWorkstationHealth | response | contributors | array of object
TenancyService | getWorkstationHealth | response | contributors[].factor | enum (heartbeatAge, deviceOffline, deviceBattery, firmwareOutdated, syncBacklog, errorRate, profileDrift)
TenancyService | getWorkstationHealth | response | contributors[].detail | string
TenancyService | getWorkstationHealth | response | contributors[].weight | integer
TenancyService | getWorkstationHealth | param (path) | workstationId | string (uuid) | yes
OrderService | getWorkstationShift | response | id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | getWorkstationShift | response | workstationId | string (uuid) | yes
OrderService | getWorkstationShift | response | venueId | string (uuid) | yes
OrderService | getWorkstationShift | response | scopePath | string | yes
OrderService | getWorkstationShift | response | principalId | string (uuid) | yes | Who opened it.
OrderService | getWorkstationShift | response | principalDisplayName | string
OrderService | getWorkstationShift | response | incidents | array of object |  | BL-097.
OrderService | getWorkstationShift | response | incidents[].kind | enum (noSale, drawerOpen, override, voidAfterPayment, guestDispute, tillJam, priceQuery, other)
OrderService | getWorkstationShift | response | incidents[].at | string (date-time)
OrderService | getWorkstationShift | response | incidents[].principalId | string (uuid)
OrderService | getWorkstationShift | response | incidents[].note | string |  | (nullable)
OrderService | getWorkstationShift | response | status | ShiftStatus: enum (pendingApproval, open, suspended, pendingVariance, pendingClosure, closed, autoClosed) | yes
OrderService | getWorkstationShift | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | getWorkstationShift | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | getWorkstationShift | response | depositBoxCode | string |  | (nullable)
OrderService | getWorkstationShift | response | bagNumber | string |  | (nullable)
OrderService | getWorkstationShift | response | openingFloat | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getWorkstationShift | response | openingFloat.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getWorkstationShift | response | openingFloat.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getWorkstationShift | response | openingFloat.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getWorkstationShift | response | salesTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getWorkstationShift | response | salesTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getWorkstationShift | response | salesTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getWorkstationShift | response | salesTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getWorkstationShift | response | refundsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getWorkstationShift | response | refundsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getWorkstationShift | response | refundsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getWorkstationShift | response | refundsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getWorkstationShift | response | liftsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | getWorkstationShift | response | liftsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getWorkstationShift | response | liftsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getWorkstationShift | response | liftsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getWorkstationShift | response | expectedCash | object |  | 26 September, pull audit R207. (read-only; nullable)
OrderService | getWorkstationShift | response | expectedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getWorkstationShift | response | expectedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getWorkstationShift | response | expectedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getWorkstationShift | response | countedCash | object |  | What the close count found. (read-only; nullable)
OrderService | getWorkstationShift | response | countedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getWorkstationShift | response | countedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getWorkstationShift | response | countedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getWorkstationShift | response | variance | object |  | Counted minus expected, as ShiftCloseResult.variance. (read-only; nullable)
OrderService | getWorkstationShift | response | variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | getWorkstationShift | response | variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | getWorkstationShift | response | variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | getWorkstationShift | response | cashierReason | enum (tillError, unrecordedRefund, miscount, other) |  | What the cashier said went wrong, given with the blind count (CloseShiftRequest.cashierReason, DI-803) without seeing the variance; the supervisor reads it beside the variance on BO-040 (CHG-FIN-003). (read-only; nullable)
OrderService | getWorkstationShift | response | cashierNote | string |  | The cashier's note with the count (CloseShiftRequest.notes; CHG-FIN-003). (max length 1000; read-only; nullable)
OrderService | getWorkstationShift | response | varianceReasonRequired | boolean |  | Computed, not stored (CHG-R4-019): true while the shift is pendingClosure because its count differs from the expected figure within the threshold and no cashierReason is recorded. (read-only)
OrderService | getWorkstationShift | response | heldLeaseCount | integer |  | Inventory leases currently held by this workstation.
OrderService | getWorkstationShift | response | openedAt | string (date-time) | yes
OrderService | getWorkstationShift | response | businessDate | string (date) |  | The business day the shift belongs to (12 October 2026, CHG-R6-032): the venue-local date of openedAt taken against the venue's businessDayCutoff (tenancy VenueSettings, inheriting the tenant default… (read-only)
OrderService | getWorkstationShift | response | recordedAt | string (date-time) |  | When the device recorded the open.
OrderService | getWorkstationShift | response | suspendedAt | string (date-time) |  | (nullable)
OrderService | getWorkstationShift | response | suspendReason | string |  | The reason given to suspendShift. (max length 200; nullable)
OrderService | getWorkstationShift | response | closedAt | string (date-time) |  | (nullable)
OrderService | getWorkstationShift | response | closedByPrincipalId | string (uuid) |  | Who submitted the close count. (nullable)
OrderService | getWorkstationShift | response | recountRequestedAt | string (date-time) |  | Set by rejectShiftVariance, cleared by the cashier's recount (decided 2 October 2026, Chinmay; DEC-175; CHG-CSP-013; DI-804). (read-only; nullable)
OrderService | getWorkstationShift | response | recountRequestedByPrincipalId | string (uuid) |  | The supervisor who sent the count back (CHG-CSP-013). (read-only; nullable)
OrderService | getWorkstationShift | response | recountReason | string |  | The supervisor's reason, shown to the cashier; never an amount (CHG-CSP-013, CHG-FIN-003). (max length 500; read-only; nullable)
OrderService | getWorkstationShift | response | countNumber | integer |  | How many close counts the shift has had: 0 before the first, 1 after it, 2 after a recount (CHG-CSP-013). (min 0; read-only)
OrderService | getWorkstationShift | response | syncedAt | string (date-time) |  | Null while the shift has unsynced operations. (nullable)
OrderService | getWorkstationShift | response | approvals | array of object
OrderService | getWorkstationShift | response | approvals[].kind | enum (open, close, variance) | yes | open from approveShiftOpen, close from approveShiftClose, variance from acceptShiftVariance.
OrderService | getWorkstationShift | response | approvals[].principalId | string (uuid) | yes
OrderService | getWorkstationShift | response | approvals[].at | string (date-time) | yes
OrderService | getWorkstationShift | response | approvals[].reason | string
OrderService | giveShiftVarianceReason | request | reason | enum (tillError, unrecordedRefund, miscount, other) | yes | The same reasons as CloseShiftRequest.cashierReason (DI-803), recorded as the shift's cashierReason.
OrderService | giveShiftVarianceReason | request | note | string |  | What happened, in the cashier's words; recorded as the shift's cashierNote (appended to a note given with the count). (max length 1000)
OrderService | giveShiftVarianceReason | response | shiftId | string (uuid) | yes
OrderService | giveShiftVarianceReason | response | status | ShiftStatus: enum (pendingApproval, open, suspended, pendingVariance, pendingClosure, closed, autoClosed) | yes
OrderService | giveShiftVarianceReason | response | outcome | enum (closed, referredToSupervisor, awaitingCloseApproval) | yes | closed: within the venue's threshold, the shift is closed.
OrderService | giveShiftVarianceReason | response | countedAt | string (date-time) | yes
OrderService | giveShiftVarianceReason | response | countNumber | integer |  | 1 for the first count of the close, 2 for a recount the supervisor asked for, and so on. (min 1)
OrderService | giveShiftVarianceReason | response | varianceReasonRequired | boolean |  | The count found a difference within the threshold and no reason came with it (the client's policy of 6 October 2026, T10.1; CHG-R4-019). (default False)
OrderService | giveShiftVarianceReason | param (path) | shiftId | string (uuid) | yes
OrderService | giveShiftVarianceReason | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | grantDelegation | request | overSubjectId | string (uuid) | yes
IdentityService | grantDelegation | request | delegationKind | enum (primaryHolder, familyMember, groupLeader, attendee, corporateAdmin, corporateMember, carer) | yes
IdentityService | grantDelegation | request | permission | string | yes
IdentityService | grantDelegation | request | overObjectRef | string |  | (nullable)
IdentityService | grantDelegation | request | quota | integer |  | (nullable)
IdentityService | grantDelegation | request | validTo | string (date-time) |  | (nullable)
IdentityService | grantDelegation | request | isRevocableBySubject | boolean |  | (default True)
IdentityService | grantDelegation | response | id | string (uuid) | yes
IdentityService | grantDelegation | response | principalId | string (uuid) |  | (nullable)
IdentityService | grantDelegation | response | roleId | string (uuid) |  | (nullable)
IdentityService | grantDelegation | response | permission | string | yes | From the permission enum.
IdentityService | grantDelegation | response | subjectId | string (uuid) |  | CF-132, CL-05. (nullable)
IdentityService | grantDelegation | response | overSubjectId | string (uuid) |  | Whose behalf. (nullable)
IdentityService | grantDelegation | response | overObjectRef | string |  | Where the authority is over a thing rather than a scope — a wallet, an entitlement, a booking. (nullable)
IdentityService | grantDelegation | response | delegationKind | enum (primaryHolder, familyMember, groupLeader, attendee, corporateAdmin, corporateMember, carer) |  | What kind of relationship this expresses, for display and for reporting. (nullable)
IdentityService | grantDelegation | response | quota | integer |  | 2.14.15 and 4.3.11. (nullable)
IdentityService | grantDelegation | response | isRevocableBySubject | boolean |  | Whether the person it is over can end it. (default True)
IdentityService | grantDelegation | response | scopePath | string | yes
IdentityService | grantDelegation | response | effect | enum (ALLOW, DENY) | yes
IdentityService | grantDelegation | response | permissionId | string (uuid) |  | Taken from identity.user_access, 20 September, when that table was collapsed into this one. (nullable)
IdentityService | grantDelegation | response | revokedAt | string (date-time) |  | Taken from identity.user_access. (read-only; nullable)
IdentityService | grantDelegation | response | validFrom | string (date-time) |  | (nullable)
IdentityService | grantDelegation | response | validTo | string (date-time) |  | (nullable)
IdentityService | grantDelegation | response | createdByPrincipalId | string (uuid)
IdentityService | grantDelegation | response | createdAt | string (date-time)
IdentityService | grantDelegation | param (path) | subjectId | string (uuid) | yes
IdentityService | grantDelegation | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | guestLogout | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | guestLogout | param (query) | allDevices | boolean
IdentityService | guestPasswordLogin | request | identifier | string | yes | The email address or E.164 mobile number the account was registered with. (max length 256)
IdentityService | guestPasswordLogin | request | password | string | yes | (min length 8; max length 256)
IdentityService | guestPasswordLogin | request | deviceId | string |  | Names the device; a new sign-in here ends the previous session on it.
IdentityService | guestPasswordLogin | request | venueId | string (uuid) |  | The venue the guest app or booking is in. (nullable)
IdentityService | guestPasswordLogin | response | subjectId | string (uuid) | yes
IdentityService | guestPasswordLogin | response | displayName | string |  | (nullable)
IdentityService | guestPasswordLogin | response | tokens | TokenPair | yes
IdentityService | guestPasswordLogin | response | tokens.accessToken | string | yes | JWT carrying sid, validated per request against the session registry.
IdentityService | guestPasswordLogin | response | tokens.refreshToken | string | yes
IdentityService | guestPasswordLogin | response | tokens.expiresIn | integer | yes | Seconds
IdentityService | guestPasswordLogin | response | isVerified | boolean | yes | False until an OTP or a verified provider identity confirms ownership.
IdentityService | guestPasswordLogin | response | identityProviders | array of enum (password, otp, apple, google, uaePass) |  | Linked providers.
IdentityService | guestPasswordLogin | response | guestLinkId | string |  | Present where the guest is linked across cells (ADR-0010). (nullable)
IdentityService | guestPasswordLogin | response | requiresMfa | boolean |  | True only where the sign-in venue enabled guest two-step verification (VenueSettings.identity.guestTwoStep, in tenancy) and this guest has an active method (decided 29 September, rev 3 GAP-B1, per ve… (default False)
IdentityService | guestPasswordLogin | response | mfaMethods | array of MfaMethod |  | The guest's active methods, so the client can offer the right one.
IdentityService | guestPasswordLogin | response | mfaMethods[].id | string (uuid) | yes
IdentityService | guestPasswordLogin | response | mfaMethods[].kind | MfaKind: enum (totp, smsOtp, emailOtp, biometric, hardwareToken) | yes
IdentityService | guestPasswordLogin | response | mfaMethods[].label | string |  | (nullable)
IdentityService | guestPasswordLogin | response | mfaMethods[].maskedTarget | string |  | Partially masked destination, so a person can tell two methods apart. (nullable)
IdentityService | guestPasswordLogin | response | mfaMethods[].isActive | boolean | yes
IdentityService | guestPasswordLogin | response | mfaMethods[].isPrimary | boolean
IdentityService | guestPasswordLogin | response | mfaMethods[].enrolledAt | string (date-time) | yes
IdentityService | guestPasswordLogin | response | mfaMethods[].lastUsedAt | string (date-time) |  | (nullable)
IdentityService | guestPasswordLogin | response | homeCellName | string |  | (nullable)
IdentityService | guestPasswordLogin | response | preferredLanguage | string |  | (nullable)
IdentityService | guestPasswordLogin | response | expiresAt | string (date-time) | yes | 30 days, sliding (decided 28 September, audit R126 (2)): each use of the session moves this to 30 days from now, and 30 days unused ends it.
IdentityService | guestPasswordLogin | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | guestSocialLogin | request | provider | enum (apple, google) | yes
IdentityService | guestSocialLogin | request | idToken | string | yes
IdentityService | guestSocialLogin | request | deviceId | string
IdentityService | guestSocialLogin | request | venueId | string (uuid) |  | The venue the guest app or booking is in. (nullable)
IdentityService | guestSocialLogin | response | subjectId | string (uuid) | yes
IdentityService | guestSocialLogin | response | displayName | string |  | (nullable)
IdentityService | guestSocialLogin | response | tokens | TokenPair | yes
IdentityService | guestSocialLogin | response | tokens.accessToken | string | yes | JWT carrying sid, validated per request against the session registry.
IdentityService | guestSocialLogin | response | tokens.refreshToken | string | yes
IdentityService | guestSocialLogin | response | tokens.expiresIn | integer | yes | Seconds
IdentityService | guestSocialLogin | response | isVerified | boolean | yes | False until an OTP or a verified provider identity confirms ownership.
IdentityService | guestSocialLogin | response | identityProviders | array of enum (password, otp, apple, google, uaePass) |  | Linked providers.
IdentityService | guestSocialLogin | response | guestLinkId | string |  | Present where the guest is linked across cells (ADR-0010). (nullable)
IdentityService | guestSocialLogin | response | requiresMfa | boolean |  | True only where the sign-in venue enabled guest two-step verification (VenueSettings.identity.guestTwoStep, in tenancy) and this guest has an active method (decided 29 September, rev 3 GAP-B1, per ve… (default False)
IdentityService | guestSocialLogin | response | mfaMethods | array of MfaMethod |  | The guest's active methods, so the client can offer the right one.
IdentityService | guestSocialLogin | response | mfaMethods[].id | string (uuid) | yes
IdentityService | guestSocialLogin | response | mfaMethods[].kind | MfaKind: enum (totp, smsOtp, emailOtp, biometric, hardwareToken) | yes
IdentityService | guestSocialLogin | response | mfaMethods[].label | string |  | (nullable)
IdentityService | guestSocialLogin | response | mfaMethods[].maskedTarget | string |  | Partially masked destination, so a person can tell two methods apart. (nullable)
IdentityService | guestSocialLogin | response | mfaMethods[].isActive | boolean | yes
IdentityService | guestSocialLogin | response | mfaMethods[].isPrimary | boolean
IdentityService | guestSocialLogin | response | mfaMethods[].enrolledAt | string (date-time) | yes
IdentityService | guestSocialLogin | response | mfaMethods[].lastUsedAt | string (date-time) |  | (nullable)
IdentityService | guestSocialLogin | response | homeCellName | string |  | (nullable)
IdentityService | guestSocialLogin | response | preferredLanguage | string |  | (nullable)
IdentityService | guestSocialLogin | response | expiresAt | string (date-time) | yes | 30 days, sliding (decided 28 September, audit R126 (2)): each use of the session moves this to 30 days from now, and 30 days unused ends it.
IdentityService | guestSocialLogin | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | guestUaePassLogin | request | code | string | yes
IdentityService | guestUaePassLogin | request | redirectUri | string | yes
IdentityService | guestUaePassLogin | request | state | string
IdentityService | guestUaePassLogin | request | deviceId | string
IdentityService | guestUaePassLogin | request | venueId | string (uuid) |  | The venue the guest app or booking is in. (nullable)
IdentityService | guestUaePassLogin | response | subjectId | string (uuid) | yes
IdentityService | guestUaePassLogin | response | displayName | string |  | (nullable)
IdentityService | guestUaePassLogin | response | tokens | TokenPair | yes
IdentityService | guestUaePassLogin | response | tokens.accessToken | string | yes | JWT carrying sid, validated per request against the session registry.
IdentityService | guestUaePassLogin | response | tokens.refreshToken | string | yes
IdentityService | guestUaePassLogin | response | tokens.expiresIn | integer | yes | Seconds
IdentityService | guestUaePassLogin | response | isVerified | boolean | yes | False until an OTP or a verified provider identity confirms ownership.
IdentityService | guestUaePassLogin | response | identityProviders | array of enum (password, otp, apple, google, uaePass) |  | Linked providers.
IdentityService | guestUaePassLogin | response | guestLinkId | string |  | Present where the guest is linked across cells (ADR-0010). (nullable)
IdentityService | guestUaePassLogin | response | requiresMfa | boolean |  | True only where the sign-in venue enabled guest two-step verification (VenueSettings.identity.guestTwoStep, in tenancy) and this guest has an active method (decided 29 September, rev 3 GAP-B1, per ve… (default False)
IdentityService | guestUaePassLogin | response | mfaMethods | array of MfaMethod |  | The guest's active methods, so the client can offer the right one.
IdentityService | guestUaePassLogin | response | mfaMethods[].id | string (uuid) | yes
IdentityService | guestUaePassLogin | response | mfaMethods[].kind | MfaKind: enum (totp, smsOtp, emailOtp, biometric, hardwareToken) | yes
IdentityService | guestUaePassLogin | response | mfaMethods[].label | string |  | (nullable)
IdentityService | guestUaePassLogin | response | mfaMethods[].maskedTarget | string |  | Partially masked destination, so a person can tell two methods apart. (nullable)
IdentityService | guestUaePassLogin | response | mfaMethods[].isActive | boolean | yes
IdentityService | guestUaePassLogin | response | mfaMethods[].isPrimary | boolean
IdentityService | guestUaePassLogin | response | mfaMethods[].enrolledAt | string (date-time) | yes
IdentityService | guestUaePassLogin | response | mfaMethods[].lastUsedAt | string (date-time) |  | (nullable)
IdentityService | guestUaePassLogin | response | homeCellName | string |  | (nullable)
IdentityService | guestUaePassLogin | response | preferredLanguage | string |  | (nullable)
IdentityService | guestUaePassLogin | response | expiresAt | string (date-time) | yes | 30 days, sliding (decided 28 September, audit R126 (2)): each use of the session moves this to 30 days from now, and 30 days unused ends it.
IdentityService | guestUaePassLogin | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | handoverToAgent | request | reason | enum (guestRequested, assistantRefused, assistantFailed, outOfScope, negativeSentiment, complexIntent, paymentIssue) | yes
MarketingService | handoverToAgent | request | summary | string |  | The assistant's own summary of what the guest wants, so the agent opens with context rather than reading a transcript while somebody waits.
MarketingService | handoverToAgent | request | preferredQueueId | string (uuid)
MarketingService | handoverToAgent | response | id | string (uuid) | yes
MarketingService | handoverToAgent | response | telephony | object |  | BL-083. (nullable)
MarketingService | handoverToAgent | response | telephony.providerCallId | string
MarketingService | handoverToAgent | response | telephony.direction | enum (inbound, outbound, transferred)
MarketingService | handoverToAgent | response | telephony.fromNumberMasked | string |  | Masked, and it is still personal data. (nullable)
MarketingService | handoverToAgent | response | telephony.recordingRef | string |  | Held by the provider, referenced here. (nullable)
MarketingService | handoverToAgent | response | telephony.agentState | enum (available, onCall, wrapUp, away, offline) |  | (nullable)
MarketingService | handoverToAgent | response | assistSessionId | string (uuid) |  | BL-094. (nullable)
MarketingService | handoverToAgent | response | channel | ConversationChannel: enum (webChat, inAppChat, whatsapp, sms, email, kiosk, voice) | yes
MarketingService | handoverToAgent | response | state | ConversationState: enum (withAssistant, queued, withAgent, waitingOnGuest, resolved, abandoned, timedOut) | yes | withAssistant and queued are different, and the second has a person waiting.
MarketingService | handoverToAgent | response | subjectId | string (uuid) |  | 22.8.3. (nullable)
MarketingService | handoverToAgent | response | venueId | string (uuid) |  | (nullable)
MarketingService | handoverToAgent | response | assignedPrincipalId | string (uuid) |  | (nullable)
MarketingService | handoverToAgent | response | queueId | string (uuid) |  | (nullable)
MarketingService | handoverToAgent | response | queuePosition | integer |  | Place among the unclaimed conversations in queueId, from the live agent queue (audit R149). (read-only; nullable)
MarketingService | handoverToAgent | response | estimatedWaitSeconds | integer |  | From the live agent queue — the conversations ahead divided across that queue's agents online now (audit R149). (read-only; nullable)
MarketingService | handoverToAgent | response | handoverReason | enum (guestRequested, assistantRefused, assistantFailed, outOfScope, negativeSentiment, complexIntent, paymentIssue) |  | (nullable)
MarketingService | handoverToAgent | response | handoverSummary | string |  | The assistant's own account of what the guest wants, so an agent opens with context rather than reading a transcript while somebody waits. (nullable)
MarketingService | handoverToAgent | response | sentiment | enum (positive, neutral, negative, escalating) |  | 22.8.16. (nullable)
MarketingService | handoverToAgent | response | intent | string |  | 22.8.13. (nullable)
MarketingService | handoverToAgent | response | locale | string
MarketingService | handoverToAgent | response | caseId | string (uuid) |  | 22.8.12. (nullable)
MarketingService | handoverToAgent | response | messages | array of ConversationMessage
MarketingService | handoverToAgent | response | messages[].id | string (uuid) | yes
MarketingService | handoverToAgent | response | messages[].sender | enum (guest, agent, assistant, system) | yes | Resolved, never declared.
MarketingService | handoverToAgent | response | messages[].senderPrincipalId | string (uuid) |  | (nullable)
MarketingService | handoverToAgent | response | messages[].body | string | yes
MarketingService | handoverToAgent | response | messages[].attachments | array of object
MarketingService | handoverToAgent | response | messages[].attachments[].assetId | string (uuid)
MarketingService | handoverToAgent | response | messages[].attachments[].kind | enum (image, video, document, ticket, qr, paymentLink)
MarketingService | handoverToAgent | response | messages[].aiInteractionId | string (uuid) |  | Where the assistant sent it. (nullable)
MarketingService | handoverToAgent | response | messages[].sentAt | string (date-time) | yes
MarketingService | handoverToAgent | response | messages[].readAt | string (date-time) |  | (nullable)
MarketingService | handoverToAgent | response | firstResponseSeconds | integer |  | (read-only; nullable)
MarketingService | handoverToAgent | response | startedAt | string (date-time)
MarketingService | handoverToAgent | response | closedAt | string (date-time) |  | (nullable)
MarketingService | handoverToAgent | response | outcome | enum (resolved, caseRaised, abandonedByGuest, timedOut, spam) |  | (nullable)
MarketingService | handoverToAgent | param (path) | conversationId | string (uuid) | yes
MarketingService | handoverToAgent | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | holdCourse | request | recordedAt | string (date-time) | yes | Device time of the act (offline-capable; replayed in this order).
FnbService | holdCourse | request | course | integer | yes | (min 1)
FnbService | holdCourse | request | reason | enum (tableNotReady, guestRequest, kitchenBackedUp, awaitingPrevious, other) |  | other is allowed only with a note, which it then requires (decided 28 September, audit R222).
FnbService | holdCourse | request | note | string |  | Free text. (max length 500; nullable)
FnbService | holdCourse | response | id | string (uuid) | yes
FnbService | holdCourse | response | orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | holdCourse | response | orderNumber | string
FnbService | holdCourse | response | outletId | string (uuid) | yes
FnbService | holdCourse | response | tableLabel | string |  | (nullable)
FnbService | holdCourse | response | serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | holdCourse | response | coursing | object |  | BL-131. (nullable)
FnbService | holdCourse | response | buzzerCode | string |  | BL-128. (nullable)
FnbService | holdCourse | response | status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | holdCourse | response | priority | integer |  | Higher fires sooner.
FnbService | holdCourse | response | prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | holdCourse | response | prioritiseReason | string |  | (nullable)
FnbService | holdCourse | response | lines | array of object | yes
FnbService | holdCourse | response | lines[].lineId | string (uuid) | yes
FnbService | holdCourse | response | lines[].name | string | yes
FnbService | holdCourse | response | lines[].quantity | integer | yes
FnbService | holdCourse | response | lines[].modifiers | array of string
FnbService | holdCourse | response | lines[].note | string |  | (nullable)
FnbService | holdCourse | response | lines[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | holdCourse | response | lines[].refireOfLineId | string (uuid) |  | Set on a refire. (read-only; nullable)
FnbService | holdCourse | response | lines[].refireReason | object |  | (read-only; nullable)
FnbService | holdCourse | response | lines[].isChargeable | boolean |  | A refire's chargeable flag. (read-only; nullable)
FnbService | holdCourse | response | lines[].course | integer |  | (nullable)
FnbService | holdCourse | response | lines[].stationId | string (uuid) |  | (nullable)
FnbService | holdCourse | response | lines[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | holdCourse | response | createdAt | string (date-time) | yes
FnbService | holdCourse | response | targetReadyAt | string (date-time) |  | (nullable)
FnbService | holdCourse | response | elapsedSeconds | integer
FnbService | holdCourse | response | visitId | string (uuid) |  | The table visit the ticket is for (4 October 2026, CHG-FXC-011; KIT-002): the {visitId} notifyServer takes. (read-only; nullable)
FnbService | holdCourse | param (path) | ticketId | string (uuid) | yes
FnbService | holdCourse | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | holdOrder | request | label | string |  | How the cashier will find it again — a name, a description, a party size. (max length 60)
OrderService | holdOrder | request | holdUntil | string (date-time)
OrderService | holdOrder | request | recordedAt | string (date-time) | yes
OrderService | holdOrder | response | id | string (uuid) | yes | The client UUIDv7 from CreateOrderRequest.id.
OrderService | holdOrder | response | orderNumber | string |  | The number a guest reads and a cashier types. (read-only)
OrderService | holdOrder | response | channel | object | yes | Where it came from.
OrderService | holdOrder | response | channelProfileId | string (uuid) |  | The named sales channel the order came through (catalogue SalesChannelProfile.id), set by the server from the caller: a partner user's or reseller's channel, an API key's channel. (read-only; nullable)
OrderService | holdOrder | response | venueId | string (uuid) | yes
OrderService | holdOrder | response | scopePath | string | yes
OrderService | holdOrder | response | status | OrderStatus: enum (pending, held, paid, partiallyPaid, completed, voided, refunded, partiallyRefunded, …) | yes | held is a parked sale — the cashier freed the till and the guest will return.
OrderService | holdOrder | response | currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | holdOrder | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | holdOrder | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | holdOrder | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | holdOrder | response | netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | refundedAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | holdOrder | response | refundedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | refundedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | refundedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | chargeCurrency | string |  | The currency the guest selected and is charged in (CHG-FIN-001, 2 October 2026). (pattern ^[A-Z]{3}$; read-only; nullable)
OrderService | holdOrder | response | chargeFxRate | object |  | Units of chargeCurrency per one unit of the base currency, from the region's tender rate in force at checkout (finance.FxRate), stored on the order so the payment, the receipt, the tax invoice and an… (read-only; nullable)
OrderService | holdOrder | response | chargeFxRateId | string (uuid) |  | The finance.FxRate row the rate was taken from, for audit. (read-only; nullable)
OrderService | holdOrder | response | chargeTotal | object |  | grossAmount converted at chargeFxRate and rounded to the charge currency's scale: what the guest pays and what the payment request to the provider asks for (CHG-FIN-001). (read-only)
OrderService | holdOrder | response | chargeTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | chargeTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | chargeTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | chargeRateLockedUntil | string (date-time) |  | The quote holds until then (the cart lease). (read-only; nullable)
OrderService | holdOrder | response | droppedPromotions | array of object |  | Promotions left off this order at checkout because their budget cap would have been exceeded (decided 28 September, audit R101 (8)). (read-only)
OrderService | holdOrder | response | droppedPromotions[].promotionId | string (uuid) | yes
OrderService | holdOrder | response | droppedPromotions[].name | string
OrderService | holdOrder | response | droppedPromotions[].reason | enum (budgetCapReached)
OrderService | holdOrder | response | totalPriceVariance | object |  | Sum across lines.
OrderService | holdOrder | response | totalPriceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | totalPriceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | totalPriceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | lines | array of OrderLine | yes
OrderService | holdOrder | response | lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | holdOrder | response | lines[].variantId | string (uuid) | yes
OrderService | holdOrder | response | lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | holdOrder | response | lines[].performanceId | string (uuid)
OrderService | holdOrder | response | lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | holdOrder | response | lines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | holdOrder | response | lines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | holdOrder | response | lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | holdOrder | response | lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | holdOrder | response | lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | holdOrder | response | lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | holdOrder | response | lines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | holdOrder | response | lines[].quantity | integer | yes | (min 1)
OrderService | holdOrder | response | lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | holdOrder | response | lines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | holdOrder | response | lines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | holdOrder | response | lines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | holdOrder | response | lines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | holdOrder | response | lines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | holdOrder | response | lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | holdOrder | response | lines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | lines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | lines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | lines[].holderName | string |  | (nullable)
OrderService | holdOrder | response | lines[].dataMaskValues | object |  | Deliberately open.
OrderService | holdOrder | response | lines[].serverUnitPrice | object | yes | What the server computed on ingest.
OrderService | holdOrder | response | lines[].serverUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | lines[].serverUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | lines[].serverUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | lines[].priceVariance | object |  | Server minus quoted.
OrderService | holdOrder | response | lines[].priceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | lines[].priceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | lines[].priceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | holdOrder | response | lines[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | lines[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | lines[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | holdOrder | response | lines[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | lines[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | lines[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | holdOrder | response | lines[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | lines[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | lines[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | lines[].entitlementIds | array of string (uuid) |  | The entitlements this line issued.
OrderService | holdOrder | response | lines[].crossRegionRightIds | array of string |  | Redemption rights propagated to other cells for this line.
OrderService | holdOrder | response | lines[].reprintCount | integer |  | How many times this line's tickets were reprinted or resent. (min 0; default 0; read-only)
OrderService | holdOrder | response | lines[].venueId | string (uuid) |  | The order's venue, copied onto the line (ADR-0044's own example; system-design review SD-008, 29 September) so a line is scoped and partitionable without its order. (read-only)
OrderService | holdOrder | response | lines[].discounts | array of OrderLineDiscount |  | The discounts applied to this line, one row each (system-design review SD-008, 29 September). (read-only)
OrderService | holdOrder | response | lines[].discounts[].id | string (uuid) | yes
OrderService | holdOrder | response | lines[].discounts[].promotionId | string (uuid) |  | The promotion that gave it. (nullable)
OrderService | holdOrder | response | lines[].discounts[].source | enum (promotion, promoCode, manual, bundle, member) | yes
OrderService | holdOrder | response | lines[].discounts[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | holdOrder | response | lines[].discounts[].reason | string |  | A cashier's reason for a manual discount. (max length 200; nullable)
OrderService | holdOrder | response | payments | array of Payment
OrderService | holdOrder | response | payments[].id | string (uuid) | yes
OrderService | holdOrder | response | payments[].orderId | string (uuid) | yes
OrderService | holdOrder | response | payments[].tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | holdOrder | response | payments[].tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | payments[].tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale.
OrderService | holdOrder | response | payments[].tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | payments[].tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | payments[].tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | payments[].fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | holdOrder | response | payments[].fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | holdOrder | response | payments[].changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | holdOrder | response | payments[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | holdOrder | response | payments[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | payments[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | payments[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | payments[].changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | holdOrder | response | payments[].changeAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | holdOrder | response | payments[].changeAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | holdOrder | response | payments[].changeAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | holdOrder | response | payments[].status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | holdOrder | response | payments[].providerName | string |  | (nullable)
OrderService | holdOrder | response | payments[].providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | holdOrder | response | payments[].providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | holdOrder | response | payments[].terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | holdOrder | response | payments[].nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | holdOrder | response | payments[].nextAction.kind | enum (redirect, terminal)
OrderService | holdOrder | response | payments[].nextAction.url | string (uri) |  | (nullable)
OrderService | holdOrder | response | payments[].nextAction.expiresAt | string (date-time) |  | (nullable)
OrderService | holdOrder | response | payments[].lastInquiryAt | string (date-time) |  | (nullable)
OrderService | holdOrder | response | payments[].recordedAt | string (date-time) | yes
OrderService | holdOrder | response | payments[].syncedAt | string (date-time) |  | (nullable)
OrderService | holdOrder | response | principalId | string (uuid)
OrderService | holdOrder | response | workstationId | string (uuid)
OrderService | holdOrder | response | shiftId | string (uuid) |  | (nullable)
OrderService | holdOrder | response | subjectId | string (uuid) |  | (nullable)
OrderService | holdOrder | response | holdLabel | string |  | The label a cashier gave when parking it with holdOrder — how they find it again. (max length 60; read-only; nullable)
OrderService | holdOrder | response | heldUntil | string (date-time) |  | When a held order expires and is voided (states/order.yaml), from holdOrder's holdUntil. (read-only; nullable)
OrderService | holdOrder | response | createdAt | string (date-time) | yes
OrderService | holdOrder | response | recordedAt | string (date-time) | yes
OrderService | holdOrder | response | syncedAt | string (date-time) |  | (nullable)
OrderService | holdOrder | param (path) | orderId | string (uuid) | yes
OrderService | holdOrder | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | identifyGuest | request | token | string | yes
MarketingService | identifyGuest | request | tokenKind | enum (qr, rfid, nfc, membershipCard, walletPass, phone, email, appDeviceId, …) |  | Optional. (nullable)
MarketingService | identifyGuest | response | subjectId | string (uuid) | yes
MarketingService | identifyGuest | response | displayName | string
MarketingService | identifyGuest | response | matchedOn | enum (qr, rfid, nfc, membershipCard, walletPass, phone, email, appDeviceId, …) | yes | Which identifier resolved.
MarketingService | identifyGuest | response | confidence | enum (exact, probable) |  | probable where the match was on a shared identifier.
MarketingService | identifyGuest | response | entitlements | array of object |  | Live entitlements, so a gate or a till does not make a second call.
MarketingService | identifyGuest | response | entitlements[].entitlementId | string (uuid)
MarketingService | identifyGuest | response | entitlements[].productName | string
MarketingService | identifyGuest | response | entitlements[].status | EntitlementStatus: enum (issued, partiallyConsumed, fullyConsumed, expired, cancelled, surrendered) |  | What the storage layer holds, and what a guest is shown.
MarketingService | identifyGuest | response | entitlements[].validTo | string (date)
MarketingService | identifyGuest | response | loyalty | LoyaltyPosition
MarketingService | identifyGuest | response | loyalty.leaderboardNickname | string |  | BL-173. (max length 24; nullable)
MarketingService | identifyGuest | response | loyalty.subjectId | string (uuid) | yes
MarketingService | identifyGuest | response | loyalty.programmeId | string (uuid) | yes
MarketingService | identifyGuest | response | loyalty.pointsBalance | integer | yes
MarketingService | identifyGuest | response | loyalty.lifetimePoints | integer
MarketingService | identifyGuest | response | loyalty.tierId | string (uuid) |  | The tier this row's tierCode and tierName are a copy of. (nullable)
MarketingService | identifyGuest | response | loyalty.tierCode | string | yes
MarketingService | identifyGuest | response | loyalty.tierName | string
MarketingService | identifyGuest | response | loyalty.pointsToNextTier | integer |  | (nullable)
MarketingService | identifyGuest | response | loyalty.nextExpiryPoints | integer |  | (nullable)
MarketingService | identifyGuest | response | loyalty.nextExpiryAt | string (date-time) |  | (nullable)
MarketingService | identifyGuest | response | isBarred | boolean |  | BL-134.
MarketingService | identifyGuest | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | importTicketTemplate | request | format | string | yes | The definition format of the file. (max length 30)
OrderService | importTicketTemplate | request | fileRef | string (uuid) | yes | The uploaded definition file.
OrderService | importTicketTemplate | request | name | string | yes | (max length 120)
OrderService | importTicketTemplate | response | id | string (uuid) | yes
OrderService | importTicketTemplate | response | name | string | yes
OrderService | importTicketTemplate | response | isRecyclable | boolean |  | BL-103. (default False)
OrderService | importTicketTemplate | response | recycleAfterDays | integer |  | A quarantine before reissue. (nullable)
OrderService | importTicketTemplate | response | mediaType | enum (thermalTicket, a4Pdf, wristband, rfidCard, walletPass, qrOnly, sms) | yes
OrderService | importTicketTemplate | response | appliesToProductKinds | array of string
OrderService | importTicketTemplate | response | appliesToChannels | array of SalesChannel: enum (pos, kiosk, guestApp, guestWeb, callCentre, partner, api, backOffice, …)
OrderService | importTicketTemplate | response | selectionPriority | integer |  | 2.16.x. (default 100)
OrderService | importTicketTemplate | response | layoutRef | string
OrderService | importTicketTemplate | response | localeVariants | object
OrderService | importTicketTemplate | response | isActive | boolean | yes
OrderService | importTicketTemplate | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | importTransportNetwork | request | format | enum (csvBundle, gtfs) | yes | A zip of the four CSV files described on importTransportNetwork, or a GTFS static feed.
VenueOpsService | importTransportNetwork | request | sourceRef | string (uuid) | yes | The uploaded file, as the MediaAsset.id from assets.completeUpload.
VenueOpsService | importTransportNetwork | request | include | array of enum (stations, routes, timetables) |  | Which parts of the file to read.
VenueOpsService | importTransportNetwork | response | id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | importTransportNetwork | response | venueId | string (uuid) | yes | (read-only)
VenueOpsService | importTransportNetwork | response | format | enum (csvBundle, gtfs) | yes
VenueOpsService | importTransportNetwork | response | sourceRef | string (uuid) | yes
VenueOpsService | importTransportNetwork | response | status | TransportNetworkImportStatus: enum (validating, previewReady, failed, applied, expired) | yes | validating → previewReady or failed; previewReady → applied, or expired after 7 days unapplied (proposed, client to correct).
VenueOpsService | importTransportNetwork | response | preview | object |  | What applying would write. (read-only; nullable)
VenueOpsService | importTransportNetwork | response | preview.stationsToCreate | integer |  | (min 0)
VenueOpsService | importTransportNetwork | response | preview.stationsToUpdate | integer |  | (min 0)
VenueOpsService | importTransportNetwork | response | preview.routesToCreate | integer |  | (min 0)
VenueOpsService | importTransportNetwork | response | preview.routesToUpdate | integer |  | (min 0)
VenueOpsService | importTransportNetwork | response | preview.stopsToWrite | integer |  | (min 0)
VenueOpsService | importTransportNetwork | response | preview.timetablesToCreate | integer |  | (min 0)
VenueOpsService | importTransportNetwork | response | findings | array of TransportNetworkImportFinding |  | (max items 1000; read-only)
VenueOpsService | importTransportNetwork | response | findings[].code | enum (nothingFound, fileMissing, headerMismatch, stationCodeDuplicate, stationCoordinatesMissing, routeCodeDuplicate, routeStopUnknownStation, routeOffsetsNotIncreasing, …) | yes | stationCoordinatesMissing is a warning (the station is listed and left off the map); routeActiveStopsChanged is a warning (those stops are skipped); every other code is an error and blocks the apply.
VenueOpsService | importTransportNetwork | response | findings[].severity | enum (error, warning) | yes
VenueOpsService | importTransportNetwork | response | findings[].file | string |  | e.g. (nullable)
VenueOpsService | importTransportNetwork | response | findings[].row | integer |  | (min 1; nullable)
VenueOpsService | importTransportNetwork | response | findings[].reference | string |  | The station (nullable)
VenueOpsService | importTransportNetwork | response | findings[].message | string | yes | (max length 500)
VenueOpsService | importTransportNetwork | response | createdBy | string (uuid) |  | (read-only)
VenueOpsService | importTransportNetwork | response | createdAt | string (date-time) |  | (read-only)
VenueOpsService | importTransportNetwork | response | appliedBy | string (uuid) |  | (read-only; nullable)
VenueOpsService | importTransportNetwork | response | appliedAt | string (date-time) |  | (read-only; nullable)
VenueOpsService | importTransportNetwork | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | importVenueGeometry | request | format | enum (pdfPlan, svgPlan, dwgPlan, dxfPlan, rasterPlan, glbModel, navigationFile) | yes | glbModel and navigationFile added 3 October 2026 (r1 additions, ADR-0069): a GLB with its navigation file, or the navigation file alone.
VenueOpsService | importVenueGeometry | request | sourceRef | string (uuid) | yes | The drawing, as the MediaAsset.id from assets.completeUpload.
VenueOpsService | importVenueGeometry | request | navigationFileRef | string (uuid) |  | The navigation (pathway) file that goes with a GLB (ADR-0069 section 2; the VenueNavigationFile schema), uploaded like sourceRef as JSON. (nullable)
VenueOpsService | importVenueGeometry | request | ocr | object |  | The OCR step (3 October 2026, r1 additions); VenueMapOcrOptions. (nullable)
VenueOpsService | importVenueGeometry | request | ocr.mode | enum (auto, off) |  | off skips it, for a plan whose text is noise (a dimensioned drawing). (default auto)
VenueOpsService | importVenueGeometry | request | ocr.languages | array of enum (en, ar) |  | The scripts to read.
VenueOpsService | importVenueGeometry | request | handMarkedPaths | object |  | A raster plan with hand-marked paths (3 October 2026, r1 additions); VenueMapHandMarkedPaths. (nullable)
VenueOpsService | importVenueGeometry | request | handMarkedPaths.markColour | string |  | The marker's colour, where the operator knows it (#E53935 for a red pen). (pattern ^#[0-9A-Fa-f]{6}$; nullable)
VenueOpsService | importVenueGeometry | request | handMarkedPaths.note | string |  | Anything the marks mean that the image does not say ("dashed = staff only"). (max length 300; nullable)
VenueOpsService | importVenueGeometry | request | layerMapping | object |  | Each role takes a list.
VenueOpsService | importVenueGeometry | request | layerMapping.buildingLayer | array of string
VenueOpsService | importVenueGeometry | request | layerMapping.pathLayer | array of string |  | Optional, and the platform derives paths without it.
VenueOpsService | importVenueGeometry | request | layerMapping.zoneLayer | array of string
VenueOpsService | importVenueGeometry | request | layerMapping.labelLayer | array of string
VenueOpsService | importVenueGeometry | request | layerMapping.boundaryLayer | array of string
VenueOpsService | importVenueGeometry | request | layerMapping.exitLayer | array of string
VenueOpsService | importVenueGeometry | request | layerMapping.emergencyExitLayer | array of string |  | Separate from exitLayer, and drawings usually blur them.
VenueOpsService | importVenueGeometry | request | layerMapping.poiLayers | object |  | Where a drawing already marks toilets, first aid and the rest.
VenueOpsService | importVenueGeometry | request | layerMapping.resourceLayer | array of string |  | The bookable resources drawn on the plan — cabanas, loungers, tables (decided 29 September, rev 3 REV3-15).
VenueOpsService | importVenueGeometry | request | layerMapping.keepOutLayer | array of string |  | Water, planting, back-of-house, plant rooms.
VenueOpsService | importVenueGeometry | request | digitNormalisation | boolean |  | A١ and A1 are one section to a person and two to a computer, and the failure is silent — the seats simply do not join, and you get geometry with no seats or seats with no geometry. (default True)
VenueOpsService | importVenueGeometry | request | georeference | object |  | 19.2.56. (nullable)
VenueOpsService | importVenueGeometry | request | georeference.originLat | number
VenueOpsService | importVenueGeometry | request | georeference.originLng | number
VenueOpsService | importVenueGeometry | request | georeference.scaleMetresPerUnit | number
VenueOpsService | importVenueGeometry | request | georeference.rotationDegrees | number |  | (default 0)
VenueOpsService | importVenueGeometry | request | georeference.anchors | array of object |  | Two points far apart. (min items 2; max items 4)
VenueOpsService | importVenueGeometry | request | georeference.anchors[].label | string
VenueOpsService | importVenueGeometry | request | georeference.anchors[].planX | number
VenueOpsService | importVenueGeometry | request | georeference.anchors[].planY | number
VenueOpsService | importVenueGeometry | request | georeference.anchors[].lat | number
VenueOpsService | importVenueGeometry | request | georeference.anchors[].lng | number
VenueOpsService | importVenueGeometry | request | manifestRef | string (uuid) |  | The seating manifest, where this map has seats, as the MediaAsset.id from assets.completeUpload, uploaded the same way as sourceRef. (nullable)
VenueOpsService | importVenueGeometry | request | resourceManifestRef | string (uuid) |  | The resource manifest, where this map carries bookable resources (decided 29 September, rev 3 REV3-15), uploaded like manifestRef. (nullable)
VenueOpsService | importVenueGeometry | request | priceBands | array of object |  | What each price band sells as, so a placed resource can be bought: the band code the manifest uses and the catalogue.ProductVariant that prices it (Family 6, Medium 10, Large 15, XL 20 on the Coastal… (nullable)
VenueOpsService | importVenueGeometry | request | priceBands[].code | string | yes | (max length 40)
VenueOpsService | importVenueGeometry | request | priceBands[].name | string |  | (nullable)
VenueOpsService | importVenueGeometry | request | priceBands[].variantId | string (uuid) | yes
VenueOpsService | importVenueGeometry | request | createMissingResources | boolean |  | Where a manifest label has no resources.Resource with that code at this venue, create one through resources.createResource (kind, capacity and zone as attributes) instead of reporting resourceCodeUnm… (default False)
VenueOpsService | importVenueGeometry | response | id | string (uuid) | yes
VenueOpsService | importVenueGeometry | response | mapId | string (uuid)
VenueOpsService | importVenueGeometry | response | status | enum (parsing, previewReady, committed, failed) | yes
VenueOpsService | importVenueGeometry | response | outcome | enum (parsed, parsedWithFindings, nothingFound, noLayersMatched, unreadable) | yes
VenueOpsService | importVenueGeometry | response | shapesFound | integer
VenueOpsService | importVenueGeometry | response | layersFound | array of string |  | Every layer name in the source, decoded.
VenueOpsService | importVenueGeometry | response | unmappedLayers | array of string
VenueOpsService | importVenueGeometry | response | manifestRowsRead | integer |  | (nullable)
VenueOpsService | importVenueGeometry | response | resourcesFound | integer |  | Bookable resource shapes found on the resource layer (rev 3 REV3-15). (nullable)
VenueOpsService | importVenueGeometry | response | resourceRowsJoined | integer |  | Resource manifest rows that joined a shape and a resources.Resource. (nullable)
VenueOpsService | importVenueGeometry | response | manifestRowsJoined | integer |  | The number to check against your own count. (nullable)
VenueOpsService | importVenueGeometry | response | findings | array of object |  | Named against the spec, so a finding maps to a section of handoff/venue-map-input-spec.md rather than to a stack trace.
VenueOpsService | importVenueGeometry | response | findings[].code | enum (duplicateLayerName, geometryOnLayerZero, unmappedLayer, mixedLayerContent, sectionCodeMismatch, digitScriptMismatch, mergedCells, totalRowDetected, …) | yes | A closed set, and each one names a rule in the spec.
VenueOpsService | importVenueGeometry | response | findings[].severity | enum (error, warning, info) | yes | warning is the important level here.
VenueOpsService | importVenueGeometry | response | findings[].message | string | yes
VenueOpsService | importVenueGeometry | response | findings[].specSection | string |  | Which part of the spec covers it — §2 Layers, §4 Digits. (nullable)
VenueOpsService | importVenueGeometry | response | findings[].affected | array of string |  | The layers, sections or rows involved.
VenueOpsService | importVenueGeometry | response | ocr | object |  | What the OCR step read off a scanned PDF or a raster (3 October 2026, r1 additions). (nullable)
VenueOpsService | importVenueGeometry | response | ocr.pagesRead | integer
VenueOpsService | importVenueGeometry | response | ocr.meanConfidence | number |  | (min 0; max 1; nullable)
VenueOpsService | importVenueGeometry | response | ocr.textBlocks | array of object
VenueOpsService | importVenueGeometry | response | ocr.textBlocks[].text | string | yes | (max length 500)
VenueOpsService | importVenueGeometry | response | ocr.textBlocks[].language | enum (en, ar) |  | (nullable)
VenueOpsService | importVenueGeometry | response | ocr.textBlocks[].confidence | number | yes | (min 0; max 1)
VenueOpsService | importVenueGeometry | response | ocr.textBlocks[].planX | number |  | (nullable)
VenueOpsService | importVenueGeometry | response | ocr.textBlocks[].planY | number |  | (nullable)
VenueOpsService | importVenueGeometry | response | ocr.textBlocks[].widthUnits | number |  | (nullable)
VenueOpsService | importVenueGeometry | response | ocr.textBlocks[].heightUnits | number |  | (nullable)
VenueOpsService | importVenueGeometry | response | handMarkedPaths | object |  | The hand-marked strokes the import found on a raster plan sent with handMarkedPaths (3 October 2026, r1 additions). (nullable)
VenueOpsService | importVenueGeometry | response | handMarkedPaths.strokesFound | integer
VenueOpsService | importVenueGeometry | response | handMarkedPaths.markColourUsed | string |  | The colour the import matched. (nullable)
VenueOpsService | importVenueGeometry | response | handMarkedPaths.totalLengthUnits | number |  | In drawing units. (nullable)
VenueOpsService | importVenueGeometry | response | model | object |  | The GLB and navigation file, measured (glbModel and navigationFile imports; ADR-0069 sections 1, 2, 3 and 6; 3 October 2026). (nullable)
VenueOpsService | importVenueGeometry | response | model.sizeBytes | integer |  | The GLB. (nullable)
VenueOpsService | importVenueGeometry | response | model.lod0TrianglesMaxZone | integer |  | The most LOD0 triangles any one zone carries, which is what is on screen near the camera. (nullable)
VenueOpsService | importVenueGeometry | response | model.trianglesTotal | integer |  | Across every zone and LOD. (nullable)
VenueOpsService | importVenueGeometry | response | model.drawCalls | integer |  | Over 150 is a warning. (nullable)
VenueOpsService | importVenueGeometry | response | model.textureMemoryBytes | integer |  | After KTX2 transcoding. (nullable)
VenueOpsService | importVenueGeometry | response | model.maxTexturePx | integer |  | Over 2048 is a warning. (nullable)
VenueOpsService | importVenueGeometry | response | model.zones | integer |  | (nullable)
VenueOpsService | importVenueGeometry | response | model.nodes | integer
VenueOpsService | importVenueGeometry | response | model.edges | integer
VenueOpsService | importVenueGeometry | response | model.locations | integer
VenueOpsService | importVenueGeometry | response | model.anchorResidualMaxMetres | number |  | The worst control point. (nullable)
VenueOpsService | importVenueGeometry | response | model.publishable3d | boolean |  | True when no finding below is an error: the next publish carries the 3D layer.
VenueOpsService | importVenueGeometry | response | model.findings | array of object
VenueOpsService | importVenueGeometry | response | model.findings[].code | enum (modelOverDownloadBudget, zoneOverDownloadBudget, triangleBudgetExceeded, triangleTotalExceeded, drawCallBudgetExceeded, textureBudgetExceeded, textureTooLarge, uncompressedTextures, …) | yes | A closed set, separate from findings so the plan importer's codes stay as they were.
VenueOpsService | importVenueGeometry | response | model.findings[].severity | enum (error, warning, info) | yes
VenueOpsService | importVenueGeometry | response | model.findings[].message | string | yes
VenueOpsService | importVenueGeometry | response | model.findings[].measured | number |  | The number found. (nullable)
VenueOpsService | importVenueGeometry | response | model.findings[].limit | number |  | The budget it was measured against. (nullable)
VenueOpsService | importVenueGeometry | response | model.findings[].affected | array of string |  | The zones, nodes, locations or codes involved.
VenueOpsService | importVenueGeometry | param (path) | mapId | string (uuid) | yes
VenueOpsService | importVenueGeometry | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | importVenueHistory | request | dataKind | enum (attendance, admissions, ticketSales, fnbSales, retailSales, queueReadings, staffShifts) | yes
AiService | importVenueHistory | request | assetId | string (uuid) | yes | The uploaded export, in the asset library.
AiService | importVenueHistory | request | sourceSystem | string |  | What produced the file, e.g. (nullable)
AiService | importVenueHistory | request | columnMapping | object | yes | Target field to source column, e.g.
AiService | importVenueHistory | request | dryRun | boolean |  | Validate and report without loading. (default False)
AiService | importVenueHistory | response | id | string (uuid) | yes | (read-only)
AiService | importVenueHistory | response | venueId | string (uuid) | yes
AiService | importVenueHistory | response | dataKind | enum (attendance, admissions, ticketSales, fnbSales, retailSales, queueReadings, staffShifts) | yes
AiService | importVenueHistory | response | assetId | string (uuid)
AiService | importVenueHistory | response | sourceSystem | string |  | (nullable)
AiService | importVenueHistory | response | columnMapping | object
AiService | importVenueHistory | response | dryRun | boolean |  | (default False)
AiService | importVenueHistory | response | status | enum (queued, validating, loading, completed, completedWithRejections, failed) | yes | (read-only)
AiService | importVenueHistory | response | periodFrom | string (date) |  | (read-only; nullable)
AiService | importVenueHistory | response | periodTo | string (date) |  | (read-only; nullable)
AiService | importVenueHistory | response | monthsCovered | integer |  | (read-only)
AiService | importVenueHistory | response | rowsRead | integer |  | (read-only)
AiService | importVenueHistory | response | rowsLoaded | integer |  | (read-only)
AiService | importVenueHistory | response | rowsRejected | integer |  | (read-only)
AiService | importVenueHistory | response | findings | array of object |  | (read-only)
AiService | importVenueHistory | response | findings[].row | integer
AiService | importVenueHistory | response | findings[].code | enum (badDate, badNumber, negativeValue, duplicateDay, unmappedColumn, outOfRange)
AiService | importVenueHistory | response | findings[].detail | string
AiService | importVenueHistory | response | requestedByPrincipalId | string (uuid) |  | (read-only)
AiService | importVenueHistory | response | createdAt | string (date-time) |  | (read-only)
AiService | importVenueHistory | response | completedAt | string (date-time) |  | (read-only; nullable)
AiService | importVenueHistory | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | importVenueHistory | param (path) | venueId | string (uuid) | yes
AiService | importVenueHistory | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
LedgerService | ingestFxRates | request | purpose | FxRatePurpose: enum (tender, interEntity, reporting, revaluation) | yes | A venue does not accept dollars at the rate it books an intercompany balance at.
LedgerService | ingestFxRates | request | pairs | array of string |  | AED/USD form.
LedgerService | ingestFxRates | request | effectiveFrom | string (date) |  | Defaults to the next business day in the region timezone. (nullable)
LedgerService | ingestFxRates | request | dryRun | boolean |  | Fetch and report without writing. (default False)
LedgerService | ingestFxRates | response | source | FxRateSource: enum (manual, uaeCentralBank, ecb, openExchangeRates, cardScheme, provider) |  | Where the rate came from, and which provider specifically.
LedgerService | ingestFxRates | response | purpose | FxRatePurpose: enum (tender, interEntity, reporting, revaluation) |  | A venue does not accept dollars at the rate it books an intercompany balance at.
LedgerService | ingestFxRates | response | ratesWritten | integer
LedgerService | ingestFxRates | response | unchanged | integer
LedgerService | ingestFxRates | response | largestMove | string |  | The number a person reads. (pattern ^-?\d+(\.\d{1,6})?$; nullable)
LedgerService | ingestFxRates | response | rates | array of FxRate
LedgerService | ingestFxRates | response | rates[].id | string (uuid) |  | (read-only)
LedgerService | ingestFxRates | response | rates[].fromCurrency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | ingestFxRates | response | rates[].toCurrency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | ingestFxRates | response | rates[].rate | object | yes | Units of toCurrency per one fromCurrency.
LedgerService | ingestFxRates | response | rates[].purpose | FxRatePurpose: enum (tender, interEntity, reporting, revaluation) | yes | A venue does not accept dollars at the rate it books an intercompany balance at.
LedgerService | ingestFxRates | response | rates[].source | object |  | (read-only)
LedgerService | ingestFxRates | response | rates[].effectiveFrom | string (date-time) | yes
LedgerService | ingestFxRates | response | rates[].effectiveTo | string (date-time) |  | A rate change is a new row. (nullable)
LedgerService | ingestFxRates | response | rates[].setByPrincipalId | string (uuid) |  | (read-only)
LedgerService | ingestFxRates | response | rates[].note | string |  | Why this rate, and from where. (max length 500; nullable)
LedgerService | ingestFxRates | response | rates[].providerReference | string |  | The provider's own identifier for this quote. (read-only; nullable)
LedgerService | ingestFxRates | response | rates[].fetchedAt | string (date-time) |  | When the rate was pulled. (read-only; nullable)
LedgerService | ingestFxRates | response | rates[].chargeable | boolean |  | With venueId, true where a guest may select this currency and pay in it at that venue (tenancy.VenueSettings.chargeCurrencies), false where it is shown as an approximate price only (CHG-FIN-001). (read-only)
LedgerService | ingestFxRates | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
AiService | ingestKnowledgeDocument | request | id | string (uuid) |  | (read-only)
AiService | ingestKnowledgeDocument | request | collectionId | string (uuid) |  | (read-only)
AiService | ingestKnowledgeDocument | request | title | string | yes
AiService | ingestKnowledgeDocument | request | sourceAssetId | string (uuid) | yes
AiService | ingestKnowledgeDocument | request | mimeType | string
AiService | ingestKnowledgeDocument | request | reingestDocumentId | string (uuid) |  | An indexed or failed document in this collection to process again from sourceAssetId. (nullable)
AiService | ingestKnowledgeDocument | request | supersedesDocumentId | string (uuid) |  | The indexed document in this collection that this one replaces. (nullable)
AiService | ingestKnowledgeDocument | request | status | enum (processing, indexed, failed, superseded) |  | (read-only)
AiService | ingestKnowledgeDocument | request | chunkCount | integer |  | (read-only)
AiService | ingestKnowledgeDocument | request | failureReason | string |  | (read-only; nullable)
AiService | ingestKnowledgeDocument | request | indexedAt | string (date-time) |  | (read-only; nullable)
AiService | ingestKnowledgeDocument | request | scopePath | string |  | Added 29 September (AI design 3.1): ai.knowledge_document had no policy, so neither did its chunks. (read-only)
AiService | ingestKnowledgeDocument | response | id | string (uuid) |  | (read-only)
AiService | ingestKnowledgeDocument | response | collectionId | string (uuid) |  | (read-only)
AiService | ingestKnowledgeDocument | response | title | string | yes
AiService | ingestKnowledgeDocument | response | sourceAssetId | string (uuid) | yes
AiService | ingestKnowledgeDocument | response | mimeType | string
AiService | ingestKnowledgeDocument | response | reingestDocumentId | string (uuid) |  | An indexed or failed document in this collection to process again from sourceAssetId. (nullable)
AiService | ingestKnowledgeDocument | response | supersedesDocumentId | string (uuid) |  | The indexed document in this collection that this one replaces. (nullable)
AiService | ingestKnowledgeDocument | response | status | enum (processing, indexed, failed, superseded) |  | (read-only)
AiService | ingestKnowledgeDocument | response | chunkCount | integer |  | (read-only)
AiService | ingestKnowledgeDocument | response | failureReason | string |  | (read-only; nullable)
AiService | ingestKnowledgeDocument | response | indexedAt | string (date-time) |  | (read-only; nullable)
AiService | ingestKnowledgeDocument | response | scopePath | string |  | Added 29 September (AI design 3.1): ai.knowledge_document had no policy, so neither did its chunks. (read-only)
AiService | ingestKnowledgeDocument | param (path) | collectionId | string (uuid) | yes
AiService | ingestKnowledgeDocument | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | inquirePaymentStatus | response | id | string (uuid) | yes
OrderService | inquirePaymentStatus | response | orderId | string (uuid) | yes
OrderService | inquirePaymentStatus | response | tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | inquirePaymentStatus | response | tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | inquirePaymentStatus | response | tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale.
OrderService | inquirePaymentStatus | response | tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | inquirePaymentStatus | response | tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | inquirePaymentStatus | response | tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | inquirePaymentStatus | response | fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | inquirePaymentStatus | response | fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | inquirePaymentStatus | response | changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | inquirePaymentStatus | response | amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | inquirePaymentStatus | response | amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | inquirePaymentStatus | response | amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | inquirePaymentStatus | response | amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | inquirePaymentStatus | response | changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | inquirePaymentStatus | response | changeAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | inquirePaymentStatus | response | changeAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | inquirePaymentStatus | response | changeAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | inquirePaymentStatus | response | status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | inquirePaymentStatus | response | providerName | string |  | (nullable)
OrderService | inquirePaymentStatus | response | providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | inquirePaymentStatus | response | providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | inquirePaymentStatus | response | terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | inquirePaymentStatus | response | nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | inquirePaymentStatus | response | nextAction.kind | enum (redirect, terminal)
OrderService | inquirePaymentStatus | response | nextAction.url | string (uri) |  | (nullable)
OrderService | inquirePaymentStatus | response | nextAction.expiresAt | string (date-time) |  | (nullable)
OrderService | inquirePaymentStatus | response | lastInquiryAt | string (date-time) |  | (nullable)
OrderService | inquirePaymentStatus | response | recordedAt | string (date-time) | yes
OrderService | inquirePaymentStatus | response | syncedAt | string (date-time) |  | (nullable)
OrderService | inquirePaymentStatus | param (path) | paymentId | string (uuid) | yes
OrderService | inquirePaymentStatus | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
LedgerService | issueCreditMemo | request | kind | enum (full, partial) | yes
LedgerService | issueCreditMemo | request | reason | enum (refund, cancellation, priceAdjustment, returnOfGoods, billingError, other) | yes
LedgerService | issueCreditMemo | request | refundId | string (uuid) |  | (nullable)
LedgerService | issueCreditMemo | request | cancelledOrderId | string (uuid) |  | (nullable)
LedgerService | issueCreditMemo | request | lines | array of object |  | Required for partial.
LedgerService | issueCreditMemo | request | lines[].lineNumber | integer | yes | (min 1)
LedgerService | issueCreditMemo | request | lines[].quantity | number |  | (nullable)
LedgerService | issueCreditMemo | request | lines[].netAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | issueCreditMemo | request | lines[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueCreditMemo | request | lines[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueCreditMemo | request | lines[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueCreditMemo | request | note | string |  | (max length 500; nullable)
LedgerService | issueCreditMemo | response | id | string (uuid) | yes | (read-only)
LedgerService | issueCreditMemo | response | creditMemoNumber | string | yes | Server-assigned from the legal entity's credit memo series, in sequence without gaps. (read-only)
LedgerService | issueCreditMemo | response | taxInvoiceId | string (uuid) | yes
LedgerService | issueCreditMemo | response | taxInvoiceNumber | string |  | (read-only)
LedgerService | issueCreditMemo | response | kind | enum (full, partial) | yes
LedgerService | issueCreditMemo | response | reason | enum (refund, cancellation, priceAdjustment, returnOfGoods, billingError, other) | yes
LedgerService | issueCreditMemo | response | refundId | string (uuid) |  | (nullable)
LedgerService | issueCreditMemo | response | cancelledOrderId | string (uuid) |  | (nullable)
LedgerService | issueCreditMemo | response | legalEntityId | string (uuid) | yes
LedgerService | issueCreditMemo | response | buyerSubjectId | string (uuid) |  | (nullable)
LedgerService | issueCreditMemo | response | issuedAt | string (date-time) | yes
LedgerService | issueCreditMemo | response | currency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | issueCreditMemo | response | netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | issueCreditMemo | response | netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueCreditMemo | response | netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueCreditMemo | response | netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueCreditMemo | response | taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | issueCreditMemo | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueCreditMemo | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueCreditMemo | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueCreditMemo | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | issueCreditMemo | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueCreditMemo | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueCreditMemo | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueCreditMemo | response | taxAmountInLegalCurrency | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | issueCreditMemo | response | taxAmountInLegalCurrency.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueCreditMemo | response | taxAmountInLegalCurrency.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueCreditMemo | response | taxAmountInLegalCurrency.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueCreditMemo | response | legalFxRate | object |  | The invoice's own legalFxRate, never today's (CHG-FIN-011). (read-only; nullable)
LedgerService | issueCreditMemo | response | invoiceSupplyValue | object |  | The value of the supply shown on the tax invoice (Executive Regulation Art. (read-only)
LedgerService | issueCreditMemo | response | invoiceSupplyValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueCreditMemo | response | invoiceSupplyValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueCreditMemo | response | invoiceSupplyValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueCreditMemo | response | correctedSupplyValue | object |  | The correct value of the supply after this credit note (Art. (read-only)
LedgerService | issueCreditMemo | response | correctedSupplyValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueCreditMemo | response | correctedSupplyValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueCreditMemo | response | correctedSupplyValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueCreditMemo | response | supplierName | string |  | Snapshot of the legal entity at issue, as on the invoice (Art. (read-only)
LedgerService | issueCreditMemo | response | supplierAddress | string |  | (read-only; nullable)
LedgerService | issueCreditMemo | response | supplierTaxRegistrationNumber | string |  | (read-only; nullable)
LedgerService | issueCreditMemo | response | buyerName | string |  | The recipient as on the invoice; name, address and TRN where they are registered (Art. (read-only; nullable)
LedgerService | issueCreditMemo | response | buyerAddress | string |  | (read-only; nullable)
LedgerService | issueCreditMemo | response | buyerTaxRegistrationNumber | string |  | (read-only; nullable)
LedgerService | issueCreditMemo | response | note | string |  | The brief explanation of why the credit note was issued, printed on it (Art. (nullable)
LedgerService | issueCreditMemo | response | renditionAssetId | string (uuid) |  | (read-only; nullable)
LedgerService | issueCreditMemo | response | eInvoiceStatus | FinEInvoiceTransmissionStatus: enum (notRequired, queued, sent, accepted, rejected, failed) |  | 6.1.1.
LedgerService | issueCreditMemo | response | issuedByPrincipalId | string (uuid) |  | (read-only; nullable)
LedgerService | issueCreditMemo | response | lines | array of FinCreditMemoLine | yes
LedgerService | issueCreditMemo | response | lines[].invoiceLineNumber | integer | yes | (min 1)
LedgerService | issueCreditMemo | response | lines[].description | string |  | (max length 500)
LedgerService | issueCreditMemo | response | lines[].quantity | number |  | (nullable)
LedgerService | issueCreditMemo | response | lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | issueCreditMemo | response | lines[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueCreditMemo | response | lines[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueCreditMemo | response | lines[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueCreditMemo | response | lines[].taxRate | number
LedgerService | issueCreditMemo | response | lines[].taxCategory | FinTaxCategory: enum (standardRated, zeroRated, exempt, outOfScope, reverseCharge) |  | How a line is treated for VAT.
LedgerService | issueCreditMemo | response | lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | issueCreditMemo | response | lines[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueCreditMemo | response | lines[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueCreditMemo | response | lines[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueCreditMemo | response | lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | issueCreditMemo | response | lines[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueCreditMemo | response | lines[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueCreditMemo | response | lines[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueCreditMemo | response | scopePath | string |  | (read-only)
LedgerService | issueCreditMemo | param (path) | invoiceId | string (uuid) | yes
LedgerService | issueCreditMemo | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | issueGameCard | request | id | string (uuid) | yes | Client-generated UUIDv7 for this request, and the idempotency key: it must equal the Idempotency-Key header, and a mismatch is the shared 409 Conflict.
VenueOpsService | issueGameCard | request | kind | enum (physical, digital) | yes
VenueOpsService | issueGameCard | request | cardCode | string |  | Required for physical cards, which are pre-printed.
VenueOpsService | issueGameCard | request | venueId | string (uuid) | yes
VenueOpsService | issueGameCard | request | subjectId | string (uuid)
VenueOpsService | issueGameCard | request | initialCredits | integer |  | (min 0; default 0)
VenueOpsService | issueGameCard | request | validMonths | integer |  | (min 1)
VenueOpsService | issueGameCard | response | cardCode | string | yes | A pre-printed card keeps the code printed on it.
VenueOpsService | issueGameCard | response | kind | string
VenueOpsService | issueGameCard | response | venueId | string (uuid) | yes
VenueOpsService | issueGameCard | response | subjectId | string (uuid) |  | (nullable)
VenueOpsService | issueGameCard | response | credits | integer | yes | Bought with money.
VenueOpsService | issueGameCard | response | bonusCredits | integer | yes | From a promotion.
VenueOpsService | issueGameCard | response | points | integer | yes | Won by playing.
VenueOpsService | issueGameCard | response | status | enum (active, blocked, expired, transferred) | yes
VenueOpsService | issueGameCard | response | blockedReason | string |  | (nullable)
VenueOpsService | issueGameCard | response | transferredToCardCode | string |  | (nullable)
VenueOpsService | issueGameCard | response | lastPlayedAt | string (date-time) |  | (nullable)
VenueOpsService | issueGameCard | response | issuedAt | string (date-time) | yes
VenueOpsService | issueGameCard | response | expiresAt | string (date-time) |  | (nullable)
VenueOpsService | issueGameCard | response | id | string (uuid) |  | The card's own id (4 October 2026, CHG-FXC-006): the {cardId} of setGameCardLifecycle, which had no column to match, and the id of the Wallet view wallet.loadGameCredits and wallet.adjustGameCard ret… (read-only)
VenueOpsService | issueGameCard | response | walletId | string (uuid) |  | Where the card's credits are held (4 October 2026, CHG-FXC-006). (read-only; nullable)
VenueOpsService | issueGameCard | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
LedgerService | issueTaxInvoice | request | invoiceType | FinTaxInvoiceType: enum (simplified, full, consolidated) | yes | 5.7.93.
LedgerService | issueTaxInvoice | request | orderIds | array of string (uuid) | yes | One order for simplified and full; one or more for consolidated. (min items 1)
LedgerService | issueTaxInvoice | request | recipient | FinTaxInvoiceRecipient |  | Who the invoice is addressed to.
LedgerService | issueTaxInvoice | request | recipient.name | string | yes | (max length 300)
LedgerService | issueTaxInvoice | request | recipient.address | string |  | (max length 1000; nullable)
LedgerService | issueTaxInvoice | request | recipient.countryCode | string |  | (pattern ^[A-Z]{2}$; nullable)
LedgerService | issueTaxInvoice | request | recipient.taxRegistrationNumber | string |  | The recipient's TRN where they are VAT-registered. (max length 30; nullable)
LedgerService | issueTaxInvoice | request | recipient.customerAccountId | string (uuid) |  | The B2B credit account (payments B2bCreditAccount) where a company is invoiced. (nullable)
LedgerService | issueTaxInvoice | request | languages | array of string |  | Overrides the template's languages for this document, within those the template offers.
LedgerService | issueTaxInvoice | request | supersedesInvoiceId | string (uuid) |  | A simplified invoice this full invoice replaces for the same supply. (nullable)
LedgerService | issueTaxInvoice | request | deliverToEmail | string (email) |  | Sends the PDF on issue as well as returning it. (nullable)
LedgerService | issueTaxInvoice | response | id | string (uuid) | yes | (read-only)
LedgerService | issueTaxInvoice | response | invoiceNumber | string | yes | Server-assigned from the legal entity's series for the document kind, in sequence and without gaps, e.g. (read-only)
LedgerService | issueTaxInvoice | response | invoiceType | FinTaxInvoiceType: enum (simplified, full, consolidated) | yes | 5.7.93.
LedgerService | issueTaxInvoice | response | status | FinTaxInvoiceStatus: enum (issued, partiallyCredited, fullyCredited, superseded) | yes | issued until a credit memo is issued against it; superseded where a full invoice replaced a simplified one for the same supply (only if the law allows it; see issueTaxInvoice).
LedgerService | issueTaxInvoice | response | legalEntityId | string (uuid) | yes
LedgerService | issueTaxInvoice | response | templateId | string (uuid) |  | (nullable)
LedgerService | issueTaxInvoice | response | venueId | string (uuid) |  | (nullable)
LedgerService | issueTaxInvoice | response | orderIds | array of string (uuid)
LedgerService | issueTaxInvoice | response | supplierName | string
LedgerService | issueTaxInvoice | response | supplierAddress | string |  | (nullable)
LedgerService | issueTaxInvoice | response | supplierTaxRegistrationNumber | string |  | (nullable)
LedgerService | issueTaxInvoice | response | buyerSubjectId | string (uuid) |  | The guest the orders belong to; the key a guest's own reads filter on. (nullable)
LedgerService | issueTaxInvoice | response | buyerName | string |  | (nullable)
LedgerService | issueTaxInvoice | response | buyerAddress | string |  | (nullable)
LedgerService | issueTaxInvoice | response | buyerCountryCode | string |  | (pattern ^[A-Z]{2}$; nullable)
LedgerService | issueTaxInvoice | response | buyerTaxRegistrationNumber | string |  | (nullable)
LedgerService | issueTaxInvoice | response | customerAccountId | string (uuid) |  | (nullable)
LedgerService | issueTaxInvoice | response | issuedAt | string (date-time) | yes
LedgerService | issueTaxInvoice | response | supplyDate | string (date) | yes | The date of supply where it differs from the issue date (the latest order's payment date on a consolidated invoice).
LedgerService | issueTaxInvoice | response | currency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | discountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | discountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | discountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | taxAmountInLegalCurrency | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | taxAmountInLegalCurrency.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | taxAmountInLegalCurrency.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | taxAmountInLegalCurrency.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | legalCurrency | string |  | The legal entity's currency (AED in the UAE), in which the law requires the tax and the gross amount (CHG-FIN-011). (pattern ^[A-Z]{3}$; read-only)
LedgerService | issueTaxInvoice | response | grossAmountInLegalCurrency | object |  | The gross amount payable in the legal currency (Executive Regulation Art. (read-only)
LedgerService | issueTaxInvoice | response | grossAmountInLegalCurrency.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | grossAmountInLegalCurrency.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | grossAmountInLegalCurrency.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | legalFxRate | object |  | Units of the legal currency per one unit of currency, printed with the tax where the invoice is not in the legal currency (Art. (read-only; nullable)
LedgerService | issueTaxInvoice | response | legalFxRateSource | object |  | uaeCentralBank for a UAE legal entity (Decree-Law Art. (read-only; nullable)
LedgerService | issueTaxInvoice | response | paidCurrency | string |  | Where the guest paid in a currency they selected (orders.Order.chargeCurrency, CHG-FIN-001), printed as payment information with paidAmount and the charge rate. (pattern ^[A-Z]{3}$; read-only; nullable)
LedgerService | issueTaxInvoice | response | paidAmount | object |  | What the guest paid in paidCurrency (orders.Order.chargeTotal). (read-only)
LedgerService | issueTaxInvoice | response | paidAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | paidAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | paidAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | reverseChargeStatement | string |  | Where the recipient must account for the tax, the statement saying so and the Decree-Law provision (Art. (read-only; nullable)
LedgerService | issueTaxInvoice | response | creditedAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | creditedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | creditedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | creditedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | languages | array of string
LedgerService | issueTaxInvoice | response | supersedesInvoiceId | string (uuid) |  | (nullable)
LedgerService | issueTaxInvoice | response | renditionAssetId | string (uuid) |  | The PDF rendered at issue; read through getTaxDocumentRendition. (read-only; nullable)
LedgerService | issueTaxInvoice | response | eInvoiceStatus | FinEInvoiceTransmissionStatus: enum (notRequired, queued, sent, accepted, rejected, failed) |  | 6.1.1.
LedgerService | issueTaxInvoice | response | issuedByPrincipalId | string (uuid) |  | Null where the platform issued it. (read-only; nullable)
LedgerService | issueTaxInvoice | response | lines | array of FinTaxInvoiceLine | yes
LedgerService | issueTaxInvoice | response | lines[].lineNumber | integer | yes | (min 1)
LedgerService | issueTaxInvoice | response | lines[].orderId | string (uuid)
LedgerService | issueTaxInvoice | response | lines[].orderLineId | string (uuid) |  | (nullable)
LedgerService | issueTaxInvoice | response | lines[].description | string | yes | (max length 500)
LedgerService | issueTaxInvoice | response | lines[].quantity | number | yes
LedgerService | issueTaxInvoice | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | lines[].discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | lines[].discountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | lines[].discountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | lines[].discountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | lines[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | lines[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | lines[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | lines[].taxCodeId | string (uuid) |  | (nullable)
LedgerService | issueTaxInvoice | response | lines[].taxRate | number |  | (min 0; max 100)
LedgerService | issueTaxInvoice | response | lines[].taxCategory | FinTaxCategory: enum (standardRated, zeroRated, exempt, outOfScope, reverseCharge) | yes | How a line is treated for VAT.
LedgerService | issueTaxInvoice | response | lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | lines[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | lines[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | lines[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | lines[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | lines[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | lines[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | lines[].creditedAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | lines[].creditedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | lines[].creditedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | lines[].creditedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | lines[].grossAmountInLegalCurrency | object |  | The amount payable for the line in the legal currency (AED), Executive Regulation Art. (read-only)
LedgerService | issueTaxInvoice | response | lines[].grossAmountInLegalCurrency.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | lines[].grossAmountInLegalCurrency.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | lines[].grossAmountInLegalCurrency.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | taxSummary | array of object |  | VAT per rate and category, summed from the lines for the response.
LedgerService | issueTaxInvoice | response | taxSummary[].taxCategory | FinTaxCategory: enum (standardRated, zeroRated, exempt, outOfScope, reverseCharge) |  | How a line is treated for VAT.
LedgerService | issueTaxInvoice | response | taxSummary[].taxRate | number
LedgerService | issueTaxInvoice | response | taxSummary[].taxableAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | taxSummary[].taxableAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | taxSummary[].taxableAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | taxSummary[].taxableAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | taxSummary[].taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | issueTaxInvoice | response | taxSummary[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | issueTaxInvoice | response | taxSummary[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | issueTaxInvoice | response | taxSummary[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | issueTaxInvoice | response | scopePath | string |  | The partition key (ADR-0005). (read-only)
LedgerService | issueTaxInvoice | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | issueWalletPass | request | entitlementId | string (uuid) | yes
OrderService | issueWalletPass | request | platform | enum (apple, google) | yes
OrderService | issueWalletPass | response | id | string (uuid) | yes
OrderService | issueWalletPass | response | entitlementId | string (uuid) | yes
OrderService | issueWalletPass | response | platform | enum (apple, google) | yes
OrderService | issueWalletPass | response | serialNumber | string | yes
OrderService | issueWalletPass | response | authenticationToken | string (password) |  | Write-only.
OrderService | issueWalletPass | response | status | enum (issued, updated, voided, expired) | yes
OrderService | issueWalletPass | response | lastPushedAt | string (date-time) |  | (nullable)
OrderService | issueWalletPass | response | deviceRegistrations | integer |  | How many devices hold it.
OrderService | issueWalletPass | response | scopePath | string |  | The partition key (ADR-0005).
OrderService | issueWalletPass | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | joinQueue | request | id | string (uuid) | yes
VenueOpsService | joinQueue | request | queueId | string (uuid) | yes
VenueOpsService | joinQueue | request | partySize | integer | yes | (min 1)
VenueOpsService | joinQueue | request | entitlementId | string |  | Fast Pass or priority entitlement. (nullable)
VenueOpsService | joinQueue | request | partyHeightsCm | array of integer |  | Where the queue has a height requirement.
VenueOpsService | joinQueue | request | accessibilityNeedDeclared | boolean |  | The party declares an accessibility need (5.6.7; decided 29 September, build pass). (default False)
VenueOpsService | joinQueue | request | promotionCode | string |  | A promotion code the guest holds, checked against the lane's QueueFastPass.promotionIds (5.6.34). (max length 64; nullable)
VenueOpsService | joinQueue | request | recordedAt | string (date-time) | yes
VenueOpsService | joinQueue | response | id | string (uuid) | yes | The client-generated UUIDv7 from JoinQueueRequest.id, and the entryId every entry path takes.
VenueOpsService | joinQueue | response | queueId | string (uuid) | yes
VenueOpsService | joinQueue | response | queueName | LocalisedText
VenueOpsService | joinQueue | response | subjectId | string (uuid) |  | (nullable)
VenueOpsService | joinQueue | response | partyNumber | integer | yes | What the guest sees and what appears on signage.
VenueOpsService | joinQueue | response | partySize | integer | yes
VenueOpsService | joinQueue | response | status | QueueEntryStatus: enum (waiting, called, redeemed, expired, noShow, cancelled, released) | yes
VenueOpsService | joinQueue | response | positionInQueue | integer |  | (nullable)
VenueOpsService | joinQueue | response | partiesAhead | integer |  | (nullable)
VenueOpsService | joinQueue | response | estimatedCallAt | string (date-time) |  | (nullable)
VenueOpsService | joinQueue | response | isFastPass | boolean
VenueOpsService | joinQueue | response | priorityBasis | enum (none, entitlement, loyaltyTier, promotion, accessibility) |  | Why this party is priority, when it is (decided 29 September, build pass; 5.6.7, 5.6.34): the first QueueFastPass criterion met at join, in the order entitlement, loyalty tier, promotion, accessibili… (default none)
VenueOpsService | joinQueue | response | priorityTierId | string (uuid) |  | The loyalty tier that granted priority, where priorityBasis is loyaltyTier. (nullable)
VenueOpsService | joinQueue | response | priorityPromotionId | string (uuid) |  | The promotion that granted priority, where priorityBasis is promotion. (nullable)
VenueOpsService | joinQueue | response | accessibilityNeedDeclared | boolean |  | What the party declared at join, shown to the operator at the front. (default False)
VenueOpsService | joinQueue | response | entitlementId | string |  | (nullable)
VenueOpsService | joinQueue | response | calledAt | string (date-time) |  | (nullable)
VenueOpsService | joinQueue | response | returnWindowEndsAt | string (date-time) |  | (nullable)
VenueOpsService | joinQueue | response | redeemedAt | string (date-time) |  | (nullable)
VenueOpsService | joinQueue | response | admittedCount | integer |  | (nullable)
VenueOpsService | joinQueue | response | joinedAt | string (date-time) | yes
VenueOpsService | joinQueue | response | syncedAt | string (date-time) |  | (nullable)
VenueOpsService | joinQueue | response | overriddenByPrincipalId | string (uuid) |  | Who let the party past the queue (overrideWaitingGuest, 4 October 2026, CHG-FXC-003), with overrideReason and overriddenAt. (read-only; nullable)
VenueOpsService | joinQueue | response | overrideReason | string |  | (read-only; nullable)
VenueOpsService | joinQueue | response | overriddenAt | string (date-time) |  | (read-only; nullable)
VenueOpsService | joinQueue | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | joinRestaurantWaitlist | request | id | string (uuid) | yes
FnbService | joinRestaurantWaitlist | request | outletId | string (uuid) | yes
FnbService | joinRestaurantWaitlist | request | subjectId | string (uuid) |  | (nullable)
FnbService | joinRestaurantWaitlist | request | partySize | integer | yes
FnbService | joinRestaurantWaitlist | request | quotedWaitMinutes | integer |  | (nullable)
FnbService | joinRestaurantWaitlist | request | seatingPreference | enum (any, indoor, outdoor, bar, booth, highChair) |  | (nullable)
FnbService | joinRestaurantWaitlist | request | status | enum (waiting, notified, seated, walkedAway, noShow, cancelled) | yes
FnbService | joinRestaurantWaitlist | request | notifiedAt | string (date-time) |  | (nullable)
FnbService | joinRestaurantWaitlist | request | recordedAt | string (date-time) | yes | When the party joined, on the device.
FnbService | joinRestaurantWaitlist | request | syncedAt | string (date-time) |  | (read-only; nullable)
FnbService | joinRestaurantWaitlist | request | holdExpiresAt | string (date-time) |  | How long a table waits for somebody who was called. (nullable)
FnbService | joinRestaurantWaitlist | response | id | string (uuid) | yes
FnbService | joinRestaurantWaitlist | response | outletId | string (uuid) | yes
FnbService | joinRestaurantWaitlist | response | subjectId | string (uuid) |  | (nullable)
FnbService | joinRestaurantWaitlist | response | partySize | integer | yes
FnbService | joinRestaurantWaitlist | response | quotedWaitMinutes | integer |  | (nullable)
FnbService | joinRestaurantWaitlist | response | seatingPreference | enum (any, indoor, outdoor, bar, booth, highChair) |  | (nullable)
FnbService | joinRestaurantWaitlist | response | status | enum (waiting, notified, seated, walkedAway, noShow, cancelled) | yes
FnbService | joinRestaurantWaitlist | response | notifiedAt | string (date-time) |  | (nullable)
FnbService | joinRestaurantWaitlist | response | recordedAt | string (date-time) | yes | When the party joined, on the device.
FnbService | joinRestaurantWaitlist | response | syncedAt | string (date-time) |  | (read-only; nullable)
FnbService | joinRestaurantWaitlist | response | holdExpiresAt | string (date-time) |  | How long a table waits for somebody who was called. (nullable)
FnbService | joinRestaurantWaitlist | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | joinWaitlist | request | id | string (uuid) |  | (read-only)
CatalogueService | joinWaitlist | request | performanceId | string (uuid) | yes
CatalogueService | joinWaitlist | request | variantId | string (uuid) |  | (nullable)
CatalogueService | joinWaitlist | request | subjectId | string (uuid) |  | (nullable)
CatalogueService | joinWaitlist | request | contactPoint | string |  | Where the offer goes.
CatalogueService | joinWaitlist | request | partySize | integer | yes | (min 1)
CatalogueService | joinWaitlist | request | status | object |  | Set by the server. (read-only)
CatalogueService | joinWaitlist | request | position | integer |  | First in, first offered. (read-only)
CatalogueService | joinWaitlist | request | offeredAt | string (date-time) |  | (read-only; nullable)
CatalogueService | joinWaitlist | request | offerExpiresAt | string (date-time) |  | The offer moves on when this passes. (read-only; nullable)
CatalogueService | joinWaitlist | request | joinedAt | string (date-time) |  | (read-only)
CatalogueService | joinWaitlist | response | id | string (uuid) |  | (read-only)
CatalogueService | joinWaitlist | response | performanceId | string (uuid) | yes
CatalogueService | joinWaitlist | response | variantId | string (uuid) |  | (nullable)
CatalogueService | joinWaitlist | response | subjectId | string (uuid) |  | (nullable)
CatalogueService | joinWaitlist | response | contactPoint | string |  | Where the offer goes.
CatalogueService | joinWaitlist | response | partySize | integer | yes | (min 1)
CatalogueService | joinWaitlist | response | status | object |  | Set by the server. (read-only)
CatalogueService | joinWaitlist | response | position | integer |  | First in, first offered. (read-only)
CatalogueService | joinWaitlist | response | offeredAt | string (date-time) |  | (read-only; nullable)
CatalogueService | joinWaitlist | response | offerExpiresAt | string (date-time) |  | The offer moves on when this passes. (read-only; nullable)
CatalogueService | joinWaitlist | response | joinedAt | string (date-time) |  | (read-only)
CatalogueService | joinWaitlist | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
MarketingService | launchCampaign | request | scheduledFor | string (date-time)
MarketingService | launchCampaign | request | confirmAudienceSize | integer |  | Guard against a segment that has grown unexpectedly.
MarketingService | launchCampaign | response | campaignId | string (uuid) | yes
MarketingService | launchCampaign | response | audienceSize | integer | yes
MarketingService | launchCampaign | response | queuedCount | integer | yes
MarketingService | launchCampaign | response | excluded | array of object | yes | Why each excluded guest was excluded, in aggregate.
MarketingService | launchCampaign | response | excluded[].reason | enum (noConsent, consentRequiresRenewal, suppressed, noAddress, frequencyCap, outsideSendWindow)
MarketingService | launchCampaign | response | excluded[].count | integer
MarketingService | launchCampaign | response | scheduledFor | string (date-time) |  | (nullable)
MarketingService | launchCampaign | param (path) | campaignId | string (uuid) | yes
MarketingService | launchCampaign | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
VenueOpsService | leaveQueue | param (path) | entryId | string (uuid) | yes
VenueOpsService | leaveQueue | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | leaveRestaurantWaitlist | request | note | string |  | Why, where the guest or host gave a reason. (max length 300; nullable)
FnbService | leaveRestaurantWaitlist | response | id | string (uuid) | yes
FnbService | leaveRestaurantWaitlist | response | outletId | string (uuid) | yes
FnbService | leaveRestaurantWaitlist | response | subjectId | string (uuid) |  | (nullable)
FnbService | leaveRestaurantWaitlist | response | partySize | integer | yes
FnbService | leaveRestaurantWaitlist | response | quotedWaitMinutes | integer |  | (nullable)
FnbService | leaveRestaurantWaitlist | response | seatingPreference | enum (any, indoor, outdoor, bar, booth, highChair) |  | (nullable)
FnbService | leaveRestaurantWaitlist | response | status | enum (waiting, notified, seated, walkedAway, noShow, cancelled) | yes
FnbService | leaveRestaurantWaitlist | response | notifiedAt | string (date-time) |  | (nullable)
FnbService | leaveRestaurantWaitlist | response | recordedAt | string (date-time) | yes | When the party joined, on the device.
FnbService | leaveRestaurantWaitlist | response | syncedAt | string (date-time) |  | (read-only; nullable)
FnbService | leaveRestaurantWaitlist | response | holdExpiresAt | string (date-time) |  | How long a table waits for somebody who was called. (nullable)
FnbService | leaveRestaurantWaitlist | param (path) | entryId | string (uuid) | yes
FnbService | leaveRestaurantWaitlist | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
CatalogueService | leaveWaitlist | param (path) | entryId | string (uuid) | yes
CatalogueService | leaveWaitlist | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | linkGuestCheckout | request | orderReference | string | yes
IdentityService | linkGuestCheckout | request | verificationCode | string |  | From the booking confirmation.
IdentityService | linkGuestCheckout | response | attachedOrderCount | integer |  | The named booking plus any other orders with the same verified contact detail.
IdentityService | linkGuestCheckout | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | list86Events | response | items | array of EightySixEvent | yes
FnbService | list86Events | response | items[].id | string (uuid) | yes
FnbService | list86Events | response | items[].outletId | string (uuid)
FnbService | list86Events | response | items[].menuItemId | string (uuid) | yes
FnbService | list86Events | response | items[].offAt | string (date-time) | yes
FnbService | list86Events | response | items[].backAt | string (date-time) |  | (nullable)
FnbService | list86Events | response | items[].reason | enum (ranOut, qualityIssue, equipmentDown, supplierFailure, seasonal, other) |  | other always carries a note (audit R222).
FnbService | list86Events | response | items[].note | string |  | The note given with the 86. (max length 500; nullable)
FnbService | list86Events | response | items[].calledByPrincipalId | string (uuid)
FnbService | list86Events | response | items[].source | enum (manual, dailyCount) |  | Who took the item off (CHG-CSA-017). (default manual; read-only)
FnbService | list86Events | response | items[].refusedOrderCount | integer |  | (default 0; read-only)
FnbService | list86Events | response | nextCursor | string
FnbService | list86Events | response | hasMore | boolean | yes
FnbService | list86Events | param (path) | outletId | string (uuid) | yes
FnbService | list86Events | param (query) | from | string (date) |  | First calendar day, in the Region's time zone, not UTC.
FnbService | list86Events | param (query) | pageSize | integer
FnbService | list86Events | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
IdentityService | listActiveSessions | response | items | array of ActiveSession | yes
IdentityService | listActiveSessions | response | items[].status | object | yes | A registry that only holds live sessions cannot answer why one ended.
IdentityService | listActiveSessions | response | items[].sessionId | string | yes
IdentityService | listActiveSessions | response | items[].principalId | string (uuid) | yes
IdentityService | listActiveSessions | response | items[].principalName | string |  | Read from identity.principal with the row.
IdentityService | listActiveSessions | response | items[].roleId | string (uuid) |  | (nullable)
IdentityService | listActiveSessions | response | items[].roleName | string |  | Read from identity.role with the row. (nullable)
IdentityService | listActiveSessions | response | items[].workstationId | string (uuid) |  | (nullable)
IdentityService | listActiveSessions | response | items[].workstationName | string |  | Read from the workstation with the row. (nullable)
IdentityService | listActiveSessions | response | items[].venueId | string (uuid) |  | (nullable)
IdentityService | listActiveSessions | response | items[].ipAddress | string |  | (nullable)
IdentityService | listActiveSessions | response | items[].deviceInfo | string |  | (nullable)
IdentityService | listActiveSessions | response | items[].hasOpenShift | boolean |  | Revoking this session leaves cash unreconciled.
IdentityService | listActiveSessions | response | items[].mfaSatisfied | boolean
IdentityService | listActiveSessions | response | items[].startedAt | string (date-time) | yes
IdentityService | listActiveSessions | response | items[].lastSeenAt | string (date-time) | yes
IdentityService | listActiveSessions | response | nextCursor | string
IdentityService | listActiveSessions | response | hasMore | boolean | yes
IdentityService | listActiveSessions | param (header) | X-Supervisor-Principal-Id | string (uuid) |  | With no session (POS-000), the supervisor signing the step-up (CHG-RUL-015).
IdentityService | listActiveSessions | param (header) | X-Supervisor-Pin | string (password) |  | With no session (POS-000), the supervisor's staff PIN, as SupervisorStepUp.credential (CHG-RUL-015).
IdentityService | listActiveSessions | param (query) | venueId | string (uuid) |  | Exact match on ActiveSession.venueId.
IdentityService | listActiveSessions | param (query) | principalId | string (uuid) |  | Exact match on ActiveSession.principalId.
IdentityService | listActiveSessions | param (query) | workstationId | string (uuid) |  | Exact match on ActiveSession.workstationId — who holds this till, which POS-000 Sign In asks before offering a force-logout, without paging through every session in the venue.
IdentityService | listActiveSessions | param (query) | pageSize | integer
IdentityService | listActiveSessions | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
AiService | listAiCapabilities | response | items | array of AiCapabilityRegistration | yes
AiService | listAiCapabilities | response | items[].id | string (uuid) |  | (read-only)
AiService | listAiCapabilities | response | items[].capabilityKey | string | yes | Stable key, unique per tenant: assistant.guest, forecast.attendance, risk.transaction, config.assistant, recommend.checkout.
AiService | listAiCapabilities | response | items[].family | AiCapabilityFamily: enum (gatewayAndModels, governance, actionPipeline, knowledgeRetrieval, assistants, analyticsInsights, configurationAssistant, forecasting, …) | yes | The fourteen capabilities of the AI system design (section 1.1), C1 to C14 in order: gateway and model registry, governance decision point, action pipeline and human oversight, knowledge and retrieva…
AiService | listAiCapabilities | response | items[].name | string
AiService | listAiCapabilities | response | items[].description | string |  | (nullable)
AiService | listAiCapabilities | response | items[].ownerPrincipalId | string (uuid) |  | The accountable business owner (AIC-144). (nullable)
AiService | listAiCapabilities | response | items[].businessFunction | string |  | (nullable)
AiService | listAiCapabilities | response | items[].riskClass | AiRiskClass: enum (low, medium, high, critical) | yes | Business, customer, financial, operational, security and compliance impact of a capability or action type (AIC-144, ADM-521).
AiService | listAiCapabilities | response | items[].autonomyCeiling | object |  | The first-release ceiling for this capability (design 3.8 table). (read-only)
AiService | listAiCapabilities | response | items[].autonomyLevel | object | yes | The level in force at this scope.
AiService | listAiCapabilities | response | items[].dataCategories | array of string |  | Data categories the capability reads (ADM-524).
AiService | listAiCapabilities | response | items[].lifecycle | object |  | Lifecycle per environment (AIC-145): a capability or model can be live in staging and still a draft in production.
AiService | listAiCapabilities | response | items[].lifecycle.development | enum (draft, pilot, active, retired)
AiService | listAiCapabilities | response | items[].lifecycle.staging | enum (draft, pilot, active, retired)
AiService | listAiCapabilities | response | items[].lifecycle.production | enum (draft, pilot, active, retired)
AiService | listAiCapabilities | response | items[].degradationMode | enum (rulesOnly, searchOnly, humanHandoff, hidden, failOpen, lastPublished) |  | What the capability does when its model or the service is unavailable (design 3.7, AIC-241).
AiService | listAiCapabilities | response | items[].status | enum (active, paused) |  | Paused by pauseAiCapability: the capability answers from its degradation mode until resumed. (read-only)
AiService | listAiCapabilities | response | items[].pausedReason | string |  | (read-only; nullable)
AiService | listAiCapabilities | response | items[].pausedAt | string (date-time) |  | (read-only; nullable)
AiService | listAiCapabilities | response | items[].updatedAt | string (date-time) |  | (read-only)
AiService | listAiCapabilities | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | listAiCapabilities | response | nextCursor | string
AiService | listAiCapabilities | response | hasMore | boolean | yes
AiService | listAiCapabilities | param (query) | family | AiCapabilityFamily: enum (gatewayAndModels, governance, actionPipeline, knowledgeRetrieval, assistants, analyticsInsights, configurationAssistant, forecasting, …)
AiService | listAiCapabilities | param (query) | status | enum (active, paused)
AiService | listAiCapabilities | param (query) | riskClass | AiRiskClass: enum (low, medium, high, critical)
AiService | listAiCapabilities | param (query) | pageSize | integer
AiService | listAiCapabilities | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
AiService | listAiConversations | response | items | array of AiConversation | yes
AiService | listAiConversations | response | items[].id | string (uuid) | yes
AiService | listAiConversations | response | items[].principalId | string (uuid) | yes
AiService | listAiConversations | response | items[].scopePath | string
AiService | listAiConversations | response | items[].module | ModuleKey: enum (core, ticketing, access, fnb, retail, inventory, seating, membership, …) | yes | What a tenant buys, and what a screen belongs to.
AiService | listAiConversations | response | items[].locale | string
AiService | listAiConversations | response | items[].messageCount | integer
AiService | listAiConversations | response | items[].startedAt | string (date-time) | yes
AiService | listAiConversations | response | items[].lastMessageAt | string (date-time)
AiService | listAiConversations | response | nextCursor | string
AiService | listAiConversations | response | hasMore | boolean | yes
AiService | listAiConversations | param (query) | pageSize | integer
AiService | listAiConversations | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
AiService | listAiEvaluations | response | items | array of AiEvaluationRun | yes
AiService | listAiEvaluations | response | items[].id | string (uuid) |  | (read-only)
AiService | listAiEvaluations | response | items[].suiteId | string (uuid) | yes
AiService | listAiEvaluations | response | items[].releaseId | string (uuid) |  | (nullable)
AiService | listAiEvaluations | response | items[].kind | enum (offline, backtest, shadow) | yes
AiService | listAiEvaluations | response | items[].candidateRef | string
AiService | listAiEvaluations | response | items[].baselineRef | string |  | (nullable)
AiService | listAiEvaluations | response | items[].status | enum (queued, running, passed, failed, error) | yes | (read-only)
AiService | listAiEvaluations | response | items[].metrics | object |  | (read-only; nullable)
AiService | listAiEvaluations | response | items[].gate | object |  | The promotion gate thresholds (design 3.5 table) and whether each passed. (read-only; nullable)
AiService | listAiEvaluations | response | items[].isolationCasesPassed | boolean |  | False blocks release, whatever the other metrics say. (read-only)
AiService | listAiEvaluations | response | items[].requestedByPrincipalId | string (uuid) |  | (read-only; nullable)
AiService | listAiEvaluations | response | items[].startedAt | string (date-time) |  | (read-only)
AiService | listAiEvaluations | response | items[].completedAt | string (date-time) |  | (read-only; nullable)
AiService | listAiEvaluations | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | listAiEvaluations | response | nextCursor | string
AiService | listAiEvaluations | response | hasMore | boolean | yes
AiService | listAiEvaluations | param (query) | releaseId | string (uuid)
AiService | listAiEvaluations | param (query) | capabilityKey | string
AiService | listAiEvaluations | param (query) | status | enum (queued, running, passed, failed, error)
AiService | listAiEvaluations | param (query) | pageSize | integer
AiService | listAiEvaluations | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
AiService | listAiGovernanceAlerts | response | items | array of AiGovernanceAlert | yes
AiService | listAiGovernanceAlerts | response | items[].id | string (uuid) |  | (read-only)
AiService | listAiGovernanceAlerts | response | items[].kind | enum (policyViolation, crossScopeAttempt, maskingDefect, dataUsage, behaviourDrift, inputDrift, bias, overrideRateShift, …) | yes
AiService | listAiGovernanceAlerts | response | items[].severity | enum (info, low, medium, high, critical) | yes
AiService | listAiGovernanceAlerts | response | items[].capabilityKey | string |  | (nullable)
AiService | listAiGovernanceAlerts | response | items[].releaseId | string (uuid) |  | For promotionReady and evaluationRegression: the release concerned. (nullable)
AiService | listAiGovernanceAlerts | response | items[].subjectRef | string |  | (nullable)
AiService | listAiGovernanceAlerts | response | items[].evidence | object |  | (nullable)
AiService | listAiGovernanceAlerts | response | items[].status | enum (open, acknowledged, dismissed, resolved, incidentOpened) | yes | (read-only)
AiService | listAiGovernanceAlerts | response | items[].incidentId | string (uuid) |  | (read-only; nullable)
AiService | listAiGovernanceAlerts | response | items[].raisedAt | string (date-time) |  | (read-only)
AiService | listAiGovernanceAlerts | response | items[].decidedByPrincipalId | string (uuid) |  | (read-only; nullable)
AiService | listAiGovernanceAlerts | response | items[].decidedAt | string (date-time) |  | (read-only; nullable)
AiService | listAiGovernanceAlerts | response | items[].note | string |  | (read-only; nullable)
AiService | listAiGovernanceAlerts | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | listAiGovernanceAlerts | response | nextCursor | string
AiService | listAiGovernanceAlerts | response | hasMore | boolean | yes
AiService | listAiGovernanceAlerts | param (query) | kind | enum (policyViolation, crossScopeAttempt, maskingDefect, dataUsage, behaviourDrift, inputDrift, bias, overrideRateShift, …)
AiService | listAiGovernanceAlerts | param (query) | status | enum (open, acknowledged, dismissed, resolved, incidentOpened)
AiService | listAiGovernanceAlerts | param (query) | severity | enum (info, low, medium, high, critical)
AiService | listAiGovernanceAlerts | param (query) | pageSize | integer
AiService | listAiGovernanceAlerts | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
AiService | listAiGovernancePolicyVersions | response | items | array of AiGovernancePolicyVersion | yes
AiService | listAiGovernancePolicyVersions | response | items[].id | string (uuid) |  | (read-only)
AiService | listAiGovernancePolicyVersions | response | items[].policyId | string (uuid) | yes
AiService | listAiGovernancePolicyVersions | response | items[].version | integer | yes | (min 1)
AiService | listAiGovernancePolicyVersions | response | items[].status | enum (draft, simulated, published, superseded) | yes
AiService | listAiGovernancePolicyVersions | response | items[].rules | array of AiGovernanceRule |  | The rules of one policy version, stored with the version as one jsonb column.
AiService | listAiGovernancePolicyVersions | response | items[].rules[].effect | AiGovernanceOutcome: enum (allow, allowWithConditions, prepareOnly, approvalRequired, escalate, block) | yes | What the governance decision point returns (design 3.8, AIC-166).
AiService | listAiGovernancePolicyVersions | response | items[].rules[].capabilityKeys | array of string |  | Registered capabilities it applies to.
AiService | listAiGovernancePolicyVersions | response | items[].rules[].actions | array of enum (read, analyze, recommend, generate, prepare, create, modify, publish, …) |  | ADM-523: what AI may do, from reading to executing.
AiService | listAiGovernancePolicyVersions | response | items[].rules[].dataCategories | array of string |  | Data categories (ADM-524), e.g.
AiService | listAiGovernancePolicyVersions | response | items[].rules[].purposes | array of string |  | Permitted purposes for those categories (AIC-156, AIR-182).
AiService | listAiGovernancePolicyVersions | response | items[].rules[].maxAmount | object |  | Above this value the effect escalates one step (for example to approvalRequired). (nullable)
AiService | listAiGovernancePolicyVersions | response | items[].rules[].roleIds | array of string (uuid) |  | Roles the rule applies to; empty means every role.
AiService | listAiGovernancePolicyVersions | response | items[].rules[].environments | array of enum (development, sandbox, staging, production) |  | ADM-525.
AiService | listAiGovernancePolicyVersions | response | items[].rules[].conditions | object |  | Conditions attached to an allowWithConditions effect, for example maskFields or requireCitation. (nullable)
AiService | listAiGovernancePolicyVersions | response | items[].changeNote | string |  | (nullable)
AiService | listAiGovernancePolicyVersions | response | items[].simulationSummary | object |  | The last simulateAiGovernancePolicy result: decisions that would change, by outcome. (read-only; nullable)
AiService | listAiGovernancePolicyVersions | response | items[].draftedByPrincipalId | string (uuid) |  | (read-only)
AiService | listAiGovernancePolicyVersions | response | items[].publishedByPrincipalId | string (uuid) |  | (read-only; nullable)
AiService | listAiGovernancePolicyVersions | response | items[].publishedAt | string (date-time) |  | (read-only; nullable)
AiService | listAiGovernancePolicyVersions | response | items[].supersededAt | string (date-time) |  | (read-only; nullable)
AiService | listAiGovernancePolicyVersions | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | listAiGovernancePolicyVersions | response | nextCursor | string
AiService | listAiGovernancePolicyVersions | response | hasMore | boolean | yes
AiService | listAiGovernancePolicyVersions | param (query) | policyId | string (uuid)
AiService | listAiGovernancePolicyVersions | param (query) | status | enum (draft, simulated, published, superseded)
AiService | listAiGovernancePolicyVersions | param (query) | kind | enum (action, data, scope, autonomy, approval, environment)
AiService | listAiGovernancePolicyVersions | param (query) | pageSize | integer
AiService | listAiGovernancePolicyVersions | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
AiService | listAiIncidents | response | items | array of AiIncident | yes
AiService | listAiIncidents | response | items[].id | string (uuid) |  | (read-only)
AiService | listAiIncidents | response | items[].reference | string | yes | (read-only)
AiService | listAiIncidents | response | items[].title | string | yes
AiService | listAiIncidents | response | items[].kind | enum (governance, operational, both)
AiService | listAiIncidents | response | items[].severity | enum (low, medium, high, critical) | yes
AiService | listAiIncidents | response | items[].status | enum (open, contained, investigating, remediating, closed) | yes | (read-only)
AiService | listAiIncidents | response | items[].capabilityKeys | array of string
AiService | listAiIncidents | response | items[].alertIds | array of string (uuid)
AiService | listAiIncidents | response | items[].operationalIncidentRef | string |  | The linked operational incident, where both apply (AIC-250). (nullable)
AiService | listAiIncidents | response | items[].containment | array of object |  | (read-only)
AiService | listAiIncidents | response | items[].containment[].action | string
AiService | listAiIncidents | response | items[].containment[].targetRef | string
AiService | listAiIncidents | response | items[].containment[].at | string (date-time)
AiService | listAiIncidents | response | items[].containment[].byPrincipalId | string (uuid)
AiService | listAiIncidents | response | items[].rootCause | string |  | (nullable)
AiService | listAiIncidents | response | items[].remediation | string |  | (nullable)
AiService | listAiIncidents | response | items[].impact | string |  | The post-incident review's impact (closeAiIncident, CHG-CSA-045). (nullable)
AiService | listAiIncidents | response | items[].controlFailure | string |  | (nullable)
AiService | listAiIncidents | response | items[].lessonsLearned | string |  | (nullable)
AiService | listAiIncidents | response | items[].ownerPrincipalId | string (uuid) |  | (nullable)
AiService | listAiIncidents | response | items[].openedAt | string (date-time) |  | (read-only)
AiService | listAiIncidents | response | items[].containedAt | string (date-time) |  | (read-only; nullable)
AiService | listAiIncidents | response | items[].closedAt | string (date-time) |  | (read-only; nullable)
AiService | listAiIncidents | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | listAiIncidents | response | nextCursor | string
AiService | listAiIncidents | response | hasMore | boolean | yes
AiService | listAiIncidents | param (query) | status | enum (open, contained, investigating, remediating, closed)
AiService | listAiIncidents | param (query) | severity | enum (low, medium, high, critical)
AiService | listAiIncidents | param (query) | pageSize | integer
AiService | listAiIncidents | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
AiService | listAiTrainingRuns | response | items | array of AiTrainingRun | yes
AiService | listAiTrainingRuns | response | items[].id | string (uuid) |  | (read-only)
AiService | listAiTrainingRuns | response | items[].capabilityKey | string | yes
AiService | listAiTrainingRuns | response | items[].suggestionKind | object |  | (nullable)
AiService | listAiTrainingRuns | response | items[].forecastDefinitionKey | string |  | (nullable)
AiService | listAiTrainingRuns | response | items[].trainingWindowFrom | string (date)
AiService | listAiTrainingRuns | response | items[].trainingWindowTo | string (date)
AiService | listAiTrainingRuns | response | items[].dataCutoffAt | string (date-time)
AiService | listAiTrainingRuns | response | items[].includesImportedHistory | boolean |  | (default False)
AiService | listAiTrainingRuns | response | items[].featureSetVersion | string
AiService | listAiTrainingRuns | response | items[].artefactRef | string |  | The model file in the tenant's Blob container. (nullable)
AiService | listAiTrainingRuns | response | items[].backtestRunId | string (uuid) |  | (nullable)
AiService | listAiTrainingRuns | response | items[].releaseId | string (uuid) |  | (nullable)
AiService | listAiTrainingRuns | response | items[].status | enum (queued, training, backtesting, shadow, gatePassed, gateFailed, failed) | yes
AiService | listAiTrainingRuns | response | items[].metrics | object |  | (nullable)
AiService | listAiTrainingRuns | response | items[].startedAt | string (date-time)
AiService | listAiTrainingRuns | response | items[].completedAt | string (date-time) |  | (nullable)
AiService | listAiTrainingRuns | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | listAiTrainingRuns | response | nextCursor | string
AiService | listAiTrainingRuns | response | hasMore | boolean | yes
AiService | listAiTrainingRuns | param (query) | capabilityKey | string
AiService | listAiTrainingRuns | param (query) | status | enum (queued, training, backtesting, shadow, gatePassed, gateFailed, failed)
AiService | listAiTrainingRuns | param (query) | pageSize | integer
AiService | listAiTrainingRuns | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
ReportingService | listAlerts | param (query) | status | AlertStatus: enum (raised, acknowledged, resolved, expired) |  | Defaults to open alerts (decided 28 September, audit R158): with no status the list holds raised and acknowledged alerts, never resolved or expired ones.
ReportingService | listAlerts | param (query) | severity | AlertSeverity: enum (info, warning, critical)
ReportingService | listAlerts | param (query) | workstationId | string (uuid) |  | Only alerts raised for this workstation.
ReportingService | listAlerts | param (query) | shiftId | string (uuid) |  | Only alerts raised during this till shift.
ReportingService | listAlerts | param (query) | itemId | string (uuid) |  | Only alerts raised about this inventory item.
CatalogueService | listAlternativeCodes | param (path) | productId | string (uuid) | yes
WhiteLabelService | listAnalyticsProviders | response | items | array of StorefrontAnalyticsProvider | yes
WhiteLabelService | listAnalyticsProviders | response | items[].id | string (uuid) |  | (read-only)
WhiteLabelService | listAnalyticsProviders | response | items[].venueId | string (uuid) |  | (nullable)
WhiteLabelService | listAnalyticsProviders | response | items[].provider | enum (googleAnalytics4, googleTagManager, adobeAnalytics, metaPixel, matomo, other) | yes
WhiteLabelService | listAnalyticsProviders | response | items[].providerLabel | string |  | The name, when provider is other. (max length 100; nullable)
WhiteLabelService | listAnalyticsProviders | response | items[].measurementId | string | yes | What the tag or SDK reports to (GA4 G-..., Tag Manager GTM-..., a pixel id). (max length 100)
WhiteLabelService | listAnalyticsProviders | response | items[].surfaces | array of enum (guestWeb, guestApp) | yes | (min items 1)
WhiteLabelService | listAnalyticsProviders | response | items[].consentCategory | enum (functional, analytics, personalisation, marketing) | yes | The cookie category the visitor must grant before this provider loads (marketing-crm CookieCategory). (default analytics)
WhiteLabelService | listAnalyticsProviders | response | items[].isEnabled | boolean | yes | (default True)
WhiteLabelService | listAnalyticsProviders | response | items[].reportingPropertyId | string |  | The property getStorefrontInsights asks the reporting API about (a GA4 property id). (max length 100; nullable)
WhiteLabelService | listAnalyticsProviders | response | items[].reportingCredentialRef | string |  | The vault reference of the reporting credential. (max length 200; nullable)
WhiteLabelService | listAnalyticsProviders | response | items[].hasReportingCredential | boolean |  | Whether a reporting credential is held, since the reference itself is never returned. (read-only)
WhiteLabelService | listAnalyticsProviders | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | listAnalyticsProviders | response | items[].updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | listAnalyticsProviders | response | nextCursor | string
WhiteLabelService | listAnalyticsProviders | response | hasMore | boolean | yes
WhiteLabelService | listAnalyticsProviders | param (query) | venueId | string (uuid) |  | Staff, the rows of this venue only; guest, the venue being browsed, so its rows win over the tenant's
WhiteLabelService | listAnalyticsProviders | param (query) | pageSize | integer
WhiteLabelService | listAnalyticsProviders | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
WhiteLabelService | listAppBuilds | response | items | array of AppBuild | yes
WhiteLabelService | listAppBuilds | response | items[].id | string (uuid) | yes | (read-only)
WhiteLabelService | listAppBuilds | response | items[].platform | enum (ios, android) | yes
WhiteLabelService | listAppBuilds | response | items[].configVersion | string | yes | The ConfigVersion.version built.
WhiteLabelService | listAppBuilds | response | items[].storeAccountId | string (uuid) |  | (read-only)
WhiteLabelService | listAppBuilds | response | items[].versionName | string |  | The marketing version, e.g. (read-only)
WhiteLabelService | listAppBuilds | response | items[].buildNumber | integer |  | (read-only)
WhiteLabelService | listAppBuilds | response | items[].status | enum (queued, building, built, failed, submitted, inReview, approved, rejected, …) | yes | queued to built or failed is the build service's; from submitted on it is read from the store with the client's credential, or stays built when the client uploads by hand. (read-only)
WhiteLabelService | listAppBuilds | response | items[].failureReason | string |  | (read-only; nullable)
WhiteLabelService | listAppBuilds | response | items[].packageAssetRef | string (uuid) |  | The signed .ipa or .aab in the assets library, for the client to download and upload. (read-only; nullable)
WhiteLabelService | listAppBuilds | response | items[].releaseNotes | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | listAppBuilds | response | items[].submitToStore | boolean |  | (default False)
WhiteLabelService | listAppBuilds | response | items[].requestedAt | string (date-time) | yes | (read-only)
WhiteLabelService | listAppBuilds | response | items[].requestedByPrincipalId | string (uuid) |  | (read-only)
WhiteLabelService | listAppBuilds | response | items[].finishedAt | string (date-time) |  | (read-only; nullable)
WhiteLabelService | listAppBuilds | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | listAppBuilds | response | nextCursor | string
WhiteLabelService | listAppBuilds | response | hasMore | boolean | yes
WhiteLabelService | listAppBuilds | param (query) | platform | enum (ios, android)
WhiteLabelService | listAppBuilds | param (query) | pageSize | integer
WhiteLabelService | listAppBuilds | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
TenancyService | listApprovalRequests | response | items | array of ApprovalRequest | yes
TenancyService | listApprovalRequests | response | items[].id | string | yes
TenancyService | listApprovalRequests | response | items[].kind | ApprovalKind: enum (refund, priceOverride, discountOverride, complimentaryTicket, membershipCancellation, accessPermissionChange, configurationChange, aiRecommendation, …) | yes | 11.1.7 and 11.1.30–11.1.37.
TenancyService | listApprovalRequests | response | items[].rerouteOnNoApprover | boolean |  | BL-154. (default True)
TenancyService | listApprovalRequests | response | items[].outOfOfficeDelegateId | string (uuid) |  | (nullable)
TenancyService | listApprovalRequests | response | items[].allowEmailApproval | boolean |  | Approving from an email link with no second factor is the weakest path in the system, so it is off by default and available only below a configured value. (default False)
TenancyService | listApprovalRequests | response | items[].reopenedFrom | string (uuid) |  | Reopening a decided approval creates a new one that points back. (nullable)
TenancyService | listApprovalRequests | response | items[].status | ApprovalStatus: enum (draft, pending, escalated, returned, informationRequested, approved, rejected, withdrawn, …) | yes
TenancyService | listApprovalRequests | response | items[].subjectContract | string
TenancyService | listApprovalRequests | response | items[].subjectType | string
TenancyService | listApprovalRequests | response | items[].subjectId | string
TenancyService | listApprovalRequests | response | items[].scopePath | string
TenancyService | listApprovalRequests | response | items[].summary | string
TenancyService | listApprovalRequests | response | items[].amount | Money |  | On the wire this is three fields; in the database it is one column.
TenancyService | listApprovalRequests | response | items[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | listApprovalRequests | response | items[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | listApprovalRequests | response | items[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | listApprovalRequests | response | items[].justification | string |  | (nullable)
TenancyService | listApprovalRequests | response | items[].requestedByPrincipalId | string (uuid) | yes
TenancyService | listApprovalRequests | response | items[].matrixVersion | integer
TenancyService | listApprovalRequests | response | items[].mode | ApprovalMode: enum (sequential, parallel, consensus, majority) |  | 11.1.43–11.1.46.
TenancyService | listApprovalRequests | response | items[].currentLevel | integer
TenancyService | listApprovalRequests | response | items[].totalLevels | integer
TenancyService | listApprovalRequests | response | items[].pendingApprovers | array of object
TenancyService | listApprovalRequests | response | items[].pendingApprovers[].principalId | string (uuid)
TenancyService | listApprovalRequests | response | items[].pendingApprovers[].displayName | string
TenancyService | listApprovalRequests | response | items[].pendingApprovers[].isDelegate | boolean
TenancyService | listApprovalRequests | response | items[].decisions | array of ApprovalDecision |  | Every decision at every level, in order.
TenancyService | listApprovalRequests | response | items[].decisions[].id | string (uuid) |  | Added 20 August. (read-only)
TenancyService | listApprovalRequests | response | items[].decisions[].level | integer | yes
TenancyService | listApprovalRequests | response | items[].decisions[].principalId | string (uuid) | yes
TenancyService | listApprovalRequests | response | items[].decisions[].displayName | string
TenancyService | listApprovalRequests | response | items[].decisions[].isDelegate | boolean
TenancyService | listApprovalRequests | response | items[].decisions[].delegatedFrom | string (uuid) |  | (nullable)
TenancyService | listApprovalRequests | response | items[].decisions[].decision | enum (approve, reject) | yes
TenancyService | listApprovalRequests | response | items[].decisions[].comment | string |  | (nullable)
TenancyService | listApprovalRequests | response | items[].decisions[].reason | string |  | (nullable)
TenancyService | listApprovalRequests | response | items[].decisions[].usedMfa | boolean
TenancyService | listApprovalRequests | response | items[].decisions[].signatureRef | string |  | (nullable)
TenancyService | listApprovalRequests | response | items[].decisions[].decidedAt | string (date-time) | yes
TenancyService | listApprovalRequests | response | items[].escalations | array of object |  | 11.1.48.
TenancyService | listApprovalRequests | response | items[].escalations[].at | string (date-time)
TenancyService | listApprovalRequests | response | items[].escalations[].reason | string
TenancyService | listApprovalRequests | response | items[].escalations[].fromLevel | integer
TenancyService | listApprovalRequests | response | items[].escalations[].toLevel | integer
TenancyService | listApprovalRequests | response | items[].escalations[].wasAutomatic | boolean
TenancyService | listApprovalRequests | response | items[].resubmittedFromId | string |  | (nullable)
TenancyService | listApprovalRequests | response | items[].reopenedFromId | string |  | (nullable)
TenancyService | listApprovalRequests | response | items[].slaDueAt | string (date-time) |  | (nullable)
TenancyService | listApprovalRequests | response | items[].slaBreached | boolean
TenancyService | listApprovalRequests | response | items[].expiresAt | string (date-time) |  | (nullable)
TenancyService | listApprovalRequests | response | items[].assignedToPrincipalId | string (uuid) |  | Who claimed or was assigned the request in a shared queue (assignApprovalRequest; DI-723; CHG-CSP-042). (read-only; nullable)
TenancyService | listApprovalRequests | response | items[].assignedToDepartmentId | string (uuid) |  | The department queue it was assigned to, where it went to a department rather than a person (CHG-CSP-042). (read-only; nullable)
TenancyService | listApprovalRequests | response | items[].assignedAt | string (date-time) |  | (read-only; nullable)
TenancyService | listApprovalRequests | response | items[].requestedAt | string (date-time) | yes
TenancyService | listApprovalRequests | response | items[].completedAt | string (date-time) |  | (nullable)
TenancyService | listApprovalRequests | response | items[].aiAssessment | object |  | AI context for the reviewer, never an input to the decision (11.1.73 to 11.1.75; MoM 8 September; 29 September, build pass, group G2). (read-only; nullable)
TenancyService | listApprovalRequests | response | items[].aiAssessment.riskScore | integer |  | (min 0; max 100)
TenancyService | listApprovalRequests | response | items[].aiAssessment.riskBand | enum (low, medium, high, critical)
TenancyService | listApprovalRequests | response | items[].aiAssessment.priorityScore | integer |  | (min 0; max 100)
TenancyService | listApprovalRequests | response | items[].aiAssessment.escalationSuggestion | object |  | A suggestion a person may act on through escalateApprovalRequest, or the tenant's own SLA policy may; nothing escalates because of it.
TenancyService | listApprovalRequests | response | items[].aiAssessment.signals | array of object |  | The signals behind the scores, largest first, as ai.AiApprovalRequestScore.signals. (max items 10)
TenancyService | listApprovalRequests | response | items[].aiAssessment.scoreId | string (uuid) |  | The ai.approval_request_score row it was copied from; ai.getApprovalRequestScore gives the full context.
TenancyService | listApprovalRequests | response | items[].aiAssessment.decisionRecordId | string |  | The ai decision record, for the audit of what the AI said and why.
TenancyService | listApprovalRequests | response | items[].aiAssessment.assessedAt | string (date-time)
TenancyService | listApprovalRequests | response | nextCursor | string
TenancyService | listApprovalRequests | response | hasMore | boolean | yes
TenancyService | listApprovalRequests | param (query) | assignedToMe | boolean
TenancyService | listApprovalRequests | param (query) | raisedByMe | boolean
TenancyService | listApprovalRequests | param (query) | status | ApprovalStatus: enum (draft, pending, escalated, returned, informationRequested, approved, rejected, withdrawn, …)
TenancyService | listApprovalRequests | param (query) | kind | ApprovalKind: enum (refund, priceOverride, discountOverride, complimentaryTicket, membershipCancellation, accessPermissionChange, configurationChange, aiRecommendation, …)
TenancyService | listApprovalRequests | param (query) | breachingWithinMinutes | integer |  | 11.1.15.
TenancyService | listApprovalRequests | param (query) | sort | enum (slaProximity, aiPriority) |  | slaProximity (the default, as before) or aiPriority: highest aiAssessment.priorityScore first, requests with no assessment after them in SLA order (29 September, build pass, group G2; 11.1.74).
TenancyService | listApprovalRequests | param (query) | pageSize | integer
TenancyService | listApprovalRequests | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
WhiteLabelService | listBanners | response | items | array of Banner | yes
WhiteLabelService | listBanners | response | items[].id | string (uuid) | yes | (read-only)
WhiteLabelService | listBanners | response | items[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | listBanners | response | items[].subtitle | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | listBanners | response | items[].imageAssetRef | string (uuid) | yes
WhiteLabelService | listBanners | response | items[].placement | enum (homepageHero, homepageBlock, explore, checkout)
WhiteLabelService | listBanners | response | items[].linkTarget | LinkTarget
WhiteLabelService | listBanners | response | items[].linkTarget.kind | enum (module, contentPage, product, event, externalUrl, appSection, none) | yes | appSection points at a section of the guest mobile app (decided 29 September, MOB-1), so the bottom navigation can hold Home, Explore, Plan and Tickets.
WhiteLabelService | listBanners | response | items[].linkTarget.moduleKey | ModuleKey: enum (ticketsAndBooking, membership, events, attractions, virtualQueue, diningAndFnb, shop, parking, …) |  | visitPlanner (decided 29 September, MOB-1 and the Plan tab in Block A) is the Plan tab and WEB-050; off, the tab and the page are not shown.
WhiteLabelService | listBanners | response | items[].linkTarget.appSection | enum (home, explore, plan, tickets, map, account, buyTickets) |  | Required when kind is appSection.
WhiteLabelService | listBanners | response | items[].linkTarget.contentPageId | string (uuid)
WhiteLabelService | listBanners | response | items[].linkTarget.productId | string (uuid)
WhiteLabelService | listBanners | response | items[].linkTarget.eventId | string (uuid)
WhiteLabelService | listBanners | response | items[].linkTarget.url | string
WhiteLabelService | listBanners | response | items[].startsAt | string (date-time) | yes
WhiteLabelService | listBanners | response | items[].endsAt | string (date-time) |  | Must follow startsAt when set (decided 28 September, audit R163). (nullable)
WhiteLabelService | listBanners | response | items[].state | object |  | Moved by updateBanner between draft and scheduled, and by the schedule timer from scheduled to active and active to expired at startsAt and endsAt, in the tenant's timezone (states/schedule.yaml). (read-only)
WhiteLabelService | listBanners | response | items[].sortOrder | integer
WhiteLabelService | listBanners | response | items[].isActive | boolean
WhiteLabelService | listBanners | response | nextCursor | string
WhiteLabelService | listBanners | response | hasMore | boolean | yes
WhiteLabelService | listBanners | param (query) | state | ScheduleState: enum (draft, scheduled, active, expired)
WhiteLabelService | listBanners | param (query) | pageSize | integer
WhiteLabelService | listBanners | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
OrderService | listBillingStatements | response | items | array of BillingStatement | yes
OrderService | listBillingStatements | response | items[].id | string (uuid) | yes
OrderService | listBillingStatements | response | items[].subjectId | string (uuid) |  | (read-only)
OrderService | listBillingStatements | response | items[].periodStart | string (date) | yes
OrderService | listBillingStatements | response | items[].periodEnd | string (date) | yes
OrderService | listBillingStatements | response | items[].lines | array of BillingStatementLine
OrderService | listBillingStatements | response | items[].lines[].occurredAt | string (date-time) | yes
OrderService | listBillingStatements | response | items[].lines[].kind | enum (charge, refund, failedAttempt, adjustment) | yes
OrderService | listBillingStatements | response | items[].lines[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listBillingStatements | response | items[].lines[].description | string
OrderService | listBillingStatements | response | items[].lines[].netAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listBillingStatements | response | items[].lines[].discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listBillingStatements | response | items[].lines[].taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listBillingStatements | response | items[].lines[].taxRate | number |  | 2.14.23. (nullable)
OrderService | listBillingStatements | response | items[].lines[].taxInvoiceId | string (uuid) |  | The finance tax invoice issued for this charge, where one was (issueTaxInvoice); the guest downloads it with getTaxDocumentRendition. (nullable)
OrderService | listBillingStatements | response | items[].lines[].declineClass | string |  | Present on failedAttempt only, and it is what turns *"your payment failed"* into something a guest can act on: a soft decline means try again, a hard one means the card needs replacing. (nullable)
OrderService | listBillingStatements | response | items[].total | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listBillingStatements | response | items[].total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listBillingStatements | response | items[].total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listBillingStatements | response | items[].total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listBillingStatements | response | items[].taxTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listBillingStatements | response | items[].taxTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listBillingStatements | response | items[].taxTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listBillingStatements | response | items[].taxTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listBillingStatements | response | items[].discountTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listBillingStatements | response | items[].discountTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listBillingStatements | response | items[].discountTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listBillingStatements | response | items[].discountTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listBillingStatements | response | items[].pdfUrl | string (uri) |  | Set when getBillingStatement is called with format=pdf; a short-lived link. (read-only; nullable)
OrderService | listBillingStatements | response | items[].isTaxInvoice | boolean | yes | Always false, and stated rather than assumed. (default False; read-only)
OrderService | listBillingStatements | response | nextCursor | string
OrderService | listBillingStatements | response | hasMore | boolean | yes
OrderService | listBillingStatements | param (query) | from | string (date) |  | Only statements whose periodEnd is on or after this date.
OrderService | listBillingStatements | param (query) | to | string (date) |  | Only statements whose periodStart is on or before this date.
OrderService | listBillingStatements | param (query) | pageSize | integer
OrderService | listBillingStatements | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
FnbService | listBookableOutlets | response | items | array of BookableOutlet | yes
FnbService | listBookableOutlets | response | items[].outletId | string (uuid) | yes
FnbService | listBookableOutlets | response | items[].venueId | string (uuid) | yes
FnbService | listBookableOutlets | response | items[].name | string | yes
FnbService | listBookableOutlets | response | items[].kind | string |  | (nullable)
FnbService | listBookableOutlets | response | items[].cuisine | array of string
FnbService | listBookableOutlets | response | items[].zone | string |  | (nullable)
FnbService | listBookableOutlets | response | items[].imageAssetRef | string |  | (nullable)
FnbService | listBookableOutlets | response | items[].depositMayApply | boolean |  | The venue's orders.DepositPolicy.dining is on, so a booking from its party size takes a deposit (rev 3 REV3-8b).
FnbService | listBookableOutlets | response | items[].waitlistOpen | boolean |  | The outlet takes walk-in waitlist places today (joinRestaurantWaitlist).
FnbService | listBookableOutlets | response | nextCursor | string
FnbService | listBookableOutlets | response | hasMore | boolean | yes
FnbService | listBookableOutlets | param (path) | venueId | string (uuid) | yes
FnbService | listBookableOutlets | param (query) | date | string (date) |  | Only outlets open on this calendar day (the region's time zone).
FnbService | listBookableOutlets | param (query) | pageSize | integer
FnbService | listBookableOutlets | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
VenueOpsService | listBookableVenueMaps | response | venueId | string (uuid) | yes
VenueOpsService | listBookableVenueMaps | response | maps | array of BookableVenueMapRef | yes | (max items 50)
VenueOpsService | listBookableVenueMaps | response | maps[].mapId | string (uuid) | yes
VenueOpsService | listBookableVenueMaps | response | maps[].name | string | yes
VenueOpsService | listBookableVenueMaps | response | maps[].kind | enum (park, floor, zone, parking) | yes
VenueOpsService | listBookableVenueMaps | response | maps[].floorLevel | integer |  | (nullable)
VenueOpsService | listBookableVenueMaps | response | maps[].publishedVersion | integer | yes | The VenueMap.publishedVersion a guest is served; send it to getVenueMap as version.
VenueOpsService | listBookableVenueMaps | response | maps[].placedResourceCount | integer | yes | Placed resources on the published version. (min 1)
VenueOpsService | listBookableVenueMaps | response | maps[].kinds | array of enum (cabana, lounger, table, pitch, other) |  | The kinds of spot on this map, e.g.
VenueOpsService | listBookableVenueMaps | param (query) | venueId | string (uuid) | yes | The venue whose bookable maps are wanted.
VenueOpsService | listBookableVenueMaps | param (query) | productId | string (uuid) |  | Only maps with a placed resource sold by this product's price-band variants.
VenueOpsService | listBookableVenueMaps | param (query) | kind | enum (cabana, lounger, table, pitch, other) |  | Only maps carrying at least one placed resource of this kind (PlacedResource.kind).
WhiteLabelService | listBookingFlowTypes | response | items | array of BookingFlowType | yes
WhiteLabelService | listBookingFlowTypes | response | items[].key | BookingFlowTypeKey: enum (datedDayPass, timedEntry, openDated, seatedFixedPerformance, seatedDateTimeSeatMap, experienceWorkshop, surfSession, meetingRoomHourly, …) | yes | The flow types the system catalogue offers (decided 29 September, W12; impact.md b).
WhiteLabelService | listBookingFlowTypes | response | items[].name | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | listBookingFlowTypes | response | items[].description | LocalisedText |  | Keyed by ISO 639-1 code.
WhiteLabelService | listBookingFlowTypes | response | items[].productKinds | array of string | yes | The catalogue ProductKind values this type books.
WhiteLabelService | listBookingFlowTypes | response | items[].steps | array of object | yes | In the type's default order.
WhiteLabelService | listBookingFlowTypes | response | items[].steps[].stepKey | BookingFlowStepKey: enum (location, helpMeChoose, product, date, time, performance, level, language, …) | yes | Every step a guest booking flow can hold (decided 29 September, W12).
WhiteLabelService | listBookingFlowTypes | response | items[].steps[].requirement | enum (required, optional, conditional) | yes
WhiteLabelService | listBookingFlowTypes | response | items[].steps[].condition | object |  | For conditional, when a guest meets the step. (nullable)
WhiteLabelService | listBookingFlowTypes | response | items[].steps[].defaultEnabled | boolean |  | (default True)
WhiteLabelService | listBookingFlowTypes | response | items[].steps[].defaultSortOrder | integer | yes | (min 0)
WhiteLabelService | listBookingFlowTypes | response | items[].steps[].settingsOwned | array of string |  | Names of BookingFlowSettings (venue-wide) or BookingFlowLevelSettings (this flow) fields shown beside the step.
WhiteLabelService | listBookingFlowTypes | response | items[].steps[].stepSettings | array of object |  | The step's own settings, kept in BookingFlowStep.settings.
WhiteLabelService | listBookingFlowTypes | response | items[].orderConstraints | array of object | yes | first and last pin a step; before puts stepKey somewhere ahead of otherStepKey.
WhiteLabelService | listBookingFlowTypes | response | items[].orderConstraints[].kind | enum (first, last, before) | yes
WhiteLabelService | listBookingFlowTypes | response | items[].orderConstraints[].stepKey | BookingFlowStepKey: enum (location, helpMeChoose, product, date, time, performance, level, language, …) | yes | Every step a guest booking flow can hold (decided 29 September, W12).
WhiteLabelService | listBookingFlowTypes | response | items[].orderConstraints[].otherStepKey | object |  | Required when kind is before. (nullable)
WhiteLabelService | listBookingFlowTypes | response | nextCursor | string
WhiteLabelService | listBookingFlowTypes | response | hasMore | boolean | yes
WhiteLabelService | listBookingFlowTypes | param (query) | productKind | string |  | Only the types that serve this catalogue product kind.
WhiteLabelService | listBookingFlowTypes | param (query) | pageSize | integer
WhiteLabelService | listBookingFlowTypes | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
WhiteLabelService | listBookingFlows | response | items | array of BookingFlow | yes
WhiteLabelService | listBookingFlows | response | items[].id | string (uuid) |  | (read-only)
WhiteLabelService | listBookingFlows | response | items[].venueId | string (uuid) |  | From the path of createBookingFlowDefinition. (read-only)
WhiteLabelService | listBookingFlows | response | items[].flowTypeKey | BookingFlowTypeKey: enum (datedDayPass, timedEntry, openDated, seatedFixedPerformance, seatedDateTimeSeatMap, experienceWorkshop, surfSession, meetingRoomHourly, …) | yes | The flow types the system catalogue offers (decided 29 September, W12; impact.md b).
WhiteLabelService | listBookingFlows | response | items[].name | string | yes | Staff-facing, e.g. (max length 80)
WhiteLabelService | listBookingFlows | response | items[].isDefaultForType | boolean |  | At most one per venue and type; setting it takes it from the previous default. (default False)
WhiteLabelService | listBookingFlows | response | items[].isEnabled | boolean |  | A disabled flow is kept and not published; products naming it fall back to the default. (default True)
WhiteLabelService | listBookingFlows | response | items[].steps | array of BookingFlowStep |  | Every step of the type, in the venue's order. (max items 30)
WhiteLabelService | listBookingFlows | response | items[].steps[].id | string (uuid) |  | (read-only)
WhiteLabelService | listBookingFlows | response | items[].steps[].bookingFlowId | string (uuid) |  | (read-only)
WhiteLabelService | listBookingFlows | response | items[].steps[].stepKey | BookingFlowStepKey: enum (location, helpMeChoose, product, date, time, performance, level, language, …) | yes | Every step a guest booking flow can hold (decided 29 September, W12).
WhiteLabelService | listBookingFlows | response | items[].steps[].enabled | boolean | yes | A required step cannot be off; the flow saves and isValid turns false.
WhiteLabelService | listBookingFlows | response | items[].steps[].sortOrder | integer | yes | (min 0)
WhiteLabelService | listBookingFlows | response | items[].steps[].requirement | enum (required, optional, conditional) |  | From the flow type, so the CMS can mark the step without a second read. (read-only)
WhiteLabelService | listBookingFlows | response | items[].steps[].settings | object |  | The step's own settings, by the names the type's stepSettings gives for this step (e.g. (default {})
WhiteLabelService | listBookingFlows | response | items[].settings | BookingFlowLevelSettings |  | The settings that belong to one flow, not to the venue (decided 29 September, W12).
WhiteLabelService | listBookingFlows | response | items[].settings.performanceReveal | enum (dateTimeTicket, allAtOnce) |  | Performance reveal (rev 3 REV3-2). (default dateTimeTicket)
WhiteLabelService | listBookingFlows | response | items[].settings.signInAt | enum (afterAddOns, atPayment) |  | Where the guest is asked to sign in, or for a guest-checkout code (rev 3 REV3-3). (default afterAddOns)
WhiteLabelService | listBookingFlows | response | items[].settings.seatEventDateMode | enum (inlineStep, popupOnSeatMap) |  | Date and time on a seated event (rev 3 REV3-4). (default inlineStep)
WhiteLabelService | listBookingFlows | response | items[].settings.extrasStep | enum (auto, always, never) |  | auto shows the extras step only when the cart's products have add-ons; never is the same as turning the optional extras step off. (default auto)
WhiteLabelService | listBookingFlows | response | items[].settings.quickTour | boolean |  | Quick tour (rev 3 REV3-20). (default False)
WhiteLabelService | listBookingFlows | response | items[].settings.consentQuestionIds | array of string (uuid) |  | The flow's own consent questions (rev 3 REV3-26). (max items 10; default [])
WhiteLabelService | listBookingFlows | response | items[].isValid | boolean |  | Whether the flow passes validateBookingFlow; worked out in the same transaction as each write. (read-only)
WhiteLabelService | listBookingFlows | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | listBookingFlows | response | items[].updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | listBookingFlows | response | nextCursor | string
WhiteLabelService | listBookingFlows | response | hasMore | boolean | yes
WhiteLabelService | listBookingFlows | param (path) | venueId | string (uuid) | yes
WhiteLabelService | listBookingFlows | param (query) | flowTypeKey | BookingFlowTypeKey: enum (datedDayPass, timedEntry, openDated, seatedFixedPerformance, seatedDateTimeSeatMap, experienceWorkshop, surfSession, meetingRoomHourly, …)
WhiteLabelService | listBookingFlows | param (query) | pageSize | integer
WhiteLabelService | listBookingFlows | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
OrderService | listCashMovements | response | items | array of CashMovement | yes
OrderService | listCashMovements | response | items[].id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | listCashMovements | response | items[].kind | CashMovementKind: enum (openingFloat, lift, add) | yes | openingFloat is written by openShift; lift by createCashMovement and by withdrawFromDepositBox, which is a lift from one cashier's box; add by createCashMovement.
OrderService | listCashMovements | response | items[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listCashMovements | response | items[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listCashMovements | response | items[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listCashMovements | response | items[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listCashMovements | response | items[].denominations | array of CashCountLine |  | A count is a list of lines and the line is the row. (min items 1)
OrderService | listCashMovements | response | items[].denominations[].id | string (uuid)
OrderService | listCashMovements | response | items[].denominations[].shiftId | string (uuid) | yes | A UUIDv7, as Shift.id and orders.pos_shift.id are.
OrderService | listCashMovements | response | items[].denominations[].depositBoxId | string (uuid) |  | (nullable)
OrderService | listCashMovements | response | items[].denominations[].countKind | enum (openingFloat, close, movement) |  | Which count this line belongs to — the opening float (openShift), the close (closeShift) or a lift or add (createCashMovement).
OrderService | listCashMovements | response | items[].denominations[].cashMovementId | string (uuid) |  | The movement this line counts, where countKind is movement. (nullable)
OrderService | listCashMovements | response | items[].denominations[].denominationId | string (uuid) | yes | References platform.denomination — face value, kind and sort order live there.
OrderService | listCashMovements | response | items[].denominations[].countedQuantity | integer | yes | How many of this note or coin were in the drawer. (min 0)
OrderService | listCashMovements | response | items[].denominations[].countedValue | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listCashMovements | response | items[].denominations[].countedBy | string (uuid) |  | (nullable)
OrderService | listCashMovements | response | items[].denominations[].countedAt | string (date-time)
OrderService | listCashMovements | response | items[].denominations[].recountOf | string (uuid) |  | A recount points at what it replaces rather than overwriting it. (nullable)
OrderService | listCashMovements | response | items[].reference | string |  | Safe drop reference or bag number. (max length 64)
OrderService | listCashMovements | response | items[].reason | string |  | (max length 500)
OrderService | listCashMovements | response | items[].recordedAt | string (date-time) | yes
OrderService | listCashMovements | response | items[].shiftId | string (uuid) | yes
OrderService | listCashMovements | response | items[].depositBoxId | string (uuid) |  | The box the cash moved in or out of. (nullable)
OrderService | listCashMovements | response | items[].witnessPrincipalId | string (uuid) |  | The cashier who countersigned a withdrawal. (nullable)
OrderService | listCashMovements | response | items[].withdrawalReason | object |  | (nullable)
OrderService | listCashMovements | response | items[].authorisedByPrincipalId | string (uuid) | yes | The principal who authorised the movement, recorded for audit.
OrderService | listCashMovements | response | items[].sequence | integer | yes | Monotonic within the shift.
OrderService | listCashMovements | response | items[].syncedAt | string (date-time) |  | (nullable)
OrderService | listCashMovements | response | nextCursor | string
OrderService | listCashMovements | response | hasMore | boolean | yes
OrderService | listCashMovements | param (path) | shiftId | string (uuid) | yes
OrderService | listCashMovements | param (query) | pageSize | integer
OrderService | listCashMovements | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
WhiteLabelService | listConfigVersions | response | items | array of ConfigVersion | yes
WhiteLabelService | listConfigVersions | response | items[].version | string | yes
WhiteLabelService | listConfigVersions | response | items[].publishedAt | string (date-time) | yes
WhiteLabelService | listConfigVersions | response | items[].publishedByPrincipalId | string (uuid) | yes
WhiteLabelService | listConfigVersions | response | items[].publishedByName | string
WhiteLabelService | listConfigVersions | response | items[].note | string | yes
WhiteLabelService | listConfigVersions | response | items[].reviewStatus | enum (notRequired, pending, approved, rejected) |  | The review step, where the tenant's publish-review policy is on (CHG-CSA-042). (default notRequired; read-only)
WhiteLabelService | listConfigVersions | response | items[].approvalRequestId | string (uuid) |  | (read-only; nullable)
WhiteLabelService | listConfigVersions | response | items[].isCurrent | boolean | yes
WhiteLabelService | listConfigVersions | response | items[].scheduledFor | string (date-time) |  | (nullable)
WhiteLabelService | listConfigVersions | response | items[].contentHash | string
WhiteLabelService | listConfigVersions | response | items[].pendingBuildTimeChanges | array of object |  | Changes in this version that will not reach guests until the next store release.
WhiteLabelService | listConfigVersions | response | items[].pendingBuildTimeChanges[].area | string
WhiteLabelService | listConfigVersions | response | items[].pendingBuildTimeChanges[].description | string
WhiteLabelService | listConfigVersions | response | items[].pendingBuildTimeChanges[].platforms | array of enum (ios, android, web)
WhiteLabelService | listConfigVersions | response | items[].snapshot | object |  | What this version contained. (read-only)
WhiteLabelService | listConfigVersions | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | listConfigVersions | response | nextCursor | string
WhiteLabelService | listConfigVersions | response | hasMore | boolean | yes
WhiteLabelService | listConfigVersions | param (query) | pageSize | integer
WhiteLabelService | listConfigVersions | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
MarketingService | listConsentAnswers | response | items | array of BookingConsentRecord | yes
MarketingService | listConsentAnswers | response | items[].id | string (uuid) | yes | (read-only)
MarketingService | listConsentAnswers | response | items[].questionId | string (uuid) | yes
MarketingService | listConsentAnswers | response | items[].questionVersion | integer | yes | (min 1)
MarketingService | listConsentAnswers | response | items[].questionKind | ConsentQuestionKind: enum (swim, scuba, risk, custom) | yes | What the question is about (decided 29 September, rev 3 REV3-26).
MarketingService | listConsentAnswers | response | items[].answer | enum (yes, no) | yes
MarketingService | listConsentAnswers | response | items[].scope | enum (perPerson, perBooking) | yes
MarketingService | listConsentAnswers | response | items[].blocksBooking | boolean |  | The answer is the question's blockingAnswer at that version. (read-only)
MarketingService | listConsentAnswers | response | items[].cartId | string (uuid) |  | (nullable)
MarketingService | listConsentAnswers | response | items[].cartLineId | string (uuid) |  | (nullable)
MarketingService | listConsentAnswers | response | items[].orderId | string (uuid) |  | Set by orders.checkoutCart when the cart becomes an order. (read-only; nullable)
MarketingService | listConsentAnswers | response | items[].orderLineId | string (uuid) |  | (read-only; nullable)
MarketingService | listConsentAnswers | response | items[].personIndex | integer |  | (min 0; nullable)
MarketingService | listConsentAnswers | response | items[].personName | string |  | (max length 120; nullable)
MarketingService | listConsentAnswers | response | items[].personSubjectId | string (uuid) |  | (nullable)
MarketingService | listConsentAnswers | response | items[].answeredBySubjectId | string (uuid) |  | The guest who answered, from the session. (read-only; nullable)
MarketingService | listConsentAnswers | response | items[].answeredByPrincipalId | string (uuid) |  | The staff member who answered on the guest's behalf. (read-only; nullable)
MarketingService | listConsentAnswers | response | items[].source | ConsentSource: enum (guestApp, website, kiosk, pos, callCentre, import, agentRecorded, cookieBanner, …) | yes | checkout (30 September, M18-15): an opt-in ticked beside the terms at checkout, carried on orders checkoutCart marketingConsents[] and recorded by recordCheckoutConsents, bound to the order and the v…
MarketingService | listConsentAnswers | response | items[].answeredAt | string (date-time) | yes
MarketingService | listConsentAnswers | response | items[].supersededAt | string (date-time) |  | (read-only; nullable)
MarketingService | listConsentAnswers | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | listConsentAnswers | response | nextCursor | string
MarketingService | listConsentAnswers | response | hasMore | boolean | yes
MarketingService | listConsentAnswers | param (query) | orderId | string (uuid)
MarketingService | listConsentAnswers | param (query) | subjectId | string (uuid)
MarketingService | listConsentAnswers | param (query) | questionId | string (uuid)
MarketingService | listConsentAnswers | param (query) | pageSize | integer
MarketingService | listConsentAnswers | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
MarketingService | listConsentPurposes | response | items | array of ConsentPurposeConfig | yes
MarketingService | listConsentPurposes | response | items[].purpose | ConsentPurpose: enum (marketing, personalisation, profiling, thirdPartySharing, aiProcessing, transactional) | yes
MarketingService | listConsentPurposes | response | items[].displayName | string
MarketingService | listConsentPurposes | response | items[].description | string
MarketingService | listConsentPurposes | response | items[].channels | array of MessageChannel: enum (email, sms, whatsapp, push, inApp, post) | yes
MarketingService | listConsentPurposes | response | items[].noticeVersion | string | yes | Current version of the notice.
MarketingService | listConsentPurposes | response | items[].isRequiredForService | boolean | yes | True for transactional.
MarketingService | listConsentPurposes | response | items[].expiresAfterMonths | integer |  | (nullable)
MarketingService | listConsentPurposes | response | nextCursor | string
MarketingService | listConsentPurposes | response | hasMore | boolean | yes
MarketingService | listConsentPurposes | param (query) | pageSize | integer
MarketingService | listConsentPurposes | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
MarketingService | listConsentQuestions | response | items | array of ConsentQuestion | yes
MarketingService | listConsentQuestions | response | items[].id | string (uuid) | yes | (read-only)
MarketingService | listConsentQuestions | response | items[].kind | ConsentQuestionKind: enum (swim, scuba, risk, custom) | yes | What the question is about (decided 29 September, rev 3 REV3-26).
MarketingService | listConsentQuestions | response | items[].text | object | yes | The question as the guest reads it, per locale.
MarketingService | listConsentQuestions | response | items[].helpText | object |  | (nullable)
MarketingService | listConsentQuestions | response | items[].version | integer | yes | Raised by one each time the question changes (updateConsentQuestion). (min 1; read-only)
MarketingService | listConsentQuestions | response | items[].scope | enum (perPerson, perBooking) | yes | Asked for each declared person, or once for the whole booking. (default perPerson)
MarketingService | listConsentQuestions | response | items[].required | boolean | yes | Checkout waits until it is answered (orders.checkoutCart 422 consentRequired). (default True)
MarketingService | listConsentQuestions | response | items[].blockingAnswer | enum (yes, no, none) | yes | The answer that stops the booking, for the person or the booking it covers. (default none)
MarketingService | listConsentQuestions | response | items[].status | enum (active, retired) | yes | (default active)
MarketingService | listConsentQuestions | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
MarketingService | listConsentQuestions | response | items[].updatedAt | string (date-time) |  | (read-only)
MarketingService | listConsentQuestions | response | nextCursor | string
MarketingService | listConsentQuestions | response | hasMore | boolean | yes
MarketingService | listConsentQuestions | param (query) | kind | ConsentQuestionKind: enum (swim, scuba, risk, custom)
MarketingService | listConsentQuestions | param (query) | status | enum (active, retired)
MarketingService | listConsentQuestions | param (query) | pageSize | integer
MarketingService | listConsentQuestions | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
WhiteLabelService | listContentBlocks | response | items | array of ContentBlock | yes
WhiteLabelService | listContentBlocks | response | items[].id | string (uuid) | yes | (read-only)
WhiteLabelService | listContentBlocks | response | items[].pageId | string (uuid) |  | (nullable)
WhiteLabelService | listContentBlocks | response | items[].kind | enum (richText, image, video, gallery, cta, faq, form, embed, …) | yes
WhiteLabelService | listContentBlocks | response | items[].position | integer
WhiteLabelService | listContentBlocks | response | items[].body | object |  | Typed by kind, and validated against the block's own schema at save.
WhiteLabelService | listContentBlocks | response | items[].localeVariants | object |  | Per-locale bodies, not per-locale pages.
WhiteLabelService | listContentBlocks | response | items[].status | enum (draft, scheduled, published, expired, archived) | yes | Created as draft; moved by publishContentBlock and the publishAt/expireAt timer (states/content-block.yaml), never by the body of a create. (read-only)
WhiteLabelService | listContentBlocks | response | items[].publishAt | string (date-time) |  | Content scheduling, which the configuration model had no room for. (nullable)
WhiteLabelService | listContentBlocks | response | items[].expireAt | string (date-time) |  | (nullable)
WhiteLabelService | listContentBlocks | response | items[].audienceSegmentId | string (uuid) |  | Personalisation, evaluated at render. (nullable)
WhiteLabelService | listContentBlocks | response | items[].approvedByPrincipalId | string (uuid) |  | (read-only; nullable)
WhiteLabelService | listContentBlocks | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | listContentBlocks | response | nextCursor | string
WhiteLabelService | listContentBlocks | response | hasMore | boolean | yes
WhiteLabelService | listContentBlocks | param (query) | pageKey | string | yes
WhiteLabelService | listContentBlocks | param (query) | pageSize | integer
WhiteLabelService | listContentBlocks | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
WhiteLabelService | listContentPages | response | items | array of ContentPage | yes
WhiteLabelService | listContentPages | response | items[].id | string (uuid) | yes | (read-only)
WhiteLabelService | listContentPages | response | items[].slug | string | yes | (pattern ^[a-z0-9-]+$)
WhiteLabelService | listContentPages | response | items[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | listContentPages | response | items[].body | LocalisedRichText | yes | Keyed by language code.
WhiteLabelService | listContentPages | response | items[].isEnabled | boolean |  | BL-005. (default True)
WhiteLabelService | listContentPages | response | items[].status | object | yes | Created as draft, published by publishTenantConfig, archived through updateContentPage (states/content.yaml). (read-only)
WhiteLabelService | listContentPages | response | items[].iconAssetRef | string (uuid) |  | (nullable)
WhiteLabelService | listContentPages | response | items[].categoryCode | string |  | (nullable)
WhiteLabelService | listContentPages | response | items[].sortOrder | integer
WhiteLabelService | listContentPages | response | items[].isReferenced | boolean |  | True when navigation or the homepage links to this page. (read-only)
WhiteLabelService | listContentPages | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
WhiteLabelService | listContentPages | response | nextCursor | string
WhiteLabelService | listContentPages | response | hasMore | boolean | yes
WhiteLabelService | listContentPages | param (query) | status | ContentStatus: enum (draft, published, archived) |  | Staff only.
WhiteLabelService | listContentPages | param (query) | categoryCode | string |  | Only pages with this categoryCode.
WhiteLabelService | listContentPages | param (query) | slug | string |  | Only the page with this slug — how a screen fetches one known page.
WhiteLabelService | listContentPages | param (query) | pageSize | integer
WhiteLabelService | listContentPages | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
LedgerService | listCreditMemos | response | items | array of FinCreditMemo | yes
LedgerService | listCreditMemos | response | items[].id | string (uuid) | yes | (read-only)
LedgerService | listCreditMemos | response | items[].creditMemoNumber | string | yes | Server-assigned from the legal entity's credit memo series, in sequence without gaps. (read-only)
LedgerService | listCreditMemos | response | items[].taxInvoiceId | string (uuid) | yes
LedgerService | listCreditMemos | response | items[].taxInvoiceNumber | string |  | (read-only)
LedgerService | listCreditMemos | response | items[].kind | enum (full, partial) | yes
LedgerService | listCreditMemos | response | items[].reason | enum (refund, cancellation, priceAdjustment, returnOfGoods, billingError, other) | yes
LedgerService | listCreditMemos | response | items[].refundId | string (uuid) |  | (nullable)
LedgerService | listCreditMemos | response | items[].cancelledOrderId | string (uuid) |  | (nullable)
LedgerService | listCreditMemos | response | items[].legalEntityId | string (uuid) | yes
LedgerService | listCreditMemos | response | items[].buyerSubjectId | string (uuid) |  | (nullable)
LedgerService | listCreditMemos | response | items[].issuedAt | string (date-time) | yes
LedgerService | listCreditMemos | response | items[].currency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | listCreditMemos | response | items[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | listCreditMemos | response | items[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | listCreditMemos | response | items[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | listCreditMemos | response | items[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | listCreditMemos | response | items[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | listCreditMemos | response | items[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | listCreditMemos | response | items[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | listCreditMemos | response | items[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | listCreditMemos | response | items[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | listCreditMemos | response | items[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | listCreditMemos | response | items[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | listCreditMemos | response | items[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | listCreditMemos | response | items[].taxAmountInLegalCurrency | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | listCreditMemos | response | items[].taxAmountInLegalCurrency.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | listCreditMemos | response | items[].taxAmountInLegalCurrency.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | listCreditMemos | response | items[].taxAmountInLegalCurrency.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | listCreditMemos | response | items[].legalFxRate | object |  | The invoice's own legalFxRate, never today's (CHG-FIN-011). (read-only; nullable)
LedgerService | listCreditMemos | response | items[].invoiceSupplyValue | object |  | The value of the supply shown on the tax invoice (Executive Regulation Art. (read-only)
LedgerService | listCreditMemos | response | items[].invoiceSupplyValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | listCreditMemos | response | items[].invoiceSupplyValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | listCreditMemos | response | items[].invoiceSupplyValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | listCreditMemos | response | items[].correctedSupplyValue | object |  | The correct value of the supply after this credit note (Art. (read-only)
LedgerService | listCreditMemos | response | items[].correctedSupplyValue.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | listCreditMemos | response | items[].correctedSupplyValue.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | listCreditMemos | response | items[].correctedSupplyValue.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | listCreditMemos | response | items[].supplierName | string |  | Snapshot of the legal entity at issue, as on the invoice (Art. (read-only)
LedgerService | listCreditMemos | response | items[].supplierAddress | string |  | (read-only; nullable)
LedgerService | listCreditMemos | response | items[].supplierTaxRegistrationNumber | string |  | (read-only; nullable)
LedgerService | listCreditMemos | response | items[].buyerName | string |  | The recipient as on the invoice; name, address and TRN where they are registered (Art. (read-only; nullable)
LedgerService | listCreditMemos | response | items[].buyerAddress | string |  | (read-only; nullable)
LedgerService | listCreditMemos | response | items[].buyerTaxRegistrationNumber | string |  | (read-only; nullable)
LedgerService | listCreditMemos | response | items[].note | string |  | The brief explanation of why the credit note was issued, printed on it (Art. (nullable)
LedgerService | listCreditMemos | response | items[].renditionAssetId | string (uuid) |  | (read-only; nullable)
LedgerService | listCreditMemos | response | items[].eInvoiceStatus | FinEInvoiceTransmissionStatus: enum (notRequired, queued, sent, accepted, rejected, failed) |  | 6.1.1.
LedgerService | listCreditMemos | response | items[].issuedByPrincipalId | string (uuid) |  | (read-only; nullable)
LedgerService | listCreditMemos | response | items[].lines | array of FinCreditMemoLine | yes
LedgerService | listCreditMemos | response | items[].lines[].invoiceLineNumber | integer | yes | (min 1)
LedgerService | listCreditMemos | response | items[].lines[].description | string |  | (max length 500)
LedgerService | listCreditMemos | response | items[].lines[].quantity | number |  | (nullable)
LedgerService | listCreditMemos | response | items[].lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | listCreditMemos | response | items[].lines[].taxRate | number
LedgerService | listCreditMemos | response | items[].lines[].taxCategory | FinTaxCategory: enum (standardRated, zeroRated, exempt, outOfScope, reverseCharge) |  | How a line is treated for VAT.
LedgerService | listCreditMemos | response | items[].lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | listCreditMemos | response | items[].lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | listCreditMemos | response | items[].scopePath | string |  | (read-only)
LedgerService | listCreditMemos | response | nextCursor | string
LedgerService | listCreditMemos | response | hasMore | boolean | yes
LedgerService | listCreditMemos | param (query) | taxInvoiceId | string (uuid)
LedgerService | listCreditMemos | param (query) | refundId | string (uuid)
LedgerService | listCreditMemos | param (query) | legalEntityId | string (uuid)
LedgerService | listCreditMemos | param (query) | issuedFrom | string (date)
LedgerService | listCreditMemos | param (query) | issuedTo | string (date)
LedgerService | listCreditMemos | param (query) | pageSize | integer
LedgerService | listCreditMemos | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
MarketingService | listCustomerBadges | response | items | array of MarketingCustomerBadge | yes
MarketingService | listCustomerBadges | response | items[].id | string (uuid)
MarketingService | listCustomerBadges | response | items[].customerId | string (uuid) | yes
MarketingService | listCustomerBadges | response | items[].badgeId | string (uuid) | yes
MarketingService | listCustomerBadges | response | items[].challengeId | string (uuid) |  | (nullable)
MarketingService | listCustomerBadges | response | items[].sourceType | string |  | (max length 30; nullable)
MarketingService | listCustomerBadges | response | items[].sourceReferenceId | string (uuid) |  | (nullable)
MarketingService | listCustomerBadges | response | items[].awardedAt | string (date-time) | yes
MarketingService | listCustomerBadges | response | items[].expiresAt | string (date-time) |  | (nullable)
MarketingService | listCustomerBadges | response | items[].status | string | yes | (max length 20)
MarketingService | listCustomerBadges | response | nextCursor | string
MarketingService | listCustomerBadges | response | hasMore | boolean | yes
MarketingService | listCustomerBadges | param (path) | customerId | string (uuid) | yes
MarketingService | listCustomerBadges | param (query) | pageSize | integer
MarketingService | listCustomerBadges | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
ReportingService | listDashboards | param (query) | module | ModuleKey: enum (core, ticketing, access, fnb, retail, inventory, seating, membership, …) |  | Narrows the library to one module.
ReportingService | listDashboards | param (query) | includeArchived | boolean |  | Archived dashboards are left out unless this is true — the "unless asked for" that Dashboard.archivedAt promises.
IdentityService | listDelegations | response | items | object | yes
IdentityService | listDelegations | response | items.heldByThisGuest | array of DelegatedAccess
IdentityService | listDelegations | response | items.heldByThisGuest[].id | string (uuid) | yes
IdentityService | listDelegations | response | items.heldByThisGuest[].principalId | string (uuid) |  | (nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].roleId | string (uuid) |  | (nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].permission | string | yes | From the permission enum.
IdentityService | listDelegations | response | items.heldByThisGuest[].subjectId | string (uuid) |  | CF-132, CL-05. (nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].overSubjectId | string (uuid) |  | Whose behalf. (nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].overObjectRef | string |  | Where the authority is over a thing rather than a scope — a wallet, an entitlement, a booking. (nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].delegationKind | enum (primaryHolder, familyMember, groupLeader, attendee, corporateAdmin, corporateMember, carer) |  | What kind of relationship this expresses, for display and for reporting. (nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].quota | integer |  | 2.14.15 and 4.3.11. (nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].isRevocableBySubject | boolean |  | Whether the person it is over can end it. (default True)
IdentityService | listDelegations | response | items.heldByThisGuest[].scopePath | string | yes
IdentityService | listDelegations | response | items.heldByThisGuest[].effect | enum (ALLOW, DENY) | yes
IdentityService | listDelegations | response | items.heldByThisGuest[].permissionId | string (uuid) |  | Taken from identity.user_access, 20 September, when that table was collapsed into this one. (nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].revokedAt | string (date-time) |  | Taken from identity.user_access. (read-only; nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].validFrom | string (date-time) |  | (nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].validTo | string (date-time) |  | (nullable)
IdentityService | listDelegations | response | items.heldByThisGuest[].createdByPrincipalId | string (uuid)
IdentityService | listDelegations | response | items.heldByThisGuest[].createdAt | string (date-time)
IdentityService | listDelegations | response | items.heldOverThisGuest | array of DelegatedAccess
IdentityService | listDelegations | response | items.heldOverThisGuest[].id | string (uuid) | yes
IdentityService | listDelegations | response | items.heldOverThisGuest[].principalId | string (uuid) |  | (nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].roleId | string (uuid) |  | (nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].permission | string | yes | From the permission enum.
IdentityService | listDelegations | response | items.heldOverThisGuest[].subjectId | string (uuid) |  | CF-132, CL-05. (nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].overSubjectId | string (uuid) |  | Whose behalf. (nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].overObjectRef | string |  | Where the authority is over a thing rather than a scope — a wallet, an entitlement, a booking. (nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].delegationKind | enum (primaryHolder, familyMember, groupLeader, attendee, corporateAdmin, corporateMember, carer) |  | What kind of relationship this expresses, for display and for reporting. (nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].quota | integer |  | 2.14.15 and 4.3.11. (nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].isRevocableBySubject | boolean |  | Whether the person it is over can end it. (default True)
IdentityService | listDelegations | response | items.heldOverThisGuest[].scopePath | string | yes
IdentityService | listDelegations | response | items.heldOverThisGuest[].effect | enum (ALLOW, DENY) | yes
IdentityService | listDelegations | response | items.heldOverThisGuest[].permissionId | string (uuid) |  | Taken from identity.user_access, 20 September, when that table was collapsed into this one. (nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].revokedAt | string (date-time) |  | Taken from identity.user_access. (read-only; nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].validFrom | string (date-time) |  | (nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].validTo | string (date-time) |  | (nullable)
IdentityService | listDelegations | response | items.heldOverThisGuest[].createdByPrincipalId | string (uuid)
IdentityService | listDelegations | response | items.heldOverThisGuest[].createdAt | string (date-time)
IdentityService | listDelegations | response | nextCursor | string
IdentityService | listDelegations | response | hasMore | boolean | yes
IdentityService | listDelegations | param (path) | subjectId | string (uuid) | yes
IdentityService | listDelegations | param (query) | pageSize | integer
IdentityService | listDelegations | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
FnbService | listDeliveryLocations | response | items | array of DeliveryLocation | yes
FnbService | listDeliveryLocations | response | items[].id | string (uuid) | yes
FnbService | listDeliveryLocations | response | items[].venueId | string (uuid) | yes
FnbService | listDeliveryLocations | response | items[].kind | DeliveryLocationKind: enum (table, seat, cabana, sunbed, poolside, box, suite, lawn, …) | yes | 4.6.26.
FnbService | listDeliveryLocations | response | items[].label | string | yes | What a runner is told.
FnbService | listDeliveryLocations | response | items[].zone | string |  | (nullable)
FnbService | listDeliveryLocations | response | items[].tableId | string (uuid) |  | Set where the location is a restaurant table, so it shares table state. (nullable)
FnbService | listDeliveryLocations | response | items[].seatId | string |  | Set where the seat is the address. (nullable)
FnbService | listDeliveryLocations | response | items[].servingOutletIds | array of string (uuid) |  | Which outlets deliver here.
FnbService | listDeliveryLocations | response | items[].isServiceable | boolean | yes | False where the location exists but is not currently taking delivery — closed section, weather, no runner on shift.
FnbService | listDeliveryLocations | response | items[].unserviceableReason | string |  | (nullable)
FnbService | listDeliveryLocations | response | items[].walkTimeMinutes | integer |  | From the serving outlet. (nullable)
FnbService | listDeliveryLocations | response | items[].codeGeneration | integer |  | Which printing of the location's ordering code is current (4 October 2026, CHG-FXC-009). (min 1; default 1)
FnbService | listDeliveryLocations | response | nextCursor | string
FnbService | listDeliveryLocations | response | hasMore | boolean | yes
FnbService | listDeliveryLocations | param (path) | venueId | string (uuid) | yes
FnbService | listDeliveryLocations | param (query) | kind | DeliveryLocationKind: enum (table, seat, cabana, sunbed, poolside, box, suite, lawn, …)
FnbService | listDeliveryLocations | param (query) | servingOutletId | string (uuid) |  | Only locations this outlet delivers to.
FnbService | listDeliveryLocations | param (query) | pageSize | integer
FnbService | listDeliveryLocations | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
OrderService | listDenominations | param (query) | includeInactive | boolean
OrderService | listDepositBoxes | response | items | array of DepositBox | yes
OrderService | listDepositBoxes | response | items[].id | string (uuid) |  | (read-only)
OrderService | listDepositBoxes | response | items[].cashierPrincipalId | string (uuid) | yes
OrderService | listDepositBoxes | response | items[].cashierName | string |  | (read-only)
OrderService | listDepositBoxes | response | items[].venueId | string (uuid) | yes
OrderService | listDepositBoxes | response | items[].workstationId | string (uuid) |  | Where it is being used now. (nullable)
OrderService | listDepositBoxes | response | items[].shiftId | string (uuid) |  | The shift trading from this box. (nullable)
OrderService | listDepositBoxes | response | items[].status | DepositBoxStatus: enum (allocated, open, suspended, closing, closed, reconciled)
OrderService | listDepositBoxes | response | items[].openingFloat | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listDepositBoxes | response | items[].openingFloat.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listDepositBoxes | response | items[].openingFloat.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listDepositBoxes | response | items[].openingFloat.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listDepositBoxes | response | items[].openingDenominations | array of object |  | 5.8.3.
OrderService | listDepositBoxes | response | items[].openingDenominations[].denominationId | string (uuid) | yes | References platform.denomination, as CashCountLine.denominationId does.
OrderService | listDepositBoxes | response | items[].openingDenominations[].count | integer | yes | (min 0)
OrderService | listDepositBoxes | response | items[].withdrawnTotal | object |  | Reduces the expected close figure. (read-only)
OrderService | listDepositBoxes | response | items[].withdrawnTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listDepositBoxes | response | items[].withdrawnTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listDepositBoxes | response | items[].withdrawnTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listDepositBoxes | response | items[].overDrawerLimit | boolean |  | The box holds more than its till's drawer limit (decided 2 October 2026, Chinmay, BO-042; DEC-179; CHG-CSP-016): computed on read from the box's expected cash against tenancy.Workstation.cashDrawerLi… (default False; read-only)
OrderService | listDepositBoxes | response | items[].foreignHoldings | array of object |  | 4.6.11 and 6.1.10.
OrderService | listDepositBoxes | response | items[].foreignHoldings[].currency | string | yes | Stored, because it is the one thing that is not the region's. (pattern ^[A-Z]{3}$)
OrderService | listDepositBoxes | response | items[].foreignHoldings[].expectedAmount | object |  | The sum of tenders taken in this currency during the shift.
OrderService | listDepositBoxes | response | items[].foreignHoldings[].countedAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listDepositBoxes | response | items[].foreignHoldings[].variance | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listDepositBoxes | response | items[].foreignHoldings[].baseEquivalent | object |  | At the rates on the payments, not today's.
OrderService | listDepositBoxes | response | items[].expectedTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listDepositBoxes | response | items[].expectedTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listDepositBoxes | response | items[].expectedTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listDepositBoxes | response | items[].expectedTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listDepositBoxes | response | items[].countedTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listDepositBoxes | response | items[].countedTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listDepositBoxes | response | items[].countedTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listDepositBoxes | response | items[].countedTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listDepositBoxes | response | items[].variance | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listDepositBoxes | response | items[].variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listDepositBoxes | response | items[].variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listDepositBoxes | response | items[].variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listDepositBoxes | response | items[].closedByPrincipalId | string (uuid) |  | Flagged where it is not the holder. (nullable)
OrderService | listDepositBoxes | response | items[].allocatedAt | string (date-time) |  | When the device recorded the allocation.
OrderService | listDepositBoxes | response | items[].closedAt | string (date-time) |  | (nullable)
OrderService | listDepositBoxes | response | nextCursor | string
OrderService | listDepositBoxes | response | hasMore | boolean | yes
OrderService | listDepositBoxes | param (query) | openOnly | boolean
OrderService | listDepositBoxes | param (query) | pageSize | integer
OrderService | listDepositBoxes | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
TenancyService | listDevices | response | items | array of RegisteredDevice | yes
TenancyService | listDevices | response | items[].id | string (uuid) | yes | (read-only)
TenancyService | listDevices | response | items[].kind | DeviceKind: enum (receiptPrinter, ticketPrinter, labelPrinter, cashDrawer, barcodeScanner, rfidReader, nfcReader, cardReader, …) | yes | mobileHandset (18.1.5, added 29 September): a staff phone or tablet running the staff app, registered for push and bound to no workstation.
TenancyService | listDevices | response | items[].driver | string | yes | Built to an open standard where one exists — ESC/POS, UnifiedPOS, OSDP.
TenancyService | listDevices | response | items[].identifier | string |  | (nullable)
TenancyService | listDevices | response | items[].workstationId | string (uuid) |  | Required for every kind except mobileHandset, which is bound to no workstation (18.1.5, 29 September), and except an access-control device (one with a hardwareType), which is placed in the gate topol… (nullable)
TenancyService | listDevices | response | items[].model | string |  | (nullable)
TenancyService | listDevices | response | items[].hardwareType | DeviceHardwareType: enum (standardTurnstile, fullHeightTurnstile, tripodTurnstile, speedGate, wideLane, accessiblePodGate, buggyGate, vipGate, …) |  | The specific hardware under a device's kind (ADR-0067, accepted 1 October: one device register).
TenancyService | listDevices | response | items[].hardwareModelId | string (uuid) |  | The model in the hardware library (access setHardwareModel; ADR-0067). (nullable)
TenancyService | listDevices | response | items[].serialNumber | string |  | The manufacturer's serial (ADR-0067: was on the access-control device row, now access.device_placement). (max length 100; nullable)
TenancyService | listDevices | response | items[].ipNetworkReference | string |  | Network address or reference the device is reached at (ADR-0067). (nullable)
TenancyService | listDevices | response | items[].configurationVersion | string |  | Access configuration version the device reports running (ADR-0067). (read-only; nullable)
TenancyService | listDevices | response | items[].localRuleVersion | string |  | Admission rule package the device reports running (ADR-0067). (read-only; nullable)
TenancyService | listDevices | response | items[].credentialSecurityPackageVersion | string |  | Credential security package the device reports running (ADR-0067). (read-only; nullable)
TenancyService | listDevices | response | items[].scannerHealth | string |  | Component health as the device or vendor reports it on its heartbeat (ADR-0067). (read-only; nullable)
TenancyService | listDevices | response | items[].controllerHealth | string |  | (read-only; nullable)
TenancyService | listDevices | response | items[].cameraHealth | string |  | Where the device has a camera. (read-only; nullable)
TenancyService | listDevices | response | items[].connectivity | string |  | Reported connectivity. (read-only; nullable)
TenancyService | listDevices | response | items[].pushToken | string (password) |  | BL-163. (nullable)
TenancyService | listDevices | response | items[].pushPlatform | enum (ios, android, web, windows) |  | (nullable)
TenancyService | listDevices | response | items[].pushFailureCount | integer |  | Consecutive failures. (default 0; read-only)
TenancyService | listDevices | response | items[].offlineScope | enum (none, readOnly, sellAndScan, fullVenue) |  | BL-163. (nullable)
TenancyService | listDevices | response | items[].firmwareVersion | string |  | As the device last reported it on its heartbeat. (read-only; nullable)
TenancyService | listDevices | response | items[].isRequired | boolean |  | True blocks shift open when the device is unreachable.
TenancyService | listDevices | response | items[].status | enum (online, offline, error, consumableLow, needsAttention, localMode, unknown) |  | What the device last said on its heartbeat; unknown until it has. (read-only)
TenancyService | listDevices | response | items[].batteryPercent | integer |  | Board 1 of the client's POS design set, 20 August. (min 0; max 100; read-only; nullable)
TenancyService | listDevices | response | items[].lastCheckedAt | string (date-time) |  | Distinct from lastHeartbeatAt. (read-only; nullable)
TenancyService | listDevices | response | items[].health | enum (healthy, warning, degraded, offline, unknown) |  | Derived, not reported. (default unknown; read-only)
TenancyService | listDevices | response | items[].lastHeartbeatAt | string (date-time) |  | (read-only; nullable)
TenancyService | listDevices | response | items[].capabilities | array of DeviceCapability: enum (genderClassification, dynamicQr, rfid, nfc, facePass, offline, heightCheck) |  | BL-179. (read-only)
TenancyService | listDevices | response | items[].enrolmentState | enum (registered, enrolled, provisioned, active, deactivated, retired) |  | BL-160. (default registered; read-only)
TenancyService | listDevices | response | items[].retiredAt | string (date-time) |  | Set when enrolmentState reaches retired, and null otherwise. (read-only; nullable)
TenancyService | listDevices | response | items[].configurationProfileId | string (uuid) |  | The profile this device was provisioned with. (read-only; nullable)
TenancyService | listDevices | response | items[].approvalStatus | object |  | A new device waits for approval before it may go live (decided 2 October 2026, Chinmay, critical set 1, BO-196: "Secure enrolment code + pending approval"; DEC-241; CHG-CSP-011; MoM 15 September, DI-… (default pendingApproval; read-only)
TenancyService | listDevices | response | items[].enrolmentCode | string |  | A one-time code the device must present to enrol (DEC-241; CHG-CSP-011). (max length 12; read-only; nullable)
TenancyService | listDevices | response | items[].enrolmentCodeExpiresAt | string (date-time) |  | When the enrolment code stops working (24 hours after registration, proposed; client to correct). (read-only; nullable)
TenancyService | listDevices | response | items[].testedByPrincipalId | string (uuid) |  | Who recorded the device's acceptance test (DeviceEnrolment.testResult on the move to provisioned). (read-only; nullable)
TenancyService | listDevices | response | items[].approvedByPrincipalId | string (uuid) |  | Who approved the device into production, never the person who tested it (decided 2 October 2026, Chinmay, critical set 1, BO-203: "Approver must differ from the tester"; DEC-245; CHG-CSP-011). (read-only; nullable)
TenancyService | listDevices | response | items[].approvedAt | string (date-time) |  | (read-only; nullable)
TenancyService | listDevices | response | nextCursor | string
TenancyService | listDevices | response | hasMore | boolean | yes
TenancyService | listDevices | param (query) | workstationId | string (uuid)
TenancyService | listDevices | param (query) | kind | DeviceKind: enum (receiptPrinter, ticketPrinter, labelPrinter, cashDrawer, barcodeScanner, rfidReader, nfcReader, cardReader, …)
TenancyService | listDevices | param (query) | pageSize | integer
TenancyService | listDevices | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
FnbService | listDiningOutlets | response | items | array of DiningOutlet | yes
FnbService | listDiningOutlets | response | items[].outletId | string (uuid) | yes
FnbService | listDiningOutlets | response | items[].name | string | yes
FnbService | listDiningOutlets | response | items[].kind | string | yes
FnbService | listDiningOutlets | response | items[].zone | string |  | (nullable)
FnbService | listDiningOutlets | response | items[].cuisine | array of string
FnbService | listDiningOutlets | response | items[].isOpenNow | boolean | yes
FnbService | listDiningOutlets | response | items[].opensAt | string (date-time) |  | (nullable)
FnbService | listDiningOutlets | response | items[].closesAt | string (date-time) |  | (nullable)
FnbService | listDiningOutlets | response | items[].orderingMethod | GuestOrderingMethod: enum (tableService, appToTable, appToCollect, counterOnly, notAvailable) | yes | How a guest may order at this outlet.
FnbService | listDiningOutlets | response | items[].estimatedWaitMinutes | integer |  | From current kitchen ticket volume, not a fixed figure. (nullable)
FnbService | listDiningOutlets | response | items[].imageAssetRef | string |  | (nullable)
FnbService | listDiningOutlets | response | items[].menuId | string (uuid) |  | (nullable)
FnbService | listDiningOutlets | response | items[].admissionContext | object |  | Inside the venue or standalone (decided 2 October 2026, Chinmay: DEC-070, workbook Q70; CHG-CLN-008): the outlet's tenancy.Outlet.admissionContext, so the guest sees before ordering whether an admiss…
FnbService | listDiningOutlets | response | nextCursor | string
FnbService | listDiningOutlets | response | hasMore | boolean | yes
FnbService | listDiningOutlets | param (path) | venueId | string (uuid) | yes
FnbService | listDiningOutlets | param (query) | openNow | boolean
FnbService | listDiningOutlets | param (query) | orderingMethod | GuestOrderingMethod: enum (tableService, appToTable, appToCollect, counterOnly, notAvailable)
FnbService | listDiningOutlets | param (query) | pageSize | integer
FnbService | listDiningOutlets | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
AccessService | listEntitlements | response | items | array of Entitlement | yes
AccessService | listEntitlements | response | items[].id | string (uuid) | yes | A UUIDv7, matching TicketStatus.ticketId — stable for the life of the ticket and independent of the media carrying it.
AccessService | listEntitlements | response | items[].templateId | string (uuid) | yes | The definition it was issued against.
AccessService | listEntitlements | response | items[].productId | string (uuid) | yes
AccessService | listEntitlements | response | items[].orderId | string (uuid) | yes | The order's id, a UUIDv7 as in /orders/{orderId} (orders.sales_order.id). (nullable)
AccessService | listEntitlements | response | items[].orderLineId | string (uuid)
AccessService | listEntitlements | response | items[].subjectId | string (uuid) | yes | Who holds it. (nullable)
AccessService | listEntitlements | response | items[].venueId | string (uuid)
AccessService | listEntitlements | response | items[].scopePath | string
AccessService | listEntitlements | response | items[].mediaCode | string |  | What is scanned — a QR payload, a wristband serial, a card number.
AccessService | listEntitlements | response | items[].credentialFormat | object |  | The credential this entitlement was issued with, resolved once at issue by issueOrderEntitlements: the product's credentialFormatOverride, else the sales channel's ticketCredentialFormat, else platfo… (nullable)
AccessService | listEntitlements | response | items[].status | EntitlementStatus: enum (issued, partiallyConsumed, fullyConsumed, expired, cancelled, surrendered) | yes | What the storage layer holds, and what a guest is shown.
AccessService | listEntitlements | response | items[].statusNote | string |  | Not TicketStatus — that is a validation result with a misleading name, computed at scan time and carrying isValid and isInsideVenue. (nullable)
AccessService | listEntitlements | response | items[].validFrom | string (date-time) | yes
AccessService | listEntitlements | response | items[].validTo | string (date-time) | yes | Resolved at issue from the template, then owned here.
AccessService | listEntitlements | response | items[].entriesUsed | integer |  | The number validateAccess decrements and nothing was decrementing. (default 0; read-only)
AccessService | listEntitlements | response | items[].entriesAllowed | integer |  | (nullable)
AccessService | listEntitlements | response | items[].lastEntryAt | string (date-time) |  | recordedAt of the latest admission counted in entriesUsed, written by the same writes. (read-only; nullable)
AccessService | listEntitlements | response | items[].firstEntryAt | string (date-time) |  | recordedAt of the first admission, written by the same writes as lastEntryAt; it starts a time-bound entitlement's window (DEC-232; CHG-CSP-030). (read-only; nullable)
AccessService | listEntitlements | response | items[].timeBoundUntil | string (date-time) |  | Where the template is time-bound, when its window closes: firstEntryAt plus the validity rule's minutesAfterFirstScan (decided 2 October 2026, Chinmay, BO-159; DEC-232; CHG-CSP-030). (read-only; nullable)
AccessService | listEntitlements | response | items[].lifecycleLabel | enum (created, pendingFulfillment, active, partiallyUsed, used, expired, suspended, cancelled, …) |  | The Virtual Ticket status in the client's 13 names, mapped onto the entitlement model (decided 2 October 2026, Chinmay, critical set 2, BO-336: "Map the pack's 13 names onto the model; add any missin… (read-only)
AccessService | listEntitlements | response | items[].cancellationKind | enum (voided, refunded, performanceCancelled, superseded) |  | Which act cancelled the entitlement, so the pack's Voided, Refunded and Reissued / superseded are told apart while status keeps the one r1 value cancelled (DEC-266; CHG-CSP-033). (read-only; nullable)
AccessService | listEntitlements | response | items[].frozenDays | integer |  | Days added by a freeze. (default 0; read-only)
AccessService | listEntitlements | response | items[].suspendedReason | string |  | (nullable)
AccessService | listEntitlements | response | items[].freezeReason | enum (travelling, injury, personal, seasonal, other) |  | The reason of the latest freezeEntitlement (audit R222). (nullable)
AccessService | listEntitlements | response | items[].freezeNote | string |  | The note the latest freezeEntitlement took, required there when reason is other (decided 28 September, audit R222). (max length 500; nullable)
AccessService | listEntitlements | response | items[].isNameBound | boolean |  | (default False)
AccessService | listEntitlements | response | items[].holderName | string |  | (nullable)
AccessService | listEntitlements | response | items[].sharedWithSubjectIds | array of string (uuid) |  | shareEntitlement.
AccessService | listEntitlements | response | items[].issuedVia | enum (sale, invitation, reissue, transfer, resale, membership, groupBooking) |  | How it came to exist, and it matters to finance.
AccessService | listEntitlements | response | items[].supersedesEntitlementId | string (uuid) |  | For a reissue or a resale. (nullable)
AccessService | listEntitlements | response | items[].walletValueId | string (uuid) |  | Where the template carries stored value. (nullable)
AccessService | listEntitlements | response | items[].facePassEnrolmentId | string (uuid) |  | The active facePass enrolment on this entitlement (FacePassEnrolment.id), or null when none is. (read-only; nullable)
AccessService | listEntitlements | response | items[].invitationId | string (uuid) |  | The invitation that issued it (4 October 2026, CHG-FXC-007): orders.issueInvitation issues the entitlement without an order, because an invitation never enters the order path. (nullable)
AccessService | listEntitlements | response | nextCursor | string
AccessService | listEntitlements | response | hasMore | boolean | yes
AccessService | listEntitlements | param (header) | X-Consistency-Token | string |  | Opaque token returned by a prior write: the database instance and its WAL LSN (SD-025, 29 September; ADR-0040 allows several instances per region, so an LSN alone is ambiguous).
AccessService | listEntitlements | param (query) | includeExpired | boolean
AccessService | listEntitlements | param (query) | pageSize | integer
AccessService | listEntitlements | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
CatalogueService | listEvents | response | items | array of Event | yes
CatalogueService | listEvents | response | items[].id | string (uuid) | yes
CatalogueService | listEvents | response | items[].code | string | yes
CatalogueService | listEvents | response | items[].name | string | yes
CatalogueService | listEvents | response | items[].venueId | string (uuid) | yes
CatalogueService | listEvents | response | items[].scopePath | string | yes
CatalogueService | listEvents | response | items[].parentEventId | string (uuid) |  | For grouped events. (nullable)
CatalogueService | listEvents | response | items[].performanceCount | integer |  | How many performances the event has. (read-only)
CatalogueService | listEvents | response | items[].isActive | boolean
CatalogueService | listEvents | response | items[].lifecycleState | enum (draft, planned, onSale, live, closed, cancelled, archived) |  | Where the event is in its lifecycle (4 October 2026, CHG-FXC-003; catalogue.event had nowhere to keep it). (read-only)
CatalogueService | listEvents | response | items[].lifecycleStateChangedAt | string (date-time) |  | (read-only; nullable)
CatalogueService | listEvents | response | nextCursor | string
CatalogueService | listEvents | response | hasMore | boolean | yes
CatalogueService | listEvents | param (query) | pageSize | integer
CatalogueService | listEvents | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
FnbService | listFnbOrders | response | items | array of FnbOrder | yes
FnbService | listFnbOrders | response | items[].id | string (uuid) | yes
FnbService | listFnbOrders | response | items[].orderNumber | string | yes
FnbService | listFnbOrders | response | items[].outletId | string (uuid) | yes
FnbService | listFnbOrders | response | items[].paymentTiming | object |  | The outlet's payment timing when the order was placed (CHG-CSA-010), kept as a snapshot. (read-only)
FnbService | listFnbOrders | response | items[].sentToKitchenAt | string (date-time) |  | When the order's kitchen tickets were created. (read-only; nullable)
FnbService | listFnbOrders | response | items[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery) | yes
FnbService | listFnbOrders | response | items[].tableVisitId | string (uuid) |  | (nullable)
FnbService | listFnbOrders | response | items[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) | yes | The full lifecycle from 4.6.35.
FnbService | listFnbOrders | response | items[].lines | array of object | yes
FnbService | listFnbOrders | response | items[].lines[].id | string (uuid) | yes
FnbService | listFnbOrders | response | items[].lines[].menuItemId | string (uuid) | yes
FnbService | listFnbOrders | response | items[].lines[].quantity | integer | yes | (min 1)
FnbService | listFnbOrders | response | items[].lines[].modifierOptionIds | array of string (uuid)
FnbService | listFnbOrders | response | items[].lines[].note | string |  | Free text to the kitchen. (max length 200)
FnbService | listFnbOrders | response | items[].lines[].seatNumber | integer |  | Which cover ordered it. (nullable)
FnbService | listFnbOrders | response | items[].lines[].course | integer |  | Course grouping, so the kitchen fires in sequence. (nullable)
FnbService | listFnbOrders | response | items[].lines[].redeemEntitlementId | string |  | A meal combo redeemed at the till or by a scan (29 September, MOB-4; applied 30 September). (nullable)
FnbService | listFnbOrders | response | items[].lines[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) |  | The full lifecycle from 4.6.35.
FnbService | listFnbOrders | response | items[].lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | listFnbOrders | response | items[].lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | listFnbOrders | response | items[].salesOrderId | string (uuid) |  | Retyped 29 September (SD-046), and format: uuid since ADR-0056 (30 September): every id is a uuid, so this joins orders.sales_order.id. (nullable)
FnbService | listFnbOrders | response | items[].updatedAt | string (date-time) |  | Taken from their fnb.order. (nullable)
FnbService | listFnbOrders | response | items[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | listFnbOrders | response | items[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | listFnbOrders | response | items[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | listFnbOrders | response | items[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | listFnbOrders | response | items[].taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | listFnbOrders | response | items[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | listFnbOrders | response | items[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | listFnbOrders | response | items[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | listFnbOrders | response | items[].kitchenTicketId | string (uuid) |  | (nullable)
FnbService | listFnbOrders | response | items[].kitchenTickets | array of KitchenTicket |  | The kitchen tickets this order created, one per station (SD-046). (read-only)
FnbService | listFnbOrders | response | items[].kitchenTickets[].id | string (uuid) | yes
FnbService | listFnbOrders | response | items[].kitchenTickets[].orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | listFnbOrders | response | items[].kitchenTickets[].orderNumber | string
FnbService | listFnbOrders | response | items[].kitchenTickets[].outletId | string (uuid) | yes
FnbService | listFnbOrders | response | items[].kitchenTickets[].tableLabel | string |  | (nullable)
FnbService | listFnbOrders | response | items[].kitchenTickets[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | listFnbOrders | response | items[].kitchenTickets[].coursing | object |  | BL-131. (nullable)
FnbService | listFnbOrders | response | items[].kitchenTickets[].buzzerCode | string |  | BL-128. (nullable)
FnbService | listFnbOrders | response | items[].kitchenTickets[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | listFnbOrders | response | items[].kitchenTickets[].priority | integer |  | Higher fires sooner.
FnbService | listFnbOrders | response | items[].kitchenTickets[].prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | listFnbOrders | response | items[].kitchenTickets[].prioritiseReason | string |  | (nullable)
FnbService | listFnbOrders | response | items[].kitchenTickets[].lines | array of object | yes
FnbService | listFnbOrders | response | items[].kitchenTickets[].createdAt | string (date-time) | yes
FnbService | listFnbOrders | response | items[].kitchenTickets[].targetReadyAt | string (date-time) |  | (nullable)
FnbService | listFnbOrders | response | items[].kitchenTickets[].elapsedSeconds | integer
FnbService | listFnbOrders | response | items[].kitchenTickets[].visitId | string (uuid) |  | The table visit the ticket is for (4 October 2026, CHG-FXC-011; KIT-002): the {visitId} notifyServer takes. (read-only; nullable)
FnbService | listFnbOrders | response | items[].estimatedReadyAt | string (date-time) |  | (nullable)
FnbService | listFnbOrders | response | items[].createdAt | string (date-time) | yes
FnbService | listFnbOrders | response | items[].recordedAt | string (date-time)
FnbService | listFnbOrders | response | items[].syncedAt | string (date-time) |  | (nullable)
FnbService | listFnbOrders | response | nextCursor | string
FnbService | listFnbOrders | response | hasMore | boolean | yes
FnbService | listFnbOrders | param (query) | outletId | string (uuid)
FnbService | listFnbOrders | param (query) | tableVisitId | string (uuid)
FnbService | listFnbOrders | param (query) | status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …)
FnbService | listFnbOrders | param (query) | pageSize | integer
FnbService | listFnbOrders | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
AiService | listForecastVersions | response | items | array of AiForecastVersion | yes
AiService | listForecastVersions | response | items[].id | string (uuid) |  | (read-only)
AiService | listForecastVersions | response | items[].definitionId | string (uuid) | yes
AiService | listForecastVersions | response | items[].versionNumber | integer | yes | (min 1)
AiService | listForecastVersions | response | items[].module | object |  | The module of the version's definition (AiForecastDefinition.module), copied when the version is produced; the module whose AI publish permission publishForecastVersion requires (CHG-FUP-004). (read-only)
AiService | listForecastVersions | response | items[].status | enum (running, draft, awaitingApproval, published, superseded, rejected, failed) | yes | (read-only)
AiService | listForecastVersions | response | items[].basis | SuggestionBasis: enum (heuristic, statistical, model, hybrid, manual) | yes | How the answer was reached, and this is the field the whole design exists for.
AiService | listForecastVersions | response | items[].maturity | AiMaturity |  | Where an answer stands, on every answer (29 September, AI functions review; baseline then learn).
AiService | listForecastVersions | response | items[].maturity.stage | enum (starting, learning, established, learned) | yes | starting: the baseline (venue AI settings, the starting pattern for the venue type, the UAE calendar, weather).
AiService | listForecastVersions | response | items[].maturity.basedOn | string | yes | The "Based on" line, in words, e.g.
AiService | listForecastVersions | response | items[].maturity.sources | array of object
AiService | listForecastVersions | response | items[].maturity.ownDataShare | number |  | The weight own data carries, n / (k + n). (min 0; max 1)
AiService | listForecastVersions | response | items[].maturity.limitedHistory | boolean
AiService | listForecastVersions | response | items[].maturity.nextStage | object |  | What the next stage needs, e.g. (nullable)
AiService | listForecastVersions | response | items[].producerRef | string
AiService | listForecastVersions | response | items[].modelVersion | string |  | (nullable)
AiService | listForecastVersions | response | items[].dataCutoffAt | string (date-time) |  | The analytical replica watermark the snapshot was taken at.
AiService | listForecastVersions | response | items[].horizonStart | string (date-time)
AiService | listForecastVersions | response | items[].horizonEnd | string (date-time)
AiService | listForecastVersions | response | items[].qualityChecks | object |  | Each gate and whether it passed. (read-only)
AiService | listForecastVersions | response | items[].publishedByPrincipalId | string (uuid) |  | Null where the definition auto-published. (read-only; nullable)
AiService | listForecastVersions | response | items[].publishedAt | string (date-time) |  | (read-only; nullable)
AiService | listForecastVersions | response | items[].decisionRecordId | string (uuid) |  | (read-only; nullable)
AiService | listForecastVersions | response | items[].createdAt | string (date-time) |  | (read-only)
AiService | listForecastVersions | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | listForecastVersions | response | nextCursor | string
AiService | listForecastVersions | response | hasMore | boolean | yes
AiService | listForecastVersions | param (query) | definitionKey | string
AiService | listForecastVersions | param (query) | status | enum (running, draft, awaitingApproval, published, superseded, rejected, failed)
AiService | listForecastVersions | param (query) | pageSize | integer
AiService | listForecastVersions | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
FnbService | listFulfilmentSlots | response | items | FulfilmentSlots | yes
FnbService | listFulfilmentSlots | response | items.slots | array of object
FnbService | listFulfilmentSlots | response | items.slots[].start | string (date-time)
FnbService | listFulfilmentSlots | response | items.slots[].end | string (date-time) |  | (nullable)
FnbService | listFulfilmentSlots | response | items.slots[].isAsap | boolean
FnbService | listFulfilmentSlots | response | nextCursor | string
FnbService | listFulfilmentSlots | response | hasMore | boolean | yes
FnbService | listFulfilmentSlots | param (path) | outletId | string (uuid) | yes
FnbService | listFulfilmentSlots | param (query) | mode | enum (collection, delivery) | yes
FnbService | listFulfilmentSlots | param (query) | date | string (date) |  | A calendar day, in the Region's time zone, not UTC.
FnbService | listFulfilmentSlots | param (query) | pageSize | integer
FnbService | listFulfilmentSlots | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
LedgerService | listFxRates | response | items | array of FxRate | yes
LedgerService | listFxRates | response | items[].id | string (uuid) |  | (read-only)
LedgerService | listFxRates | response | items[].fromCurrency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | listFxRates | response | items[].toCurrency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | listFxRates | response | items[].rate | object | yes | Units of toCurrency per one fromCurrency.
LedgerService | listFxRates | response | items[].purpose | FxRatePurpose: enum (tender, interEntity, reporting, revaluation) | yes | A venue does not accept dollars at the rate it books an intercompany balance at.
LedgerService | listFxRates | response | items[].source | object |  | (read-only)
LedgerService | listFxRates | response | items[].effectiveFrom | string (date-time) | yes
LedgerService | listFxRates | response | items[].effectiveTo | string (date-time) |  | A rate change is a new row. (nullable)
LedgerService | listFxRates | response | items[].setByPrincipalId | string (uuid) |  | (read-only)
LedgerService | listFxRates | response | items[].note | string |  | Why this rate, and from where. (max length 500; nullable)
LedgerService | listFxRates | response | items[].providerReference | string |  | The provider's own identifier for this quote. (read-only; nullable)
LedgerService | listFxRates | response | items[].fetchedAt | string (date-time) |  | When the rate was pulled. (read-only; nullable)
LedgerService | listFxRates | response | items[].chargeable | boolean |  | With venueId, true where a guest may select this currency and pay in it at that venue (tenancy.VenueSettings.chargeCurrencies), false where it is shown as an approximate price only (CHG-FIN-001). (read-only)
LedgerService | listFxRates | response | nextCursor | string
LedgerService | listFxRates | response | hasMore | boolean | yes
LedgerService | listFxRates | param (query) | asAt | string (date-time) |  | Rates in force at this instant.
LedgerService | listFxRates | param (query) | purpose | FxRatePurpose: enum (tender, interEntity, reporting, revaluation)
LedgerService | listFxRates | param (query) | venueId | string (uuid) |  | Narrows the region's rates to the currencies this venue shows.
LedgerService | listFxRates | param (query) | chargeable | boolean |  | With venueId, only the currencies a guest may select and pay in at that venue (tenancy.VenueSettings.chargeCurrencies; CHG-FIN-001).
LedgerService | listFxRates | param (query) | pageSize | integer
LedgerService | listFxRates | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
OrderService | listGroupArrivalCheck | param (query) | pageSize | integer
CatalogueService | listGroupPackages | response | items | array of GroupPackageDefinition | yes
CatalogueService | listGroupPackages | response | items[].id | string (uuid) |  | (read-only)
CatalogueService | listGroupPackages | response | items[].productId | string |  | (read-only)
CatalogueService | listGroupPackages | response | items[].kind | enum (school, party) | yes
CatalogueService | listGroupPackages | response | items[].maxParticipants | integer | yes | Pupils or children, e.g. (min 1)
CatalogueService | listGroupPackages | response | items[].durationMinutes | integer | yes | (min 15)
CatalogueService | listGroupPackages | response | items[].hostCount | integer |  | Party hosts included. (min 0; default 1)
CatalogueService | listGroupPackages | response | items[].pricingBasis | enum (perParticipant, perPackage)
CatalogueService | listGroupPackages | response | items[].freeLeaderRatio | integer |  | Schools: one teacher or assistant enters free per this many pupils. (default 10; nullable)
CatalogueService | listGroupPackages | response | items[].paymentMode | enum (invoice, deposit, full) |  | Schools are invoiced; parties take a deposit (see DepositPolicy).
CatalogueService | listGroupPackages | response | items[].includes | array of string
CatalogueService | listGroupPackages | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
CatalogueService | listGroupPackages | response | nextCursor | string
CatalogueService | listGroupPackages | response | hasMore | boolean | yes
CatalogueService | listGroupPackages | param (query) | kind | enum (school, party)
CatalogueService | listGroupPackages | param (query) | pageSize | integer
CatalogueService | listGroupPackages | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
MarketingService | listGuestDevices | response | items | array of GuestDevice | yes
MarketingService | listGuestDevices | response | items[].id | string (uuid) | yes
MarketingService | listGuestDevices | response | items[].subjectId | string (uuid) | yes
MarketingService | listGuestDevices | response | items[].platform | enum (ios, android, web) | yes
MarketingService | listGuestDevices | response | items[].tokenFingerprint | string |  | Hash of the token, not the token.
MarketingService | listGuestDevices | response | items[].tokenRef | string |  | A vault reference to the push token, written by the server from registerGuestDevice.token — the same pattern as PaymentProvider.credentialRef.
MarketingService | listGuestDevices | response | items[].appVersion | string |  | (nullable)
MarketingService | listGuestDevices | response | items[].osVersion | string |  | (nullable)
MarketingService | listGuestDevices | response | items[].deviceModel | string |  | (nullable)
MarketingService | listGuestDevices | response | items[].locale | string |  | (nullable)
MarketingService | listGuestDevices | response | items[].status | enum (active, revoked, failed) | yes
MarketingService | listGuestDevices | response | items[].failureCount | integer |  | Consecutive delivery failures.
MarketingService | listGuestDevices | response | items[].registeredAt | string (date-time) | yes
MarketingService | listGuestDevices | response | items[].lastSeenAt | string (date-time) |  | (nullable)
MarketingService | listGuestDevices | response | items[].revokedAt | string (date-time) |  | (nullable)
MarketingService | listGuestDevices | response | nextCursor | string
MarketingService | listGuestDevices | response | hasMore | boolean | yes
MarketingService | listGuestDevices | param (path) | subjectId | string (uuid) | yes
MarketingService | listGuestDevices | param (query) | pageSize | integer
MarketingService | listGuestDevices | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
WhiteLabelService | listGuidedChoices | response | items | array of GuidedChoice | yes
WhiteLabelService | listGuidedChoices | response | items[].id | string (uuid) | yes | UUIDv7. (read-only)
WhiteLabelService | listGuidedChoices | response | items[].venueId | string (uuid) | yes | From the path of createGuidedChoice. (read-only)
WhiteLabelService | listGuidedChoices | response | items[].name | string | yes | Staff-facing name, e.g. (max length 80)
WhiteLabelService | listGuidedChoices | response | items[].mode | enum (button, popupOnArrival, off) | yes | How the guest reaches it (rev 3 REV3-11). (default button)
WhiteLabelService | listGuidedChoices | response | items[].showBanner | boolean |  | The dark banner under the products ("Choose from the experiences above or let us help you decide") with a Help me choose button. (default True)
WhiteLabelService | listGuidedChoices | response | items[].behaviour | enum (filter, recommend) |  | filter (default) narrows the list; recommend ends on one result card (decided 29 September, W4). (default filter)
WhiteLabelService | listGuidedChoices | response | items[].showEverything | boolean |  | The "Show everything" link under a filtered list, which clears the answers (W4). (default True)
WhiteLabelService | listGuidedChoices | response | items[].questions | array of object | yes | One to four questions (decided 29 September, W4: the Deep Dive reference asks three or four; rev 3 REV3-11 allowed two). (min items 1; max items 4)
WhiteLabelService | listGuidedChoices | response | items[].questions[].id | string (uuid) |  | UUIDv7. (read-only)
WhiteLabelService | listGuidedChoices | response | items[].questions[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | listGuidedChoices | response | items[].questions[].kind | enum (choice, yesNo, age, level, certification) |  | What the question asks (decided 29 September, W4). (default choice)
WhiteLabelService | listGuidedChoices | response | items[].questions[].sortOrder | integer | yes | (min 0)
WhiteLabelService | listGuidedChoices | response | items[].questions[].answers | array of object | yes | Two to four answers; the prototype shows three (proposed, client to correct, rev 3 REV3-11). (min items 2; max items 4)
WhiteLabelService | listGuidedChoices | response | items[].status | object | yes | (read-only)
WhiteLabelService | listGuidedChoices | response | items[].source | enum (manual, aiSuggested) | yes | manual when staff created it; aiSuggested when the ai service proposed it (a service caller). (read-only)
WhiteLabelService | listGuidedChoices | response | items[].suggestionRef | string |  | For aiSuggested, the id of the ai job that proposed it. (read-only; nullable)
WhiteLabelService | listGuidedChoices | response | items[].publishedAt | string (date-time) |  | (read-only; nullable)
WhiteLabelService | listGuidedChoices | response | items[].publishedBy | string (uuid) |  | The person who published it. (read-only; nullable)
WhiteLabelService | listGuidedChoices | response | items[].updatedAt | string (date-time) |  | (read-only)
WhiteLabelService | listGuidedChoices | response | nextCursor | string
WhiteLabelService | listGuidedChoices | response | hasMore | boolean | yes
WhiteLabelService | listGuidedChoices | param (path) | venueId | string (uuid) | yes
WhiteLabelService | listGuidedChoices | param (query) | status | GuidedChoiceStatus: enum (draft, published)
WhiteLabelService | listGuidedChoices | param (query) | source | enum (manual, aiSuggested)
WhiteLabelService | listGuidedChoices | param (query) | pageSize | integer
WhiteLabelService | listGuidedChoices | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
OrderService | listInstalmentPlans | response | items | array of PayInstalmentPlan | yes
OrderService | listInstalmentPlans | response | items[].id | string (uuid) | yes
OrderService | listInstalmentPlans | response | items[].orderId | string (uuid) | yes
OrderService | listInstalmentPlans | response | items[].subjectId | string (uuid) |  | (nullable)
OrderService | listInstalmentPlans | response | items[].frequency | enum (monthly, quarterly, custom) | yes
OrderService | listInstalmentPlans | response | items[].paymentTokenId | string (uuid)
OrderService | listInstalmentPlans | response | items[].status | enum (active, completed, inArrears, cancelled) | yes
OrderService | listInstalmentPlans | response | items[].total | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listInstalmentPlans | response | items[].total.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listInstalmentPlans | response | items[].total.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listInstalmentPlans | response | items[].total.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listInstalmentPlans | response | items[].paidToDate | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listInstalmentPlans | response | items[].paidToDate.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listInstalmentPlans | response | items[].paidToDate.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listInstalmentPlans | response | items[].paidToDate.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listInstalmentPlans | response | items[].nextDueDate | string (date) |  | (nullable)
OrderService | listInstalmentPlans | response | items[].instalments | array of PayInstalment | yes
OrderService | listInstalmentPlans | response | items[].instalments[].sequence | integer | yes | (min 1)
OrderService | listInstalmentPlans | response | items[].instalments[].dueDate | string (date) | yes
OrderService | listInstalmentPlans | response | items[].instalments[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listInstalmentPlans | response | items[].instalments[].status | enum (scheduled, paid, failed, waived, cancelled) | yes
OrderService | listInstalmentPlans | response | items[].instalments[].paymentId | string (uuid) |  | (nullable)
OrderService | listInstalmentPlans | response | items[].instalments[].dunningCaseId | string (uuid) |  | (nullable)
OrderService | listInstalmentPlans | response | items[].instalments[].attemptedAt | string (date-time) |  | (nullable)
OrderService | listInstalmentPlans | response | items[].createdAt | string (date-time)
OrderService | listInstalmentPlans | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
OrderService | listInstalmentPlans | response | nextCursor | string
OrderService | listInstalmentPlans | response | hasMore | boolean | yes
OrderService | listInstalmentPlans | param (query) | orderId | string (uuid)
OrderService | listInstalmentPlans | param (query) | status | enum (active, completed, inArrears, cancelled)
OrderService | listInstalmentPlans | param (query) | pageSize | integer
OrderService | listInstalmentPlans | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
CatalogueService | listInventoryHolds | response | items | array of InventoryHold | yes
CatalogueService | listInventoryHolds | response | items[].id | string | yes
CatalogueService | listInventoryHolds | response | items[].channelCapacityId | string (uuid) | yes
CatalogueService | listInventoryHolds | response | items[].holderKind | InventoryHoldHolderKind: enum (workstation, cart) | yes | Who holds the units (decided 29 September, SD-023). (default workstation)
CatalogueService | listInventoryHolds | response | items[].holderWorkstationId | string (uuid) |  | The holding workstation when holderKind is workstation; null on a cart hold, because a browser has none (SD-023, 29 September). (nullable)
CatalogueService | listInventoryHolds | response | items[].holderCartId | string (uuid) |  | The holding cart (orders.cart) when holderKind is cart (SD-023, 29 September). (nullable)
CatalogueService | listInventoryHolds | response | items[].convertedOrderId | string (uuid) |  | The paid order the hold was converted for, set by convertInventoryHold. (read-only; nullable)
CatalogueService | listInventoryHolds | response | items[].convertedAt | string (date-time) |  | (read-only; nullable)
CatalogueService | listInventoryHolds | response | items[].parentLeaseId | string |  | Present when sub-leased from a venue edge node. (nullable)
CatalogueService | listInventoryHolds | response | items[].requestedUnits | integer
CatalogueService | listInventoryHolds | response | items[].channel | object |  | Allocation this lease draws from.
CatalogueService | listInventoryHolds | response | items[].grantedUnits | integer | yes | May be less than requested — a partial grant is not an error.
CatalogueService | listInventoryHolds | response | items[].consumedUnits | integer | yes
CatalogueService | listInventoryHolds | response | items[].status | LeaseStatus: enum (active, expired, released, forceReleased, converted) | yes | states/lease.yaml.
CatalogueService | listInventoryHolds | response | items[].acquiredAt | string (date-time) | yes
CatalogueService | listInventoryHolds | response | items[].expiresAt | string (date-time) | yes
CatalogueService | listInventoryHolds | response | items[].releasedAt | string (date-time) |  | (nullable)
CatalogueService | listInventoryHolds | response | items[].forceReleasedByPrincipalId | string (uuid) |  | (nullable)
CatalogueService | listInventoryHolds | response | items[].forceReleaseReason | string |  | (nullable)
CatalogueService | listInventoryHolds | response | nextCursor | string
CatalogueService | listInventoryHolds | response | hasMore | boolean | yes
CatalogueService | listInventoryHolds | param (query) | channelCapacityId | string (uuid)
CatalogueService | listInventoryHolds | param (query) | holderWorkstationId | string (uuid)
CatalogueService | listInventoryHolds | param (query) | status | LeaseStatus: enum (active, expired, released, forceReleased, converted)
CatalogueService | listInventoryHolds | param (query) | pageSize | integer
CatalogueService | listInventoryHolds | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
FnbService | listKitchenStations | response | items | array of KitchenStation | yes
FnbService | listKitchenStations | response | items[].id | string (uuid) | yes
FnbService | listKitchenStations | response | items[].code | string | yes
FnbService | listKitchenStations | response | items[].name | string | yes
FnbService | listKitchenStations | response | items[].outletId | string (uuid)
FnbService | listKitchenStations | response | items[].menuItemIds | array of string (uuid) |  | Items routed to this station.
FnbService | listKitchenStations | response | items[].displayWorkstationIds | array of string (uuid) |  | The kitchen displays assigned to this station (decided 28 September, audit R277), as tenancy Workstation ids, primary first and fallbacks after it.
FnbService | listKitchenStations | response | items[].displayEndpoint | string |  | The P15 Kitchen Display device this station's tickets go to (19 Sep: the display is TICVAI software on commodity hardware, per station, with a fallback device where the primary is down — 18 Aug minut… (nullable)
FnbService | listKitchenStations | response | items[].printerDeviceIds | array of string (uuid) |  | The kitchen printers assigned to this station (Chinmay, 2 October, workbook Q187: kitchen printers are in release 1; CHG-CSA-014), as tenancy RegisteredDevice ids of kind receiptPrinter or labelPrint…
FnbService | listKitchenStations | response | items[].servesOutletIds | array of string (uuid) |  | A producing outlet's station serving other outlets (Chinmay, 2 October, workbook Q186 and Q188; DI-330; CHG-CSA-015).
FnbService | listKitchenStations | response | items[].isActive | boolean
FnbService | listKitchenStations | response | nextCursor | string
FnbService | listKitchenStations | response | hasMore | boolean | yes
FnbService | listKitchenStations | param (query) | outletId | string (uuid) |  | One outlet's stations.
FnbService | listKitchenStations | param (query) | pageSize | integer
FnbService | listKitchenStations | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
FnbService | listKitchenTickets | response | items | array of KitchenTicket | yes
FnbService | listKitchenTickets | response | items[].id | string (uuid) | yes
FnbService | listKitchenTickets | response | items[].orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | listKitchenTickets | response | items[].orderNumber | string
FnbService | listKitchenTickets | response | items[].outletId | string (uuid) | yes
FnbService | listKitchenTickets | response | items[].tableLabel | string |  | (nullable)
FnbService | listKitchenTickets | response | items[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | listKitchenTickets | response | items[].coursing | object |  | BL-131. (nullable)
FnbService | listKitchenTickets | response | items[].buzzerCode | string |  | BL-128. (nullable)
FnbService | listKitchenTickets | response | items[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | listKitchenTickets | response | items[].priority | integer |  | Higher fires sooner.
FnbService | listKitchenTickets | response | items[].prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | listKitchenTickets | response | items[].prioritiseReason | string |  | (nullable)
FnbService | listKitchenTickets | response | items[].lines | array of object | yes
FnbService | listKitchenTickets | response | items[].lines[].lineId | string (uuid) | yes
FnbService | listKitchenTickets | response | items[].lines[].name | string | yes
FnbService | listKitchenTickets | response | items[].lines[].quantity | integer | yes
FnbService | listKitchenTickets | response | items[].lines[].modifiers | array of string
FnbService | listKitchenTickets | response | items[].lines[].note | string |  | (nullable)
FnbService | listKitchenTickets | response | items[].lines[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | listKitchenTickets | response | items[].lines[].refireOfLineId | string (uuid) |  | Set on a refire. (read-only; nullable)
FnbService | listKitchenTickets | response | items[].lines[].refireReason | object |  | (read-only; nullable)
FnbService | listKitchenTickets | response | items[].lines[].isChargeable | boolean |  | A refire's chargeable flag. (read-only; nullable)
FnbService | listKitchenTickets | response | items[].lines[].course | integer |  | (nullable)
FnbService | listKitchenTickets | response | items[].lines[].stationId | string (uuid) |  | (nullable)
FnbService | listKitchenTickets | response | items[].lines[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | listKitchenTickets | response | items[].createdAt | string (date-time) | yes
FnbService | listKitchenTickets | response | items[].targetReadyAt | string (date-time) |  | (nullable)
FnbService | listKitchenTickets | response | items[].elapsedSeconds | integer
FnbService | listKitchenTickets | response | items[].visitId | string (uuid) |  | The table visit the ticket is for (4 October 2026, CHG-FXC-011; KIT-002): the {visitId} notifyServer takes. (read-only; nullable)
FnbService | listKitchenTickets | response | nextCursor | string
FnbService | listKitchenTickets | response | hasMore | boolean | yes
FnbService | listKitchenTickets | param (query) | stationId | string (uuid) |  | Route to a preparation station — grill, cold, bar.
FnbService | listKitchenTickets | param (query) | status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled)
FnbService | listKitchenTickets | param (query) | course | integer |  | The course filter (decided 28 September, audit R277).
FnbService | listKitchenTickets | param (query) | pageSize | integer
FnbService | listKitchenTickets | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
WhiteLabelService | listLandingPageTemplates | response | items | array of LandingPageTemplate | yes
WhiteLabelService | listLandingPageTemplates | response | items[].templateKey | string | yes
WhiteLabelService | listLandingPageTemplates | response | items[].name | string | yes
WhiteLabelService | listLandingPageTemplates | response | items[].presetKey | string |  | The Site Builder preset it belongs to (SiteSetupProgress.presetKey). (nullable)
WhiteLabelService | listLandingPageTemplates | response | items[].thumbnailUrl | string |  | (nullable)
WhiteLabelService | listLandingPageTemplates | response | items[].layout | HomepageLayout | yes | The client-approved web and app wireframes are the layout (Chinmay, 2 October, workbook Q163; CHG-CSA-040): sections, their order and their options follow the approved wireframes and change only wher…
WhiteLabelService | listLandingPageTemplates | response | items[].layout.templateKey | string |  | The landing-page template this layout started from (listLandingPageTemplates), or null for a layout composed from scratch (CHG-CSA-037). (nullable)
WhiteLabelService | listLandingPageTemplates | response | items[].layout.landingSource | enum (storefront, ownSite) |  | storefront: this home is the tenant's landing page. (default storefront)
WhiteLabelService | listLandingPageTemplates | response | items[].layout.id | string (uuid) |  | Added 20 August. (read-only)
WhiteLabelService | listLandingPageTemplates | response | items[].layout.sections | array of object | yes
WhiteLabelService | listLandingPageTemplates | response | nextCursor | string
WhiteLabelService | listLandingPageTemplates | response | hasMore | boolean | yes
WhiteLabelService | listLandingPageTemplates | param (query) | pageSize | integer
WhiteLabelService | listLandingPageTemplates | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
MarketingService | listLeaderboard | response | items | array of LeaderboardEntry | yes
MarketingService | listLeaderboard | response | items[].rank | integer | yes | (min 1)
MarketingService | listLeaderboard | response | items[].nickname | string | yes | Always present, and never their real name.
MarketingService | listLeaderboard | response | items[].points | integer | yes
MarketingService | listLeaderboard | response | items[].isMe | boolean |  | How a client highlights the caller's own row without learning who anybody else is. (default False)
MarketingService | listLeaderboard | response | nextCursor | string
MarketingService | listLeaderboard | response | hasMore | boolean | yes
MarketingService | listLeaderboard | param (query) | programmeId | string (uuid) | yes
MarketingService | listLeaderboard | param (query) | window | enum (week, month, season) |  | Monthly, confirmed 20 September.
MarketingService | listLeaderboard | param (query) | pageSize | integer
MarketingService | listLeaderboard | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
MarketingService | listLoyaltyProgrammes | response | items | array of LoyaltyProgramme | yes
MarketingService | listLoyaltyProgrammes | response | items[].tiers | array of MarketingProgrammeTier | yes | Rows of marketing.programme_tier, the same shape MarketingProgrammeTier has — one definition of a tier, not a second copy that cannot round-trip.
MarketingService | listLoyaltyProgrammes | response | items[].tiers[].id | string (uuid) |  | (read-only)
MarketingService | listLoyaltyProgrammes | response | items[].tiers[].loyaltyProgrammeId | string (uuid) | yes | (read-only)
MarketingService | listLoyaltyProgrammes | response | items[].tiers[].code | string | yes | (max length 40)
MarketingService | listLoyaltyProgrammes | response | items[].tiers[].name | string | yes | (max length 120)
MarketingService | listLoyaltyProgrammes | response | items[].tiers[].rank | integer | yes | Order, not threshold.
MarketingService | listLoyaltyProgrammes | response | items[].tiers[].minLifetimePoints | integer |  | What reaching this tier requires. (nullable)
MarketingService | listLoyaltyProgrammes | response | items[].tiers[].retainLifetimePoints | integer |  | What keeping it requires, per review period. (nullable)
MarketingService | listLoyaltyProgrammes | response | items[].tiers[].validityMonths | integer |  | Null means the tier does not lapse on its own. (nullable)
MarketingService | listLoyaltyProgrammes | response | items[].tiers[].benefits | array of string |  | What the tier gives, as the guest reads it.
MarketingService | listLoyaltyProgrammes | response | items[].tiers[].earnMultiplier | number |  | Applied to every earn rule while the guest holds this tier. (nullable)
MarketingService | listLoyaltyProgrammes | response | items[].tiers[].isActive | boolean |  | (default True)
MarketingService | listLoyaltyProgrammes | response | items[].id | string (uuid) | yes | (read-only)
MarketingService | listLoyaltyProgrammes | response | items[].code | string | yes | Unique per tenant (decided 28 September, audit R108).
MarketingService | listLoyaltyProgrammes | response | items[].name | string | yes
MarketingService | listLoyaltyProgrammes | response | items[].venueId | string (uuid) |  | (nullable)
MarketingService | listLoyaltyProgrammes | response | items[].pointsLiabilityAccountId | string (uuid) |  | Points post here on accrual.
MarketingService | listLoyaltyProgrammes | response | items[].earnRules | array of object | yes
MarketingService | listLoyaltyProgrammes | response | items[].earnRules[].trigger | enum (perCurrencyUnit, perVisit, perProduct, onSignup, onBirthday, onReview) | yes
MarketingService | listLoyaltyProgrammes | response | items[].earnRules[].points | number | yes
MarketingService | listLoyaltyProgrammes | response | items[].earnRules[].productKinds | array of ProductKind: enum (admission, timedAdmission, datedAdmission, openDated, seated, membership, bundle, fnb, …) |  | Limits a perProduct or perCurrencyUnit rule to these kinds.
MarketingService | listLoyaltyProgrammes | response | items[].earnRules[].multiplier | number
MarketingService | listLoyaltyProgrammes | response | items[].pointsExpireAfterMonths | integer |  | (nullable)
MarketingService | listLoyaltyProgrammes | response | items[].isActive | boolean
MarketingService | listLoyaltyProgrammes | response | nextCursor | string
MarketingService | listLoyaltyProgrammes | response | hasMore | boolean | yes
MarketingService | listLoyaltyProgrammes | param (query) | pageSize | integer
MarketingService | listLoyaltyProgrammes | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
RetailService | listMerchandise | response | items | array of MerchandiseItem or GuestMerchandiseItem | yes
RetailService | listMerchandise | response | nextCursor | string
RetailService | listMerchandise | response | hasMore | boolean | yes
RetailService | listMerchandise | param (query) | outletId | string (uuid) |  | Exact match.
RetailService | listMerchandise | param (query) | categoryId | string (uuid) |  | Exact match on categoryId.
RetailService | listMerchandise | param (query) | inStockOnly | boolean |  | True returns only items with onHand greater than zero at their own outlet.
RetailService | listMerchandise | param (query) | search | string |  | Case-insensitive "contains" match over name, sku, barcode and description.
RetailService | listMerchandise | param (query) | pageSize | integer
RetailService | listMerchandise | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
MarketingService | listMyCases | response | items | array of Case | yes
MarketingService | listMyCases | response | items[].id | string (uuid) | yes | Created on the device (CreateCaseRequest.id, raiseMyCase), so a UUIDv7.
MarketingService | listMyCases | response | items[].caseNumber | string | yes | Server-assigned: the venue prefix plus a sequence per venue (decided 28 September, audit R152). (read-only)
MarketingService | listMyCases | response | items[].subjectId | string (uuid) |  | (nullable)
MarketingService | listMyCases | response | items[].guestName | string |  | Resolved from pii.subject when the case is read, never stored on the case. (read-only; nullable)
MarketingService | listMyCases | response | items[].subject | string | yes | The case's one-line title, not a person.
MarketingService | listMyCases | response | items[].kind | object |  | What the guest said it was about, where the guest raised it. (nullable)
MarketingService | listMyCases | response | items[].channel | object |  | How the guest reached the venue — CreateCaseRequest.channel, or inApp for a case raised through raiseMyCase.
MarketingService | listMyCases | response | items[].recordedAt | string (date-time) |  | Device time the case was raised — the start of the SLA clock.
MarketingService | listMyCases | response | items[].syncedAt | string (date-time) |  | Server time the case arrived. (read-only)
MarketingService | listMyCases | response | items[].categoryId | string (uuid) |  | (nullable)
MarketingService | listMyCases | response | items[].queueId | string (uuid) |  | The ServiceQueue the case waits in, set by routing (CaseRoutingRule.queueId). (nullable)
MarketingService | listMyCases | response | items[].membershipId | string (uuid) |  | The identity membership this case concerns (identity.customer_membership); member case notes are cases with this set. (nullable)
MarketingService | listMyCases | response | items[].status | CaseStatus: enum (open, inProgress, awaitingGuest, escalated, resolved, closed) | yes
MarketingService | listMyCases | response | items[].priority | CasePriority: enum (low, normal, high, urgent) | yes
MarketingService | listMyCases | response | items[].assignedToPrincipalId | string (uuid) |  | (nullable)
MarketingService | listMyCases | response | items[].venueId | string (uuid) |  | (nullable)
MarketingService | listMyCases | response | items[].relatedOrderId | string |  | (nullable)
MarketingService | listMyCases | response | items[].slaDueAt | string (date-time) |  | (nullable)
MarketingService | listMyCases | response | items[].isSlaBreached | boolean |  | Computed when read, never stored. (read-only)
MarketingService | listMyCases | response | items[].slaPausedSeconds | integer |  | Accrued only while awaiting the guest.
MarketingService | listMyCases | response | items[].escalationCount | integer
MarketingService | listMyCases | response | items[].createdAt | string (date-time) | yes
MarketingService | listMyCases | response | items[].resolvedAt | string (date-time) |  | (nullable)
MarketingService | listMyCases | response | nextCursor | string
MarketingService | listMyCases | response | hasMore | boolean | yes
MarketingService | listMyCases | param (query) | pageSize | integer
MarketingService | listMyCases | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
AccessService | listMyEntitlements | response | items | array of Entitlement | yes
AccessService | listMyEntitlements | response | items[].id | string (uuid) | yes | A UUIDv7, matching TicketStatus.ticketId — stable for the life of the ticket and independent of the media carrying it.
AccessService | listMyEntitlements | response | items[].templateId | string (uuid) | yes | The definition it was issued against.
AccessService | listMyEntitlements | response | items[].productId | string (uuid) | yes
AccessService | listMyEntitlements | response | items[].orderId | string (uuid) | yes | The order's id, a UUIDv7 as in /orders/{orderId} (orders.sales_order.id). (nullable)
AccessService | listMyEntitlements | response | items[].orderLineId | string (uuid)
AccessService | listMyEntitlements | response | items[].subjectId | string (uuid) | yes | Who holds it. (nullable)
AccessService | listMyEntitlements | response | items[].venueId | string (uuid)
AccessService | listMyEntitlements | response | items[].scopePath | string
AccessService | listMyEntitlements | response | items[].mediaCode | string |  | What is scanned — a QR payload, a wristband serial, a card number.
AccessService | listMyEntitlements | response | items[].credentialFormat | object |  | The credential this entitlement was issued with, resolved once at issue by issueOrderEntitlements: the product's credentialFormatOverride, else the sales channel's ticketCredentialFormat, else platfo… (nullable)
AccessService | listMyEntitlements | response | items[].status | EntitlementStatus: enum (issued, partiallyConsumed, fullyConsumed, expired, cancelled, surrendered) | yes | What the storage layer holds, and what a guest is shown.
AccessService | listMyEntitlements | response | items[].statusNote | string |  | Not TicketStatus — that is a validation result with a misleading name, computed at scan time and carrying isValid and isInsideVenue. (nullable)
AccessService | listMyEntitlements | response | items[].validFrom | string (date-time) | yes
AccessService | listMyEntitlements | response | items[].validTo | string (date-time) | yes | Resolved at issue from the template, then owned here.
AccessService | listMyEntitlements | response | items[].entriesUsed | integer |  | The number validateAccess decrements and nothing was decrementing. (default 0; read-only)
AccessService | listMyEntitlements | response | items[].entriesAllowed | integer |  | (nullable)
AccessService | listMyEntitlements | response | items[].lastEntryAt | string (date-time) |  | recordedAt of the latest admission counted in entriesUsed, written by the same writes. (read-only; nullable)
AccessService | listMyEntitlements | response | items[].firstEntryAt | string (date-time) |  | recordedAt of the first admission, written by the same writes as lastEntryAt; it starts a time-bound entitlement's window (DEC-232; CHG-CSP-030). (read-only; nullable)
AccessService | listMyEntitlements | response | items[].timeBoundUntil | string (date-time) |  | Where the template is time-bound, when its window closes: firstEntryAt plus the validity rule's minutesAfterFirstScan (decided 2 October 2026, Chinmay, BO-159; DEC-232; CHG-CSP-030). (read-only; nullable)
AccessService | listMyEntitlements | response | items[].lifecycleLabel | enum (created, pendingFulfillment, active, partiallyUsed, used, expired, suspended, cancelled, …) |  | The Virtual Ticket status in the client's 13 names, mapped onto the entitlement model (decided 2 October 2026, Chinmay, critical set 2, BO-336: "Map the pack's 13 names onto the model; add any missin… (read-only)
AccessService | listMyEntitlements | response | items[].cancellationKind | enum (voided, refunded, performanceCancelled, superseded) |  | Which act cancelled the entitlement, so the pack's Voided, Refunded and Reissued / superseded are told apart while status keeps the one r1 value cancelled (DEC-266; CHG-CSP-033). (read-only; nullable)
AccessService | listMyEntitlements | response | items[].frozenDays | integer |  | Days added by a freeze. (default 0; read-only)
AccessService | listMyEntitlements | response | items[].suspendedReason | string |  | (nullable)
AccessService | listMyEntitlements | response | items[].freezeReason | enum (travelling, injury, personal, seasonal, other) |  | The reason of the latest freezeEntitlement (audit R222). (nullable)
AccessService | listMyEntitlements | response | items[].freezeNote | string |  | The note the latest freezeEntitlement took, required there when reason is other (decided 28 September, audit R222). (max length 500; nullable)
AccessService | listMyEntitlements | response | items[].isNameBound | boolean |  | (default False)
AccessService | listMyEntitlements | response | items[].holderName | string |  | (nullable)
AccessService | listMyEntitlements | response | items[].sharedWithSubjectIds | array of string (uuid) |  | shareEntitlement.
AccessService | listMyEntitlements | response | items[].issuedVia | enum (sale, invitation, reissue, transfer, resale, membership, groupBooking) |  | How it came to exist, and it matters to finance.
AccessService | listMyEntitlements | response | items[].supersedesEntitlementId | string (uuid) |  | For a reissue or a resale. (nullable)
AccessService | listMyEntitlements | response | items[].walletValueId | string (uuid) |  | Where the template carries stored value. (nullable)
AccessService | listMyEntitlements | response | items[].facePassEnrolmentId | string (uuid) |  | The active facePass enrolment on this entitlement (FacePassEnrolment.id), or null when none is. (read-only; nullable)
AccessService | listMyEntitlements | response | items[].invitationId | string (uuid) |  | The invitation that issued it (4 October 2026, CHG-FXC-007): orders.issueInvitation issues the entitlement without an order, because an invitation never enters the order path. (nullable)
AccessService | listMyEntitlements | response | nextCursor | string
AccessService | listMyEntitlements | response | hasMore | boolean | yes
AccessService | listMyEntitlements | param (header) | X-Consistency-Token | string |  | Opaque token returned by a prior write: the database instance and its WAL LSN (SD-025, 29 September; ADR-0040 allows several instances per region, so an LSN alone is ambiguous).
AccessService | listMyEntitlements | param (query) | state | enum (usableNow, upcoming, expired, all)
AccessService | listMyEntitlements | param (query) | includeShared | boolean |  | Entitlements shared with this guest by somebody else (shareEntitlement).
AccessService | listMyEntitlements | param (query) | pageSize | integer
AccessService | listMyEntitlements | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
VenueOpsService | listMyFavouriteRoutes | response | items | array of FavouriteRoute | yes
VenueOpsService | listMyFavouriteRoutes | response | items[].id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | listMyFavouriteRoutes | response | items[].venueId | string (uuid) | yes
VenueOpsService | listMyFavouriteRoutes | response | items[].fromStationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | listMyFavouriteRoutes | response | items[].toStationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | listMyFavouriteRoutes | response | items[].fromStationName | string |  | (read-only)
VenueOpsService | listMyFavouriteRoutes | response | items[].toStationName | string |  | (read-only)
VenueOpsService | listMyFavouriteRoutes | response | items[].label | string |  | (nullable)
VenueOpsService | listMyFavouriteRoutes | response | items[].adultFare | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | listMyFavouriteRoutes | response | items[].adultFare.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | listMyFavouriteRoutes | response | items[].adultFare.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | listMyFavouriteRoutes | response | items[].adultFare.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | listMyFavouriteRoutes | response | items[].createdAt | string (date-time) | yes
VenueOpsService | listMyFavouriteRoutes | response | items[].subjectId | string (uuid) |  | The guest who saved it (4 October 2026, CHG-FXC-003; transport.favourite_route had no owner column). (read-only)
VenueOpsService | listMyFavouriteRoutes | response | nextCursor | string
VenueOpsService | listMyFavouriteRoutes | response | hasMore | boolean | yes
VenueOpsService | listMyFavouriteRoutes | param (query) | venueId | string (uuid) | yes
VenueOpsService | listMyFavouriteRoutes | param (query) | pageSize | integer
VenueOpsService | listMyFavouriteRoutes | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
MarketingService | listMyNotifications | response | items | array of GuestNotification | yes
MarketingService | listMyNotifications | response | items[].id | string | yes
MarketingService | listMyNotifications | response | items[].kind | enum (queueCall, orderReady, bookingChange, venueAlert, offer, other)
MarketingService | listMyNotifications | response | items[].title | LocalisedText | yes | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | listMyNotifications | response | items[].body | LocalisedText |  | Text keyed by locale code, one entry per locale the venue publishes.
MarketingService | listMyNotifications | response | items[].venueId | string (uuid) |  | (nullable)
MarketingService | listMyNotifications | response | items[].deepLink | string |  | Where tapping the notification leads in the app (an order, a queue ticket, a booking). (nullable)
MarketingService | listMyNotifications | response | items[].queuedAt | string (date-time) | yes
MarketingService | listMyNotifications | response | items[].read | boolean | yes
MarketingService | listMyNotifications | response | nextCursor | string
MarketingService | listMyNotifications | response | hasMore | boolean | yes
MarketingService | listMyNotifications | response | unreadCount | integer |  | (min 0)
MarketingService | listMyNotifications | param (query) | pageSize | integer
MarketingService | listMyNotifications | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
MarketingService | listMyNotifications | param (query) | unreadOnly | boolean
MarketingService | listMyNotifications | param (query) | venueId | string (uuid) |  | Only notifications from this venue.
OrderService | listMyOrders | response | items | array of Order | yes
OrderService | listMyOrders | response | items[].id | string (uuid) | yes | The client UUIDv7 from CreateOrderRequest.id.
OrderService | listMyOrders | response | items[].orderNumber | string |  | The number a guest reads and a cashier types. (read-only)
OrderService | listMyOrders | response | items[].channel | object | yes | Where it came from.
OrderService | listMyOrders | response | items[].channelProfileId | string (uuid) |  | The named sales channel the order came through (catalogue SalesChannelProfile.id), set by the server from the caller: a partner user's or reseller's channel, an API key's channel. (read-only; nullable)
OrderService | listMyOrders | response | items[].venueId | string (uuid) | yes
OrderService | listMyOrders | response | items[].scopePath | string | yes
OrderService | listMyOrders | response | items[].status | OrderStatus: enum (pending, held, paid, partiallyPaid, completed, voided, refunded, partiallyRefunded, …) | yes | held is a parked sale — the cashier freed the till and the guest will return.
OrderService | listMyOrders | response | items[].currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | listMyOrders | response | items[].currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | listMyOrders | response | items[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listMyOrders | response | items[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listMyOrders | response | items[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listMyOrders | response | items[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listMyOrders | response | items[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listMyOrders | response | items[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listMyOrders | response | items[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listMyOrders | response | items[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listMyOrders | response | items[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listMyOrders | response | items[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listMyOrders | response | items[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listMyOrders | response | items[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listMyOrders | response | items[].refundedAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listMyOrders | response | items[].refundedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listMyOrders | response | items[].refundedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listMyOrders | response | items[].refundedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listMyOrders | response | items[].chargeCurrency | string |  | The currency the guest selected and is charged in (CHG-FIN-001, 2 October 2026). (pattern ^[A-Z]{3}$; read-only; nullable)
OrderService | listMyOrders | response | items[].chargeFxRate | object |  | Units of chargeCurrency per one unit of the base currency, from the region's tender rate in force at checkout (finance.FxRate), stored on the order so the payment, the receipt, the tax invoice and an… (read-only; nullable)
OrderService | listMyOrders | response | items[].chargeFxRateId | string (uuid) |  | The finance.FxRate row the rate was taken from, for audit. (read-only; nullable)
OrderService | listMyOrders | response | items[].chargeTotal | object |  | grossAmount converted at chargeFxRate and rounded to the charge currency's scale: what the guest pays and what the payment request to the provider asks for (CHG-FIN-001). (read-only)
OrderService | listMyOrders | response | items[].chargeTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listMyOrders | response | items[].chargeTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listMyOrders | response | items[].chargeTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listMyOrders | response | items[].chargeRateLockedUntil | string (date-time) |  | The quote holds until then (the cart lease). (read-only; nullable)
OrderService | listMyOrders | response | items[].droppedPromotions | array of object |  | Promotions left off this order at checkout because their budget cap would have been exceeded (decided 28 September, audit R101 (8)). (read-only)
OrderService | listMyOrders | response | items[].droppedPromotions[].promotionId | string (uuid) | yes
OrderService | listMyOrders | response | items[].droppedPromotions[].name | string
OrderService | listMyOrders | response | items[].droppedPromotions[].reason | enum (budgetCapReached)
OrderService | listMyOrders | response | items[].totalPriceVariance | object |  | Sum across lines.
OrderService | listMyOrders | response | items[].totalPriceVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listMyOrders | response | items[].totalPriceVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listMyOrders | response | items[].totalPriceVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listMyOrders | response | items[].lines | array of OrderLine | yes
OrderService | listMyOrders | response | items[].lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | listMyOrders | response | items[].lines[].variantId | string (uuid) | yes
OrderService | listMyOrders | response | items[].lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | listMyOrders | response | items[].lines[].performanceId | string (uuid)
OrderService | listMyOrders | response | items[].lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | listMyOrders | response | items[].lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | listMyOrders | response | items[].lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | listMyOrders | response | items[].lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | listMyOrders | response | items[].lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | listMyOrders | response | items[].lines[].quantity | integer | yes | (min 1)
OrderService | listMyOrders | response | items[].lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | listMyOrders | response | items[].lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | listMyOrders | response | items[].lines[].holderName | string |  | (nullable)
OrderService | listMyOrders | response | items[].lines[].dataMaskValues | object |  | Deliberately open.
OrderService | listMyOrders | response | items[].lines[].serverUnitPrice | object | yes | What the server computed on ingest.
OrderService | listMyOrders | response | items[].lines[].priceVariance | object |  | Server minus quoted.
OrderService | listMyOrders | response | items[].lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listMyOrders | response | items[].lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listMyOrders | response | items[].lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listMyOrders | response | items[].lines[].entitlementIds | array of string (uuid) |  | The entitlements this line issued.
OrderService | listMyOrders | response | items[].lines[].crossRegionRightIds | array of string |  | Redemption rights propagated to other cells for this line.
OrderService | listMyOrders | response | items[].lines[].reprintCount | integer |  | How many times this line's tickets were reprinted or resent. (min 0; default 0; read-only)
OrderService | listMyOrders | response | items[].lines[].venueId | string (uuid) |  | The order's venue, copied onto the line (ADR-0044's own example; system-design review SD-008, 29 September) so a line is scoped and partitionable without its order. (read-only)
OrderService | listMyOrders | response | items[].lines[].discounts | array of OrderLineDiscount |  | The discounts applied to this line, one row each (system-design review SD-008, 29 September). (read-only)
OrderService | listMyOrders | response | items[].payments | array of Payment
OrderService | listMyOrders | response | items[].payments[].id | string (uuid) | yes
OrderService | listMyOrders | response | items[].payments[].orderId | string (uuid) | yes
OrderService | listMyOrders | response | items[].payments[].tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) | yes | wallet is a digital wallet (Apple Pay, Google Pay and the like, taken through the gateway), the value the guest channels accept beside card (decided 28 September, audit R080 (a)).
OrderService | listMyOrders | response | items[].payments[].tenderCurrency | string |  | 4.6.11. (pattern ^[A-Z]{3}$)
OrderService | listMyOrders | response | items[].payments[].tenderAmount | object |  | The amount in tenderCurrency, at that currency's own scale.
OrderService | listMyOrders | response | items[].payments[].fxRate | object |  | The rate applied, stored on the payment rather than looked up later (CF-37). (nullable)
OrderService | listMyOrders | response | items[].payments[].fxRateSource | enum (manual, feed, cardScheme) |  | 4.2.8. (nullable)
OrderService | listMyOrders | response | items[].payments[].changeCurrency | string |  | 4.6.11 is deliberately asymmetric: accept foreign currency, refund in local. (pattern ^[A-Z]{3}$; nullable)
OrderService | listMyOrders | response | items[].payments[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listMyOrders | response | items[].payments[].changeAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listMyOrders | response | items[].payments[].status | enum (authorised, captured, pendingConfirmation, declined, failed, voided, refunded) | yes
OrderService | listMyOrders | response | items[].payments[].providerName | string |  | (nullable)
OrderService | listMyOrders | response | items[].payments[].providerReference | string |  | The provider's own id for the charge (Stripe PaymentIntent, NI order reference). (nullable)
OrderService | listMyOrders | response | items[].payments[].providerIdempotencyKey | string |  | The idempotency key sent to the provider, which is this payment's id (SD-034, 29 September). (read-only; nullable)
OrderService | listMyOrders | response | items[].payments[].terminalId | string (uuid) |  | The card terminal a till payment ran on (ECR flow, SD-034). (nullable)
OrderService | listMyOrders | response | items[].payments[].nextAction | object |  | What the caller does while the payment is pendingConfirmation (SD-034, 29 September). (nullable)
OrderService | listMyOrders | response | items[].payments[].lastInquiryAt | string (date-time) |  | (nullable)
OrderService | listMyOrders | response | items[].payments[].recordedAt | string (date-time) | yes
OrderService | listMyOrders | response | items[].payments[].syncedAt | string (date-time) |  | (nullable)
OrderService | listMyOrders | response | items[].principalId | string (uuid)
OrderService | listMyOrders | response | items[].workstationId | string (uuid)
OrderService | listMyOrders | response | items[].shiftId | string (uuid) |  | (nullable)
OrderService | listMyOrders | response | items[].subjectId | string (uuid) |  | (nullable)
OrderService | listMyOrders | response | items[].holdLabel | string |  | The label a cashier gave when parking it with holdOrder — how they find it again. (max length 60; read-only; nullable)
OrderService | listMyOrders | response | items[].heldUntil | string (date-time) |  | When a held order expires and is voided (states/order.yaml), from holdOrder's holdUntil. (read-only; nullable)
OrderService | listMyOrders | response | items[].createdAt | string (date-time) | yes
OrderService | listMyOrders | response | items[].recordedAt | string (date-time) | yes
OrderService | listMyOrders | response | items[].syncedAt | string (date-time) |  | (nullable)
OrderService | listMyOrders | response | nextCursor | string
OrderService | listMyOrders | response | hasMore | boolean | yes
OrderService | listMyOrders | param (header) | X-Consistency-Token | string |  | Opaque token returned by a prior write: the database instance and its WAL LSN (SD-025, 29 September; ADR-0040 allows several instances per region, so an LSN alone is ambiguous).
OrderService | listMyOrders | param (query) | since | string (date) |  | Only orders whose createdAt falls on or after this date.
OrderService | listMyOrders | param (query) | pageSize | integer
OrderService | listMyOrders | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
OrderService | listMyPaymentIssues | response | items | array of DunningCase | yes
OrderService | listMyPaymentIssues | response | items[].id | string (uuid) | yes
OrderService | listMyPaymentIssues | response | items[].subjectId | string (uuid)
OrderService | listMyPaymentIssues | response | items[].orderId | string |  | The order whose renewal failed.
OrderService | listMyPaymentIssues | response | items[].amount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listMyPaymentIssues | response | items[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listMyPaymentIssues | response | items[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listMyPaymentIssues | response | items[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listMyPaymentIssues | response | items[].state | DunningState: enum (scheduled, inProgress, exhausted, recovered, resolvedManually) | yes | BL-100.
OrderService | listMyPaymentIssues | response | items[].declineClass | object |  | From the most recent attempt.
OrderService | listMyPaymentIssues | response | items[].attemptsMade | integer | yes
OrderService | listMyPaymentIssues | response | items[].nextAttemptAt | string (date-time) |  | Null where the case has ended or the decline is hard. (nullable)
OrderService | listMyPaymentIssues | response | items[].firstFailedAt | string (date-time) | yes
OrderService | listMyPaymentIssues | response | items[].resolvedAt | string (date-time) |  | (nullable)
OrderService | listMyPaymentIssues | response | items[].resolution | enum (paidByOtherMeans, cardReplaced, writeOff, cancelledByGuest, None) |  | (nullable)
OrderService | listMyPaymentIssues | response | items[].resolutionNote | string |  | What resolveDunningCase was told, which had nowhere to land until now. (max length 500; nullable)
OrderService | listMyPaymentIssues | response | items[].resolvedByPrincipalId | string (uuid) |  | Who closed it. (read-only; nullable)
OrderService | listMyPaymentIssues | response | items[].scopePath | string |  | The partition key (ADR-0005).
OrderService | listMyPaymentIssues | response | nextCursor | string
OrderService | listMyPaymentIssues | response | hasMore | boolean | yes
OrderService | listMyPaymentIssues | param (query) | pageSize | integer
OrderService | listMyPaymentIssues | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
FnbService | listMyTableReservations | response | items | array of MyTableBooking | yes
FnbService | listMyTableReservations | response | items[].kind | enum (reservation, waitlist) | yes
FnbService | listMyTableReservations | response | items[].outletId | string (uuid) | yes
FnbService | listMyTableReservations | response | items[].outletName | string
FnbService | listMyTableReservations | response | items[].reservation | object |  | (nullable)
FnbService | listMyTableReservations | response | items[].reservation.id | string (uuid) |  | (read-only)
FnbService | listMyTableReservations | response | items[].reservation.outletId | string (uuid) | yes
FnbService | listMyTableReservations | response | items[].reservation.subjectId | string (uuid) |  | (nullable)
FnbService | listMyTableReservations | response | items[].reservation.guestName | string
FnbService | listMyTableReservations | response | items[].reservation.contactPoint | string
FnbService | listMyTableReservations | response | items[].reservation.partySize | integer | yes | (min 1)
FnbService | listMyTableReservations | response | items[].reservation.startsAt | string (date-time) | yes
FnbService | listMyTableReservations | response | items[].reservation.durationMinutes | integer |  | How long the cover is held.
FnbService | listMyTableReservations | response | items[].reservation.tables | array of FnbReservationTable |  | The dining tables assigned to this reservation, one row each.
FnbService | listMyTableReservations | response | items[].reservation.status | TableReservationStatus: enum (awaitingDeposit, booked, confirmed, seated, completed, cancelled, noShow) |  | awaitingDeposit only where the venue's dining deposit applies (decided 29 September, rev 3 REV3-8b); a booking with no deposit starts booked.
FnbService | listMyTableReservations | response | items[].reservation.groupId | string (uuid) |  | 5.1.2. (nullable)
FnbService | listMyTableReservations | response | items[].reservation.notes | string |  | Allergies, accessibility needs and other requests, as the guest wrote them.
FnbService | listMyTableReservations | response | items[].reservation.seatingPreference | string |  | The seating area the guest asked for, e.g. (max length 64; nullable)
FnbService | listMyTableReservations | response | items[].reservation.occasion | enum (birthday, anniversary, business, celebration, other) |  | The occasion the guest named (workbook Q204, DI-337; CHG-CSA-018). (nullable)
FnbService | listMyTableReservations | response | items[].reservation.takenByPrincipalId | string (uuid) |  | The staff member who took the booking (createTableReservationForGuest); null for a guest's own booking (CHG-CSA-045). (read-only; nullable)
FnbService | listMyTableReservations | response | items[].reservation.actualPartySize | integer |  | (read-only; nullable)
FnbService | listMyTableReservations | response | items[].reservation.tableVisitId | string (uuid) |  | (read-only; nullable)
FnbService | listMyTableReservations | response | items[].reservation.deposit | TableReservationDeposit |  | The deposit this booking holds, snapshotted from orders.DepositPolicy.dining when it was made (decided 29 September, rev 3 REV3-8b). (read-only; nullable)
FnbService | listMyTableReservations | response | items[].reservation.createdAt | string (date-time) |  | (read-only)
FnbService | listMyTableReservations | response | items[].waitlistEntry | object |  | (nullable)
FnbService | listMyTableReservations | response | items[].waitlistEntry.id | string (uuid) | yes
FnbService | listMyTableReservations | response | items[].waitlistEntry.outletId | string (uuid) | yes
FnbService | listMyTableReservations | response | items[].waitlistEntry.subjectId | string (uuid) |  | (nullable)
FnbService | listMyTableReservations | response | items[].waitlistEntry.partySize | integer | yes
FnbService | listMyTableReservations | response | items[].waitlistEntry.quotedWaitMinutes | integer |  | (nullable)
FnbService | listMyTableReservations | response | items[].waitlistEntry.seatingPreference | enum (any, indoor, outdoor, bar, booth, highChair) |  | (nullable)
FnbService | listMyTableReservations | response | items[].waitlistEntry.status | enum (waiting, notified, seated, walkedAway, noShow, cancelled) | yes
FnbService | listMyTableReservations | response | items[].waitlistEntry.notifiedAt | string (date-time) |  | (nullable)
FnbService | listMyTableReservations | response | items[].waitlistEntry.recordedAt | string (date-time) | yes | When the party joined, on the device.
FnbService | listMyTableReservations | response | items[].waitlistEntry.syncedAt | string (date-time) |  | (read-only; nullable)
FnbService | listMyTableReservations | response | items[].waitlistEntry.holdExpiresAt | string (date-time) |  | How long a table waits for somebody who was called. (nullable)
FnbService | listMyTableReservations | response | nextCursor | string
FnbService | listMyTableReservations | response | hasMore | boolean | yes
FnbService | listMyTableReservations | param (query) | include | enum (reservations, waitlist) |  | Which kinds to list.
FnbService | listMyTableReservations | param (query) | upcomingOnly | boolean |  | Only bookings from today and live waitlist places (waiting, notified).
FnbService | listMyTableReservations | param (query) | pageSize | integer
FnbService | listMyTableReservations | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
AiService | listOperationalRequirements | response | items | array of AiOperationalRequirement | yes
AiService | listOperationalRequirements | response | items[].id | string (uuid) |  | (read-only)
AiService | listOperationalRequirements | response | items[].versionId | string (uuid) | yes
AiService | listOperationalRequirements | response | items[].kind | enum (staff, pos, kiosk, gates, fnb, retail, stock, resource, …) | yes
AiService | listOperationalRequirements | response | items[].targetContract | string |  | The owning module that applies it: workforce, fnb, inventory, resources, access.
AiService | listOperationalRequirements | response | items[].subjectRef | string |  | A role, outlet, gate, item or resource type. (nullable)
AiService | listOperationalRequirements | response | items[].periodStart | string (date-time) | yes
AiService | listOperationalRequirements | response | items[].periodEnd | string (date-time)
AiService | listOperationalRequirements | response | items[].quantity | number | yes
AiService | listOperationalRequirements | response | items[].quantityP90 | number |  | The requirement at the forecast's 90th percentile, for planning to the busy case. (nullable)
AiService | listOperationalRequirements | response | items[].unit | string
AiService | listOperationalRequirements | response | items[].productivityStandard | object |  | The standard used, e.g. (nullable)
AiService | listOperationalRequirements | response | items[].status | enum (issued, accepted, modified, rejected, handedOver, expired) |  | (read-only)
AiService | listOperationalRequirements | response | items[].decidedByPrincipalId | string (uuid) |  | (read-only; nullable)
AiService | listOperationalRequirements | response | items[].decidedAt | string (date-time) |  | (read-only; nullable)
AiService | listOperationalRequirements | response | items[].decisionNote | string |  | (nullable)
AiService | listOperationalRequirements | response | items[].handoverRef | string |  | The owning module's record once handed over. (read-only; nullable)
AiService | listOperationalRequirements | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | listOperationalRequirements | response | nextCursor | string
AiService | listOperationalRequirements | response | hasMore | boolean | yes
AiService | listOperationalRequirements | param (query) | kind | enum (staff, pos, kiosk, gates, fnb, retail, stock, resource, …)
AiService | listOperationalRequirements | param (query) | status | enum (issued, accepted, modified, rejected, handedOver, expired)
AiService | listOperationalRequirements | param (query) | from | string (date-time)
AiService | listOperationalRequirements | param (query) | to | string (date-time)
AiService | listOperationalRequirements | param (query) | versionId | string (uuid)
AiService | listOperationalRequirements | param (query) | pageSize | integer
AiService | listOperationalRequirements | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
OrderService | listOrderRefunds | response | items | array of Refund | yes
OrderService | listOrderRefunds | response | items[].id | string (uuid) | yes
OrderService | listOrderRefunds | response | items[].orderId | string (uuid) | yes
OrderService | listOrderRefunds | response | items[].batchId | string (uuid) |  | The RefundBatch that raised this refund, where createBulkRefund did. (read-only; nullable)
OrderService | listOrderRefunds | response | items[].fxRate | object |  | The rate on the original payment, not today's (BL-087, CF-118). (read-only; nullable)
OrderService | listOrderRefunds | response | items[].taxReversalEntryId | string (uuid) |  | A refund reverses the tax entry it created, and this is where that is stated rather than implied. (read-only; nullable)
OrderService | listOrderRefunds | response | items[].settleTo | enum (originalTender, advanceBalance, wireTransfer, storeCredit) |  | BL-086. (default originalTender)
OrderService | listOrderRefunds | response | items[].fxVariance | object |  | Where the sale rate and the current rate differ, the difference is booked as an FX variance rather than hidden in the refund.
OrderService | listOrderRefunds | response | items[].fxVariance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listOrderRefunds | response | items[].fxVariance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listOrderRefunds | response | items[].fxVariance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listOrderRefunds | response | items[].tenderCurrency | string |  | A refund goes back in the currency the guest paid (decided 2 October 2026, Chinmay; CHG-FIN-001). (pattern ^[A-Z]{3}$; read-only; nullable)
OrderService | listOrderRefunds | response | items[].tenderAmount | object |  | The refund in tenderCurrency, at that currency's own scale (CHG-FIN-001). (read-only)
OrderService | listOrderRefunds | response | items[].tenderAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listOrderRefunds | response | items[].tenderAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listOrderRefunds | response | items[].tenderAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listOrderRefunds | response | items[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listOrderRefunds | response | items[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listOrderRefunds | response | items[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listOrderRefunds | response | items[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listOrderRefunds | response | items[].appliedPercentage | number |  | From the venue's time bands, or an approver override.
OrderService | listOrderRefunds | response | items[].status | enum (pendingApproval, pendingGateway, completed, declined, failed) | yes
OrderService | listOrderRefunds | response | items[].reason | string
OrderService | listOrderRefunds | response | items[].requestedByPrincipalId | string (uuid)
OrderService | listOrderRefunds | response | items[].secondaryPrincipalId | string (uuid) |  | (nullable)
OrderService | listOrderRefunds | response | items[].approvedByPrincipalId | string (uuid) |  | (nullable)
OrderService | listOrderRefunds | response | items[].ledgerEntryId | string (uuid) |  | Written before the gateway is called. (nullable)
OrderService | listOrderRefunds | response | items[].gatewayReference | string |  | (nullable)
OrderService | listOrderRefunds | response | items[].createdAt | string (date-time) | yes
OrderService | listOrderRefunds | response | items[].completedAt | string (date-time) |  | (nullable)
OrderService | listOrderRefunds | response | nextCursor | string
OrderService | listOrderRefunds | response | hasMore | boolean | yes
OrderService | listOrderRefunds | param (path) | orderId | string (uuid) | yes
OrderService | listOrderRefunds | param (query) | pageSize | integer
OrderService | listOrderRefunds | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
OrderService | listOrders | response | items | array of OrderSummary | yes
OrderService | listOrders | response | items[].id | string (uuid) | yes
OrderService | listOrders | response | items[].orderNumber | string | yes
OrderService | listOrders | response | items[].status | OrderStatus: enum (pending, held, paid, partiallyPaid, completed, voided, refunded, partiallyRefunded, …) | yes | held is a parked sale — the cashier freed the till and the guest will return.
OrderService | listOrders | response | items[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | listOrders | response | items[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listOrders | response | items[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listOrders | response | items[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listOrders | response | items[].refundedAmount | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listOrders | response | items[].refundedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listOrders | response | items[].refundedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listOrders | response | items[].refundedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listOrders | response | items[].channel | object |  | The same vocabulary as Order.channel, which this projects.
OrderService | listOrders | response | items[].lineCount | integer
OrderService | listOrders | response | items[].principalId | string (uuid) |  | The cashier who raised it — what the held-orders list shows.
OrderService | listOrders | response | items[].holdLabel | string |  | As Order.holdLabel. (nullable)
OrderService | listOrders | response | items[].heldUntil | string (date-time) |  | As Order.heldUntil, so a held-orders list can warn about the ones about to lapse. (nullable)
OrderService | listOrders | response | items[].createdAt | string (date-time) | yes
OrderService | listOrders | response | nextCursor | string
OrderService | listOrders | response | hasMore | boolean | yes
OrderService | listOrders | param (query) | venueId | string (uuid) |  | Exact match.
OrderService | listOrders | param (query) | principalId | string (uuid) |  | The cashier who raised the order.
OrderService | listOrders | param (query) | shiftId | string (uuid) |  | Exact match on the shift the order was taken in.
OrderService | listOrders | param (query) | status | OrderStatus: enum (pending, held, paid, partiallyPaid, completed, voided, refunded, partiallyRefunded, …)
OrderService | listOrders | param (query) | createdFrom | string (date-time) |  | Only orders whose createdAt is at or after this instant.
OrderService | listOrders | param (query) | createdTo | string (date-time) |  | Only orders whose createdAt is before this instant.
OrderService | listOrders | param (query) | workstationId | string (uuid) |  | Exact match on the till the order was taken on (Order.workstationId).
OrderService | listOrders | param (query) | subjectId | string (uuid) |  | Exact match on the guest the order belongs to (Order.subjectId).
OrderService | listOrders | param (query) | tender | TenderKind: enum (cash, card, wallet, voucher, bankTransfer, hotelCharge, installment, giftCard, …) |  | Only orders with at least one payment in this tender (Payment.tender), so a split order matches each tender it used.
OrderService | listOrders | param (query) | pageSize | integer
OrderService | listOrders | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
TenancyService | listOrgUnits | response | items | array of OrgUnit | yes
TenancyService | listOrgUnits | response | items[].id | string (uuid) | yes
TenancyService | listOrgUnits | response | items[].level | ScopeLevel: enum (tenant, brand, region, venue, department, subDepartment, workstation, outlet) | yes | Seven organisational levels, confirmed binding (ADR-0011), plus outlet.
TenancyService | listOrgUnits | response | items[].parentId | string (uuid) |  | (nullable)
TenancyService | listOrgUnits | response | items[].path | string | yes | Materialised ltree path, e.g. (pattern ^[a-z0-9_]+(\.[a-z0-9_]+)*$)
TenancyService | listOrgUnits | response | items[].code | string | yes | (max length 64)
TenancyService | listOrgUnits | response | items[].name | string | yes | (max length 200)
TenancyService | listOrgUnits | response | items[].isActive | boolean | yes | False causes every permission query at or beneath this node to resolve to DENY.
TenancyService | listOrgUnits | response | items[].childCount | integer |  | (min 0)
TenancyService | listOrgUnits | response | nextCursor | string
TenancyService | listOrgUnits | response | hasMore | boolean | yes
TenancyService | listOrgUnits | param (query) | under | string |  | Return descendants of this path only.
TenancyService | listOrgUnits | param (query) | level | ScopeLevel: enum (tenant, brand, region, venue, department, subDepartment, workstation, outlet)
TenancyService | listOrgUnits | param (query) | includeInactive | boolean
TenancyService | listOrgUnits | param (query) | pageSize | integer
TenancyService | listOrgUnits | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
IdentityService | listOwnPlatformStaffGrants | response | items | array of PlatformStaffGrant | yes
IdentityService | listOwnPlatformStaffGrants | response | items[].id | string (uuid) | yes
IdentityService | listOwnPlatformStaffGrants | response | items[].operatorPrincipalId | string (uuid) | yes | The platform operator, from the Control Plane token. (read-only)
IdentityService | listOwnPlatformStaffGrants | response | items[].operatorDisplayName | string |  | (read-only)
IdentityService | listOwnPlatformStaffGrants | response | items[].permissions | array of Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) | yes
IdentityService | listOwnPlatformStaffGrants | response | items[].reason | string | yes
IdentityService | listOwnPlatformStaffGrants | response | items[].ticketRef | string |  | (nullable)
IdentityService | listOwnPlatformStaffGrants | response | items[].openedAt | string (date-time) | yes | (read-only)
IdentityService | listOwnPlatformStaffGrants | response | items[].expiresAt | string (date-time) | yes
IdentityService | listOwnPlatformStaffGrants | response | items[].scopePath | string |  | The tenant root. (read-only)
IdentityService | listOwnPlatformStaffGrants | response | nextCursor | string
IdentityService | listOwnPlatformStaffGrants | response | hasMore | boolean | yes
IdentityService | listOwnPlatformStaffGrants | param (query) | activeOnly | boolean |  | True returns only grants whose window is open now.
IdentityService | listOwnPlatformStaffGrants | param (query) | pageSize | integer
IdentityService | listOwnPlatformStaffGrants | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
AccessService | listParkingFacilities | response | items | array of ParkingFacility | yes
AccessService | listParkingFacilities | response | items[].id | string (uuid) |  | Server-assigned, and the upsert key of setParkingFacility.
AccessService | listParkingFacilities | response | items[].name | string | yes
AccessService | listParkingFacilities | response | items[].venueId | string (uuid) | yes
AccessService | listParkingFacilities | response | items[].mode | ParkingIntegrationMode: enum (none, plateWhitelist, qrHandoff) | yes | CF-52, settled 14 August.
AccessService | listParkingFacilities | response | items[].capacity | integer |  | What "full" means in the first release (decided 28 September, audit R166): the facility is full when the issued ParkingEntitlements valid for a time reach this number. (nullable)
AccessService | listParkingFacilities | response | items[].takesPayment | boolean |  | Always false, and stated rather than assumed (19.2.78, CF-124). (default False; read-only)
AccessService | listParkingFacilities | response | items[].vendorSwapTargetDays | integer |  | A new parking vendor should take days, not weeks — Qossai, 14 August. (default 5; read-only)
AccessService | listParkingFacilities | response | items[].vendorName | string |  | Staff only — omitted from a guest's listParkingFacilities response. (nullable)
AccessService | listParkingFacilities | response | items[].endpoint | string |  | Staff only — omitted from a guest's listParkingFacilities response. (nullable)
AccessService | listParkingFacilities | response | items[].credentialRef | string |  | A vault reference, never the credential. (nullable)
AccessService | listParkingFacilities | response | items[].pushLeadMinutes | integer |  | Staff only — omitted from a guest's listParkingFacilities response. (nullable)
AccessService | listParkingFacilities | response | items[].accessPointIds | array of string (uuid) |  | Where the platform validates its own code, in none and qrHandoff modes.
AccessService | listParkingFacilities | response | items[].isActive | boolean
AccessService | listParkingFacilities | response | items[].productVariantId | string (uuid) |  | The catalogue variant sold for parking here (4 October 2026, CHG-FXC-010; GST-027, WEB-041): what addCartLine sells when a guest buys parking at this car park. (nullable)
AccessService | listParkingFacilities | response | nextCursor | string
AccessService | listParkingFacilities | response | hasMore | boolean | yes
AccessService | listParkingFacilities | param (query) | venueId | string (uuid) |  | Required for a guest caller; optional for staff, where it narrows the list.
AccessService | listParkingFacilities | param (query) | pageSize | integer
AccessService | listParkingFacilities | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
OrderService | listPaymentTokens | response | items | array of PaymentToken | yes
OrderService | listPaymentTokens | response | items[].id | string (uuid) | yes
OrderService | listPaymentTokens | response | items[].subjectId | string (uuid) | yes
OrderService | listPaymentTokens | response | items[].providerId | string (uuid) | yes
OrderService | listPaymentTokens | response | items[].token | string (password) | yes | Write-only, never returned.
OrderService | listPaymentTokens | response | items[].method | string
OrderService | listPaymentTokens | response | items[].maskedIdentifier | string |  | What a guest sees — the last four digits, the card brand.
OrderService | listPaymentTokens | response | items[].expiresAt | string (date) |  | (nullable)
OrderService | listPaymentTokens | response | items[].isDefault | boolean | yes
OrderService | listPaymentTokens | response | items[].consentPurposeId | string (uuid) |  | Storing a card for future use is a purpose a guest consents to, separate from the payment they are making now. (nullable)
OrderService | listPaymentTokens | response | nextCursor | string
OrderService | listPaymentTokens | response | hasMore | boolean | yes
OrderService | listPaymentTokens | param (query) | pageSize | integer
OrderService | listPaymentTokens | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
CatalogueService | listPerformances | response | items | array of Performance | yes
CatalogueService | listPerformances | response | items[].id | string (uuid) | yes
CatalogueService | listPerformances | response | items[].eventId | string (uuid) | yes
CatalogueService | listPerformances | response | items[].startsAt | string (date-time) | yes
CatalogueService | listPerformances | response | items[].endsAt | string (date-time) | yes
CatalogueService | listPerformances | response | items[].approvalRequestId | string (uuid) |  | BL-048. (nullable)
CatalogueService | listPerformances | response | items[].requiresApprovalToCancel | boolean |  | Cancelling a sold performance is the one transition that needs a name against it. (default True)
CatalogueService | listPerformances | response | items[].status | enum (scheduled, onSale, soldOut, suspended, cancelled, completed) | yes
CatalogueService | listPerformances | response | items[].admissionRulesId | string (uuid) |  | (nullable)
CatalogueService | listPerformances | response | items[].seatMapId | string (uuid) |  | (nullable)
CatalogueService | listPerformances | response | items[].language | string |  | The language the performance is given in, as a BCP 47 tag (en, ar, fr, de, zh, ru, ar-AE). (max length 35; pattern ^[A-Za-z]{2,3}(-[A-Za-z0-9]{1,8})*$; nullable)
CatalogueService | listPerformances | response | items[].format | string |  | How it is presented, free text the venue chooses, e.g. (max length 40; nullable)
CatalogueService | listPerformances | response | items[].minutesOnScreen | integer |  | "Minutes on screen": how long after startsAt the slot is still sold (agreed 7 August, DI-167 and DI-169; added 6 October 2026, CHG-R4-014). (min 0; max 1440; default 0)
CatalogueService | listPerformances | response | nextCursor | string
CatalogueService | listPerformances | response | hasMore | boolean | yes
CatalogueService | listPerformances | param (path) | eventId | string (uuid) | yes
CatalogueService | listPerformances | param (query) | from | string (date-time) |  | Only performances whose startsAt is at or after this instant.
CatalogueService | listPerformances | param (query) | to | string (date-time) |  | Only performances whose startsAt is before this instant.
CatalogueService | listPerformances | param (query) | categoryId | string (uuid) |  | Only performances of products in this product category (a product in several categories matches each), the calendar's category filter (17 September minutes M17-03, added 30 September).
CatalogueService | listPerformances | param (query) | language | string |  | Only performances given in this language, e.g.
CatalogueService | listPerformances | param (query) | pageSize | integer
CatalogueService | listPerformances | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
WhiteLabelService | listPolicies | param (query) | includeHistory | boolean |  | Every version rather than the current one per kind (audit R163).
WhiteLabelService | listPolicies | param (query) | kind | PolicyKind: enum (privacy, termsAndConditions, refund, cookie, accessibility) |  | Only this policy kind.
IdentityService | listPrincipals | response | items | array of Principal | yes
IdentityService | listPrincipals | response | items[].id | string (uuid) | yes
IdentityService | listPrincipals | response | items[].username | string | yes
IdentityService | listPrincipals | response | items[].displayName | string | yes
IdentityService | listPrincipals | response | items[].isActive | boolean | yes
IdentityService | listPrincipals | response | items[].validFrom | string (date-time) |  | (nullable)
IdentityService | listPrincipals | response | items[].validTo | string (date-time) |  | Past this, resolution returns DENY regardless of grants. (nullable)
IdentityService | listPrincipals | response | items[].primaryRoleId | string (uuid) |  | Determines the landing screen when the principal holds several roles and picks one at login. (nullable)
IdentityService | listPrincipals | response | items[].roles | array of RoleSummary
IdentityService | listPrincipals | response | items[].roles[].id | string (uuid) | yes
IdentityService | listPrincipals | response | items[].roles[].code | string | yes
IdentityService | listPrincipals | response | items[].roles[].name | string | yes
IdentityService | listPrincipals | response | items[].roles[].isPrimary | boolean
IdentityService | listPrincipals | response | items[].lastLoginAt | string (date-time) |  | (nullable)
IdentityService | listPrincipals | response | nextCursor | string
IdentityService | listPrincipals | response | hasMore | boolean | yes
IdentityService | listPrincipals | param (query) | scopePath | string |  | Principals whose home scope (identity.principal.home_scope_id) is this node or any node beneath it — a prefix match on the materialised path, the way scope_path is compared everywhere (shared/common.…
IdentityService | listPrincipals | param (query) | isActive | boolean |  | Exact match on Principal.isActive.
IdentityService | listPrincipals | param (query) | pageSize | integer
IdentityService | listPrincipals | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
VenueOpsService | listProductStartTimes | response | items | array of ProductStartTime | yes
VenueOpsService | listProductStartTimes | response | items[].startsAt | string (date-time) | yes
VenueOpsService | listProductStartTimes | response | items[].endsAt | string (date-time) | yes | startsAt plus the variant's durationMinutes; the cart line's bookedWindow.endsAt.
VenueOpsService | listProductStartTimes | response | items[].freeCount | integer | yes | Resources of the room type free for the whole window. (min 1)
VenueOpsService | listProductStartTimes | response | nextCursor | string
VenueOpsService | listProductStartTimes | response | hasMore | boolean | yes
VenueOpsService | listProductStartTimes | param (query) | productId | string (uuid) | yes | A catalogue.Product with requiresTimeWindow true, else 422.
VenueOpsService | listProductStartTimes | param (query) | variantId | string (uuid) | yes | The length variant; its length value's durationMinutes is the window.
VenueOpsService | listProductStartTimes | param (query) | date | string (date) | yes | The venue-local date.
VenueOpsService | listProductStartTimes | param (query) | stepMinutes | enum (15, 30, 60) |  | Spacing of the offered start times.
VenueOpsService | listProductStartTimes | param (query) | pageSize | integer
VenueOpsService | listProductStartTimes | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
CatalogueService | listProductVariants | response | items | array of ProductVariant | yes
CatalogueService | listProductVariants | response | items[].id | string (uuid) | yes
CatalogueService | listProductVariants | response | items[].productId | string (uuid) | yes
CatalogueService | listProductVariants | response | items[].sku | string | yes
CatalogueService | listProductVariants | response | items[].axisValues | object | yes
CatalogueService | listProductVariants | response | items[].name | string |  | Taken from their variant tables, 20 September. (max length 150; nullable)
CatalogueService | listProductVariants | response | items[].barcode | string |  | Taken from their variant tables, 20 September. (max length 64; nullable)
CatalogueService | listProductVariants | response | items[].isDefault | boolean |  | Taken from their variant tables. (default False)
CatalogueService | listProductVariants | response | items[].isActive | boolean | yes | False when retired.
CatalogueService | listProductVariants | response | items[].description | object |  | Who this ticket type is for and what it includes, shown behind the (i) on each Adult, Child, Senior or Infant row (decided 29 September, 23SEP-6). (nullable)
CatalogueService | listProductVariants | response | nextCursor | string
CatalogueService | listProductVariants | response | hasMore | boolean | yes
CatalogueService | listProductVariants | param (path) | productId | string (uuid) | yes
CatalogueService | listProductVariants | param (query) | pageSize | integer
CatalogueService | listProductVariants | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
CatalogueService | listProducts | response | items | array of Product | yes
CatalogueService | listProducts | response | items[].id | string (uuid) | yes
CatalogueService | listProducts | response | items[].code | string | yes | (max length 64)
CatalogueService | listProducts | response | items[].familyKey | string |  | The same product at another location (decided 29 September, rev 3 REV3-18). (max length 64; pattern ^[A-Za-z0-9_-]+$; nullable)
CatalogueService | listProducts | response | items[].name | string | yes | (max length 200)
CatalogueService | listProducts | response | items[].description | string
CatalogueService | listProducts | response | items[].nameLocalised | object |  | The product's name in each language the venue sells in (6 October 2026, CHG-R4-011), keyed by ISO 639-1 code, e.g. (nullable)
CatalogueService | listProducts | response | items[].descriptionLocalised | object |  | The product's description in each language, as nameLocalised; falls back to description (6 October 2026, CHG-R4-011). (nullable)
CatalogueService | listProducts | response | items[].kind | ProductKind: enum (admission, timedAdmission, datedAdmission, openDated, seated, membership, bundle, fnb, …) | yes | openDated added 24 August from the client's *Create Ticket Flow* board, which names six main ticket types and this was the one with no kind: valid on any date within an eligible range, rather than fo…
CatalogueService | listProducts | response | items[].venueId | string (uuid) | yes
CatalogueService | listProducts | response | items[].scopePath | string | yes
CatalogueService | listProducts | response | items[].createdByPrincipalId | string (uuid) |  | 1.4.18. (read-only)
CatalogueService | listProducts | response | items[].approvedByPrincipalId | string (uuid) |  | (read-only; nullable)
CatalogueService | listProducts | response | items[].responsibleDepartmentId | string (uuid) |  | Who owns this product commercially. (nullable)
CatalogueService | listProducts | response | items[].onSaleFrom | string (date-time) |  | 1.4.8. (nullable)
CatalogueService | listProducts | response | items[].onSaleTo | string (date-time) |  | Retires the product automatically. (nullable)
CatalogueService | listProducts | response | items[].categoryId | string (uuid) |  | Taken from their fnb.product and retail.product, 20 September. (nullable)
CatalogueService | listProducts | response | items[].lifecycleState | ProductLifecycleState: enum (draft, inReview, approved, live, withdrawn, archived)
CatalogueService | listProducts | response | items[].isSellable | boolean | yes | True only when live and carried by a published bundle. (read-only)
CatalogueService | listProducts | response | items[].isStockTracked | boolean |  | Taken from their fnb.product, 20 September. (default False)
CatalogueService | listProducts | response | items[].hasVariants | boolean | yes
CatalogueService | listProducts | response | items[].variantCount | integer
CatalogueService | listProducts | response | items[].segmentTags | array of string |  | 7.3.5.
CatalogueService | listProducts | response | items[].codeSchema | string |  | 7.3.4 specifies [ParkCode]-[ProductType]-[Variant]. (read-only)
CatalogueService | listProducts | response | items[].channels | array of Channel: enum (pos, kiosk, web, mobile, b2b, ota, callCentre)
CatalogueService | listProducts | response | items[].entitlementTemplateId | string (uuid) |  | What the buyer receives. (nullable)
CatalogueService | listProducts | response | items[].blockedOffline | boolean |  | True for seated and retail.
CatalogueService | listProducts | response | items[].dataMaskValues | object |  | Custom fields.
CatalogueService | listProducts | response | items[].guestListing | GuestListing: enum (bookable, infoOnly, hidden) |  | How a product appears to a guest (decided 29 September, rev 3 REV3-14). (default bookable)
CatalogueService | listProducts | response | items[].notBookableLabel | object |  | The label a guest reads on an infoOnly product, e.g. (nullable)
CatalogueService | listProducts | response | items[].salesContact | object |  | Who a guest contacts to book a view-only product (decided 29 September, W3), e.g. (nullable)
CatalogueService | listProducts | response | items[].salesContact.phone | string |  | (max length 32; nullable)
CatalogueService | listProducts | response | items[].salesContact.email | string (email) |  | (max length 254; nullable)
CatalogueService | listProducts | response | items[].salesContact.note | object |  | A line shown under the contact, e.g. (nullable)
CatalogueService | listProducts | response | items[].bookingFlowId | string (uuid) |  | The booking flow this product is sold through (decided 29 September, W8 and W12): a white-label BookingFlow of the venue, which orders the guest's steps (for a workshop, the product first and then th… (nullable)
CatalogueService | listProducts | response | items[].displayTags | array of ProductDisplayTag |  | Short facts a guest reads on the ticket card and under *Read more*: *2 Hours*, *Min 1.10 m*, *Free adult entry*, *Valid 90 days*, *Emirates ID* (decided 29 September, 23SEP-3). (max items 6)
CatalogueService | listProducts | response | items[].displayTags[].kind | enum (clock, height, free, calendar, id) | yes | clock a duration, height a height rule, free something included free, calendar a validity, id a document the guest must bring.
CatalogueService | listProducts | response | items[].displayTags[].label | object | yes | What the guest reads, e.g.
CatalogueService | listProducts | response | items[].displayTags[].derived | boolean |  | True on a tag the server derived on read because the venue set none. (default False; read-only)
CatalogueService | listProducts | response | items[].media | array of ProductMedia |  | The product's own photos and video (decided 29 September, 23SEP-4). (max items 20)
CatalogueService | listProducts | response | items[].media[].assetId | string (uuid) | yes | A MediaAsset of assets.yaml, in status ready.
CatalogueService | listProducts | response | items[].media[].kind | enum (image, video) | yes
CatalogueService | listProducts | response | items[].media[].isPrimary | boolean | yes | The item *Read more* opens on and a listing shows. (default False)
CatalogueService | listProducts | response | items[].media[].displayOrder | integer |  | (default 100)
CatalogueService | listProducts | response | items[].media[].altText | object |  | (nullable)
CatalogueService | listProducts | response | items[].consentQuestionIds | array of string (uuid) |  | The consent questions a guest answers when booking this product, in the order they are asked (decided 29 September, rev 3 REV3-26): *Are you able to swim?*, *Do you hold a scuba certification?*, *I a… (max items 10)
CatalogueService | listProducts | response | items[].requiresTimeWindow | boolean |  | True for a space sold by the hour, e.g. (default False)
CatalogueService | listProducts | response | items[].productOwnerPrincipalId | string (uuid) |  | The product owner (29 September, data model DM3), set with setProductContextOwnership. (nullable)
CatalogueService | listProducts | response | items[].operationalContact | string |  | A principal id or a name, as the context screen takes it. (max length 200; nullable)
CatalogueService | listProducts | response | items[].businessUnitId | string (uuid) |  | (nullable)
CatalogueService | listProducts | response | items[].legalEntityId | string (uuid) |  | A ledger.legal_entity, read through finance. (nullable)
CatalogueService | listProducts | response | items[].attractionId | string (uuid) |  | (nullable)
CatalogueService | listProducts | response | items[].siteId | string (uuid) |  | (nullable)
CatalogueService | listProducts | response | items[].locationId | string (uuid) |  | (nullable)
CatalogueService | listProducts | response | items[].brandId | string (uuid) |  | The brand, as the context screen names it (a catalogue brand category). (nullable)
CatalogueService | listProducts | response | items[].marketCode | string |  | (max length 40; nullable)
CatalogueService | listProducts | response | items[].salesTerritory | string |  | (max length 100; nullable)
CatalogueService | listProducts | response | items[].eventId | string (uuid) |  | The event this product sells admission to (4 October 2026, CHG-FXC-011; WEB-002, WEB-004): a product page finds its event and the event's performances (Performance.eventId) give it dates. (nullable)
CatalogueService | listProducts | response | nextCursor | string
CatalogueService | listProducts | response | hasMore | boolean | yes
CatalogueService | listProducts | param (query) | venueId | string (uuid)
CatalogueService | listProducts | param (query) | kind | ProductKind: enum (admission, timedAdmission, datedAdmission, openDated, seated, membership, bundle, fnb, …)
CatalogueService | listProducts | param (query) | isSellable | boolean
CatalogueService | listProducts | param (query) | categoryId | string (uuid) |  | Only products filed under this category (Product.categoryId) or any category below it in the tree, so a tile for *Guided tours* also lists what sits under its subcategories.
CatalogueService | listProducts | param (query) | entitlementTemplateId | string (uuid) |  | Products using this template (client feedback of 6 October 2026, N32; CHG-R6-040): only products whose entitlementTemplateId is this one.
CatalogueService | listProducts | param (query) | segmentTag | string |  | Only products carrying this tag in segmentTags, or a tag below it (level matches level/beginner; level/beginner matches only itself).
CatalogueService | listProducts | param (query) | guidedAnswerIds | array of string (uuid) |  | Help me choose answers, as filters (decided 29 September, W4).
CatalogueService | listProducts | param (query) | pageSize | integer
CatalogueService | listProducts | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
CatalogueService | listPromotions | response | items | array of Promotion or GuestPromotion | yes
CatalogueService | listPromotions | response | nextCursor | string
CatalogueService | listPromotions | response | hasMore | boolean | yes
CatalogueService | listPromotions | param (query) | venueId | string (uuid)
CatalogueService | listPromotions | param (query) | status | PromotionStatus: enum (draft, scheduled, live, paused, expired, ended)
CatalogueService | listPromotions | param (query) | activeAt | string (date-time)
CatalogueService | listPromotions | param (query) | pageSize | integer
CatalogueService | listPromotions | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
WhiteLabelService | listPublishedContentPages | response | items | array of PublishedContentPage | yes
WhiteLabelService | listPublishedContentPages | response | items[].id | string (uuid) | yes
WhiteLabelService | listPublishedContentPages | response | items[].slug | string | yes | (pattern ^[a-z0-9-]+$)
WhiteLabelService | listPublishedContentPages | response | items[].title | LocalisedText | yes | Keyed by ISO 639-1 code.
WhiteLabelService | listPublishedContentPages | response | items[].body | LocalisedRichText | yes | Keyed by language code.
WhiteLabelService | listPublishedContentPages | response | items[].iconAssetRef | string (uuid) |  | (nullable)
WhiteLabelService | listPublishedContentPages | response | items[].categoryCode | string |  | (nullable)
WhiteLabelService | listPublishedContentPages | response | items[].sortOrder | integer
WhiteLabelService | listPublishedContentPages | response | nextCursor | string
WhiteLabelService | listPublishedContentPages | response | hasMore | boolean | yes
WhiteLabelService | listPublishedContentPages | param (query) | categoryCode | string |  | Only live pages with this categoryCode.
WhiteLabelService | listPublishedContentPages | param (query) | slug | string |  | Only the live page with this slug.
WhiteLabelService | listPublishedContentPages | param (query) | pageSize | integer
WhiteLabelService | listPublishedContentPages | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
WhiteLabelService | listPublishedPolicies | param (query) | kind | PolicyKind: enum (privacy, termsAndConditions, refund, cookie, accessibility) |  | Only this policy kind, how the checkout reads the terms alone.
MarketingService | listPublishedTrackingTechnologies | response | items | array of PublishedTrackingTechnology | yes
MarketingService | listPublishedTrackingTechnologies | response | items[].name | string | yes
MarketingService | listPublishedTrackingTechnologies | response | items[].provider | string | yes
MarketingService | listPublishedTrackingTechnologies | response | items[].category | CookieCategory: enum (strictlyNecessary, functional, analytics, personalisation, marketing) | yes | 2.6.53.
MarketingService | listPublishedTrackingTechnologies | response | items[].technologyType | string
MarketingService | listPublishedTrackingTechnologies | response | items[].purpose | string |  | (nullable)
MarketingService | listPublishedTrackingTechnologies | response | items[].durationDays | integer |  | Null for session storage. (nullable)
MarketingService | listPublishedTrackingTechnologies | response | items[].isThirdParty | boolean | yes
MarketingService | listPublishedTrackingTechnologies | response | items[].privacyInformation | string |  | (nullable)
MarketingService | listPublishedTrackingTechnologies | response | nextCursor | string
MarketingService | listPublishedTrackingTechnologies | response | hasMore | boolean | yes
MarketingService | listPublishedTrackingTechnologies | param (query) | channel | CookieConsentChannel: enum (b2cWebsite, customerPortal, mobileApp, embeddedCheckout, whiteLabelSite, partnerMicrosite) | yes
MarketingService | listPublishedTrackingTechnologies | param (query) | category | CookieCategory: enum (strictlyNecessary, functional, analytics, personalisation, marketing)
MarketingService | listPublishedTrackingTechnologies | param (query) | pageSize | integer
MarketingService | listPublishedTrackingTechnologies | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
VenueOpsService | listQueues | response | items | array of Queue | yes
VenueOpsService | listQueues | response | items[].code | string | yes | (max length 64)
VenueOpsService | listQueues | response | items[].name | LocalisedText | yes
VenueOpsService | listQueues | response | items[].venueId | string (uuid) | yes
VenueOpsService | listQueues | response | items[].attractionProductId | string (uuid)
VenueOpsService | listQueues | response | items[].assetId | string (uuid) |  | The ride. (nullable)
VenueOpsService | listQueues | response | items[].accessPointId | string (uuid) |  | (nullable)
VenueOpsService | listQueues | response | items[].kind | enum (standby, singleRider, fastPass, virtual, accessible, groupOnly, staffOnly) |  | 5.6.x. (default standby)
VenueOpsService | listQueues | response | items[].operatingWindows | array of object |  | When the queue runs, which is not when the venue is open.
VenueOpsService | listQueues | response | items[].operatingWindows[].day | enum (mon, tue, wed, thu, fri, sat, sun) | yes
VenueOpsService | listQueues | response | items[].operatingWindows[].from | string | yes | Venue local time, 24-hour HH:MM, when the queue starts running. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
VenueOpsService | listQueues | response | items[].operatingWindows[].to | string | yes | Venue local time, 24-hour HH:MM, when the queue stops running. (pattern ^([01][0-9]¦2[0-3]):[0-5][0-9]$)
VenueOpsService | listQueues | response | items[].operatingWindows[].lastEntryMinutesBefore | integer |  | When the queue stops accepting, which is before it stops running. (default 0)
VenueOpsService | listQueues | response | items[].parentQueueId | string (uuid) |  | Where several queues share one capacity. (nullable)
VenueOpsService | listQueues | response | items[].loadBalanceWithQueueIds | array of string (uuid) |  | BL-137.
VenueOpsService | listQueues | response | items[].inQueueOfferEnabled | boolean |  | A guest with twenty minutes to wait is a guest with twenty minutes to buy something. (default False)
VenueOpsService | listQueues | response | items[].notifyBeforeCallMinutes | integer |  | BL-017, 19.2.61. (default 5)
VenueOpsService | listQueues | response | items[].capacityPerCycle | integer | yes | (min 1)
VenueOpsService | listQueues | response | items[].cycleMinutes | number | yes | (min 0)
VenueOpsService | listQueues | response | items[].maxPartySize | integer |  | (default 6)
VenueOpsService | listQueues | response | items[].returnWindowMinutes | integer |  | How long a called party has to arrive before the entry expires. (default 15)
VenueOpsService | listQueues | response | items[].heightRequirementCm | integer |  | (nullable)
VenueOpsService | listQueues | response | items[].fastPassAllocationPercent | number |  | Share of each cycle reserved for Fast Pass holders. (min 0; max 100; default 0)
VenueOpsService | listQueues | response | items[].zone | string |  | (nullable)
VenueOpsService | listQueues | response | items[].fastPass | object |  | The lane's Fast Pass block (decided 29 September, VM close-out). (nullable)
VenueOpsService | listQueues | response | items[].fastPass.entitlementProductIds | array of string (uuid) | yes | Catalogue products whose entitlement admits to this lane.
VenueOpsService | listQueues | response | items[].fastPass.loyaltyTierIds | array of string (uuid) |  | 5.6.7 and 5.6.34 (decided 29 September, build pass).
VenueOpsService | listQueues | response | items[].fastPass.promotionIds | array of string (uuid) |  | 5.6.34 (decided 29 September, build pass).
VenueOpsService | listQueues | response | items[].fastPass.accessibilityPriority | boolean |  | 5.6.7 (decided 29 September, build pass). (default False)
VenueOpsService | listQueues | response | items[].fastPass.returnWindowMinutes | integer |  | How long after the booked return time a Fast Pass holder may still enter. (min 1; max 240; default 60)
VenueOpsService | listQueues | response | items[].fastPass.maxPerGuestPerDay | integer |  | Fast Pass redemptions one guest may make on this lane per day; null is no cap. (min 1; nullable)
VenueOpsService | listQueues | response | items[].fastPass.allowedAccessPointIds | array of string (uuid) |  | Access points that redeem Fast Pass for this lane; empty is the queue's own.
VenueOpsService | listQueues | response | items[].id | string (uuid) | yes
VenueOpsService | listQueues | response | items[].status | QueueStatus: enum (open, paused, closed, atCapacity) | yes
VenueOpsService | listQueues | response | items[].statusReason | string |  | (nullable)
VenueOpsService | listQueues | response | items[].waitingPartyCount | integer | yes
VenueOpsService | listQueues | response | items[].waitingGuestCount | integer
VenueOpsService | listQueues | response | items[].currentWaitMinutes | integer |  | (nullable)
VenueOpsService | listQueues | response | items[].waitTimeSource | WaitTimeSource: enum (sensor, throughput, manual, unavailable) |  | Where the estimate came from.
VenueOpsService | listQueues | response | items[].waitTimeAsOf | string (date-time) |  | When currentWaitMinutes was last set, by whichever source set it. (read-only; nullable)
VenueOpsService | listQueues | response | items[].manualWaitExpiresAt | string (date-time) |  | Set by setWaitTime as now plus expiresInMinutes. (read-only; nullable)
VenueOpsService | listQueues | response | items[].manualWaitNote | string |  | The note given with the current manual figure. (max length 200; read-only; nullable)
VenueOpsService | listQueues | response | items[].expectedReopenAt | string (date-time) |  | (nullable)
VenueOpsService | listQueues | response | nextCursor | string
VenueOpsService | listQueues | response | hasMore | boolean | yes
VenueOpsService | listQueues | param (query) | venueId | string (uuid)
VenueOpsService | listQueues | param (query) | openOnly | boolean
VenueOpsService | listQueues | param (query) | pageSize | integer
VenueOpsService | listQueues | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
ReportingService | listReports | response | items | array of ReportDefinition | yes
ReportingService | listReports | response | items[].name | string | yes | (max length 200)
ReportingService | listReports | response | items[].description | string |  | (max length 1000)
ReportingService | listReports | response | items[].category | ReportCategory: enum (sales, admission, financial, inventory, guest, operations, marketing, workforce, …) | yes
ReportingService | listReports | response | items[].dataSource | DataSource: enum (orders, orderLines, payments, refunds, shifts, scanEvents, entitlements, products, …) | yes | What a report may be built over.
ReportingService | listReports | response | items[].columns | array of ReportColumn | yes | (min items 1)
ReportingService | listReports | response | items[].columns[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | listReports | response | items[].columns[].field | string | yes
ReportingService | listReports | response | items[].columns[].label | string
ReportingService | listReports | response | items[].columns[].aggregation | object |  | (default none)
ReportingService | listReports | response | items[].columns[].sortOrder | integer
ReportingService | listReports | response | items[].columns[].sortDirection | enum (asc, desc)
ReportingService | listReports | response | items[].columns[].format | string |  | (nullable)
ReportingService | listReports | response | items[].columns[].role | enum (dimension, measure) |  | What the column is to a chart (decided 2 October 2026, Chinmay; CHG-FIN-007). (nullable)
ReportingService | listReports | response | items[].columns[].encoding | enum (category, x, y, series, value, size, colour, location, …) |  | Which field well the column fills (CHG-FIN-007), the binding the twenty marks of DashboardTile.visualisation need. (nullable)
ReportingService | listReports | response | items[].columns[].axis | enum (primary, secondary) |  | For a measure on a combo, the axis it is drawn against. (nullable)
ReportingService | listReports | response | items[].columns[].seriesType | enum (bar, line, area) |  | For a measure on a combo, how that series is drawn (CHG-FIN-007). (nullable)
ReportingService | listReports | response | items[].columns[].hierarchyLevel | integer |  | For matrix rows and columns, treemap nesting and decompositionTree levels, the depth of this dimension, 1 outermost. (min 1; nullable)
ReportingService | listReports | response | items[].columns[].unitLabel | string |  | The unit an axis states, for example "AED" or "Admissions". (max length 40; nullable)
ReportingService | listReports | response | items[].filters | array of ReportFilter
ReportingService | listReports | response | items[].filters[].id | string (uuid) |  | Added 20 August. (read-only)
ReportingService | listReports | response | items[].filters[].field | string | yes
ReportingService | listReports | response | items[].filters[].operator | enum (equals, notEquals, greaterThan, lessThan, between, in, notIn, contains, …) | yes
ReportingService | listReports | response | items[].filters[].value | object |  | Open on purpose; its type is the field's.
ReportingService | listReports | response | items[].filters[].values | array of object |  | The values for in and notIn, or exactly two (from, to) for between.
ReportingService | listReports | response | items[].filters[].isParameter | boolean |  | Prompted at run time rather than fixed. (default False)
ReportingService | listReports | response | items[].groupBy | array of string
ReportingService | listReports | response | items[].parameters | array of ReportParameter
ReportingService | listReports | response | items[].parameters[].key | string | yes
ReportingService | listReports | response | items[].parameters[].label | string | yes
ReportingService | listReports | response | items[].parameters[].type | FieldType: enum (string, integer, decimal, money, boolean, date, dateTime, uuid, …) | yes
ReportingService | listReports | response | items[].parameters[].isRequired | boolean | yes
ReportingService | listReports | response | items[].parameters[].defaultValue | object |  | Open on purpose.
ReportingService | listReports | response | items[].requiredPermission | Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) | yes | Permission needed to run this report, from the shared Permission vocabulary.
ReportingService | listReports | response | items[].maxDateRangeDays | integer |  | Guards against a query spanning years of scan events. (min 1; default 366; nullable)
ReportingService | listReports | response | items[].id | string (uuid) | yes
ReportingService | listReports | response | items[].version | string | yes | The current version.
ReportingService | listReports | response | items[].isSystem | boolean | yes | Shipped with the platform — seeded at provisioning (BL-053, SeededReport).
ReportingService | listReports | response | items[].isRetired | boolean | yes
ReportingService | listReports | response | items[].estimatedCost | enum (low, medium, high) |  | Informs whether it may run inline or must be queued.
ReportingService | listReports | response | items[].createdByPrincipalId | string (uuid) |  | (nullable)
ReportingService | listReports | response | items[].createdAt | string (date-time) | yes
ReportingService | listReports | response | items[].lastRunAt | string (date-time) |  | (nullable)
ReportingService | listReports | response | items[].scopePath | string |  | The partition key (ADR-0005).
ReportingService | listReports | response | nextCursor | string
ReportingService | listReports | response | hasMore | boolean | yes
ReportingService | listReports | param (query) | category | ReportCategory: enum (sales, admission, financial, inventory, guest, operations, marketing, workforce, …)
ReportingService | listReports | param (query) | search | string
ReportingService | listReports | param (query) | pageSize | integer
ReportingService | listReports | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
OrderService | listReservations | response | items | array of Reservation | yes
OrderService | listReservations | response | items[].id | string (uuid) | yes
OrderService | listReservations | response | items[].venueId | string (uuid) | yes
OrderService | listReservations | response | items[].subjectId | string (uuid) |  | The guest it is held for, from CreateReservationRequest.subjectId. (nullable)
OrderService | listReservations | response | items[].status | enum (held, converted, expired, cancelled) | yes
OrderService | listReservations | response | items[].lines | array of CreateOrderLine
OrderService | listReservations | response | items[].lines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | listReservations | response | items[].lines[].variantId | string (uuid) | yes
OrderService | listReservations | response | items[].lines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | listReservations | response | items[].lines[].performanceId | string (uuid)
OrderService | listReservations | response | items[].lines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | listReservations | response | items[].lines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | listReservations | response | items[].lines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | listReservations | response | items[].lines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | listReservations | response | items[].lines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | listReservations | response | items[].lines[].quantity | integer | yes | (min 1)
OrderService | listReservations | response | items[].lines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | listReservations | response | items[].lines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | listReservations | response | items[].lines[].holderName | string |  | (nullable)
OrderService | listReservations | response | items[].lines[].dataMaskValues | object |  | Deliberately open.
OrderService | listReservations | response | items[].expiresAt | string (date-time) | yes
OrderService | listReservations | response | items[].createdAt | string (date-time) | yes
OrderService | listReservations | response | items[].convertedOrderId | string (uuid) |  | (nullable)
OrderService | listReservations | response | nextCursor | string
OrderService | listReservations | response | hasMore | boolean | yes
OrderService | listReservations | param (query) | status | enum (held, converted, expired, cancelled) |  | Exact match.
OrderService | listReservations | param (query) | expiringWithinMinutes | integer |  | Only held reservations whose expiresAt falls within this many minutes of now — the ones about to release capacity.
OrderService | listReservations | param (query) | pageSize | integer
OrderService | listReservations | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
RetailService | listRetailSales | response | items | array of RetailSale | yes
RetailService | listRetailSales | response | items[].id | string | yes
RetailService | listRetailSales | response | items[].receiptNumber | string | yes | Server-assigned: the venue prefix plus a sequence per venue (decided 28 September, audit R152). (read-only)
RetailService | listRetailSales | response | items[].orderId | string | yes | The order in the Order & Payment context.
RetailService | listRetailSales | response | items[].outletId | string (uuid) | yes
RetailService | listRetailSales | response | items[].shiftId | string |  | (nullable)
RetailService | listRetailSales | response | items[].subjectId | string (uuid) |  | (nullable)
RetailService | listRetailSales | response | items[].lines | array of object | yes
RetailService | listRetailSales | response | items[].lines[].lineId | string
RetailService | listRetailSales | response | items[].lines[].merchandiseId | string (uuid)
RetailService | listRetailSales | response | items[].lines[].name | string
RetailService | listRetailSales | response | items[].lines[].quantity | integer
RetailService | listRetailSales | response | items[].lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | listRetailSales | response | items[].lines[].discount | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | listRetailSales | response | items[].lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | listRetailSales | response | items[].lines[].serialNumbers | array of string
RetailService | listRetailSales | response | items[].lines[].returnedQuantity | integer
RetailService | listRetailSales | response | items[].lines[].isReturnable | boolean |  | False once the window has passed or the line is fully returned.
RetailService | listRetailSales | response | items[].lines[].notReturnableReason | string |  | (nullable)
RetailService | listRetailSales | response | items[].subtotal | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | listRetailSales | response | items[].subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | listRetailSales | response | items[].subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | listRetailSales | response | items[].subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | listRetailSales | response | items[].discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | listRetailSales | response | items[].discountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | listRetailSales | response | items[].discountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | listRetailSales | response | items[].discountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | listRetailSales | response | items[].taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | listRetailSales | response | items[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | listRetailSales | response | items[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | listRetailSales | response | items[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | listRetailSales | response | items[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
RetailService | listRetailSales | response | items[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | listRetailSales | response | items[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | listRetailSales | response | items[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | listRetailSales | response | items[].reprintCount | integer
RetailService | listRetailSales | response | items[].createdAt | string (date-time) | yes
RetailService | listRetailSales | response | items[].recordedAt | string (date-time)
RetailService | listRetailSales | response | nextCursor | string
RetailService | listRetailSales | response | hasMore | boolean | yes
RetailService | listRetailSales | param (query) | outletId | string (uuid) |  | Exact match.
RetailService | listRetailSales | param (query) | shiftId | string |  | Exact match.
RetailService | listRetailSales | param (query) | createdFrom | string (date-time) |  | Sales with createdAt at or after this instant.
RetailService | listRetailSales | param (query) | createdTo | string (date-time) |  | Sales with createdAt before this instant.
RetailService | listRetailSales | param (query) | pageSize | integer
RetailService | listRetailSales | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
MarketingService | listRewards | response | items | array of MarketingReward | yes
MarketingService | listRewards | response | items[].id | string (uuid)
MarketingService | listRewards | response | items[].loyaltyProgramId | string (uuid) | yes
MarketingService | listRewards | response | items[].code | string | yes | (max length 100)
MarketingService | listRewards | response | items[].name | string | yes | (max length 200)
MarketingService | listRewards | response | items[].type | string | yes | (max length 30)
MarketingService | listRewards | response | items[].productId | string (uuid) |  | (nullable)
MarketingService | listRewards | response | items[].pointsCost | number |  | (nullable)
MarketingService | listRewards | response | items[].discountValue | number |  | (nullable)
MarketingService | listRewards | response | items[].validityDays | integer |  | (nullable)
MarketingService | listRewards | response | items[].isActive | boolean | yes
MarketingService | listRewards | response | nextCursor | string
MarketingService | listRewards | response | hasMore | boolean | yes
MarketingService | listRewards | param (query) | programmeId | string (uuid)
MarketingService | listRewards | param (query) | pageSize | integer
MarketingService | listRewards | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
IdentityService | listRoles | response | items | array of Role | yes
IdentityService | listRoles | response | items[].id | string (uuid) | yes
IdentityService | listRoles | response | items[].code | string | yes | Unique within the tenant (decided 28 September, audit R108).
IdentityService | listRoles | response | items[].name | string | yes
IdentityService | listRoles | response | items[].description | string
IdentityService | listRoles | response | items[].permissions | array of Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) |  | A role that grants no permissions is not a role.
IdentityService | listRoles | response | items[].inheritsFromRoleId | string (uuid) |  | Role composition, one level deep and no deeper. (nullable)
IdentityService | listRoles | response | items[].isSystem | boolean |  | Seeded roles ship and are editable; deleting one is refused. (default False)
IdentityService | listRoles | response | items[].presetCode | string |  | The preset this role was started from, for the record only (decided 2 October 2026, Chinmay; DEC-007; CHG-CSP-003): the first of createRole.presetCodes, or null for a role ticked by hand. (max length 64; read-only; nullable)
IdentityService | listRoles | response | items[].principalCount | integer
IdentityService | listRoles | response | items[].grantCount | integer
IdentityService | listRoles | response | nextCursor | string
IdentityService | listRoles | response | hasMore | boolean | yes
IdentityService | listRoles | param (query) | pageSize | integer
IdentityService | listRoles | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
TenancyService | listRotaAssignments | response | items | array of RotaAssignment | yes
TenancyService | listRotaAssignments | response | items[].overtimeMinutes | integer |  | BL-044, 1.2.83. (read-only; nullable)
TenancyService | listRotaAssignments | response | items[].restPeriodBefore | integer |  | Minutes since the previous shift ended. (nullable)
TenancyService | listRotaAssignments | response | items[].breachesWorkingHourLimit | boolean |  | Flagged at assignment, not discovered at payroll. (default False; read-only)
TenancyService | listRotaAssignments | response | items[].labourCost | object |  | Cost at the point of scheduling.
TenancyService | listRotaAssignments | response | items[].labourCost.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
TenancyService | listRotaAssignments | response | items[].labourCost.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
TenancyService | listRotaAssignments | response | items[].labourCost.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
TenancyService | listRotaAssignments | response | items[].id | string (uuid) |  | (read-only)
TenancyService | listRotaAssignments | response | items[].principalId | string (uuid) | yes
TenancyService | listRotaAssignments | response | items[].displayName | string |  | (read-only)
TenancyService | listRotaAssignments | response | items[].venueId | string (uuid) | yes
TenancyService | listRotaAssignments | response | items[].departmentId | string (uuid) |  | (nullable)
TenancyService | listRotaAssignments | response | items[].position | string | yes | What they are rostered to do — gate steward, cashier, lifeguard, technician.
TenancyService | listRotaAssignments | response | items[].requiredRoleId | string (uuid) |  | Checked on assignment. (nullable)
TenancyService | listRotaAssignments | response | items[].workstationId | string (uuid) |  | Where the position needs a till. (nullable)
TenancyService | listRotaAssignments | response | items[].startsAt | string (date-time) | yes
TenancyService | listRotaAssignments | response | items[].endsAt | string (date-time) | yes
TenancyService | listRotaAssignments | response | items[].status | RotaStatus: enum (planned, published, confirmed, swapPending, cancelled, completed, noShow)
TenancyService | listRotaAssignments | response | items[].breakMinutes | integer |  | (nullable)
TenancyService | listRotaAssignments | response | items[].note | string |  | (nullable)
TenancyService | listRotaAssignments | response | nextCursor | string
TenancyService | listRotaAssignments | response | hasMore | boolean | yes
TenancyService | listRotaAssignments | param (query) | from | string (date) |  | First calendar day, in the Region's time zone, not UTC.
TenancyService | listRotaAssignments | param (query) | to | string (date) |  | Last calendar day, in the Region's time zone, not UTC.
TenancyService | listRotaAssignments | param (query) | principalId | string (uuid)
TenancyService | listRotaAssignments | param (query) | departmentId | string (uuid)
TenancyService | listRotaAssignments | param (query) | pageSize | integer
TenancyService | listRotaAssignments | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
TenancyService | listSaleBoards | param (query) | venueId | string (uuid)
TenancyService | listSaleBoards | param (query) | kind | SaleBoardKind: enum (ticketing, fnb, retail, mixed)
InventoryService | listSerialisedItems | response | items | array of SerialisedItem | yes
InventoryService | listSerialisedItems | response | items[].id | string (uuid) | yes
InventoryService | listSerialisedItems | response | items[].itemId | string (uuid) | yes
InventoryService | listSerialisedItems | response | items[].batchId | string (uuid) |  | The batch it arrived in, where the item is both lotted and serialised. (nullable)
InventoryService | listSerialisedItems | response | items[].serial | string | yes | Unique within the item, not globally.
InventoryService | listSerialisedItems | response | items[].locationId | string (uuid)
InventoryService | listSerialisedItems | response | items[].status | enum (inStock, reserved, sold, returned, damaged, lost, inTransit, warranty) | yes
InventoryService | listSerialisedItems | response | items[].soldOnOrderLineId | string (uuid) |  | The link that makes serialisation worth having. (nullable)
InventoryService | listSerialisedItems | response | items[].warrantyUntil | string (date) |  | (nullable)
InventoryService | listSerialisedItems | response | items[].receivedAt | string (date-time)
InventoryService | listSerialisedItems | response | nextCursor | string
InventoryService | listSerialisedItems | response | hasMore | boolean | yes
InventoryService | listSerialisedItems | param (query) | serial | string |  | Exact match.
InventoryService | listSerialisedItems | param (query) | status | string
InventoryService | listSerialisedItems | param (query) | pageSize | integer
InventoryService | listSerialisedItems | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
OrderService | listShifts | response | items | array of Shift | yes
OrderService | listShifts | response | items[].id | string (uuid) | yes | Client-generated UUIDv7.
OrderService | listShifts | response | items[].workstationId | string (uuid) | yes
OrderService | listShifts | response | items[].venueId | string (uuid) | yes
OrderService | listShifts | response | items[].scopePath | string | yes
OrderService | listShifts | response | items[].principalId | string (uuid) | yes | Who opened it.
OrderService | listShifts | response | items[].principalDisplayName | string
OrderService | listShifts | response | items[].incidents | array of object |  | BL-097.
OrderService | listShifts | response | items[].incidents[].kind | enum (noSale, drawerOpen, override, voidAfterPayment, guestDispute, tillJam, priceQuery, other)
OrderService | listShifts | response | items[].incidents[].at | string (date-time)
OrderService | listShifts | response | items[].incidents[].principalId | string (uuid)
OrderService | listShifts | response | items[].incidents[].note | string |  | (nullable)
OrderService | listShifts | response | items[].status | ShiftStatus: enum (pendingApproval, open, suspended, pendingVariance, pendingClosure, closed, autoClosed) | yes
OrderService | listShifts | response | items[].currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | listShifts | response | items[].currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | listShifts | response | items[].depositBoxCode | string |  | (nullable)
OrderService | listShifts | response | items[].bagNumber | string |  | (nullable)
OrderService | listShifts | response | items[].openingFloat | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listShifts | response | items[].openingFloat.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listShifts | response | items[].openingFloat.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listShifts | response | items[].openingFloat.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listShifts | response | items[].salesTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listShifts | response | items[].salesTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listShifts | response | items[].salesTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listShifts | response | items[].salesTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listShifts | response | items[].refundsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listShifts | response | items[].refundsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listShifts | response | items[].refundsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listShifts | response | items[].refundsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listShifts | response | items[].liftsTotal | Money |  | On the wire this is three fields; in the database it is one column.
OrderService | listShifts | response | items[].liftsTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listShifts | response | items[].liftsTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listShifts | response | items[].liftsTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listShifts | response | items[].expectedCash | object |  | 26 September, pull audit R207. (read-only; nullable)
OrderService | listShifts | response | items[].expectedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listShifts | response | items[].expectedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listShifts | response | items[].expectedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listShifts | response | items[].countedCash | object |  | What the close count found. (read-only; nullable)
OrderService | listShifts | response | items[].countedCash.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listShifts | response | items[].countedCash.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listShifts | response | items[].countedCash.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listShifts | response | items[].variance | object |  | Counted minus expected, as ShiftCloseResult.variance. (read-only; nullable)
OrderService | listShifts | response | items[].variance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | listShifts | response | items[].variance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | listShifts | response | items[].variance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | listShifts | response | items[].cashierReason | enum (tillError, unrecordedRefund, miscount, other) |  | What the cashier said went wrong, given with the blind count (CloseShiftRequest.cashierReason, DI-803) without seeing the variance; the supervisor reads it beside the variance on BO-040 (CHG-FIN-003). (read-only; nullable)
OrderService | listShifts | response | items[].cashierNote | string |  | The cashier's note with the count (CloseShiftRequest.notes; CHG-FIN-003). (max length 1000; read-only; nullable)
OrderService | listShifts | response | items[].varianceReasonRequired | boolean |  | Computed, not stored (CHG-R4-019): true while the shift is pendingClosure because its count differs from the expected figure within the threshold and no cashierReason is recorded. (read-only)
OrderService | listShifts | response | items[].heldLeaseCount | integer |  | Inventory leases currently held by this workstation.
OrderService | listShifts | response | items[].openedAt | string (date-time) | yes
OrderService | listShifts | response | items[].businessDate | string (date) |  | The business day the shift belongs to (12 October 2026, CHG-R6-032): the venue-local date of openedAt taken against the venue's businessDayCutoff (tenancy VenueSettings, inheriting the tenant default… (read-only)
OrderService | listShifts | response | items[].recordedAt | string (date-time) |  | When the device recorded the open.
OrderService | listShifts | response | items[].suspendedAt | string (date-time) |  | (nullable)
OrderService | listShifts | response | items[].suspendReason | string |  | The reason given to suspendShift. (max length 200; nullable)
OrderService | listShifts | response | items[].closedAt | string (date-time) |  | (nullable)
OrderService | listShifts | response | items[].closedByPrincipalId | string (uuid) |  | Who submitted the close count. (nullable)
OrderService | listShifts | response | items[].recountRequestedAt | string (date-time) |  | Set by rejectShiftVariance, cleared by the cashier's recount (decided 2 October 2026, Chinmay; DEC-175; CHG-CSP-013; DI-804). (read-only; nullable)
OrderService | listShifts | response | items[].recountRequestedByPrincipalId | string (uuid) |  | The supervisor who sent the count back (CHG-CSP-013). (read-only; nullable)
OrderService | listShifts | response | items[].recountReason | string |  | The supervisor's reason, shown to the cashier; never an amount (CHG-CSP-013, CHG-FIN-003). (max length 500; read-only; nullable)
OrderService | listShifts | response | items[].countNumber | integer |  | How many close counts the shift has had: 0 before the first, 1 after it, 2 after a recount (CHG-CSP-013). (min 0; read-only)
OrderService | listShifts | response | items[].syncedAt | string (date-time) |  | Null while the shift has unsynced operations. (nullable)
OrderService | listShifts | response | items[].approvals | array of object
OrderService | listShifts | response | items[].approvals[].kind | enum (open, close, variance) | yes | open from approveShiftOpen, close from approveShiftClose, variance from acceptShiftVariance.
OrderService | listShifts | response | items[].approvals[].principalId | string (uuid) | yes
OrderService | listShifts | response | items[].approvals[].at | string (date-time) | yes
OrderService | listShifts | response | items[].approvals[].reason | string
OrderService | listShifts | response | nextCursor | string
OrderService | listShifts | response | hasMore | boolean | yes
OrderService | listShifts | param (query) | workstationId | string (uuid)
OrderService | listShifts | param (query) | status | ShiftStatus: enum (pendingApproval, open, suspended, pendingVariance, pendingClosure, closed, autoClosed)
OrderService | listShifts | param (query) | openedFrom | string (date-time)
OrderService | listShifts | param (query) | openedTo | string (date-time)
OrderService | listShifts | param (query) | businessDate | string (date) |  | The shifts of one business date (Shift.businessDate, closing at the venue's businessDayCutoff; CHG-R6-032), as the daily reconciliation asks for them.
OrderService | listShifts | param (query) | pageSize | integer
OrderService | listShifts | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
OrderService | listSyncRejections | response | items | array of SyncRejection | yes
OrderService | listSyncRejections | response | items[].id | string (uuid) | yes
OrderService | listSyncRejections | response | items[].workstationId | string (uuid) | yes
OrderService | listSyncRejections | response | items[].kind | enum (order, payment, refund, void, scan) | yes
OrderService | listSyncRejections | response | items[].recordedAt | string (date-time)
OrderService | listSyncRejections | response | items[].rejectedAt | string (date-time) | yes
OrderService | listSyncRejections | response | items[].problem | Problem | yes | RFC 9457 problem details.
OrderService | listSyncRejections | response | items[].problem.type | string (uri) | yes | The problem type URI, https://api.ticvai.com/problems/<slug>.
OrderService | listSyncRejections | response | items[].problem.title | string | yes
OrderService | listSyncRejections | response | items[].problem.status | integer | yes
OrderService | listSyncRejections | response | items[].problem.detail | string
OrderService | listSyncRejections | response | items[].problem.instance | string
OrderService | listSyncRejections | response | items[].problem.traceId | string
OrderService | listSyncRejections | response | items[].problem.errors | array of object
OrderService | listSyncRejections | response | items[].payload | object |  | Deliberately open: the journal entry exactly as the till sent it.
OrderService | listSyncRejections | response | items[].resolvedAt | string (date-time) |  | (read-only; nullable)
OrderService | listSyncRejections | response | items[].resolvedByPrincipalId | string (uuid) |  | (read-only; nullable)
OrderService | listSyncRejections | response | items[].resolution | enum (posted, voided, refunded) |  | What resolveSyncRejection recorded. (read-only; nullable)
OrderService | listSyncRejections | response | items[].resolvedRecordId | string (uuid) |  | The order, void or refund the resolution produced — what stops the entry being posted twice. (read-only; nullable)
OrderService | listSyncRejections | response | nextCursor | string
OrderService | listSyncRejections | response | hasMore | boolean | yes
OrderService | listSyncRejections | param (query) | workstationId | string (uuid) |  | Exact match on the till that journalled the entry.
OrderService | listSyncRejections | param (query) | kind | enum (order, payment, refund, void, scan) |  | Exact match on SyncRejection.kind.
OrderService | listSyncRejections | param (query) | resolved | boolean |  | false returns only rejections still waiting for a decision (resolvedAt null), true only those resolved.
OrderService | listSyncRejections | param (query) | pageSize | integer
OrderService | listSyncRejections | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
FnbService | listTableCombinations | response | items | array of TableCombination | yes
FnbService | listTableCombinations | response | items[].id | string (uuid) |  | (read-only)
FnbService | listTableCombinations | response | items[].outletId | string (uuid) |  | The outlet in the path. (read-only)
FnbService | listTableCombinations | response | items[].tableIds | array of string (uuid) | yes | (min items 2)
FnbService | listTableCombinations | response | items[].combinedCovers | integer | yes | (min 1)
FnbService | listTableCombinations | response | items[].setupMinutes | integer |  | (default 5)
FnbService | listTableCombinations | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
FnbService | listTableCombinations | response | nextCursor | string
FnbService | listTableCombinations | response | hasMore | boolean | yes
FnbService | listTableCombinations | param (path) | outletId | string (uuid) | yes
FnbService | listTableCombinations | param (path) | outletId | string (uuid) | yes
FnbService | listTableCombinations | param (query) | pageSize | integer
FnbService | listTableCombinations | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
FnbService | listTableReservations | response | items | array of TableReservation | yes
FnbService | listTableReservations | response | items[].id | string (uuid) |  | (read-only)
FnbService | listTableReservations | response | items[].outletId | string (uuid) | yes
FnbService | listTableReservations | response | items[].subjectId | string (uuid) |  | (nullable)
FnbService | listTableReservations | response | items[].guestName | string
FnbService | listTableReservations | response | items[].contactPoint | string
FnbService | listTableReservations | response | items[].partySize | integer | yes | (min 1)
FnbService | listTableReservations | response | items[].startsAt | string (date-time) | yes
FnbService | listTableReservations | response | items[].durationMinutes | integer |  | How long the cover is held.
FnbService | listTableReservations | response | items[].tables | array of FnbReservationTable |  | The dining tables assigned to this reservation, one row each.
FnbService | listTableReservations | response | items[].tables[].reservationId | string (uuid) | yes
FnbService | listTableReservations | response | items[].tables[].tableId | string (uuid) | yes
FnbService | listTableReservations | response | items[].tables[].createdAt | string (date-time) | yes
FnbService | listTableReservations | response | items[].status | TableReservationStatus: enum (awaitingDeposit, booked, confirmed, seated, completed, cancelled, noShow) |  | awaitingDeposit only where the venue's dining deposit applies (decided 29 September, rev 3 REV3-8b); a booking with no deposit starts booked.
FnbService | listTableReservations | response | items[].groupId | string (uuid) |  | 5.1.2. (nullable)
FnbService | listTableReservations | response | items[].notes | string |  | Allergies, accessibility needs and other requests, as the guest wrote them.
FnbService | listTableReservations | response | items[].seatingPreference | string |  | The seating area the guest asked for, e.g. (max length 64; nullable)
FnbService | listTableReservations | response | items[].occasion | enum (birthday, anniversary, business, celebration, other) |  | The occasion the guest named (workbook Q204, DI-337; CHG-CSA-018). (nullable)
FnbService | listTableReservations | response | items[].takenByPrincipalId | string (uuid) |  | The staff member who took the booking (createTableReservationForGuest); null for a guest's own booking (CHG-CSA-045). (read-only; nullable)
FnbService | listTableReservations | response | items[].actualPartySize | integer |  | (read-only; nullable)
FnbService | listTableReservations | response | items[].tableVisitId | string (uuid) |  | (read-only; nullable)
FnbService | listTableReservations | response | items[].deposit | TableReservationDeposit |  | The deposit this booking holds, snapshotted from orders.DepositPolicy.dining when it was made (decided 29 September, rev 3 REV3-8b). (read-only; nullable)
FnbService | listTableReservations | response | items[].deposit.amount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | listTableReservations | response | items[].deposit.basis | enum (fixedPerGuest, fixedPerTable, percentOfMinimumSpend) | yes
FnbService | listTableReservations | response | items[].deposit.holdExpiresAt | string (date-time) |  | While awaitingDeposit, when the held cover is released if the deposit has not been authorised. (nullable)
FnbService | listTableReservations | response | items[].deposit.refundableUntil | string (date-time) |  | startsAt less dining.refundableUntilHours. (nullable)
FnbService | listTableReservations | response | items[].deposit.variantId | string (uuid) |  | The venue's table-deposit variant, DepositPolicy.dining.depositVariantId, which the client sends to addCartLine with this booking's id.
FnbService | listTableReservations | response | items[].deposit.cartLineId | string (uuid) |  | The orders.CartLine carrying the deposit, once added. (nullable)
FnbService | listTableReservations | response | items[].deposit.depositId | string (uuid) |  | The orders.deposit row, once the payment is authorised. (nullable)
FnbService | listTableReservations | response | items[].createdAt | string (date-time) |  | (read-only)
FnbService | listTableReservations | response | nextCursor | string
FnbService | listTableReservations | response | hasMore | boolean | yes
FnbService | listTableReservations | param (query) | outletId | string (uuid)
FnbService | listTableReservations | param (query) | date | string (date) |  | A calendar day, in the Region's time zone, not UTC.
FnbService | listTableReservations | param (query) | pageSize | integer
FnbService | listTableReservations | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
LedgerService | listTaxInvoices | response | items | array of FinTaxInvoice | yes
LedgerService | listTaxInvoices | response | items[].id | string (uuid) | yes | (read-only)
LedgerService | listTaxInvoices | response | items[].invoiceNumber | string | yes | Server-assigned from the legal entity's series for the document kind, in sequence and without gaps, e.g. (read-only)
LedgerService | listTaxInvoices | response | items[].invoiceType | FinTaxInvoiceType: enum (simplified, full, consolidated) | yes | 5.7.93.
LedgerService | listTaxInvoices | response | items[].status | FinTaxInvoiceStatus: enum (issued, partiallyCredited, fullyCredited, superseded) | yes | issued until a credit memo is issued against it; superseded where a full invoice replaced a simplified one for the same supply (only if the law allows it; see issueTaxInvoice).
LedgerService | listTaxInvoices | response | items[].legalEntityId | string (uuid) | yes
LedgerService | listTaxInvoices | response | items[].templateId | string (uuid) |  | (nullable)
LedgerService | listTaxInvoices | response | items[].venueId | string (uuid) |  | (nullable)
LedgerService | listTaxInvoices | response | items[].orderIds | array of string (uuid)
LedgerService | listTaxInvoices | response | items[].supplierName | string
LedgerService | listTaxInvoices | response | items[].supplierAddress | string |  | (nullable)
LedgerService | listTaxInvoices | response | items[].supplierTaxRegistrationNumber | string |  | (nullable)
LedgerService | listTaxInvoices | response | items[].buyerSubjectId | string (uuid) |  | The guest the orders belong to; the key a guest's own reads filter on. (nullable)
LedgerService | listTaxInvoices | response | items[].buyerName | string |  | (nullable)
LedgerService | listTaxInvoices | response | items[].buyerAddress | string |  | (nullable)
LedgerService | listTaxInvoices | response | items[].buyerCountryCode | string |  | (pattern ^[A-Z]{2}$; nullable)
LedgerService | listTaxInvoices | response | items[].buyerTaxRegistrationNumber | string |  | (nullable)
LedgerService | listTaxInvoices | response | items[].customerAccountId | string (uuid) |  | (nullable)
LedgerService | listTaxInvoices | response | items[].issuedAt | string (date-time) | yes
LedgerService | listTaxInvoices | response | items[].supplyDate | string (date) | yes | The date of supply where it differs from the issue date (the latest order's payment date on a consolidated invoice).
LedgerService | listTaxInvoices | response | items[].currency | string | yes | (pattern ^[A-Z]{3}$)
LedgerService | listTaxInvoices | response | items[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].netAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | listTaxInvoices | response | items[].netAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | listTaxInvoices | response | items[].netAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | listTaxInvoices | response | items[].discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].discountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | listTaxInvoices | response | items[].discountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | listTaxInvoices | response | items[].discountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | listTaxInvoices | response | items[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | listTaxInvoices | response | items[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | listTaxInvoices | response | items[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | listTaxInvoices | response | items[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | listTaxInvoices | response | items[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | listTaxInvoices | response | items[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | listTaxInvoices | response | items[].taxAmountInLegalCurrency | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].taxAmountInLegalCurrency.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | listTaxInvoices | response | items[].taxAmountInLegalCurrency.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | listTaxInvoices | response | items[].taxAmountInLegalCurrency.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | listTaxInvoices | response | items[].legalCurrency | string |  | The legal entity's currency (AED in the UAE), in which the law requires the tax and the gross amount (CHG-FIN-011). (pattern ^[A-Z]{3}$; read-only)
LedgerService | listTaxInvoices | response | items[].grossAmountInLegalCurrency | object |  | The gross amount payable in the legal currency (Executive Regulation Art. (read-only)
LedgerService | listTaxInvoices | response | items[].grossAmountInLegalCurrency.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | listTaxInvoices | response | items[].grossAmountInLegalCurrency.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | listTaxInvoices | response | items[].grossAmountInLegalCurrency.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | listTaxInvoices | response | items[].legalFxRate | object |  | Units of the legal currency per one unit of currency, printed with the tax where the invoice is not in the legal currency (Art. (read-only; nullable)
LedgerService | listTaxInvoices | response | items[].legalFxRateSource | object |  | uaeCentralBank for a UAE legal entity (Decree-Law Art. (read-only; nullable)
LedgerService | listTaxInvoices | response | items[].paidCurrency | string |  | Where the guest paid in a currency they selected (orders.Order.chargeCurrency, CHG-FIN-001), printed as payment information with paidAmount and the charge rate. (pattern ^[A-Z]{3}$; read-only; nullable)
LedgerService | listTaxInvoices | response | items[].paidAmount | object |  | What the guest paid in paidCurrency (orders.Order.chargeTotal). (read-only)
LedgerService | listTaxInvoices | response | items[].paidAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | listTaxInvoices | response | items[].paidAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | listTaxInvoices | response | items[].paidAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | listTaxInvoices | response | items[].reverseChargeStatement | string |  | Where the recipient must account for the tax, the statement saying so and the Decree-Law provision (Art. (read-only; nullable)
LedgerService | listTaxInvoices | response | items[].creditedAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].creditedAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
LedgerService | listTaxInvoices | response | items[].creditedAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
LedgerService | listTaxInvoices | response | items[].creditedAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
LedgerService | listTaxInvoices | response | items[].languages | array of string
LedgerService | listTaxInvoices | response | items[].supersedesInvoiceId | string (uuid) |  | (nullable)
LedgerService | listTaxInvoices | response | items[].renditionAssetId | string (uuid) |  | The PDF rendered at issue; read through getTaxDocumentRendition. (read-only; nullable)
LedgerService | listTaxInvoices | response | items[].eInvoiceStatus | FinEInvoiceTransmissionStatus: enum (notRequired, queued, sent, accepted, rejected, failed) |  | 6.1.1.
LedgerService | listTaxInvoices | response | items[].issuedByPrincipalId | string (uuid) |  | Null where the platform issued it. (read-only; nullable)
LedgerService | listTaxInvoices | response | items[].lines | array of FinTaxInvoiceLine | yes
LedgerService | listTaxInvoices | response | items[].lines[].lineNumber | integer | yes | (min 1)
LedgerService | listTaxInvoices | response | items[].lines[].orderId | string (uuid)
LedgerService | listTaxInvoices | response | items[].lines[].orderLineId | string (uuid) |  | (nullable)
LedgerService | listTaxInvoices | response | items[].lines[].description | string | yes | (max length 500)
LedgerService | listTaxInvoices | response | items[].lines[].quantity | number | yes
LedgerService | listTaxInvoices | response | items[].lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].lines[].discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].lines[].netAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].lines[].taxCodeId | string (uuid) |  | (nullable)
LedgerService | listTaxInvoices | response | items[].lines[].taxRate | number |  | (min 0; max 100)
LedgerService | listTaxInvoices | response | items[].lines[].taxCategory | FinTaxCategory: enum (standardRated, zeroRated, exempt, outOfScope, reverseCharge) | yes | How a line is treated for VAT.
LedgerService | listTaxInvoices | response | items[].lines[].taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].lines[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].lines[].creditedAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].lines[].grossAmountInLegalCurrency | object |  | The amount payable for the line in the legal currency (AED), Executive Regulation Art. (read-only)
LedgerService | listTaxInvoices | response | items[].taxSummary | array of object |  | VAT per rate and category, summed from the lines for the response.
LedgerService | listTaxInvoices | response | items[].taxSummary[].taxCategory | FinTaxCategory: enum (standardRated, zeroRated, exempt, outOfScope, reverseCharge) |  | How a line is treated for VAT.
LedgerService | listTaxInvoices | response | items[].taxSummary[].taxRate | number
LedgerService | listTaxInvoices | response | items[].taxSummary[].taxableAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].taxSummary[].taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
LedgerService | listTaxInvoices | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
LedgerService | listTaxInvoices | response | nextCursor | string
LedgerService | listTaxInvoices | response | hasMore | boolean | yes
LedgerService | listTaxInvoices | param (query) | orderId | string (uuid) |  | Invoices covering this order, including a consolidated invoice that names it.
LedgerService | listTaxInvoices | param (query) | legalEntityId | string (uuid)
LedgerService | listTaxInvoices | param (query) | invoiceType | FinTaxInvoiceType: enum (simplified, full, consolidated)
LedgerService | listTaxInvoices | param (query) | status | FinTaxInvoiceStatus: enum (issued, partiallyCredited, fullyCredited, superseded)
LedgerService | listTaxInvoices | param (query) | issuedFrom | string (date) |  | A day in the region's time zone, local midnight to local midnight.
LedgerService | listTaxInvoices | param (query) | issuedTo | string (date) |  | A day in the region's time zone, local midnight to local midnight.
LedgerService | listTaxInvoices | param (query) | pageSize | integer
LedgerService | listTaxInvoices | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
PlatformService | listTenants | response | items | array of Tenant | yes
PlatformService | listTenants | response | items[].id | string (uuid) | yes
PlatformService | listTenants | response | items[].code | string | yes
PlatformService | listTenants | response | items[].name | string | yes
PlatformService | listTenants | response | items[].status | TenantStatus: enum (onboarding, active, suspended, terminating, terminated) | yes
PlatformService | listTenants | response | items[].suspensionMode | SuspensionMode: enum (readOnly, noNewSales, fullLockout) |  | Access validation continues under every mode.
PlatformService | listTenants | response | items[].suspensionReason | string |  | (nullable)
PlatformService | listTenants | response | items[].suspensionEffectiveAt | string (date-time) |  | When the suspension takes, or took, effect — suspendTenant.effectiveAt. (nullable)
PlatformService | listTenants | response | items[].suspensionNoticeMessage | LocalisedText |  | The notice shown to the tenant's users about the suspension — suspendTenant.noticeMessage.
PlatformService | listTenants | response | items[].terminationScheduledAt | string (date-time) |  | When terminateTenant started the retention window. (nullable)
PlatformService | listTenants | response | items[].terminationRetentionUntil | string (date-time) |  | terminationScheduledAt plus the request's retentionDays. (nullable)
PlatformService | listTenants | response | items[].terminationReason | string |  | (max length 1000; nullable)
PlatformService | listTenants | response | items[].terminationRequestedByPrincipalId | string (uuid) |  | (nullable)
PlatformService | listTenants | response | items[].planId | string (uuid) |  | (nullable)
PlatformService | listTenants | response | items[].planName | string |  | (nullable)
PlatformService | listTenants | response | items[].cellCount | integer
PlatformService | listTenants | response | items[].venueCount | integer
PlatformService | listTenants | response | items[].regionId | string (uuid) |  | The tenant's home region: the tenancy region node whose RegionSettings govern tenant-wide gates, today allowedAiResidencies (decided 28 September, audit R203). (read-only; nullable)
PlatformService | listTenants | response | items[].billingEmail | string
PlatformService | listTenants | response | items[].billingAddress | string |  | Accepted by createTenant and updateTenant; stored here so the response can return what was sent. (max length 500; nullable)
PlatformService | listTenants | response | items[].accountManagerPrincipalId | string (uuid) |  | (nullable)
PlatformService | listTenants | response | items[].createdAt | string (date-time) | yes
PlatformService | listTenants | response | items[].activatedAt | string (date-time) |  | (nullable)
PlatformService | listTenants | response | nextCursor | string
PlatformService | listTenants | response | hasMore | boolean | yes
PlatformService | listTenants | param (query) | status | TenantStatus: enum (onboarding, active, suspended, terminating, terminated)
PlatformService | listTenants | param (query) | planId | string (uuid)
PlatformService | listTenants | param (query) | pageSize | integer
PlatformService | listTenants | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
OrderService | listTicketTransfers | response | items | array of TicketTransfer | yes
OrderService | listTicketTransfers | response | items[].id | string (uuid) | yes
OrderService | listTicketTransfers | response | items[].orderId | string (uuid) | yes
OrderService | listTicketTransfers | response | items[].ticketIds | array of string (uuid) | yes | The entitlements offered — Entitlement.id values, since a ticket is an entitlement.
OrderService | listTicketTransfers | response | items[].fromSubjectId | string (uuid)
OrderService | listTicketTransfers | response | items[].toSubjectId | string (uuid) |  | Set only on claim. (nullable)
OrderService | listTicketTransfers | response | items[].recipientAddressMasked | string
OrderService | listTicketTransfers | response | items[].status | enum (offered, claimed, expired, cancelled) | yes
OrderService | listTicketTransfers | response | items[].claimUrl | string |  | (nullable)
OrderService | listTicketTransfers | response | items[].claimToken | string (password) |  | What claimTicketTransfer checks the presented claimToken against.
OrderService | listTicketTransfers | response | items[].offeredAt | string (date-time) | yes
OrderService | listTicketTransfers | response | items[].claimedAt | string (date-time) |  | (nullable)
OrderService | listTicketTransfers | response | items[].expiresAt | string (date-time) | yes | An unclaimed transfer expires and the tickets return.
OrderService | listTicketTransfers | response | nextCursor | string
OrderService | listTicketTransfers | response | hasMore | boolean | yes
OrderService | listTicketTransfers | param (query) | direction | enum (sent, received) |  | sent for transfers the caller offered, received for those they claimed.
OrderService | listTicketTransfers | param (query) | status | enum (offered, claimed, expired, cancelled) |  | Exact match on TicketTransfer.status.
OrderService | listTicketTransfers | param (query) | pageSize | integer
OrderService | listTicketTransfers | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
VenueOpsService | listTransportPassOffers | response | items | array of PassOffer | yes
VenueOpsService | listTransportPassOffers | response | items[].passTypeId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | listTransportPassOffers | response | items[].catalogueProductId | string (uuid) | yes
VenueOpsService | listTransportPassOffers | response | items[].routeId | string (uuid) |  | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | listTransportPassOffers | response | items[].name | string | yes
VenueOpsService | listTransportPassOffers | response | items[].description | string
VenueOpsService | listTransportPassOffers | response | items[].kind | enum (multiTrip, unlimited)
VenueOpsService | listTransportPassOffers | response | items[].trips | integer |  | (nullable)
VenueOpsService | listTransportPassOffers | response | items[].validityDays | integer | yes
VenueOpsService | listTransportPassOffers | response | items[].price | Money | yes | On the wire this is three fields; in the database it is one column.
VenueOpsService | listTransportPassOffers | response | items[].price.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | listTransportPassOffers | response | items[].price.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | listTransportPassOffers | response | items[].price.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | listTransportPassOffers | response | items[].saving | Money |  | On the wire this is three fields; in the database it is one column.
VenueOpsService | listTransportPassOffers | response | items[].saving.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
VenueOpsService | listTransportPassOffers | response | items[].saving.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
VenueOpsService | listTransportPassOffers | response | items[].saving.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
VenueOpsService | listTransportPassOffers | response | items[].variants | array of object |  | What addCartLine sells for this pass (4 October 2026, CHG-FXC-011; GST-050, GST-056): one catalogue variant of catalogueProductId per passenger type.
VenueOpsService | listTransportPassOffers | response | items[].variants[].passengerTypeId | string (uuid) | yes
VenueOpsService | listTransportPassOffers | response | items[].variants[].variantId | string (uuid) | yes
VenueOpsService | listTransportPassOffers | response | nextCursor | string
VenueOpsService | listTransportPassOffers | response | hasMore | boolean | yes
VenueOpsService | listTransportPassOffers | param (query) | fromStationId | string (uuid) | yes
VenueOpsService | listTransportPassOffers | param (query) | toStationId | string (uuid) | yes
VenueOpsService | listTransportPassOffers | param (query) | pageSize | integer
VenueOpsService | listTransportPassOffers | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
VenueOpsService | listTransportRoutes | response | items | array of TransportRoute | yes
VenueOpsService | listTransportRoutes | response | items[].venueId | string (uuid) | yes
VenueOpsService | listTransportRoutes | response | items[].code | string | yes | The line and direction, e.g. (max length 32)
VenueOpsService | listTransportRoutes | response | items[].lineCode | string |  | The public line number shared by both directions, e.g. (max length 16)
VenueOpsService | listTransportRoutes | response | items[].name | LocalisedText | yes
VenueOpsService | listTransportRoutes | response | items[].colour | string |  | (pattern ^#[0-9a-fA-F]{6}$)
VenueOpsService | listTransportRoutes | response | items[].pairedRouteId | string (uuid) |  | The same line run the other way. (nullable)
VenueOpsService | listTransportRoutes | response | items[].bookingCutoffMinutes | integer |  | How long before a departure leaves the boarding stop that online sale stops. (min 0; max 1440; default 5)
VenueOpsService | listTransportRoutes | response | items[].stops | array of RouteStop | yes
VenueOpsService | listTransportRoutes | response | items[].stops[].stationId | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | listTransportRoutes | response | items[].stops[].offsetMinutes | integer | yes | Minutes after the departure from the first stop that the coach leaves this one. (min 0; max 1440)
VenueOpsService | listTransportRoutes | response | items[].stops[].boardingAllowed | boolean |  | (default True)
VenueOpsService | listTransportRoutes | response | items[].stops[].alightingAllowed | boolean |  | (default True)
VenueOpsService | listTransportRoutes | response | items[].stops[].id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | listTransportRoutes | response | items[].stops[].sequence | integer | yes | 1 for the origin. (min 1)
VenueOpsService | listTransportRoutes | response | items[].stops[].station | Station
VenueOpsService | listTransportRoutes | response | items[].id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | listTransportRoutes | response | items[].status | TransportRouteStatus: enum (draft, active, suspended, retired) | yes
VenueOpsService | listTransportRoutes | response | items[].totalMinutes | integer |  | The last stop's offset. (read-only)
VenueOpsService | listTransportRoutes | response | items[].catalogueEventId | string (uuid) |  | The catalogue event its departures are performances of. (read-only)
VenueOpsService | listTransportRoutes | response | items[].catalogueProductId | string (uuid) |  | The one-way trip product (kind timedAdmission); one variant per passenger type. (read-only)
VenueOpsService | listTransportRoutes | response | nextCursor | string
VenueOpsService | listTransportRoutes | response | hasMore | boolean | yes
VenueOpsService | listTransportRoutes | param (query) | venueId | string (uuid) | yes
VenueOpsService | listTransportRoutes | param (query) | fromStationId | string (uuid)
VenueOpsService | listTransportRoutes | param (query) | toStationId | string (uuid)
VenueOpsService | listTransportRoutes | param (query) | status | TransportRouteStatus: enum (draft, active, suspended, retired)
VenueOpsService | listTransportRoutes | param (query) | pageSize | integer
VenueOpsService | listTransportRoutes | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
VenueOpsService | listTransportStations | response | items | array of Station | yes
VenueOpsService | listTransportStations | response | items[].venueId | string (uuid) | yes
VenueOpsService | listTransportStations | response | items[].code | string | yes | Short operator code, e.g. (max length 32)
VenueOpsService | listTransportStations | response | items[].name | LocalisedText | yes
VenueOpsService | listTransportStations | response | items[].shortName | LocalisedText |  | The label on the route diagram and the map pin (Union Sq, MoE).
VenueOpsService | listTransportStations | response | items[].latitude | number |  | (min -90; max 90; nullable)
VenueOpsService | listTransportStations | response | items[].longitude | number |  | (min -180; max 180; nullable)
VenueOpsService | listTransportStations | response | items[].id | string (uuid) | yes | Every id is a uuid, and every new one is a UUIDv7 (ADR-0056, 30 September): time-ordered, so a key in an index stays in insertion order, and minted by the service with the kernel's Id.New().
VenueOpsService | listTransportStations | response | items[].active | boolean | yes | (default True)
VenueOpsService | listTransportStations | response | nextCursor | string
VenueOpsService | listTransportStations | response | hasMore | boolean | yes
VenueOpsService | listTransportStations | param (query) | venueId | string (uuid) | yes
VenueOpsService | listTransportStations | param (query) | includeInactive | boolean
VenueOpsService | listTransportStations | param (query) | pageSize | integer
VenueOpsService | listTransportStations | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
AiService | listVenueHistoryImports | response | items | array of AiHistoryImport | yes
AiService | listVenueHistoryImports | response | items[].id | string (uuid) | yes | (read-only)
AiService | listVenueHistoryImports | response | items[].venueId | string (uuid) | yes
AiService | listVenueHistoryImports | response | items[].dataKind | enum (attendance, admissions, ticketSales, fnbSales, retailSales, queueReadings, staffShifts) | yes
AiService | listVenueHistoryImports | response | items[].assetId | string (uuid)
AiService | listVenueHistoryImports | response | items[].sourceSystem | string |  | (nullable)
AiService | listVenueHistoryImports | response | items[].columnMapping | object
AiService | listVenueHistoryImports | response | items[].dryRun | boolean |  | (default False)
AiService | listVenueHistoryImports | response | items[].status | enum (queued, validating, loading, completed, completedWithRejections, failed) | yes | (read-only)
AiService | listVenueHistoryImports | response | items[].periodFrom | string (date) |  | (read-only; nullable)
AiService | listVenueHistoryImports | response | items[].periodTo | string (date) |  | (read-only; nullable)
AiService | listVenueHistoryImports | response | items[].monthsCovered | integer |  | (read-only)
AiService | listVenueHistoryImports | response | items[].rowsRead | integer |  | (read-only)
AiService | listVenueHistoryImports | response | items[].rowsLoaded | integer |  | (read-only)
AiService | listVenueHistoryImports | response | items[].rowsRejected | integer |  | (read-only)
AiService | listVenueHistoryImports | response | items[].findings | array of object |  | (read-only)
AiService | listVenueHistoryImports | response | items[].findings[].row | integer
AiService | listVenueHistoryImports | response | items[].findings[].code | enum (badDate, badNumber, negativeValue, duplicateDay, unmappedColumn, outOfRange)
AiService | listVenueHistoryImports | response | items[].findings[].detail | string
AiService | listVenueHistoryImports | response | items[].requestedByPrincipalId | string (uuid) |  | (read-only)
AiService | listVenueHistoryImports | response | items[].createdAt | string (date-time) |  | (read-only)
AiService | listVenueHistoryImports | response | items[].completedAt | string (date-time) |  | (read-only; nullable)
AiService | listVenueHistoryImports | response | items[].scopePath | string |  | The partition key (ADR-0005). (read-only)
AiService | listVenueHistoryImports | response | nextCursor | string
AiService | listVenueHistoryImports | response | hasMore | boolean | yes
AiService | listVenueHistoryImports | param (path) | venueId | string (uuid) | yes
AiService | listVenueHistoryImports | param (query) | pageSize | integer
AiService | listVenueHistoryImports | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
VenueOpsService | listVisitPlanAlternatives | response | items | array of VisitPlanAlternative | yes
VenueOpsService | listVisitPlanAlternatives | response | items[].kind | enum (attraction, show, meal, shop, rest) | yes
VenueOpsService | listVisitPlanAlternatives | response | items[].venueId | string (uuid) | yes | The item's day venue; an alternative is never from another venue (30 September, MoM 4.7).
VenueOpsService | listVisitPlanAlternatives | response | items[].pointId | string (uuid) |  | (nullable)
VenueOpsService | listVisitPlanAlternatives | response | items[].productId | string (uuid) |  | (nullable)
VenueOpsService | listVisitPlanAlternatives | response | items[].performanceId | string (uuid) |  | (nullable)
VenueOpsService | listVisitPlanAlternatives | response | items[].name | string
VenueOpsService | listVisitPlanAlternatives | response | items[].startsAt | string (date-time) | yes
VenueOpsService | listVisitPlanAlternatives | response | items[].durationMinutes | integer
VenueOpsService | listVisitPlanAlternatives | response | items[].walkMinutes | integer |  | (nullable)
VenueOpsService | listVisitPlanAlternatives | response | items[].expectedWaitMinutes | integer |  | (nullable)
VenueOpsService | listVisitPlanAlternatives | response | items[].matchedInterests | array of string
VenueOpsService | listVisitPlanAlternatives | response | items[].reason | string | yes | Why it is offered, in words the sheet shows, e.g.
VenueOpsService | listVisitPlanAlternatives | response | nextCursor | string
VenueOpsService | listVisitPlanAlternatives | response | hasMore | boolean | yes
VenueOpsService | listVisitPlanAlternatives | param (path) | planId | string (uuid) | yes
VenueOpsService | listVisitPlanAlternatives | param (path) | itemId | string (uuid) | yes
VenueOpsService | listVisitPlanAlternatives | param (query) | kind | enum (attraction, show, meal, shop, rest) |  | Only alternatives of this kind.
VenueOpsService | listVisitPlanAlternatives | param (query) | pageSize | integer
VenueOpsService | listVisitPlanAlternatives | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
WalletService | listWalletTransactions | response | items | array of WalletTransaction | yes
WalletService | listWalletTransactions | response | items[].id | string | yes
WalletService | listWalletTransactions | response | items[].walletId | string (uuid) |  | The wallet this movement is on (SD-027, 29 September).
WalletService | listWalletTransactions | response | items[].walletHoldId | string (uuid) |  | The hold a spend settled, where it came through holdWalletFunds. (nullable)
WalletService | listWalletTransactions | response | items[].kind | WalletTransactionKind: enum (topUp, spend, refund, adjustment, bonus, expiry, transfer) | yes
WalletService | listWalletTransactions | response | items[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | listWalletTransactions | response | items[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | listWalletTransactions | response | items[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | listWalletTransactions | response | items[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | listWalletTransactions | response | items[].balanceAfter | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | listWalletTransactions | response | items[].balanceAfter.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | listWalletTransactions | response | items[].balanceAfter.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | listWalletTransactions | response | items[].balanceAfter.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | listWalletTransactions | response | items[].orderId | string |  | (nullable)
WalletService | listWalletTransactions | response | items[].venueId | string (uuid) |  | (nullable)
WalletService | listWalletTransactions | response | items[].reason | string |  | (nullable)
WalletService | listWalletTransactions | response | items[].principalId | string (uuid) |  | (nullable)
WalletService | listWalletTransactions | response | items[].recordedAt | string (date-time) | yes
WalletService | listWalletTransactions | response | nextCursor | string
WalletService | listWalletTransactions | response | hasMore | boolean | yes
WalletService | listWalletTransactions | param (path) | subjectId | string (uuid) | yes
WalletService | listWalletTransactions | param (header) | X-Consistency-Token | string |  | Opaque token returned by a prior write: the database instance and its WAL LSN (SD-025, 29 September; ADR-0040 allows several instances per region, so an LSN alone is ambiguous).
WalletService | listWalletTransactions | param (query) | pageSize | integer
WalletService | listWalletTransactions | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
WalletService | loadGameCredits | request | id | string (uuid) | yes
WalletService | loadGameCredits | request | credits | integer | yes | (min 1)
WalletService | loadGameCredits | request | bonusCredits | integer |  | (min 0; default 0)
WalletService | loadGameCredits | request | amountPaid | Money |  | On the wire this is three fields; in the database it is one column.
WalletService | loadGameCredits | request | amountPaid.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | loadGameCredits | request | amountPaid.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | loadGameCredits | request | amountPaid.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | loadGameCredits | request | orderId | string
WalletService | loadGameCredits | request | recordedAt | string (date-time) | yes
WalletService | loadGameCredits | response | id | string (uuid) |  | Added 20 August. (read-only)
WalletService | loadGameCredits | response | subjectId | string (uuid) | yes
WalletService | loadGameCredits | response | balance | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | loadGameCredits | response | balance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | loadGameCredits | response | balance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | loadGameCredits | response | balance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | loadGameCredits | response | credits | array of object |  | 4.3.5 and 4.3.19.
WalletService | loadGameCredits | response | credits[].kind | enum (cash, bonus, redemption, refund, goodwill) | yes | cash is money the guest paid and the others are not.
WalletService | loadGameCredits | response | credits[].amount | Money | yes | On the wire this is three fields; in the database it is one column.
WalletService | loadGameCredits | response | credits[].amount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | loadGameCredits | response | credits[].amount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | loadGameCredits | response | credits[].amount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | loadGameCredits | response | credits[].expiresAt | string (date-time) |  | (nullable)
WalletService | loadGameCredits | response | credits[].sourceRef | string |  | (nullable)
WalletService | loadGameCredits | response | credits[].isRefundable | boolean |  | True only for cash. (default False)
WalletService | loadGameCredits | response | bonusBalance | object |  | Promotional value.
WalletService | loadGameCredits | response | bonusBalance.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
WalletService | loadGameCredits | response | bonusBalance.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
WalletService | loadGameCredits | response | bonusBalance.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
WalletService | loadGameCredits | response | currency | string | yes | (pattern ^[A-Z]{3}$)
WalletService | loadGameCredits | response | status | enum (active, suspended, closed) | yes
WalletService | loadGameCredits | response | homeCellName | string |  | Where the authoritative balance lives. (nullable)
WalletService | loadGameCredits | response | expiresAt | string (date-time) |  | (nullable)
WalletService | loadGameCredits | response | lastActivityAt | string (date-time) |  | (nullable)
WalletService | loadGameCredits | param (path) | cardCode | string | yes
WalletService | loadGameCredits | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | logColdChain | request | id | string (uuid) | yes
FnbService | logColdChain | request | goodsReceiptId | string (uuid) |  | (nullable)
FnbService | logColdChain | request | transferId | string (uuid) |  | (nullable)
FnbService | logColdChain | request | recordedAt | string (date-time) | yes
FnbService | logColdChain | request | valueCelsius | number | yes
FnbService | logColdChain | request | thresholdCelsius | number
FnbService | logColdChain | request | decision | enum (accepted, acceptedWithNote, partiallyRejected, rejected) | yes
FnbService | logColdChain | request | correctiveActionId | string (uuid) |  | (nullable)
FnbService | logColdChain | request | supplierClaimRaised | boolean |  | (default False)
FnbService | logColdChain | response | id | string (uuid) | yes
FnbService | logColdChain | response | goodsReceiptId | string (uuid) |  | (nullable)
FnbService | logColdChain | response | transferId | string (uuid) |  | (nullable)
FnbService | logColdChain | response | recordedAt | string (date-time) | yes
FnbService | logColdChain | response | valueCelsius | number | yes
FnbService | logColdChain | response | thresholdCelsius | number
FnbService | logColdChain | response | decision | enum (accepted, acceptedWithNote, partiallyRejected, rejected) | yes
FnbService | logColdChain | response | correctiveActionId | string (uuid) |  | (nullable)
FnbService | logColdChain | response | supplierClaimRaised | boolean |  | (default False)
FnbService | logColdChain | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | logKitchenException | request | kind | enum (equipmentDown, itemRanOut, lateDelivery, staffShort, powerLoss, spillage, other) | yes | chased is not offered here — chaseStation records it.
FnbService | logKitchenException | request | outletId | string (uuid) | yes | The outlet whose kitchen it happened in.
FnbService | logKitchenException | request | stationId | string (uuid) |  | (nullable)
FnbService | logKitchenException | request | ticketId | string (uuid) |  | The ticket it happened on, where there was one. (nullable)
FnbService | logKitchenException | request | durationMinutes | integer |  | (nullable)
FnbService | logKitchenException | request | note | string |  | (nullable)
FnbService | logKitchenException | request | recordedAt | string (date-time) | yes | Device time, not arrival time.
FnbService | logKitchenException | response | id | string (uuid) | yes
FnbService | logKitchenException | response | outletId | string (uuid)
FnbService | logKitchenException | response | stationId | string (uuid) |  | (nullable)
FnbService | logKitchenException | response | ticketId | string (uuid) |  | (nullable)
FnbService | logKitchenException | response | kind | enum (equipmentDown, itemRanOut, lateDelivery, staffShort, powerLoss, spillage, chased, other) | yes | other always carries a note (audit R222).
FnbService | logKitchenException | response | durationMinutes | integer |  | (nullable)
FnbService | logKitchenException | response | raisedAt | string (date-time) | yes
FnbService | logKitchenException | response | raisedByPrincipalId | string (uuid)
FnbService | logKitchenException | response | note | string |  | (nullable)
FnbService | logKitchenException | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | logTemperature | request | id | string (uuid) | yes
FnbService | logTemperature | request | checkPointId | string (uuid) | yes | The unit, station or delivery being read.
FnbService | logTemperature | request | checkPointKind | enum (fridge, freezer, holdingCabinet, blastChiller, coreProbe, delivery, displayCounter, ambient)
FnbService | logTemperature | request | recordedAt | string (date-time) | yes
FnbService | logTemperature | request | recordedByPrincipalId | string (uuid)
FnbService | logTemperature | request | valueCelsius | number | yes
FnbService | logTemperature | request | minCelsius | number |  | (nullable)
FnbService | logTemperature | request | maxCelsius | number |  | (nullable)
FnbService | logTemperature | request | outcome | enum (inRange, outOfRange, notTaken) | yes | notTaken is a record, not an absence.
FnbService | logTemperature | request | deviceReported | boolean |  | A probe reading and a person's reading are different evidence. (default False)
FnbService | logTemperature | request | correctiveActionId | string (uuid) |  | (nullable)
FnbService | logTemperature | response | log | TemperatureLog |  | Board 5J of the client F&B pack, 20 August.
FnbService | logTemperature | response | log.id | string (uuid) | yes
FnbService | logTemperature | response | log.checkPointId | string (uuid) | yes | The unit, station or delivery being read.
FnbService | logTemperature | response | log.checkPointKind | enum (fridge, freezer, holdingCabinet, blastChiller, coreProbe, delivery, displayCounter, ambient)
FnbService | logTemperature | response | log.recordedAt | string (date-time) | yes
FnbService | logTemperature | response | log.recordedByPrincipalId | string (uuid)
FnbService | logTemperature | response | log.valueCelsius | number | yes
FnbService | logTemperature | response | log.minCelsius | number |  | (nullable)
FnbService | logTemperature | response | log.maxCelsius | number |  | (nullable)
FnbService | logTemperature | response | log.outcome | enum (inRange, outOfRange, notTaken) | yes | notTaken is a record, not an absence.
FnbService | logTemperature | response | log.deviceReported | boolean |  | A probe reading and a person's reading are different evidence. (default False)
FnbService | logTemperature | response | log.correctiveActionId | string (uuid) |  | (nullable)
FnbService | logTemperature | response | correctiveAction | CorrectiveAction |  | What was done about a finding, and who signed it.
FnbService | logTemperature | response | correctiveAction.id | string (uuid) | yes
FnbService | logTemperature | response | correctiveAction.raisedAt | string (date-time) | yes
FnbService | logTemperature | response | correctiveAction.raisedByPrincipalId | string (uuid) |  | Who raised it, which is who may not sign it when it is critical (signCorrectiveAction). (read-only; nullable)
FnbService | logTemperature | response | correctiveAction.source | enum (temperatureExcursion, coldChainBreach, expiredStock, contamination, pestSighting, equipmentFailure, missedCheck, manual) | yes | missedCheck is raised by the server when a checkpoint goes past its checkFrequencyMinutes with no reading (audit R125 (5)).
FnbService | logTemperature | response | correctiveAction.sourceRef | string (uuid) |  | (nullable)
FnbService | logTemperature | response | correctiveAction.severity | enum (observation, minor, major, critical) |  | Set by the source when the platform opens it (decided 28 September, audit R125 (5)): an out-of-range reading or a cold-chain breach opens at major, a missed check at minor.
FnbService | logTemperature | response | correctiveAction.actionTaken | string |  | (nullable)
FnbService | logTemperature | response | correctiveAction.disposal | enum (none, discarded, reworked, quarantined, returned) |  | (nullable)
FnbService | logTemperature | response | correctiveAction.status | enum (open, actioned, signed, escalated, closed) | yes
FnbService | logTemperature | response | correctiveAction.signedByPrincipalId | string (uuid) |  | (nullable)
FnbService | logTemperature | response | correctiveAction.signedAt | string (date-time) |  | (nullable)
FnbService | logTemperature | response | correctiveAction.escalatedToPrincipalId | string (uuid) |  | A critical finding a shift cannot close. (nullable)
FnbService | logTemperature | response | correctiveAction.scopePath | string |  | The partition key (ADR-0005).
FnbService | logTemperature | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
IdentityService | login | request | username | string | yes | (max length 256)
IdentityService | login | request | credential | string | yes | Password, PIN, card token or RFID token depending on method. (max length 512)
IdentityService | login | request | method | enum (password, pin, card, rfid, sso) |  | pin is how a till is actually used. (default password)
IdentityService | login | request | workstationId | string (uuid) |  | Identifies the device.
IdentityService | login | request | deviceFingerprint | string |  | (max length 256)
IdentityService | login | response | accessToken | string | yes | JWT carrying sid, validated per request against the session registry.
IdentityService | login | response | refreshToken | string | yes
IdentityService | login | response | expiresIn | integer | yes | Seconds
IdentityService | login | response | requiresRoleSelection | boolean | yes
IdentityService | login | response | requiresMfa | boolean | yes | True when the principal holds any permission listed in PasswordPolicy.mfaRequiredForPermissions (decided 28 September, audit R135).
IdentityService | login | response | hasMfaMethod | boolean |  | Whether the principal has an active MFA method.
IdentityService | login | response | mfaMethods | array of MfaMethod |  | The principal's active methods, so the client can offer the right one for the signIn challenge.
IdentityService | login | response | mfaMethods[].id | string (uuid) | yes
IdentityService | login | response | mfaMethods[].kind | MfaKind: enum (totp, smsOtp, emailOtp, biometric, hardwareToken) | yes
IdentityService | login | response | mfaMethods[].label | string |  | (nullable)
IdentityService | login | response | mfaMethods[].maskedTarget | string |  | Partially masked destination, so a person can tell two methods apart. (nullable)
IdentityService | login | response | mfaMethods[].isActive | boolean | yes
IdentityService | login | response | mfaMethods[].isPrimary | boolean
IdentityService | login | response | mfaMethods[].enrolledAt | string (date-time) | yes
IdentityService | login | response | mfaMethods[].lastUsedAt | string (date-time) |  | (nullable)
IdentityService | login | response | availableRoles | array of RoleSummary
IdentityService | login | response | availableRoles[].id | string (uuid) | yes
IdentityService | login | response | availableRoles[].code | string | yes
IdentityService | login | response | availableRoles[].name | string | yes
IdentityService | login | response | availableRoles[].isPrimary | boolean
IdentityService | login | response | session | Session
IdentityService | login | response | session.sessionId | string (uuid) | yes
IdentityService | login | response | session.principalId | string (uuid) | yes
IdentityService | login | response | session.roleId | string (uuid) | yes
IdentityService | login | response | session.displayName | string
IdentityService | login | response | session.scope | array of ScopeRef | yes | Scope nodes this session may act within, resolved once at login from the ltree hierarchy with deny-overrides-allow.
IdentityService | login | response | session.scope[].id | string (uuid) | yes
IdentityService | login | response | session.scope[].level | ScopeLevel: enum (tenant, brand, region, venue, department, subDepartment, workstation, outlet, …) | yes | The eight organisational levels, plus subject.
IdentityService | login | response | session.scope[].path | string | yes | Materialised ltree path.
IdentityService | login | response | session.scope[].code | string |  | (nullable)
IdentityService | login | response | session.scope[].name | string |  | (nullable)
IdentityService | login | response | session.effectivePermissions | object | yes | Flattened set across all granted scopes, after deny resolution.
IdentityService | login | response | session.permissionsByScope | array of ScopedPermissions |  | Permissions effective at each granted scope path.
IdentityService | login | response | session.permissionsByScope[].scopePath | string | yes | (pattern ^[a-z0-9_]+(\.[a-z0-9_]+)*$)
IdentityService | login | response | session.permissionsByScope[].permissions | array of Permission: enum (SESSION_FORCE_LOGOUT, USER_MANAGE, ROLE_MANAGE, PERMISSION_GRANT, PERMISSION_VIEW, PERMISSION_MANAGE, PLATFORM_TENANT_VIEW, PLATFORM_TENANT_MANAGE, …) | yes
IdentityService | login | response | session.saleBoardId | string (uuid) |  | Landing surface, derived from the WORKSTATION, not the role (12 Aug 2026 §3).
IdentityService | login | response | session.workstation | WorkstationContext
IdentityService | login | response | session.workstation.id | string (uuid) | yes
IdentityService | login | response | session.workstation.code | string | yes
IdentityService | login | response | session.workstation.venueId | string (uuid) | yes
IdentityService | login | response | session.workstation.regionId | string (uuid) | yes
IdentityService | login | response | session.workstation.accessPointId | string (uuid) |  | Inherited from the workstation, never selected by the operator.
IdentityService | login | response | session.workstation.devices | array of object
IdentityService | login | response | session.workstation.currency | string |  | (pattern ^[A-Z]{3}$)
IdentityService | login | response | session.workstation.currencyScale | integer |  | (min 0; max 4)
IdentityService | login | response | session.workstation.timezone | string
IdentityService | login | response | session.workstation.cellName | string |  | The cell serving this workstation's region.
IdentityService | login | response | session.workstation.deploymentProfile | enum (terminalLocal, venueEdge, thin) |  | Whether this surface reads catalogue locally (ADR-0013).
IdentityService | login | response | session.openedAt | string (date-time)
IdentityService | login | response | session.expiresAt | string (date-time)
IdentityService | login | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
RetailService | lookupMerchandise | response | merchandiseId | string (uuid) | yes
RetailService | lookupMerchandise | response | outletId | string (uuid) |  | The outlet whose price and stock this is: the asking workstation's outlet, or outletId for a caller with none (decided 28 September, audit R215).
RetailService | lookupMerchandise | response | sku | string
RetailService | lookupMerchandise | response | name | string | yes
RetailService | lookupMerchandise | response | listPrice | Money | yes | On the wire this is three fields; in the database it is one column.
RetailService | lookupMerchandise | response | listPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | lookupMerchandise | response | listPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | lookupMerchandise | response | listPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | lookupMerchandise | response | effectivePrice | object | yes | After any live promotion.
RetailService | lookupMerchandise | response | effectivePrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | lookupMerchandise | response | effectivePrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | lookupMerchandise | response | effectivePrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | lookupMerchandise | response | appliedPromotionCode | string |  | (nullable)
RetailService | lookupMerchandise | response | onHand | number | yes
RetailService | lookupMerchandise | response | isAvailable | boolean
RetailService | lookupMerchandise | response | siblingOutlets | array of object |  | Stock elsewhere in the venue, so a colleague can be sent.
RetailService | lookupMerchandise | response | siblingOutlets[].outletId | string (uuid)
RetailService | lookupMerchandise | response | siblingOutlets[].outletName | string
RetailService | lookupMerchandise | response | siblingOutlets[].onHand | number
RetailService | lookupMerchandise | param (query) | barcode | string |  | Exact match on barcode, within the venue.
RetailService | lookupMerchandise | param (query) | sku | string |  | Exact match on sku, within the venue.
RetailService | lookupMerchandise | param (query) | includeSiblingOutlets | boolean |  | False leaves siblingOutlets empty.
RetailService | lookupMerchandise | param (query) | outletId | string (uuid) |  | The outlet to price and count at, for a caller with no workstation (audit R215).
RetailService | lookupRetailSale | response | items | array of RetailSale | yes
RetailService | lookupRetailSale | response | items[].id | string | yes
RetailService | lookupRetailSale | response | items[].receiptNumber | string | yes | Server-assigned: the venue prefix plus a sequence per venue (decided 28 September, audit R152). (read-only)
RetailService | lookupRetailSale | response | items[].orderId | string | yes | The order in the Order & Payment context.
RetailService | lookupRetailSale | response | items[].outletId | string (uuid) | yes
RetailService | lookupRetailSale | response | items[].shiftId | string |  | (nullable)
RetailService | lookupRetailSale | response | items[].subjectId | string (uuid) |  | (nullable)
RetailService | lookupRetailSale | response | items[].lines | array of object | yes
RetailService | lookupRetailSale | response | items[].lines[].lineId | string
RetailService | lookupRetailSale | response | items[].lines[].merchandiseId | string (uuid)
RetailService | lookupRetailSale | response | items[].lines[].name | string
RetailService | lookupRetailSale | response | items[].lines[].quantity | integer
RetailService | lookupRetailSale | response | items[].lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | lookupRetailSale | response | items[].lines[].discount | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | lookupRetailSale | response | items[].lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | lookupRetailSale | response | items[].lines[].serialNumbers | array of string
RetailService | lookupRetailSale | response | items[].lines[].returnedQuantity | integer
RetailService | lookupRetailSale | response | items[].lines[].isReturnable | boolean |  | False once the window has passed or the line is fully returned.
RetailService | lookupRetailSale | response | items[].lines[].notReturnableReason | string |  | (nullable)
RetailService | lookupRetailSale | response | items[].subtotal | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | lookupRetailSale | response | items[].subtotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | lookupRetailSale | response | items[].subtotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | lookupRetailSale | response | items[].subtotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | lookupRetailSale | response | items[].discountAmount | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | lookupRetailSale | response | items[].discountAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | lookupRetailSale | response | items[].discountAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | lookupRetailSale | response | items[].discountAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | lookupRetailSale | response | items[].taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
RetailService | lookupRetailSale | response | items[].taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | lookupRetailSale | response | items[].taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | lookupRetailSale | response | items[].taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | lookupRetailSale | response | items[].grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
RetailService | lookupRetailSale | response | items[].grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
RetailService | lookupRetailSale | response | items[].grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
RetailService | lookupRetailSale | response | items[].grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
RetailService | lookupRetailSale | response | items[].reprintCount | integer
RetailService | lookupRetailSale | response | items[].createdAt | string (date-time) | yes
RetailService | lookupRetailSale | response | items[].recordedAt | string (date-time)
RetailService | lookupRetailSale | response | nextCursor | string
RetailService | lookupRetailSale | response | hasMore | boolean | yes
RetailService | lookupRetailSale | response | matchedBy | enum (receiptBarcode, receiptNumber, orderNumber) | yes | The identifier used, by the precedence above (audit R215).
RetailService | lookupRetailSale | param (query) | receiptNumber | string |  | Exact match on receiptNumber.
RetailService | lookupRetailSale | param (query) | orderNumber | string |  | Exact match on the order number of the order in the Order & Payment context.
RetailService | lookupRetailSale | param (query) | receiptBarcode | string |  | Exact match on the barcode printed on the receipt.
RetailService | lookupRetailSale | param (query) | pageSize | integer
RetailService | lookupRetailSale | param (query) | cursor | string |  | Opaque cursor: the nextCursor of the previous page.
RetailService | lookupShopAndDrop | param (query) | entitlementId | string |  | Exact match on the ticket scanned at the collection point.
RetailService | lookupShopAndDrop | param (query) | dropReference | string |  | Exact match on dropReference, as printed on the slip.
RetailService | lookupShopAndDrop | param (query) | receiptNumber | string |  | Exact match on the receipt number of the sale the goods came from.
MarketingService | markMyNotificationsRead | request | ids | array of string |  | (max items 200)
MarketingService | markMyNotificationsRead | request | all | boolean |  | (default False)
MarketingService | markMyNotificationsRead | response | unreadCount | integer | yes | (min 0)
MarketingService | markMyNotificationsRead | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
FnbService | markOrderCollected | request | verifiedBy | enum (buzzer, orderNumber, name, qr, none)
FnbService | markOrderCollected | request | recordedAt | string (date-time) | yes | Device time of the collection.
FnbService | markOrderCollected | response | id | string (uuid) | yes
FnbService | markOrderCollected | response | orderNumber | string | yes
FnbService | markOrderCollected | response | outletId | string (uuid) | yes
FnbService | markOrderCollected | response | paymentTiming | object |  | The outlet's payment timing when the order was placed (CHG-CSA-010), kept as a snapshot. (read-only)
FnbService | markOrderCollected | response | sentToKitchenAt | string (date-time) |  | When the order's kitchen tickets were created. (read-only; nullable)
FnbService | markOrderCollected | response | serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery) | yes
FnbService | markOrderCollected | response | tableVisitId | string (uuid) |  | (nullable)
FnbService | markOrderCollected | response | status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) | yes | The full lifecycle from 4.6.35.
FnbService | markOrderCollected | response | lines | array of object | yes
FnbService | markOrderCollected | response | lines[].id | string (uuid) | yes
FnbService | markOrderCollected | response | lines[].menuItemId | string (uuid) | yes
FnbService | markOrderCollected | response | lines[].quantity | integer | yes | (min 1)
FnbService | markOrderCollected | response | lines[].modifierOptionIds | array of string (uuid)
FnbService | markOrderCollected | response | lines[].note | string |  | Free text to the kitchen. (max length 200)
FnbService | markOrderCollected | response | lines[].seatNumber | integer |  | Which cover ordered it. (nullable)
FnbService | markOrderCollected | response | lines[].course | integer |  | Course grouping, so the kitchen fires in sequence. (nullable)
FnbService | markOrderCollected | response | lines[].redeemEntitlementId | string |  | A meal combo redeemed at the till or by a scan (29 September, MOB-4; applied 30 September). (nullable)
FnbService | markOrderCollected | response | lines[].status | FnbOrderStatus: enum (ordered, accepted, inPreparation, ready, served, collected, delivered, cancelled, …) |  | The full lifecycle from 4.6.35.
FnbService | markOrderCollected | response | lines[].unitPrice | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | markOrderCollected | response | lines[].unitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | markOrderCollected | response | lines[].unitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | markOrderCollected | response | lines[].unitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | markOrderCollected | response | lines[].lineTotal | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | markOrderCollected | response | lines[].lineTotal.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | markOrderCollected | response | lines[].lineTotal.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | markOrderCollected | response | lines[].lineTotal.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | markOrderCollected | response | salesOrderId | string (uuid) |  | Retyped 29 September (SD-046), and format: uuid since ADR-0056 (30 September): every id is a uuid, so this joins orders.sales_order.id. (nullable)
FnbService | markOrderCollected | response | updatedAt | string (date-time) |  | Taken from their fnb.order. (nullable)
FnbService | markOrderCollected | response | grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
FnbService | markOrderCollected | response | grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | markOrderCollected | response | grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | markOrderCollected | response | grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | markOrderCollected | response | taxAmount | Money |  | On the wire this is three fields; in the database it is one column.
FnbService | markOrderCollected | response | taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
FnbService | markOrderCollected | response | taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
FnbService | markOrderCollected | response | taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
FnbService | markOrderCollected | response | kitchenTicketId | string (uuid) |  | (nullable)
FnbService | markOrderCollected | response | kitchenTickets | array of KitchenTicket |  | The kitchen tickets this order created, one per station (SD-046). (read-only)
FnbService | markOrderCollected | response | kitchenTickets[].id | string (uuid) | yes
FnbService | markOrderCollected | response | kitchenTickets[].orderId | string (uuid) | yes | The F&B order the ticket was created from on acceptance (FnbOrder.id).
FnbService | markOrderCollected | response | kitchenTickets[].orderNumber | string
FnbService | markOrderCollected | response | kitchenTickets[].outletId | string (uuid) | yes
FnbService | markOrderCollected | response | kitchenTickets[].tableLabel | string |  | (nullable)
FnbService | markOrderCollected | response | kitchenTickets[].serviceMode | ServiceMode: enum (quickService, tableService, roomService, collection, delivery)
FnbService | markOrderCollected | response | kitchenTickets[].coursing | object |  | BL-131. (nullable)
FnbService | markOrderCollected | response | kitchenTickets[].buzzerCode | string |  | BL-128. (nullable)
FnbService | markOrderCollected | response | kitchenTickets[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | markOrderCollected | response | kitchenTickets[].priority | integer |  | Higher fires sooner.
FnbService | markOrderCollected | response | kitchenTickets[].prioritisedByPrincipalId | string (uuid) |  | (nullable)
FnbService | markOrderCollected | response | kitchenTickets[].prioritiseReason | string |  | (nullable)
FnbService | markOrderCollected | response | kitchenTickets[].lines | array of object | yes
FnbService | markOrderCollected | response | kitchenTickets[].lines[].lineId | string (uuid) | yes
FnbService | markOrderCollected | response | kitchenTickets[].lines[].name | string | yes
FnbService | markOrderCollected | response | kitchenTickets[].lines[].quantity | integer | yes
FnbService | markOrderCollected | response | kitchenTickets[].lines[].modifiers | array of string
FnbService | markOrderCollected | response | kitchenTickets[].lines[].note | string |  | (nullable)
FnbService | markOrderCollected | response | kitchenTickets[].lines[].allergens | array of AllergenCode: enum (gluten, crustaceans, eggs, fish, peanuts, soybeans, milk, nuts, …)
FnbService | markOrderCollected | response | kitchenTickets[].lines[].refireOfLineId | string (uuid) |  | Set on a refire. (read-only; nullable)
FnbService | markOrderCollected | response | kitchenTickets[].lines[].refireReason | object |  | (read-only; nullable)
FnbService | markOrderCollected | response | kitchenTickets[].lines[].isChargeable | boolean |  | A refire's chargeable flag. (read-only; nullable)
FnbService | markOrderCollected | response | kitchenTickets[].lines[].course | integer |  | (nullable)
FnbService | markOrderCollected | response | kitchenTickets[].lines[].stationId | string (uuid) |  | (nullable)
FnbService | markOrderCollected | response | kitchenTickets[].lines[].status | KitchenTicketStatus: enum (received, preparing, ready, served, recalled, cancelled) | yes
FnbService | markOrderCollected | response | kitchenTickets[].createdAt | string (date-time) | yes
FnbService | markOrderCollected | response | kitchenTickets[].targetReadyAt | string (date-time) |  | (nullable)
FnbService | markOrderCollected | response | kitchenTickets[].elapsedSeconds | integer
FnbService | markOrderCollected | response | kitchenTickets[].visitId | string (uuid) |  | The table visit the ticket is for (4 October 2026, CHG-FXC-011; KIT-002): the {visitId} notifyServer takes. (read-only; nullable)
FnbService | markOrderCollected | response | estimatedReadyAt | string (date-time) |  | (nullable)
FnbService | markOrderCollected | response | createdAt | string (date-time) | yes
FnbService | markOrderCollected | response | recordedAt | string (date-time)
FnbService | markOrderCollected | response | syncedAt | string (date-time) |  | (nullable)
FnbService | markOrderCollected | param (path) | orderId | string (uuid) | yes | The F&B order (FnbOrder.id), which is what this closes — not a sales order.
FnbService | markOrderCollected | param (header) | Idempotency-Key | string (uuid) | yes | Client-generated UUIDv7.
OrderService | modifyOrder | request | id | string (uuid) | yes | Client-generated UUIDv7 of this modification, not of the order — the order is the path's orderId.
OrderService | modifyOrder | request | addLines | array of CreateOrderLine
OrderService | modifyOrder | request | addLines[].id | string (uuid) | yes | Client-generated UUIDv7 of the line.
OrderService | modifyOrder | request | addLines[].variantId | string (uuid) | yes
OrderService | modifyOrder | request | addLines[].recommendationId | string (uuid) |  | The trackingId of the ai decideRecommendations item this line came from (29 September, build, AI system design 2.2 A step 8), so a purchase is attributed to the recommendation that led to it rather t… (nullable)
OrderService | modifyOrder | request | addLines[].performanceId | string (uuid)
OrderService | modifyOrder | request | addLines[].bookedWindow | BookedWindow |  | The booked time window of an hourly product, such as a meeting room (decided 29 September, rev 3 REV3-13: meeting rooms by the hour are in scope). (nullable)
OrderService | modifyOrder | request | addLines[].bookedWindow.startsAt | string (date-time) | yes
OrderService | modifyOrder | request | addLines[].bookedWindow.endsAt | string (date-time) | yes | After startsAt, on the same venue day.
OrderService | modifyOrder | request | addLines[].inventoryHoldId | string |  | Lease the units were drawn from — a catalogue.InventoryHold.id. (nullable)
OrderService | modifyOrder | request | addLines[].seatIds | array of string (uuid) |  | Seated products only, as seating.Seat.id. (max items 50)
OrderService | modifyOrder | request | addLines[].resourceHoldId | string (uuid) |  | A resources.ResourceHold on a resource the guest picked on a venue map (decided 29 September, rev 3 REV3-15); variantId is the placed resource's price-band variant. (nullable)
OrderService | modifyOrder | request | addLines[].attributes | OrderLineAttributes |  | Open attributes of a line, kept from the cart to the order line. (nullable)
OrderService | modifyOrder | request | addLines[].attributes.transport | TransportLineAttributes |  | What a transport line is for (decided 29 September, rev 3 REV3-21). (nullable)
OrderService | modifyOrder | request | addLines[].quantity | integer | yes | (min 1)
OrderService | modifyOrder | request | addLines[].eligibilityDeclaration | array of object |  | What was declared for each guest on this line, kept as the record staff check at the gate. (nullable)
OrderService | modifyOrder | request | addLines[].eligibilityDeclaration[].ageBand | enum (infant, child, junior, adult, senior) |  | Infant under 3, child 3–12, junior 13–17, adult 18–59, senior 60+.
OrderService | modifyOrder | request | addLines[].eligibilityDeclaration[].ageYears | integer |  | (nullable)
OrderService | modifyOrder | request | addLines[].eligibilityDeclaration[].heightBandIndex | integer |  | (nullable)
OrderService | modifyOrder | request | addLines[].eligibilityDeclaration[].confidentSwimmer | boolean |  | Derived, kept for the gate check (decided 29 September, rev 3 REV3-26). (nullable)
OrderService | modifyOrder | request | addLines[].eligibilityDeclaration[].guardianSigned | boolean
OrderService | modifyOrder | request | addLines[].quotedUnitPrice | object | yes | What the client charged, from its local bundle.
OrderService | modifyOrder | request | addLines[].quotedUnitPrice.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | modifyOrder | request | addLines[].quotedUnitPrice.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | modifyOrder | request | addLines[].quotedUnitPrice.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | modifyOrder | request | addLines[].holderName | string |  | (nullable)
OrderService | modifyOrder | request | addLines[].dataMaskValues | object |  | Deliberately open.
OrderService | modifyOrder | request | removeLineIds | array of string (uuid)
OrderService | modifyOrder | request | reason | string |  | (max length 500)
OrderService | modifyOrder | request | recordedAt | string (date-time) | yes
OrderService | modifyOrder | response | order | Order | yes
OrderService | modifyOrder | response | order.id | string (uuid) | yes | The client UUIDv7 from CreateOrderRequest.id.
OrderService | modifyOrder | response | order.orderNumber | string |  | The number a guest reads and a cashier types. (read-only)
OrderService | modifyOrder | response | order.channel | object | yes | Where it came from.
OrderService | modifyOrder | response | order.channelProfileId | string (uuid) |  | The named sales channel the order came through (catalogue SalesChannelProfile.id), set by the server from the caller: a partner user's or reseller's channel, an API key's channel. (read-only; nullable)
OrderService | modifyOrder | response | order.venueId | string (uuid) | yes
OrderService | modifyOrder | response | order.scopePath | string | yes
OrderService | modifyOrder | response | order.status | OrderStatus: enum (pending, held, paid, partiallyPaid, completed, voided, refunded, partiallyRefunded, …) | yes | held is a parked sale — the cashier freed the till and the guest will return.
OrderService | modifyOrder | response | order.currency | string | yes | Resolved from the region, not stored (ADR-0018, 24 August). (pattern ^[A-Z]{3}$)
OrderService | modifyOrder | response | order.currencyScale | integer | yes | Resolved from the region, not stored (ADR-0018, 24 August). (min 0; max 4)
OrderService | modifyOrder | response | order.grossAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | modifyOrder | response | order.grossAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | modifyOrder | response | order.grossAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | modifyOrder | response | order.grossAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | modifyOrder | response | order.taxAmount | Money | yes | On the wire this is three fields; in the database it is one column.
OrderService | modifyOrder | response | order.taxAmount.amount | string | yes | Decimal string, never a float. (pattern ^-?\d+(\.\d{1,4})?$)
OrderService | modifyOrder | response | order.taxAmount.currency | string | yes | Resolved from the region, not stored on the row (ADR-0018). (pattern ^[A-Z]{3}$)
OrderService | modifyOrder | response | order.taxAmount.scale | integer | yes | Resolved from the region alongside currency. (min 0; max 4)
OrderService | modifyOrder | response | order.netAmount | Money | yes | On the wire this is three fields; in the database it is one column.