## Summary
Platform | Name | Screens | Operations called | Unagreed | Screens with no operation | What gets it to 100%
P01 | Guest Web | 49 | 186 | 0 | 0 | wireframes: 49 to verify
P02 | Guest App | 77 | 189 | 0 | 1 | 1 screens to specify; wireframes: 77 to verify
P04 | Venue POS | 30 | 144 | 0 | 0 | wireframes: 30 to verify
P05 | Guest Kiosk | 17 | 22 | 0 | 2 | 2 screens to specify; wireframes: 17 to verify
P06 | Venue Staff App | 96 | 212 | 0 | 2 | 2 screens to specify; wireframes: 96 to verify
P07 | Venue Scanner | 11 | 27 | 0 | 0 | wireframes: 11 to verify
P08 | Venue Management | 1186 | 1362 | 3 | 8 | 3 make-or-break question(s) for the client; 8 screens to specify; wireframes: 1186 to verify
P09 | TICVAI Web | 676 | 583 | 1 | 88 | 1 make-or-break question(s) for the client; 88 screens to specify; wireframes: 676 to verify
P10 | Partner Web | 51 | 151 | 0 | 0 | wireframes: 51 to verify
P11 | Accreditation Web | 8 | 6 | 0 | 1 | 1 screens to specify; wireframes: 8 to verify
P12 | Venue Support | 28 | 59 | 0 | 0 | wireframes: 28 to verify
P13 | Venue CMS | 100 | 142 | 0 | 0 | wireframes: 100 to verify
P14 | Developer | 8 | 21 | 0 | 0 | wireframes: 8 to verify
P15 | Kitchen Display | 10 | 27 | 0 | 0 | wireframes: 10 to verify
P16 | Venue Analytics | 69 | 58 | 0 | 1 | 1 screens to specify; wireframes: 69 to verify
P17 | TICVAI Sign-up | 24 | 14 | 0 | 0 | wireframes: 24 to verify

## Make or break
Id | Topic | Detail | Why only the client | Question | Screens | Answer
listBiometricConsentGuardian | access | Biometric Consent & Guardian Management | (a) | At what age must a guardian consent to a minor's Face Pass enrolment, per jurisdiction? — why: (a) biometric data protection and age-of-majority law differ by country; counsel sets the age (R205) | P08 BO-187 Biometric Consent & Guardian Management
listBiometricLifecycleRetention | access | Biometric Lifecycle, Retention & Deletion | (a) | How long may Face Pass, Face Tag and failed or abandoned capture data be retained in each region the client operates? — why: (a) biometric data protection law sets the maximum and the client's counsel must confirm it (MoM 2 Sep open item) | P08 BO-192 Biometric Lifecycle, Retention & Deletion
setBiometricLifecycleRetention | access | Save a biometric retention rule | (a) | How long may Face Pass, Face Tag and failed or abandoned capture data be retained in each region the client operates? — why: (a) biometric data protection law sets the maximum and the client's counsel must confirm it (MoM 2 Sep open item). retentionDays has no default. | P08 BO-192 Biometric Lifecycle, Retention & Deletion
listRefundDisputeResale | orders | Refunds, Disputes & Resale Exceptions | (c) | When an event is cancelled after a resale, who is refunded and how much: the resale buyer at the resale price, the original purchaser at face value, or a split, and is the seller's payout clawed back if already paid? The pack itself says this 'cannot be assumed'. A wrong default changes what customers are refunded in a way the client's commercial and finance teams would reverse (c). | P09 ADM-295 Refunds, Disputes & Resale Exceptions
setFaceTagTemporaryEnrollment | access | Save a Face Tag profile | (a) | How long may a Face Tag be kept when deletionTrigger is operationalRetentionThreshold (retentionThresholdHours)? — why: (a) biometric data protection law sets the maximum and the client's counsel must confirm it (MoM 2 Sep open item). The field has no default; every other Face Tag setting is decided.
R038 | Approved dependencies | [client to name] | (b) | A value only the client can name
R065 | Payment sandbox access | [client to name] | (b) | A value only the client can name
R065 | Payment sandbox access | [client to set] | (b) | A value only the client can name
R126 / R205 | The age below which a guest is a minor |  | (a) law
R149 (3) | How long each kind of guest document is kept |  | (a) law
R077 (b) | The facial-reader vendor, which sets the SDK and template format |  | (b) vendor
R252 | One design reviewer who signs off each wireframe batch within 3 working days |  | (b) a person only the client can name
Consumer law | A/B price tests on live customers: allowed, and with what notice? |  | (a) law, not blocking
Consumer law | Cooling-off rights after an auto-renewal charge |  | (a) law, not blocking

## Decided by us
What | Where it is recorded | Count
Audit questions, our recommendation (28 September) | docs/registers/audit-decisions.md | 77
Rev 3 prototype feedback (29 September) | docs/registers/rev3-decisions.md
Operations agreed from minutes, packs and build plan (29 September) | docs/registers/readiness-closeout.md
Design pack scope (29 September) | docs/active/design-pack-coverage.md | 40
Requirements re-traced against the current contracts (29 September) | handoff/traceability.json | 198
AI system design questions and trade-offs (29 September) | docs/architecture/ai-system-design.md, section 8 (draft, final read pending) | 16

## Our work
Design pack or platform | Verdict | Gap | New operations (estimate) | Action
AI_Configuration_Assistant_Reference.pdf | in scope, gap | 28 screens have no operation. Board 1 (guided discovery, configuration blueprint) and board 2 (builder validation) have none; board 3 (approval, execution) maps to decideProposedAction plus approvals; ADM-489 readiness maps to subscription.runGoLiveValidation | 12-18 | Draft about 12-18 operations in ai.yaml (blueprint session, draft validation, applied-draft history) and bind the 28 screens. It drafts, a person applies (ai-scope s2)
AI_Governance_Reference.pdf | in scope, gap | 39 screens unbound. No AI capability registry, risk register, decision trace (explainability) read, compliance monitor or intervention (switch-off) operation. P16 ANL-060 (AI analytics governance) belongs here too | 15-20 | Bind the about 8 existing operations; draft about 15-20 in ai.yaml; approval routing stays in approvals
Entitlement Lifecycle.pdf | in scope, gap | 0 of 20 pack screens declared. No operation anywhere names a portfolio: board 1 portfolio command centre, profile and structure, corporate/school/group portfolio, unified entitlement inventory, assignment manager, portfolio 360 | 10-14 | Draft a portfolio read model plus assignment and transfer operations, about 10-14; declare the 20 screens (about half bind to existing operations)
Event_Management_Configuration_Backend_Structure_v1.0.pdf | in scope, gap | 67 of 100 pack screens never declared (the parser missed the PAGE n convention). Residual: board 5 registration and invitations, board 9 session manifest and check-in, board 10 sponsorship | 20-35 | Re-parse the pack, declare the 67 screens, draft about 20-35 operations for invitations, manifest and check-in, and sponsorship
F&B_Backend_Structure_Module Sample Reference v1.0.pdf | covered, residual | The 60 pack screens were never reconciled one by one against the framed screens. The 20 Sep upper bound is 53 operations; our read is about 10-15, because the contract is already ahead of the screens (27 fnb operations sit on no screen) | 10-15 | Reconcile the 60 screens against the board-framed screens; draft only the residual
Retail_Backend_Structure_Module_Reference_v1.0.pdf | covered, residual | No screen cites the pack. Residual about 10-20 operations, mostly board 1 store configuration (store types, sales periods, channel set-up: reuse the outlet configuration) and board 3 omnichannel fulfilment. The 20 Sep upper bound is 60 | 10-20 | Reconcile the 60 screens with the Retail-framed screens; draft only the residual
TICVAI Finance Backend Structure Reference v1.0.pdf | in scope, gap | 2 of 70 pack screens declared. No credit memo operation (the RFP names it and no screen carries it); the board 7 finance controls are thin | 8-15 | Re-parse the pack, declare the roughly 30 screens that are not already payments or shift screens, draft about 8-15 operations (credit memo, controls)
TICVAI_Inventory_and_Procurement_Backend_Structure_Sample v1.0.pdf | covered, residual | Missing: three-way match (PO, GRN, invoice) with a supplier invoice, and spend analysis (MoM 18 Aug). Out: granular warehouse statuses (MoM 18 Aug decided against), dock appointments (not in the matrix); boards 5 and 7 AI optimisation deferred (MoM 14 Aug) | 5-8 | Draft about 5-8 operations; map the 70 pack screens onto the 38 existing ones
TICVAI_Ticket_Types_Product_Configuration_Scope_of_Work_v1.0.pdf | covered, residual | 0 of 120 pack screens declared. The 20 Sep estimate of 120 operations assumed a ticket type is not a product and no longer stands. Residual about 5-15 (validity exceptions; the AI draft from unstructured input in MoM 25 Aug goes to ai.generateConfiguration) | 5-15 | Map the 12 boards to existing catalogue screens; draft the residual only
Unified_BI_Reporting_and_AI_Analytics_Platform_Reference.pdf | covered, residual | Boards 5-8 (40 screens) are a domain filter on P16, not screens (bi-domain-boards-9-september.md), and the filter is not yet on 59 of the 60 screens. ANL-060 moves to AI Governance | 0 | Add a domain query parameter to the reporting reads (no new operations) and put the filter on the P16 screens
Virtual_Queue.pdf | in scope, gap | None of the 36 pack sections declared. Missing: per-ride capacity split between express, virtual and walk-in (MoM 7 Sep s4.12), express queue rules, ride-by-day enablement and operating schedule, joining without a phone at water parks (MoM 7 Sep s4.14: kiosk or wristband). Board 4 AI prediction deferred | 8-12 | Draft about 8-12 operations and declare about 25 screens (boards 1-3)
Requirements | not covered or partly covered | 67 requirements: 5 not covered, 62 partly covered. Each is listed in TICVAI - Build Readiness.xlsx (sheet Missing, and its application's sheet) |  | Each has a contract-backlog entry naming the operation that would serve it
P02 | screen names no operation | GST-043 Arabic / RTL Experience |  | Specify from its pack
P05 | screen names no operation | KSK-001 Attract Loop |  | Specify from its pack
P05 | screen names no operation | KSK-014 Out of service |  | Specify from its pack
P06 | screen names no operation | EMP-044 Accessibility |  | Specify from its pack
P06 | screen names no operation | EMP-045 Arabic / RTL |  | Specify from its pack
P08 | screen names no operation | BO-919 AI Event Resource Forecasting |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P08 | screen names no operation | BO-925 AI Staff Recommendation & Workforce Matching |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P08 | screen names no operation | BO-926 Resource Demand Forecasting |  | Specify from its pack
P08 | screen names no operation | BO-927 AI Staffing Requirement Forecast |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P08 | screen names no operation | BO-928 AI Conflict Resolution Assistant |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P08 | screen names no operation | BO-929 Automatic Schedule Optimization |  | Specify from its pack
P08 | screen names no operation | BO-931 Operational Scenario Simulator & Digital Twin |  | Specify from its pack
P08 | screen names no operation | BO-932 Conversational AI Resource Copilot |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-469 AI Configuration Home & Start |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-470 Setup Type & Business Intent Discovery |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-471 Venue & Business Model Discovery |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-472 Guided Question & Answer Workspace |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-473 Product & Admission Model Discovery |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-474 Operational Requirement Discovery |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-475 Commercial Requirement Discovery |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-476 Required, Recommended & Optional Decisions |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-477 Missing Information & Clarification Center |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-478 Configuration Blueprint & Dependency Map |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-479 AI Configuration Build Command Center |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-480 Venue & Organization Configuration |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-481 Product Configuration Assistant |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-482 Schedule, Capacity & Availability Configuration |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-484 Promotion, Bundle & Upsell Configuration |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-485 Seating, Access & Operational Configuration |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-486 Channel, Media & Fulfillment Configuration |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-487 Cross-Module Conflict & Dependency Validation |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-488 Configuration Preview & Impact Analysis |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-489 AI Configuration Readiness Center |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-490 Configuration Validation Results |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-491 AI Recommendations & Best-Practice Review |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-493 AI Configuration Execution Center |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-494 Execution Progress & Dependency Monitor |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-495 Configuration Results & Object Mapping |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-496 Configuration Change & Modification Assistant |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-497 Configuration History, Versions & Rollback |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-498 AI Configuration Audit & Governance |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-499 Forecasting Command Center |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-500 Forecast Configuration & Forecasting Strategy |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-501 Forecast Data & Signal Configuration |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-502 Attendance & Visitation Forecast |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-503 Ticket, Product & Timeslot Demand Forecast |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-504 Channel & Booking Pace Forecast |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-505 Revenue & Commercial Forecast |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-506 Forecast Drivers, Confidence & Explainability |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-507 Forecast Scenario & What-If Simulator |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-508 Forecast Accuracy, Review & Publication Center |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-509 Operational Forecasting Command Center |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-510 Capacity & Occupancy Forecast |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-511 Attraction Utilization & Queue Forecast |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-512 Entry, Access & Guest Flow Forecast |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-513 Workforce Demand & Staffing Forecast |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-514 POS, Kiosk & Frontline Service Forecast |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-515 F&B, Retail & Inventory Demand Forecast |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-516 Resource, Equipment & Facility Requirement Forecast |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-517 Operational Scenario & Readiness Simulator |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-518 Operational Forecast Review, Recommendations & Handover |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-519 AI Governance Command Center |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-520 AI Capability Registry & Ownership |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-521 AI Risk Classification & Assessment |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-522 AI Autonomy Level Configuration |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-523 AI Action & Permission Policy Builder |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-524 AI Data Access & Usage Policy |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-525 Environment, Tenant & Scope Governance |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-526 AI Policy Conflict, Exception & Override Management |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-527 AI Policy Testing & Governance Simulation |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-528 AI Governance Policy Publication & Effective Policy Map |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-529 AI Human Oversight Command Center |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-530 AI Approval Requirement & Routing Configuration |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-531 AI Approval Review Workspace |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-532 Conditional Approval & Approval Conditions |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-533 Human Review, Challenge & AI Clarification Workspace |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-534 Escalation, Delegation & Approval SLA Management |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-535 Live AI Execution Oversight & Human Intervention |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-536 Human Override & Manual Control Center |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-537 Approval & Intervention History / Decision Timeline |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-538 Human Oversight Workflow Simulator & Readiness Center |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-539 AI Explainability & Audit Command Center |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-540 AI Decision Explorer & Search |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-541 AI Decision Explanation Workspace |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-542 Data, Feature & Evidence Provenance |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-543 Candidate, Rule & Decision Path Trace |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-544 Model, Provider & AI Runtime Trace |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-545 Governance, Approval & Human Decision Trace |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-546 Execution & Business Outcome Trace |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-547 AI Audit Record & Evidence Package |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-548 AI Trace Investigation & Replay Simulator |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-550 AI Risk Register & Risk Exposure Management |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-551 AI Governance Control Library & Control Effectiveness |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-552 AI Policy Compliance & Violation Monitoring |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-553 AI Data, Privacy & Usage Compliance Monitoring |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-554 AI Quality, Behavior & Governance Drift Monitoring |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-555 AI Governance Alert & Detection Center |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-556 AI Incident & Remediation Management |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-557 AI Compliance, Assurance & Governance Reporting |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-558 AI Governance Review, Action Plan & Continuous Improvement |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P09 | screen names no operation | ADM-618 Refund Simulator, Risk Analysis & AI Advisor\t126 |  | Waits on the AI operations in ai.yaml (design decided 29 September)
P11 | screen names no operation | ACC-001 Landing / Programme Overview |  | Specify from its pack
P16 | screen names no operation | ANL-060 AI Analytics Governance & Model Control |  | Waits on the AI operations in ai.yaml (design decided 29 September)

## Wireframes
Platform | Name | Screens | Frame status now | Question | Answer
P01 | Guest Web | 49 | review 46, notStarted 3 | Who verifies this platform's frames, and by when? Frames arrive by batch; each is signed off within 3 working days (audit R252).
P02 | Guest App | 77 | notStarted 77 | Who verifies this platform's frames, and by when? Frames arrive by batch; each is signed off within 3 working days (audit R252).
P04 | Venue POS | 30 | notStarted 30 | Who verifies this platform's frames, and by when? Frames arrive by batch; each is signed off within 3 working days (audit R252).
P05 | Guest Kiosk | 17 | notStarted 17 | Who verifies this platform's frames, and by when? Frames arrive by batch; each is signed off within 3 working days (audit R252).
P06 | Venue Staff App | 96 | notStarted 96 | Who verifies this platform's frames, and by when? Frames arrive by batch; each is signed off within 3 working days (audit R252).
P07 | Venue Scanner | 11 | notStarted 11 | Who verifies this platform's frames, and by when? Frames arrive by batch; each is signed off within 3 working days (audit R252).
P08 | Venue Management | 1186 | notStarted 1186 | Who verifies this platform's frames, and by when? Frames arrive by batch; each is signed off within 3 working days (audit R252).
P09 | TICVAI Web | 676 | notStarted 676 | Who verifies this platform's frames, and by when? Frames arrive by batch; each is signed off within 3 working days (audit R252).
P10 | Partner Web | 51 | notStarted 51 | Who verifies this platform's frames, and by when? Frames arrive by batch; each is signed off within 3 working days (audit R252).
P11 | Accreditation Web | 8 | notStarted 8 | Who verifies this platform's frames, and by when? Frames arrive by batch; each is signed off within 3 working days (audit R252).
P12 | Venue Support | 28 | notStarted 28 | Who verifies this platform's frames, and by when? Frames arrive by batch; each is signed off within 3 working days (audit R252).
P13 | Venue CMS | 100 | notStarted 100 | Who verifies this platform's frames, and by when? Frames arrive by batch; each is signed off within 3 working days (audit R252).
P14 | Developer | 8 | notStarted 8 | Who verifies this platform's frames, and by when? Frames arrive by batch; each is signed off within 3 working days (audit R252).
P15 | Kitchen Display | 10 | notStarted 10 | Who verifies this platform's frames, and by when? Frames arrive by batch; each is signed off within 3 working days (audit R252).
P16 | Venue Analytics | 69 | notStarted 69 | Who verifies this platform's frames, and by when? Frames arrive by batch; each is signed off within 3 working days (audit R252).
P17 | TICVAI Sign-up | 24 | notStarted 24 | Who verifies this platform's frames, and by when? Frames arrive by batch; each is signed off within 3 working days (audit R252).