## 1. Product Overview
TAIS Platform — Product Planning & Delivery Document
Tourism & Attraction Intelligence System · Multi-tenant venue operating platform · Generated from requirement matrix (3,332 line-items)
PRODUCT SUMMARY
TAIS is a multi-tenant, cloud-agnostic operating platform for large-scale entertainment & attraction venues (theme parks, water parks, arenas, museums, resorts). It unifies ticketing, sales across all channels, gate access, payments & wallet, F&B and retail operations, inventory, CRM/loyalty, memberships, events & reserved seating, promotions, guest & staff mobile apps, operational intelligence/AI, device fleet management, maintenance, and a governed integration & API layer — supporting English/Arabic (RTL), offline-first POS and gate validation, and AI-augmented operations with human-led governance.
BUSINESS GOALS
1. Run 7–10 venues on one multi-tenant platform with per-tenant isolation and configuration.
2. Protect and grow revenue across every sales channel with one cart, pricing and wallet backbone.
3. Deliver fast, fraud-resistant, offline-capable gate access at scale.
4. Increase guest lifetime value via unified Guest-360, loyalty, memberships and personalised offers.
5. Improve operational efficiency through device management, maintenance, inventory and (phased) AI/forecasting.
6. Meet UAE compliance (PDPL, PCI-DSS) and tourism-authority integration (UAE Pass, DET, DCT, Al Hosn).
USER PERSONAS
• Guest — buys tickets online/app/kiosk, enters via QR/RFID/face, pays with wallet, uses F&B/retail.
• Cashier / Gate Operator — sells and validates at POS/turnstile/handheld, often offline.
• Venue Operations Manager — monitors live attendance, capacity, devices, incidents via command centre.
• Commercial / Revenue Manager — configures products, pricing, promotions, bundles, B2B partners.
• B2B Partner / Reseller / OTA — books inventory via portal/API under credit and commission terms.
• Marketing / CRM Manager — runs segmentation, campaigns, loyalty, guest engagement.
• Finance / Accounting — reconciliation, tax, revenue recognition, gift-card liability.
• Platform / Tenant Administrator — onboarding, RBAC/ABAC, licensing, configuration.
• Developer / Integrator — consumes managed APIs and the developer portal.
HIGH-LEVEL ARCHITECTURE
Domain-driven, API-first, cloud-agnostic microservices on a multi-tenant core. Offline-first thick clients for POS and gate validation with local cache + sync. Unified payment/wallet layer (PCI-scoped). Central data platform feeding reporting and (phased) ML/AI services with human-in-the-loop governance. Eventing/integration bus to third parties (gateways, OTA, ERP, gov authorities, telephony, hardware). Observability, IaC and CI/CD across all services. Postgres-aligned data stack.
MAJOR WORKFLOWS
• Purchase: browse → cart (cross-channel) → price/tax/promo → pay (gateway/wallet) → issue media (QR/RFID/wallet pass).
• Admission: present media → validate (online/offline crypto) → access decision → attendance/entitlement update.
• F&B/Retail: order (POS/kiosk/QR/app) → kitchen/inventory → pay → fulfil → reconcile.
• Membership: enrol → recurring billing → renew/dunning → benefits & entitlements at gate/POS.
• B2B: onboard partner → allocate quota/credit → sell via portal/API/channel-manager → invoice/settle.
• Operations: monitor devices/attendance → maintenance/work orders → reporting → (phased) forecasting & recommendations.
HOW TO USE THIS WORKBOOK
Sheet 2 Epic Register (23 epics, objectives & risks) · Sheet 3 Feature Register (444 features, full attributes) · Sheet 4 Task Register (2,100+ tasks) · Sheet 5 Milestones · Sheet 6 Roadmap · Sheet 7 Dependency Matrix · Sheet 8 Missing/Recommended Components · Sheet 9 Jira/ADO/ClickUp import. Effort is a gross order-of-magnitude estimate assuming fully-custom build; expect material reduction after Out-of-the-box / Configurable marking and de-duplication during Discovery.

## 2. Epic Register
Epic | Platform(s) | Business Objective | Modules | Features | Reqs | Effort (pd) | Priority | Milestone(s) | Key Risk
E01 Ticketing & Product Catalogue | Mobile, POS, Server Side | Single source of truth for every sellable product; reduce SKU duplication and time-to-launch for new tickets/passes. | 28 | 28 | 295 | 572 | P1 - Must | M2, M4 | Scope creep from ~15 entitlement types and operator-specific ticket variants (camp, tunnel sessions, donations).
E02 Sales Channels & Checkout | Cross, POS, Server Side | Maximise conversion and reach across every channel (web, B2B, kiosk, POS, call-centre) with one cart and pricing engine. | 22 | 22 | 115 | 275 | P1 - Must | M2, M4 | Channel sprawl (web/B2B/kiosk/POS/call-centre) each with bespoke rules; cart consistency across channels is hard.
E03 Admission & Access Control | Cross, Mobile, POS, Server Side | Fast, fraud-resistant, offline-capable entry that protects revenue and guest flow at the gate. | 40 | 40 | 259 | 511 | P1 - Must | M2, M4 | Biometric/facial recognition with automated gender gating raises PDPL/ethics and accuracy/liability risk; offline crypto validation is complex.
E04 Payments, Wallet & Financial | Cross, Mobile, POS, Server Side | Secure, PCI-compliant money movement; one wallet and reconciliation backbone across all channels. | 54 | 54 | 475 | 976 | P1 - Must | M2, M4 | PCI-DSS scope, multi-gateway routing, reconciliation accuracy and gift-card breakage accounting; financial-grade correctness required.
E05 F&B Operations & POS | POS | Efficient F&B service with kitchen integration, recipe costing and table/QR ordering. | 14 | 14 | 251 | 497 | P2 - Should | M3, M4 | Deep F&B/kitchen/recipe scope rivals a standalone F&B product; hardware (KDS, printers) dependency.
E06 Retail Operations & POS | POS | Unified retail selling and stock visibility across stores, kiosks and online. | 10 | 10 | 78 | 165 | P2 - Should | M3, M4 | Real-time multi-store inventory consistency; overlaps heavily with E07.
E07 Inventory & Procurement | Mobile, POS, Server Side | Accurate stock and procurement to cut shrinkage and stockouts across venues. | 28 | 28 | 176 | 424 | P2 - Should | M3, M4 | Procurement + costing (FIFO/LIFO) is finance-sensitive and duplicated across F&B and retail.
E08 CRM, Marketing & Loyalty | Mobile, Server Side | Grow guest lifetime value through a unified profile, segmentation and loyalty. | 22 | 22 | 163 | 436 | P3 - Could | M3, M4 | Guest-360 depends on clean identity resolution across channels; data quality risk.
E09 Membership & Subscriptions | Mobile, POS, Server Side | Recurring revenue via memberships/annual passes with automated billing and retention. | 40 | 40 | 164 | 449 | P2 - Should | M3, M4 | Recurring billing, dunning and pro-rata correctness; tax interaction.
E10 Events, Seating & Venue Mapping | Cross, Mobile, POS, Server Side | Sell reserved-seat and timed experiences with live capacity and rich seat maps. | 52 | 52 | 250 | 625 | P2 - Should | M2, M4 | Reserved-seating concurrency (no double-booking) and AI seat-map-from-CAD are high-complexity.
E11 Bundles, Promotions & Pricing | Mobile, POS, Server Side | Lift average order value through bundles, promotions and demand-based pricing. | 48 | 48 | 349 | 896 | P3 - Could | M3, M4 | Promotion conflict/stacking resolution and dynamic pricing depend on data maturity (Phase 2+).
E12 Guest Mobile Experience | Mobile | A branded, self-service guest app that carries tickets, wallet and personalised offers. | 12 | 12 | 93 | 186 | P2 - Should | M3, M4 | App-store cycles, device fragmentation, offline sync; client expects rich Phase-1 app.
E13 Employee Mobile & Workforce | Mobile | Empower frontline staff with mobile operations, scheduling and an AI assistant. | 5 | 5 | 17 | 55 | P3 - Could | M3, M4 | Smallest epic but AI voice assistant adds NLP dependency.
E14 Intelligence, Reporting & AI | Server Side | Turn operational data into forecasting, recommendations and governed AI decisions. | 19 | 19 | 313 | 592 | P3 - Could | M3, M4 | AI assumed real-time/Phase-1 in matrix vs our ML-when-data-ready position — the central phasing conflict; needs cold-start strategy.
E15 Device & Peripheral Management | Cross, Server Side | Centrally manage the device fleet (POS, kiosks, gates, peripherals) and firmware. | 8 | 8 | 39 | 95 | P3 - Could | M4 | Firmware OTA across heterogeneous third-party hardware; vendor SDK availability.
E16 Maintenance, Safety & Asset Mgmt | Server Side | Keep assets safe and available through preventive maintenance and work orders. | 4 | 4 | 22 | 39 | P3 - Could | M3 | Full CMVS scope was a single line in our proposal — under-scoped if taken literally.
E17 Identity, Security & Access Policy | Cross, Server Side | Enforce identity, least-privilege access and security across the multi-tenant platform. | 6 | 6 | 14 | 82 | P1 - Must | M1, M5 | ABAC policy engine depth (policy builder/testing/anomaly) is larger than typical RBAC; security audit exposure.
E18 Governance, Approval & Accreditation | Server Side | Govern change through approval workflows, accreditation and full auditability. | 4 | 4 | 59 | 109 | P2 - Should | M3 | Approval workflows touch every module; engine must be generic and configurable.
E19 Developer Platform & API Mgmt | Cross | Expose the platform safely to partners and internal teams via a managed API layer. | 5 | 5 | 19 | 72 | P3 - Could | M1, M3, M5 | Partner API security, rate limiting and versioning; governance overhead.
E20 Tenant, Subscription & Licensing | Server Side | Operate as a true multi-tenant SaaS with self-service onboarding and licensing. | 5 | 5 | 29 | 49 | P2 - Should | M3 | Self-service onboarding + module marketplace is a SaaS layer beyond our license-mgmt baseline.
E21 Digital Asset Management | Server Side | Manage brand and media assets centrally with versioning and rights control. | 1 | 1 | 15 | 33 | P3 - Could | M4 | Smallest scope; risk is integration with every consuming module.
E22 Integrations & Ecosystem | POS, Server Side | Connect the platform to payment, tourism-authority, ERP, OTA and hardware ecosystems. | 3 | 3 | 35 | 84 | P3 - Could | M1, M4 | Third-party dependency risk: gateway certs, gov-authority approvals (UAE Pass/DET/DCT/Al Hosn), hardware vendor lead times.
E23 Platform Foundations & NFR | Cross, Server Side | A scalable, observable, secure and recoverable foundation meeting all NFRs. | 14 | 14 | 102 | 330 | P1 - Must | M1, M5, M6 | Uptime (99.9% proposal vs 99.5% SLA), RPO/RTO, performance SLOs must be pinned; DR scope (62 items) under-reflected in contracts.
TOTAL |  |  | 444 | 444 | 3332 | 7552

## 3. Feature Register
Feature ID | Platform | Epic | Module | Feature | Description | Dependencies | Priority | Complexity | Effort (pd) | Milestone | Phase | Source Req IDs
FEAT-001 | Server Side / Backend | E01 Ticketing & Product Catalogue | Resource Management | Resource Management | Covers 63 matrix requirement(s). The system should allow management of all types of resources: - Areas with limited capacity (e.g. Meeting rooms, Cabanas, etc.) - Staff (e.g. Ski School Instructors, etc.) - Objects (e.g. Strollers, T… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 110 | M4 - Integrations | Phase 4 - Integration | 1.2.1; 1.2.2; 1.2.5; 1.2.7; 1.2.9; 1.2.10; 1.2.11; 1.2.12 … (+55 more)
FEAT-002 | Server Side / Backend | E01 Ticketing & Product Catalogue | Ticket Types | Ticket Types | Covers 61 matrix requirement(s). The system should be able to sell open-dated tickets for attractions. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 107 | M4 - Integrations | Phase 4 - Integration | 1.1.1; 1.1.2; 1.1.7; 1.1.8; 1.1.11; 1.1.13; 1.1.14; 1.1.18 … (+53 more)
FEAT-003 | Server Side / Backend | E01 Ticketing & Product Catalogue | Accounting | Accounting | Covers 34 matrix requirement(s). The system should validate that required A/R account fields are populated with correct length and format based on the requirements provided by ERP. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | High | 63 | M2 - Core Platform | Phase 3 - Development | 5.7.5; 5.7.20; 5.7.25; 5.7.27; 5.7.28; 5.7.32; 5.7.33; 5.7.34 … (+26 more)
FEAT-004 | Server Side / Backend | E01 Ticketing & Product Catalogue | Virtual Queue | Virtual Queue | Covers 18 matrix requirement(s). Multiple Queue Types: First-come-first-serve, priority/VIP, group queues. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 38 | M4 - Integrations | Phase 4 - Integration | 5.6.1; 5.6.2; 5.6.3; 5.6.7; 5.6.8; 5.6.2; 5.6.3; 5.6.6 … (+10 more)
FEAT-005 | Server Side / Backend | E01 Ticketing & Product Catalogue | Profile Management | Profile Management | Covers 15 matrix requirement(s). The system should allow creation of guest accounts. Mandatory and optional details needed for a guest account must be configurable by the System Admin user. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 19 | M2 - Core Platform | Phase 3 - Development | 5.3.1; 5.3.4; 5.3.5; 5.3.6; 5.3.7; 5.3.8; 5.3.9; 5.3.11 … (+7 more)
FEAT-006 | Mobile App | E01 Ticketing & Product Catalogue | Authentication And Login | Authentication And Login | Covers 12 matrix requirement(s). Ticket Purchase - System shall support ticket purchases. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Ticketing & Product Catalogue | P1 - Must | Medium | 16 | M2 - Core Platform | Phase 3 - Development | 19.2.10; 19.2.11; 19.2.12; 19.2.13; 19.2.14; 19.2.15; 19.2.16; 19.2.17 … (+4 more)
FEAT-007 | Server Side / Backend | E01 Ticketing & Product Catalogue | Product Lifecycle | Product Lifecycle | Covers 10 matrix requirement(s). The system should allow configuration of workflows to manage the creation of new tickets and products. The workflow should involve setup of different status values (e.g. disabled, approval pending, et… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 14 | M2 - Core Platform | Phase 3 - Development | 1.4.1; 1.4.2; 1.4.3; 1.4.6; 1.4.10; 1.4.12; 1.4.14; 1.4.17 … (+2 more)
FEAT-008 | Server Side / Backend | E01 Ticketing & Product Catalogue | Ticket Resale Marketplace | Ticket Resale Marketplace | Covers 10 matrix requirement(s). System shall support a configurable ticket resale marketplace allowing eligible ticket holders to list tickets for resale through web, mobile application, partner channels, or marketplace portals. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | High | 25 | M2 - Core Platform | Phase 3 - Development | 1.6.1; 1.6.4; 1.6.6; 1.6.7; 1.6.8; 1.6.10; 1.6.13; 1.6.14 … (+2 more)
FEAT-009 | Server Side / Backend | E01 Ticketing & Product Catalogue | Game And Ride Payment And Redemption | Game And Ride Payment And Redemption | Covers 9 matrix requirement(s). The system should have ability to define multiple types of readers (minimum three). The properties of the readers should be configurable: - type of credit accepted at a reader - amount of credit requi… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 13 | M2 - Core Platform | Phase 3 - Development | 10.2.6; 10.2.8; 10.2.11; 10.2.12; 10.2.14; 10.2.18; 10.2.19; 10.2.20 … (+1 more)
FEAT-010 | Server Side / Backend | E01 Ticketing & Product Catalogue | Digital Waiver Management | Digital Waiver Management | Covers 8 matrix requirement(s). To provide ability that allows Guest to fill in the form at the desk using a tablet. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 12 | M2 - Core Platform | Phase 3 - Development | 2.15.1; 2.15.2; 2.15.3; 2.15.6; 2.15.9; 2.15.13; 2.15.15; 2.15.16
FEAT-011 | Server Side / Backend | E01 Ticketing & Product Catalogue | Ticket Media | Ticket Media | Covers 8 matrix requirement(s). Waiver-Ticket Linkage | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 12 | M2 - Core Platform | Phase 3 - Development | 2.16.1; 2.16.3; 2.16.4; 2.16.6; 2.16.7; 2.16.10; 2.16.12; 2.16.15
FEAT-012 | Server Side / Backend | E01 Ticketing & Product Catalogue | Portfolio And Entitlement Management | Portfolio And Entitlement Management | Covers 7 matrix requirement(s). Support temporary and permanent portfolio sharing while maintaining ownership controls. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | High | 20 | M2 - Core Platform | Phase 3 - Development | 5.5.13; 5.5.18; 5.5.19; 5.5.20; 5.5.21; 5.5.28; 5.5.29
FEAT-013 | Server Side / Backend | E01 Ticketing & Product Catalogue | Digital Waivers And Signature Management | Digital Waivers And Signature Management | Covers 7 matrix requirement(s). Waiver Template Builder System shall allow administrators to create and manage waiver templates, liability releases, consent forms, parental consent forms, medical declarations, activity agreements, a… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 11 | M2 - Core Platform | Phase 3 - Development | 22.12.1; 22.12.7; 22.12.15; 22.12.17; 22.12.18; 22.12.19; 22.12.20
FEAT-014 | Server Side / Backend | E01 Ticketing & Product Catalogue | Fraud Detection | Fraud Detection | Covers 6 matrix requirement(s). System shall detect duplicate ticket usage. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 10 | M2 - Core Platform | Phase 3 - Development | 8.3.24; 8.3.25; 8.3.27; 8.3.28; 8.3.29; 8.3.30
FEAT-015 | Server Side / Backend | E01 Ticketing & Product Catalogue | Ticket Upgrades | Ticket Upgrades | Covers 5 matrix requirement(s). The system should guarantee the integrity of all pre-existing revenue by ensuring that when an amount is amended, the value of prior sales is not modified. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 9 | M2 - Core Platform | Phase 3 - Development | 2.9.7; 2.11.7; 2.11.8; 2.11.9; 2.11.10
FEAT-016 | POS App | E01 Ticketing & Product Catalogue | Cash Handling | Cash Handling | Covers 5 matrix requirement(s). The system should allow allocation of a deposit box for each cashier. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Ticketing & Product Catalogue | P1 - Must | Medium | 9 | M2 - Core Platform | Phase 3 - Development | 5.8.1; 5.8.4; 5.8.6; 5.8.7; 5.8.8
FEAT-017 | Server Side / Backend | E01 Ticketing & Product Catalogue | Payment Methods | Payment Methods | Covers 2 matrix requirement(s). The system should be able to have a cover level widget on the home screen of the table management - to understand the available cover vs. engaged covers. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 7 | M2 - Core Platform | Phase 3 - Development | 5.1.3; 5.1.7
FEAT-018 | Server Side / Backend | E01 Ticketing & Product Catalogue | Portfolio Management | Portfolio Management | Covers 2 matrix requirement(s). The system should support a ticketing data model which allows a guest to purchase and manage multiple tickets (portfolio of tickets) under their account. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 7 | M2 - Core Platform | Phase 3 - Development | 5.5.1; 5.5.2
FEAT-019 | Server Side / Backend | E01 Ticketing & Product Catalogue | Receipt | Receipt | Covers 2 matrix requirement(s). The system should provide a simple way to print receipts for guests depending on their purchases and their consumptions (i.e. pay‐per‐use). | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 7 | M2 - Core Platform | Phase 3 - Development | 5.10.1; 5.10.2
FEAT-020 | Server Side / Backend | E01 Ticketing & Product Catalogue | Ai Engine | Ai Engine | Covers 2 matrix requirement(s). System shall support AI-powered ticketing assistance. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 12 | M4 - Integrations | Phase 4 - Integration | 8.4.19; 8.4.38
FEAT-021 | Server Side / Backend | E01 Ticketing & Product Catalogue | Guest Profiles And Data Management | Guest Profiles And Data Management | Covers 2 matrix requirement(s). Consent Management Guest profiles shall store marketing consents, privacy preferences, opt-ins, opt-outs, waiver acknowledgements, and consent audit trails. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 7 | M2 - Core Platform | Phase 3 - Development | 22.2.18; 22.2.19
FEAT-022 | Server Side / Backend | E01 Ticketing & Product Catalogue | Loyalty | Loyalty | Covers 1 matrix requirement(s). The system should be able to integrate with a loyalty point system which would provide the guest with a list of loyalty points according to the purchase value/purchased tickets/purchased services and … | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Low | 2 | M2 - Core Platform | Phase 3 - Development | 5.4.3
FEAT-023 | Server Side / Backend | E01 Ticketing & Product Catalogue | Ai Configuration Assistant | Ai Configuration Assistant | Covers 1 matrix requirement(s). It is possible to manage Invitations or complimentary Ticketing PLUs for which, no payment is expected. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 6 | M2 - Core Platform | Phase 3 - Development | 8.1.3
FEAT-024 | Server Side / Backend | E01 Ticketing & Product Catalogue | Recommendation Engine | Recommendation Engine | Covers 1 matrix requirement(s). System shall provide personalized ticket recommendations. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 11 | M4 - Integrations | Phase 4 - Integration | 8.6.1
FEAT-025 | Server Side / Backend | E01 Ticketing & Product Catalogue | Bi And Reporting | Bi And Reporting | Covers 1 matrix requirement(s). System shall provide ticketing dashboards. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Low | 2 | M2 - Core Platform | Phase 3 - Development | 8.7.6
FEAT-026 | Server Side / Backend | E01 Ticketing & Product Catalogue | Reporting And Dashboards | Reporting And Dashboards | Covers 1 matrix requirement(s). Expiration Management System shall support temporary and permanent accreditation validity periods. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 6 | M2 - Core Platform | Phase 3 - Development | 12.1.6
FEAT-027 | Server Side / Backend | E01 Ticketing & Product Catalogue | Device Integrations | Device Integrations | Covers 1 matrix requirement(s). Printer Integration - System shall support receipt and ticket printer integration. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | High | 11 | M2 - Core Platform | Phase 3 - Development | 16.8.42
FEAT-028 | Server Side / Backend | E01 Ticketing & Product Catalogue | Module Marketplace And Management | Module Marketplace And Management | Covers 1 matrix requirement(s). Marketplace Catalog - System shall provide a marketplace of available modules. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 6 | M2 - Core Platform | Phase 3 - Development | 20.4.1
FEAT-029 | Server Side / Backend | E02 Sales Channels & Checkout | Call Center Sales | Call Center Sales | Covers 36 matrix requirement(s). It should have the ability to have one API connecting the system to the external B2B website | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 67 | M4 - Integrations | Phase 4 - Integration | 2.6.5; 2.6.6; 2.6.7; 2.6.8; 2.6.14; 2.6.16; 2.6.19; 2.6.20 … (+28 more)
FEAT-030 | Server Side / Backend | E02 Sales Channels & Checkout | Sales Channels | Sales Channels | Covers 15 matrix requirement(s). The system should allow for any ticket type to be removed from sale without suspending that ticket type from use (i.e. Tickets that were already sold to guests should remain valid). | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | High | 33 | M2 - Core Platform | Phase 3 - Development | 1.5.1; 1.5.2; 1.5.4; 2.1.1; 2.1.2; 2.1.4; 2.1.5; 2.1.6 … (+7 more)
FEAT-031 | Server Side / Backend | E02 Sales Channels & Checkout | Work Order Management | Work Order Management | Covers 15 matrix requirement(s). Work Order Creation - System shall support work order creation. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 19 | M2 - Core Platform | Phase 3 - Development | 17.4.1; 17.4.2; 17.4.3; 17.4.4; 17.4.5; 17.4.6; 17.4.7; 17.4.8 … (+7 more)
FEAT-032 | Server Side / Backend | E02 Sales Channels & Checkout | Order Management | Order Management | Covers 10 matrix requirement(s). The system should support configuration of required access level to allow refund, exchange and/or void actions. At minimum, the system should provide: - Ability to enable/disable supervisor access req… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 14 | M2 - Core Platform | Phase 3 - Development | 2.12.4; 2.12.7; 2.12.10; 2.12.22; 2.12.23; 2.12.25; 2.12.26; 2.12.29 … (+2 more)
FEAT-033 | Cross Platform | E02 Sales Channels & Checkout | Usage And Quota Monitoring | Usage And Quota Monitoring | Covers 7 matrix requirement(s). User Usage Monitoring - System shall monitor active user consumption. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 11 | M2 - Core Platform | Phase 3 - Development | 20.6.1; 20.6.2; 20.6.3; 20.6.4; 20.6.5; 20.6.7; 20.6.8
FEAT-034 | Server Side / Backend | E02 Sales Channels & Checkout | Ticket Upgrades | Ticket Upgrades | Covers 4 matrix requirement(s). The system should allow configuration of a holding time for a capacity-based product. When a capacity-based product is added to the cart, the capacity should be reserved for configurable X minutes; if… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 9 | M2 - Core Platform | Phase 3 - Development | 2.9.4; 2.9.5; 2.11.1; 2.11.11
FEAT-035 | Server Side / Backend | E02 Sales Channels & Checkout | Ticket Types | Ticket Types | Covers 3 matrix requirement(s). Functional Requirements Fixed Donation Fixed donation amount. Multiple predefined donation values. Variable Donation Customer enters donation amount. Configurable minimum and maximum donation values. … | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Low | 3 | M2 - Core Platform | Phase 3 - Development | 1.1.129; 1.1.130; 1.1.133
FEAT-036 | Server Side / Backend | E02 Sales Channels & Checkout | Product Lifecycle | Product Lifecycle | Covers 3 matrix requirement(s). System shall support creation and maintenance of products in Draft status without exposing them to sales channels. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 8 | M2 - Core Platform | Phase 3 - Development | 1.4.5; 1.4.7; 1.4.19
FEAT-037 | Server Side / Backend | E02 Sales Channels & Checkout | B2B Sales | B2B Sales | Covers 3 matrix requirement(s). The system should support multiple languages for the Ticketing POS, Self-Service Kiosks, websites mobile app and backend . | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | High | 14 | M2 - Core Platform | Phase 3 - Development | 2.4.1; 2.5.2; 2.5.3
FEAT-038 | Server Side / Backend | E02 Sales Channels & Checkout | Case Management And Sla | Case Management And Sla | Covers 3 matrix requirement(s). Case Creation System shall support creation of customer service cases originating from website, mobile app, POS, kiosk, call center, CRM, email, chat, WhatsApp, API integrations, and internal users. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | High | 14 | M2 - Core Platform | Phase 3 - Development | 22.3.1; 22.3.3; 22.3.6
FEAT-039 | Server Side / Backend | E02 Sales Channels & Checkout | Digital Waiver Management | Digital Waiver Management | Covers 2 matrix requirement(s). The system should be to apply a transaction fee to ticket orders taken over specific sales channels, such as the call center. The transaction fee should also be applicable for actions like ticket modi… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 7 | M2 - Core Platform | Phase 3 - Development | 2.10.1; 2.15.7
FEAT-040 | Server Side / Backend | E02 Sales Channels & Checkout | Accounting | Accounting | Covers 2 matrix requirement(s). The system should be able to validate that all transactions are balanced. Total debits must equal total credits per transaction. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 7 | M2 - Core Platform | Phase 3 - Development | 5.7.16; 5.7.31
FEAT-041 | Server Side / Backend | E02 Sales Channels & Checkout | Demand Forecasting | Demand Forecasting | Covers 2 matrix requirement(s). System shall forecast revenue by sales channel. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 12 | M4 - Integrations | Phase 4 - Integration | 8.2.25; 8.2.32
FEAT-042 | Server Side / Backend | E02 Sales Channels & Checkout | Digital Waivers And Signature Management | Digital Waivers And Signature Management | Covers 2 matrix requirement(s). Digital Signature Capture System shall support electronic signatures through website, mobile application, kiosks, tablets, POS devices, and dedicated waiver stations. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 7 | M2 - Core Platform | Phase 3 - Development | 22.12.4; 22.12.10
FEAT-043 | POS App | E02 Sales Channels & Checkout | Ticketing Pos And Kiosks | Ticketing Pos And Kiosks | Covers 1 matrix requirement(s). The system should provide a sales interface that is as close to a website interface, considering UX design for a seamless journey. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Sales Channels & Checkout | P1 - Must | Medium | 6 | M2 - Core Platform | Phase 3 - Development | 2.2.1
FEAT-044 | Server Side / Backend | E02 Sales Channels & Checkout | Profile Management | Profile Management | Covers 1 matrix requirement(s). The system should be able to accept checkout for guests that do not wish to create an account in order to complete an order. Minimum required information as configured (e.g. email address) will still … | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Low | 2 | M2 - Core Platform | Phase 3 - Development | 5.3.3
FEAT-045 | POS App | E02 Sales Channels & Checkout | Virtual Queue | Virtual Queue | Covers 1 matrix requirement(s). Expose APIs for third-party systems, kiosks, apps, CRM, and partners. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Sales Channels & Checkout | P1 - Must | Medium | 6 | M2 - Core Platform | Phase 3 - Development | 5.6.30
FEAT-046 | POS App | E02 Sales Channels & Checkout | Cash Handling | Cash Handling | Covers 1 matrix requirement(s). The system should allow the cashier to enter a total amount counted, or to count by denomination. For denomination counts, the cashier counts and enters each denomination separately and each count is … | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Sales Channels & Checkout | P1 - Must | Medium | 6 | M2 - Core Platform | Phase 3 - Development | 5.8.3
FEAT-047 | Server Side / Backend | E02 Sales Channels & Checkout | Recommendation Engine | Recommendation Engine | Covers 1 matrix requirement(s). System shall provide checkout recommendations. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 11 | M4 - Integrations | Phase 4 - Integration | 8.6.9
FEAT-048 | POS App | E02 Sales Channels & Checkout | Device Integrations | Device Integrations | Covers 1 matrix requirement(s). Kiosk Integration - System shall support kiosk integration. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Sales Channels & Checkout | P1 - Must | High | 11 | M2 - Core Platform | Phase 3 - Development | 16.8.46
FEAT-049 | POS App | E02 Sales Channels & Checkout | Notifications And Messaging | Notifications And Messaging | Covers 1 matrix requirement(s). Multi-Channel Delivery Notifications shall be delivered through email, SMS, WhatsApp, mobile push notifications, in-app messages, web notifications, kiosks, digital signage, and integrated third-party… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Sales Channels & Checkout | P1 - Must | Low | 2 | M2 - Core Platform | Phase 3 - Development | 22.9.2
FEAT-050 | Server Side / Backend | E02 Sales Channels & Checkout | Audience Segmentation | Audience Segmentation | Covers 1 matrix requirement(s). Cross-Channel Attribution System shall track guest interactions across website, mobile app, email, SMS, WhatsApp, social channels, call center, POS, kiosks, APIs, and B2B channels. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 6 | M2 - Core Platform | Phase 3 - Development | 22.14.18
FEAT-051 | Server Side / Backend | E03 Admission & Access Control | Access Control System | Access Control System | Covers 114 matrix requirement(s). The Ticketing PLUs shall be printed on E-tickets Ticketing PLUs shall be printed on Wristbands (paper and RFID) | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 120 | M4 - Integrations | Phase 4 - Integration | 3.2.2; 3.2.3; 3.2.4; 3.2.5; 3.2.7; 3.2.8; 3.2.11; 3.2.12 … (+106 more)
FEAT-052 | POS App | E03 Admission & Access Control | Front Gate Sales | Front Gate Sales | Covers 36 matrix requirement(s). The operator can register the payment. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Admission & Access Control · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 67 | M4 - Integrations | Phase 4 - Integration | 2.13.2; 2.13.3; 2.13.4; 2.13.5; 2.13.6; 2.13.7; 2.13.8; 2.13.9 … (+28 more)
FEAT-053 | Server Side / Backend | E03 Admission & Access Control | Demand Forecasting | Demand Forecasting | Covers 19 matrix requirement(s). System shall forecast attendance based on historical attendance patterns. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 39 | M4 - Integrations | Phase 4 - Integration | 8.2.1; 8.2.2; 8.2.3; 8.2.6; 8.2.7; 8.2.8; 8.2.9; 8.2.10 … (+11 more)
FEAT-054 | Server Side / Backend | E03 Admission & Access Control | Ticket Types | Ticket Types | Covers 8 matrix requirement(s). The system should be able to sell multiple day tickets for attractions. The number of days should be configurable. This type of ticket should require a start date to be specified before first entry. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 12 | M2 - Core Platform | Phase 3 - Development | 1.1.5; 1.1.12; 1.1.51; 1.1.52; 1.1.61; 1.1.64; 1.1.109; 1.1.120
FEAT-055 | Server Side / Backend | E03 Admission & Access Control | Accounting | Accounting | Covers 6 matrix requirement(s). The system should support entry and maintenance of data in accounts related information tables. The primary usage of this data will be to derive accounts for billing records and interface with the Fin… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 10 | M2 - Core Platform | Phase 3 - Development | 5.7.1; 5.7.4; 5.7.10; 5.7.11; 5.7.12; 11.1.8
FEAT-056 | Server Side / Backend | E03 Admission & Access Control | Order Management | Order Management | Covers 5 matrix requirement(s). The system should have the ability for order entry: - Select an item to place on an order. - Indicate quantity of item selected - Apply a name to an order (e.g. Smith Party). Each admission on the ord… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 9 | M2 - Core Platform | Phase 3 - Development | 2.12.1; 2.12.6; 2.12.8; 2.12.9; 2.12.21
FEAT-057 | Server Side / Backend | E03 Admission & Access Control | Double-Entry Financial Ledger | Double-Entry Financial Ledger | Covers 5 matrix requirement(s). Provides accounting-grade financial recording of all platform transactions. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 9 | M2 - Core Platform | Phase 3 - Development | 5.11.1; 5.11.2; 5.11.3; 5.11.4; 5.11.5
FEAT-058 | POS App | E03 Admission & Access Control | Device Integrations | Device Integrations | Covers 5 matrix requirement(s). Handheld Scanner Integration - System shall support handheld scanner integration. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Admission & Access Control | P1 - Must | High | 17 | M2 - Core Platform | Phase 3 - Development | 16.8.43; 16.8.44; 16.8.45; 16.8.48; 16.8.49
FEAT-059 | POS App | E03 Admission & Access Control | Asset Scanning And Lookup | Asset Scanning And Lookup | Covers 5 matrix requirement(s). QR Asset Scanning - Users shall scan asset QR codes. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Admission & Access Control | P1 - Must | Medium | 9 | M2 - Core Platform | Phase 3 - Development | 18.3.1; 18.3.2; 18.3.3; 18.3.4; 18.3.5
FEAT-060 | Mobile App | E03 Admission & Access Control | Attendance And Communications | Attendance And Communications | Covers 5 matrix requirement(s). Attendance Management - Users shall clock in and clock out. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Admission & Access Control | P1 - Must | Medium | 9 | M2 - Core Platform | Phase 3 - Development | 18.9.1; 18.9.2; 18.9.3; 18.9.4; 18.9.5
FEAT-061 | Server Side / Backend | E03 Admission & Access Control | Call Center Sales | Call Center Sales | Covers 4 matrix requirement(s). Post-order service 1) On the order details page, users can view the order number, amount, time, payment method, user information, refund/change policies, and the QR code of the e-ticket 2) During the … | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 9 | M2 - Core Platform | Phase 3 - Development | 2.6.2; 2.6.18; 2.6.57; 2.6.64
FEAT-062 | Server Side / Backend | E03 Admission & Access Control | Ticket Media | Ticket Media | Covers 4 matrix requirement(s). Unique Code per Ticket: Generate a unique QR code for every issued ticket or pass. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | High | 15 | M2 - Core Platform | Phase 3 - Development | 3.1.2; 3.1.4; 3.1.5; 3.1.6
FEAT-063 | Server Side / Backend | E03 Admission & Access Control | Resource Management | Resource Management | Covers 3 matrix requirement(s). The system should allow management of the schedules of the staff resources with the possibility to set the parameters such as total hours, breaks, leave plan, absences. This data can be captured via m… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | High | 14 | M2 - Core Platform | Phase 3 - Development | 1.2.3; 1.2.80; 1.2.81
FEAT-064 | Server Side / Backend | E03 Admission & Access Control | Virtual Queue | Virtual Queue | Covers 3 matrix requirement(s). VIP / Priority Handling: Separate or fast-track queues for premium guests. Virtual Ticketing: QR code / app-based entry into queues. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | High | 14 | M2 - Core Platform | Phase 3 - Development | 5.6.4; 5.6.5; 5.6.11
FEAT-065 | Server Side / Backend | E03 Admission & Access Control | Operations Command Center | Operations Command Center | Covers 3 matrix requirement(s). System shall display current attendance, occupancy levels, capacity utilization, and crowd distribution across parks, venues, facilities, and attractions. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Low | 3 | M2 - Core Platform | Phase 3 - Development | 8.9.2; 8.9.6; 8.9.7
FEAT-066 | Server Side / Backend | E03 Admission & Access Control | Sales Channels | Sales Channels | Covers 2 matrix requirement(s). The system should allow the user to filter the ticket by all types and available properties. For example, dated/non-dated, single-entry/multiple-entry, adult/child, standard/VIP, attraction selection,… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Low | 3 | M2 - Core Platform | Phase 3 - Development | 1.5.3; 2.1.19
FEAT-067 | Server Side / Backend | E03 Admission & Access Control | Parking Integration | Parking Integration | Covers 2 matrix requirement(s). The payment can be done upfront or at exit. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 7 | M2 - Core Platform | Phase 3 - Development | 3.4.1; 3.4.2
FEAT-068 | Server Side / Backend | E03 Admission & Access Control | Profile Management | Profile Management | Covers 2 matrix requirement(s). The system should validate the data captured for a guest profile. Validation should include but not limited to: - Phone number is only numbers. - Name is only alphabets. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 7 | M2 - Core Platform | Phase 3 - Development | 5.3.2; 5.3.16
FEAT-069 | Server Side / Backend | E03 Admission & Access Control | Loyalty | Loyalty | Covers 2 matrix requirement(s). The system should support loyalty point redemption in place for the guests to redeem their earned point for either products or services under venue offerings. B2C website should support: 1. Points acq… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Low | 3 | M2 - Core Platform | Phase 3 - Development | 5.4.2; 5.4.26
FEAT-070 | Server Side / Backend | E03 Admission & Access Control | Bi And Reporting | Bi And Reporting | Covers 2 matrix requirement(s). System shall provide access control dashboards. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | High | 12 | M2 - Core Platform | Phase 3 - Development | 8.7.7; 8.7.33
FEAT-071 | Server Side / Backend | E03 Admission & Access Control | Game And Ride Payment And Redemption | Game And Ride Payment And Redemption | Covers 2 matrix requirement(s). Gameplay validation Prices to be defined for each game Assign prices for the Group. Game Reader - Access to the particular game - Bonus deduction should be done first Package - To create a package wit… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 7 | M2 - Core Platform | Phase 3 - Development | 10.2.7; 10.2.13
FEAT-072 | Server Side / Backend | E03 Admission & Access Control | Gamification And Loyalty | Gamification And Loyalty | Covers 2 matrix requirement(s). Achievement Engine System shall automatically award achievements when guests complete predefined milestones, goals, challenges, loyalty activities, purchases, or attendance requirements. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 7 | M2 - Core Platform | Phase 3 - Development | 22.6.2; 22.6.5
FEAT-073 | Server Side / Backend | E03 Admission & Access Control | Omnichannel Communications And Ai Chatbot | Omnichannel Communications And Ai Chatbot | Covers 2 matrix requirement(s). Loyalty Integration Guests shall be able to view loyalty balances, redeem rewards, track achievements, review tier status, and receive loyalty recommendations through chat. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 12 | M4 - Integrations | Phase 4 - Integration | 22.8.9; 22.8.20
FEAT-074 | Server Side / Backend | E03 Admission & Access Control | Notifications And Messaging | Notifications And Messaging | Covers 2 matrix requirement(s). Ticketing Notifications System shall automatically send booking confirmations, tickets, reminders, seat assignments, changes, cancellations, upgrades, transfers, and attendance notifications. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Low | 3 | M2 - Core Platform | Phase 3 - Development | 22.9.12; 22.9.22
FEAT-075 | POS App | E03 Admission & Access Control | Product Lifecycle | Product Lifecycle | Covers 1 matrix requirement(s). The system should propagate any changes made to the properties of a product to the already sold tickets as well. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Admission & Access Control | P1 - Must | Medium | 6 | M2 - Core Platform | Phase 3 - Development | 1.4.4
FEAT-076 | Server Side / Backend | E03 Admission & Access Control | Ticket Upgrades | Ticket Upgrades | Covers 1 matrix requirement(s). The system should allow upgrade of all type of Tickets (Not redeemed, partially redeemed, fully redeemed or expired). Tickets can be upgraded to a longer duration ticket or a greater access ticket (e.… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 6 | M2 - Core Platform | Phase 3 - Development | 2.11.2
FEAT-077 | Server Side / Backend | E03 Admission & Access Control | Portfolio Management | Portfolio Management | Covers 1 matrix requirement(s). The system should be able to print media which are linked to guest's portfolios, this way multiple media can be availed/printed to the same guest portfolio. (examples: lost/soiled ticket reprints, web… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 6 | M2 - Core Platform | Phase 3 - Development | 5.5.4
FEAT-078 | Server Side / Backend | E03 Admission & Access Control | Portfolio And Entitlement Management | Portfolio And Entitlement Management | Covers 1 matrix requirement(s). Support issuance and management of QR codes, RFID wristbands, RFID cards, NFC passes, digital tickets, and printed tickets linked to portfolios. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 6 | M2 - Core Platform | Phase 3 - Development | 5.5.4
FEAT-079 | POS App | E03 Admission & Access Control | Fraud Detection | Fraud Detection | Covers 1 matrix requirement(s). System shall detect duplicate ticket scans. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Admission & Access Control | P1 - Must | Medium | 6 | M2 - Core Platform | Phase 3 - Development | 8.3.23
FEAT-080 | Server Side / Backend | E03 Admission & Access Control | Recommendation Engine | Recommendation Engine | Covers 1 matrix requirement(s). System shall provide recommendations based on attendance history. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 11 | M4 - Integrations | Phase 4 - Integration | 8.6.16
FEAT-081 | Server Side / Backend | E03 Admission & Access Control | Reporting And Dashboards | Reporting And Dashboards | Covers 1 matrix requirement(s). Credential Generation System shall generate accreditation IDs, QR codes, NFC cards or digital credentials. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 6 | M2 - Core Platform | Phase 3 - Development | 12.1.4
FEAT-082 | Server Side / Backend | E03 Admission & Access Control | Sandbox | Sandbox | Covers 1 matrix requirement(s). Sandbox Access Control - System shall support role-based sandbox access. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 6 | M2 - Core Platform | Phase 3 - Development | 13.2.14
FEAT-083 | Server Side / Backend | E03 Admission & Access Control | Asset Management | Asset Management | Covers 1 matrix requirement(s). Asset QR Code Management - System shall generate and manage asset QR codes. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 6 | M2 - Core Platform | Phase 3 - Development | 17.1.7
FEAT-084 | Server Side / Backend | E03 Admission & Access Control | Licensing Models | Licensing Models | Covers 1 matrix requirement(s). Attendance-Based Licensing - System shall support licensing based on attendance volumes. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 6 | M2 - Core Platform | Phase 3 - Development | 20.3.6
FEAT-085 | Cross Platform | E03 Admission & Access Control | Usage And Quota Monitoring | Usage And Quota Monitoring | Covers 1 matrix requirement(s). Attendance Usage Monitoring - System shall monitor attendance volumes. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 6 | M2 - Core Platform | Phase 3 - Development | 20.6.6
FEAT-086 | Server Side / Backend | E03 Admission & Access Control | Guest Profiles And Data Management | Guest Profiles And Data Management | Covers 1 matrix requirement(s). Loyalty History Guest profiles shall display loyalty points earned, redeemed, adjusted, expired, rewards claimed, tier progression, and loyalty transactions. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Low | 2 | M2 - Core Platform | Phase 3 - Development | 22.2.13
FEAT-087 | Server Side / Backend | E03 Admission & Access Control | Reviews And Ratings | Reviews And Ratings | Covers 1 matrix requirement(s). Multi-Channel Review Capture Reviews may be collected through email, SMS, WhatsApp, mobile application, website, kiosks, surveys, QR codes, and third-party review platforms. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Low | 2 | M2 - Core Platform | Phase 3 - Development | 22.5.2
FEAT-088 | Server Side / Backend | E03 Admission & Access Control | Surveys And Feedback | Surveys And Feedback | Covers 1 matrix requirement(s). Multi-Channel Distribution Surveys shall be distributed through email, SMS, WhatsApp, push notifications, mobile applications, websites, kiosks, QR codes, and third-party communication channels. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Low | 2 | M2 - Core Platform | Phase 3 - Development | 22.7.6
FEAT-089 | Server Side / Backend | E03 Admission & Access Control | Marketing | Marketing | Covers 1 matrix requirement(s). Accessibility Compliance CMS shall support accessibility standards including WCAG compliance, screen readers, keyboard navigation, alternative text, and accessibility validation. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 6 | M2 - Core Platform | Phase 3 - Development | 22.10.28
FEAT-090 | Server Side / Backend | E03 Admission & Access Control | Digital Waivers And Signature Management | Digital Waivers And Signature Management | Covers 1 matrix requirement(s). Access Control Integration Access Control shall automatically deny or restrict entry to activities requiring valid waivers if a signed waiver is not available. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | High | 11 | M2 - Core Platform | Phase 3 - Development | 22.12.12
FEAT-091 | Server Side / Backend | E04 Payments, Wallet & Financial | Revenue Recognition | Revenue Recognition | Covers 120 matrix requirement(s). Supports recognition of revenue according to accounting policies rather than immediately upon sale. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · PCI-DSS scope & gateway certification | P1 - Must | High | 120 | M2 - Core Platform | Phase 3 - Development | 5.12.1; 5.12.2; 5.12.3; 5.12.4; 5.12.5; 5.12.6; 5.12.7; 5.12.8 … (+112 more)
FEAT-092 | Server Side / Backend | E04 Payments, Wallet & Financial | Wallet | Wallet | Covers 57 matrix requirement(s). The system should be EMV (Euro pay, MasterCard and Visa) certified for offline and online payments. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) · PCI-DSS scope & gateway certification | P3 - Could | High | 100 | M4 - Integrations | Phase 4 - Integration | 4.3.1; 4.3.2; 4.3.3; 4.3.4; 4.3.5; 4.3.6; 4.3.7; 4.3.8 … (+49 more)
FEAT-093 | Server Side / Backend | E04 Payments, Wallet & Financial | Accounting | Accounting | Covers 33 matrix requirement(s). The system should be able to store account information for each Offset/Balancing Account by Payment Type (e.g. cash, bank card, tax, etc.). At minimum, the below fields should be included for storage:… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · PCI-DSS scope & gateway certification | P1 - Must | High | 62 | M2 - Core Platform | Phase 3 - Development | 5.7.2; 5.7.8; 5.7.9; 5.7.14; 5.7.15; 5.7.17; 5.7.18; 5.7.19 … (+25 more)
FEAT-094 | Server Side / Backend | E04 Payments, Wallet & Financial | Pricing | Pricing | Covers 21 matrix requirement(s). 1.B2B Management backend should support: 1) Ability to create new B2B company master accounts, including setting the account name, password, and company information 2) Ability to group B2B company acc… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · PCI-DSS scope & gateway certification | P1 - Must | High | 43 | M2 - Core Platform | Phase 3 - Development | 2.7.1; 2.7.3; 2.7.8; 2.7.9; 2.7.35; 2.7.38; 2.7.39; 2.7.40 … (+13 more)
FEAT-095 | Server Side / Backend | E04 Payments, Wallet & Financial | Order Management | Order Management | Covers 18 matrix requirement(s). The system should allow for order adjustments. Following adjustments should be supported: - Users to refund guests (with supervisor approval) - Users to manually adjust guest orders (date, time, numbe… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · PCI-DSS scope & gateway certification | P1 - Must | High | 38 | M2 - Core Platform | Phase 3 - Development | 2.12.2; 2.12.3; 2.12.5; 2.12.11; 2.12.12; 2.12.13; 2.12.14; 2.12.15 … (+10 more)
FEAT-096 | Mobile App | E04 Payments, Wallet & Financial | Authentication And Login | Authentication And Login | Covers 16 matrix requirement(s). Digital Wallet - System shall provide a digital wallet. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Payments, Wallet & Financial · PCI-DSS scope & gateway certification | P1 - Must | Medium | 19 | M2 - Core Platform | Phase 3 - Development | 19.2.9; 19.2.26; 19.2.29; 19.2.30; 19.2.31; 19.2.32; 19.2.33; 19.2.34 … (+8 more)
FEAT-097 | Server Side / Backend | E04 Payments, Wallet & Financial | Promotions | Promotions | Covers 15 matrix requirement(s). The system should be able to refund transactions that contain promotions and ensure discounted amount is not refunded | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · PCI-DSS scope & gateway certification | P1 - Must | High | 33 | M2 - Core Platform | Phase 3 - Development | 4.2.2; 4.2.8; 4.2.9; 4.2.10; 4.2.14; 4.2.15; 4.2.16; 4.2.17 … (+7 more)
FEAT-098 | Server Side / Backend | E04 Payments, Wallet & Financial | Ticket Types | Ticket Types | Covers 14 matrix requirement(s). The system should allow the capacity for all type of ticket to be configurable. Capacity of a ticket can be configurable at multiple levels: 1) Sales Capacity: Allow only a fixed number of tickets to … | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · PCI-DSS scope & gateway certification | P1 - Must | High | 31 | M2 - Core Platform | Phase 3 - Development | 1.1.10; 1.1.15; 1.1.22; 1.1.24; 1.1.37; 1.1.55; 1.1.100; 1.1.105 … (+6 more)
FEAT-099 | Server Side / Backend | E04 Payments, Wallet & Financial | Fraud Detection | Fraud Detection | Covers 12 matrix requirement(s). System shall identify transactions with elevated chargeback risk. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) · PCI-DSS scope & gateway certification | P3 - Could | High | 28 | M4 - Integrations | Phase 4 - Integration | 8.3.11; 8.3.12; 8.3.13; 8.3.14; 8.3.15; 8.3.16; 8.3.17; 8.3.18 … (+4 more)
FEAT-100 | Server Side / Backend | E04 Payments, Wallet & Financial | Call Center Sales | Call Center Sales | Covers 10 matrix requirement(s). B2C website should support: 1.Home page 1) Banners display packages, upgrades, and discounts 2) All available products are shown by category: Packages, Tickets, Experiences, Annual Passes, Others 3) P… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · PCI-DSS scope & gateway certification | P1 - Must | High | 25 | M2 - Core Platform | Phase 3 - Development | 2.6.1; 2.6.4; 2.6.21; 2.6.33; 2.6.35; 2.6.38; 2.6.42; 2.6.47 … (+2 more)
FEAT-101 | Server Side / Backend | E04 Payments, Wallet & Financial | Portfolio And Entitlement Management | Portfolio And Entitlement Management | Covers 9 matrix requirement(s). Allow configurable transfer of stored value, wallet balances, promotional credits, and vouchers between linked portfolios with full audit tracking. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · PCI-DSS scope & gateway certification | P1 - Must | High | 23 | M2 - Core Platform | Phase 3 - Development | 5.5.3; 5.5.6; 5.5.9; 5.5.10; 5.5.17; 5.5.23; 5.5.24; 5.5.25 … (+1 more)
FEAT-102 | Server Side / Backend | E04 Payments, Wallet & Financial | Virtual Queue | Virtual Queue | Covers 9 matrix requirement(s). Automatically assign guests to queues based on ticket type, attraction, capacity availability, reservation rules, guest profile, or business policies. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · PCI-DSS scope & gateway certification | P1 - Must | Medium | 13 | M2 - Core Platform | Phase 3 - Development | 5.6.4; 5.6.12; 5.6.13; 5.6.20; 5.6.21; 5.6.23; 5.6.24; 5.6.29 … (+1 more)
FEAT-103 | Server Side / Backend | E04 Payments, Wallet & Financial | Ticket Upgrades | Ticket Upgrades | Covers 8 matrix requirement(s). The system should display prices in multiple currencies in the B2C portal for guests comparison although the sale will be finalized always in local currency. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · PCI-DSS scope & gateway certification | P1 - Must | Medium | 12 | M2 - Core Platform | Phase 3 - Development | 2.9.1; 2.9.3; 2.9.11; 2.9.12; 2.9.13; 2.9.14; 2.9.19; 2.11.4
FEAT-104 | Server Side / Backend | E04 Payments, Wallet & Financial | Profile Management | Profile Management | Covers 8 matrix requirement(s). The system should allow the guests to upload photos to create avatars for their profiles. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) · PCI-DSS scope & gateway certification | P3 - Could | High | 22 | M4 - Integrations | Phase 4 - Integration | 5.3.10; 5.3.14; 5.3.15; 5.3.17; 5.3.22; 5.3.33; 5.3.34; 5.3.35
FEAT-105 | Server Side / Backend | E04 Payments, Wallet & Financial | Ticket Media | Ticket Media | Covers 7 matrix requirement(s). The system should support multiple media types for a ticket. Expected formats: - Paper/thermal tickets with QR, Barcode, RFID - Print at home tickets with QR, Barcode - Smartphones: NFC (near-field co… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · PCI-DSS scope & gateway certification | P1 - Must | High | 20 | M2 - Core Platform | Phase 3 - Development | 2.16.2; 2.16.9; 2.16.11; 2.16.13; 2.16.17; 3.1.7; 3.1.10
FEAT-106 | Server Side / Backend | E04 Payments, Wallet & Financial | Guest Profiles And Data Management | Guest Profiles And Data Management | Covers 7 matrix requirement(s). Unified Guest Profile System shall maintain a single consolidated guest profile containing personal information, tickets, memberships, loyalty accounts, wallet balances, reservations, purchases, visit… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · PCI-DSS scope & gateway certification | P1 - Must | Medium | 11 | M2 - Core Platform | Phase 3 - Development | 22.2.1; 22.2.3; 22.2.11; 22.2.14; 22.2.15; 22.2.17; 22.2.26
FEAT-107 | Server Side / Backend | E04 Payments, Wallet & Financial | Omnichannel Communications And Ai Chatbot | Omnichannel Communications And Ai Chatbot | Covers 7 matrix requirement(s). Unified Guest Identification System shall automatically identify guests using phone number, email, membership number, loyalty account, wallet ID, booking reference, or authenticated user session. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) · PCI-DSS scope & gateway certification | P3 - Could | High | 20 | M4 - Integrations | Phase 4 - Integration | 22.8.3; 22.8.6; 22.8.7; 22.8.10; 22.8.11; 22.8.13; 22.8.22
FEAT-108 | Server Side / Backend | E04 Payments, Wallet & Financial | Event Management | Event Management | Covers 6 matrix requirement(s). The system should allow configuration of event details such as start time (date & time), end time, duration of event, capacity (amount of places that can be sold for an event), seating categories, num… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · PCI-DSS scope & gateway certification | P1 - Must | Medium | 10 | M2 - Core Platform | Phase 3 - Development | 1.3.2; 1.3.10; 1.3.12; 1.3.20; 1.3.21; 1.3.51
FEAT-109 | Server Side / Backend | E04 Payments, Wallet & Financial | Audience Segmentation | Audience Segmentation | Covers 6 matrix requirement(s). Audience Segmentation Engine System shall provide a centralized segmentation engine allowing users to create, manage, and reuse guest audiences based on demographic, behavioral, transactional, loyalty… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) · PCI-DSS scope & gateway certification | P3 - Could | High | 19 | M4 - Integrations | Phase 4 - Integration | 22.14.1; 22.14.4; 22.14.8; 22.14.15; 22.14.19; 22.14.22
FEAT-110 | Server Side / Backend | E04 Payments, Wallet & Financial | Resource Management | Resource Management | Covers 5 matrix requirement(s). The system should allow linking of staff resources in different combinations and time-slot capacity with individual attraction experiences such as group lessons and private lessons. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · PCI-DSS scope & gateway certification | P1 - Must | Medium | 9 | M2 - Core Platform | Phase 3 - Development | 1.2.4; 1.2.20; 1.2.30; 1.2.31; 1.2.51
FEAT-111 | Server Side / Backend | E04 Payments, Wallet & Financial | Sales Channels | Sales Channels | Covers 5 matrix requirement(s). The system should allow specification of rules and conditions associated with a ticket. These rules and conditions will govern the usage of the ticket and any transactions associated with a ticket suc… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · PCI-DSS scope & gateway certification | P1 - Must | Medium | 9 | M2 - Core Platform | Phase 3 - Development | 1.5.5; 2.1.17; 2.1.21; 2.1.24; 2.1.29
FEAT-112 | Server Side / Backend | E04 Payments, Wallet & Financial | Upsell And Cross-Sell | Upsell And Cross-Sell | Covers 5 matrix requirement(s). Upsell recommendations shall remain synchronized across B2C, B2B, Mobile App, POS, Kiosk, Call Center, API, Membership, Loyalty, and Wallet channels. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) · PCI-DSS scope & gateway certification | P3 - Could | High | 17 | M4 - Integrations | Phase 4 - Integration | 3.7.12; 4.4.5; 4.4.22; 4.4.28; 4.4.29
FEAT-113 | Server Side / Backend | E04 Payments, Wallet & Financial | Game And Ride Payment And Redemption | Game And Ride Payment And Redemption | Covers 5 matrix requirement(s). The system should allow the usage of digital wallet credits for pay as you go for Redemption /Skill games /Rides /Video games | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · PCI-DSS scope & gateway certification | P1 - Must | High | 17 | M2 - Core Platform | Phase 3 - Development | 10.2.1; 10.2.2; 10.2.3; 10.2.5; 10.2.22
FEAT-114 | Server Side / Backend | E04 Payments, Wallet & Financial | Api Business Coverage | Api Business Coverage | Covers 5 matrix requirement(s). APIs shall support wallet funding, spending, refunds, balance inquiry, transaction history and wallet status management. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · PCI-DSS scope & gateway certification | P1 - Must | High | 17 | M2 - Core Platform | Phase 3 - Development | 13.3.5; 13.3.7; 13.3.11; 13.3.16; 13.3.17
FEAT-115 | Server Side / Backend | E04 Payments, Wallet & Financial | Group Reservations And Blocks | Group Reservations And Blocks | Covers 5 matrix requirement(s). Group Reservations System shall support group reservations. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · PCI-DSS scope & gateway certification | P1 - Must | Medium | 9 | M2 - Core Platform | Phase 3 - Development | 21.9.1; 21.9.2; 21.9.3; 21.9.4; 21.9.5
FEAT-116 | Server Side / Backend | E04 Payments, Wallet & Financial | Campaign Management | Campaign Management | Covers 5 matrix requirement(s). Campaign Approval Workflow System shall support configurable approval workflows before campaign activation, including creator, reviewer, approver, and publisher roles with full audit tracking. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · PCI-DSS scope & gateway certification | P1 - Must | Medium | 9 | M2 - Core Platform | Phase 3 - Development | 22.1.5; 22.1.6; 22.1.10; 22.1.15; 22.1.19
FEAT-117 | Server Side / Backend | E04 Payments, Wallet & Financial | Case Management And Sla | Case Management And Sla | Covers 5 matrix requirement(s). Event Trigger Engine System shall automatically trigger marketing journeys based on business events including ticket purchases, reservations, check-ins, membership renewals, membership expiration, loy… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · PCI-DSS scope & gateway certification | P1 - Must | Medium | 9 | M2 - Core Platform | Phase 3 - Development | 22.3.2; 22.3.4; 22.3.9; 22.3.15; 22.3.21
FEAT-118 | Server Side / Backend | E04 Payments, Wallet & Financial | Notifications And Messaging | Notifications And Messaging | Covers 5 matrix requirement(s). Dynamic Personalization Notification content shall support dynamic placeholders including guest name, booking reference, event details, membership status, loyalty balance, wallet balance, venue inform… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) · PCI-DSS scope & gateway certification | P3 - Could | High | 17 | M4 - Integrations | Phase 4 - Integration | 22.9.3; 22.9.4; 22.9.9; 22.9.11; 22.9.13
FEAT-119 | Server Side / Backend | E04 Payments, Wallet & Financial | Product Lifecycle | Product Lifecycle | Covers 4 matrix requirement(s). System shall support future publication, activation, deactivation and automatic retirement of products based on configurable dates and times. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) · PCI-DSS scope & gateway certification | P3 - Could | High | 15 | M4 - Integrations | Phase 4 - Integration | 1.4.8; 1.4.15; 1.4.16; 1.4.26
FEAT-120 | Server Side / Backend | E04 Payments, Wallet & Financial | Membership | Membership | Covers 4 matrix requirement(s). Annual-pass reservation quota engine linked to biometric identity, with self-service reschedule/cancel | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) · PCI-DSS scope & gateway certification | P3 - Could | High | 15 | M4 - Integrations | Phase 4 - Integration | 2.14.7; 2.14.10; 2.14.16; 2.14.18
FEAT-121 | POS App | E04 Payments, Wallet & Financial | Front Gate Sales | Front Gate Sales | Covers 3 matrix requirement(s). Before closing the order, it is possible to have upsells / cross sells functionalities activated. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Payments, Wallet & Financial · PCI-DSS scope & gateway certification | P1 - Must | High | 14 | M2 - Core Platform | Phase 3 - Development | 2.13.1; 2.13.34; 2.13.36
FEAT-122 | Server Side / Backend | E04 Payments, Wallet & Financial | Loyalty | Loyalty | Covers 3 matrix requirement(s). Configure redemption rules and conversion rates. System shall support configurable points redemption rules including points-to-currency conversion, product redemption, ticket redemption, experience re… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · PCI-DSS scope & gateway certification | P1 - Must | Low | 3 | M2 - Core Platform | Phase 3 - Development | 5.4.13; 5.4.19; 5.4.27
FEAT-123 | Server Side / Backend | E04 Payments, Wallet & Financial | Gamification And Loyalty | Gamification And Loyalty | Covers 3 matrix requirement(s). Points-Based Activities Guests shall earn points through visits, purchases, event attendance, referrals, reviews, surveys, memberships, wallet activity, and other configurable actions. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · PCI-DSS scope & gateway certification | P1 - Must | High | 14 | M2 - Core Platform | Phase 3 - Development | 22.6.4; 22.6.13; 22.6.17
FEAT-124 | Server Side / Backend | E04 Payments, Wallet & Financial | Ticket Resale Marketplace | Ticket Resale Marketplace | Covers 2 matrix requirement(s). System shall allow ticket holders to create, update, activate, deactivate, cancel, and manage resale listings. Listing status shall be tracked throughout its lifecycle. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · PCI-DSS scope & gateway certification | P1 - Must | Low | 3 | M2 - Core Platform | Phase 3 - Development | 1.6.3; 1.6.12
FEAT-125 | Server Side / Backend | E04 Payments, Wallet & Financial | Unified Platform | Unified Platform | Covers 2 matrix requirement(s). Display memberships, wallet balances, points and vouchers in one view. System shall provide a single guest wallet view combining membership status, loyalty points, stored value, gift cards, vouchers, … | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) · PCI-DSS scope & gateway certification | P3 - Could | High | 12 | M4 - Integrations | Phase 4 - Integration | 5.4.32; 5.4.33
FEAT-126 | Server Side / Backend | E04 Payments, Wallet & Financial | Device Registration | Device Registration | Covers 2 matrix requirement(s). Device Activation - System shall support device activation. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · PCI-DSS scope & gateway certification | P1 - Must | Medium | 7 | M2 - Core Platform | Phase 3 - Development | 16.1.4; 16.1.5
FEAT-127 | Server Side / Backend | E04 Payments, Wallet & Financial | Module Marketplace And Management | Module Marketplace And Management | Covers 2 matrix requirement(s). Module Activation - System shall support module activation. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · PCI-DSS scope & gateway certification | P1 - Must | Medium | 7 | M2 - Core Platform | Phase 3 - Development | 20.4.4; 20.4.5
FEAT-128 | Server Side / Backend | E04 Payments, Wallet & Financial | Billing And Payment | Billing And Payment | Covers 2 matrix requirement(s). Subscription Invoicing - System shall generate subscription invoices. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · PCI-DSS scope & gateway certification | P1 - Must | Medium | 7 | M2 - Core Platform | Phase 3 - Development | 20.7.1; 20.7.6
FEAT-129 | Server Side / Backend | E04 Payments, Wallet & Financial | Newsletter And Email Marketing | Newsletter And Email Marketing | Covers 2 matrix requirement(s). Product & Event Integration Newsletter content shall automatically retrieve information from Ticketing, Events, Memberships, Loyalty, Wallet, Retail, F&B, and Resource Management modules without manua… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · PCI-DSS scope & gateway certification | P1 - Must | High | 12 | M2 - Core Platform | Phase 3 - Development | 22.4.8; 22.4.16
FEAT-130 | Server Side / Backend | E04 Payments, Wallet & Financial | Reviews And Ratings | Reviews And Ratings | Covers 2 matrix requirement(s). Review Collection System shall automatically collect reviews and ratings from guests following visits, ticket usage, completed events, reservations, purchases, membership activities, and customer serv… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · PCI-DSS scope & gateway certification | P1 - Must | Low | 3 | M2 - Core Platform | Phase 3 - Development | 22.5.1; 22.5.8
FEAT-131 | Server Side / Backend | E04 Payments, Wallet & Financial | Surveys And Feedback | Surveys And Feedback | Covers 2 matrix requirement(s). Trigger-Based Surveys Surveys shall automatically trigger based on ticket usage, event attendance, reservation completion, membership activity, wallet activity, loyalty activity, support interactions,… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · PCI-DSS scope & gateway certification | P1 - Must | Medium | 7 | M2 - Core Platform | Phase 3 - Development | 22.7.5; 22.7.12
FEAT-132 | Server Side / Backend | E04 Payments, Wallet & Financial | Marketing | Marketing | Covers 2 matrix requirement(s). Content Scheduling Content shall support publishing schedules, expiration dates, seasonal activation, campaign activation, and future publication. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · PCI-DSS scope & gateway certification | P1 - Must | High | 12 | M2 - Core Platform | Phase 3 - Development | 22.10.8; 22.10.18
FEAT-133 | POS App | E04 Payments, Wallet & Financial | Ticketing Pos And Kiosks | Ticketing Pos And Kiosks | Covers 1 matrix requirement(s). The system should allow creation of Mobile POS, depending on the activities, activation on demand, either on site or off site. Mobile-POS should have all the same features as a normal POS. The sales j… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Payments, Wallet & Financial · PCI-DSS scope & gateway certification | P1 - Must | High | 11 | M2 - Core Platform | Phase 3 - Development | 2.2.2
FEAT-134 | POS App | E04 Payments, Wallet & Financial | Flying Pos | Flying Pos | Covers 1 matrix requirement(s). The system should support offline mode for POS and Kiosk: - Ability to switch automatically to offline mode in case of server outage / network loss - Definition of which functionality will be lost in … | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Payments, Wallet & Financial · PCI-DSS scope & gateway certification | P1 - Must | High | 11 | M2 - Core Platform | Phase 3 - Development | 2.3.1
FEAT-135 | Server Side / Backend | E04 Payments, Wallet & Financial | Digital Waiver Management | Digital Waiver Management | Covers 1 matrix requirement(s). System shall display a detailed breakdown of all applicable fees, taxes, discounts, promotions, surcharges, and charges during checkout, order confirmation, receipts, invoices, and financial documents… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · PCI-DSS scope & gateway certification | P1 - Must | Low | 2 | M2 - Core Platform | Phase 3 - Development | 2.10.5
FEAT-136 | POS App | E04 Payments, Wallet & Financial | Bundles | Bundles | Covers 1 matrix requirement(s). Redeem gift cards at POS and digital channels. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Payments, Wallet & Financial · PCI-DSS scope & gateway certification | P1 - Must | Medium | 6 | M2 - Core Platform | Phase 3 - Development | 4.1.25
FEAT-137 | Server Side / Backend | E04 Payments, Wallet & Financial | Payment Methods | Payment Methods | Covers 1 matrix requirement(s). The system should be able to provide a way for central reservations where the guest should be able to place a booking from various touchpoints. The system should provide APIs to facilitate reservation… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · PCI-DSS scope & gateway certification | P1 - Must | Medium | 6 | M2 - Core Platform | Phase 3 - Development | 5.1.4
FEAT-138 | Server Side / Backend | E04 Payments, Wallet & Financial | Cash Handling | Cash Handling | Covers 1 matrix requirement(s). The system should allow print and reprint of deposit box transactions. The output should be bilingual (Arabic and English) and simplified for tax handling. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · PCI-DSS scope & gateway certification | P1 - Must | Medium | 6 | M2 - Core Platform | Phase 3 - Development | 5.8.5
FEAT-139 | Server Side / Backend | E04 Payments, Wallet & Financial | Receipt | Receipt | Covers 1 matrix requirement(s). The system should show all required fields on the receipt in accordance with VAT regulations. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · PCI-DSS scope & gateway certification | P1 - Must | Medium | 6 | M2 - Core Platform | Phase 3 - Development | 5.10.3
FEAT-140 | Server Side / Backend | E04 Payments, Wallet & Financial | Double-Entry Financial Ledger | Double-Entry Financial Ledger | Covers 1 matrix requirement(s). Multi-Currency Support System shall support accounting entries across multiple currencies. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · PCI-DSS scope & gateway certification | P1 - Must | Medium | 6 | M2 - Core Platform | Phase 3 - Development | 5.11.6
FEAT-141 | Server Side / Backend | E04 Payments, Wallet & Financial | Dynamic Pricing | Dynamic Pricing | Covers 1 matrix requirement(s). System shall support simulation of pricing scenarios before activation. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · PCI-DSS scope & gateway certification | P1 - Must | Medium | 6 | M2 - Core Platform | Phase 3 - Development | 8.5.44
FEAT-142 | Server Side / Backend | E04 Payments, Wallet & Financial | Ai Configuration Assistant | Ai Configuration Assistant | Covers 1 matrix requirement(s). System shall support automatic activation of future pricing. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · PCI-DSS scope & gateway certification | P1 - Must | Medium | 6 | M2 - Core Platform | Phase 3 - Development | 8.8.6
FEAT-143 | Cross Platform | E04 Payments, Wallet & Financial | Operations Command Center | Operations Command Center | Covers 1 matrix requirement(s). System shall provide real-time monitoring of ticket sales, memberships, F&B sales, retail sales, refunds, upgrades, and transaction performance. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · PCI-DSS scope & gateway certification | P1 - Must | High | 11 | M2 - Core Platform | Phase 3 - Development | 8.9.8
FEAT-144 | Server Side / Backend | E04 Payments, Wallet & Financial | Seat Tracking And Holds | Seat Tracking And Holds | Covers 1 matrix requirement(s). Seat Reservation Tracking System shall support seat reservation tracking. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · PCI-DSS scope & gateway certification | P1 - Must | Medium | 6 | M2 - Core Platform | Phase 3 - Development | 21.4.4
FEAT-145 | POS App | E05 F&B Operations & POS | Table Reservation | Table Reservation | Covers 69 matrix requirement(s). The system should have the ability to set mandatory or optional modifiers for items. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for F&B Operations & POS · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 119 | M4 - Integrations | Phase 4 - Integration | 4.9.1; 4.9.2; 4.9.3; 4.9.4; 4.9.5; 4.9.6; 4.9.7; 4.9.8 … (+61 more)
FEAT-146 | POS App | E05 F&B Operations & POS | Retail Pos | Retail Pos | Covers 62 matrix requirement(s). The system should be able to assign rights to groups and further add the users to that particular groups (which should be tier based), | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for F&B Operations & POS · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 108 | M4 - Integrations | Phase 4 - Integration | 7.1.1; 7.1.2; 7.1.3; 7.1.4; 7.1.5; 7.1.6; 7.1.7; 7.1.8 … (+54 more)
FEAT-147 | POS App | E05 F&B Operations & POS | Fandb Pos - Core Ordering | Fandb Pos - Core Ordering | Covers 37 matrix requirement(s). The system should be able to record a sale to guests from the POS register using menu screens/buttons. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for F&B Operations & POS | P2 - Should | High | 68 | M3 - Business Features | Phase 3 - Development | 4.6.1; 4.6.2; 4.6.3; 4.6.4; 4.6.5; 4.6.6; 4.6.7; 4.6.8 … (+29 more)
FEAT-148 | POS App | E05 F&B Operations & POS | Fandb Pos - Menu Management | Fandb Pos - Menu Management | Covers 29 matrix requirement(s). The system should have the ability to add and remove multiple ingredients on one type of recipe order, while there are other recipe products on the same order without any modifications. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for F&B Operations & POS · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 55 | M4 - Integrations | Phase 4 - Integration | 4.8.1; 4.8.2; 4.8.3; 4.8.4; 4.8.5; 4.8.6; 4.8.7; 4.8.8 … (+21 more)
FEAT-149 | POS App | E05 F&B Operations & POS | Inventory Management Integration | Inventory Management Integration | Covers 15 matrix requirement(s). Functional Requirements Ability to create and manage rental products (Bike, Kayak, Watercraft, Stroller, Cabana, Locker, Wheelchair, etc.). Configure: - Product Code - Product Name - Description - Pro… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for F&B Operations & POS · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 33 | M4 - Integrations | Phase 4 - Integration | 7.6.1; 7.6.2; 7.6.3; 7.6.4; 7.6.5; 7.6.6; 7.6.7; 7.6.8 … (+7 more)
FEAT-150 | POS App | E05 F&B Operations & POS | Kitchen Display | Kitchen Display | Covers 10 matrix requirement(s). Event scheduled services such as table booking or meal delivery can be managed by the system (sales only) | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for F&B Operations & POS | P2 - Should | High | 25 | M3 - Business Features | Phase 3 - Development | 7.5.1; 7.5.2; 7.5.3; 7.5.4; 7.5.5; 7.5.6; 7.5.7; 7.5.8 … (+2 more)
FEAT-151 | POS App | E05 F&B Operations & POS | Payment Methods | Payment Methods | Covers 9 matrix requirement(s). The system should be able to allow table reservations view for the available tables in real-time, for the guests to choose/request. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for F&B Operations & POS | P2 - Should | High | 23 | M3 - Business Features | Phase 3 - Development | 5.1.1; 5.1.2; 5.1.5; 5.1.6; 5.1.8; 5.1.9; 5.1.10; 5.1.11 … (+1 more)
FEAT-152 | POS App | E05 F&B Operations & POS | Fandb Pos - Modifiers | Fandb Pos - Modifiers | Covers 8 matrix requirement(s). The system should be able to create a new Check with table and guest numbers, add items to print in kitchen or on QSR(Quick service restaurants), void items and ensure they don't appear in kitchen. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for F&B Operations & POS | P2 - Should | Medium | 12 | M3 - Business Features | Phase 3 - Development | 4.7.1; 4.7.2; 4.7.3; 4.7.4; 4.7.5; 4.7.6; 7.2.1; 7.2.2
FEAT-153 | POS App | E05 F&B Operations & POS | Kitchen Display And Inventory Sync | Kitchen Display And Inventory Sync | Covers 5 matrix requirement(s). The system should allow send special request comments/directions on the kitchen display/printers for the kitchen preparation guest requests/inputs. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for F&B Operations & POS | P2 - Should | High | 17 | M3 - Business Features | Phase 3 - Development | 10.1.1; 10.1.2; 10.1.3; 10.1.4; 10.1.5
FEAT-154 | POS App | E05 F&B Operations & POS | Wallet | Wallet | Covers 3 matrix requirement(s). The system should be able to work with kitchen displays, bump bar, kitchen printers and accept kitchen respective devices. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for F&B Operations & POS | P2 - Should | Low | 3 | M3 - Business Features | Phase 3 - Development | 5.2.1; 5.2.2; 6.1.29
FEAT-155 | POS App | E05 F&B Operations & POS | Sales Channels | Sales Channels | Covers 1 matrix requirement(s). System shall allow guests to purchase food and beverage items through self-service kiosks. The kiosk shall support menu browsing, product customization, combo meals, upsell recommendations, promotions… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for F&B Operations & POS · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 11 | M4 - Integrations | Phase 4 - Integration | 2.1.32
FEAT-156 | POS App | E05 F&B Operations & POS | Bundles | Bundles | Covers 1 matrix requirement(s). Recommend actions to reduce waste and spoilage. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for F&B Operations & POS · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 11 | M4 - Integrations | Phase 4 - Integration | 4.1.19
FEAT-157 | POS App | E05 F&B Operations & POS | Api Business Coverage | Api Business Coverage | Covers 1 matrix requirement(s). APIs shall support menu retrieval, order creation, order status, kitchen status, inventory updates and promotions. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for F&B Operations & POS | P2 - Should | Medium | 6 | M3 - Business Features | Phase 3 - Development | 13.3.9
FEAT-158 | POS App | E05 F&B Operations & POS | Digital Waivers And Signature Management | Digital Waivers And Signature Management | Covers 1 matrix requirement(s). Medical Declaration Forms System shall support collection of medical information, allergies, health declarations, emergency contacts, and special requirements when permitted by organizational policies… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for F&B Operations & POS | P2 - Should | Medium | 6 | M3 - Business Features | Phase 3 - Development | 22.12.16
FEAT-159 | POS App | E06 Retail Operations & POS | Wallet | Wallet | Covers 59 matrix requirement(s). The system should share all transactions and receipts generated in the system with the external e-invoicing solution. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Retail Operations & POS · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 103 | M4 - Integrations | Phase 4 - Integration | 6.1.1; 6.1.4; 6.1.5; 6.1.6; 6.1.7; 6.1.8; 6.1.10; 6.1.11 … (+51 more)
FEAT-160 | POS App | E06 Retail Operations & POS | Upsell And Cross-Sell | Upsell And Cross-Sell | Covers 4 matrix requirement(s). The system should allow multi-store retailing where the stores are connected with the inventory information of other stores. This should allow the guests to order items which are out of stock in the c… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Retail Operations & POS | P2 - Should | Medium | 9 | M3 - Business Features | Phase 3 - Development | 4.4.9; 4.4.10; 4.4.11; 4.4.12
FEAT-161 | POS App | E06 Retail Operations & POS | Authentication And Login | Authentication And Login | Covers 4 matrix requirement(s). Merchandise Catalog - System shall provide merchandise browsing. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Retail Operations & POS | P2 - Should | Medium | 9 | M3 - Business Features | Phase 3 - Development | 19.2.51; 19.2.52; 19.2.53; 19.2.54
FEAT-162 | POS App | E06 Retail Operations & POS | Newsletter And Email Marketing | Newsletter And Email Marketing | Covers 3 matrix requirement(s). AI Subject Line Generation AI shall generate and recommend subject lines optimized for open rates, click-through rates, and conversion performance. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Retail Operations & POS · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 14 | M4 - Integrations | Phase 4 - Integration | 22.4.10; 22.4.15; 22.4.18
FEAT-163 | POS App | E06 Retail Operations & POS | Inventory Management | Inventory Management | Covers 2 matrix requirement(s). SKU Management - System shall support SKU management. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Retail Operations & POS | P2 - Should | Medium | 7 | M3 - Business Features | Phase 3 - Development | 15.1.3; 15.1.6
FEAT-164 | POS App | E06 Retail Operations & POS | Notifications And Messaging | Notifications And Messaging | Covers 2 matrix requirement(s). Notification Delivery Tracking System shall track delivery status, failures, retries, opens, clicks, read receipts, engagement metrics, and communication outcomes. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Retail Operations & POS | P2 - Should | Low | 3 | M3 - Business Features | Phase 3 - Development | 22.9.19; 22.9.24
FEAT-165 | POS App | E06 Retail Operations & POS | Promotions | Promotions | Covers 1 matrix requirement(s). Cart-level promotions & bundle logic (e.g., “Buy 4 Pay 3”, multi-park family packs) applied automatically at checkout, without new SKUs | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Retail Operations & POS | P2 - Should | Medium | 6 | M3 - Business Features | Phase 3 - Development | 3.6.34
FEAT-166 | POS App | E06 Retail Operations & POS | Accounting | Accounting | Covers 1 matrix requirement(s). The system should be able to store account information for each Revenue Account by Item or Item Type (Merchandise, etc.). At minimum, the below fields should be included for storage: - Company I Attra… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Retail Operations & POS | P2 - Should | Medium | 6 | M3 - Business Features | Phase 3 - Development | 5.7.3
FEAT-167 | POS App | E06 Retail Operations & POS | Seat Map Import | Seat Map Import | Covers 1 matrix requirement(s). One-Click Publishing Publish seating map. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Retail Operations & POS | P2 - Should | Medium | 6 | M3 - Business Features | Phase 3 - Development | 21.2.16
FEAT-168 | POS App | E06 Retail Operations & POS | Seo Management And Optimization | Seo Management And Optimization | Covers 1 matrix requirement(s). SEO Analytics Dashboard System shall provide dashboards showing indexed pages, keyword rankings, organic traffic, click-through rates, conversions, search performance, and revenue generated from organ… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Retail Operations & POS | P2 - Should | Low | 2 | M3 - Business Features | Phase 3 - Development | 22.11.10
FEAT-169 | Server Side / Backend | E07 Inventory & Procurement | Inventory Management | Inventory Management | Covers 36 matrix requirement(s). Inventory Item Master - System shall support centralized inventory item management. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | High | 67 | M3 - Business Features | Phase 3 - Development | 15.1.1; 15.1.2; 15.1.4; 15.1.5; 15.1.7; 15.1.8; 15.1.9; 15.1.10 … (+28 more)
FEAT-170 | Server Side / Backend | E07 Inventory & Procurement | Fandb And Retail Offers And Promotions | Fandb And Retail Offers And Promotions | Covers 26 matrix requirement(s). The system should be able to sync all the products and associated information from the inventory management on real-time or timed intervals, to be able to scan/search for the product and complete the … | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | High | 51 | M3 - Business Features | Phase 3 - Development | 4.5.1; 4.5.2; 4.5.4; 4.5.5; 4.5.6; 4.5.7; 4.5.8; 4.5.9 … (+18 more)
FEAT-171 | Server Side / Backend | E07 Inventory & Procurement | Warehouse Management | Warehouse Management | Covers 22 matrix requirement(s). Warehouse Master - System shall support warehouse master management. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 44 | M4 - Integrations | Phase 4 - Integration | 15.2.1; 15.2.2; 15.2.3; 15.2.4; 15.2.5; 15.2.6; 15.2.7; 15.2.8 … (+14 more)
FEAT-172 | Server Side / Backend | E07 Inventory & Procurement | Procurement | Procurement | Covers 18 matrix requirement(s). Supplier Master - System shall support supplier management. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 21 | M3 - Business Features | Phase 3 - Development | 15.3.1; 15.3.2; 15.3.3; 15.3.4; 15.3.5; 15.3.6; 15.3.7; 15.3.8 … (+10 more)
FEAT-173 | Server Side / Backend | E07 Inventory & Procurement | Upsell And Cross-Sell | Upsell And Cross-Sell | Covers 11 matrix requirement(s). The system should be able to change transaction status to Refunded after the Refund transaction is posted and the same needs to be updated in inventory as well | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 27 | M4 - Integrations | Phase 4 - Integration | 4.4.6; 4.4.13; 4.4.14; 4.4.15; 4.4.16; 4.4.17; 4.4.18; 4.4.19 … (+3 more)
FEAT-174 | Server Side / Backend | E07 Inventory & Procurement | Enterprise Features | Enterprise Features | Covers 11 matrix requirement(s). Tenant-Specific Inventory - System shall support tenant-specific inventory. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 15 | M3 - Business Features | Phase 3 - Development | 15.5.1; 15.5.2; 15.5.3; 15.5.4; 15.5.5; 15.5.6; 15.5.7; 15.5.8 … (+3 more)
FEAT-175 | Server Side / Backend | E07 Inventory & Procurement | Inventory Planning | Inventory Planning | Covers 9 matrix requirement(s). Inventory Demand Forecasting - System shall forecast inventory demand. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 23 | M4 - Integrations | Phase 4 - Integration | 15.4.1; 15.4.2; 15.4.3; 15.4.4; 15.4.5; 15.4.6; 15.4.7; 15.4.8 … (+1 more)
FEAT-176 | Server Side / Backend | E07 Inventory & Procurement | Device Inventory | Device Inventory | Covers 6 matrix requirement(s). Device Inventory Management - System shall maintain device inventories. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 10 | M3 - Business Features | Phase 3 - Development | 16.2.7; 16.2.8; 16.2.9; 16.2.10; 16.2.11; 16.2.12
FEAT-177 | Server Side / Backend | E07 Inventory & Procurement | Spare Parts And Procurement | Spare Parts And Procurement | Covers 5 matrix requirement(s). Spare Parts Management - System shall support maintenance spare parts management. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | High | 17 | M3 - Business Features | Phase 3 - Development | 17.6.1; 17.6.2; 17.6.3; 17.6.4; 17.6.5
FEAT-178 | POS App | E07 Inventory & Procurement | Sales Channels | Sales Channels | Covers 4 matrix requirement(s). The system should provide real-time notifications for stock replenishment of wearables/consumables (e.g. receipt roll) in the POS and self-service kiosks. Entry of new stock received should be support… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Inventory & Procurement | P2 - Should | High | 15 | M3 - Business Features | Phase 3 - Development | 2.1.12; 2.1.14; 2.1.26; 2.1.33
FEAT-179 | Server Side / Backend | E07 Inventory & Procurement | Pricing | Pricing | Covers 4 matrix requirement(s). Selling Event with a seat map, shared inventory with onsite sales. For non-dated tickets, customers must reserve an entry time after completing the purchase | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 15 | M4 - Integrations | Phase 4 - Integration | 2.7.2; 2.7.27; 2.7.53; 2.7.54
FEAT-180 | Mobile App | E07 Inventory & Procurement | Inventory And Stock Management | Inventory And Stock Management | Covers 4 matrix requirement(s). Inventory Lookup - Users shall view inventory availability. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Inventory & Procurement | P2 - Should | Medium | 9 | M3 - Business Features | Phase 3 - Development | 18.7.1; 18.7.2; 18.7.3; 18.7.4
FEAT-181 | Server Side / Backend | E07 Inventory & Procurement | Ticket Resale Marketplace | Ticket Resale Marketplace | Covers 3 matrix requirement(s). System shall maintain real-time resale inventory and synchronize resale inventory with ticket ownership records. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 14 | M4 - Integrations | Phase 4 - Integration | 1.6.5; 1.6.18; 1.6.19
FEAT-182 | Server Side / Backend | E07 Inventory & Procurement | Ticket Types | Ticket Types | Covers 2 matrix requirement(s). System shall support dynamic adjustment of ticket inventory and capacity based on demand forecasts, operational capacity and business rules. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 12 | M4 - Integrations | Phase 4 - Integration | 1.1.32; 1.1.39
FEAT-183 | Server Side / Backend | E07 Inventory & Procurement | Api Business Coverage | Api Business Coverage | Covers 2 matrix requirement(s). APIs shall support ticket creation, modification, cancellation, exchange, upgrade, validation, inventory, availability and pricing operations. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 7 | M3 - Business Features | Phase 3 - Development | 13.3.2; 13.3.10
FEAT-184 | Server Side / Backend | E07 Inventory & Procurement | Resource Management | Resource Management | Covers 1 matrix requirement(s). The system should allow check out & check in feature for rental resources. For example, towels in the water park. Inventory management of these resources should be handled in the system. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 6 | M3 - Business Features | Phase 3 - Development | 1.2.8
FEAT-185 | Server Side / Backend | E07 Inventory & Procurement | Event Management | Event Management | Covers 1 matrix requirement(s). System shall support sponsor packages, sponsor entitlements, sponsorship inventory and sponsor reporting. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Low | 2 | M3 - Business Features | Phase 3 - Development | 1.3.24
FEAT-186 | Server Side / Backend | E07 Inventory & Procurement | Call Center Sales | Call Center Sales | Covers 1 matrix requirement(s). Selling Event with a seat map, shared inventory with onsite sales. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | High | 11 | M3 - Business Features | Phase 3 - Development | 2.6.31
FEAT-187 | Server Side / Backend | E07 Inventory & Procurement | Ticket Media | Ticket Media | Covers 1 matrix requirement(s). The system shall track inventory levels of RFID cards, wristbands, printed tickets, NFC cards, and other physical media across locations and warehouses. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 6 | M3 - Business Features | Phase 3 - Development | 2.16.16
FEAT-188 | POS App | E07 Inventory & Procurement | Access Control System | Access Control System | Covers 1 matrix requirement(s). The access control can be operated with the hardware selected by the venue. Hardware includes turnstiles and handheld devices. Any limitation coming from specific hardware must be highlighted and reco… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Inventory & Procurement · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 11 | M4 - Integrations | Phase 4 - Integration | 3.2.74
FEAT-189 | Server Side / Backend | E07 Inventory & Procurement | Bundles | Bundles | Covers 1 matrix requirement(s). Each component within a bundle shall maintain independent inventory, capacity, validity period, redemption rules, and availability. The sale of a bundle must validate the availability of all included … | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 6 | M3 - Business Features | Phase 3 - Development | 3.5.8
FEAT-190 | Server Side / Backend | E07 Inventory & Procurement | Promotions | Promotions | Covers 1 matrix requirement(s). Discounts can be under conditions (dynamic discounts): - early birds, - subject to volume (buy one get one, 4 for 3 …), - subject to the type of tickets or - subject to the customer segment. B2B Compa… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Low | 2 | M3 - Business Features | Phase 3 - Development | 3.6.32
FEAT-191 | POS App | E07 Inventory & Procurement | Wallet | Wallet | Covers 1 matrix requirement(s). The system should be able to extract a report for: 1.Number of repeated visits by Passes 2.Ticketed Footfall( including demographic) 3.Monthly Inventory Consumptions in Units | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Inventory & Procurement | P2 - Should | Low | 2 | M3 - Business Features | Phase 3 - Development | 6.1.62
FEAT-192 | Server Side / Backend | E07 Inventory & Procurement | Dynamic Pricing | Dynamic Pricing | Covers 1 matrix requirement(s). System shall support inventory-based pricing. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 6 | M3 - Business Features | Phase 3 - Development | 8.5.12
FEAT-193 | Server Side / Backend | E07 Inventory & Procurement | Game And Ride Payment And Redemption | Game And Ride Payment And Redemption | Covers 1 matrix requirement(s). The system should allow usage of redemption tickets credits in the digital wallet at redemption counter for prizes. Prizes on redemption counter, skill games, direct pay machines (e.g. cranes) should … | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 6 | M3 - Business Features | Phase 3 - Development | 10.2.4
FEAT-194 | Server Side / Backend | E07 Inventory & Procurement | Seat Revenue Management And Forecasting | Seat Revenue Management And Forecasting | Covers 1 matrix requirement(s). Seat Inventory Forecasting System shall support seat inventory forecasting. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 11 | M4 - Integrations | Phase 4 - Integration | 21.11.3
FEAT-195 | Server Side / Backend | E07 Inventory & Procurement | Seat Reporting And Analytics | Seat Reporting And Analytics | Covers 1 matrix requirement(s). Hold Inventory Reporting System shall support hold inventory reporting. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Low | 2 | M3 - Business Features | Phase 3 - Development | 21.12.6
FEAT-196 | Server Side / Backend | E07 Inventory & Procurement | Campaign Management | Campaign Management | Covers 1 matrix requirement(s). Ticketing Campaigns System shall support campaigns specifically for ticket sales, events, attractions, seat inventory promotions, capacity-driven offers, and last-minute sales. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 6 | M3 - Business Features | Phase 3 - Development | 22.1.12
FEAT-197 | Server Side / Backend | E08 CRM, Marketing & Loyalty | Case Management And Sla | Case Management And Sla | Covers 17 matrix requirement(s). Case Classification System shall support configurable case categories, subcategories, priorities, severity levels, service types, business units, venues, attractions, and departments. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 36 | M4 - Integrations | Phase 4 - Integration | 22.3.2; 22.3.3; 22.3.4; 22.3.5; 22.3.6; 22.3.7; 22.3.8; 22.3.9 … (+9 more)
FEAT-198 | Server Side / Backend | E08 CRM, Marketing & Loyalty | Consent Management | Consent Management | Covers 14 matrix requirement(s). Consent Management Framework System shall provide a centralized framework for collecting, managing, validating, and enforcing guest consent across all modules and communication channels. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 31 | M4 - Integrations | Phase 4 - Integration | 22.13.1; 22.13.3; 22.13.5; 22.13.6; 22.13.8; 22.13.9; 22.13.10; 22.13.11 … (+6 more)
FEAT-199 | Server Side / Backend | E08 CRM, Marketing & Loyalty | Marketing | Marketing | Covers 13 matrix requirement(s). Multi-Site CMS System shall support creation and management of multiple websites, portals, mobile app experiences, microsites, and landing pages from a single centralized CMS platform. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 30 | M4 - Integrations | Phase 4 - Integration | 22.10.1; 22.10.2; 22.10.4; 22.10.9; 22.10.10; 22.10.11; 22.10.13; 22.10.15 … (+5 more)
FEAT-200 | Server Side / Backend | E08 CRM, Marketing & Loyalty | Surveys And Feedback | Surveys And Feedback | Covers 12 matrix requirement(s). Multi-Format Questions Surveys shall support multiple question types including single choice, multiple choice, rating scales, NPS scores, text responses, rankings, matrices, images, file uploads, and … | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 28 | M4 - Integrations | Phase 4 - Integration | 22.7.3; 22.7.7; 22.7.9; 22.7.10; 22.7.11; 22.7.13; 22.7.14; 22.7.16 … (+4 more)
FEAT-201 | Server Side / Backend | E08 CRM, Marketing & Loyalty | Omnichannel Communications And Ai Chatbot | Omnichannel Communications And Ai Chatbot | Covers 12 matrix requirement(s). Omnichannel Inbox System shall provide a centralized inbox for managing guest conversations from WhatsApp, Web Chat, Mobile App Chat, Facebook Messenger, Instagram, Email, SMS, and future supported ch… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 28 | M4 - Integrations | Phase 4 - Integration | 22.8.1; 22.8.2; 22.8.4; 22.8.5; 22.8.12; 22.8.16; 22.8.17; 22.8.18 … (+4 more)
FEAT-202 | Server Side / Backend | E08 CRM, Marketing & Loyalty | Audience Segmentation | Audience Segmentation | Covers 12 matrix requirement(s). Static Segments System shall support manually maintained static segments for operational, marketing, and reporting purposes. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 28 | M4 - Integrations | Phase 4 - Integration | 22.14.3; 22.14.5; 22.14.7; 22.14.9; 22.14.10; 22.14.11; 22.14.12; 22.14.16 … (+4 more)
FEAT-203 | Server Side / Backend | E08 CRM, Marketing & Loyalty | Loyalty | Loyalty | Covers 11 matrix requirement(s). The system should have the ability to integrate and exchange client information with a loyalty point system which will manage the loyalty points credited on to the loyalty account as per the offerings… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | High | 27 | M3 - Business Features | Phase 3 - Development | 5.4.1; 5.4.4; 5.4.6; 5.4.7; 5.4.8; 5.4.16; 5.4.17; 5.4.18 … (+3 more)
FEAT-204 | Server Side / Backend | E08 CRM, Marketing & Loyalty | Reviews And Ratings | Reviews And Ratings | Covers 11 matrix requirement(s). Configurable Rating Framework System shall support configurable rating scales including 5-star ratings, NPS scores, satisfaction ratings, thumbs-up/down, custom scoring models, and category-based rati… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 27 | M4 - Integrations | Phase 4 - Integration | 22.5.3; 22.5.5; 22.5.7; 22.5.9; 22.5.11; 22.5.12; 22.5.13; 22.5.14 … (+3 more)
FEAT-205 | Server Side / Backend | E08 CRM, Marketing & Loyalty | Notifications And Messaging | Notifications And Messaging | Covers 11 matrix requirement(s). Notification Template Management System shall provide centralized management of notification templates for email, SMS, WhatsApp, push notifications, mobile app notifications, web notifications, and fu… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 27 | M4 - Integrations | Phase 4 - Integration | 22.9.1; 22.9.5; 22.9.6; 22.9.7; 22.9.8; 22.9.17; 22.9.18; 22.9.20 … (+3 more)
FEAT-206 | Server Side / Backend | E08 CRM, Marketing & Loyalty | Guest Profiles And Data Management | Guest Profiles And Data Management | Covers 9 matrix requirement(s). Guest Master Record System shall automatically create and maintain a master guest record that serves as the primary source of truth for all guest-related information across the platform. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 23 | M4 - Integrations | Phase 4 - Integration | 22.2.2; 22.2.4; 22.2.5; 22.2.9; 22.2.16; 22.2.21; 22.2.22; 22.2.27 … (+1 more)
FEAT-207 | Server Side / Backend | E08 CRM, Marketing & Loyalty | Newsletter And Email Marketing | Newsletter And Email Marketing | Covers 7 matrix requirement(s). Subscription Management Guests shall be able to subscribe, unsubscribe, manage preferences, select communication categories, and update consent settings through self-service preference centers. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 20 | M4 - Integrations | Phase 4 - Integration | 22.4.5; 22.4.6; 22.4.11; 22.4.13; 22.4.14; 22.4.17; 22.4.20
FEAT-208 | Server Side / Backend | E08 CRM, Marketing & Loyalty | Campaign Management | Campaign Management | Covers 6 matrix requirement(s). Campaign Creation System shall allow authorized users to create marketing campaigns across email, SMS, WhatsApp, push notifications, mobile app, website banners, social media integrations, and third-p… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 19 | M4 - Integrations | Phase 4 - Integration | 22.1.1; 22.1.3; 22.1.14; 22.1.17; 22.1.18; 22.1.20
FEAT-209 | Server Side / Backend | E08 CRM, Marketing & Loyalty | Gamification And Loyalty | Gamification And Loyalty | Covers 6 matrix requirement(s). Family Challenges System shall support family-based challenges where multiple linked family members can contribute toward shared goals, rewards, achievements, and engagement activities. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 19 | M4 - Integrations | Phase 4 - Integration | 22.6.7; 22.6.11; 22.6.14; 22.6.15; 22.6.18; 22.6.19
FEAT-210 | Server Side / Backend | E08 CRM, Marketing & Loyalty | Seo Management And Optimization | Seo Management And Optimization | Covers 6 matrix requirement(s). AI SEO Optimization AI shall recommend SEO titles, descriptions, keywords, content improvements, internal linking opportunities, and search ranking enhancements based on page content and search trends… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 19 | M4 - Integrations | Phase 4 - Integration | 22.11.3; 22.11.6; 22.11.7; 22.11.8; 22.11.11; 22.11.12
FEAT-211 | Server Side / Backend | E08 CRM, Marketing & Loyalty | Recommendation Engine | Recommendation Engine | Covers 3 matrix requirement(s). System shall provide email campaign recommendations. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 14 | M4 - Integrations | Phase 4 - Integration | 8.6.11; 8.6.15; 8.6.17
FEAT-212 | Server Side / Backend | E08 CRM, Marketing & Loyalty | Bi And Reporting | Bi And Reporting | Covers 3 matrix requirement(s). System shall provide marketing dashboards. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | High | 14 | M3 - Business Features | Phase 3 - Development | 8.7.5; 8.7.9; 8.7.34
FEAT-213 | Mobile App | E08 CRM, Marketing & Loyalty | Authentication And Login | Authentication And Login | Covers 3 matrix requirement(s). Loyalty Balance - System shall display loyalty balances. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for CRM, Marketing & Loyalty | P2 - Should | Low | 3 | M3 - Business Features | Phase 3 - Development | 19.2.43; 19.2.44; 19.2.70
FEAT-214 | Server Side / Backend | E08 CRM, Marketing & Loyalty | Profile Management | Profile Management | Covers 2 matrix requirement(s). Maintain auditable consent records for Email, SMS, WhatsApp, Push Notifications, Marketing Communications, Privacy Policies, Terms & Conditions, and GDPR compliance. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Low | 3 | M3 - Business Features | Phase 3 - Development | 5.3.18; 5.3.23
FEAT-215 | Server Side / Backend | E08 CRM, Marketing & Loyalty | Api Business Coverage | Api Business Coverage | Covers 2 matrix requirement(s). APIs shall support point accrual, point redemption, balance inquiry, loyalty tier management and rewards retrieval. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 7 | M3 - Business Features | Phase 3 - Development | 13.3.4; 13.3.8
FEAT-216 | Server Side / Backend | E08 CRM, Marketing & Loyalty | Demand Forecasting | Demand Forecasting | Covers 1 matrix requirement(s). System shall forecast revenue by customer segment. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 11 | M4 - Integrations | Phase 4 - Integration | 8.2.27
FEAT-217 | Server Side / Backend | E08 CRM, Marketing & Loyalty | Fraud Detection | Fraud Detection | Covers 1 matrix requirement(s). System shall support fraud case management. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 11 | M4 - Integrations | Phase 4 - Integration | 8.3.51
FEAT-218 | Server Side / Backend | E08 CRM, Marketing & Loyalty | Operations Command Center | Operations Command Center | Covers 1 matrix requirement(s). System shall provide real-time visibility of incidents, hazards, complaints, emergencies, and operational disruptions. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | High | 11 | M3 - Business Features | Phase 3 - Development | 8.9.5
FEAT-219 | Server Side / Backend | E09 Membership & Subscriptions | Ticket Types | Ticket Types | Covers 19 matrix requirement(s). The system should be able to sell membership passes for an attraction (e.g. annual pass, monthly pass) for configurable duration. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 22 | M3 - Business Features | Phase 3 - Development | 1.1.6; 1.1.9; 1.1.23; 1.1.31; 1.1.38; 1.1.44; 1.1.93; 1.1.94 … (+11 more)
FEAT-220 | Server Side / Backend | E09 Membership & Subscriptions | Membership | Membership | Covers 14 matrix requirement(s). For all sales at POS, it is possible to have an offline mode. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | High | 31 | M3 - Business Features | Phase 3 - Development | 2.14.2; 2.14.3; 2.14.4; 2.14.5; 2.14.6; 2.14.11; 2.14.13; 2.14.14 … (+6 more)
FEAT-221 | Server Side / Backend | E09 Membership & Subscriptions | Portfolio And Entitlement Management | Portfolio And Entitlement Management | Covers 11 matrix requirement(s). Support purchase, ownership, management, and consumption of multiple tickets, passes, memberships, and entitlements under a single portfolio. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 15 | M3 - Business Features | Phase 3 - Development | 5.5.1; 5.5.2; 5.5.5; 5.5.7; 5.5.8; 5.5.11; 5.5.12; 5.5.14 … (+3 more)
FEAT-222 | Server Side / Backend | E09 Membership & Subscriptions | Guest Profiles And Data Management | Guest Profiles And Data Management | Covers 9 matrix requirement(s). Household & Family Relationships System shall support linking family members, dependents, guardians, spouses, and household relationships while maintaining individual profiles and permissions. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 23 | M4 - Integrations | Phase 4 - Integration | 22.2.6; 22.2.7; 22.2.8; 22.2.10; 22.2.12; 22.2.20; 22.2.23; 22.2.24 … (+1 more)
FEAT-223 | Server Side / Backend | E09 Membership & Subscriptions | License Enforcement And Renewal | License Enforcement And Renewal | Covers 8 matrix requirement(s). License Generation - System shall generate subscription licenses. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 12 | M3 - Business Features | Phase 3 - Development | 20.5.1; 20.5.2; 20.5.3; 20.5.4; 20.5.5; 20.5.6; 20.5.7; 20.5.8
FEAT-224 | Server Side / Backend | E09 Membership & Subscriptions | Digital Waivers And Signature Management | Digital Waivers And Signature Management | Covers 8 matrix requirement(s). Multi-Activity Waivers System shall support different waiver templates for different attractions, events, activities, memberships, venues, products, and risk categories. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | High | 22 | M3 - Business Features | Phase 3 - Development | 22.12.2; 22.12.3; 22.12.5; 22.12.6; 22.12.8; 22.12.9; 22.12.11; 22.12.13
FEAT-225 | Server Side / Backend | E09 Membership & Subscriptions | Loyalty | Loyalty | Covers 7 matrix requirement(s). Support configurable loyalty tiers and progression rules. System shall support configurable loyalty tiers such as Bronze, Silver, Gold, Platinum, VIP, or client-defined tiers. Tier progression shall b… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 20 | M4 - Integrations | Phase 4 - Integration | 5.4.9; 5.4.11; 5.4.12; 5.4.20; 5.4.21; 5.4.22; 5.4.24
FEAT-226 | Mobile App | E09 Membership & Subscriptions | Authentication And Login | Authentication And Login | Covers 6 matrix requirement(s). Membership Purchase - System shall support membership purchases. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Membership & Subscriptions | P2 - Should | Medium | 10 | M3 - Business Features | Phase 3 - Development | 19.2.23; 19.2.24; 19.2.25; 19.2.27; 19.2.28; 19.2.81
FEAT-227 | Server Side / Backend | E09 Membership & Subscriptions | Gamification And Loyalty | Gamification And Loyalty | Covers 6 matrix requirement(s). Challenge Management System shall allow administrators to create configurable challenges, missions, quests, activities, and engagement campaigns based on visits, purchases, attendance, loyalty actions… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | High | 19 | M3 - Business Features | Phase 3 - Development | 22.6.1; 22.6.6; 22.6.8; 22.6.10; 22.6.12; 22.6.20
FEAT-228 | Server Side / Backend | E09 Membership & Subscriptions | Digital Waiver Management | Digital Waiver Management | Covers 5 matrix requirement(s). The system should allow definition of a transaction fee as a fixed value or a percentage based value dependent on the ticket price. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 9 | M3 - Business Features | Phase 3 - Development | 2.10.3; 2.15.4; 2.15.5; 2.15.8; 2.15.14
FEAT-229 | Server Side / Backend | E09 Membership & Subscriptions | Access Control System | Access Control System | Covers 5 matrix requirement(s). The system should be able to validate tickets and membership passes with different rules based on entitlements, manage black and white list of tickets. Upon a scanning a valid ticket, the system shoul… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | High | 17 | M3 - Business Features | Phase 3 - Development | 3.2.6; 3.2.9; 3.2.19; 3.2.43; 3.3.9
FEAT-230 | Server Side / Backend | E09 Membership & Subscriptions | Surveys And Feedback | Surveys And Feedback | Covers 5 matrix requirement(s). Survey Builder System shall provide a drag-and-drop survey builder allowing administrators to create questionnaires, feedback forms, operational surveys, satisfaction surveys, event surveys, membershi… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | High | 17 | M3 - Business Features | Phase 3 - Development | 22.7.1; 22.7.2; 22.7.4; 22.7.8; 22.7.15
FEAT-231 | Server Side / Backend | E09 Membership & Subscriptions | Marketing | Marketing | Covers 5 matrix requirement(s). Multi-Brand Management System shall support multiple brands, venues, attractions, destinations, events, and business units from a single deployment while maintaining independent branding and content. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 9 | M3 - Business Features | Phase 3 - Development | 22.10.3; 22.10.6; 22.10.12; 22.10.24; 22.10.27
FEAT-232 | Server Side / Backend | E09 Membership & Subscriptions | Virtual Queue | Virtual Queue | Covers 4 matrix requirement(s). Support First-Come-First-Served, Virtual Queue, Fast Pass, VIP Queue, Express Queue, Group Queue, Membership Queue, Accessibility Queue, and Staff Queue. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 9 | M3 - Business Features | Phase 3 - Development | 5.6.1; 5.6.5; 5.6.7; 5.6.10
FEAT-233 | Mobile App | E09 Membership & Subscriptions | Ticket And Membership Scanning | Ticket And Membership Scanning | Covers 4 matrix requirement(s). Ticket Scanning - Users shall scan tickets. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Membership & Subscriptions | P2 - Should | Medium | 9 | M3 - Business Features | Phase 3 - Development | 18.8.1; 18.8.2; 18.8.3; 18.8.4
FEAT-234 | Server Side / Backend | E09 Membership & Subscriptions | Consent Management | Consent Management | Covers 4 matrix requirement(s). Consent Capture Workflows Consent shall be captured through website registrations, ticket purchases, memberships, mobile applications, surveys, waivers, kiosks, POS, call center interactions, and API … | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | High | 15 | M3 - Business Features | Phase 3 - Development | 22.13.4; 22.13.7; 22.13.12; 22.13.15
FEAT-235 | Server Side / Backend | E09 Membership & Subscriptions | Audience Segmentation | Audience Segmentation | Covers 4 matrix requirement(s). Dynamic Segments System shall support real-time dynamic segments that automatically update when guest attributes, behaviors, purchases, memberships, loyalty status, or engagement activities change. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 15 | M4 - Integrations | Phase 4 - Integration | 22.14.2; 22.14.6; 22.14.13; 22.14.20
FEAT-236 | POS App | E09 Membership & Subscriptions | Front Gate Sales | Front Gate Sales | Covers 3 matrix requirement(s). The POS can be connected to a ZEBRA printer or datamax printer or Evolis, for annual pass (it is expected to have the list of plastic card pass printing hardware compatible) | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Membership & Subscriptions | P2 - Should | Low | 3 | M3 - Business Features | Phase 3 - Development | 2.13.10; 2.13.14; 2.13.32
FEAT-237 | Server Side / Backend | E09 Membership & Subscriptions | Newsletter And Email Marketing | Newsletter And Email Marketing | Covers 3 matrix requirement(s). Dynamic Personalization Newsletter content shall automatically personalize based on guest profile information including name, language, location, membership status, loyalty tier, interests, previous p… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 8 | M3 - Business Features | Phase 3 - Development | 22.4.3; 22.4.4; 22.4.19
FEAT-238 | Server Side / Backend | E09 Membership & Subscriptions | Reviews And Ratings | Reviews And Ratings | Covers 3 matrix requirement(s). Category-Based Reviews Guests shall be able to rate specific areas such as attractions, events, facilities, staff, food and beverage, retail, cleanliness, accessibility, membership experience, mobile … | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | High | 14 | M3 - Business Features | Phase 3 - Development | 22.5.4; 22.5.6; 22.5.16
FEAT-239 | Server Side / Backend | E09 Membership & Subscriptions | Omnichannel Communications And Ai Chatbot | Omnichannel Communications And Ai Chatbot | Covers 3 matrix requirement(s). Membership Integration Guests shall be able to purchase, renew, upgrade, freeze, or inquire about memberships through supported chat channels. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 14 | M4 - Integrations | Phase 4 - Integration | 22.8.8; 22.8.14; 22.8.15
FEAT-240 | Server Side / Backend | E09 Membership & Subscriptions | Call Center Sales | Call Center Sales | Covers 2 matrix requirement(s). System shall allow guests to save tickets, memberships, events, packages, add-ons, F&B items, retail products, and experiences to a wishlist for future purchase. Wishlist items shall remain linked to … | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 12 | M4 - Integrations | Phase 4 - Integration | 2.6.44; 2.6.46
FEAT-241 | Server Side / Backend | E09 Membership & Subscriptions | Order Management | Order Management | Covers 2 matrix requirement(s). Annual Pass Products 1) Customers must first fill in personal information via the annual pass registration page or can go to the ticket counter onsite to purchase Annual Pass Ticket 2) At the ticketin… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 7 | M3 - Business Features | Phase 3 - Development | 2.12.20; 2.12.33
FEAT-242 | Server Side / Backend | E09 Membership & Subscriptions | Ticket Media | Ticket Media | Covers 2 matrix requirement(s). The system shall automatically determine the most suitable media type based on product type, guest segment, sales channel, membership level, venue rules, and business policies. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 12 | M4 - Integrations | Phase 4 - Integration | 2.16.14; 3.1.9
FEAT-243 | Server Side / Backend | E09 Membership & Subscriptions | Profile Management | Profile Management | Covers 2 matrix requirement(s). Maintain a complete chronological timeline of all guest interactions including ticket purchases, memberships, annual passes, retail purchases, F&B transactions, upgrades, refunds, reservations, access… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 7 | M3 - Business Features | Phase 3 - Development | 5.3.13; 5.3.19
FEAT-244 | Server Side / Backend | E09 Membership & Subscriptions | Reporting And Dashboards | Reporting And Dashboards | Covers 2 matrix requirement(s). Accreditation Renewal - System shall support accreditation renewal workflows. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Low | 3 | M3 - Business Features | Phase 3 - Development | 12.1.37; 12.1.45
FEAT-245 | Server Side / Backend | E09 Membership & Subscriptions | Api Business Coverage | Api Business Coverage | Covers 2 matrix requirement(s). APIs shall support membership creation, renewal, upgrade, downgrade, freeze, entitlement validation and membership status retrieval. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Low | 3 | M3 - Business Features | Phase 3 - Development | 13.3.3; 13.3.14
FEAT-246 | Server Side / Backend | E09 Membership & Subscriptions | Campaign Management | Campaign Management | Covers 2 matrix requirement(s). Dynamic Personalization Campaign content shall support dynamic personalization using guest attributes such as name, language, loyalty tier, membership type, favorite attractions, previous purchases, a… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 7 | M3 - Business Features | Phase 3 - Development | 22.1.7; 22.1.13
FEAT-247 | Server Side / Backend | E09 Membership & Subscriptions | Case Management And Sla | Case Management And Sla | Covers 2 matrix requirement(s). Membership Lifecycle Automation System shall automate membership acquisition, onboarding, benefit education, renewal reminders, upgrade offers, expiration warnings, and win-back campaigns. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 7 | M3 - Business Features | Phase 3 - Development | 22.3.7; 22.3.10
FEAT-248 | Server Side / Backend | E09 Membership & Subscriptions | Seo Management And Optimization | Seo Management And Optimization | Covers 2 matrix requirement(s). Sitemap Management System shall automatically generate and maintain XML sitemaps for websites, events, attractions, products, memberships, landing pages, and content sections. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 7 | M3 - Business Features | Phase 3 - Development | 22.11.4; 22.11.5
FEAT-249 | Server Side / Backend | E09 Membership & Subscriptions | Ticket Resale Marketplace | Ticket Resale Marketplace | Covers 1 matrix requirement(s). System shall support configurable resale eligibility rules based on ticket type, event, venue, attraction, membership level, sales channel, ticket status, purchase source, usage status, and business p… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 6 | M3 - Business Features | Phase 3 - Development | 1.6.2
FEAT-250 | Server Side / Backend | E09 Membership & Subscriptions | Ticket Upgrades | Ticket Upgrades | Covers 1 matrix requirement(s). The system should support upgrade of: - A 1 day ticket to a multi-day ticket or membership pass. - A multi-day ticket to a membership pass. - A single attraction ticket to multiple attraction ticket. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 6 | M3 - Business Features | Phase 3 - Development | 2.11.3
FEAT-251 | Server Side / Backend | E09 Membership & Subscriptions | Portfolio Management | Portfolio Management | Covers 1 matrix requirement(s). The system should provide the ability to move stored credit between portfolios linked to different accounts. For Example: each family member have their own portfolio with the possibility to transfer p… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 6 | M3 - Business Features | Phase 3 - Development | 5.5.3
FEAT-252 | Server Side / Backend | E09 Membership & Subscriptions | Demand Forecasting | Demand Forecasting | Covers 1 matrix requirement(s). System shall forecast membership revenue. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 11 | M4 - Integrations | Phase 4 - Integration | 8.2.31
FEAT-253 | Server Side / Backend | E09 Membership & Subscriptions | Ai Engine | Ai Engine | Covers 1 matrix requirement(s). System shall support semantic search across products, tickets, memberships, documents, knowledge bases, support content, assets, and operational data using vector-based retrieval and relevance ranking… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 6 | M3 - Business Features | Phase 3 - Development | 8.4.39
FEAT-254 | Server Side / Backend | E09 Membership & Subscriptions | Recommendation Engine | Recommendation Engine | Covers 1 matrix requirement(s). System shall provide personalized membership recommendations. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 11 | M4 - Integrations | Phase 4 - Integration | 8.6.2
FEAT-255 | Server Side / Backend | E09 Membership & Subscriptions | Bi And Reporting | Bi And Reporting | Covers 1 matrix requirement(s). System shall provide membership dashboards. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Low | 2 | M3 - Business Features | Phase 3 - Development | 8.7.8
FEAT-256 | Server Side / Backend | E09 Membership & Subscriptions | Operations Command Center | Operations Command Center | Covers 1 matrix requirement(s). System shall provide a centralized operational dashboard displaying real-time information across ticketing, access control, attractions, queues, memberships, POS, retail, F&B, devices, incidents, and … | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | High | 11 | M3 - Business Features | Phase 3 - Development | 8.9.1
FEAT-257 | Server Side / Backend | E09 Membership & Subscriptions | Accounting | Accounting | Covers 1 matrix requirement(s). Membership Cancellation Approval Workflow - System shall support approval workflows for membership cancellation requests. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 6 | M3 - Business Features | Phase 3 - Development | 11.1.34
FEAT-258 | Server Side / Backend | E09 Membership & Subscriptions | Subscription Management | Subscription Management | Covers 1 matrix requirement(s). Subscription Renewal - System shall support automatic renewals. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 6 | M3 - Business Features | Phase 3 - Development | 20.2.4
FEAT-259 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Event Management | Event Management | Covers 39 matrix requirement(s). The system should allow creation of events such as performances, workshops, activities or guided-tours. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 71 | M4 - Integrations | Phase 4 - Integration | 1.3.1; 1.3.3; 1.3.4; 1.3.5; 1.3.6; 1.3.7; 1.3.8; 1.3.11 … (+31 more)
FEAT-260 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Selection And Assignment | Seat Selection And Assignment | Covers 23 matrix requirement(s). Choose My Seats System shall support choose my seats. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 46 | M4 - Integrations | Phase 4 - Integration | 21.5.1; 21.5.2; 21.5.3; 21.5.4; 21.5.5; 21.5.7; 21.5.8; 21.5.9 … (+15 more)
FEAT-261 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Map Import | Seat Map Import | Covers 16 matrix requirement(s). PDF Seat Map Import Import PDF venue plans. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 35 | M4 - Integrations | Phase 4 - Integration | 21.2.1; 21.2.2; 21.2.3; 21.2.4; 21.2.5; 21.2.6; 21.2.7; 21.2.8 … (+8 more)
FEAT-262 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Resource Management | Resource Management | Covers 12 matrix requirement(s). The system should provide a calendar view for all the resources (e.g. instructors) and associated time slots (e.g. ski school session by an instructor). The calendar should support application of filt… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 28 | M4 - Integrations | Phase 4 - Integration | 1.2.6; 1.2.14; 1.2.17; 1.2.21; 1.2.22; 1.2.40; 1.2.47; 1.2.48 … (+4 more)
FEAT-263 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Call Center Sales | Call Center Sales | Covers 8 matrix requirement(s). The system should support email templates for e-ticket purchase confirmation supporting dynamic parameters. The email templates should be configurable per site, per event | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | High | 22 | M2 - Core Platform | Phase 3 - Development | 2.6.3; 2.6.10; 2.6.15; 2.6.32; 2.6.53; 2.6.55; 2.6.58; 2.6.65
FEAT-264 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Api Business Coverage | Api Business Coverage | Covers 8 matrix requirement(s). APIs shall support access validation, entry events, exit events, occupancy management and access entitlement verification. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | High | 22 | M2 - Core Platform | Phase 3 - Development | 13.3.6; 13.3.18; 13.3.19; 13.3.20; 13.3.21; 13.3.22; 13.3.23; 13.3.24
FEAT-265 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Map Builder | Seat Map Builder | Covers 8 matrix requirement(s). Drag & Drop Venue Builder Visual designer to create venue layouts without coding. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 12 | M2 - Core Platform | Phase 3 - Development | 21.1.1; 21.1.3; 21.1.4; 21.1.5; 21.1.6; 21.1.7; 21.1.8; 21.1.9
FEAT-266 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Holds And Blocks | Seat Holds And Blocks | Covers 8 matrix requirement(s). VIP Seat Holds System shall support vip seat holds. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 12 | M2 - Core Platform | Phase 3 - Development | 21.6.1; 21.6.2; 21.6.3; 21.6.4; 21.6.5; 21.6.6; 21.6.7; 21.6.8
FEAT-267 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Preventive Maintenance Planning | Preventive Maintenance Planning | Covers 7 matrix requirement(s). Maintenance Plans - System shall support preventive maintenance plans. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 11 | M2 - Core Platform | Phase 3 - Development | 17.2.1; 17.2.2; 17.2.3; 17.2.4; 17.2.5; 17.2.6; 17.2.7
FEAT-268 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Layout And Templates | Layout And Templates | Covers 7 matrix requirement(s). Layout Templates System shall support layout templates. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 11 | M2 - Core Platform | Phase 3 - Development | 21.3.1; 21.3.2; 21.3.3; 21.3.4; 21.3.5; 21.3.6; 21.3.7
FEAT-269 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Tracking And Holds | Seat Tracking And Holds | Covers 7 matrix requirement(s). Seat Status Management System shall support seat status management. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 11 | M2 - Core Platform | Phase 3 - Development | 21.4.1; 21.4.2; 21.4.3; 21.4.5; 21.4.6; 21.4.7; 21.4.8
FEAT-270 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Recommendations | Seat Recommendations | Covers 7 matrix requirement(s). Best Seat Recommendations System shall support best seat recommendations. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 20 | M4 - Integrations | Phase 4 - Integration | 21.10.1; 21.10.2; 21.10.3; 21.10.4; 21.10.5; 21.10.6; 21.10.7
FEAT-271 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Product Lifecycle | Product Lifecycle | Covers 6 matrix requirement(s). AI should significantly streamline the creation and configuration of venue seat maps by automating design, validation, categorization, and optimization tasks. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 19 | M4 - Integrations | Phase 4 - Integration | 1.4.22; 1.4.23; 1.4.24; 1.4.25; 1.4.28; 1.4.29
FEAT-272 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Accounting | Accounting | Covers 6 matrix requirement(s). The system allow general ledger revenue rules to be configured to trigger account allocation based on product sale and redemption events. Revenue allocation rules can be defined for all products and s… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 10 | M2 - Core Platform | Phase 3 - Development | 5.7.6; 11.1.24; 11.1.49; 11.1.56; 11.1.64; 11.1.66
FEAT-273 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Reporting And Dashboards | Reporting And Dashboards | Covers 6 matrix requirement(s). Event-Specific Accreditation - System shall support accreditations linked to specific events. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 10 | M2 - Core Platform | Phase 3 - Development | 12.1.38; 12.1.41; 12.1.53; 13.1.19; 13.1.28; 13.1.40
FEAT-274 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Seating Rules And Buffer | Seating Rules And Buffer | Covers 6 matrix requirement(s). Seat Kill Rules System shall support seat kill rules. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 10 | M2 - Core Platform | Phase 3 - Development | 21.7.1; 21.7.2; 21.7.3; 21.7.4; 21.7.5; 21.7.6
FEAT-275 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Platform And Api | Seat Platform And Api | Covers 6 matrix requirement(s). Multi-Tenant Support System shall support multi-tenant support. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 10 | M2 - Core Platform | Phase 3 - Development | 21.13.1; 21.13.2; 21.13.3; 21.13.4; 21.13.5; 21.13.6
FEAT-276 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Ticket Types | Ticket Types | Covers 5 matrix requirement(s). The system should be able to sell time-slot based tickets for attractions. The system should support: - Creation of timeslots for a whole day or for a period - Configuration of capacity for each times… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 9 | M2 - Core Platform | Phase 3 - Development | 1.1.3; 1.1.4; 1.1.40; 1.1.85; 1.1.86
FEAT-277 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Reporting And Analytics | Seat Reporting And Analytics | Covers 5 matrix requirement(s). Seat Occupancy Reporting System shall support seat occupancy reporting. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 9 | M2 - Core Platform | Phase 3 - Development | 21.12.1; 21.12.2; 21.12.3; 21.12.4; 21.12.5
FEAT-278 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Access Control System | Access Control System | Covers 4 matrix requirement(s). The system should be able to expire a ticket if it is not used within a specified time (e.g. 20 minutes) from the admission time specified on the ticket or based on the time of the performance/event. … | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 15 | M4 - Integrations | Phase 4 - Integration | 3.2.10; 3.2.63; 3.2.71; 3.3.18
FEAT-279 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Demand Forecasting | Demand Forecasting | Covers 4 matrix requirement(s). System shall forecast attendance by event. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 15 | M4 - Integrations | Phase 4 - Integration | 8.2.4; 8.2.5; 8.2.24; 8.2.37
FEAT-280 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Accessible Seating | Accessible Seating | Covers 4 matrix requirement(s). Wheelchair Seating System shall support wheelchair seating. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 9 | M2 - Core Platform | Phase 3 - Development | 21.8.1; 21.8.2; 21.8.3; 21.8.4
FEAT-281 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Ticket Resale Marketplace | Ticket Resale Marketplace | Covers 3 matrix requirement(s). System shall prevent duplicate usage, duplicate resale, credential sharing, ticket cloning, and unauthorized ownership changes. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Low | 3 | M2 - Core Platform | Phase 3 - Development | 1.6.9; 1.6.11; 1.6.15
FEAT-282 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Ticket Media | Ticket Media | Covers 3 matrix requirement(s). Dynamic QR Code Supports: 1. Registration: Customers select "Digital Ticket" via the confirmation page, email, or ticket PDF to begin the enrollment process. 2.Activation: After registration, the tick… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 14 | M4 - Integrations | Phase 4 - Integration | 3.1.1; 3.1.3; 3.1.8
FEAT-283 | POS App | E10 Events, Seating & Venue Mapping | Shift Opening And Closing | Shift Opening And Closing | Covers 3 matrix requirement(s). The system should allow automatic closing of a cashier's session after a configurable time period. The supervisor should be notified on closing of the session. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Events, Seating & Venue Mapping | P2 - Should | Low | 3 | M2 - Core Platform | Phase 3 - Development | 5.9.5; 5.9.8; 5.9.9
FEAT-284 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Campaign Management | Campaign Management | Covers 3 matrix requirement(s). Campaign Scheduling System shall support immediate, scheduled, recurring, event-triggered, and timezone-aware campaign execution with configurable send windows and blackout periods. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 14 | M4 - Integrations | Phase 4 - Integration | 22.1.4; 22.1.8; 22.1.16
FEAT-285 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Gamification And Loyalty | Gamification And Loyalty | Covers 3 matrix requirement(s). Digital Badges System shall support creation and management of digital badges that can be awarded to guests for completing activities, visiting attractions, attending events, reaching loyalty mileston… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 8 | M2 - Core Platform | Phase 3 - Development | 22.6.3; 22.6.9; 22.6.16
FEAT-286 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Cash Handling | Cash Handling | Covers 2 matrix requirement(s). The system should only allow one session per user. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Low | 3 | M2 - Core Platform | Phase 3 - Development | 5.8.2; 5.8.9
FEAT-287 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Ai Governance | Ai Governance | Covers 2 matrix requirement(s). System shall prevent unauthorized access to AI functions. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 12 | M4 - Integrations | Phase 4 - Integration | 8.3.74; 8.3.82
FEAT-288 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Recommendation Engine | Recommendation Engine | Covers 2 matrix requirement(s). System shall provide personalized event recommendations. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 12 | M4 - Integrations | Phase 4 - Integration | 8.6.4; 8.6.21
FEAT-289 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Revenue Management And Forecasting | Seat Revenue Management And Forecasting | Covers 2 matrix requirement(s). Seat Demand Forecasting System shall support seat demand forecasting. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 12 | M4 - Integrations | Phase 4 - Integration | 21.11.2; 21.11.4
FEAT-290 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Case Management And Sla | Case Management And Sla | Covers 2 matrix requirement(s). Visual Journey Builder System shall provide a drag-and-drop visual journey builder allowing marketing users to design automated customer journeys using events, conditions, actions, delays, approvals, … | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 12 | M4 - Integrations | Phase 4 - Integration | 22.3.1; 22.3.17
FEAT-291 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Newsletter And Email Marketing | Newsletter And Email Marketing | Covers 2 matrix requirement(s). Newsletter Builder System shall provide a drag-and-drop newsletter designer allowing marketing users to create responsive newsletters without technical knowledge. The editor shall support text blocks,… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Low | 3 | M2 - Core Platform | Phase 3 - Development | 22.4.1; 22.4.12
FEAT-292 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Notifications And Messaging | Notifications And Messaging | Covers 2 matrix requirement(s). Operational Alerts System shall support operational notifications to staff regarding incidents, capacity thresholds, device failures, approvals, escalations, maintenance events, and workflow activitie… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 12 | M4 - Integrations | Phase 4 - Integration | 22.9.15; 22.9.16
FEAT-293 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Marketing | Marketing | Covers 2 matrix requirement(s). AI Mobile App Content Builder AI shall generate mobile app homepages, menus, banners, announcements, event sections, and content structures based on available products and branding. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 12 | M4 - Integrations | Phase 4 - Integration | 22.10.17; 22.10.29
FEAT-294 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Digital Waiver Management | Digital Waiver Management | Covers 1 matrix requirement(s). The system should be to apply a transaction fee to orders for a specific ticket (e.g. Event Ticket). The transaction fee should also be applicable for actions like ticket modification and cancellation… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 6 | M2 - Core Platform | Phase 3 - Development | 2.10.2
FEAT-295 | POS App | E10 Events, Seating & Venue Mapping | Profile Management | Profile Management | Covers 1 matrix requirement(s). Maintain detailed access validation history including gate entries, exits, attraction validations, RFID scans, QR scans, and turnstile events. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Events, Seating & Venue Mapping | P2 - Should | Medium | 6 | M2 - Core Platform | Phase 3 - Development | 5.3.28
FEAT-296 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Loyalty | Loyalty | Covers 1 matrix requirement(s). Reward customers for successful referrals. System shall allow guests to refer new customers and receive rewards when referral conditions are met. Rules shall define referral code, eligibility, reward … | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 11 | M4 - Integrations | Phase 4 - Integration | 5.4.15
FEAT-297 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Portfolio And Entitlement Management | Portfolio And Entitlement Management | Covers 1 matrix requirement(s). Support schools, tour operators, travel agencies, corporate groups, and event organizers. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 6 | M2 - Core Platform | Phase 3 - Development | 5.5.16
FEAT-298 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Ai Configuration Assistant | Ai Configuration Assistant | Covers 1 matrix requirement(s). The AI assistant can configure: Operating hours Performances Blackout periods Special opening hours Example: "Add evening slots from 6 PM to 10 PM every Friday for Ladies Night event." | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 11 | M4 - Integrations | Phase 4 - Integration | 8.8.14
FEAT-299 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Operations Command Center | Operations Command Center | Covers 1 matrix requirement(s). System shall provide dashboards, reports, drill-down analytics, alerts, and historical operational performance analysis. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Low | 2 | M2 - Core Platform | Phase 3 - Development | 8.9.10
FEAT-300 | Cross Platform | E10 Events, Seating & Venue Mapping | Sandbox | Sandbox | Covers 1 matrix requirement(s). Performance Testing - System shall support performance testing. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 6 | M2 - Core Platform | Phase 3 - Development | 13.2.9
FEAT-301 | Cross Platform | E10 Events, Seating & Venue Mapping | Device Monitoring | Device Monitoring | Covers 1 matrix requirement(s). Device Performance Monitoring - System shall monitor device performance. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 6 | M2 - Core Platform | Phase 3 - Development | 16.4.22
FEAT-302 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Device Maintenance | Device Maintenance | Covers 1 matrix requirement(s). Preventive Maintenance - System shall support preventive maintenance schedules. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 6 | M2 - Core Platform | Phase 3 - Development | 16.5.24
FEAT-303 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Maintenance Reporting And Analytics | Maintenance Reporting And Analytics | Covers 1 matrix requirement(s). Asset Performance Reporting - System shall provide asset performance reports. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Low | 2 | M2 - Core Platform | Phase 3 - Development | 17.7.3
FEAT-304 | Mobile App | E10 Events, Seating & Venue Mapping | Authentication And Login | Authentication And Login | Covers 1 matrix requirement(s). Interactive Venue Map - System shall provide interactive venue maps. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Events, Seating & Venue Mapping | P2 - Should | Medium | 6 | M2 - Core Platform | Phase 3 - Development | 19.2.55
FEAT-305 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Reviews And Ratings | Reviews And Ratings | Covers 1 matrix requirement(s). Review Analytics Dashboard System shall provide dashboards displaying review volume, average ratings, sentiment trends, category ratings, response times, unresolved issues, and service performance met… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Low | 2 | M2 - Core Platform | Phase 3 - Development | 22.5.18
FEAT-306 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Omnichannel Communications And Ai Chatbot | Omnichannel Communications And Ai Chatbot | Covers 1 matrix requirement(s). Chat Analytics Dashboard System shall provide analytics including conversation volumes, response times, resolution times, sentiment trends, conversion rates, sales generated, agent performance, and cu… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Low | 2 | M2 - Core Platform | Phase 3 - Development | 22.8.25
FEAT-307 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Seo Management And Optimization | Seo Management And Optimization | Covers 1 matrix requirement(s). SEO Metadata Management System shall allow administrators to manage SEO titles, meta descriptions, keywords, canonical URLs, social sharing metadata, and Open Graph properties for all content, product… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 6 | M2 - Core Platform | Phase 3 - Development | 22.11.1
FEAT-308 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Digital Waivers And Signature Management | Digital Waivers And Signature Management | Covers 1 matrix requirement(s). Event Waiver Management Events shall support event-specific waivers and liability acknowledgements linked directly to event registrations and attendance. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 6 | M2 - Core Platform | Phase 3 - Development | 22.12.14
FEAT-309 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Consent Management | Consent Management | Covers 1 matrix requirement(s). Privacy Incident Tracking System shall support recording, tracking, investigation, and reporting of privacy incidents, consent violations, data access issues, and compliance-related events. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Low | 2 | M2 - Core Platform | Phase 3 - Development | 22.13.18
FEAT-310 | Server Side / Backend | E10 Events, Seating & Venue Mapping | Audience Segmentation | Audience Segmentation | Covers 1 matrix requirement(s). Marketing ROI Dashboard System shall provide dashboards displaying campaign ROI, cost per acquisition, revenue attribution, conversion rates, customer acquisition cost, and lifetime value performance. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Low | 2 | M2 - Core Platform | Phase 3 - Development | 22.14.23
FEAT-311 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Promotions | Promotions | Covers 47 matrix requirement(s). Integration with Identity: Tie QR code validity to user identity (Account ID, email address, or device). | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 84 | M4 - Integrations | Phase 4 - Integration | 3.6.1; 3.6.3; 3.6.4; 3.6.5; 3.6.6; 3.6.7; 3.6.8; 3.6.9 … (+39 more)
FEAT-312 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Dynamic Pricing | Dynamic Pricing | Covers 44 matrix requirement(s). System shall support dynamic ticket pricing. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 79 | M4 - Integrations | Phase 4 - Integration | 8.5.1; 8.5.2; 8.5.3; 8.5.4; 8.5.5; 8.5.6; 8.5.7; 8.5.8 … (+36 more)
FEAT-313 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Pricing | Pricing | Covers 42 matrix requirement(s). For BtoB online sales, the following points shall be available online: | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 76 | M4 - Integrations | Phase 4 - Integration | 2.7.5; 2.7.6; 2.7.7; 2.7.10; 2.7.11; 2.7.12; 2.7.13; 2.7.14 … (+34 more)
FEAT-314 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Bundles | Bundles | Covers 35 matrix requirement(s). Encrypted Payload: QR codes contain encrypted or tokenized identifiers (not raw PII). | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 65 | M4 - Integrations | Phase 4 - Integration | 3.5.1; 3.5.2; 3.5.3; 3.5.4; 3.5.5; 3.5.6; 3.5.7; 3.5.9 … (+27 more)
FEAT-315 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Upsell And Cross-Sell | Upsell And Cross-Sell | Covers 21 matrix requirement(s). The system should be able to support and create bundles managed by external destinations, Online travel aggregators and Hotel chains | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 43 | M4 - Integrations | Phase 4 - Integration | 3.7.1; 3.7.2; 3.7.3; 3.7.4; 3.7.5; 3.7.6; 3.7.7; 3.7.8 … (+13 more)
FEAT-316 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Ai Configuration Assistant | Ai Configuration Assistant | Covers 15 matrix requirement(s). For no-shows, the revenue attached to this ticket is moved from differed to earned revenue AI Discount Assistant: 1) For seasonal, early bird, bulk discounts, last minute discounts: Provide AI-driven … | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 33 | M4 - Integrations | Phase 4 - Integration | 8.1.1; 8.1.2; 8.1.6; 8.8.1; 8.8.2; 8.8.3; 8.8.4; 8.8.5 … (+7 more)
FEAT-317 | POS App | E11 Bundles, Promotions & Pricing | Sales Channels | Sales Channels | Covers 11 matrix requirement(s). The system should store and manage all rules for product compatibility, eligibility and pricing that will be applicable to for each sales channel. These rules will be part of the system and not extern… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Bundles, Promotions & Pricing · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 27 | M4 - Integrations | Phase 4 - Integration | 2.1.3; 2.1.8; 2.1.10; 2.1.11; 2.1.16; 2.1.20; 2.1.22; 2.1.23 … (+3 more)
FEAT-318 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Ticket Upgrades | Ticket Upgrades | Covers 11 matrix requirement(s). The system should provide a service to enable the dynamic composition of the shop cart. The system must provide back all the information in real time, such as the performance availabilities of an even… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 27 | M4 - Integrations | Phase 4 - Integration | 2.9.2; 2.9.6; 2.9.8; 2.9.9; 2.9.10; 2.9.15; 2.9.16; 2.9.17 … (+3 more)
FEAT-319 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Ticket Types | Ticket Types | Covers 10 matrix requirement(s). System shall allow administrators to create reusable ticket templates containing pricing, validity, capacity, access rights, add-ons, restrictions and approval workflows. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 25 | M4 - Integrations | Phase 4 - Integration | 1.1.16; 1.1.17; 1.1.20; 1.1.21; 1.1.28; 1.1.30; 1.1.33; 1.1.35 … (+2 more)
FEAT-320 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Recommendation Engine | Recommendation Engine | Covers 9 matrix requirement(s). System shall provide upsell recommendations. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 23 | M4 - Integrations | Phase 4 - Integration | 8.6.6; 8.6.7; 8.6.30; 8.6.31; 8.6.32; 8.6.33; 8.6.34; 8.6.35 … (+1 more)
FEAT-321 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Fandb And Retail Offers And Promotions | Fandb And Retail Offers And Promotions | Covers 7 matrix requirement(s). Track expiration dates and generate alerts. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 11 | M3 - Business Features | Phase 3 - Development | 4.5.17; 4.5.19; 4.5.23; 4.5.24; 4.5.25; 4.5.27; 4.5.32
FEAT-322 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Marketing | Marketing | Covers 7 matrix requirement(s). Component-Based Design System System shall provide reusable content components including banners, event widgets, ticket widgets, membership widgets, loyalty widgets, galleries, videos, maps, forms, co… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 20 | M4 - Integrations | Phase 4 - Integration | 22.10.5; 22.10.7; 22.10.14; 22.10.19; 22.10.20; 22.10.21; 22.10.22
FEAT-323 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Event Management | Event Management | Covers 6 matrix requirement(s). The system should allow a seating plan to be created for each space. Different type of seats can be configured within the seating plan and a space can have multiple seating arrangements. The system sh… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | High | 19 | M3 - Business Features | Phase 3 - Development | 1.3.9; 1.3.15; 1.3.17; 1.3.18; 1.3.39; 1.3.49
FEAT-324 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Product Lifecycle | Product Lifecycle | Covers 6 matrix requirement(s). System shall maintain version history of all product configurations including pricing, rules, entitlements and capacities. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 19 | M4 - Integrations | Phase 4 - Integration | 1.4.9; 1.4.11; 1.4.13; 1.4.21; 1.4.27; 1.4.30
FEAT-325 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Call Center Sales | Call Center Sales | Covers 6 matrix requirement(s). - Upsells / cross sells functionalities are expected | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 19 | M4 - Integrations | Phase 4 - Integration | 2.6.9; 2.6.11; 2.6.12; 2.6.13; 2.6.17; 2.6.43
FEAT-326 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Loyalty | Loyalty | Covers 6 matrix requirement(s). The system should support loyalty point system to provide access to products, promotions and prices which are meant to be for guests based on their loyalty profile tier and also customize the journey … | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 19 | M4 - Integrations | Phase 4 - Integration | 5.4.5; 5.4.10; 5.4.14; 5.4.23; 5.4.25; 5.4.31
FEAT-327 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Accounting | Accounting | Covers 6 matrix requirement(s). The system should be able to sell multi-attraction and combination tickets with configurable revenue split. Revenue rules should apply financial clearings based on products and client behaviors. The s… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 19 | M4 - Integrations | Phase 4 - Integration | 5.7.7; 5.7.13; 5.7.95; 11.1.7; 11.1.31; 11.1.32
FEAT-328 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Ai Engine | Ai Engine | Covers 6 matrix requirement(s). System shall support AI-assisted promotion configuration. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 10 | M3 - Business Features | Phase 3 - Development | 8.4.31; 8.4.32; 8.4.33; 8.4.34; 8.4.36; 8.4.37
FEAT-329 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Membership | Membership | Covers 5 matrix requirement(s). 1.General Annual card User Journey: 1) Customers need to visit the annual card information registration page to fill in their personal information 2) After the customer arrives at the counter, if the … | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 9 | M3 - Business Features | Phase 3 - Development | 2.14.1; 2.14.8; 2.14.9; 2.14.12; 2.14.23
FEAT-330 | POS App | E11 Bundles, Promotions & Pricing | Front Gate Sales | Front Gate Sales | Covers 3 matrix requirement(s). The discounts,coupon or voucher redeem functionalities shall be available. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Bundles, Promotions & Pricing · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 14 | M4 - Integrations | Phase 4 - Integration | 2.13.22; 2.13.23; 2.13.39
FEAT-331 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Game And Ride Payment And Redemption | Game And Ride Payment And Redemption | Covers 3 matrix requirement(s). Dynamic pricing for games - System should provide an ability to set up peak / nonpeak pricing for all the games / rides based on specific date / time | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 14 | M4 - Integrations | Phase 4 - Integration | 10.2.15; 10.2.16; 10.2.17
FEAT-332 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Campaign Management | Campaign Management | Covers 3 matrix requirement(s). Campaign Templates System shall provide reusable campaign templates for ticket sales, memberships, annual passes, loyalty promotions, events, seasonal promotions, abandoned carts, birthday campaigns, … | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | High | 14 | M3 - Business Features | Phase 3 - Development | 22.1.2; 22.1.9; 22.1.11
FEAT-333 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Case Management And Sla | Case Management And Sla | Covers 3 matrix requirement(s). Cross-Sell & Upsell Automation System shall automatically recommend products, memberships, packages, upgrades, F&B offers, retail items, experiences, and loyalty rewards based on guest behavior and pu… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 14 | M4 - Integrations | Phase 4 - Integration | 22.3.14; 22.3.18; 22.3.20
FEAT-334 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Newsletter And Email Marketing | Newsletter And Email Marketing | Covers 3 matrix requirement(s). Newsletter Templates System shall provide reusable templates for ticket promotions, events, memberships, loyalty campaigns, seasonal campaigns, surveys, announcements, operational updates, and venue c… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 14 | M4 - Integrations | Phase 4 - Integration | 22.4.2; 22.4.7; 22.4.9
FEAT-335 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Ticket Media | Ticket Media | Covers 2 matrix requirement(s). The system should allow configuration of ticket templates. Tickets can have fixed elements and dynamic fields. There should be possibility to insert visuals and 2D codes and hide the price of the tick… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Low | 3 | M3 - Business Features | Phase 3 - Development | 2.16.5; 2.16.8
FEAT-336 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Virtual Queue | Virtual Queue | Covers 2 matrix requirement(s). Support queue privileges based on memberships, annual passes, loyalty tiers, and promotions. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 12 | M4 - Integrations | Phase 4 - Integration | 5.6.34; 5.6.35
FEAT-337 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Ai Governance | Ai Governance | Covers 2 matrix requirement(s). System shall require approval before AI-driven pricing changes. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 7 | M3 - Business Features | Phase 3 - Development | 8.3.61; 8.3.62
FEAT-338 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Api Business Coverage | Api Business Coverage | Covers 2 matrix requirement(s). APIs shall expose pricing calculations, price recommendations and pricing rule management. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 12 | M4 - Integrations | Phase 4 - Integration | 13.3.12; 13.3.13
FEAT-339 | Mobile App | E11 Bundles, Promotions & Pricing | Branding And White-Label Configuration | Branding And White-Label Configuration | Covers 2 matrix requirement(s). Banner Management - System shall support configurable promotional banners. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Bundles, Promotions & Pricing | P2 - Should | Medium | 7 | M3 - Business Features | Phase 3 - Development | 19.1.10; 19.1.11
FEAT-340 | Mobile App | E11 Bundles, Promotions & Pricing | Authentication And Login | Authentication And Login | Covers 2 matrix requirement(s). Dynamic Pricing Display - System shall display dynamic pricing. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Bundles, Promotions & Pricing · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 12 | M4 - Integrations | Phase 4 - Integration | 19.2.22; 19.2.63
FEAT-341 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Seat Revenue Management And Forecasting | Seat Revenue Management And Forecasting | Covers 2 matrix requirement(s). Dynamic Seat Pricing System shall support dynamic seat pricing. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 12 | M4 - Integrations | Phase 4 - Integration | 21.11.1; 21.11.5
FEAT-342 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Reviews And Ratings | Reviews And Ratings | Covers 2 matrix requirement(s). AI Topic Detection AI shall automatically identify recurring topics including pricing, staff service, wait times, cleanliness, ticketing experience, memberships, loyalty programs, food quality, events… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 12 | M4 - Integrations | Phase 4 - Integration | 22.5.10; 22.5.15
FEAT-343 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Notifications And Messaging | Notifications And Messaging | Covers 2 matrix requirement(s). Loyalty Notifications System shall automatically notify guests regarding points earned, points redeemed, tier changes, reward availability, promotions, point expirations, and loyalty campaigns. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Low | 3 | M3 - Business Features | Phase 3 - Development | 22.9.10; 22.9.14
FEAT-344 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Seo Management And Optimization | Seo Management And Optimization | Covers 2 matrix requirement(s). Dynamic SEO Generation SEO metadata shall be automatically generated for events, attractions, memberships, ticket types, promotions, and dynamically generated pages based on configurable templates. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 12 | M4 - Integrations | Phase 4 - Integration | 22.11.2; 22.11.9
FEAT-345 | Server Side / Backend | E11 Bundles, Promotions & Pricing | B2B Sales | B2B Sales | Covers 1 matrix requirement(s). The system should expose APIs. Systems allowing the guest to perform online ticket purchasing from Web-sites / mobile applications. The functionalities should include: - Selling all the type of ticket… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 11 | M4 - Integrations | Phase 4 - Integration | 2.5.1
FEAT-346 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Digital Waiver Management | Digital Waiver Management | Covers 1 matrix requirement(s). The system should allow sales of free tickets. These tickets can be configured as a standard ticket with a price of zero or as a full price ticket with a 100% discount. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Low | 2 | M3 - Business Features | Phase 3 - Development | 2.10.4
FEAT-347 | POS App | E11 Bundles, Promotions & Pricing | Order Management | Order Management | Covers 1 matrix requirement(s). Order Sales 1) The POS home page displays available products by category, for the current POS. 2) Staff can click a specific product to add it to the cart; quantity can be adjusted 3) The system displ… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Bundles, Promotions & Pricing | P2 - Should | Low | 2 | M3 - Business Features | Phase 3 - Development | 2.12.19
FEAT-348 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Access Control System | Access Control System | Covers 1 matrix requirement(s). One QR to rule them all—single barcode that grants park entry, ride entitlement, meal voucher, coupon, Photo Voucher download, and re-entry rights | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 6 | M3 - Business Features | Phase 3 - Development | 3.2.1
FEAT-349 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Profile Management | Profile Management | Covers 1 matrix requirement(s). Generate AI insights such as predicted next visit, churn risk, preferred products, preferred attractions, lifetime value, and upsell recommendations. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 11 | M4 - Integrations | Phase 4 - Integration | 5.3.25
FEAT-350 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Portfolio And Entitlement Management | Portfolio And Entitlement Management | Covers 1 matrix requirement(s). Generate AI-driven recommendations, expiring entitlement alerts, cross-sell opportunities, and portfolio optimization suggestions. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 11 | M4 - Integrations | Phase 4 - Integration | 5.5.30
FEAT-351 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Ai Governance And Explainability | Ai Governance And Explainability | Covers 1 matrix requirement(s). Approval Before Execution AI recommendations affecting pricing or financial operations shall require approval before execution | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 11 | M4 - Integrations | Phase 4 - Integration | 8.1.4
FEAT-352 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Module Marketplace And Management | Module Marketplace And Management | Covers 1 matrix requirement(s). Module Pricing - System shall support module-specific pricing. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 6 | M3 - Business Features | Phase 3 - Development | 20.4.8
FEAT-353 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Seat Map Builder | Seat Map Builder | Covers 1 matrix requirement(s). Section Builder Manage venue sections and pricing zones. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 6 | M3 - Business Features | Phase 3 - Development | 21.1.2
FEAT-354 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Seat Selection And Assignment | Seat Selection And Assignment | Covers 1 matrix requirement(s). Price Filters System shall support price filters. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 6 | M3 - Business Features | Phase 3 - Development | 21.5.6
FEAT-355 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Surveys And Feedback | Surveys And Feedback | Covers 1 matrix requirement(s). AI Topic Detection AI shall automatically identify recurring topics, operational issues, service gaps, staff performance concerns, pricing feedback, attraction feedback, and guest preferences. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 11 | M4 - Integrations | Phase 4 - Integration | 22.7.17
FEAT-356 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Omnichannel Communications And Ai Chatbot | Omnichannel Communications And Ai Chatbot | Covers 1 matrix requirement(s). Marketing Integration Chat interactions shall integrate with marketing campaigns, promotions, abandoned cart recovery, loyalty offers, and personalized guest engagement initiatives. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | High | 11 | M3 - Business Features | Phase 3 - Development | 22.8.23
FEAT-357 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Consent Management | Consent Management | Covers 1 matrix requirement(s). Marketing Consent Management Guests shall be able to provide, modify, withdraw, and manage consent for marketing communications including email, SMS, WhatsApp, push notifications, newsletters, surveys… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Low | 2 | M3 - Business Features | Phase 3 - Development | 22.13.2
FEAT-358 | Server Side / Backend | E11 Bundles, Promotions & Pricing | Audience Segmentation | Audience Segmentation | Covers 1 matrix requirement(s). AI Upgrade Opportunities AI shall identify guests likely to purchase memberships, loyalty upgrades, premium experiences, packages, annual passes, or upsell products. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 11 | M4 - Integrations | Phase 4 - Integration | 22.14.14
FEAT-359 | Mobile App | E12 Guest Mobile Experience | Authentication And Login | Authentication And Login | Covers 39 matrix requirement(s). User Registration - System shall support user registration. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Guest Mobile Experience · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 71 | M4 - Integrations | Phase 4 - Integration | 19.2.1; 19.2.2; 19.2.3; 19.2.4; 19.2.5; 19.2.6; 19.2.7; 19.2.8 … (+31 more)
FEAT-360 | Mobile App | E12 Guest Mobile Experience | Branding And White-Label Configuration | Branding And White-Label Configuration | Covers 22 matrix requirement(s). Logo Management - System shall allow changing the mobile app logo through configuration. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Guest Mobile Experience | P2 - Should | Medium | 25 | M3 - Business Features | Phase 3 - Development | 19.1.1; 19.1.2; 19.1.3; 19.1.4; 19.1.5; 19.1.6; 19.1.7; 19.1.8 … (+14 more)
FEAT-361 | Mobile App | E12 Guest Mobile Experience | Safety And Incident Reporting | Safety And Incident Reporting | Covers 6 matrix requirement(s). Hazard Reporting - Users shall submit hazard reports. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Guest Mobile Experience | P2 - Should | Medium | 10 | M3 - Business Features | Phase 3 - Development | 18.4.1; 18.4.2; 18.4.3; 18.4.4; 18.4.5; 18.4.6
FEAT-362 | Mobile App | E12 Guest Mobile Experience | Mobile App Core (Ios And Android) | Mobile App Core (Ios And Android) | Covers 5 matrix requirement(s). iOS Mobile Application - System shall provide a native iOS application. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Guest Mobile Experience | P2 - Should | High | 17 | M3 - Business Features | Phase 3 - Development | 18.1.1; 18.1.2; 18.1.3; 18.1.4; 18.1.5
FEAT-363 | Mobile App | E12 Guest Mobile Experience | Media Capture And Notes | Media Capture And Notes | Covers 5 matrix requirement(s). Photo Capture - Users shall capture photos. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Guest Mobile Experience | P2 - Should | Medium | 9 | M3 - Business Features | Phase 3 - Development | 18.5.1; 18.5.2; 18.5.3; 18.5.4; 18.5.5
FEAT-364 | Mobile App | E12 Guest Mobile Experience | Ai Assistant And Voice Interface | Ai Assistant And Voice Interface | Covers 5 matrix requirement(s). AI Assistant - System shall provide an AI assistant for employees. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Guest Mobile Experience · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 17 | M4 - Integrations | Phase 4 - Integration | 18.10.1; 18.10.2; 18.10.3; 18.10.4; 18.10.5
FEAT-365 | Mobile App | E12 Guest Mobile Experience | Approvals And Notifications | Approvals And Notifications | Covers 4 matrix requirement(s). Approval Inbox - Users shall view pending approvals. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Guest Mobile Experience | P2 - Should | Medium | 9 | M3 - Business Features | Phase 3 - Development | 18.6.1; 18.6.2; 18.6.3; 18.6.4
FEAT-366 | Mobile App | E12 Guest Mobile Experience | Virtual Queue | Virtual Queue | Covers 3 matrix requirement(s). SMS, email, or whats app , app push notifications when it’s nearly their turn. Allow guests to reserve time slots in advance. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Guest Mobile Experience | P2 - Should | Low | 3 | M3 - Business Features | Phase 3 - Development | 5.6.6; 5.6.14; 5.6.31
FEAT-367 | Mobile App | E12 Guest Mobile Experience | Recommendation Engine | Recommendation Engine | Covers 1 matrix requirement(s). System shall provide mobile app recommendations. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Guest Mobile Experience · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 11 | M4 - Integrations | Phase 4 - Integration | 8.6.12
FEAT-368 | Mobile App | E12 Guest Mobile Experience | Accounting | Accounting | Covers 1 matrix requirement(s). Mobile Approvals - System shall support approval actions through mobile applications. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Guest Mobile Experience | P2 - Should | Medium | 6 | M3 - Business Features | Phase 3 - Development | 11.1.28
FEAT-369 | Mobile App | E12 Guest Mobile Experience | Reporting And Dashboards | Reporting And Dashboards | Covers 1 matrix requirement(s). Accreditation Branding - System shall support tenant-specific accreditation branding. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Guest Mobile Experience | P2 - Should | Medium | 6 | M3 - Business Features | Phase 3 - Development | 12.1.57
FEAT-370 | Mobile App | E12 Guest Mobile Experience | Api Business Coverage | Api Business Coverage | Covers 1 matrix requirement(s). APIs shall support email, SMS, push notifications, WhatsApp notifications and notification status retrieval. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Guest Mobile Experience | P2 - Should | Low | 2 | M3 - Business Features | Phase 3 - Development | 13.3.15
FEAT-371 | Mobile App | E13 Employee Mobile & Workforce | Shift Opening And Closing | Shift Opening And Closing | Covers 7 matrix requirement(s). The system should be able to manage end of day shift closing and provide the ability to close out each cash register. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Employee Mobile & Workforce | P3 - Could | Medium | 11 | M3 - Business Features | Phase 3 - Development | 5.9.1; 5.9.2; 5.9.3; 5.9.4; 5.9.6; 5.9.7; 5.9.10
FEAT-372 | Mobile App | E13 Employee Mobile & Workforce | Demand Forecasting | Demand Forecasting | Covers 7 matrix requirement(s). System shall forecast staffing requirements by venue. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Employee Mobile & Workforce · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 20 | M4 - Integrations | Phase 4 - Integration | 8.2.43; 8.2.44; 8.2.45; 8.2.46; 8.2.48; 8.2.49; 8.2.50
FEAT-373 | Mobile App | E13 Employee Mobile & Workforce | Virtual Queue | Virtual Queue | Covers 1 matrix requirement(s). Recommend staffing adjustments, ride allocation, and queue balancing. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Employee Mobile & Workforce · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 11 | M4 - Integrations | Phase 4 - Integration | 5.6.27
FEAT-374 | Mobile App | E13 Employee Mobile & Workforce | Bi And Reporting | Bi And Reporting | Covers 1 matrix requirement(s). System shall support report scheduling. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Employee Mobile & Workforce | P3 - Could | Low | 2 | M3 - Business Features | Phase 3 - Development | 8.7.15
FEAT-375 | Mobile App | E13 Employee Mobile & Workforce | Operations Command Center | Operations Command Center | Covers 1 matrix requirement(s). AI shall identify operational risks, anomalies, congestion, capacity issues, device failures, staffing shortages, and service disruptions and provide recommendations. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Employee Mobile & Workforce · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 11 | M4 - Integrations | Phase 4 - Integration | 8.9.9
FEAT-376 | Server Side / Backend | E14 Intelligence, Reporting & AI | Reporting And Dashboards | Reporting And Dashboards | Covers 97 matrix requirement(s). Allows management of credentials and access rights for staff, contractors, VIPs, media personnel and special guests. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P3 - Could | High | 120 | M3 - Business Features | Phase 3 - Development | 12.1.1; 12.1.2; 12.1.3; 12.1.5; 12.1.7; 12.1.8; 12.1.9; 12.1.10 … (+89 more)
FEAT-377 | Server Side / Backend | E14 Intelligence, Reporting & AI | Fraud Detection | Fraud Detection | Covers 34 matrix requirement(s). System shall detect abnormal payment activity. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 63 | M4 - Integrations | Phase 4 - Integration | 8.3.1; 8.3.2; 8.3.3; 8.3.4; 8.3.5; 8.3.6; 8.3.7; 8.3.8 … (+26 more)
FEAT-378 | Server Side / Backend | E14 Intelligence, Reporting & AI | Accounting | Accounting | Covers 30 matrix requirement(s). Support account roll-up reporting. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 57 | M4 - Integrations | Phase 4 - Integration | 5.7.44; 5.7.51; 5.7.52; 5.7.55; 5.7.71; 5.7.72; 5.7.73; 5.7.74 … (+22 more)
FEAT-379 | Server Side / Backend | E14 Intelligence, Reporting & AI | Ai Engine | Ai Engine | Covers 29 matrix requirement(s). System shall provide a conversational AI assistant across all platform modules. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 55 | M4 - Integrations | Phase 4 - Integration | 8.4.1; 8.4.2; 8.4.3; 8.4.4; 8.4.5; 8.4.6; 8.4.7; 8.4.8 … (+21 more)
FEAT-380 | Server Side / Backend | E14 Intelligence, Reporting & AI | Bi And Reporting | Bi And Reporting | Covers 26 matrix requirement(s). System shall provide executive dashboards. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 51 | M4 - Integrations | Phase 4 - Integration | 8.7.1; 8.7.2; 8.7.3; 8.7.4; 8.7.10; 8.7.11; 8.7.12; 8.7.13 … (+18 more)
FEAT-381 | Server Side / Backend | E14 Intelligence, Reporting & AI | Ai Governance | Ai Governance | Covers 25 matrix requirement(s). System shall log all AI prompts. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 49 | M4 - Integrations | Phase 4 - Integration | 8.3.55; 8.3.56; 8.3.57; 8.3.58; 8.3.59; 8.3.60; 8.3.63; 8.3.64 … (+17 more)
FEAT-382 | Server Side / Backend | E14 Intelligence, Reporting & AI | Demand Forecasting | Demand Forecasting | Covers 24 matrix requirement(s). System shall provide forecast accuracy measurements. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 47 | M4 - Integrations | Phase 4 - Integration | 8.2.18; 8.2.21; 8.2.22; 8.2.23; 8.2.26; 8.2.28; 8.2.29; 8.2.30 … (+16 more)
FEAT-383 | Server Side / Backend | E14 Intelligence, Reporting & AI | Recommendation Engine | Recommendation Engine | Covers 17 matrix requirement(s). System shall provide personalized attraction recommendations. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 36 | M4 - Integrations | Phase 4 - Integration | 8.6.3; 8.6.5; 8.6.8; 8.6.10; 8.6.13; 8.6.14; 8.6.18; 8.6.19 … (+9 more)
FEAT-384 | Server Side / Backend | E14 Intelligence, Reporting & AI | Ai Governance And Explainability | Ai Governance And Explainability | Covers 6 matrix requirement(s). Provides control, transparency and accountability over AI-generated outputs. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 19 | M4 - Integrations | Phase 4 - Integration | 8.1.1; 8.1.2; 8.1.3; 8.1.5; 8.1.6; 8.1.7
FEAT-385 | Server Side / Backend | E14 Intelligence, Reporting & AI | Customer Support And Helpdesk | Customer Support And Helpdesk | Covers 5 matrix requirement(s). AI Subscription Recommendations - System shall recommend optimal subscription plans. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 17 | M4 - Integrations | Phase 4 - Integration | 20.8.1; 20.8.2; 20.8.3; 20.8.4; 20.8.5
FEAT-386 | Server Side / Backend | E14 Intelligence, Reporting & AI | Virtual Queue | Virtual Queue | Covers 4 matrix requirement(s). Automatically recommend or redirect guests to alternative attractions or queues. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 15 | M4 - Integrations | Phase 4 - Integration | 5.6.8; 5.6.26; 5.6.28; 5.6.38
FEAT-387 | Server Side / Backend | E14 Intelligence, Reporting & AI | Maintenance Reporting And Analytics | Maintenance Reporting And Analytics | Covers 4 matrix requirement(s). Maintenance Dashboard - System shall provide maintenance dashboards. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P3 - Could | Medium | 9 | M3 - Business Features | Phase 3 - Development | 17.7.1; 17.7.2; 17.7.4; 17.7.5
FEAT-388 | Server Side / Backend | E14 Intelligence, Reporting & AI | Enterprise Features | Enterprise Features | Covers 3 matrix requirement(s). Device Dashboards - System shall provide device management dashboards. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P3 - Could | Low | 3 | M3 - Business Features | Phase 3 - Development | 16.9.53; 16.9.54; 16.9.60
FEAT-389 | Server Side / Backend | E14 Intelligence, Reporting & AI | Safety And Compliance | Safety And Compliance | Covers 3 matrix requirement(s). Hazard Reporting - System shall support hazard reporting. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P3 - Could | Low | 3 | M3 - Business Features | Phase 3 - Development | 17.5.3; 17.5.4; 17.5.5
FEAT-390 | Server Side / Backend | E14 Intelligence, Reporting & AI | Ai Configuration Assistant | Ai Configuration Assistant | Covers 2 matrix requirement(s). It is possible to register who has offered the Invitation. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P3 - Could | Medium | 7 | M3 - Business Features | Phase 3 - Development | 8.1.4; 8.1.5
FEAT-391 | Server Side / Backend | E14 Intelligence, Reporting & AI | Operations Command Center | Operations Command Center | Covers 2 matrix requirement(s). System shall display queue lengths, estimated wait times, queue utilization, queue alerts, and queue prediction metrics. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 12 | M4 - Integrations | Phase 4 - Integration | 8.9.3; 8.9.4
FEAT-392 | Server Side / Backend | E14 Intelligence, Reporting & AI | Sandbox | Sandbox | Covers 1 matrix requirement(s). Sandbox Usage Analytics - System shall provide sandbox usage reporting. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P3 - Could | Low | 2 | M3 - Business Features | Phase 3 - Development | 13.2.17
FEAT-393 | Server Side / Backend | E14 Intelligence, Reporting & AI | Self-Service Onboarding | Self-Service Onboarding | Covers 1 matrix requirement(s). AI Setup Wizard - System shall provide AI-assisted onboarding. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 11 | M4 - Integrations | Phase 4 - Integration | 20.1.3
FEAT-394 | Server Side / Backend | E15 Device & Peripheral Management | Enterprise Features | Enterprise Features | Covers 7 matrix requirement(s). Multi-Tenant Device Management - System shall support tenant-specific device management. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | Medium | 11 | M4 - Integrations | Phase 4 - Integration | 16.9.51; 16.9.52; 16.9.55; 16.9.56; 16.9.57; 16.9.58; 16.9.59
FEAT-395 | Server Side / Backend | E15 Device & Peripheral Management | Device Configuration | Device Configuration | Covers 5 matrix requirement(s). Device Configuration Management - System shall support device configuration management. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | Medium | 9 | M4 - Integrations | Phase 4 - Integration | 16.3.13; 16.3.14; 16.3.15; 16.3.16; 16.3.17
FEAT-396 | Cross Platform | E15 Device & Peripheral Management | Device Monitoring | Device Monitoring | Covers 5 matrix requirement(s). Device Health Monitoring - System shall monitor device health. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | Medium | 9 | M4 - Integrations | Phase 4 - Integration | 16.4.18; 16.4.19; 16.4.20; 16.4.21; 16.4.23
FEAT-397 | Server Side / Backend | E15 Device & Peripheral Management | Device Maintenance | Device Maintenance | Covers 5 matrix requirement(s). Corrective Maintenance - System shall support corrective maintenance tracking. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | Medium | 9 | M4 - Integrations | Phase 4 - Integration | 16.5.25; 16.5.26; 16.5.27; 16.5.28; 16.5.29
FEAT-398 | Server Side / Backend | E15 Device & Peripheral Management | Firmware And Software Management | Firmware And Software Management | Covers 5 matrix requirement(s). Firmware Management - System shall support firmware management. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 17 | M4 - Integrations | Phase 4 - Integration | 16.6.30; 16.6.31; 16.6.32; 16.6.33; 16.6.34
FEAT-399 | Server Side / Backend | E15 Device & Peripheral Management | Security | Security | Covers 5 matrix requirement(s). Device Authentication - System shall support device authentication. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 17 | M4 - Integrations | Phase 4 - Integration | 16.7.35; 16.7.37; 16.7.38; 16.7.39; 16.7.40
FEAT-400 | Server Side / Backend | E15 Device & Peripheral Management | Device Registration | Device Registration | Covers 4 matrix requirement(s). Device Registration - System shall support registration of devices. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | Medium | 9 | M4 - Integrations | Phase 4 - Integration | 16.1.1; 16.1.2; 16.1.3; 16.1.6
FEAT-401 | Server Side / Backend | E15 Device & Peripheral Management | Device Integrations | Device Integrations | Covers 3 matrix requirement(s). POS Device Integration - System shall support POS device integration. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 14 | M4 - Integrations | Phase 4 - Integration | 16.8.41; 16.8.47; 16.8.50
FEAT-402 | Server Side / Backend | E16 Maintenance, Safety & Asset Mgmt | Asset Management | Asset Management | Covers 7 matrix requirement(s). Asset Master - System shall support centralized asset management. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P3 - Could | Medium | 11 | M3 - Business Features | Phase 3 - Development | 17.1.1; 17.1.2; 17.1.3; 17.1.4; 17.1.5; 17.1.6; 17.1.8
FEAT-403 | Server Side / Backend | E16 Maintenance, Safety & Asset Mgmt | Corrective Maintenance And Incident | Corrective Maintenance And Incident | Covers 7 matrix requirement(s). Maintenance Requests - System shall support maintenance requests. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P3 - Could | Medium | 11 | M3 - Business Features | Phase 3 - Development | 17.3.1; 17.3.2; 17.3.3; 17.3.4; 17.3.5; 17.3.6; 17.3.7
FEAT-404 | Server Side / Backend | E16 Maintenance, Safety & Asset Mgmt | Safety And Compliance | Safety And Compliance | Covers 7 matrix requirement(s). Safety Inspections - System shall support safety inspections. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P3 - Could | Medium | 11 | M3 - Business Features | Phase 3 - Development | 17.5.1; 17.5.2; 17.5.6; 17.5.7; 17.5.8; 17.5.9; 17.5.10
FEAT-405 | Server Side / Backend | E16 Maintenance, Safety & Asset Mgmt | Accounting | Accounting | Covers 1 matrix requirement(s). System shall support Asset, Liability, Equity, Revenue, and Expense account types. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P3 - Could | Medium | 6 | M3 - Business Features | Phase 3 - Development | 5.7.26
FEAT-406 | Server Side / Backend | E17 Identity, Security & Access Policy | Compliance And Security | Compliance And Security | Covers 11 matrix requirement(s). Privacy & Compliance Management | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P3 - Could | High | 27 | M1 - Foundation | Phase 3 - Development | COM-1; COM-2; COM-3; COM-4; COM-5; COM-6; COM-7; COM-8 … (+3 more)
FEAT-407 | Server Side / Backend | E17 Identity, Security & Access Policy | Profile Management | Profile Management | Covers 2 matrix requirement(s). Allow authorized users to maintain internal notes, VIP indicators, accessibility requirements, blacklist flags, security alerts, and custom tags. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Low | 3 | M1 - Foundation | Phase 3 - Development | 5.3.24; 5.3.31
FEAT-408 | Server Side / Backend | E17 Identity, Security & Access Policy | Security | Security | Covers 1 matrix requirement(s). Device Authorization - System shall support device authorization. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 6 | M1 - Foundation | Phase 3 - Development | 16.7.36
FEAT-409 | Server Side / Backend | E18 Governance, Approval & Accreditation | Accounting | Accounting | Covers 56 matrix requirement(s). System shall maintain account type audit history. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | High | 99 | M3 - Business Features | Phase 3 - Development | 5.7.30; 5.7.89; 11.1.1; 11.1.2; 11.1.3; 11.1.4; 11.1.5; 11.1.6 … (+48 more)
FEAT-410 | Server Side / Backend | E18 Governance, Approval & Accreditation | Profile Management | Profile Management | Covers 1 matrix requirement(s). Support retention policies, anonymization, guest deletion requests, right-to-be-forgotten workflows, GDPR compliance, and privacy audits. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 6 | M3 - Business Features | Phase 3 - Development | 5.3.32
FEAT-411 | Server Side / Backend | E18 Governance, Approval & Accreditation | Virtual Queue | Virtual Queue | Covers 1 matrix requirement(s). Allow authorized users to transfer guests between queues with audit logging. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Low | 2 | M3 - Business Features | Phase 3 - Development | 5.6.22
FEAT-412 | Server Side / Backend | E18 Governance, Approval & Accreditation | Sandbox | Sandbox | Covers 1 matrix requirement(s). Sandbox Audit Logs - System shall maintain sandbox audit logs. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Low | 2 | M3 - Business Features | Phase 3 - Development | 13.2.15
FEAT-413 | Cross Platform | E19 Developer Platform & API Mgmt | Sandbox | Sandbox | Covers 16 matrix requirement(s). Sandbox Environment Provisioning - System shall provide isolated sandbox environments. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P3 - Could | High | 35 | M3 - Business Features | Phase 3 - Development | 13.2.1; 13.2.2; 13.2.3; 13.2.4; 13.2.5; 13.2.6; 13.2.7; 13.2.8 … (+8 more)
FEAT-414 | Cross Platform | E19 Developer Platform & API Mgmt | Accounting | Accounting | Covers 2 matrix requirement(s). An API must deliver the sales transactions to the FE accounting system which will be in charge of the invoicing. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P3 - Could | Medium | 7 | M3 - Business Features | Phase 3 - Development | 5.7.23; 5.7.86
FEAT-415 | Cross Platform | E19 Developer Platform & API Mgmt | Api Business Coverage | Api Business Coverage | Covers 1 matrix requirement(s). All business functionality available through the TAIS user interface shall be exposed through documented APIs unless restricted by security, compliance or operational considerations. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P3 - Could | Medium | 6 | M3 - Business Features | Phase 3 - Development | 13.3.1
FEAT-416 | Server Side / Backend | E20 Tenant, Subscription & Licensing | Subscription Management | Subscription Management | Covers 7 matrix requirement(s). Subscription Plans - System shall support configurable subscription plans. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 11 | M3 - Business Features | Phase 3 - Development | 20.2.1; 20.2.2; 20.2.3; 20.2.5; 20.2.6; 20.2.7; 20.2.8
FEAT-417 | Server Side / Backend | E20 Tenant, Subscription & Licensing | Licensing Models | Licensing Models | Covers 6 matrix requirement(s). Venue Size Index - System shall support licensing based on Venue Size Index. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 10 | M3 - Business Features | Phase 3 - Development | 20.3.1; 20.3.2; 20.3.3; 20.3.4; 20.3.5; 20.3.7
FEAT-418 | Server Side / Backend | E20 Tenant, Subscription & Licensing | Module Marketplace And Management | Module Marketplace And Management | Covers 6 matrix requirement(s). Module Discovery - System shall allow customers to browse modules. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 10 | M3 - Business Features | Phase 3 - Development | 20.4.2; 20.4.3; 20.4.6; 20.4.7; 20.4.9; 20.4.10
FEAT-419 | Server Side / Backend | E20 Tenant, Subscription & Licensing | Self-Service Onboarding | Self-Service Onboarding | Covers 5 matrix requirement(s). Customer Registration - System shall support self-service customer registration. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 9 | M3 - Business Features | Phase 3 - Development | 20.1.1; 20.1.2; 20.1.4; 20.1.5; 20.1.6
FEAT-420 | Server Side / Backend | E20 Tenant, Subscription & Licensing | Billing And Payment | Billing And Payment | Covers 5 matrix requirement(s). Online Payments - System shall support online payments. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Medium | 9 | M3 - Business Features | Phase 3 - Development | 20.7.2; 20.7.3; 20.7.4; 20.7.5; 20.7.7
FEAT-421 | Server Side / Backend | E21 Digital Asset Management | Digital Asset Management | Digital Asset Management | Covers 15 matrix requirement(s). System shall provide a centralized repository for storing and managing digital assets including images, videos, documents, PDFs, marketing materials, brand assets, audio files, templates, and creative… | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 33 | M4 - Integrations | Phase 4 - Integration | 23.1.1; 23.1.2; 23.1.3; 23.1.4; 23.1.5; 23.1.6; 23.1.7; 23.1.8 … (+7 more)
FEAT-422 | Server Side / Backend | E22 Integrations & Ecosystem | Software Integration | Software Integration | Covers 19 matrix requirement(s). UAE Pass | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 39 | M4 - Integrations | Phase 4 - Integration | INT-2-2; INT-2-3; INT-2-4; INT-2-5; INT-2-6; INT-2-7; INT-2-8; INT-2-9 … (+11 more)
FEAT-423 | POS App | E22 Integrations & Ecosystem | Hardware Integration | Hardware Integration | Covers 16 matrix requirement(s). Emirates ID Reader Integration | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Backend APIs for Integrations & Ecosystem · Reporting/Analytics platform + 6–12 mo operational data (AI cold-start) · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P3 - Could | High | 35 | M4 - Integrations | Phase 4 - Integration | INT-5-2; INT-5-3; INT-5-4; INT-5-5; INT-5-6; INT-5-7; INT-5-8; INT-5-9 … (+8 more)
FEAT-424 | Cross Platform | E23 Platform Foundations & NFR | Disaster Recovery | Disaster Recovery | Covers 62 matrix requirement(s). Automated Backups - System shall perform automated backups. | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | High | 108 | M1 - Foundation | Phase 2 - Architecture | DIS-1; DIS-2; DIS-3; DIS-4; DIS-5; DIS-6; DIS-7; DIS-8 … (+54 more)
FEAT-425 | Cross Platform | E23 Platform Foundations & NFR | Training And Support | Training And Support | Covers 40 matrix requirement(s). Administrator Training | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | High | 73 | M1 - Foundation | Phase 2 - Architecture | TRA-1; TRA-2; TRA-3; TRA-4; TRA-5; TRA-6; TRA-7; TRA-8 … (+32 more)
FEAT-426 | Server Side / Backend | E23 Platform Foundations & NFR | Multi-Tenant Core & Tenant Isolation | Multi-Tenant Core & Tenant Isolation | ENGINEERED FOUNDATION ITEM (under-specified or absent in client matrix; required for enterprise delivery). Multi-Tenant Core & Tenant Isolation | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | High | 18 | M1 - Foundation | Phase 2 - Architecture | Engineered (not in matrix)
FEAT-427 | Server Side / Backend | E17 Identity, Security & Access Policy | Identity, SSO & MFA Service | Identity, SSO & MFA Service | ENGINEERED FOUNDATION ITEM (under-specified or absent in client matrix; required for enterprise delivery). Identity, SSO & MFA Service | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | High | 14 | M1 - Foundation | Phase 2 - Architecture | Engineered (not in matrix)
FEAT-428 | Server Side / Backend | E17 Identity, Security & Access Policy | RBAC + ABAC Policy Engine | RBAC + ABAC Policy Engine | ENGINEERED FOUNDATION ITEM (under-specified or absent in client matrix; required for enterprise delivery). RBAC + ABAC Policy Engine | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | High | 20 | M1 - Foundation | Phase 2 - Architecture | Engineered (not in matrix)
FEAT-429 | Cross Platform | E19 Developer Platform & API Mgmt | API Gateway & Service Framework | API Gateway & Service Framework | ENGINEERED FOUNDATION ITEM (under-specified or absent in client matrix; required for enterprise delivery). API Gateway & Service Framework | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | High | 16 | M1 - Foundation | Phase 2 - Architecture | Engineered (not in matrix)
FEAT-430 | Server Side / Backend | E23 Platform Foundations & NFR | Core Data Model & Schema Migrations | Core Data Model & Schema Migrations | ENGINEERED FOUNDATION ITEM (under-specified or absent in client matrix; required for enterprise delivery). Core Data Model & Schema Migrations | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | High | 15 | M1 - Foundation | Phase 2 - Architecture | Engineered (not in matrix)
FEAT-431 | Server Side / Backend | E22 Integrations & Ecosystem | Notification Service (Email/SMS/WhatsApp/Push) | Notification Service (Email/SMS/WhatsApp/Push) | ENGINEERED FOUNDATION ITEM (under-specified or absent in client matrix; required for enterprise delivery). Notification Service (Email/SMS/WhatsApp/Push) | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway · Third-party credentials/contracts (gateway, OTA, gov authority, hardware vendor) | P1 - Must | Medium | 10 | M1 - Foundation | Phase 3 - Development | Engineered (not in matrix)
FEAT-432 | Cross Platform | E23 Platform Foundations & NFR | Observability: Logging, Metrics, Tracing, Alerting | Observability: Logging, Metrics, Tracing, Alerting | ENGINEERED FOUNDATION ITEM (under-specified or absent in client matrix; required for enterprise delivery). Observability: Logging, Metrics, Tracing, Alerting | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | High | 12 | M1 - Foundation | Phase 2 - Architecture | Engineered (not in matrix)
FEAT-433 | Cross Platform | E23 Platform Foundations & NFR | CI/CD Pipelines & Infrastructure-as-Code | CI/CD Pipelines & Infrastructure-as-Code | ENGINEERED FOUNDATION ITEM (under-specified or absent in client matrix; required for enterprise delivery). CI/CD Pipelines & Infrastructure-as-Code | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | High | 12 | M1 - Foundation | Phase 2 - Architecture | Engineered (not in matrix)
FEAT-434 | Server Side / Backend | E23 Platform Foundations & NFR | Error Handling & Resilience Framework | Error Handling & Resilience Framework | ENGINEERED FOUNDATION ITEM (under-specified or absent in client matrix; required for enterprise delivery). Error Handling & Resilience Framework | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 8 | M1 - Foundation | Phase 2 - Architecture | Engineered (not in matrix)
FEAT-435 | Server Side / Backend | E23 Platform Foundations & NFR | Configuration Management & Feature Flags | Configuration Management & Feature Flags | ENGINEERED FOUNDATION ITEM (under-specified or absent in client matrix; required for enterprise delivery). Configuration Management & Feature Flags | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 6 | M1 - Foundation | Phase 2 - Architecture | Engineered (not in matrix)
FEAT-436 | Server Side / Backend | E14 Intelligence, Reporting & AI | Reporting & Analytics Platform | Reporting & Analytics Platform | ENGINEERED FOUNDATION ITEM (under-specified or absent in client matrix; required for enterprise delivery). Reporting & Analytics Platform | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | High | 16 | M3 - Business Features | Phase 3 - Development | Engineered (not in matrix)
FEAT-437 | Cross Platform | E23 Platform Foundations & NFR | Backup, Disaster Recovery & BCP | Backup, Disaster Recovery & BCP | ENGINEERED FOUNDATION ITEM (under-specified or absent in client matrix; required for enterprise delivery). Backup, Disaster Recovery & BCP | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | High | 14 | M1 - Foundation | Phase 2 - Architecture | Engineered (not in matrix)
FEAT-438 | Cross Platform | E17 Identity, Security & Access Policy | Security Hardening & Penetration Testing | Security Hardening & Penetration Testing | ENGINEERED FOUNDATION ITEM (under-specified or absent in client matrix; required for enterprise delivery). Security Hardening & Penetration Testing | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | High | 12 | M5 - Testing & UAT | Phase 5 - QA | Engineered (not in matrix)
FEAT-439 | Cross Platform | E23 Platform Foundations & NFR | Performance & Load Testing | Performance & Load Testing | ENGINEERED FOUNDATION ITEM (under-specified or absent in client matrix; required for enterprise delivery). Performance & Load Testing | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 10 | M5 - Testing & UAT | Phase 5 - QA | Engineered (not in matrix)
FEAT-440 | Cross Platform | E23 Platform Foundations & NFR | Automated Test Suite & QA Framework | Automated Test Suite & QA Framework | ENGINEERED FOUNDATION ITEM (under-specified or absent in client matrix; required for enterprise delivery). Automated Test Suite & QA Framework | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | High | 18 | M5 - Testing & UAT | Phase 5 - QA | Engineered (not in matrix)
FEAT-441 | Cross Platform | E23 Platform Foundations & NFR | UAT, Defect Triage & Sign-off | UAT, Defect Triage & Sign-off | ENGINEERED FOUNDATION ITEM (under-specified or absent in client matrix; required for enterprise delivery). UAT, Defect Triage & Sign-off | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 10 | M5 - Testing & UAT | Phase 5 - QA | Engineered (not in matrix)
FEAT-442 | Server Side / Backend | E23 Platform Foundations & NFR | Data Migration & Cutover | Data Migration & Cutover | ENGINEERED FOUNDATION ITEM (under-specified or absent in client matrix; required for enterprise delivery). Data Migration & Cutover | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | High | 12 | M6 - Production Release | Phase 6 - Deployment | Engineered (not in matrix)
FEAT-443 | Cross Platform | E19 Developer Platform & API Mgmt | Documentation & API Reference | Documentation & API Reference | ENGINEERED FOUNDATION ITEM (under-specified or absent in client matrix; required for enterprise delivery). Documentation & API Reference | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P2 - Should | Low | 8 | M5 - Testing & UAT | Phase 5 - QA | Engineered (not in matrix)
FEAT-444 | Cross Platform | E23 Platform Foundations & NFR | Production Deployment & Hypercare | Production Deployment & Hypercare | ENGINEERED FOUNDATION ITEM (under-specified or absent in client matrix; required for enterprise delivery). Production Deployment & Hypercare | M1 Foundation: Auth/RBAC, Core Data Model, API Gateway | P1 - Must | Medium | 14 | M6 - Production Release | Phase 6 - Deployment | Engineered (not in matrix)

## 4. Task Register
+ | Epic | Module | Feature | Task | Purpose / Type | Effort (pd) | Acceptance Criteria | Priority | Milestone
Server Side / Backend | E01 Ticketing & Product Catalogue | Resource Management | Resource Management | Data model & schema | Define entities, relationships, constraints and migrations | 17 | 'Resource Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E01 Ticketing & Product Catalogue | Resource Management | Resource Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 25 | 'Resource Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E01 Ticketing & Product Catalogue | Resource Management | Resource Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 34 | 'Resource Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E01 Ticketing & Product Catalogue | Resource Management | Resource Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 17 | 'Resource Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E01 Ticketing & Product Catalogue | Resource Management | Resource Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 17 | 'Resource Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E01 Ticketing & Product Catalogue | Ticket Types | Ticket Types | Data model & schema | Define entities, relationships, constraints and migrations | 16 | 'Ticket Types' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E01 Ticketing & Product Catalogue | Ticket Types | Ticket Types | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 25 | 'Ticket Types' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E01 Ticketing & Product Catalogue | Ticket Types | Ticket Types | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 33 | 'Ticket Types' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E01 Ticketing & Product Catalogue | Ticket Types | Ticket Types | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 16 | 'Ticket Types' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E01 Ticketing & Product Catalogue | Ticket Types | Ticket Types | Unit & integration tests | Automated tests incl. negative and concurrency cases | 16 | 'Ticket Types' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E01 Ticketing & Product Catalogue | Accounting | Accounting | Data model & schema | Define entities, relationships, constraints and migrations | 10 | 'Accounting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Accounting | Accounting | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 15 | 'Accounting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Accounting | Accounting | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 19 | 'Accounting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Accounting | Accounting | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 10 | 'Accounting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Accounting | Accounting | Unit & integration tests | Automated tests incl. negative and concurrency cases | 10 | 'Accounting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Virtual Queue | Virtual Queue | Data model & schema | Define entities, relationships, constraints and migrations | 6 | 'Virtual Queue' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E01 Ticketing & Product Catalogue | Virtual Queue | Virtual Queue | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 9 | 'Virtual Queue' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E01 Ticketing & Product Catalogue | Virtual Queue | Virtual Queue | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 12 | 'Virtual Queue' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E01 Ticketing & Product Catalogue | Virtual Queue | Virtual Queue | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 6 | 'Virtual Queue' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E01 Ticketing & Product Catalogue | Virtual Queue | Virtual Queue | Unit & integration tests | Automated tests incl. negative and concurrency cases | 6 | 'Virtual Queue' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E01 Ticketing & Product Catalogue | Profile Management | Profile Management | Data model & schema | Define entities, relationships, constraints and migrations | 3 | 'Profile Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Profile Management | Profile Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 4 | 'Profile Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Profile Management | Profile Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 6 | 'Profile Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Profile Management | Profile Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 3 | 'Profile Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Profile Management | Profile Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 3 | 'Profile Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Mobile App | E01 Ticketing & Product Catalogue | Authentication And Login | Authentication And Login | UI screens (iOS & Android) | Implement shared + platform UI components | 5 | 'Authentication And Login' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Mobile App | E01 Ticketing & Product Catalogue | Authentication And Login | Authentication And Login | State & API integration | Data layer, caching and API wiring | 5 | 'Authentication And Login' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Mobile App | E01 Ticketing & Product Catalogue | Authentication And Login | Authentication And Login | Offline & push handling | Offline storage, sync and push notifications | 3 | 'Authentication And Login' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Mobile App | E01 Ticketing & Product Catalogue | Authentication And Login | Authentication And Login | Mobile E2E tests | Automated tests across iOS/Android | 3 | 'Authentication And Login' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Product Lifecycle | Product Lifecycle | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Product Lifecycle' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Product Lifecycle | Product Lifecycle | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Product Lifecycle' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Product Lifecycle | Product Lifecycle | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Product Lifecycle' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Product Lifecycle | Product Lifecycle | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Product Lifecycle' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Product Lifecycle | Product Lifecycle | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Product Lifecycle' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Ticket Resale Marketplace | Ticket Resale Marketplace | Data model & schema | Define entities, relationships, constraints and migrations | 4 | 'Ticket Resale Marketplace' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Ticket Resale Marketplace | Ticket Resale Marketplace | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 6 | 'Ticket Resale Marketplace' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Ticket Resale Marketplace | Ticket Resale Marketplace | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 8 | 'Ticket Resale Marketplace' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Ticket Resale Marketplace | Ticket Resale Marketplace | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 4 | 'Ticket Resale Marketplace' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Ticket Resale Marketplace | Ticket Resale Marketplace | Unit & integration tests | Automated tests incl. negative and concurrency cases | 4 | 'Ticket Resale Marketplace' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Game And Ride Payment And Redemption | Game And Ride Payment And Redemption | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Game And Ride Payment And Redemption' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Game And Ride Payment And Redemption | Game And Ride Payment And Redemption | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Game And Ride Payment And Redemption' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Game And Ride Payment And Redemption | Game And Ride Payment And Redemption | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Game And Ride Payment And Redemption' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Game And Ride Payment And Redemption | Game And Ride Payment And Redemption | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Game And Ride Payment And Redemption' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Game And Ride Payment And Redemption | Game And Ride Payment And Redemption | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Game And Ride Payment And Redemption' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Digital Waiver Management | Digital Waiver Management | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Digital Waiver Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Digital Waiver Management | Digital Waiver Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Digital Waiver Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Digital Waiver Management | Digital Waiver Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Digital Waiver Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Digital Waiver Management | Digital Waiver Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Digital Waiver Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Digital Waiver Management | Digital Waiver Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Digital Waiver Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Ticket Media | Ticket Media | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Ticket Media' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Ticket Media | Ticket Media | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Ticket Media' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Ticket Media | Ticket Media | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Ticket Media' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Ticket Media | Ticket Media | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Ticket Media' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Ticket Media | Ticket Media | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Ticket Media' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Portfolio And Entitlement Management | Portfolio And Entitlement Management | Data model & schema | Define entities, relationships, constraints and migrations | 3 | 'Portfolio And Entitlement Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Portfolio And Entitlement Management | Portfolio And Entitlement Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 5 | 'Portfolio And Entitlement Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Portfolio And Entitlement Management | Portfolio And Entitlement Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 6 | 'Portfolio And Entitlement Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Portfolio And Entitlement Management | Portfolio And Entitlement Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 3 | 'Portfolio And Entitlement Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Portfolio And Entitlement Management | Portfolio And Entitlement Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 3 | 'Portfolio And Entitlement Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Digital Waivers And Signature Management | Digital Waivers And Signature Management | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Digital Waivers And Signature Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Digital Waivers And Signature Management | Digital Waivers And Signature Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Digital Waivers And Signature Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Digital Waivers And Signature Management | Digital Waivers And Signature Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Digital Waivers And Signature Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Digital Waivers And Signature Management | Digital Waivers And Signature Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Digital Waivers And Signature Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Digital Waivers And Signature Management | Digital Waivers And Signature Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Digital Waivers And Signature Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Fraud Detection | Fraud Detection | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Fraud Detection' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Fraud Detection | Fraud Detection | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Fraud Detection' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Fraud Detection | Fraud Detection | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Fraud Detection' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Fraud Detection | Fraud Detection | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Fraud Detection' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Fraud Detection | Fraud Detection | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Fraud Detection' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Ticket Upgrades | Ticket Upgrades | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Ticket Upgrades' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Ticket Upgrades | Ticket Upgrades | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Ticket Upgrades' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Ticket Upgrades | Ticket Upgrades | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Ticket Upgrades' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Ticket Upgrades | Ticket Upgrades | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Ticket Upgrades' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Ticket Upgrades | Ticket Upgrades | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Ticket Upgrades' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E01 Ticketing & Product Catalogue | Cash Handling | Cash Handling | POS screen & flow | Build cashier/kiosk UI and transaction flow | 2 | 'Cash Handling' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E01 Ticketing & Product Catalogue | Cash Handling | Cash Handling | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 1 | 'Cash Handling' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E01 Ticketing & Product Catalogue | Cash Handling | Cash Handling | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 2 | 'Cash Handling' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E01 Ticketing & Product Catalogue | Cash Handling | Cash Handling | Offline handling & sync | Local cache, queue and conflict resolution | 2 | 'Cash Handling' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E01 Ticketing & Product Catalogue | Cash Handling | Cash Handling | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 1 | 'Cash Handling' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Payment Methods | Payment Methods | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Payment Methods' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Payment Methods | Payment Methods | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Payment Methods' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Payment Methods | Payment Methods | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Payment Methods' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Payment Methods | Payment Methods | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Payment Methods' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Payment Methods | Payment Methods | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Payment Methods' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Portfolio Management | Portfolio Management | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Portfolio Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Portfolio Management | Portfolio Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Portfolio Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Portfolio Management | Portfolio Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Portfolio Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Portfolio Management | Portfolio Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Portfolio Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Portfolio Management | Portfolio Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Portfolio Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Receipt | Receipt | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Receipt' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Receipt | Receipt | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Receipt' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Receipt | Receipt | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Receipt' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Receipt | Receipt | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Receipt' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Receipt | Receipt | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Receipt' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Ai Engine | Ai Engine | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Ai Engine' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E01 Ticketing & Product Catalogue | Ai Engine | Ai Engine | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Ai Engine' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E01 Ticketing & Product Catalogue | Ai Engine | Ai Engine | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Ai Engine' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E01 Ticketing & Product Catalogue | Ai Engine | Ai Engine | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Ai Engine' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E01 Ticketing & Product Catalogue | Ai Engine | Ai Engine | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Ai Engine' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E01 Ticketing & Product Catalogue | Guest Profiles And Data Management | Guest Profiles And Data Management | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Guest Profiles And Data Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Guest Profiles And Data Management | Guest Profiles And Data Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Guest Profiles And Data Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Guest Profiles And Data Management | Guest Profiles And Data Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Guest Profiles And Data Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Guest Profiles And Data Management | Guest Profiles And Data Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Guest Profiles And Data Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Guest Profiles And Data Management | Guest Profiles And Data Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Guest Profiles And Data Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Loyalty | Loyalty | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Loyalty' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Loyalty | Loyalty | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Loyalty' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Loyalty | Loyalty | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Loyalty' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Loyalty | Loyalty | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Loyalty' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Loyalty | Loyalty | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Loyalty' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Ai Configuration Assistant | Ai Configuration Assistant | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Ai Configuration Assistant' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Ai Configuration Assistant | Ai Configuration Assistant | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Ai Configuration Assistant' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Ai Configuration Assistant | Ai Configuration Assistant | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Ai Configuration Assistant' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Ai Configuration Assistant | Ai Configuration Assistant | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Ai Configuration Assistant' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Ai Configuration Assistant | Ai Configuration Assistant | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Ai Configuration Assistant' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Recommendation Engine | Recommendation Engine | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Recommendation Engine' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E01 Ticketing & Product Catalogue | Recommendation Engine | Recommendation Engine | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Recommendation Engine' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E01 Ticketing & Product Catalogue | Recommendation Engine | Recommendation Engine | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Recommendation Engine' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E01 Ticketing & Product Catalogue | Recommendation Engine | Recommendation Engine | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Recommendation Engine' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E01 Ticketing & Product Catalogue | Recommendation Engine | Recommendation Engine | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Recommendation Engine' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E01 Ticketing & Product Catalogue | Bi And Reporting | Bi And Reporting | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Bi And Reporting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Bi And Reporting | Bi And Reporting | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Bi And Reporting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Bi And Reporting | Bi And Reporting | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Bi And Reporting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Bi And Reporting | Bi And Reporting | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Bi And Reporting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Bi And Reporting | Bi And Reporting | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Bi And Reporting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Reporting And Dashboards | Reporting And Dashboards | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Reporting And Dashboards' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Reporting And Dashboards | Reporting And Dashboards | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Reporting And Dashboards' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Reporting And Dashboards | Reporting And Dashboards | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Reporting And Dashboards' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Reporting And Dashboards | Reporting And Dashboards | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Reporting And Dashboards' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Reporting And Dashboards | Reporting And Dashboards | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Reporting And Dashboards' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Device Integrations | Device Integrations | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Device Integrations' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Device Integrations | Device Integrations | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Device Integrations' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Device Integrations | Device Integrations | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Device Integrations' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Device Integrations | Device Integrations | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Device Integrations' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Device Integrations | Device Integrations | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Device Integrations' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Module Marketplace And Management | Module Marketplace And Management | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Module Marketplace And Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Module Marketplace And Management | Module Marketplace And Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Module Marketplace And Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Module Marketplace And Management | Module Marketplace And Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Module Marketplace And Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Module Marketplace And Management | Module Marketplace And Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Module Marketplace And Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E01 Ticketing & Product Catalogue | Module Marketplace And Management | Module Marketplace And Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Module Marketplace And Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Call Center Sales | Call Center Sales | Data model & schema | Define entities, relationships, constraints and migrations | 10 | 'Call Center Sales' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E02 Sales Channels & Checkout | Call Center Sales | Call Center Sales | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 15 | 'Call Center Sales' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E02 Sales Channels & Checkout | Call Center Sales | Call Center Sales | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 21 | 'Call Center Sales' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E02 Sales Channels & Checkout | Call Center Sales | Call Center Sales | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 10 | 'Call Center Sales' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E02 Sales Channels & Checkout | Call Center Sales | Call Center Sales | Unit & integration tests | Automated tests incl. negative and concurrency cases | 10 | 'Call Center Sales' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E02 Sales Channels & Checkout | Sales Channels | Sales Channels | Data model & schema | Define entities, relationships, constraints and migrations | 5 | 'Sales Channels' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Sales Channels | Sales Channels | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 8 | 'Sales Channels' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Sales Channels | Sales Channels | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 10 | 'Sales Channels' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Sales Channels | Sales Channels | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 5 | 'Sales Channels' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Sales Channels | Sales Channels | Unit & integration tests | Automated tests incl. negative and concurrency cases | 5 | 'Sales Channels' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Work Order Management | Work Order Management | Data model & schema | Define entities, relationships, constraints and migrations | 3 | 'Work Order Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Work Order Management | Work Order Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 4 | 'Work Order Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Work Order Management | Work Order Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 6 | 'Work Order Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Work Order Management | Work Order Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 3 | 'Work Order Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Work Order Management | Work Order Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 3 | 'Work Order Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Order Management | Order Management | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Order Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Order Management | Order Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Order Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Order Management | Order Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Order Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Order Management | Order Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Order Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Order Management | Order Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Order Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Cross Platform | E02 Sales Channels & Checkout | Usage And Quota Monitoring | Usage And Quota Monitoring | Design & technical spec | Architecture, interfaces and acceptance criteria | 2 | 'Usage And Quota Monitoring' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Cross Platform | E02 Sales Channels & Checkout | Usage And Quota Monitoring | Usage And Quota Monitoring | Implementation | Build the capability / automation | 4 | 'Usage And Quota Monitoring' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Cross Platform | E02 Sales Channels & Checkout | Usage And Quota Monitoring | Usage And Quota Monitoring | Automation & CI integration | Pipeline, IaC and gates | 2 | 'Usage And Quota Monitoring' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Cross Platform | E02 Sales Channels & Checkout | Usage And Quota Monitoring | Usage And Quota Monitoring | Verification & sign-off | Validate against NFR/acceptance criteria | 2 | 'Usage And Quota Monitoring' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Ticket Upgrades | Ticket Upgrades | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Ticket Upgrades' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Ticket Upgrades | Ticket Upgrades | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Ticket Upgrades' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Ticket Upgrades | Ticket Upgrades | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Ticket Upgrades' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Ticket Upgrades | Ticket Upgrades | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Ticket Upgrades' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Ticket Upgrades | Ticket Upgrades | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Ticket Upgrades' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Ticket Types | Ticket Types | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Ticket Types' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Ticket Types | Ticket Types | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Ticket Types' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Ticket Types | Ticket Types | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Ticket Types' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Ticket Types | Ticket Types | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Ticket Types' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Ticket Types | Ticket Types | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Ticket Types' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Product Lifecycle | Product Lifecycle | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Product Lifecycle' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Product Lifecycle | Product Lifecycle | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Product Lifecycle' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Product Lifecycle | Product Lifecycle | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Product Lifecycle' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Product Lifecycle | Product Lifecycle | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Product Lifecycle' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Product Lifecycle | Product Lifecycle | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Product Lifecycle' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | B2B Sales | B2B Sales | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'B2B Sales' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | B2B Sales | B2B Sales | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'B2B Sales' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | B2B Sales | B2B Sales | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'B2B Sales' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | B2B Sales | B2B Sales | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'B2B Sales' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | B2B Sales | B2B Sales | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'B2B Sales' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Case Management And Sla | Case Management And Sla | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Case Management And Sla' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Case Management And Sla | Case Management And Sla | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Case Management And Sla' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Case Management And Sla | Case Management And Sla | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Case Management And Sla' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Case Management And Sla | Case Management And Sla | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Case Management And Sla' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Case Management And Sla | Case Management And Sla | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Case Management And Sla' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Digital Waiver Management | Digital Waiver Management | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Digital Waiver Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Digital Waiver Management | Digital Waiver Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Digital Waiver Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Digital Waiver Management | Digital Waiver Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Digital Waiver Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Digital Waiver Management | Digital Waiver Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Digital Waiver Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Digital Waiver Management | Digital Waiver Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Digital Waiver Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Accounting | Accounting | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Accounting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Accounting | Accounting | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Accounting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Accounting | Accounting | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Accounting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Accounting | Accounting | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Accounting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Accounting | Accounting | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Accounting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Demand Forecasting | Demand Forecasting | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Demand Forecasting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E02 Sales Channels & Checkout | Demand Forecasting | Demand Forecasting | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Demand Forecasting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E02 Sales Channels & Checkout | Demand Forecasting | Demand Forecasting | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Demand Forecasting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E02 Sales Channels & Checkout | Demand Forecasting | Demand Forecasting | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Demand Forecasting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E02 Sales Channels & Checkout | Demand Forecasting | Demand Forecasting | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Demand Forecasting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E02 Sales Channels & Checkout | Digital Waivers And Signature Management | Digital Waivers And Signature Management | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Digital Waivers And Signature Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Digital Waivers And Signature Management | Digital Waivers And Signature Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Digital Waivers And Signature Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Digital Waivers And Signature Management | Digital Waivers And Signature Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Digital Waivers And Signature Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Digital Waivers And Signature Management | Digital Waivers And Signature Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Digital Waivers And Signature Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Digital Waivers And Signature Management | Digital Waivers And Signature Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Digital Waivers And Signature Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E02 Sales Channels & Checkout | Ticketing Pos And Kiosks | Ticketing Pos And Kiosks | POS screen & flow | Build cashier/kiosk UI and transaction flow | 1 | 'Ticketing Pos And Kiosks' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E02 Sales Channels & Checkout | Ticketing Pos And Kiosks | Ticketing Pos And Kiosks | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 1 | 'Ticketing Pos And Kiosks' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E02 Sales Channels & Checkout | Ticketing Pos And Kiosks | Ticketing Pos And Kiosks | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 1 | 'Ticketing Pos And Kiosks' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E02 Sales Channels & Checkout | Ticketing Pos And Kiosks | Ticketing Pos And Kiosks | Offline handling & sync | Local cache, queue and conflict resolution | 1 | 'Ticketing Pos And Kiosks' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E02 Sales Channels & Checkout | Ticketing Pos And Kiosks | Ticketing Pos And Kiosks | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 1 | 'Ticketing Pos And Kiosks' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Profile Management | Profile Management | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Profile Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Profile Management | Profile Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Profile Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Profile Management | Profile Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Profile Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Profile Management | Profile Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Profile Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Profile Management | Profile Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Profile Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E02 Sales Channels & Checkout | Virtual Queue | Virtual Queue | POS screen & flow | Build cashier/kiosk UI and transaction flow | 1 | 'Virtual Queue' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E02 Sales Channels & Checkout | Virtual Queue | Virtual Queue | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 1 | 'Virtual Queue' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E02 Sales Channels & Checkout | Virtual Queue | Virtual Queue | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 1 | 'Virtual Queue' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E02 Sales Channels & Checkout | Virtual Queue | Virtual Queue | Offline handling & sync | Local cache, queue and conflict resolution | 1 | 'Virtual Queue' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E02 Sales Channels & Checkout | Virtual Queue | Virtual Queue | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 1 | 'Virtual Queue' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E02 Sales Channels & Checkout | Cash Handling | Cash Handling | POS screen & flow | Build cashier/kiosk UI and transaction flow | 1 | 'Cash Handling' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E02 Sales Channels & Checkout | Cash Handling | Cash Handling | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 1 | 'Cash Handling' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E02 Sales Channels & Checkout | Cash Handling | Cash Handling | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 1 | 'Cash Handling' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E02 Sales Channels & Checkout | Cash Handling | Cash Handling | Offline handling & sync | Local cache, queue and conflict resolution | 1 | 'Cash Handling' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E02 Sales Channels & Checkout | Cash Handling | Cash Handling | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 1 | 'Cash Handling' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Recommendation Engine | Recommendation Engine | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Recommendation Engine' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E02 Sales Channels & Checkout | Recommendation Engine | Recommendation Engine | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Recommendation Engine' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E02 Sales Channels & Checkout | Recommendation Engine | Recommendation Engine | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Recommendation Engine' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E02 Sales Channels & Checkout | Recommendation Engine | Recommendation Engine | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Recommendation Engine' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E02 Sales Channels & Checkout | Recommendation Engine | Recommendation Engine | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Recommendation Engine' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E02 Sales Channels & Checkout | Device Integrations | Device Integrations | POS screen & flow | Build cashier/kiosk UI and transaction flow | 3 | 'Device Integrations' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E02 Sales Channels & Checkout | Device Integrations | Device Integrations | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 2 | 'Device Integrations' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E02 Sales Channels & Checkout | Device Integrations | Device Integrations | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 3 | 'Device Integrations' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E02 Sales Channels & Checkout | Device Integrations | Device Integrations | Offline handling & sync | Local cache, queue and conflict resolution | 3 | 'Device Integrations' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E02 Sales Channels & Checkout | Device Integrations | Device Integrations | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 2 | 'Device Integrations' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E02 Sales Channels & Checkout | Notifications And Messaging | Notifications And Messaging | POS screen & flow | Build cashier/kiosk UI and transaction flow | 1 | 'Notifications And Messaging' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E02 Sales Channels & Checkout | Notifications And Messaging | Notifications And Messaging | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 1 | 'Notifications And Messaging' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E02 Sales Channels & Checkout | Notifications And Messaging | Notifications And Messaging | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 1 | 'Notifications And Messaging' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E02 Sales Channels & Checkout | Notifications And Messaging | Notifications And Messaging | Offline handling & sync | Local cache, queue and conflict resolution | 1 | 'Notifications And Messaging' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E02 Sales Channels & Checkout | Notifications And Messaging | Notifications And Messaging | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 1 | 'Notifications And Messaging' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Audience Segmentation | Audience Segmentation | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Audience Segmentation' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Audience Segmentation | Audience Segmentation | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Audience Segmentation' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Audience Segmentation | Audience Segmentation | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Audience Segmentation' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Audience Segmentation | Audience Segmentation | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Audience Segmentation' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E02 Sales Channels & Checkout | Audience Segmentation | Audience Segmentation | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Audience Segmentation' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Access Control System | Access Control System | Data model & schema | Define entities, relationships, constraints and migrations | 18 | 'Access Control System' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E03 Admission & Access Control | Access Control System | Access Control System | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 28 | 'Access Control System' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E03 Admission & Access Control | Access Control System | Access Control System | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 37 | 'Access Control System' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E03 Admission & Access Control | Access Control System | Access Control System | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 18 | 'Access Control System' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E03 Admission & Access Control | Access Control System | Access Control System | Unit & integration tests | Automated tests incl. negative and concurrency cases | 18 | 'Access Control System' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E03 Admission & Access Control | Front Gate Sales | Front Gate Sales | POS screen & flow | Build cashier/kiosk UI and transaction flow | 15 | 'Front Gate Sales' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E03 Admission & Access Control | Front Gate Sales | Front Gate Sales | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 10 | 'Front Gate Sales' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E03 Admission & Access Control | Front Gate Sales | Front Gate Sales | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 15 | 'Front Gate Sales' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E03 Admission & Access Control | Front Gate Sales | Front Gate Sales | Offline handling & sync | Local cache, queue and conflict resolution | 15 | 'Front Gate Sales' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E03 Admission & Access Control | Front Gate Sales | Front Gate Sales | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 10 | 'Front Gate Sales' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E03 Admission & Access Control | Demand Forecasting | Demand Forecasting | Data model & schema | Define entities, relationships, constraints and migrations | 6 | 'Demand Forecasting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E03 Admission & Access Control | Demand Forecasting | Demand Forecasting | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 9 | 'Demand Forecasting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E03 Admission & Access Control | Demand Forecasting | Demand Forecasting | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 12 | 'Demand Forecasting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E03 Admission & Access Control | Demand Forecasting | Demand Forecasting | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 6 | 'Demand Forecasting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E03 Admission & Access Control | Demand Forecasting | Demand Forecasting | Unit & integration tests | Automated tests incl. negative and concurrency cases | 6 | 'Demand Forecasting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E03 Admission & Access Control | Ticket Types | Ticket Types | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Ticket Types' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Ticket Types | Ticket Types | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Ticket Types' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Ticket Types | Ticket Types | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Ticket Types' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Ticket Types | Ticket Types | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Ticket Types' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Ticket Types | Ticket Types | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Ticket Types' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Accounting | Accounting | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Accounting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Accounting | Accounting | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Accounting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Accounting | Accounting | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Accounting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Accounting | Accounting | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Accounting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Accounting | Accounting | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Accounting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Order Management | Order Management | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Order Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Order Management | Order Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Order Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Order Management | Order Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Order Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Order Management | Order Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Order Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Order Management | Order Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Order Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Double-Entry Financial Ledger | Double-Entry Financial Ledger | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Double-Entry Financial Ledger' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Double-Entry Financial Ledger | Double-Entry Financial Ledger | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Double-Entry Financial Ledger' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Double-Entry Financial Ledger | Double-Entry Financial Ledger | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Double-Entry Financial Ledger' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Double-Entry Financial Ledger | Double-Entry Financial Ledger | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Double-Entry Financial Ledger' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Double-Entry Financial Ledger | Double-Entry Financial Ledger | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Double-Entry Financial Ledger' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E03 Admission & Access Control | Device Integrations | Device Integrations | POS screen & flow | Build cashier/kiosk UI and transaction flow | 4 | 'Device Integrations' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E03 Admission & Access Control | Device Integrations | Device Integrations | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 3 | 'Device Integrations' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E03 Admission & Access Control | Device Integrations | Device Integrations | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 4 | 'Device Integrations' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E03 Admission & Access Control | Device Integrations | Device Integrations | Offline handling & sync | Local cache, queue and conflict resolution | 4 | 'Device Integrations' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E03 Admission & Access Control | Device Integrations | Device Integrations | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 3 | 'Device Integrations' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E03 Admission & Access Control | Asset Scanning And Lookup | Asset Scanning And Lookup | POS screen & flow | Build cashier/kiosk UI and transaction flow | 2 | 'Asset Scanning And Lookup' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E03 Admission & Access Control | Asset Scanning And Lookup | Asset Scanning And Lookup | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 1 | 'Asset Scanning And Lookup' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E03 Admission & Access Control | Asset Scanning And Lookup | Asset Scanning And Lookup | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 2 | 'Asset Scanning And Lookup' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E03 Admission & Access Control | Asset Scanning And Lookup | Asset Scanning And Lookup | Offline handling & sync | Local cache, queue and conflict resolution | 2 | 'Asset Scanning And Lookup' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E03 Admission & Access Control | Asset Scanning And Lookup | Asset Scanning And Lookup | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 1 | 'Asset Scanning And Lookup' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Mobile App | E03 Admission & Access Control | Attendance And Communications | Attendance And Communications | UI screens (iOS & Android) | Implement shared + platform UI components | 3 | 'Attendance And Communications' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Mobile App | E03 Admission & Access Control | Attendance And Communications | Attendance And Communications | State & API integration | Data layer, caching and API wiring | 3 | 'Attendance And Communications' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Mobile App | E03 Admission & Access Control | Attendance And Communications | Attendance And Communications | Offline & push handling | Offline storage, sync and push notifications | 2 | 'Attendance And Communications' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Mobile App | E03 Admission & Access Control | Attendance And Communications | Attendance And Communications | Mobile E2E tests | Automated tests across iOS/Android | 2 | 'Attendance And Communications' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Call Center Sales | Call Center Sales | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Call Center Sales' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Call Center Sales | Call Center Sales | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Call Center Sales' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Call Center Sales | Call Center Sales | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Call Center Sales' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Call Center Sales | Call Center Sales | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Call Center Sales' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Call Center Sales | Call Center Sales | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Call Center Sales' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Ticket Media | Ticket Media | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Ticket Media' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Ticket Media | Ticket Media | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Ticket Media' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Ticket Media | Ticket Media | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 5 | 'Ticket Media' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Ticket Media | Ticket Media | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Ticket Media' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Ticket Media | Ticket Media | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Ticket Media' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Resource Management | Resource Management | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Resource Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Resource Management | Resource Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Resource Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Resource Management | Resource Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Resource Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Resource Management | Resource Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Resource Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Resource Management | Resource Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Resource Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Virtual Queue | Virtual Queue | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Virtual Queue' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Virtual Queue | Virtual Queue | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Virtual Queue' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Virtual Queue | Virtual Queue | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Virtual Queue' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Virtual Queue | Virtual Queue | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Virtual Queue' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Virtual Queue | Virtual Queue | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Virtual Queue' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Operations Command Center | Operations Command Center | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Operations Command Center' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Operations Command Center | Operations Command Center | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Operations Command Center' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Operations Command Center | Operations Command Center | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Operations Command Center' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Operations Command Center | Operations Command Center | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Operations Command Center' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Operations Command Center | Operations Command Center | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Operations Command Center' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Sales Channels | Sales Channels | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Sales Channels' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Sales Channels | Sales Channels | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Sales Channels' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Sales Channels | Sales Channels | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Sales Channels' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Sales Channels | Sales Channels | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Sales Channels' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Sales Channels | Sales Channels | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Sales Channels' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Parking Integration | Parking Integration | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Parking Integration' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Parking Integration | Parking Integration | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Parking Integration' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Parking Integration | Parking Integration | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Parking Integration' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Parking Integration | Parking Integration | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Parking Integration' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Parking Integration | Parking Integration | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Parking Integration' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Profile Management | Profile Management | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Profile Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Profile Management | Profile Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Profile Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Profile Management | Profile Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Profile Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Profile Management | Profile Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Profile Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Profile Management | Profile Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Profile Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Loyalty | Loyalty | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Loyalty' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Loyalty | Loyalty | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Loyalty' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Loyalty | Loyalty | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Loyalty' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Loyalty | Loyalty | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Loyalty' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Loyalty | Loyalty | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Loyalty' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Bi And Reporting | Bi And Reporting | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Bi And Reporting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Bi And Reporting | Bi And Reporting | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Bi And Reporting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Bi And Reporting | Bi And Reporting | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Bi And Reporting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Bi And Reporting | Bi And Reporting | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Bi And Reporting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Bi And Reporting | Bi And Reporting | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Bi And Reporting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Game And Ride Payment And Redemption | Game And Ride Payment And Redemption | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Game And Ride Payment And Redemption' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Game And Ride Payment And Redemption | Game And Ride Payment And Redemption | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Game And Ride Payment And Redemption' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Game And Ride Payment And Redemption | Game And Ride Payment And Redemption | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Game And Ride Payment And Redemption' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Game And Ride Payment And Redemption | Game And Ride Payment And Redemption | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Game And Ride Payment And Redemption' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Game And Ride Payment And Redemption | Game And Ride Payment And Redemption | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Game And Ride Payment And Redemption' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Gamification And Loyalty | Gamification And Loyalty | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Gamification And Loyalty' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Gamification And Loyalty | Gamification And Loyalty | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Gamification And Loyalty' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Gamification And Loyalty | Gamification And Loyalty | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Gamification And Loyalty' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Gamification And Loyalty | Gamification And Loyalty | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Gamification And Loyalty' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Gamification And Loyalty | Gamification And Loyalty | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Gamification And Loyalty' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Omnichannel Communications And Ai Chatbot | Omnichannel Communications And Ai Chatbot | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Omnichannel Communications And Ai Chatbot' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E03 Admission & Access Control | Omnichannel Communications And Ai Chatbot | Omnichannel Communications And Ai Chatbot | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Omnichannel Communications And Ai Chatbot' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E03 Admission & Access Control | Omnichannel Communications And Ai Chatbot | Omnichannel Communications And Ai Chatbot | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Omnichannel Communications And Ai Chatbot' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E03 Admission & Access Control | Omnichannel Communications And Ai Chatbot | Omnichannel Communications And Ai Chatbot | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Omnichannel Communications And Ai Chatbot' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E03 Admission & Access Control | Omnichannel Communications And Ai Chatbot | Omnichannel Communications And Ai Chatbot | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Omnichannel Communications And Ai Chatbot' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E03 Admission & Access Control | Notifications And Messaging | Notifications And Messaging | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Notifications And Messaging' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Notifications And Messaging | Notifications And Messaging | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Notifications And Messaging' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Notifications And Messaging | Notifications And Messaging | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Notifications And Messaging' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Notifications And Messaging | Notifications And Messaging | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Notifications And Messaging' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Notifications And Messaging | Notifications And Messaging | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Notifications And Messaging' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E03 Admission & Access Control | Product Lifecycle | Product Lifecycle | POS screen & flow | Build cashier/kiosk UI and transaction flow | 1 | 'Product Lifecycle' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E03 Admission & Access Control | Product Lifecycle | Product Lifecycle | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 1 | 'Product Lifecycle' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E03 Admission & Access Control | Product Lifecycle | Product Lifecycle | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 1 | 'Product Lifecycle' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E03 Admission & Access Control | Product Lifecycle | Product Lifecycle | Offline handling & sync | Local cache, queue and conflict resolution | 1 | 'Product Lifecycle' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E03 Admission & Access Control | Product Lifecycle | Product Lifecycle | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 1 | 'Product Lifecycle' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Ticket Upgrades | Ticket Upgrades | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Ticket Upgrades' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Ticket Upgrades | Ticket Upgrades | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Ticket Upgrades' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Ticket Upgrades | Ticket Upgrades | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Ticket Upgrades' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Ticket Upgrades | Ticket Upgrades | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Ticket Upgrades' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Ticket Upgrades | Ticket Upgrades | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Ticket Upgrades' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Portfolio Management | Portfolio Management | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Portfolio Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Portfolio Management | Portfolio Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Portfolio Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Portfolio Management | Portfolio Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Portfolio Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Portfolio Management | Portfolio Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Portfolio Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Portfolio Management | Portfolio Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Portfolio Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Portfolio And Entitlement Management | Portfolio And Entitlement Management | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Portfolio And Entitlement Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Portfolio And Entitlement Management | Portfolio And Entitlement Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Portfolio And Entitlement Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Portfolio And Entitlement Management | Portfolio And Entitlement Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Portfolio And Entitlement Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Portfolio And Entitlement Management | Portfolio And Entitlement Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Portfolio And Entitlement Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Portfolio And Entitlement Management | Portfolio And Entitlement Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Portfolio And Entitlement Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E03 Admission & Access Control | Fraud Detection | Fraud Detection | POS screen & flow | Build cashier/kiosk UI and transaction flow | 1 | 'Fraud Detection' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E03 Admission & Access Control | Fraud Detection | Fraud Detection | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 1 | 'Fraud Detection' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E03 Admission & Access Control | Fraud Detection | Fraud Detection | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 1 | 'Fraud Detection' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E03 Admission & Access Control | Fraud Detection | Fraud Detection | Offline handling & sync | Local cache, queue and conflict resolution | 1 | 'Fraud Detection' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E03 Admission & Access Control | Fraud Detection | Fraud Detection | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 1 | 'Fraud Detection' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Recommendation Engine | Recommendation Engine | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Recommendation Engine' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E03 Admission & Access Control | Recommendation Engine | Recommendation Engine | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Recommendation Engine' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E03 Admission & Access Control | Recommendation Engine | Recommendation Engine | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Recommendation Engine' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E03 Admission & Access Control | Recommendation Engine | Recommendation Engine | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Recommendation Engine' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E03 Admission & Access Control | Recommendation Engine | Recommendation Engine | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Recommendation Engine' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E03 Admission & Access Control | Reporting And Dashboards | Reporting And Dashboards | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Reporting And Dashboards' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Reporting And Dashboards | Reporting And Dashboards | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Reporting And Dashboards' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Reporting And Dashboards | Reporting And Dashboards | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Reporting And Dashboards' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Reporting And Dashboards | Reporting And Dashboards | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Reporting And Dashboards' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Reporting And Dashboards | Reporting And Dashboards | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Reporting And Dashboards' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Sandbox | Sandbox | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Sandbox' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Sandbox | Sandbox | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Sandbox' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Sandbox | Sandbox | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Sandbox' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Sandbox | Sandbox | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Sandbox' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Sandbox | Sandbox | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Sandbox' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Asset Management | Asset Management | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Asset Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Asset Management | Asset Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Asset Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Asset Management | Asset Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Asset Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Asset Management | Asset Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Asset Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Asset Management | Asset Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Asset Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Licensing Models | Licensing Models | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Licensing Models' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Licensing Models | Licensing Models | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Licensing Models' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Licensing Models | Licensing Models | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Licensing Models' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Licensing Models | Licensing Models | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Licensing Models' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Licensing Models | Licensing Models | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Licensing Models' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Cross Platform | E03 Admission & Access Control | Usage And Quota Monitoring | Usage And Quota Monitoring | Design & technical spec | Architecture, interfaces and acceptance criteria | 1 | 'Usage And Quota Monitoring' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Cross Platform | E03 Admission & Access Control | Usage And Quota Monitoring | Usage And Quota Monitoring | Implementation | Build the capability / automation | 2 | 'Usage And Quota Monitoring' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Cross Platform | E03 Admission & Access Control | Usage And Quota Monitoring | Usage And Quota Monitoring | Automation & CI integration | Pipeline, IaC and gates | 1 | 'Usage And Quota Monitoring' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Cross Platform | E03 Admission & Access Control | Usage And Quota Monitoring | Usage And Quota Monitoring | Verification & sign-off | Validate against NFR/acceptance criteria | 1 | 'Usage And Quota Monitoring' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Guest Profiles And Data Management | Guest Profiles And Data Management | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Guest Profiles And Data Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Guest Profiles And Data Management | Guest Profiles And Data Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Guest Profiles And Data Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Guest Profiles And Data Management | Guest Profiles And Data Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Guest Profiles And Data Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Guest Profiles And Data Management | Guest Profiles And Data Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Guest Profiles And Data Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Guest Profiles And Data Management | Guest Profiles And Data Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Guest Profiles And Data Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Reviews And Ratings | Reviews And Ratings | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Reviews And Ratings' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Reviews And Ratings | Reviews And Ratings | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Reviews And Ratings' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Reviews And Ratings | Reviews And Ratings | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Reviews And Ratings' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Reviews And Ratings | Reviews And Ratings | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Reviews And Ratings' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Reviews And Ratings | Reviews And Ratings | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Reviews And Ratings' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Surveys And Feedback | Surveys And Feedback | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Surveys And Feedback' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Surveys And Feedback | Surveys And Feedback | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Surveys And Feedback' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Surveys And Feedback | Surveys And Feedback | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Surveys And Feedback' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Surveys And Feedback | Surveys And Feedback | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Surveys And Feedback' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Surveys And Feedback | Surveys And Feedback | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Surveys And Feedback' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Marketing | Marketing | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Marketing' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Marketing | Marketing | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Marketing' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Marketing | Marketing | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Marketing' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Marketing | Marketing | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Marketing' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Marketing | Marketing | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Marketing' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Digital Waivers And Signature Management | Digital Waivers And Signature Management | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Digital Waivers And Signature Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Digital Waivers And Signature Management | Digital Waivers And Signature Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Digital Waivers And Signature Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Digital Waivers And Signature Management | Digital Waivers And Signature Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Digital Waivers And Signature Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Digital Waivers And Signature Management | Digital Waivers And Signature Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Digital Waivers And Signature Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E03 Admission & Access Control | Digital Waivers And Signature Management | Digital Waivers And Signature Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Digital Waivers And Signature Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Revenue Recognition | Revenue Recognition | Data model & schema | Define entities, relationships, constraints and migrations | 18 | 'Revenue Recognition' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Revenue Recognition | Revenue Recognition | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 28 | 'Revenue Recognition' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Revenue Recognition | Revenue Recognition | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 37 | 'Revenue Recognition' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Revenue Recognition | Revenue Recognition | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 18 | 'Revenue Recognition' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Revenue Recognition | Revenue Recognition | Unit & integration tests | Automated tests incl. negative and concurrency cases | 18 | 'Revenue Recognition' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Wallet | Wallet | Data model & schema | Define entities, relationships, constraints and migrations | 15 | 'Wallet' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Wallet | Wallet | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 23 | 'Wallet' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Wallet | Wallet | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 31 | 'Wallet' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Wallet | Wallet | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 15 | 'Wallet' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Wallet | Wallet | Unit & integration tests | Automated tests incl. negative and concurrency cases | 15 | 'Wallet' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Accounting | Accounting | Data model & schema | Define entities, relationships, constraints and migrations | 10 | 'Accounting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Accounting | Accounting | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 14 | 'Accounting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Accounting | Accounting | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 19 | 'Accounting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Accounting | Accounting | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 10 | 'Accounting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Accounting | Accounting | Unit & integration tests | Automated tests incl. negative and concurrency cases | 10 | 'Accounting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Pricing | Pricing | Data model & schema | Define entities, relationships, constraints and migrations | 7 | 'Pricing' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Pricing | Pricing | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 10 | 'Pricing' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Pricing | Pricing | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 13 | 'Pricing' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Pricing | Pricing | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 7 | 'Pricing' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Pricing | Pricing | Unit & integration tests | Automated tests incl. negative and concurrency cases | 7 | 'Pricing' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Order Management | Order Management | Data model & schema | Define entities, relationships, constraints and migrations | 6 | 'Order Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Order Management | Order Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 9 | 'Order Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Order Management | Order Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 12 | 'Order Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Order Management | Order Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 6 | 'Order Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Order Management | Order Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 6 | 'Order Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Mobile App | E04 Payments, Wallet & Financial | Authentication And Login | Authentication And Login | UI screens (iOS & Android) | Implement shared + platform UI components | 6 | 'Authentication And Login' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Mobile App | E04 Payments, Wallet & Financial | Authentication And Login | Authentication And Login | State & API integration | Data layer, caching and API wiring | 6 | 'Authentication And Login' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Mobile App | E04 Payments, Wallet & Financial | Authentication And Login | Authentication And Login | Offline & push handling | Offline storage, sync and push notifications | 4 | 'Authentication And Login' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Mobile App | E04 Payments, Wallet & Financial | Authentication And Login | Authentication And Login | Mobile E2E tests | Automated tests across iOS/Android | 4 | 'Authentication And Login' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Promotions | Promotions | Data model & schema | Define entities, relationships, constraints and migrations | 5 | 'Promotions' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Promotions | Promotions | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 8 | 'Promotions' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Promotions | Promotions | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 10 | 'Promotions' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Promotions | Promotions | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 5 | 'Promotions' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Promotions | Promotions | Unit & integration tests | Automated tests incl. negative and concurrency cases | 5 | 'Promotions' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Ticket Types | Ticket Types | Data model & schema | Define entities, relationships, constraints and migrations | 5 | 'Ticket Types' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Ticket Types | Ticket Types | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 7 | 'Ticket Types' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Ticket Types | Ticket Types | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 10 | 'Ticket Types' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Ticket Types | Ticket Types | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 5 | 'Ticket Types' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Ticket Types | Ticket Types | Unit & integration tests | Automated tests incl. negative and concurrency cases | 5 | 'Ticket Types' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Fraud Detection | Fraud Detection | Data model & schema | Define entities, relationships, constraints and migrations | 4 | 'Fraud Detection' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Fraud Detection | Fraud Detection | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 6 | 'Fraud Detection' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Fraud Detection | Fraud Detection | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 9 | 'Fraud Detection' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Fraud Detection | Fraud Detection | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 4 | 'Fraud Detection' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Fraud Detection | Fraud Detection | Unit & integration tests | Automated tests incl. negative and concurrency cases | 4 | 'Fraud Detection' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Call Center Sales | Call Center Sales | Data model & schema | Define entities, relationships, constraints and migrations | 4 | 'Call Center Sales' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Call Center Sales | Call Center Sales | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 6 | 'Call Center Sales' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Call Center Sales | Call Center Sales | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 8 | 'Call Center Sales' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Call Center Sales | Call Center Sales | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 4 | 'Call Center Sales' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Call Center Sales | Call Center Sales | Unit & integration tests | Automated tests incl. negative and concurrency cases | 4 | 'Call Center Sales' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Portfolio And Entitlement Management | Portfolio And Entitlement Management | Data model & schema | Define entities, relationships, constraints and migrations | 4 | 'Portfolio And Entitlement Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Portfolio And Entitlement Management | Portfolio And Entitlement Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 5 | 'Portfolio And Entitlement Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Portfolio And Entitlement Management | Portfolio And Entitlement Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 7 | 'Portfolio And Entitlement Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Portfolio And Entitlement Management | Portfolio And Entitlement Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 4 | 'Portfolio And Entitlement Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Portfolio And Entitlement Management | Portfolio And Entitlement Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 4 | 'Portfolio And Entitlement Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Virtual Queue | Virtual Queue | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Virtual Queue' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Virtual Queue | Virtual Queue | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Virtual Queue' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Virtual Queue | Virtual Queue | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Virtual Queue' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Virtual Queue | Virtual Queue | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Virtual Queue' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Virtual Queue | Virtual Queue | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Virtual Queue' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Ticket Upgrades | Ticket Upgrades | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Ticket Upgrades' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Ticket Upgrades | Ticket Upgrades | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Ticket Upgrades' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Ticket Upgrades | Ticket Upgrades | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Ticket Upgrades' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Ticket Upgrades | Ticket Upgrades | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Ticket Upgrades' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Ticket Upgrades | Ticket Upgrades | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Ticket Upgrades' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Profile Management | Profile Management | Data model & schema | Define entities, relationships, constraints and migrations | 3 | 'Profile Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Profile Management | Profile Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 5 | 'Profile Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Profile Management | Profile Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 7 | 'Profile Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Profile Management | Profile Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 3 | 'Profile Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Profile Management | Profile Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 3 | 'Profile Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Ticket Media | Ticket Media | Data model & schema | Define entities, relationships, constraints and migrations | 3 | 'Ticket Media' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Ticket Media | Ticket Media | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 5 | 'Ticket Media' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Ticket Media | Ticket Media | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 6 | 'Ticket Media' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Ticket Media | Ticket Media | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 3 | 'Ticket Media' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Ticket Media | Ticket Media | Unit & integration tests | Automated tests incl. negative and concurrency cases | 3 | 'Ticket Media' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Guest Profiles And Data Management | Guest Profiles And Data Management | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Guest Profiles And Data Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Guest Profiles And Data Management | Guest Profiles And Data Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Guest Profiles And Data Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Guest Profiles And Data Management | Guest Profiles And Data Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Guest Profiles And Data Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Guest Profiles And Data Management | Guest Profiles And Data Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Guest Profiles And Data Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Guest Profiles And Data Management | Guest Profiles And Data Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Guest Profiles And Data Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Omnichannel Communications And Ai Chatbot | Omnichannel Communications And Ai Chatbot | Data model & schema | Define entities, relationships, constraints and migrations | 3 | 'Omnichannel Communications And Ai Chatbot' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Omnichannel Communications And Ai Chatbot | Omnichannel Communications And Ai Chatbot | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 5 | 'Omnichannel Communications And Ai Chatbot' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Omnichannel Communications And Ai Chatbot | Omnichannel Communications And Ai Chatbot | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 6 | 'Omnichannel Communications And Ai Chatbot' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Omnichannel Communications And Ai Chatbot | Omnichannel Communications And Ai Chatbot | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 3 | 'Omnichannel Communications And Ai Chatbot' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Omnichannel Communications And Ai Chatbot | Omnichannel Communications And Ai Chatbot | Unit & integration tests | Automated tests incl. negative and concurrency cases | 3 | 'Omnichannel Communications And Ai Chatbot' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Event Management | Event Management | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Event Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Event Management | Event Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Event Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Event Management | Event Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Event Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Event Management | Event Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Event Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Event Management | Event Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Event Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Audience Segmentation | Audience Segmentation | Data model & schema | Define entities, relationships, constraints and migrations | 3 | 'Audience Segmentation' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Audience Segmentation | Audience Segmentation | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 4 | 'Audience Segmentation' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Audience Segmentation | Audience Segmentation | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 6 | 'Audience Segmentation' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Audience Segmentation | Audience Segmentation | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 3 | 'Audience Segmentation' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Audience Segmentation | Audience Segmentation | Unit & integration tests | Automated tests incl. negative and concurrency cases | 3 | 'Audience Segmentation' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Resource Management | Resource Management | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Resource Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Resource Management | Resource Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Resource Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Resource Management | Resource Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Resource Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Resource Management | Resource Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Resource Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Resource Management | Resource Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Resource Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Sales Channels | Sales Channels | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Sales Channels' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Sales Channels | Sales Channels | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Sales Channels' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Sales Channels | Sales Channels | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Sales Channels' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Sales Channels | Sales Channels | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Sales Channels' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Sales Channels | Sales Channels | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Sales Channels' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Upsell And Cross-Sell | Upsell And Cross-Sell | Data model & schema | Define entities, relationships, constraints and migrations | 3 | 'Upsell And Cross-Sell' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Upsell And Cross-Sell | Upsell And Cross-Sell | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 4 | 'Upsell And Cross-Sell' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Upsell And Cross-Sell | Upsell And Cross-Sell | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 5 | 'Upsell And Cross-Sell' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Upsell And Cross-Sell | Upsell And Cross-Sell | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 3 | 'Upsell And Cross-Sell' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Upsell And Cross-Sell | Upsell And Cross-Sell | Unit & integration tests | Automated tests incl. negative and concurrency cases | 3 | 'Upsell And Cross-Sell' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Game And Ride Payment And Redemption | Game And Ride Payment And Redemption | Data model & schema | Define entities, relationships, constraints and migrations | 3 | 'Game And Ride Payment And Redemption' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Game And Ride Payment And Redemption | Game And Ride Payment And Redemption | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 4 | 'Game And Ride Payment And Redemption' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Game And Ride Payment And Redemption | Game And Ride Payment And Redemption | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 5 | 'Game And Ride Payment And Redemption' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Game And Ride Payment And Redemption | Game And Ride Payment And Redemption | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 3 | 'Game And Ride Payment And Redemption' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Game And Ride Payment And Redemption | Game And Ride Payment And Redemption | Unit & integration tests | Automated tests incl. negative and concurrency cases | 3 | 'Game And Ride Payment And Redemption' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Api Business Coverage | Api Business Coverage | Data model & schema | Define entities, relationships, constraints and migrations | 3 | 'Api Business Coverage' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Api Business Coverage | Api Business Coverage | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 4 | 'Api Business Coverage' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Api Business Coverage | Api Business Coverage | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 5 | 'Api Business Coverage' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Api Business Coverage | Api Business Coverage | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 3 | 'Api Business Coverage' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Api Business Coverage | Api Business Coverage | Unit & integration tests | Automated tests incl. negative and concurrency cases | 3 | 'Api Business Coverage' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Group Reservations And Blocks | Group Reservations And Blocks | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Group Reservations And Blocks' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Group Reservations And Blocks | Group Reservations And Blocks | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Group Reservations And Blocks' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Group Reservations And Blocks | Group Reservations And Blocks | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Group Reservations And Blocks' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Group Reservations And Blocks | Group Reservations And Blocks | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Group Reservations And Blocks' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Group Reservations And Blocks | Group Reservations And Blocks | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Group Reservations And Blocks' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Campaign Management | Campaign Management | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Campaign Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Campaign Management | Campaign Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Campaign Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Campaign Management | Campaign Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Campaign Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Campaign Management | Campaign Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Campaign Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Campaign Management | Campaign Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Campaign Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Case Management And Sla | Case Management And Sla | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Case Management And Sla' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Case Management And Sla | Case Management And Sla | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Case Management And Sla' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Case Management And Sla | Case Management And Sla | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Case Management And Sla' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Case Management And Sla | Case Management And Sla | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Case Management And Sla' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Case Management And Sla | Case Management And Sla | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Case Management And Sla' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Notifications And Messaging | Notifications And Messaging | Data model & schema | Define entities, relationships, constraints and migrations | 3 | 'Notifications And Messaging' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Notifications And Messaging | Notifications And Messaging | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 4 | 'Notifications And Messaging' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Notifications And Messaging | Notifications And Messaging | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 5 | 'Notifications And Messaging' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Notifications And Messaging | Notifications And Messaging | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 3 | 'Notifications And Messaging' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Notifications And Messaging | Notifications And Messaging | Unit & integration tests | Automated tests incl. negative and concurrency cases | 3 | 'Notifications And Messaging' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Product Lifecycle | Product Lifecycle | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Product Lifecycle' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Product Lifecycle | Product Lifecycle | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Product Lifecycle' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Product Lifecycle | Product Lifecycle | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 5 | 'Product Lifecycle' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Product Lifecycle | Product Lifecycle | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Product Lifecycle' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Product Lifecycle | Product Lifecycle | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Product Lifecycle' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Membership | Membership | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Membership' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Membership | Membership | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Membership' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Membership | Membership | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 5 | 'Membership' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Membership | Membership | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Membership' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Membership | Membership | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Membership' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E04 Payments, Wallet & Financial | Front Gate Sales | Front Gate Sales | POS screen & flow | Build cashier/kiosk UI and transaction flow | 3 | 'Front Gate Sales' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E04 Payments, Wallet & Financial | Front Gate Sales | Front Gate Sales | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 2 | 'Front Gate Sales' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E04 Payments, Wallet & Financial | Front Gate Sales | Front Gate Sales | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 3 | 'Front Gate Sales' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E04 Payments, Wallet & Financial | Front Gate Sales | Front Gate Sales | Offline handling & sync | Local cache, queue and conflict resolution | 3 | 'Front Gate Sales' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E04 Payments, Wallet & Financial | Front Gate Sales | Front Gate Sales | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 2 | 'Front Gate Sales' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Loyalty | Loyalty | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Loyalty' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Loyalty | Loyalty | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Loyalty' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Loyalty | Loyalty | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Loyalty' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Loyalty | Loyalty | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Loyalty' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Loyalty | Loyalty | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Loyalty' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Gamification And Loyalty | Gamification And Loyalty | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Gamification And Loyalty' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Gamification And Loyalty | Gamification And Loyalty | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Gamification And Loyalty' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Gamification And Loyalty | Gamification And Loyalty | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Gamification And Loyalty' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Gamification And Loyalty | Gamification And Loyalty | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Gamification And Loyalty' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Gamification And Loyalty | Gamification And Loyalty | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Gamification And Loyalty' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Ticket Resale Marketplace | Ticket Resale Marketplace | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Ticket Resale Marketplace' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Ticket Resale Marketplace | Ticket Resale Marketplace | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Ticket Resale Marketplace' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Ticket Resale Marketplace | Ticket Resale Marketplace | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Ticket Resale Marketplace' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Ticket Resale Marketplace | Ticket Resale Marketplace | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Ticket Resale Marketplace' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Ticket Resale Marketplace | Ticket Resale Marketplace | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Ticket Resale Marketplace' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Unified Platform | Unified Platform | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Unified Platform' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Unified Platform | Unified Platform | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Unified Platform' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Unified Platform | Unified Platform | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Unified Platform' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Unified Platform | Unified Platform | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Unified Platform' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Unified Platform | Unified Platform | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Unified Platform' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E04 Payments, Wallet & Financial | Device Registration | Device Registration | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Device Registration' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Device Registration | Device Registration | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Device Registration' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Device Registration | Device Registration | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Device Registration' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Device Registration | Device Registration | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Device Registration' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Device Registration | Device Registration | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Device Registration' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Module Marketplace And Management | Module Marketplace And Management | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Module Marketplace And Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Module Marketplace And Management | Module Marketplace And Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Module Marketplace And Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Module Marketplace And Management | Module Marketplace And Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Module Marketplace And Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Module Marketplace And Management | Module Marketplace And Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Module Marketplace And Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Module Marketplace And Management | Module Marketplace And Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Module Marketplace And Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Billing And Payment | Billing And Payment | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Billing And Payment' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Billing And Payment | Billing And Payment | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Billing And Payment' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Billing And Payment | Billing And Payment | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Billing And Payment' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Billing And Payment | Billing And Payment | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Billing And Payment' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Billing And Payment | Billing And Payment | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Billing And Payment' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Newsletter And Email Marketing | Newsletter And Email Marketing | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Newsletter And Email Marketing' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Newsletter And Email Marketing | Newsletter And Email Marketing | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Newsletter And Email Marketing' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Newsletter And Email Marketing | Newsletter And Email Marketing | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Newsletter And Email Marketing' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Newsletter And Email Marketing | Newsletter And Email Marketing | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Newsletter And Email Marketing' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Newsletter And Email Marketing | Newsletter And Email Marketing | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Newsletter And Email Marketing' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Reviews And Ratings | Reviews And Ratings | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Reviews And Ratings' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Reviews And Ratings | Reviews And Ratings | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Reviews And Ratings' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Reviews And Ratings | Reviews And Ratings | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Reviews And Ratings' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Reviews And Ratings | Reviews And Ratings | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Reviews And Ratings' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Reviews And Ratings | Reviews And Ratings | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Reviews And Ratings' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Surveys And Feedback | Surveys And Feedback | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Surveys And Feedback' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Surveys And Feedback | Surveys And Feedback | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Surveys And Feedback' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Surveys And Feedback | Surveys And Feedback | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Surveys And Feedback' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Surveys And Feedback | Surveys And Feedback | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Surveys And Feedback' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Surveys And Feedback | Surveys And Feedback | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Surveys And Feedback' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Marketing | Marketing | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Marketing' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Marketing | Marketing | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Marketing' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Marketing | Marketing | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Marketing' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Marketing | Marketing | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Marketing' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Marketing | Marketing | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Marketing' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E04 Payments, Wallet & Financial | Ticketing Pos And Kiosks | Ticketing Pos And Kiosks | POS screen & flow | Build cashier/kiosk UI and transaction flow | 3 | 'Ticketing Pos And Kiosks' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E04 Payments, Wallet & Financial | Ticketing Pos And Kiosks | Ticketing Pos And Kiosks | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 2 | 'Ticketing Pos And Kiosks' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E04 Payments, Wallet & Financial | Ticketing Pos And Kiosks | Ticketing Pos And Kiosks | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 3 | 'Ticketing Pos And Kiosks' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E04 Payments, Wallet & Financial | Ticketing Pos And Kiosks | Ticketing Pos And Kiosks | Offline handling & sync | Local cache, queue and conflict resolution | 3 | 'Ticketing Pos And Kiosks' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E04 Payments, Wallet & Financial | Ticketing Pos And Kiosks | Ticketing Pos And Kiosks | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 2 | 'Ticketing Pos And Kiosks' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E04 Payments, Wallet & Financial | Flying Pos | Flying Pos | POS screen & flow | Build cashier/kiosk UI and transaction flow | 3 | 'Flying Pos' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E04 Payments, Wallet & Financial | Flying Pos | Flying Pos | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 2 | 'Flying Pos' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E04 Payments, Wallet & Financial | Flying Pos | Flying Pos | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 3 | 'Flying Pos' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E04 Payments, Wallet & Financial | Flying Pos | Flying Pos | Offline handling & sync | Local cache, queue and conflict resolution | 3 | 'Flying Pos' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E04 Payments, Wallet & Financial | Flying Pos | Flying Pos | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 2 | 'Flying Pos' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Digital Waiver Management | Digital Waiver Management | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Digital Waiver Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Digital Waiver Management | Digital Waiver Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Digital Waiver Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Digital Waiver Management | Digital Waiver Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Digital Waiver Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Digital Waiver Management | Digital Waiver Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Digital Waiver Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Digital Waiver Management | Digital Waiver Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Digital Waiver Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E04 Payments, Wallet & Financial | Bundles | Bundles | POS screen & flow | Build cashier/kiosk UI and transaction flow | 1 | 'Bundles' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E04 Payments, Wallet & Financial | Bundles | Bundles | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 1 | 'Bundles' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E04 Payments, Wallet & Financial | Bundles | Bundles | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 1 | 'Bundles' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E04 Payments, Wallet & Financial | Bundles | Bundles | Offline handling & sync | Local cache, queue and conflict resolution | 1 | 'Bundles' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E04 Payments, Wallet & Financial | Bundles | Bundles | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 1 | 'Bundles' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Payment Methods | Payment Methods | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Payment Methods' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Payment Methods | Payment Methods | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Payment Methods' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Payment Methods | Payment Methods | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Payment Methods' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Payment Methods | Payment Methods | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Payment Methods' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Payment Methods | Payment Methods | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Payment Methods' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Cash Handling | Cash Handling | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Cash Handling' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Cash Handling | Cash Handling | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Cash Handling' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Cash Handling | Cash Handling | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Cash Handling' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Cash Handling | Cash Handling | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Cash Handling' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Cash Handling | Cash Handling | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Cash Handling' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Receipt | Receipt | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Receipt' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Receipt | Receipt | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Receipt' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Receipt | Receipt | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Receipt' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Receipt | Receipt | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Receipt' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Receipt | Receipt | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Receipt' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Double-Entry Financial Ledger | Double-Entry Financial Ledger | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Double-Entry Financial Ledger' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Double-Entry Financial Ledger | Double-Entry Financial Ledger | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Double-Entry Financial Ledger' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Double-Entry Financial Ledger | Double-Entry Financial Ledger | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Double-Entry Financial Ledger' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Double-Entry Financial Ledger | Double-Entry Financial Ledger | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Double-Entry Financial Ledger' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Double-Entry Financial Ledger | Double-Entry Financial Ledger | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Double-Entry Financial Ledger' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Dynamic Pricing | Dynamic Pricing | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Dynamic Pricing' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Dynamic Pricing | Dynamic Pricing | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Dynamic Pricing' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Dynamic Pricing | Dynamic Pricing | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Dynamic Pricing' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Dynamic Pricing | Dynamic Pricing | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Dynamic Pricing' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Dynamic Pricing | Dynamic Pricing | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Dynamic Pricing' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Ai Configuration Assistant | Ai Configuration Assistant | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Ai Configuration Assistant' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Ai Configuration Assistant | Ai Configuration Assistant | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Ai Configuration Assistant' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Ai Configuration Assistant | Ai Configuration Assistant | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Ai Configuration Assistant' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Ai Configuration Assistant | Ai Configuration Assistant | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Ai Configuration Assistant' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Ai Configuration Assistant | Ai Configuration Assistant | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Ai Configuration Assistant' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Cross Platform | E04 Payments, Wallet & Financial | Operations Command Center | Operations Command Center | Design & technical spec | Architecture, interfaces and acceptance criteria | 2 | 'Operations Command Center' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Cross Platform | E04 Payments, Wallet & Financial | Operations Command Center | Operations Command Center | Implementation | Build the capability / automation | 4 | 'Operations Command Center' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Cross Platform | E04 Payments, Wallet & Financial | Operations Command Center | Operations Command Center | Automation & CI integration | Pipeline, IaC and gates | 2 | 'Operations Command Center' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Cross Platform | E04 Payments, Wallet & Financial | Operations Command Center | Operations Command Center | Verification & sign-off | Validate against NFR/acceptance criteria | 2 | 'Operations Command Center' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Seat Tracking And Holds | Seat Tracking And Holds | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Seat Tracking And Holds' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Seat Tracking And Holds | Seat Tracking And Holds | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Seat Tracking And Holds' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Seat Tracking And Holds | Seat Tracking And Holds | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Seat Tracking And Holds' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Seat Tracking And Holds | Seat Tracking And Holds | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Seat Tracking And Holds' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
Server Side / Backend | E04 Payments, Wallet & Financial | Seat Tracking And Holds | Seat Tracking And Holds | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Seat Tracking And Holds' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M2 - Core Platform
POS App | E05 F&B Operations & POS | Table Reservation | Table Reservation | POS screen & flow | Build cashier/kiosk UI and transaction flow | 27 | 'Table Reservation' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E05 F&B Operations & POS | Table Reservation | Table Reservation | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 18 | 'Table Reservation' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E05 F&B Operations & POS | Table Reservation | Table Reservation | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 27 | 'Table Reservation' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E05 F&B Operations & POS | Table Reservation | Table Reservation | Offline handling & sync | Local cache, queue and conflict resolution | 27 | 'Table Reservation' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E05 F&B Operations & POS | Table Reservation | Table Reservation | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 18 | 'Table Reservation' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E05 F&B Operations & POS | Retail Pos | Retail Pos | POS screen & flow | Build cashier/kiosk UI and transaction flow | 25 | 'Retail Pos' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E05 F&B Operations & POS | Retail Pos | Retail Pos | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 17 | 'Retail Pos' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E05 F&B Operations & POS | Retail Pos | Retail Pos | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 25 | 'Retail Pos' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E05 F&B Operations & POS | Retail Pos | Retail Pos | Offline handling & sync | Local cache, queue and conflict resolution | 25 | 'Retail Pos' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E05 F&B Operations & POS | Retail Pos | Retail Pos | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 17 | 'Retail Pos' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E05 F&B Operations & POS | Fandb Pos - Core Ordering | Fandb Pos - Core Ordering | POS screen & flow | Build cashier/kiosk UI and transaction flow | 16 | 'Fandb Pos - Core Ordering' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E05 F&B Operations & POS | Fandb Pos - Core Ordering | Fandb Pos - Core Ordering | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 10 | 'Fandb Pos - Core Ordering' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E05 F&B Operations & POS | Fandb Pos - Core Ordering | Fandb Pos - Core Ordering | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 16 | 'Fandb Pos - Core Ordering' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E05 F&B Operations & POS | Fandb Pos - Core Ordering | Fandb Pos - Core Ordering | Offline handling & sync | Local cache, queue and conflict resolution | 16 | 'Fandb Pos - Core Ordering' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E05 F&B Operations & POS | Fandb Pos - Core Ordering | Fandb Pos - Core Ordering | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 10 | 'Fandb Pos - Core Ordering' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E05 F&B Operations & POS | Fandb Pos - Menu Management | Fandb Pos - Menu Management | POS screen & flow | Build cashier/kiosk UI and transaction flow | 13 | 'Fandb Pos - Menu Management' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E05 F&B Operations & POS | Fandb Pos - Menu Management | Fandb Pos - Menu Management | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 8 | 'Fandb Pos - Menu Management' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E05 F&B Operations & POS | Fandb Pos - Menu Management | Fandb Pos - Menu Management | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 13 | 'Fandb Pos - Menu Management' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E05 F&B Operations & POS | Fandb Pos - Menu Management | Fandb Pos - Menu Management | Offline handling & sync | Local cache, queue and conflict resolution | 13 | 'Fandb Pos - Menu Management' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E05 F&B Operations & POS | Fandb Pos - Menu Management | Fandb Pos - Menu Management | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 8 | 'Fandb Pos - Menu Management' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E05 F&B Operations & POS | Inventory Management Integration | Inventory Management Integration | POS screen & flow | Build cashier/kiosk UI and transaction flow | 8 | 'Inventory Management Integration' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E05 F&B Operations & POS | Inventory Management Integration | Inventory Management Integration | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 5 | 'Inventory Management Integration' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E05 F&B Operations & POS | Inventory Management Integration | Inventory Management Integration | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 8 | 'Inventory Management Integration' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E05 F&B Operations & POS | Inventory Management Integration | Inventory Management Integration | Offline handling & sync | Local cache, queue and conflict resolution | 8 | 'Inventory Management Integration' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E05 F&B Operations & POS | Inventory Management Integration | Inventory Management Integration | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 5 | 'Inventory Management Integration' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E05 F&B Operations & POS | Kitchen Display | Kitchen Display | POS screen & flow | Build cashier/kiosk UI and transaction flow | 6 | 'Kitchen Display' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E05 F&B Operations & POS | Kitchen Display | Kitchen Display | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 4 | 'Kitchen Display' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E05 F&B Operations & POS | Kitchen Display | Kitchen Display | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 6 | 'Kitchen Display' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E05 F&B Operations & POS | Kitchen Display | Kitchen Display | Offline handling & sync | Local cache, queue and conflict resolution | 6 | 'Kitchen Display' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E05 F&B Operations & POS | Kitchen Display | Kitchen Display | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 4 | 'Kitchen Display' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E05 F&B Operations & POS | Payment Methods | Payment Methods | POS screen & flow | Build cashier/kiosk UI and transaction flow | 5 | 'Payment Methods' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E05 F&B Operations & POS | Payment Methods | Payment Methods | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 4 | 'Payment Methods' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E05 F&B Operations & POS | Payment Methods | Payment Methods | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 5 | 'Payment Methods' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E05 F&B Operations & POS | Payment Methods | Payment Methods | Offline handling & sync | Local cache, queue and conflict resolution | 5 | 'Payment Methods' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E05 F&B Operations & POS | Payment Methods | Payment Methods | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 4 | 'Payment Methods' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E05 F&B Operations & POS | Fandb Pos - Modifiers | Fandb Pos - Modifiers | POS screen & flow | Build cashier/kiosk UI and transaction flow | 3 | 'Fandb Pos - Modifiers' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E05 F&B Operations & POS | Fandb Pos - Modifiers | Fandb Pos - Modifiers | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 2 | 'Fandb Pos - Modifiers' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E05 F&B Operations & POS | Fandb Pos - Modifiers | Fandb Pos - Modifiers | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 3 | 'Fandb Pos - Modifiers' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E05 F&B Operations & POS | Fandb Pos - Modifiers | Fandb Pos - Modifiers | Offline handling & sync | Local cache, queue and conflict resolution | 3 | 'Fandb Pos - Modifiers' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E05 F&B Operations & POS | Fandb Pos - Modifiers | Fandb Pos - Modifiers | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 2 | 'Fandb Pos - Modifiers' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E05 F&B Operations & POS | Kitchen Display And Inventory Sync | Kitchen Display And Inventory Sync | POS screen & flow | Build cashier/kiosk UI and transaction flow | 4 | 'Kitchen Display And Inventory Sync' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E05 F&B Operations & POS | Kitchen Display And Inventory Sync | Kitchen Display And Inventory Sync | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 3 | 'Kitchen Display And Inventory Sync' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E05 F&B Operations & POS | Kitchen Display And Inventory Sync | Kitchen Display And Inventory Sync | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 4 | 'Kitchen Display And Inventory Sync' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E05 F&B Operations & POS | Kitchen Display And Inventory Sync | Kitchen Display And Inventory Sync | Offline handling & sync | Local cache, queue and conflict resolution | 4 | 'Kitchen Display And Inventory Sync' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E05 F&B Operations & POS | Kitchen Display And Inventory Sync | Kitchen Display And Inventory Sync | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 3 | 'Kitchen Display And Inventory Sync' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E05 F&B Operations & POS | Wallet | Wallet | POS screen & flow | Build cashier/kiosk UI and transaction flow | 1 | 'Wallet' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E05 F&B Operations & POS | Wallet | Wallet | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 1 | 'Wallet' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E05 F&B Operations & POS | Wallet | Wallet | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 1 | 'Wallet' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E05 F&B Operations & POS | Wallet | Wallet | Offline handling & sync | Local cache, queue and conflict resolution | 1 | 'Wallet' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E05 F&B Operations & POS | Wallet | Wallet | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 1 | 'Wallet' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E05 F&B Operations & POS | Sales Channels | Sales Channels | POS screen & flow | Build cashier/kiosk UI and transaction flow | 3 | 'Sales Channels' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E05 F&B Operations & POS | Sales Channels | Sales Channels | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 2 | 'Sales Channels' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E05 F&B Operations & POS | Sales Channels | Sales Channels | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 3 | 'Sales Channels' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E05 F&B Operations & POS | Sales Channels | Sales Channels | Offline handling & sync | Local cache, queue and conflict resolution | 3 | 'Sales Channels' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E05 F&B Operations & POS | Sales Channels | Sales Channels | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 2 | 'Sales Channels' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E05 F&B Operations & POS | Bundles | Bundles | POS screen & flow | Build cashier/kiosk UI and transaction flow | 3 | 'Bundles' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E05 F&B Operations & POS | Bundles | Bundles | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 2 | 'Bundles' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E05 F&B Operations & POS | Bundles | Bundles | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 3 | 'Bundles' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E05 F&B Operations & POS | Bundles | Bundles | Offline handling & sync | Local cache, queue and conflict resolution | 3 | 'Bundles' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E05 F&B Operations & POS | Bundles | Bundles | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 2 | 'Bundles' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E05 F&B Operations & POS | Api Business Coverage | Api Business Coverage | POS screen & flow | Build cashier/kiosk UI and transaction flow | 1 | 'Api Business Coverage' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E05 F&B Operations & POS | Api Business Coverage | Api Business Coverage | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 1 | 'Api Business Coverage' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E05 F&B Operations & POS | Api Business Coverage | Api Business Coverage | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 1 | 'Api Business Coverage' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E05 F&B Operations & POS | Api Business Coverage | Api Business Coverage | Offline handling & sync | Local cache, queue and conflict resolution | 1 | 'Api Business Coverage' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E05 F&B Operations & POS | Api Business Coverage | Api Business Coverage | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 1 | 'Api Business Coverage' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E05 F&B Operations & POS | Digital Waivers And Signature Management | Digital Waivers And Signature Management | POS screen & flow | Build cashier/kiosk UI and transaction flow | 1 | 'Digital Waivers And Signature Management' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E05 F&B Operations & POS | Digital Waivers And Signature Management | Digital Waivers And Signature Management | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 1 | 'Digital Waivers And Signature Management' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E05 F&B Operations & POS | Digital Waivers And Signature Management | Digital Waivers And Signature Management | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 1 | 'Digital Waivers And Signature Management' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E05 F&B Operations & POS | Digital Waivers And Signature Management | Digital Waivers And Signature Management | Offline handling & sync | Local cache, queue and conflict resolution | 1 | 'Digital Waivers And Signature Management' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E05 F&B Operations & POS | Digital Waivers And Signature Management | Digital Waivers And Signature Management | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 1 | 'Digital Waivers And Signature Management' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Wallet | Wallet | POS screen & flow | Build cashier/kiosk UI and transaction flow | 24 | 'Wallet' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E06 Retail Operations & POS | Wallet | Wallet | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 16 | 'Wallet' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E06 Retail Operations & POS | Wallet | Wallet | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 24 | 'Wallet' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E06 Retail Operations & POS | Wallet | Wallet | Offline handling & sync | Local cache, queue and conflict resolution | 24 | 'Wallet' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E06 Retail Operations & POS | Wallet | Wallet | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 16 | 'Wallet' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E06 Retail Operations & POS | Upsell And Cross-Sell | Upsell And Cross-Sell | POS screen & flow | Build cashier/kiosk UI and transaction flow | 2 | 'Upsell And Cross-Sell' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Upsell And Cross-Sell | Upsell And Cross-Sell | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 1 | 'Upsell And Cross-Sell' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Upsell And Cross-Sell | Upsell And Cross-Sell | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 2 | 'Upsell And Cross-Sell' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Upsell And Cross-Sell | Upsell And Cross-Sell | Offline handling & sync | Local cache, queue and conflict resolution | 2 | 'Upsell And Cross-Sell' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Upsell And Cross-Sell | Upsell And Cross-Sell | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 1 | 'Upsell And Cross-Sell' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Authentication And Login | Authentication And Login | POS screen & flow | Build cashier/kiosk UI and transaction flow | 2 | 'Authentication And Login' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Authentication And Login | Authentication And Login | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 1 | 'Authentication And Login' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Authentication And Login | Authentication And Login | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 2 | 'Authentication And Login' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Authentication And Login | Authentication And Login | Offline handling & sync | Local cache, queue and conflict resolution | 2 | 'Authentication And Login' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Authentication And Login | Authentication And Login | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 1 | 'Authentication And Login' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Newsletter And Email Marketing | Newsletter And Email Marketing | POS screen & flow | Build cashier/kiosk UI and transaction flow | 3 | 'Newsletter And Email Marketing' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E06 Retail Operations & POS | Newsletter And Email Marketing | Newsletter And Email Marketing | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 2 | 'Newsletter And Email Marketing' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E06 Retail Operations & POS | Newsletter And Email Marketing | Newsletter And Email Marketing | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 3 | 'Newsletter And Email Marketing' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E06 Retail Operations & POS | Newsletter And Email Marketing | Newsletter And Email Marketing | Offline handling & sync | Local cache, queue and conflict resolution | 3 | 'Newsletter And Email Marketing' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E06 Retail Operations & POS | Newsletter And Email Marketing | Newsletter And Email Marketing | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 2 | 'Newsletter And Email Marketing' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E06 Retail Operations & POS | Inventory Management | Inventory Management | POS screen & flow | Build cashier/kiosk UI and transaction flow | 2 | 'Inventory Management' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Inventory Management | Inventory Management | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 1 | 'Inventory Management' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Inventory Management | Inventory Management | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 2 | 'Inventory Management' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Inventory Management | Inventory Management | Offline handling & sync | Local cache, queue and conflict resolution | 2 | 'Inventory Management' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Inventory Management | Inventory Management | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 1 | 'Inventory Management' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Notifications And Messaging | Notifications And Messaging | POS screen & flow | Build cashier/kiosk UI and transaction flow | 1 | 'Notifications And Messaging' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Notifications And Messaging | Notifications And Messaging | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 1 | 'Notifications And Messaging' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Notifications And Messaging | Notifications And Messaging | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 1 | 'Notifications And Messaging' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Notifications And Messaging | Notifications And Messaging | Offline handling & sync | Local cache, queue and conflict resolution | 1 | 'Notifications And Messaging' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Notifications And Messaging | Notifications And Messaging | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 1 | 'Notifications And Messaging' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Promotions | Promotions | POS screen & flow | Build cashier/kiosk UI and transaction flow | 1 | 'Promotions' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Promotions | Promotions | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 1 | 'Promotions' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Promotions | Promotions | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 1 | 'Promotions' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Promotions | Promotions | Offline handling & sync | Local cache, queue and conflict resolution | 1 | 'Promotions' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Promotions | Promotions | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 1 | 'Promotions' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Accounting | Accounting | POS screen & flow | Build cashier/kiosk UI and transaction flow | 1 | 'Accounting' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Accounting | Accounting | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 1 | 'Accounting' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Accounting | Accounting | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 1 | 'Accounting' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Accounting | Accounting | Offline handling & sync | Local cache, queue and conflict resolution | 1 | 'Accounting' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Accounting | Accounting | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 1 | 'Accounting' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Seat Map Import | Seat Map Import | POS screen & flow | Build cashier/kiosk UI and transaction flow | 1 | 'Seat Map Import' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Seat Map Import | Seat Map Import | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 1 | 'Seat Map Import' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Seat Map Import | Seat Map Import | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 1 | 'Seat Map Import' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Seat Map Import | Seat Map Import | Offline handling & sync | Local cache, queue and conflict resolution | 1 | 'Seat Map Import' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Seat Map Import | Seat Map Import | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 1 | 'Seat Map Import' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Seo Management And Optimization | Seo Management And Optimization | POS screen & flow | Build cashier/kiosk UI and transaction flow | 1 | 'Seo Management And Optimization' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Seo Management And Optimization | Seo Management And Optimization | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 1 | 'Seo Management And Optimization' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Seo Management And Optimization | Seo Management And Optimization | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 1 | 'Seo Management And Optimization' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Seo Management And Optimization | Seo Management And Optimization | Offline handling & sync | Local cache, queue and conflict resolution | 1 | 'Seo Management And Optimization' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E06 Retail Operations & POS | Seo Management And Optimization | Seo Management And Optimization | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 1 | 'Seo Management And Optimization' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Inventory Management | Inventory Management | Data model & schema | Define entities, relationships, constraints and migrations | 10 | 'Inventory Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Inventory Management | Inventory Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 15 | 'Inventory Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Inventory Management | Inventory Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 21 | 'Inventory Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Inventory Management | Inventory Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 10 | 'Inventory Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Inventory Management | Inventory Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 10 | 'Inventory Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Fandb And Retail Offers And Promotions | Fandb And Retail Offers And Promotions | Data model & schema | Define entities, relationships, constraints and migrations | 8 | 'Fandb And Retail Offers And Promotions' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Fandb And Retail Offers And Promotions | Fandb And Retail Offers And Promotions | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 12 | 'Fandb And Retail Offers And Promotions' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Fandb And Retail Offers And Promotions | Fandb And Retail Offers And Promotions | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 16 | 'Fandb And Retail Offers And Promotions' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Fandb And Retail Offers And Promotions | Fandb And Retail Offers And Promotions | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 8 | 'Fandb And Retail Offers And Promotions' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Fandb And Retail Offers And Promotions | Fandb And Retail Offers And Promotions | Unit & integration tests | Automated tests incl. negative and concurrency cases | 8 | 'Fandb And Retail Offers And Promotions' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Warehouse Management | Warehouse Management | Data model & schema | Define entities, relationships, constraints and migrations | 7 | 'Warehouse Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E07 Inventory & Procurement | Warehouse Management | Warehouse Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 10 | 'Warehouse Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E07 Inventory & Procurement | Warehouse Management | Warehouse Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 14 | 'Warehouse Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E07 Inventory & Procurement | Warehouse Management | Warehouse Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 7 | 'Warehouse Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E07 Inventory & Procurement | Warehouse Management | Warehouse Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 7 | 'Warehouse Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E07 Inventory & Procurement | Procurement | Procurement | Data model & schema | Define entities, relationships, constraints and migrations | 3 | 'Procurement' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Procurement | Procurement | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 5 | 'Procurement' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Procurement | Procurement | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 6 | 'Procurement' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Procurement | Procurement | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 3 | 'Procurement' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Procurement | Procurement | Unit & integration tests | Automated tests incl. negative and concurrency cases | 3 | 'Procurement' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Upsell And Cross-Sell | Upsell And Cross-Sell | Data model & schema | Define entities, relationships, constraints and migrations | 4 | 'Upsell And Cross-Sell' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E07 Inventory & Procurement | Upsell And Cross-Sell | Upsell And Cross-Sell | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 6 | 'Upsell And Cross-Sell' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E07 Inventory & Procurement | Upsell And Cross-Sell | Upsell And Cross-Sell | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 8 | 'Upsell And Cross-Sell' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E07 Inventory & Procurement | Upsell And Cross-Sell | Upsell And Cross-Sell | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 4 | 'Upsell And Cross-Sell' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E07 Inventory & Procurement | Upsell And Cross-Sell | Upsell And Cross-Sell | Unit & integration tests | Automated tests incl. negative and concurrency cases | 4 | 'Upsell And Cross-Sell' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E07 Inventory & Procurement | Enterprise Features | Enterprise Features | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Enterprise Features' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Enterprise Features | Enterprise Features | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Enterprise Features' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Enterprise Features | Enterprise Features | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 5 | 'Enterprise Features' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Enterprise Features | Enterprise Features | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Enterprise Features' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Enterprise Features | Enterprise Features | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Enterprise Features' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Inventory Planning | Inventory Planning | Data model & schema | Define entities, relationships, constraints and migrations | 4 | 'Inventory Planning' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E07 Inventory & Procurement | Inventory Planning | Inventory Planning | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 5 | 'Inventory Planning' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E07 Inventory & Procurement | Inventory Planning | Inventory Planning | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 7 | 'Inventory Planning' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E07 Inventory & Procurement | Inventory Planning | Inventory Planning | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 4 | 'Inventory Planning' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E07 Inventory & Procurement | Inventory Planning | Inventory Planning | Unit & integration tests | Automated tests incl. negative and concurrency cases | 4 | 'Inventory Planning' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E07 Inventory & Procurement | Device Inventory | Device Inventory | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Device Inventory' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Device Inventory | Device Inventory | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Device Inventory' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Device Inventory | Device Inventory | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Device Inventory' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Device Inventory | Device Inventory | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Device Inventory' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Device Inventory | Device Inventory | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Device Inventory' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Spare Parts And Procurement | Spare Parts And Procurement | Data model & schema | Define entities, relationships, constraints and migrations | 3 | 'Spare Parts And Procurement' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Spare Parts And Procurement | Spare Parts And Procurement | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 4 | 'Spare Parts And Procurement' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Spare Parts And Procurement | Spare Parts And Procurement | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 5 | 'Spare Parts And Procurement' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Spare Parts And Procurement | Spare Parts And Procurement | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 3 | 'Spare Parts And Procurement' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Spare Parts And Procurement | Spare Parts And Procurement | Unit & integration tests | Automated tests incl. negative and concurrency cases | 3 | 'Spare Parts And Procurement' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E07 Inventory & Procurement | Sales Channels | Sales Channels | POS screen & flow | Build cashier/kiosk UI and transaction flow | 3 | 'Sales Channels' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E07 Inventory & Procurement | Sales Channels | Sales Channels | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 2 | 'Sales Channels' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E07 Inventory & Procurement | Sales Channels | Sales Channels | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 3 | 'Sales Channels' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E07 Inventory & Procurement | Sales Channels | Sales Channels | Offline handling & sync | Local cache, queue and conflict resolution | 3 | 'Sales Channels' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E07 Inventory & Procurement | Sales Channels | Sales Channels | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 2 | 'Sales Channels' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Pricing | Pricing | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Pricing' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E07 Inventory & Procurement | Pricing | Pricing | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Pricing' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E07 Inventory & Procurement | Pricing | Pricing | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 5 | 'Pricing' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E07 Inventory & Procurement | Pricing | Pricing | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Pricing' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E07 Inventory & Procurement | Pricing | Pricing | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Pricing' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Mobile App | E07 Inventory & Procurement | Inventory And Stock Management | Inventory And Stock Management | UI screens (iOS & Android) | Implement shared + platform UI components | 3 | 'Inventory And Stock Management' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E07 Inventory & Procurement | Inventory And Stock Management | Inventory And Stock Management | State & API integration | Data layer, caching and API wiring | 3 | 'Inventory And Stock Management' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E07 Inventory & Procurement | Inventory And Stock Management | Inventory And Stock Management | Offline & push handling | Offline storage, sync and push notifications | 2 | 'Inventory And Stock Management' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E07 Inventory & Procurement | Inventory And Stock Management | Inventory And Stock Management | Mobile E2E tests | Automated tests across iOS/Android | 2 | 'Inventory And Stock Management' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Ticket Resale Marketplace | Ticket Resale Marketplace | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Ticket Resale Marketplace' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E07 Inventory & Procurement | Ticket Resale Marketplace | Ticket Resale Marketplace | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Ticket Resale Marketplace' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E07 Inventory & Procurement | Ticket Resale Marketplace | Ticket Resale Marketplace | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Ticket Resale Marketplace' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E07 Inventory & Procurement | Ticket Resale Marketplace | Ticket Resale Marketplace | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Ticket Resale Marketplace' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E07 Inventory & Procurement | Ticket Resale Marketplace | Ticket Resale Marketplace | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Ticket Resale Marketplace' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E07 Inventory & Procurement | Ticket Types | Ticket Types | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Ticket Types' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E07 Inventory & Procurement | Ticket Types | Ticket Types | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Ticket Types' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E07 Inventory & Procurement | Ticket Types | Ticket Types | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Ticket Types' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E07 Inventory & Procurement | Ticket Types | Ticket Types | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Ticket Types' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E07 Inventory & Procurement | Ticket Types | Ticket Types | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Ticket Types' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E07 Inventory & Procurement | Api Business Coverage | Api Business Coverage | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Api Business Coverage' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Api Business Coverage | Api Business Coverage | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Api Business Coverage' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Api Business Coverage | Api Business Coverage | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Api Business Coverage' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Api Business Coverage | Api Business Coverage | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Api Business Coverage' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Api Business Coverage | Api Business Coverage | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Api Business Coverage' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Resource Management | Resource Management | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Resource Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Resource Management | Resource Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Resource Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Resource Management | Resource Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Resource Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Resource Management | Resource Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Resource Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Resource Management | Resource Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Resource Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Event Management | Event Management | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Event Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Event Management | Event Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Event Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Event Management | Event Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Event Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Event Management | Event Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Event Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Event Management | Event Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Event Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Call Center Sales | Call Center Sales | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Call Center Sales' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Call Center Sales | Call Center Sales | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Call Center Sales' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Call Center Sales | Call Center Sales | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Call Center Sales' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Call Center Sales | Call Center Sales | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Call Center Sales' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Call Center Sales | Call Center Sales | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Call Center Sales' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Ticket Media | Ticket Media | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Ticket Media' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Ticket Media | Ticket Media | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Ticket Media' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Ticket Media | Ticket Media | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Ticket Media' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Ticket Media | Ticket Media | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Ticket Media' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Ticket Media | Ticket Media | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Ticket Media' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E07 Inventory & Procurement | Access Control System | Access Control System | POS screen & flow | Build cashier/kiosk UI and transaction flow | 3 | 'Access Control System' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E07 Inventory & Procurement | Access Control System | Access Control System | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 2 | 'Access Control System' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E07 Inventory & Procurement | Access Control System | Access Control System | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 3 | 'Access Control System' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E07 Inventory & Procurement | Access Control System | Access Control System | Offline handling & sync | Local cache, queue and conflict resolution | 3 | 'Access Control System' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E07 Inventory & Procurement | Access Control System | Access Control System | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 2 | 'Access Control System' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E07 Inventory & Procurement | Bundles | Bundles | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Bundles' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Bundles | Bundles | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Bundles' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Bundles | Bundles | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Bundles' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Bundles | Bundles | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Bundles' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Bundles | Bundles | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Bundles' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Promotions | Promotions | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Promotions' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Promotions | Promotions | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Promotions' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Promotions | Promotions | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Promotions' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Promotions | Promotions | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Promotions' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Promotions | Promotions | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Promotions' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E07 Inventory & Procurement | Wallet | Wallet | POS screen & flow | Build cashier/kiosk UI and transaction flow | 1 | 'Wallet' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E07 Inventory & Procurement | Wallet | Wallet | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 1 | 'Wallet' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E07 Inventory & Procurement | Wallet | Wallet | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 1 | 'Wallet' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E07 Inventory & Procurement | Wallet | Wallet | Offline handling & sync | Local cache, queue and conflict resolution | 1 | 'Wallet' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E07 Inventory & Procurement | Wallet | Wallet | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 1 | 'Wallet' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Dynamic Pricing | Dynamic Pricing | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Dynamic Pricing' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Dynamic Pricing | Dynamic Pricing | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Dynamic Pricing' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Dynamic Pricing | Dynamic Pricing | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Dynamic Pricing' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Dynamic Pricing | Dynamic Pricing | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Dynamic Pricing' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Dynamic Pricing | Dynamic Pricing | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Dynamic Pricing' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Game And Ride Payment And Redemption | Game And Ride Payment And Redemption | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Game And Ride Payment And Redemption' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Game And Ride Payment And Redemption | Game And Ride Payment And Redemption | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Game And Ride Payment And Redemption' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Game And Ride Payment And Redemption | Game And Ride Payment And Redemption | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Game And Ride Payment And Redemption' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Game And Ride Payment And Redemption | Game And Ride Payment And Redemption | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Game And Ride Payment And Redemption' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Game And Ride Payment And Redemption | Game And Ride Payment And Redemption | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Game And Ride Payment And Redemption' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Seat Revenue Management And Forecasting | Seat Revenue Management And Forecasting | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Seat Revenue Management And Forecasting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E07 Inventory & Procurement | Seat Revenue Management And Forecasting | Seat Revenue Management And Forecasting | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Seat Revenue Management And Forecasting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E07 Inventory & Procurement | Seat Revenue Management And Forecasting | Seat Revenue Management And Forecasting | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Seat Revenue Management And Forecasting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E07 Inventory & Procurement | Seat Revenue Management And Forecasting | Seat Revenue Management And Forecasting | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Seat Revenue Management And Forecasting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E07 Inventory & Procurement | Seat Revenue Management And Forecasting | Seat Revenue Management And Forecasting | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Seat Revenue Management And Forecasting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E07 Inventory & Procurement | Seat Reporting And Analytics | Seat Reporting And Analytics | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Seat Reporting And Analytics' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Seat Reporting And Analytics | Seat Reporting And Analytics | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Seat Reporting And Analytics' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Seat Reporting And Analytics | Seat Reporting And Analytics | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Seat Reporting And Analytics' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Seat Reporting And Analytics | Seat Reporting And Analytics | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Seat Reporting And Analytics' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Seat Reporting And Analytics | Seat Reporting And Analytics | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Seat Reporting And Analytics' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Campaign Management | Campaign Management | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Campaign Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Campaign Management | Campaign Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Campaign Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Campaign Management | Campaign Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Campaign Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Campaign Management | Campaign Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Campaign Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E07 Inventory & Procurement | Campaign Management | Campaign Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Campaign Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E08 CRM, Marketing & Loyalty | Case Management And Sla | Case Management And Sla | Data model & schema | Define entities, relationships, constraints and migrations | 6 | 'Case Management And Sla' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Case Management And Sla | Case Management And Sla | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 8 | 'Case Management And Sla' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Case Management And Sla | Case Management And Sla | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 11 | 'Case Management And Sla' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Case Management And Sla | Case Management And Sla | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 6 | 'Case Management And Sla' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Case Management And Sla | Case Management And Sla | Unit & integration tests | Automated tests incl. negative and concurrency cases | 6 | 'Case Management And Sla' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Consent Management | Consent Management | Data model & schema | Define entities, relationships, constraints and migrations | 5 | 'Consent Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Consent Management | Consent Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 7 | 'Consent Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Consent Management | Consent Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 10 | 'Consent Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Consent Management | Consent Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 5 | 'Consent Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Consent Management | Consent Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 5 | 'Consent Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Marketing | Marketing | Data model & schema | Define entities, relationships, constraints and migrations | 5 | 'Marketing' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Marketing | Marketing | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 7 | 'Marketing' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Marketing | Marketing | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 9 | 'Marketing' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Marketing | Marketing | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 5 | 'Marketing' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Marketing | Marketing | Unit & integration tests | Automated tests incl. negative and concurrency cases | 5 | 'Marketing' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Surveys And Feedback | Surveys And Feedback | Data model & schema | Define entities, relationships, constraints and migrations | 4 | 'Surveys And Feedback' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Surveys And Feedback | Surveys And Feedback | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 6 | 'Surveys And Feedback' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Surveys And Feedback | Surveys And Feedback | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 9 | 'Surveys And Feedback' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Surveys And Feedback | Surveys And Feedback | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 4 | 'Surveys And Feedback' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Surveys And Feedback | Surveys And Feedback | Unit & integration tests | Automated tests incl. negative and concurrency cases | 4 | 'Surveys And Feedback' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Omnichannel Communications And Ai Chatbot | Omnichannel Communications And Ai Chatbot | Data model & schema | Define entities, relationships, constraints and migrations | 4 | 'Omnichannel Communications And Ai Chatbot' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Omnichannel Communications And Ai Chatbot | Omnichannel Communications And Ai Chatbot | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 6 | 'Omnichannel Communications And Ai Chatbot' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Omnichannel Communications And Ai Chatbot | Omnichannel Communications And Ai Chatbot | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 9 | 'Omnichannel Communications And Ai Chatbot' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Omnichannel Communications And Ai Chatbot | Omnichannel Communications And Ai Chatbot | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 4 | 'Omnichannel Communications And Ai Chatbot' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Omnichannel Communications And Ai Chatbot | Omnichannel Communications And Ai Chatbot | Unit & integration tests | Automated tests incl. negative and concurrency cases | 4 | 'Omnichannel Communications And Ai Chatbot' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Audience Segmentation | Audience Segmentation | Data model & schema | Define entities, relationships, constraints and migrations | 4 | 'Audience Segmentation' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Audience Segmentation | Audience Segmentation | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 6 | 'Audience Segmentation' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Audience Segmentation | Audience Segmentation | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 9 | 'Audience Segmentation' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Audience Segmentation | Audience Segmentation | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 4 | 'Audience Segmentation' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Audience Segmentation | Audience Segmentation | Unit & integration tests | Automated tests incl. negative and concurrency cases | 4 | 'Audience Segmentation' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Loyalty | Loyalty | Data model & schema | Define entities, relationships, constraints and migrations | 4 | 'Loyalty' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E08 CRM, Marketing & Loyalty | Loyalty | Loyalty | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 6 | 'Loyalty' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E08 CRM, Marketing & Loyalty | Loyalty | Loyalty | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 8 | 'Loyalty' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E08 CRM, Marketing & Loyalty | Loyalty | Loyalty | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 4 | 'Loyalty' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E08 CRM, Marketing & Loyalty | Loyalty | Loyalty | Unit & integration tests | Automated tests incl. negative and concurrency cases | 4 | 'Loyalty' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E08 CRM, Marketing & Loyalty | Reviews And Ratings | Reviews And Ratings | Data model & schema | Define entities, relationships, constraints and migrations | 4 | 'Reviews And Ratings' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Reviews And Ratings | Reviews And Ratings | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 6 | 'Reviews And Ratings' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Reviews And Ratings | Reviews And Ratings | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 8 | 'Reviews And Ratings' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Reviews And Ratings | Reviews And Ratings | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 4 | 'Reviews And Ratings' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Reviews And Ratings | Reviews And Ratings | Unit & integration tests | Automated tests incl. negative and concurrency cases | 4 | 'Reviews And Ratings' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Notifications And Messaging | Notifications And Messaging | Data model & schema | Define entities, relationships, constraints and migrations | 4 | 'Notifications And Messaging' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Notifications And Messaging | Notifications And Messaging | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 6 | 'Notifications And Messaging' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Notifications And Messaging | Notifications And Messaging | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 8 | 'Notifications And Messaging' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Notifications And Messaging | Notifications And Messaging | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 4 | 'Notifications And Messaging' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Notifications And Messaging | Notifications And Messaging | Unit & integration tests | Automated tests incl. negative and concurrency cases | 4 | 'Notifications And Messaging' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Guest Profiles And Data Management | Guest Profiles And Data Management | Data model & schema | Define entities, relationships, constraints and migrations | 4 | 'Guest Profiles And Data Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Guest Profiles And Data Management | Guest Profiles And Data Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 5 | 'Guest Profiles And Data Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Guest Profiles And Data Management | Guest Profiles And Data Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 7 | 'Guest Profiles And Data Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Guest Profiles And Data Management | Guest Profiles And Data Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 4 | 'Guest Profiles And Data Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Guest Profiles And Data Management | Guest Profiles And Data Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 4 | 'Guest Profiles And Data Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Newsletter And Email Marketing | Newsletter And Email Marketing | Data model & schema | Define entities, relationships, constraints and migrations | 3 | 'Newsletter And Email Marketing' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Newsletter And Email Marketing | Newsletter And Email Marketing | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 5 | 'Newsletter And Email Marketing' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Newsletter And Email Marketing | Newsletter And Email Marketing | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 6 | 'Newsletter And Email Marketing' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Newsletter And Email Marketing | Newsletter And Email Marketing | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 3 | 'Newsletter And Email Marketing' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Newsletter And Email Marketing | Newsletter And Email Marketing | Unit & integration tests | Automated tests incl. negative and concurrency cases | 3 | 'Newsletter And Email Marketing' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Campaign Management | Campaign Management | Data model & schema | Define entities, relationships, constraints and migrations | 3 | 'Campaign Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Campaign Management | Campaign Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 4 | 'Campaign Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Campaign Management | Campaign Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 6 | 'Campaign Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Campaign Management | Campaign Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 3 | 'Campaign Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Campaign Management | Campaign Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 3 | 'Campaign Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Gamification And Loyalty | Gamification And Loyalty | Data model & schema | Define entities, relationships, constraints and migrations | 3 | 'Gamification And Loyalty' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Gamification And Loyalty | Gamification And Loyalty | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 4 | 'Gamification And Loyalty' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Gamification And Loyalty | Gamification And Loyalty | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 6 | 'Gamification And Loyalty' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Gamification And Loyalty | Gamification And Loyalty | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 3 | 'Gamification And Loyalty' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Gamification And Loyalty | Gamification And Loyalty | Unit & integration tests | Automated tests incl. negative and concurrency cases | 3 | 'Gamification And Loyalty' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Seo Management And Optimization | Seo Management And Optimization | Data model & schema | Define entities, relationships, constraints and migrations | 3 | 'Seo Management And Optimization' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Seo Management And Optimization | Seo Management And Optimization | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 4 | 'Seo Management And Optimization' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Seo Management And Optimization | Seo Management And Optimization | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 6 | 'Seo Management And Optimization' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Seo Management And Optimization | Seo Management And Optimization | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 3 | 'Seo Management And Optimization' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Seo Management And Optimization | Seo Management And Optimization | Unit & integration tests | Automated tests incl. negative and concurrency cases | 3 | 'Seo Management And Optimization' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Recommendation Engine | Recommendation Engine | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Recommendation Engine' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Recommendation Engine | Recommendation Engine | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Recommendation Engine' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Recommendation Engine | Recommendation Engine | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Recommendation Engine' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Recommendation Engine | Recommendation Engine | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Recommendation Engine' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Recommendation Engine | Recommendation Engine | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Recommendation Engine' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Bi And Reporting | Bi And Reporting | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Bi And Reporting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E08 CRM, Marketing & Loyalty | Bi And Reporting | Bi And Reporting | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Bi And Reporting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E08 CRM, Marketing & Loyalty | Bi And Reporting | Bi And Reporting | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Bi And Reporting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E08 CRM, Marketing & Loyalty | Bi And Reporting | Bi And Reporting | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Bi And Reporting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E08 CRM, Marketing & Loyalty | Bi And Reporting | Bi And Reporting | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Bi And Reporting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E08 CRM, Marketing & Loyalty | Authentication And Login | Authentication And Login | UI screens (iOS & Android) | Implement shared + platform UI components | 1 | 'Authentication And Login' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E08 CRM, Marketing & Loyalty | Authentication And Login | Authentication And Login | State & API integration | Data layer, caching and API wiring | 1 | 'Authentication And Login' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E08 CRM, Marketing & Loyalty | Authentication And Login | Authentication And Login | Offline & push handling | Offline storage, sync and push notifications | 1 | 'Authentication And Login' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E08 CRM, Marketing & Loyalty | Authentication And Login | Authentication And Login | Mobile E2E tests | Automated tests across iOS/Android | 1 | 'Authentication And Login' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E08 CRM, Marketing & Loyalty | Profile Management | Profile Management | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Profile Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E08 CRM, Marketing & Loyalty | Profile Management | Profile Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Profile Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E08 CRM, Marketing & Loyalty | Profile Management | Profile Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Profile Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E08 CRM, Marketing & Loyalty | Profile Management | Profile Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Profile Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E08 CRM, Marketing & Loyalty | Profile Management | Profile Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Profile Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E08 CRM, Marketing & Loyalty | Api Business Coverage | Api Business Coverage | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Api Business Coverage' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E08 CRM, Marketing & Loyalty | Api Business Coverage | Api Business Coverage | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Api Business Coverage' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E08 CRM, Marketing & Loyalty | Api Business Coverage | Api Business Coverage | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Api Business Coverage' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E08 CRM, Marketing & Loyalty | Api Business Coverage | Api Business Coverage | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Api Business Coverage' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E08 CRM, Marketing & Loyalty | Api Business Coverage | Api Business Coverage | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Api Business Coverage' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E08 CRM, Marketing & Loyalty | Demand Forecasting | Demand Forecasting | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Demand Forecasting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Demand Forecasting | Demand Forecasting | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Demand Forecasting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Demand Forecasting | Demand Forecasting | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Demand Forecasting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Demand Forecasting | Demand Forecasting | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Demand Forecasting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Demand Forecasting | Demand Forecasting | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Demand Forecasting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Fraud Detection | Fraud Detection | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Fraud Detection' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Fraud Detection | Fraud Detection | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Fraud Detection' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Fraud Detection | Fraud Detection | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Fraud Detection' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Fraud Detection | Fraud Detection | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Fraud Detection' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Fraud Detection | Fraud Detection | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Fraud Detection' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E08 CRM, Marketing & Loyalty | Operations Command Center | Operations Command Center | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Operations Command Center' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E08 CRM, Marketing & Loyalty | Operations Command Center | Operations Command Center | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Operations Command Center' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E08 CRM, Marketing & Loyalty | Operations Command Center | Operations Command Center | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Operations Command Center' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E08 CRM, Marketing & Loyalty | Operations Command Center | Operations Command Center | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Operations Command Center' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E08 CRM, Marketing & Loyalty | Operations Command Center | Operations Command Center | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Operations Command Center' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Ticket Types | Ticket Types | Data model & schema | Define entities, relationships, constraints and migrations | 3 | 'Ticket Types' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Ticket Types | Ticket Types | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 5 | 'Ticket Types' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Ticket Types | Ticket Types | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 7 | 'Ticket Types' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Ticket Types | Ticket Types | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 3 | 'Ticket Types' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Ticket Types | Ticket Types | Unit & integration tests | Automated tests incl. negative and concurrency cases | 3 | 'Ticket Types' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Membership | Membership | Data model & schema | Define entities, relationships, constraints and migrations | 5 | 'Membership' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Membership | Membership | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 7 | 'Membership' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Membership | Membership | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 10 | 'Membership' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Membership | Membership | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 5 | 'Membership' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Membership | Membership | Unit & integration tests | Automated tests incl. negative and concurrency cases | 5 | 'Membership' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Portfolio And Entitlement Management | Portfolio And Entitlement Management | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Portfolio And Entitlement Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Portfolio And Entitlement Management | Portfolio And Entitlement Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Portfolio And Entitlement Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Portfolio And Entitlement Management | Portfolio And Entitlement Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 5 | 'Portfolio And Entitlement Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Portfolio And Entitlement Management | Portfolio And Entitlement Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Portfolio And Entitlement Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Portfolio And Entitlement Management | Portfolio And Entitlement Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Portfolio And Entitlement Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Guest Profiles And Data Management | Guest Profiles And Data Management | Data model & schema | Define entities, relationships, constraints and migrations | 4 | 'Guest Profiles And Data Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E09 Membership & Subscriptions | Guest Profiles And Data Management | Guest Profiles And Data Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 5 | 'Guest Profiles And Data Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E09 Membership & Subscriptions | Guest Profiles And Data Management | Guest Profiles And Data Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 7 | 'Guest Profiles And Data Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E09 Membership & Subscriptions | Guest Profiles And Data Management | Guest Profiles And Data Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 4 | 'Guest Profiles And Data Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E09 Membership & Subscriptions | Guest Profiles And Data Management | Guest Profiles And Data Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 4 | 'Guest Profiles And Data Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E09 Membership & Subscriptions | License Enforcement And Renewal | License Enforcement And Renewal | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'License Enforcement And Renewal' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | License Enforcement And Renewal | License Enforcement And Renewal | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'License Enforcement And Renewal' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | License Enforcement And Renewal | License Enforcement And Renewal | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'License Enforcement And Renewal' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | License Enforcement And Renewal | License Enforcement And Renewal | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'License Enforcement And Renewal' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | License Enforcement And Renewal | License Enforcement And Renewal | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'License Enforcement And Renewal' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Digital Waivers And Signature Management | Digital Waivers And Signature Management | Data model & schema | Define entities, relationships, constraints and migrations | 3 | 'Digital Waivers And Signature Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Digital Waivers And Signature Management | Digital Waivers And Signature Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 5 | 'Digital Waivers And Signature Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Digital Waivers And Signature Management | Digital Waivers And Signature Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 7 | 'Digital Waivers And Signature Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Digital Waivers And Signature Management | Digital Waivers And Signature Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 3 | 'Digital Waivers And Signature Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Digital Waivers And Signature Management | Digital Waivers And Signature Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 3 | 'Digital Waivers And Signature Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Loyalty | Loyalty | Data model & schema | Define entities, relationships, constraints and migrations | 3 | 'Loyalty' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E09 Membership & Subscriptions | Loyalty | Loyalty | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 5 | 'Loyalty' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E09 Membership & Subscriptions | Loyalty | Loyalty | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 6 | 'Loyalty' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E09 Membership & Subscriptions | Loyalty | Loyalty | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 3 | 'Loyalty' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E09 Membership & Subscriptions | Loyalty | Loyalty | Unit & integration tests | Automated tests incl. negative and concurrency cases | 3 | 'Loyalty' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Mobile App | E09 Membership & Subscriptions | Authentication And Login | Authentication And Login | UI screens (iOS & Android) | Implement shared + platform UI components | 3 | 'Authentication And Login' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E09 Membership & Subscriptions | Authentication And Login | Authentication And Login | State & API integration | Data layer, caching and API wiring | 3 | 'Authentication And Login' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E09 Membership & Subscriptions | Authentication And Login | Authentication And Login | Offline & push handling | Offline storage, sync and push notifications | 2 | 'Authentication And Login' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E09 Membership & Subscriptions | Authentication And Login | Authentication And Login | Mobile E2E tests | Automated tests across iOS/Android | 2 | 'Authentication And Login' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Gamification And Loyalty | Gamification And Loyalty | Data model & schema | Define entities, relationships, constraints and migrations | 3 | 'Gamification And Loyalty' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Gamification And Loyalty | Gamification And Loyalty | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 4 | 'Gamification And Loyalty' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Gamification And Loyalty | Gamification And Loyalty | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 6 | 'Gamification And Loyalty' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Gamification And Loyalty | Gamification And Loyalty | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 3 | 'Gamification And Loyalty' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Gamification And Loyalty | Gamification And Loyalty | Unit & integration tests | Automated tests incl. negative and concurrency cases | 3 | 'Gamification And Loyalty' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Digital Waiver Management | Digital Waiver Management | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Digital Waiver Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Digital Waiver Management | Digital Waiver Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Digital Waiver Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Digital Waiver Management | Digital Waiver Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Digital Waiver Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Digital Waiver Management | Digital Waiver Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Digital Waiver Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Digital Waiver Management | Digital Waiver Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Digital Waiver Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Access Control System | Access Control System | Data model & schema | Define entities, relationships, constraints and migrations | 3 | 'Access Control System' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Access Control System | Access Control System | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 4 | 'Access Control System' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Access Control System | Access Control System | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 5 | 'Access Control System' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Access Control System | Access Control System | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 3 | 'Access Control System' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Access Control System | Access Control System | Unit & integration tests | Automated tests incl. negative and concurrency cases | 3 | 'Access Control System' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Surveys And Feedback | Surveys And Feedback | Data model & schema | Define entities, relationships, constraints and migrations | 3 | 'Surveys And Feedback' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Surveys And Feedback | Surveys And Feedback | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 4 | 'Surveys And Feedback' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Surveys And Feedback | Surveys And Feedback | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 5 | 'Surveys And Feedback' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Surveys And Feedback | Surveys And Feedback | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 3 | 'Surveys And Feedback' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Surveys And Feedback | Surveys And Feedback | Unit & integration tests | Automated tests incl. negative and concurrency cases | 3 | 'Surveys And Feedback' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Marketing | Marketing | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Marketing' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Marketing | Marketing | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Marketing' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Marketing | Marketing | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Marketing' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Marketing | Marketing | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Marketing' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Marketing | Marketing | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Marketing' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Virtual Queue | Virtual Queue | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Virtual Queue' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Virtual Queue | Virtual Queue | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Virtual Queue' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Virtual Queue | Virtual Queue | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Virtual Queue' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Virtual Queue | Virtual Queue | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Virtual Queue' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Virtual Queue | Virtual Queue | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Virtual Queue' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E09 Membership & Subscriptions | Ticket And Membership Scanning | Ticket And Membership Scanning | UI screens (iOS & Android) | Implement shared + platform UI components | 3 | 'Ticket And Membership Scanning' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E09 Membership & Subscriptions | Ticket And Membership Scanning | Ticket And Membership Scanning | State & API integration | Data layer, caching and API wiring | 3 | 'Ticket And Membership Scanning' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E09 Membership & Subscriptions | Ticket And Membership Scanning | Ticket And Membership Scanning | Offline & push handling | Offline storage, sync and push notifications | 2 | 'Ticket And Membership Scanning' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E09 Membership & Subscriptions | Ticket And Membership Scanning | Ticket And Membership Scanning | Mobile E2E tests | Automated tests across iOS/Android | 2 | 'Ticket And Membership Scanning' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Consent Management | Consent Management | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Consent Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Consent Management | Consent Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Consent Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Consent Management | Consent Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 5 | 'Consent Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Consent Management | Consent Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Consent Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Consent Management | Consent Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Consent Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Audience Segmentation | Audience Segmentation | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Audience Segmentation' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E09 Membership & Subscriptions | Audience Segmentation | Audience Segmentation | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Audience Segmentation' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E09 Membership & Subscriptions | Audience Segmentation | Audience Segmentation | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 5 | 'Audience Segmentation' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E09 Membership & Subscriptions | Audience Segmentation | Audience Segmentation | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Audience Segmentation' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E09 Membership & Subscriptions | Audience Segmentation | Audience Segmentation | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Audience Segmentation' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E09 Membership & Subscriptions | Front Gate Sales | Front Gate Sales | POS screen & flow | Build cashier/kiosk UI and transaction flow | 1 | 'Front Gate Sales' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E09 Membership & Subscriptions | Front Gate Sales | Front Gate Sales | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 1 | 'Front Gate Sales' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E09 Membership & Subscriptions | Front Gate Sales | Front Gate Sales | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 1 | 'Front Gate Sales' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E09 Membership & Subscriptions | Front Gate Sales | Front Gate Sales | Offline handling & sync | Local cache, queue and conflict resolution | 1 | 'Front Gate Sales' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E09 Membership & Subscriptions | Front Gate Sales | Front Gate Sales | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 1 | 'Front Gate Sales' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Newsletter And Email Marketing | Newsletter And Email Marketing | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Newsletter And Email Marketing' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Newsletter And Email Marketing | Newsletter And Email Marketing | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Newsletter And Email Marketing' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Newsletter And Email Marketing | Newsletter And Email Marketing | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Newsletter And Email Marketing' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Newsletter And Email Marketing | Newsletter And Email Marketing | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Newsletter And Email Marketing' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Newsletter And Email Marketing | Newsletter And Email Marketing | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Newsletter And Email Marketing' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Reviews And Ratings | Reviews And Ratings | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Reviews And Ratings' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Reviews And Ratings | Reviews And Ratings | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Reviews And Ratings' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Reviews And Ratings | Reviews And Ratings | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Reviews And Ratings' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Reviews And Ratings | Reviews And Ratings | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Reviews And Ratings' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Reviews And Ratings | Reviews And Ratings | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Reviews And Ratings' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Omnichannel Communications And Ai Chatbot | Omnichannel Communications And Ai Chatbot | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Omnichannel Communications And Ai Chatbot' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E09 Membership & Subscriptions | Omnichannel Communications And Ai Chatbot | Omnichannel Communications And Ai Chatbot | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Omnichannel Communications And Ai Chatbot' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E09 Membership & Subscriptions | Omnichannel Communications And Ai Chatbot | Omnichannel Communications And Ai Chatbot | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Omnichannel Communications And Ai Chatbot' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E09 Membership & Subscriptions | Omnichannel Communications And Ai Chatbot | Omnichannel Communications And Ai Chatbot | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Omnichannel Communications And Ai Chatbot' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E09 Membership & Subscriptions | Omnichannel Communications And Ai Chatbot | Omnichannel Communications And Ai Chatbot | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Omnichannel Communications And Ai Chatbot' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E09 Membership & Subscriptions | Call Center Sales | Call Center Sales | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Call Center Sales' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E09 Membership & Subscriptions | Call Center Sales | Call Center Sales | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Call Center Sales' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E09 Membership & Subscriptions | Call Center Sales | Call Center Sales | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Call Center Sales' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E09 Membership & Subscriptions | Call Center Sales | Call Center Sales | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Call Center Sales' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E09 Membership & Subscriptions | Call Center Sales | Call Center Sales | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Call Center Sales' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E09 Membership & Subscriptions | Order Management | Order Management | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Order Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Order Management | Order Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Order Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Order Management | Order Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Order Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Order Management | Order Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Order Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Order Management | Order Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Order Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Ticket Media | Ticket Media | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Ticket Media' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E09 Membership & Subscriptions | Ticket Media | Ticket Media | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Ticket Media' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E09 Membership & Subscriptions | Ticket Media | Ticket Media | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Ticket Media' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E09 Membership & Subscriptions | Ticket Media | Ticket Media | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Ticket Media' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E09 Membership & Subscriptions | Ticket Media | Ticket Media | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Ticket Media' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E09 Membership & Subscriptions | Profile Management | Profile Management | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Profile Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Profile Management | Profile Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Profile Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Profile Management | Profile Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Profile Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Profile Management | Profile Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Profile Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Profile Management | Profile Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Profile Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Reporting And Dashboards | Reporting And Dashboards | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Reporting And Dashboards' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Reporting And Dashboards | Reporting And Dashboards | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Reporting And Dashboards' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Reporting And Dashboards | Reporting And Dashboards | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Reporting And Dashboards' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Reporting And Dashboards | Reporting And Dashboards | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Reporting And Dashboards' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Reporting And Dashboards | Reporting And Dashboards | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Reporting And Dashboards' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Api Business Coverage | Api Business Coverage | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Api Business Coverage' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Api Business Coverage | Api Business Coverage | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Api Business Coverage' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Api Business Coverage | Api Business Coverage | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Api Business Coverage' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Api Business Coverage | Api Business Coverage | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Api Business Coverage' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Api Business Coverage | Api Business Coverage | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Api Business Coverage' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Campaign Management | Campaign Management | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Campaign Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Campaign Management | Campaign Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Campaign Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Campaign Management | Campaign Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Campaign Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Campaign Management | Campaign Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Campaign Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Campaign Management | Campaign Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Campaign Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Case Management And Sla | Case Management And Sla | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Case Management And Sla' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Case Management And Sla | Case Management And Sla | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Case Management And Sla' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Case Management And Sla | Case Management And Sla | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Case Management And Sla' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Case Management And Sla | Case Management And Sla | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Case Management And Sla' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Case Management And Sla | Case Management And Sla | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Case Management And Sla' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Seo Management And Optimization | Seo Management And Optimization | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Seo Management And Optimization' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Seo Management And Optimization | Seo Management And Optimization | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Seo Management And Optimization' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Seo Management And Optimization | Seo Management And Optimization | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Seo Management And Optimization' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Seo Management And Optimization | Seo Management And Optimization | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Seo Management And Optimization' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Seo Management And Optimization | Seo Management And Optimization | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Seo Management And Optimization' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Ticket Resale Marketplace | Ticket Resale Marketplace | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Ticket Resale Marketplace' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Ticket Resale Marketplace | Ticket Resale Marketplace | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Ticket Resale Marketplace' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Ticket Resale Marketplace | Ticket Resale Marketplace | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Ticket Resale Marketplace' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Ticket Resale Marketplace | Ticket Resale Marketplace | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Ticket Resale Marketplace' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Ticket Resale Marketplace | Ticket Resale Marketplace | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Ticket Resale Marketplace' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Ticket Upgrades | Ticket Upgrades | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Ticket Upgrades' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Ticket Upgrades | Ticket Upgrades | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Ticket Upgrades' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Ticket Upgrades | Ticket Upgrades | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Ticket Upgrades' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Ticket Upgrades | Ticket Upgrades | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Ticket Upgrades' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Ticket Upgrades | Ticket Upgrades | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Ticket Upgrades' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Portfolio Management | Portfolio Management | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Portfolio Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Portfolio Management | Portfolio Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Portfolio Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Portfolio Management | Portfolio Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Portfolio Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Portfolio Management | Portfolio Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Portfolio Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Portfolio Management | Portfolio Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Portfolio Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Demand Forecasting | Demand Forecasting | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Demand Forecasting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E09 Membership & Subscriptions | Demand Forecasting | Demand Forecasting | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Demand Forecasting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E09 Membership & Subscriptions | Demand Forecasting | Demand Forecasting | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Demand Forecasting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E09 Membership & Subscriptions | Demand Forecasting | Demand Forecasting | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Demand Forecasting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E09 Membership & Subscriptions | Demand Forecasting | Demand Forecasting | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Demand Forecasting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E09 Membership & Subscriptions | Ai Engine | Ai Engine | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Ai Engine' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Ai Engine | Ai Engine | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Ai Engine' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Ai Engine | Ai Engine | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Ai Engine' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Ai Engine | Ai Engine | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Ai Engine' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Ai Engine | Ai Engine | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Ai Engine' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Recommendation Engine | Recommendation Engine | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Recommendation Engine' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E09 Membership & Subscriptions | Recommendation Engine | Recommendation Engine | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Recommendation Engine' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E09 Membership & Subscriptions | Recommendation Engine | Recommendation Engine | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Recommendation Engine' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E09 Membership & Subscriptions | Recommendation Engine | Recommendation Engine | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Recommendation Engine' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E09 Membership & Subscriptions | Recommendation Engine | Recommendation Engine | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Recommendation Engine' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E09 Membership & Subscriptions | Bi And Reporting | Bi And Reporting | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Bi And Reporting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Bi And Reporting | Bi And Reporting | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Bi And Reporting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Bi And Reporting | Bi And Reporting | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Bi And Reporting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Bi And Reporting | Bi And Reporting | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Bi And Reporting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Bi And Reporting | Bi And Reporting | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Bi And Reporting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Operations Command Center | Operations Command Center | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Operations Command Center' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Operations Command Center | Operations Command Center | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Operations Command Center' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Operations Command Center | Operations Command Center | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Operations Command Center' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Operations Command Center | Operations Command Center | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Operations Command Center' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Operations Command Center | Operations Command Center | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Operations Command Center' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Accounting | Accounting | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Accounting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Accounting | Accounting | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Accounting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Accounting | Accounting | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Accounting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Accounting | Accounting | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Accounting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Accounting | Accounting | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Accounting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Subscription Management | Subscription Management | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Subscription Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Subscription Management | Subscription Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Subscription Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Subscription Management | Subscription Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Subscription Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Subscription Management | Subscription Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Subscription Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E09 Membership & Subscriptions | Subscription Management | Subscription Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Subscription Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E10 Events, Seating & Venue Mapping | Event Management | Event Management | Data model & schema | Define entities, relationships, constraints and migrations | 11 | 'Event Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Event Management | Event Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 16 | 'Event Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Event Management | Event Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 22 | 'Event Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Event Management | Event Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 11 | 'Event Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Event Management | Event Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 11 | 'Event Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Selection And Assignment | Seat Selection And Assignment | Data model & schema | Define entities, relationships, constraints and migrations | 7 | 'Seat Selection And Assignment' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Selection And Assignment | Seat Selection And Assignment | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 11 | 'Seat Selection And Assignment' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Selection And Assignment | Seat Selection And Assignment | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 14 | 'Seat Selection And Assignment' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Selection And Assignment | Seat Selection And Assignment | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 7 | 'Seat Selection And Assignment' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Selection And Assignment | Seat Selection And Assignment | Unit & integration tests | Automated tests incl. negative and concurrency cases | 7 | 'Seat Selection And Assignment' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Map Import | Seat Map Import | Data model & schema | Define entities, relationships, constraints and migrations | 5 | 'Seat Map Import' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Map Import | Seat Map Import | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 8 | 'Seat Map Import' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Map Import | Seat Map Import | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 11 | 'Seat Map Import' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Map Import | Seat Map Import | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 5 | 'Seat Map Import' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Map Import | Seat Map Import | Unit & integration tests | Automated tests incl. negative and concurrency cases | 5 | 'Seat Map Import' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Resource Management | Resource Management | Data model & schema | Define entities, relationships, constraints and migrations | 4 | 'Resource Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Resource Management | Resource Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 6 | 'Resource Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Resource Management | Resource Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 9 | 'Resource Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Resource Management | Resource Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 4 | 'Resource Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Resource Management | Resource Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 4 | 'Resource Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Call Center Sales | Call Center Sales | Data model & schema | Define entities, relationships, constraints and migrations | 3 | 'Call Center Sales' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Call Center Sales | Call Center Sales | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 5 | 'Call Center Sales' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Call Center Sales | Call Center Sales | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 7 | 'Call Center Sales' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Call Center Sales | Call Center Sales | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 3 | 'Call Center Sales' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Call Center Sales | Call Center Sales | Unit & integration tests | Automated tests incl. negative and concurrency cases | 3 | 'Call Center Sales' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Api Business Coverage | Api Business Coverage | Data model & schema | Define entities, relationships, constraints and migrations | 3 | 'Api Business Coverage' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Api Business Coverage | Api Business Coverage | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 5 | 'Api Business Coverage' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Api Business Coverage | Api Business Coverage | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 7 | 'Api Business Coverage' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Api Business Coverage | Api Business Coverage | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 3 | 'Api Business Coverage' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Api Business Coverage | Api Business Coverage | Unit & integration tests | Automated tests incl. negative and concurrency cases | 3 | 'Api Business Coverage' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Map Builder | Seat Map Builder | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Seat Map Builder' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Map Builder | Seat Map Builder | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Seat Map Builder' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Map Builder | Seat Map Builder | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Seat Map Builder' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Map Builder | Seat Map Builder | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Seat Map Builder' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Map Builder | Seat Map Builder | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Seat Map Builder' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Holds And Blocks | Seat Holds And Blocks | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Seat Holds And Blocks' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Holds And Blocks | Seat Holds And Blocks | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Seat Holds And Blocks' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Holds And Blocks | Seat Holds And Blocks | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Seat Holds And Blocks' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Holds And Blocks | Seat Holds And Blocks | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Seat Holds And Blocks' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Holds And Blocks | Seat Holds And Blocks | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Seat Holds And Blocks' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Preventive Maintenance Planning | Preventive Maintenance Planning | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Preventive Maintenance Planning' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Preventive Maintenance Planning | Preventive Maintenance Planning | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Preventive Maintenance Planning' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Preventive Maintenance Planning | Preventive Maintenance Planning | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Preventive Maintenance Planning' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Preventive Maintenance Planning | Preventive Maintenance Planning | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Preventive Maintenance Planning' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Preventive Maintenance Planning | Preventive Maintenance Planning | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Preventive Maintenance Planning' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Layout And Templates | Layout And Templates | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Layout And Templates' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Layout And Templates | Layout And Templates | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Layout And Templates' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Layout And Templates | Layout And Templates | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Layout And Templates' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Layout And Templates | Layout And Templates | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Layout And Templates' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Layout And Templates | Layout And Templates | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Layout And Templates' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Tracking And Holds | Seat Tracking And Holds | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Seat Tracking And Holds' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Tracking And Holds | Seat Tracking And Holds | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Seat Tracking And Holds' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Tracking And Holds | Seat Tracking And Holds | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Seat Tracking And Holds' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Tracking And Holds | Seat Tracking And Holds | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Seat Tracking And Holds' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Tracking And Holds | Seat Tracking And Holds | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Seat Tracking And Holds' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Recommendations | Seat Recommendations | Data model & schema | Define entities, relationships, constraints and migrations | 3 | 'Seat Recommendations' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Recommendations | Seat Recommendations | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 5 | 'Seat Recommendations' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Recommendations | Seat Recommendations | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 6 | 'Seat Recommendations' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Recommendations | Seat Recommendations | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 3 | 'Seat Recommendations' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Recommendations | Seat Recommendations | Unit & integration tests | Automated tests incl. negative and concurrency cases | 3 | 'Seat Recommendations' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Product Lifecycle | Product Lifecycle | Data model & schema | Define entities, relationships, constraints and migrations | 3 | 'Product Lifecycle' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Product Lifecycle | Product Lifecycle | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 4 | 'Product Lifecycle' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Product Lifecycle | Product Lifecycle | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 6 | 'Product Lifecycle' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Product Lifecycle | Product Lifecycle | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 3 | 'Product Lifecycle' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Product Lifecycle | Product Lifecycle | Unit & integration tests | Automated tests incl. negative and concurrency cases | 3 | 'Product Lifecycle' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Accounting | Accounting | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Accounting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Accounting | Accounting | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Accounting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Accounting | Accounting | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Accounting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Accounting | Accounting | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Accounting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Accounting | Accounting | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Accounting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Reporting And Dashboards | Reporting And Dashboards | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Reporting And Dashboards' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Reporting And Dashboards | Reporting And Dashboards | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Reporting And Dashboards' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Reporting And Dashboards | Reporting And Dashboards | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Reporting And Dashboards' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Reporting And Dashboards | Reporting And Dashboards | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Reporting And Dashboards' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Reporting And Dashboards | Reporting And Dashboards | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Reporting And Dashboards' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seating Rules And Buffer | Seating Rules And Buffer | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Seating Rules And Buffer' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seating Rules And Buffer | Seating Rules And Buffer | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Seating Rules And Buffer' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seating Rules And Buffer | Seating Rules And Buffer | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Seating Rules And Buffer' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seating Rules And Buffer | Seating Rules And Buffer | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Seating Rules And Buffer' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seating Rules And Buffer | Seating Rules And Buffer | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Seating Rules And Buffer' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Platform And Api | Seat Platform And Api | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Seat Platform And Api' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Platform And Api | Seat Platform And Api | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Seat Platform And Api' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Platform And Api | Seat Platform And Api | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Seat Platform And Api' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Platform And Api | Seat Platform And Api | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Seat Platform And Api' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Platform And Api | Seat Platform And Api | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Seat Platform And Api' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Ticket Types | Ticket Types | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Ticket Types' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Ticket Types | Ticket Types | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Ticket Types' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Ticket Types | Ticket Types | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Ticket Types' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Ticket Types | Ticket Types | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Ticket Types' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Ticket Types | Ticket Types | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Ticket Types' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Reporting And Analytics | Seat Reporting And Analytics | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Seat Reporting And Analytics' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Reporting And Analytics | Seat Reporting And Analytics | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Seat Reporting And Analytics' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Reporting And Analytics | Seat Reporting And Analytics | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Seat Reporting And Analytics' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Reporting And Analytics | Seat Reporting And Analytics | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Seat Reporting And Analytics' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Reporting And Analytics | Seat Reporting And Analytics | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Seat Reporting And Analytics' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Access Control System | Access Control System | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Access Control System' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Access Control System | Access Control System | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Access Control System' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Access Control System | Access Control System | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 5 | 'Access Control System' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Access Control System | Access Control System | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Access Control System' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Access Control System | Access Control System | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Access Control System' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Demand Forecasting | Demand Forecasting | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Demand Forecasting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Demand Forecasting | Demand Forecasting | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Demand Forecasting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Demand Forecasting | Demand Forecasting | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 5 | 'Demand Forecasting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Demand Forecasting | Demand Forecasting | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Demand Forecasting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Demand Forecasting | Demand Forecasting | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Demand Forecasting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Accessible Seating | Accessible Seating | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Accessible Seating' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Accessible Seating | Accessible Seating | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Accessible Seating' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Accessible Seating | Accessible Seating | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Accessible Seating' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Accessible Seating | Accessible Seating | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Accessible Seating' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Accessible Seating | Accessible Seating | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Accessible Seating' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Ticket Resale Marketplace | Ticket Resale Marketplace | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Ticket Resale Marketplace' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Ticket Resale Marketplace | Ticket Resale Marketplace | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Ticket Resale Marketplace' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Ticket Resale Marketplace | Ticket Resale Marketplace | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Ticket Resale Marketplace' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Ticket Resale Marketplace | Ticket Resale Marketplace | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Ticket Resale Marketplace' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Ticket Resale Marketplace | Ticket Resale Marketplace | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Ticket Resale Marketplace' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Ticket Media | Ticket Media | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Ticket Media' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Ticket Media | Ticket Media | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Ticket Media' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Ticket Media | Ticket Media | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Ticket Media' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Ticket Media | Ticket Media | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Ticket Media' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Ticket Media | Ticket Media | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Ticket Media' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E10 Events, Seating & Venue Mapping | Shift Opening And Closing | Shift Opening And Closing | POS screen & flow | Build cashier/kiosk UI and transaction flow | 1 | 'Shift Opening And Closing' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
POS App | E10 Events, Seating & Venue Mapping | Shift Opening And Closing | Shift Opening And Closing | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 1 | 'Shift Opening And Closing' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
POS App | E10 Events, Seating & Venue Mapping | Shift Opening And Closing | Shift Opening And Closing | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 1 | 'Shift Opening And Closing' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
POS App | E10 Events, Seating & Venue Mapping | Shift Opening And Closing | Shift Opening And Closing | Offline handling & sync | Local cache, queue and conflict resolution | 1 | 'Shift Opening And Closing' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
POS App | E10 Events, Seating & Venue Mapping | Shift Opening And Closing | Shift Opening And Closing | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 1 | 'Shift Opening And Closing' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Campaign Management | Campaign Management | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Campaign Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Campaign Management | Campaign Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Campaign Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Campaign Management | Campaign Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Campaign Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Campaign Management | Campaign Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Campaign Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Campaign Management | Campaign Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Campaign Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Gamification And Loyalty | Gamification And Loyalty | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Gamification And Loyalty' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Gamification And Loyalty | Gamification And Loyalty | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Gamification And Loyalty' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Gamification And Loyalty | Gamification And Loyalty | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Gamification And Loyalty' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Gamification And Loyalty | Gamification And Loyalty | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Gamification And Loyalty' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Gamification And Loyalty | Gamification And Loyalty | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Gamification And Loyalty' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Cash Handling | Cash Handling | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Cash Handling' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Cash Handling | Cash Handling | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Cash Handling' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Cash Handling | Cash Handling | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Cash Handling' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Cash Handling | Cash Handling | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Cash Handling' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Cash Handling | Cash Handling | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Cash Handling' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Ai Governance | Ai Governance | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Ai Governance' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Ai Governance | Ai Governance | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Ai Governance' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Ai Governance | Ai Governance | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Ai Governance' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Ai Governance | Ai Governance | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Ai Governance' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Ai Governance | Ai Governance | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Ai Governance' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Recommendation Engine | Recommendation Engine | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Recommendation Engine' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Recommendation Engine | Recommendation Engine | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Recommendation Engine' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Recommendation Engine | Recommendation Engine | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Recommendation Engine' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Recommendation Engine | Recommendation Engine | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Recommendation Engine' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Recommendation Engine | Recommendation Engine | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Recommendation Engine' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Revenue Management And Forecasting | Seat Revenue Management And Forecasting | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Seat Revenue Management And Forecasting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Revenue Management And Forecasting | Seat Revenue Management And Forecasting | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Seat Revenue Management And Forecasting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Revenue Management And Forecasting | Seat Revenue Management And Forecasting | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Seat Revenue Management And Forecasting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Revenue Management And Forecasting | Seat Revenue Management And Forecasting | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Seat Revenue Management And Forecasting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seat Revenue Management And Forecasting | Seat Revenue Management And Forecasting | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Seat Revenue Management And Forecasting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Case Management And Sla | Case Management And Sla | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Case Management And Sla' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Case Management And Sla | Case Management And Sla | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Case Management And Sla' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Case Management And Sla | Case Management And Sla | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Case Management And Sla' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Case Management And Sla | Case Management And Sla | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Case Management And Sla' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Case Management And Sla | Case Management And Sla | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Case Management And Sla' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Newsletter And Email Marketing | Newsletter And Email Marketing | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Newsletter And Email Marketing' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Newsletter And Email Marketing | Newsletter And Email Marketing | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Newsletter And Email Marketing' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Newsletter And Email Marketing | Newsletter And Email Marketing | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Newsletter And Email Marketing' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Newsletter And Email Marketing | Newsletter And Email Marketing | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Newsletter And Email Marketing' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Newsletter And Email Marketing | Newsletter And Email Marketing | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Newsletter And Email Marketing' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Notifications And Messaging | Notifications And Messaging | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Notifications And Messaging' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Notifications And Messaging | Notifications And Messaging | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Notifications And Messaging' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Notifications And Messaging | Notifications And Messaging | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Notifications And Messaging' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Notifications And Messaging | Notifications And Messaging | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Notifications And Messaging' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Notifications And Messaging | Notifications And Messaging | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Notifications And Messaging' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Marketing | Marketing | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Marketing' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Marketing | Marketing | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Marketing' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Marketing | Marketing | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Marketing' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Marketing | Marketing | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Marketing' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Marketing | Marketing | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Marketing' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Digital Waiver Management | Digital Waiver Management | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Digital Waiver Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Digital Waiver Management | Digital Waiver Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Digital Waiver Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Digital Waiver Management | Digital Waiver Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Digital Waiver Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Digital Waiver Management | Digital Waiver Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Digital Waiver Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Digital Waiver Management | Digital Waiver Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Digital Waiver Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
POS App | E10 Events, Seating & Venue Mapping | Profile Management | Profile Management | POS screen & flow | Build cashier/kiosk UI and transaction flow | 1 | 'Profile Management' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
POS App | E10 Events, Seating & Venue Mapping | Profile Management | Profile Management | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 1 | 'Profile Management' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
POS App | E10 Events, Seating & Venue Mapping | Profile Management | Profile Management | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 1 | 'Profile Management' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
POS App | E10 Events, Seating & Venue Mapping | Profile Management | Profile Management | Offline handling & sync | Local cache, queue and conflict resolution | 1 | 'Profile Management' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
POS App | E10 Events, Seating & Venue Mapping | Profile Management | Profile Management | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 1 | 'Profile Management' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Loyalty | Loyalty | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Loyalty' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Loyalty | Loyalty | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Loyalty' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Loyalty | Loyalty | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Loyalty' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Loyalty | Loyalty | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Loyalty' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Loyalty | Loyalty | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Loyalty' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Portfolio And Entitlement Management | Portfolio And Entitlement Management | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Portfolio And Entitlement Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Portfolio And Entitlement Management | Portfolio And Entitlement Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Portfolio And Entitlement Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Portfolio And Entitlement Management | Portfolio And Entitlement Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Portfolio And Entitlement Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Portfolio And Entitlement Management | Portfolio And Entitlement Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Portfolio And Entitlement Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Portfolio And Entitlement Management | Portfolio And Entitlement Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Portfolio And Entitlement Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Ai Configuration Assistant | Ai Configuration Assistant | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Ai Configuration Assistant' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Ai Configuration Assistant | Ai Configuration Assistant | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Ai Configuration Assistant' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Ai Configuration Assistant | Ai Configuration Assistant | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Ai Configuration Assistant' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Ai Configuration Assistant | Ai Configuration Assistant | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Ai Configuration Assistant' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Ai Configuration Assistant | Ai Configuration Assistant | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Ai Configuration Assistant' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E10 Events, Seating & Venue Mapping | Operations Command Center | Operations Command Center | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Operations Command Center' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Operations Command Center | Operations Command Center | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Operations Command Center' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Operations Command Center | Operations Command Center | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Operations Command Center' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Operations Command Center | Operations Command Center | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Operations Command Center' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Operations Command Center | Operations Command Center | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Operations Command Center' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Cross Platform | E10 Events, Seating & Venue Mapping | Sandbox | Sandbox | Design & technical spec | Architecture, interfaces and acceptance criteria | 1 | 'Sandbox' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Cross Platform | E10 Events, Seating & Venue Mapping | Sandbox | Sandbox | Implementation | Build the capability / automation | 2 | 'Sandbox' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Cross Platform | E10 Events, Seating & Venue Mapping | Sandbox | Sandbox | Automation & CI integration | Pipeline, IaC and gates | 1 | 'Sandbox' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Cross Platform | E10 Events, Seating & Venue Mapping | Sandbox | Sandbox | Verification & sign-off | Validate against NFR/acceptance criteria | 1 | 'Sandbox' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Cross Platform | E10 Events, Seating & Venue Mapping | Device Monitoring | Device Monitoring | Design & technical spec | Architecture, interfaces and acceptance criteria | 1 | 'Device Monitoring' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Cross Platform | E10 Events, Seating & Venue Mapping | Device Monitoring | Device Monitoring | Implementation | Build the capability / automation | 2 | 'Device Monitoring' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Cross Platform | E10 Events, Seating & Venue Mapping | Device Monitoring | Device Monitoring | Automation & CI integration | Pipeline, IaC and gates | 1 | 'Device Monitoring' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Cross Platform | E10 Events, Seating & Venue Mapping | Device Monitoring | Device Monitoring | Verification & sign-off | Validate against NFR/acceptance criteria | 1 | 'Device Monitoring' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Device Maintenance | Device Maintenance | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Device Maintenance' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Device Maintenance | Device Maintenance | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Device Maintenance' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Device Maintenance | Device Maintenance | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Device Maintenance' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Device Maintenance | Device Maintenance | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Device Maintenance' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Device Maintenance | Device Maintenance | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Device Maintenance' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Maintenance Reporting And Analytics | Maintenance Reporting And Analytics | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Maintenance Reporting And Analytics' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Maintenance Reporting And Analytics | Maintenance Reporting And Analytics | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Maintenance Reporting And Analytics' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Maintenance Reporting And Analytics | Maintenance Reporting And Analytics | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Maintenance Reporting And Analytics' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Maintenance Reporting And Analytics | Maintenance Reporting And Analytics | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Maintenance Reporting And Analytics' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Maintenance Reporting And Analytics | Maintenance Reporting And Analytics | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Maintenance Reporting And Analytics' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Mobile App | E10 Events, Seating & Venue Mapping | Authentication And Login | Authentication And Login | UI screens (iOS & Android) | Implement shared + platform UI components | 2 | 'Authentication And Login' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Mobile App | E10 Events, Seating & Venue Mapping | Authentication And Login | Authentication And Login | State & API integration | Data layer, caching and API wiring | 2 | 'Authentication And Login' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Mobile App | E10 Events, Seating & Venue Mapping | Authentication And Login | Authentication And Login | Offline & push handling | Offline storage, sync and push notifications | 1 | 'Authentication And Login' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Mobile App | E10 Events, Seating & Venue Mapping | Authentication And Login | Authentication And Login | Mobile E2E tests | Automated tests across iOS/Android | 1 | 'Authentication And Login' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Reviews And Ratings | Reviews And Ratings | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Reviews And Ratings' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Reviews And Ratings | Reviews And Ratings | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Reviews And Ratings' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Reviews And Ratings | Reviews And Ratings | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Reviews And Ratings' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Reviews And Ratings | Reviews And Ratings | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Reviews And Ratings' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Reviews And Ratings | Reviews And Ratings | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Reviews And Ratings' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Omnichannel Communications And Ai Chatbot | Omnichannel Communications And Ai Chatbot | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Omnichannel Communications And Ai Chatbot' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Omnichannel Communications And Ai Chatbot | Omnichannel Communications And Ai Chatbot | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Omnichannel Communications And Ai Chatbot' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Omnichannel Communications And Ai Chatbot | Omnichannel Communications And Ai Chatbot | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Omnichannel Communications And Ai Chatbot' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Omnichannel Communications And Ai Chatbot | Omnichannel Communications And Ai Chatbot | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Omnichannel Communications And Ai Chatbot' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Omnichannel Communications And Ai Chatbot | Omnichannel Communications And Ai Chatbot | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Omnichannel Communications And Ai Chatbot' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seo Management And Optimization | Seo Management And Optimization | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Seo Management And Optimization' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seo Management And Optimization | Seo Management And Optimization | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Seo Management And Optimization' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seo Management And Optimization | Seo Management And Optimization | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Seo Management And Optimization' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seo Management And Optimization | Seo Management And Optimization | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Seo Management And Optimization' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Seo Management And Optimization | Seo Management And Optimization | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Seo Management And Optimization' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Digital Waivers And Signature Management | Digital Waivers And Signature Management | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Digital Waivers And Signature Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Digital Waivers And Signature Management | Digital Waivers And Signature Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Digital Waivers And Signature Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Digital Waivers And Signature Management | Digital Waivers And Signature Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Digital Waivers And Signature Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Digital Waivers And Signature Management | Digital Waivers And Signature Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Digital Waivers And Signature Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Digital Waivers And Signature Management | Digital Waivers And Signature Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Digital Waivers And Signature Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Consent Management | Consent Management | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Consent Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Consent Management | Consent Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Consent Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Consent Management | Consent Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Consent Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Consent Management | Consent Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Consent Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Consent Management | Consent Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Consent Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Audience Segmentation | Audience Segmentation | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Audience Segmentation' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Audience Segmentation | Audience Segmentation | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Audience Segmentation' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Audience Segmentation | Audience Segmentation | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Audience Segmentation' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Audience Segmentation | Audience Segmentation | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Audience Segmentation' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E10 Events, Seating & Venue Mapping | Audience Segmentation | Audience Segmentation | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Audience Segmentation' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M2 - Core Platform
Server Side / Backend | E11 Bundles, Promotions & Pricing | Promotions | Promotions | Data model & schema | Define entities, relationships, constraints and migrations | 13 | 'Promotions' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Promotions | Promotions | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 19 | 'Promotions' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Promotions | Promotions | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 26 | 'Promotions' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Promotions | Promotions | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 13 | 'Promotions' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Promotions | Promotions | Unit & integration tests | Automated tests incl. negative and concurrency cases | 13 | 'Promotions' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Dynamic Pricing | Dynamic Pricing | Data model & schema | Define entities, relationships, constraints and migrations | 12 | 'Dynamic Pricing' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Dynamic Pricing | Dynamic Pricing | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 18 | 'Dynamic Pricing' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Dynamic Pricing | Dynamic Pricing | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 24 | 'Dynamic Pricing' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Dynamic Pricing | Dynamic Pricing | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 12 | 'Dynamic Pricing' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Dynamic Pricing | Dynamic Pricing | Unit & integration tests | Automated tests incl. negative and concurrency cases | 12 | 'Dynamic Pricing' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Pricing | Pricing | Data model & schema | Define entities, relationships, constraints and migrations | 12 | 'Pricing' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Pricing | Pricing | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 18 | 'Pricing' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Pricing | Pricing | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 23 | 'Pricing' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Pricing | Pricing | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 12 | 'Pricing' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Pricing | Pricing | Unit & integration tests | Automated tests incl. negative and concurrency cases | 12 | 'Pricing' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Bundles | Bundles | Data model & schema | Define entities, relationships, constraints and migrations | 10 | 'Bundles' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Bundles | Bundles | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 15 | 'Bundles' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Bundles | Bundles | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 20 | 'Bundles' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Bundles | Bundles | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 10 | 'Bundles' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Bundles | Bundles | Unit & integration tests | Automated tests incl. negative and concurrency cases | 10 | 'Bundles' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Upsell And Cross-Sell | Upsell And Cross-Sell | Data model & schema | Define entities, relationships, constraints and migrations | 7 | 'Upsell And Cross-Sell' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Upsell And Cross-Sell | Upsell And Cross-Sell | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 10 | 'Upsell And Cross-Sell' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Upsell And Cross-Sell | Upsell And Cross-Sell | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 13 | 'Upsell And Cross-Sell' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Upsell And Cross-Sell | Upsell And Cross-Sell | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 7 | 'Upsell And Cross-Sell' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Upsell And Cross-Sell | Upsell And Cross-Sell | Unit & integration tests | Automated tests incl. negative and concurrency cases | 7 | 'Upsell And Cross-Sell' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Ai Configuration Assistant | Ai Configuration Assistant | Data model & schema | Define entities, relationships, constraints and migrations | 5 | 'Ai Configuration Assistant' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Ai Configuration Assistant | Ai Configuration Assistant | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 8 | 'Ai Configuration Assistant' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Ai Configuration Assistant | Ai Configuration Assistant | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 10 | 'Ai Configuration Assistant' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Ai Configuration Assistant | Ai Configuration Assistant | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 5 | 'Ai Configuration Assistant' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Ai Configuration Assistant | Ai Configuration Assistant | Unit & integration tests | Automated tests incl. negative and concurrency cases | 5 | 'Ai Configuration Assistant' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E11 Bundles, Promotions & Pricing | Sales Channels | Sales Channels | POS screen & flow | Build cashier/kiosk UI and transaction flow | 6 | 'Sales Channels' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E11 Bundles, Promotions & Pricing | Sales Channels | Sales Channels | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 4 | 'Sales Channels' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E11 Bundles, Promotions & Pricing | Sales Channels | Sales Channels | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 6 | 'Sales Channels' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E11 Bundles, Promotions & Pricing | Sales Channels | Sales Channels | Offline handling & sync | Local cache, queue and conflict resolution | 6 | 'Sales Channels' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E11 Bundles, Promotions & Pricing | Sales Channels | Sales Channels | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 4 | 'Sales Channels' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Ticket Upgrades | Ticket Upgrades | Data model & schema | Define entities, relationships, constraints and migrations | 4 | 'Ticket Upgrades' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Ticket Upgrades | Ticket Upgrades | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 6 | 'Ticket Upgrades' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Ticket Upgrades | Ticket Upgrades | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 8 | 'Ticket Upgrades' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Ticket Upgrades | Ticket Upgrades | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 4 | 'Ticket Upgrades' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Ticket Upgrades | Ticket Upgrades | Unit & integration tests | Automated tests incl. negative and concurrency cases | 4 | 'Ticket Upgrades' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Ticket Types | Ticket Types | Data model & schema | Define entities, relationships, constraints and migrations | 4 | 'Ticket Types' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Ticket Types | Ticket Types | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 6 | 'Ticket Types' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Ticket Types | Ticket Types | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 8 | 'Ticket Types' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Ticket Types | Ticket Types | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 4 | 'Ticket Types' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Ticket Types | Ticket Types | Unit & integration tests | Automated tests incl. negative and concurrency cases | 4 | 'Ticket Types' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Recommendation Engine | Recommendation Engine | Data model & schema | Define entities, relationships, constraints and migrations | 4 | 'Recommendation Engine' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Recommendation Engine | Recommendation Engine | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 5 | 'Recommendation Engine' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Recommendation Engine | Recommendation Engine | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 7 | 'Recommendation Engine' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Recommendation Engine | Recommendation Engine | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 4 | 'Recommendation Engine' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Recommendation Engine | Recommendation Engine | Unit & integration tests | Automated tests incl. negative and concurrency cases | 4 | 'Recommendation Engine' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Fandb And Retail Offers And Promotions | Fandb And Retail Offers And Promotions | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Fandb And Retail Offers And Promotions' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Fandb And Retail Offers And Promotions | Fandb And Retail Offers And Promotions | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Fandb And Retail Offers And Promotions' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Fandb And Retail Offers And Promotions | Fandb And Retail Offers And Promotions | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Fandb And Retail Offers And Promotions' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Fandb And Retail Offers And Promotions | Fandb And Retail Offers And Promotions | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Fandb And Retail Offers And Promotions' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Fandb And Retail Offers And Promotions | Fandb And Retail Offers And Promotions | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Fandb And Retail Offers And Promotions' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Marketing | Marketing | Data model & schema | Define entities, relationships, constraints and migrations | 3 | 'Marketing' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Marketing | Marketing | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 5 | 'Marketing' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Marketing | Marketing | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 6 | 'Marketing' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Marketing | Marketing | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 3 | 'Marketing' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Marketing | Marketing | Unit & integration tests | Automated tests incl. negative and concurrency cases | 3 | 'Marketing' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Event Management | Event Management | Data model & schema | Define entities, relationships, constraints and migrations | 3 | 'Event Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Event Management | Event Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 4 | 'Event Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Event Management | Event Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 6 | 'Event Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Event Management | Event Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 3 | 'Event Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Event Management | Event Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 3 | 'Event Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Product Lifecycle | Product Lifecycle | Data model & schema | Define entities, relationships, constraints and migrations | 3 | 'Product Lifecycle' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Product Lifecycle | Product Lifecycle | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 4 | 'Product Lifecycle' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Product Lifecycle | Product Lifecycle | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 6 | 'Product Lifecycle' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Product Lifecycle | Product Lifecycle | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 3 | 'Product Lifecycle' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Product Lifecycle | Product Lifecycle | Unit & integration tests | Automated tests incl. negative and concurrency cases | 3 | 'Product Lifecycle' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Call Center Sales | Call Center Sales | Data model & schema | Define entities, relationships, constraints and migrations | 3 | 'Call Center Sales' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Call Center Sales | Call Center Sales | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 4 | 'Call Center Sales' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Call Center Sales | Call Center Sales | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 6 | 'Call Center Sales' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Call Center Sales | Call Center Sales | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 3 | 'Call Center Sales' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Call Center Sales | Call Center Sales | Unit & integration tests | Automated tests incl. negative and concurrency cases | 3 | 'Call Center Sales' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Loyalty | Loyalty | Data model & schema | Define entities, relationships, constraints and migrations | 3 | 'Loyalty' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Loyalty | Loyalty | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 4 | 'Loyalty' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Loyalty | Loyalty | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 6 | 'Loyalty' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Loyalty | Loyalty | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 3 | 'Loyalty' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Loyalty | Loyalty | Unit & integration tests | Automated tests incl. negative and concurrency cases | 3 | 'Loyalty' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Accounting | Accounting | Data model & schema | Define entities, relationships, constraints and migrations | 3 | 'Accounting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Accounting | Accounting | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 4 | 'Accounting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Accounting | Accounting | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 6 | 'Accounting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Accounting | Accounting | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 3 | 'Accounting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Accounting | Accounting | Unit & integration tests | Automated tests incl. negative and concurrency cases | 3 | 'Accounting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Ai Engine | Ai Engine | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Ai Engine' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Ai Engine | Ai Engine | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Ai Engine' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Ai Engine | Ai Engine | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Ai Engine' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Ai Engine | Ai Engine | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Ai Engine' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Ai Engine | Ai Engine | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Ai Engine' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Membership | Membership | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Membership' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Membership | Membership | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Membership' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Membership | Membership | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Membership' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Membership | Membership | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Membership' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Membership | Membership | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Membership' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E11 Bundles, Promotions & Pricing | Front Gate Sales | Front Gate Sales | POS screen & flow | Build cashier/kiosk UI and transaction flow | 3 | 'Front Gate Sales' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E11 Bundles, Promotions & Pricing | Front Gate Sales | Front Gate Sales | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 2 | 'Front Gate Sales' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E11 Bundles, Promotions & Pricing | Front Gate Sales | Front Gate Sales | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 3 | 'Front Gate Sales' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E11 Bundles, Promotions & Pricing | Front Gate Sales | Front Gate Sales | Offline handling & sync | Local cache, queue and conflict resolution | 3 | 'Front Gate Sales' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E11 Bundles, Promotions & Pricing | Front Gate Sales | Front Gate Sales | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 2 | 'Front Gate Sales' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Game And Ride Payment And Redemption | Game And Ride Payment And Redemption | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Game And Ride Payment And Redemption' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Game And Ride Payment And Redemption | Game And Ride Payment And Redemption | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Game And Ride Payment And Redemption' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Game And Ride Payment And Redemption | Game And Ride Payment And Redemption | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Game And Ride Payment And Redemption' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Game And Ride Payment And Redemption | Game And Ride Payment And Redemption | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Game And Ride Payment And Redemption' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Game And Ride Payment And Redemption | Game And Ride Payment And Redemption | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Game And Ride Payment And Redemption' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Campaign Management | Campaign Management | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Campaign Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Campaign Management | Campaign Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Campaign Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Campaign Management | Campaign Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Campaign Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Campaign Management | Campaign Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Campaign Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Campaign Management | Campaign Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Campaign Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Case Management And Sla | Case Management And Sla | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Case Management And Sla' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Case Management And Sla | Case Management And Sla | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Case Management And Sla' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Case Management And Sla | Case Management And Sla | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Case Management And Sla' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Case Management And Sla | Case Management And Sla | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Case Management And Sla' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Case Management And Sla | Case Management And Sla | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Case Management And Sla' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Newsletter And Email Marketing | Newsletter And Email Marketing | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Newsletter And Email Marketing' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Newsletter And Email Marketing | Newsletter And Email Marketing | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Newsletter And Email Marketing' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Newsletter And Email Marketing | Newsletter And Email Marketing | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Newsletter And Email Marketing' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Newsletter And Email Marketing | Newsletter And Email Marketing | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Newsletter And Email Marketing' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Newsletter And Email Marketing | Newsletter And Email Marketing | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Newsletter And Email Marketing' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Ticket Media | Ticket Media | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Ticket Media' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Ticket Media | Ticket Media | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Ticket Media' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Ticket Media | Ticket Media | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Ticket Media' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Ticket Media | Ticket Media | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Ticket Media' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Ticket Media | Ticket Media | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Ticket Media' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Virtual Queue | Virtual Queue | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Virtual Queue' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Virtual Queue | Virtual Queue | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Virtual Queue' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Virtual Queue | Virtual Queue | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Virtual Queue' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Virtual Queue | Virtual Queue | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Virtual Queue' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Virtual Queue | Virtual Queue | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Virtual Queue' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Ai Governance | Ai Governance | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Ai Governance' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Ai Governance | Ai Governance | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Ai Governance' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Ai Governance | Ai Governance | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Ai Governance' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Ai Governance | Ai Governance | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Ai Governance' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Ai Governance | Ai Governance | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Ai Governance' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Api Business Coverage | Api Business Coverage | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Api Business Coverage' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Api Business Coverage | Api Business Coverage | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Api Business Coverage' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Api Business Coverage | Api Business Coverage | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Api Business Coverage' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Api Business Coverage | Api Business Coverage | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Api Business Coverage' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Api Business Coverage | Api Business Coverage | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Api Business Coverage' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Mobile App | E11 Bundles, Promotions & Pricing | Branding And White-Label Configuration | Branding And White-Label Configuration | UI screens (iOS & Android) | Implement shared + platform UI components | 2 | 'Branding And White-Label Configuration' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E11 Bundles, Promotions & Pricing | Branding And White-Label Configuration | Branding And White-Label Configuration | State & API integration | Data layer, caching and API wiring | 2 | 'Branding And White-Label Configuration' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E11 Bundles, Promotions & Pricing | Branding And White-Label Configuration | Branding And White-Label Configuration | Offline & push handling | Offline storage, sync and push notifications | 1 | 'Branding And White-Label Configuration' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E11 Bundles, Promotions & Pricing | Branding And White-Label Configuration | Branding And White-Label Configuration | Mobile E2E tests | Automated tests across iOS/Android | 1 | 'Branding And White-Label Configuration' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E11 Bundles, Promotions & Pricing | Authentication And Login | Authentication And Login | UI screens (iOS & Android) | Implement shared + platform UI components | 4 | 'Authentication And Login' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Mobile App | E11 Bundles, Promotions & Pricing | Authentication And Login | Authentication And Login | State & API integration | Data layer, caching and API wiring | 4 | 'Authentication And Login' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Mobile App | E11 Bundles, Promotions & Pricing | Authentication And Login | Authentication And Login | Offline & push handling | Offline storage, sync and push notifications | 2 | 'Authentication And Login' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Mobile App | E11 Bundles, Promotions & Pricing | Authentication And Login | Authentication And Login | Mobile E2E tests | Automated tests across iOS/Android | 2 | 'Authentication And Login' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Seat Revenue Management And Forecasting | Seat Revenue Management And Forecasting | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Seat Revenue Management And Forecasting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Seat Revenue Management And Forecasting | Seat Revenue Management And Forecasting | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Seat Revenue Management And Forecasting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Seat Revenue Management And Forecasting | Seat Revenue Management And Forecasting | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Seat Revenue Management And Forecasting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Seat Revenue Management And Forecasting | Seat Revenue Management And Forecasting | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Seat Revenue Management And Forecasting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Seat Revenue Management And Forecasting | Seat Revenue Management And Forecasting | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Seat Revenue Management And Forecasting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Reviews And Ratings | Reviews And Ratings | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Reviews And Ratings' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Reviews And Ratings | Reviews And Ratings | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Reviews And Ratings' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Reviews And Ratings | Reviews And Ratings | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Reviews And Ratings' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Reviews And Ratings | Reviews And Ratings | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Reviews And Ratings' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Reviews And Ratings | Reviews And Ratings | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Reviews And Ratings' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Notifications And Messaging | Notifications And Messaging | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Notifications And Messaging' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Notifications And Messaging | Notifications And Messaging | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Notifications And Messaging' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Notifications And Messaging | Notifications And Messaging | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Notifications And Messaging' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Notifications And Messaging | Notifications And Messaging | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Notifications And Messaging' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Notifications And Messaging | Notifications And Messaging | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Notifications And Messaging' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Seo Management And Optimization | Seo Management And Optimization | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Seo Management And Optimization' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Seo Management And Optimization | Seo Management And Optimization | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Seo Management And Optimization' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Seo Management And Optimization | Seo Management And Optimization | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Seo Management And Optimization' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Seo Management And Optimization | Seo Management And Optimization | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Seo Management And Optimization' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Seo Management And Optimization | Seo Management And Optimization | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Seo Management And Optimization' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | B2B Sales | B2B Sales | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'B2B Sales' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | B2B Sales | B2B Sales | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'B2B Sales' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | B2B Sales | B2B Sales | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'B2B Sales' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | B2B Sales | B2B Sales | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'B2B Sales' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | B2B Sales | B2B Sales | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'B2B Sales' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Digital Waiver Management | Digital Waiver Management | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Digital Waiver Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Digital Waiver Management | Digital Waiver Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Digital Waiver Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Digital Waiver Management | Digital Waiver Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Digital Waiver Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Digital Waiver Management | Digital Waiver Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Digital Waiver Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Digital Waiver Management | Digital Waiver Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Digital Waiver Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E11 Bundles, Promotions & Pricing | Order Management | Order Management | POS screen & flow | Build cashier/kiosk UI and transaction flow | 1 | 'Order Management' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E11 Bundles, Promotions & Pricing | Order Management | Order Management | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 1 | 'Order Management' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E11 Bundles, Promotions & Pricing | Order Management | Order Management | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 1 | 'Order Management' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E11 Bundles, Promotions & Pricing | Order Management | Order Management | Offline handling & sync | Local cache, queue and conflict resolution | 1 | 'Order Management' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
POS App | E11 Bundles, Promotions & Pricing | Order Management | Order Management | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 1 | 'Order Management' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Access Control System | Access Control System | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Access Control System' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Access Control System | Access Control System | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Access Control System' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Access Control System | Access Control System | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Access Control System' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Access Control System | Access Control System | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Access Control System' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Access Control System | Access Control System | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Access Control System' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Profile Management | Profile Management | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Profile Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Profile Management | Profile Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Profile Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Profile Management | Profile Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Profile Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Profile Management | Profile Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Profile Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Profile Management | Profile Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Profile Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Portfolio And Entitlement Management | Portfolio And Entitlement Management | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Portfolio And Entitlement Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Portfolio And Entitlement Management | Portfolio And Entitlement Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Portfolio And Entitlement Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Portfolio And Entitlement Management | Portfolio And Entitlement Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Portfolio And Entitlement Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Portfolio And Entitlement Management | Portfolio And Entitlement Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Portfolio And Entitlement Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Portfolio And Entitlement Management | Portfolio And Entitlement Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Portfolio And Entitlement Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Ai Governance And Explainability | Ai Governance And Explainability | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Ai Governance And Explainability' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Ai Governance And Explainability | Ai Governance And Explainability | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Ai Governance And Explainability' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Ai Governance And Explainability | Ai Governance And Explainability | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Ai Governance And Explainability' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Ai Governance And Explainability | Ai Governance And Explainability | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Ai Governance And Explainability' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Ai Governance And Explainability | Ai Governance And Explainability | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Ai Governance And Explainability' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Module Marketplace And Management | Module Marketplace And Management | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Module Marketplace And Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Module Marketplace And Management | Module Marketplace And Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Module Marketplace And Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Module Marketplace And Management | Module Marketplace And Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Module Marketplace And Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Module Marketplace And Management | Module Marketplace And Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Module Marketplace And Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Module Marketplace And Management | Module Marketplace And Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Module Marketplace And Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Seat Map Builder | Seat Map Builder | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Seat Map Builder' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Seat Map Builder | Seat Map Builder | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Seat Map Builder' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Seat Map Builder | Seat Map Builder | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Seat Map Builder' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Seat Map Builder | Seat Map Builder | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Seat Map Builder' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Seat Map Builder | Seat Map Builder | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Seat Map Builder' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Seat Selection And Assignment | Seat Selection And Assignment | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Seat Selection And Assignment' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Seat Selection And Assignment | Seat Selection And Assignment | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Seat Selection And Assignment' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Seat Selection And Assignment | Seat Selection And Assignment | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Seat Selection And Assignment' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Seat Selection And Assignment | Seat Selection And Assignment | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Seat Selection And Assignment' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Seat Selection And Assignment | Seat Selection And Assignment | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Seat Selection And Assignment' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Surveys And Feedback | Surveys And Feedback | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Surveys And Feedback' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Surveys And Feedback | Surveys And Feedback | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Surveys And Feedback' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Surveys And Feedback | Surveys And Feedback | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Surveys And Feedback' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Surveys And Feedback | Surveys And Feedback | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Surveys And Feedback' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Surveys And Feedback | Surveys And Feedback | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Surveys And Feedback' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Omnichannel Communications And Ai Chatbot | Omnichannel Communications And Ai Chatbot | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Omnichannel Communications And Ai Chatbot' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Omnichannel Communications And Ai Chatbot | Omnichannel Communications And Ai Chatbot | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Omnichannel Communications And Ai Chatbot' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Omnichannel Communications And Ai Chatbot | Omnichannel Communications And Ai Chatbot | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Omnichannel Communications And Ai Chatbot' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Omnichannel Communications And Ai Chatbot | Omnichannel Communications And Ai Chatbot | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Omnichannel Communications And Ai Chatbot' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Omnichannel Communications And Ai Chatbot | Omnichannel Communications And Ai Chatbot | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Omnichannel Communications And Ai Chatbot' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Consent Management | Consent Management | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Consent Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Consent Management | Consent Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Consent Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Consent Management | Consent Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Consent Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Consent Management | Consent Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Consent Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Consent Management | Consent Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Consent Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E11 Bundles, Promotions & Pricing | Audience Segmentation | Audience Segmentation | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Audience Segmentation' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Audience Segmentation | Audience Segmentation | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Audience Segmentation' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Audience Segmentation | Audience Segmentation | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Audience Segmentation' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Audience Segmentation | Audience Segmentation | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Audience Segmentation' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E11 Bundles, Promotions & Pricing | Audience Segmentation | Audience Segmentation | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Audience Segmentation' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Mobile App | E12 Guest Mobile Experience | Authentication And Login | Authentication And Login | UI screens (iOS & Android) | Implement shared + platform UI components | 21 | 'Authentication And Login' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Mobile App | E12 Guest Mobile Experience | Authentication And Login | Authentication And Login | State & API integration | Data layer, caching and API wiring | 21 | 'Authentication And Login' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Mobile App | E12 Guest Mobile Experience | Authentication And Login | Authentication And Login | Offline & push handling | Offline storage, sync and push notifications | 14 | 'Authentication And Login' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Mobile App | E12 Guest Mobile Experience | Authentication And Login | Authentication And Login | Mobile E2E tests | Automated tests across iOS/Android | 14 | 'Authentication And Login' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Mobile App | E12 Guest Mobile Experience | Branding And White-Label Configuration | Branding And White-Label Configuration | UI screens (iOS & Android) | Implement shared + platform UI components | 8 | 'Branding And White-Label Configuration' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E12 Guest Mobile Experience | Branding And White-Label Configuration | Branding And White-Label Configuration | State & API integration | Data layer, caching and API wiring | 8 | 'Branding And White-Label Configuration' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E12 Guest Mobile Experience | Branding And White-Label Configuration | Branding And White-Label Configuration | Offline & push handling | Offline storage, sync and push notifications | 5 | 'Branding And White-Label Configuration' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E12 Guest Mobile Experience | Branding And White-Label Configuration | Branding And White-Label Configuration | Mobile E2E tests | Automated tests across iOS/Android | 5 | 'Branding And White-Label Configuration' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E12 Guest Mobile Experience | Safety And Incident Reporting | Safety And Incident Reporting | UI screens (iOS & Android) | Implement shared + platform UI components | 3 | 'Safety And Incident Reporting' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E12 Guest Mobile Experience | Safety And Incident Reporting | Safety And Incident Reporting | State & API integration | Data layer, caching and API wiring | 3 | 'Safety And Incident Reporting' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E12 Guest Mobile Experience | Safety And Incident Reporting | Safety And Incident Reporting | Offline & push handling | Offline storage, sync and push notifications | 2 | 'Safety And Incident Reporting' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E12 Guest Mobile Experience | Safety And Incident Reporting | Safety And Incident Reporting | Mobile E2E tests | Automated tests across iOS/Android | 2 | 'Safety And Incident Reporting' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E12 Guest Mobile Experience | Mobile App Core (Ios And Android) | Mobile App Core (Ios And Android) | UI screens (iOS & Android) | Implement shared + platform UI components | 5 | 'Mobile App Core (Ios And Android)' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E12 Guest Mobile Experience | Mobile App Core (Ios And Android) | Mobile App Core (Ios And Android) | State & API integration | Data layer, caching and API wiring | 5 | 'Mobile App Core (Ios And Android)' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E12 Guest Mobile Experience | Mobile App Core (Ios And Android) | Mobile App Core (Ios And Android) | Offline & push handling | Offline storage, sync and push notifications | 3 | 'Mobile App Core (Ios And Android)' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E12 Guest Mobile Experience | Mobile App Core (Ios And Android) | Mobile App Core (Ios And Android) | Mobile E2E tests | Automated tests across iOS/Android | 3 | 'Mobile App Core (Ios And Android)' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E12 Guest Mobile Experience | Media Capture And Notes | Media Capture And Notes | UI screens (iOS & Android) | Implement shared + platform UI components | 3 | 'Media Capture And Notes' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E12 Guest Mobile Experience | Media Capture And Notes | Media Capture And Notes | State & API integration | Data layer, caching and API wiring | 3 | 'Media Capture And Notes' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E12 Guest Mobile Experience | Media Capture And Notes | Media Capture And Notes | Offline & push handling | Offline storage, sync and push notifications | 2 | 'Media Capture And Notes' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E12 Guest Mobile Experience | Media Capture And Notes | Media Capture And Notes | Mobile E2E tests | Automated tests across iOS/Android | 2 | 'Media Capture And Notes' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E12 Guest Mobile Experience | Ai Assistant And Voice Interface | Ai Assistant And Voice Interface | UI screens (iOS & Android) | Implement shared + platform UI components | 5 | 'Ai Assistant And Voice Interface' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Mobile App | E12 Guest Mobile Experience | Ai Assistant And Voice Interface | Ai Assistant And Voice Interface | State & API integration | Data layer, caching and API wiring | 5 | 'Ai Assistant And Voice Interface' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Mobile App | E12 Guest Mobile Experience | Ai Assistant And Voice Interface | Ai Assistant And Voice Interface | Offline & push handling | Offline storage, sync and push notifications | 3 | 'Ai Assistant And Voice Interface' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Mobile App | E12 Guest Mobile Experience | Ai Assistant And Voice Interface | Ai Assistant And Voice Interface | Mobile E2E tests | Automated tests across iOS/Android | 3 | 'Ai Assistant And Voice Interface' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Mobile App | E12 Guest Mobile Experience | Approvals And Notifications | Approvals And Notifications | UI screens (iOS & Android) | Implement shared + platform UI components | 3 | 'Approvals And Notifications' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E12 Guest Mobile Experience | Approvals And Notifications | Approvals And Notifications | State & API integration | Data layer, caching and API wiring | 3 | 'Approvals And Notifications' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E12 Guest Mobile Experience | Approvals And Notifications | Approvals And Notifications | Offline & push handling | Offline storage, sync and push notifications | 2 | 'Approvals And Notifications' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E12 Guest Mobile Experience | Approvals And Notifications | Approvals And Notifications | Mobile E2E tests | Automated tests across iOS/Android | 2 | 'Approvals And Notifications' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E12 Guest Mobile Experience | Virtual Queue | Virtual Queue | UI screens (iOS & Android) | Implement shared + platform UI components | 1 | 'Virtual Queue' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E12 Guest Mobile Experience | Virtual Queue | Virtual Queue | State & API integration | Data layer, caching and API wiring | 1 | 'Virtual Queue' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E12 Guest Mobile Experience | Virtual Queue | Virtual Queue | Offline & push handling | Offline storage, sync and push notifications | 1 | 'Virtual Queue' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E12 Guest Mobile Experience | Virtual Queue | Virtual Queue | Mobile E2E tests | Automated tests across iOS/Android | 1 | 'Virtual Queue' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E12 Guest Mobile Experience | Recommendation Engine | Recommendation Engine | UI screens (iOS & Android) | Implement shared + platform UI components | 3 | 'Recommendation Engine' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Mobile App | E12 Guest Mobile Experience | Recommendation Engine | Recommendation Engine | State & API integration | Data layer, caching and API wiring | 3 | 'Recommendation Engine' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Mobile App | E12 Guest Mobile Experience | Recommendation Engine | Recommendation Engine | Offline & push handling | Offline storage, sync and push notifications | 2 | 'Recommendation Engine' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Mobile App | E12 Guest Mobile Experience | Recommendation Engine | Recommendation Engine | Mobile E2E tests | Automated tests across iOS/Android | 2 | 'Recommendation Engine' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Mobile App | E12 Guest Mobile Experience | Accounting | Accounting | UI screens (iOS & Android) | Implement shared + platform UI components | 2 | 'Accounting' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E12 Guest Mobile Experience | Accounting | Accounting | State & API integration | Data layer, caching and API wiring | 2 | 'Accounting' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E12 Guest Mobile Experience | Accounting | Accounting | Offline & push handling | Offline storage, sync and push notifications | 1 | 'Accounting' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E12 Guest Mobile Experience | Accounting | Accounting | Mobile E2E tests | Automated tests across iOS/Android | 1 | 'Accounting' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E12 Guest Mobile Experience | Reporting And Dashboards | Reporting And Dashboards | UI screens (iOS & Android) | Implement shared + platform UI components | 2 | 'Reporting And Dashboards' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E12 Guest Mobile Experience | Reporting And Dashboards | Reporting And Dashboards | State & API integration | Data layer, caching and API wiring | 2 | 'Reporting And Dashboards' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E12 Guest Mobile Experience | Reporting And Dashboards | Reporting And Dashboards | Offline & push handling | Offline storage, sync and push notifications | 1 | 'Reporting And Dashboards' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E12 Guest Mobile Experience | Reporting And Dashboards | Reporting And Dashboards | Mobile E2E tests | Automated tests across iOS/Android | 1 | 'Reporting And Dashboards' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E12 Guest Mobile Experience | Api Business Coverage | Api Business Coverage | UI screens (iOS & Android) | Implement shared + platform UI components | 1 | 'Api Business Coverage' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E12 Guest Mobile Experience | Api Business Coverage | Api Business Coverage | State & API integration | Data layer, caching and API wiring | 1 | 'Api Business Coverage' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E12 Guest Mobile Experience | Api Business Coverage | Api Business Coverage | Offline & push handling | Offline storage, sync and push notifications | 1 | 'Api Business Coverage' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E12 Guest Mobile Experience | Api Business Coverage | Api Business Coverage | Mobile E2E tests | Automated tests across iOS/Android | 1 | 'Api Business Coverage' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Mobile App | E13 Employee Mobile & Workforce | Shift Opening And Closing | Shift Opening And Closing | UI screens (iOS & Android) | Implement shared + platform UI components | 3 | 'Shift Opening And Closing' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Mobile App | E13 Employee Mobile & Workforce | Shift Opening And Closing | Shift Opening And Closing | State & API integration | Data layer, caching and API wiring | 3 | 'Shift Opening And Closing' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Mobile App | E13 Employee Mobile & Workforce | Shift Opening And Closing | Shift Opening And Closing | Offline & push handling | Offline storage, sync and push notifications | 2 | 'Shift Opening And Closing' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Mobile App | E13 Employee Mobile & Workforce | Shift Opening And Closing | Shift Opening And Closing | Mobile E2E tests | Automated tests across iOS/Android | 2 | 'Shift Opening And Closing' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Mobile App | E13 Employee Mobile & Workforce | Demand Forecasting | Demand Forecasting | UI screens (iOS & Android) | Implement shared + platform UI components | 6 | 'Demand Forecasting' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Mobile App | E13 Employee Mobile & Workforce | Demand Forecasting | Demand Forecasting | State & API integration | Data layer, caching and API wiring | 6 | 'Demand Forecasting' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Mobile App | E13 Employee Mobile & Workforce | Demand Forecasting | Demand Forecasting | Offline & push handling | Offline storage, sync and push notifications | 4 | 'Demand Forecasting' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Mobile App | E13 Employee Mobile & Workforce | Demand Forecasting | Demand Forecasting | Mobile E2E tests | Automated tests across iOS/Android | 4 | 'Demand Forecasting' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Mobile App | E13 Employee Mobile & Workforce | Virtual Queue | Virtual Queue | UI screens (iOS & Android) | Implement shared + platform UI components | 3 | 'Virtual Queue' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Mobile App | E13 Employee Mobile & Workforce | Virtual Queue | Virtual Queue | State & API integration | Data layer, caching and API wiring | 3 | 'Virtual Queue' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Mobile App | E13 Employee Mobile & Workforce | Virtual Queue | Virtual Queue | Offline & push handling | Offline storage, sync and push notifications | 2 | 'Virtual Queue' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Mobile App | E13 Employee Mobile & Workforce | Virtual Queue | Virtual Queue | Mobile E2E tests | Automated tests across iOS/Android | 2 | 'Virtual Queue' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Mobile App | E13 Employee Mobile & Workforce | Bi And Reporting | Bi And Reporting | UI screens (iOS & Android) | Implement shared + platform UI components | 1 | 'Bi And Reporting' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Mobile App | E13 Employee Mobile & Workforce | Bi And Reporting | Bi And Reporting | State & API integration | Data layer, caching and API wiring | 1 | 'Bi And Reporting' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Mobile App | E13 Employee Mobile & Workforce | Bi And Reporting | Bi And Reporting | Offline & push handling | Offline storage, sync and push notifications | 1 | 'Bi And Reporting' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Mobile App | E13 Employee Mobile & Workforce | Bi And Reporting | Bi And Reporting | Mobile E2E tests | Automated tests across iOS/Android | 1 | 'Bi And Reporting' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Mobile App | E13 Employee Mobile & Workforce | Operations Command Center | Operations Command Center | UI screens (iOS & Android) | Implement shared + platform UI components | 3 | 'Operations Command Center' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Mobile App | E13 Employee Mobile & Workforce | Operations Command Center | Operations Command Center | State & API integration | Data layer, caching and API wiring | 3 | 'Operations Command Center' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Mobile App | E13 Employee Mobile & Workforce | Operations Command Center | Operations Command Center | Offline & push handling | Offline storage, sync and push notifications | 2 | 'Operations Command Center' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Mobile App | E13 Employee Mobile & Workforce | Operations Command Center | Operations Command Center | Mobile E2E tests | Automated tests across iOS/Android | 2 | 'Operations Command Center' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Reporting And Dashboards | Reporting And Dashboards | Data model & schema | Define entities, relationships, constraints and migrations | 18 | 'Reporting And Dashboards' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E14 Intelligence, Reporting & AI | Reporting And Dashboards | Reporting And Dashboards | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 28 | 'Reporting And Dashboards' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E14 Intelligence, Reporting & AI | Reporting And Dashboards | Reporting And Dashboards | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 37 | 'Reporting And Dashboards' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E14 Intelligence, Reporting & AI | Reporting And Dashboards | Reporting And Dashboards | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 18 | 'Reporting And Dashboards' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E14 Intelligence, Reporting & AI | Reporting And Dashboards | Reporting And Dashboards | Unit & integration tests | Automated tests incl. negative and concurrency cases | 18 | 'Reporting And Dashboards' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E14 Intelligence, Reporting & AI | Fraud Detection | Fraud Detection | Data model & schema | Define entities, relationships, constraints and migrations | 10 | 'Fraud Detection' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Fraud Detection | Fraud Detection | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 15 | 'Fraud Detection' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Fraud Detection | Fraud Detection | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 19 | 'Fraud Detection' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Fraud Detection | Fraud Detection | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 10 | 'Fraud Detection' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Fraud Detection | Fraud Detection | Unit & integration tests | Automated tests incl. negative and concurrency cases | 10 | 'Fraud Detection' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Accounting | Accounting | Data model & schema | Define entities, relationships, constraints and migrations | 9 | 'Accounting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Accounting | Accounting | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 13 | 'Accounting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Accounting | Accounting | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 18 | 'Accounting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Accounting | Accounting | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 9 | 'Accounting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Accounting | Accounting | Unit & integration tests | Automated tests incl. negative and concurrency cases | 9 | 'Accounting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Ai Engine | Ai Engine | Data model & schema | Define entities, relationships, constraints and migrations | 8 | 'Ai Engine' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Ai Engine | Ai Engine | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 13 | 'Ai Engine' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Ai Engine | Ai Engine | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 17 | 'Ai Engine' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Ai Engine | Ai Engine | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 8 | 'Ai Engine' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Ai Engine | Ai Engine | Unit & integration tests | Automated tests incl. negative and concurrency cases | 8 | 'Ai Engine' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Bi And Reporting | Bi And Reporting | Data model & schema | Define entities, relationships, constraints and migrations | 8 | 'Bi And Reporting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Bi And Reporting | Bi And Reporting | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 12 | 'Bi And Reporting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Bi And Reporting | Bi And Reporting | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 16 | 'Bi And Reporting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Bi And Reporting | Bi And Reporting | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 8 | 'Bi And Reporting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Bi And Reporting | Bi And Reporting | Unit & integration tests | Automated tests incl. negative and concurrency cases | 8 | 'Bi And Reporting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Ai Governance | Ai Governance | Data model & schema | Define entities, relationships, constraints and migrations | 8 | 'Ai Governance' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Ai Governance | Ai Governance | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 11 | 'Ai Governance' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Ai Governance | Ai Governance | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 15 | 'Ai Governance' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Ai Governance | Ai Governance | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 8 | 'Ai Governance' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Ai Governance | Ai Governance | Unit & integration tests | Automated tests incl. negative and concurrency cases | 8 | 'Ai Governance' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Demand Forecasting | Demand Forecasting | Data model & schema | Define entities, relationships, constraints and migrations | 7 | 'Demand Forecasting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Demand Forecasting | Demand Forecasting | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 11 | 'Demand Forecasting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Demand Forecasting | Demand Forecasting | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 14 | 'Demand Forecasting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Demand Forecasting | Demand Forecasting | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 7 | 'Demand Forecasting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Demand Forecasting | Demand Forecasting | Unit & integration tests | Automated tests incl. negative and concurrency cases | 7 | 'Demand Forecasting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Recommendation Engine | Recommendation Engine | Data model & schema | Define entities, relationships, constraints and migrations | 6 | 'Recommendation Engine' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Recommendation Engine | Recommendation Engine | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 8 | 'Recommendation Engine' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Recommendation Engine | Recommendation Engine | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 11 | 'Recommendation Engine' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Recommendation Engine | Recommendation Engine | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 6 | 'Recommendation Engine' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Recommendation Engine | Recommendation Engine | Unit & integration tests | Automated tests incl. negative and concurrency cases | 6 | 'Recommendation Engine' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Ai Governance And Explainability | Ai Governance And Explainability | Data model & schema | Define entities, relationships, constraints and migrations | 3 | 'Ai Governance And Explainability' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Ai Governance And Explainability | Ai Governance And Explainability | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 4 | 'Ai Governance And Explainability' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Ai Governance And Explainability | Ai Governance And Explainability | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 6 | 'Ai Governance And Explainability' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Ai Governance And Explainability | Ai Governance And Explainability | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 3 | 'Ai Governance And Explainability' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Ai Governance And Explainability | Ai Governance And Explainability | Unit & integration tests | Automated tests incl. negative and concurrency cases | 3 | 'Ai Governance And Explainability' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Customer Support And Helpdesk | Customer Support And Helpdesk | Data model & schema | Define entities, relationships, constraints and migrations | 3 | 'Customer Support And Helpdesk' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Customer Support And Helpdesk | Customer Support And Helpdesk | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 4 | 'Customer Support And Helpdesk' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Customer Support And Helpdesk | Customer Support And Helpdesk | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 5 | 'Customer Support And Helpdesk' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Customer Support And Helpdesk | Customer Support And Helpdesk | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 3 | 'Customer Support And Helpdesk' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Customer Support And Helpdesk | Customer Support And Helpdesk | Unit & integration tests | Automated tests incl. negative and concurrency cases | 3 | 'Customer Support And Helpdesk' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Virtual Queue | Virtual Queue | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Virtual Queue' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Virtual Queue | Virtual Queue | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Virtual Queue' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Virtual Queue | Virtual Queue | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 5 | 'Virtual Queue' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Virtual Queue | Virtual Queue | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Virtual Queue' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Virtual Queue | Virtual Queue | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Virtual Queue' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Maintenance Reporting And Analytics | Maintenance Reporting And Analytics | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Maintenance Reporting And Analytics' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E14 Intelligence, Reporting & AI | Maintenance Reporting And Analytics | Maintenance Reporting And Analytics | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Maintenance Reporting And Analytics' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E14 Intelligence, Reporting & AI | Maintenance Reporting And Analytics | Maintenance Reporting And Analytics | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Maintenance Reporting And Analytics' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E14 Intelligence, Reporting & AI | Maintenance Reporting And Analytics | Maintenance Reporting And Analytics | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Maintenance Reporting And Analytics' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E14 Intelligence, Reporting & AI | Maintenance Reporting And Analytics | Maintenance Reporting And Analytics | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Maintenance Reporting And Analytics' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E14 Intelligence, Reporting & AI | Enterprise Features | Enterprise Features | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Enterprise Features' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E14 Intelligence, Reporting & AI | Enterprise Features | Enterprise Features | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Enterprise Features' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E14 Intelligence, Reporting & AI | Enterprise Features | Enterprise Features | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Enterprise Features' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E14 Intelligence, Reporting & AI | Enterprise Features | Enterprise Features | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Enterprise Features' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E14 Intelligence, Reporting & AI | Enterprise Features | Enterprise Features | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Enterprise Features' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E14 Intelligence, Reporting & AI | Safety And Compliance | Safety And Compliance | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Safety And Compliance' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E14 Intelligence, Reporting & AI | Safety And Compliance | Safety And Compliance | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Safety And Compliance' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E14 Intelligence, Reporting & AI | Safety And Compliance | Safety And Compliance | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Safety And Compliance' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E14 Intelligence, Reporting & AI | Safety And Compliance | Safety And Compliance | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Safety And Compliance' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E14 Intelligence, Reporting & AI | Safety And Compliance | Safety And Compliance | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Safety And Compliance' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E14 Intelligence, Reporting & AI | Ai Configuration Assistant | Ai Configuration Assistant | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Ai Configuration Assistant' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E14 Intelligence, Reporting & AI | Ai Configuration Assistant | Ai Configuration Assistant | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Ai Configuration Assistant' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E14 Intelligence, Reporting & AI | Ai Configuration Assistant | Ai Configuration Assistant | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Ai Configuration Assistant' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E14 Intelligence, Reporting & AI | Ai Configuration Assistant | Ai Configuration Assistant | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Ai Configuration Assistant' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E14 Intelligence, Reporting & AI | Ai Configuration Assistant | Ai Configuration Assistant | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Ai Configuration Assistant' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E14 Intelligence, Reporting & AI | Operations Command Center | Operations Command Center | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Operations Command Center' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Operations Command Center | Operations Command Center | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Operations Command Center' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Operations Command Center | Operations Command Center | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Operations Command Center' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Operations Command Center | Operations Command Center | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Operations Command Center' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Operations Command Center | Operations Command Center | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Operations Command Center' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Sandbox | Sandbox | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Sandbox' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E14 Intelligence, Reporting & AI | Sandbox | Sandbox | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Sandbox' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E14 Intelligence, Reporting & AI | Sandbox | Sandbox | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Sandbox' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E14 Intelligence, Reporting & AI | Sandbox | Sandbox | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Sandbox' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E14 Intelligence, Reporting & AI | Sandbox | Sandbox | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Sandbox' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E14 Intelligence, Reporting & AI | Self-Service Onboarding | Self-Service Onboarding | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Self-Service Onboarding' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Self-Service Onboarding | Self-Service Onboarding | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Self-Service Onboarding' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Self-Service Onboarding | Self-Service Onboarding | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Self-Service Onboarding' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Self-Service Onboarding | Self-Service Onboarding | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Self-Service Onboarding' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E14 Intelligence, Reporting & AI | Self-Service Onboarding | Self-Service Onboarding | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Self-Service Onboarding' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E15 Device & Peripheral Management | Enterprise Features | Enterprise Features | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Enterprise Features' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E15 Device & Peripheral Management | Enterprise Features | Enterprise Features | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Enterprise Features' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E15 Device & Peripheral Management | Enterprise Features | Enterprise Features | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Enterprise Features' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E15 Device & Peripheral Management | Enterprise Features | Enterprise Features | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Enterprise Features' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E15 Device & Peripheral Management | Enterprise Features | Enterprise Features | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Enterprise Features' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E15 Device & Peripheral Management | Device Configuration | Device Configuration | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Device Configuration' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E15 Device & Peripheral Management | Device Configuration | Device Configuration | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Device Configuration' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E15 Device & Peripheral Management | Device Configuration | Device Configuration | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Device Configuration' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E15 Device & Peripheral Management | Device Configuration | Device Configuration | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Device Configuration' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E15 Device & Peripheral Management | Device Configuration | Device Configuration | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Device Configuration' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Cross Platform | E15 Device & Peripheral Management | Device Monitoring | Device Monitoring | Design & technical spec | Architecture, interfaces and acceptance criteria | 2 | 'Device Monitoring' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Cross Platform | E15 Device & Peripheral Management | Device Monitoring | Device Monitoring | Implementation | Build the capability / automation | 4 | 'Device Monitoring' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Cross Platform | E15 Device & Peripheral Management | Device Monitoring | Device Monitoring | Automation & CI integration | Pipeline, IaC and gates | 2 | 'Device Monitoring' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Cross Platform | E15 Device & Peripheral Management | Device Monitoring | Device Monitoring | Verification & sign-off | Validate against NFR/acceptance criteria | 2 | 'Device Monitoring' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E15 Device & Peripheral Management | Device Maintenance | Device Maintenance | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Device Maintenance' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E15 Device & Peripheral Management | Device Maintenance | Device Maintenance | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Device Maintenance' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E15 Device & Peripheral Management | Device Maintenance | Device Maintenance | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Device Maintenance' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E15 Device & Peripheral Management | Device Maintenance | Device Maintenance | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Device Maintenance' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E15 Device & Peripheral Management | Device Maintenance | Device Maintenance | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Device Maintenance' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E15 Device & Peripheral Management | Firmware And Software Management | Firmware And Software Management | Data model & schema | Define entities, relationships, constraints and migrations | 3 | 'Firmware And Software Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E15 Device & Peripheral Management | Firmware And Software Management | Firmware And Software Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 4 | 'Firmware And Software Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E15 Device & Peripheral Management | Firmware And Software Management | Firmware And Software Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 5 | 'Firmware And Software Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E15 Device & Peripheral Management | Firmware And Software Management | Firmware And Software Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 3 | 'Firmware And Software Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E15 Device & Peripheral Management | Firmware And Software Management | Firmware And Software Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 3 | 'Firmware And Software Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E15 Device & Peripheral Management | Security | Security | Data model & schema | Define entities, relationships, constraints and migrations | 3 | 'Security' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E15 Device & Peripheral Management | Security | Security | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 4 | 'Security' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E15 Device & Peripheral Management | Security | Security | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 5 | 'Security' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E15 Device & Peripheral Management | Security | Security | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 3 | 'Security' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E15 Device & Peripheral Management | Security | Security | Unit & integration tests | Automated tests incl. negative and concurrency cases | 3 | 'Security' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E15 Device & Peripheral Management | Device Registration | Device Registration | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Device Registration' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E15 Device & Peripheral Management | Device Registration | Device Registration | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Device Registration' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E15 Device & Peripheral Management | Device Registration | Device Registration | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Device Registration' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E15 Device & Peripheral Management | Device Registration | Device Registration | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Device Registration' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E15 Device & Peripheral Management | Device Registration | Device Registration | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Device Registration' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E15 Device & Peripheral Management | Device Integrations | Device Integrations | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Device Integrations' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E15 Device & Peripheral Management | Device Integrations | Device Integrations | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Device Integrations' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E15 Device & Peripheral Management | Device Integrations | Device Integrations | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Device Integrations' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E15 Device & Peripheral Management | Device Integrations | Device Integrations | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Device Integrations' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E15 Device & Peripheral Management | Device Integrations | Device Integrations | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Device Integrations' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E16 Maintenance, Safety & Asset Mgmt | Asset Management | Asset Management | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Asset Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E16 Maintenance, Safety & Asset Mgmt | Asset Management | Asset Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Asset Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E16 Maintenance, Safety & Asset Mgmt | Asset Management | Asset Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Asset Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E16 Maintenance, Safety & Asset Mgmt | Asset Management | Asset Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Asset Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E16 Maintenance, Safety & Asset Mgmt | Asset Management | Asset Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Asset Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E16 Maintenance, Safety & Asset Mgmt | Corrective Maintenance And Incident | Corrective Maintenance And Incident | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Corrective Maintenance And Incident' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E16 Maintenance, Safety & Asset Mgmt | Corrective Maintenance And Incident | Corrective Maintenance And Incident | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Corrective Maintenance And Incident' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E16 Maintenance, Safety & Asset Mgmt | Corrective Maintenance And Incident | Corrective Maintenance And Incident | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Corrective Maintenance And Incident' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E16 Maintenance, Safety & Asset Mgmt | Corrective Maintenance And Incident | Corrective Maintenance And Incident | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Corrective Maintenance And Incident' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E16 Maintenance, Safety & Asset Mgmt | Corrective Maintenance And Incident | Corrective Maintenance And Incident | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Corrective Maintenance And Incident' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E16 Maintenance, Safety & Asset Mgmt | Safety And Compliance | Safety And Compliance | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Safety And Compliance' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E16 Maintenance, Safety & Asset Mgmt | Safety And Compliance | Safety And Compliance | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Safety And Compliance' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E16 Maintenance, Safety & Asset Mgmt | Safety And Compliance | Safety And Compliance | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Safety And Compliance' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E16 Maintenance, Safety & Asset Mgmt | Safety And Compliance | Safety And Compliance | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Safety And Compliance' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E16 Maintenance, Safety & Asset Mgmt | Safety And Compliance | Safety And Compliance | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Safety And Compliance' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E16 Maintenance, Safety & Asset Mgmt | Accounting | Accounting | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Accounting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E16 Maintenance, Safety & Asset Mgmt | Accounting | Accounting | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Accounting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E16 Maintenance, Safety & Asset Mgmt | Accounting | Accounting | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Accounting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E16 Maintenance, Safety & Asset Mgmt | Accounting | Accounting | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Accounting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E16 Maintenance, Safety & Asset Mgmt | Accounting | Accounting | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Accounting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E17 Identity, Security & Access Policy | Compliance And Security | Compliance And Security | Data model & schema | Define entities, relationships, constraints and migrations | 4 | 'Compliance And Security' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M1 - Foundation
Server Side / Backend | E17 Identity, Security & Access Policy | Compliance And Security | Compliance And Security | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 6 | 'Compliance And Security' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M1 - Foundation
Server Side / Backend | E17 Identity, Security & Access Policy | Compliance And Security | Compliance And Security | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 8 | 'Compliance And Security' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M1 - Foundation
Server Side / Backend | E17 Identity, Security & Access Policy | Compliance And Security | Compliance And Security | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 4 | 'Compliance And Security' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M1 - Foundation
Server Side / Backend | E17 Identity, Security & Access Policy | Compliance And Security | Compliance And Security | Unit & integration tests | Automated tests incl. negative and concurrency cases | 4 | 'Compliance And Security' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M1 - Foundation
Server Side / Backend | E17 Identity, Security & Access Policy | Profile Management | Profile Management | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Profile Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E17 Identity, Security & Access Policy | Profile Management | Profile Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Profile Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E17 Identity, Security & Access Policy | Profile Management | Profile Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Profile Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E17 Identity, Security & Access Policy | Profile Management | Profile Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Profile Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E17 Identity, Security & Access Policy | Profile Management | Profile Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Profile Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E17 Identity, Security & Access Policy | Security | Security | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Security' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E17 Identity, Security & Access Policy | Security | Security | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Security' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E17 Identity, Security & Access Policy | Security | Security | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Security' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E17 Identity, Security & Access Policy | Security | Security | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Security' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E17 Identity, Security & Access Policy | Security | Security | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Security' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E18 Governance, Approval & Accreditation | Accounting | Accounting | Data model & schema | Define entities, relationships, constraints and migrations | 15 | 'Accounting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E18 Governance, Approval & Accreditation | Accounting | Accounting | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 23 | 'Accounting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E18 Governance, Approval & Accreditation | Accounting | Accounting | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 30 | 'Accounting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E18 Governance, Approval & Accreditation | Accounting | Accounting | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 15 | 'Accounting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E18 Governance, Approval & Accreditation | Accounting | Accounting | Unit & integration tests | Automated tests incl. negative and concurrency cases | 15 | 'Accounting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E18 Governance, Approval & Accreditation | Profile Management | Profile Management | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Profile Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E18 Governance, Approval & Accreditation | Profile Management | Profile Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Profile Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E18 Governance, Approval & Accreditation | Profile Management | Profile Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Profile Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E18 Governance, Approval & Accreditation | Profile Management | Profile Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Profile Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E18 Governance, Approval & Accreditation | Profile Management | Profile Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Profile Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E18 Governance, Approval & Accreditation | Virtual Queue | Virtual Queue | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Virtual Queue' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E18 Governance, Approval & Accreditation | Virtual Queue | Virtual Queue | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Virtual Queue' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E18 Governance, Approval & Accreditation | Virtual Queue | Virtual Queue | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Virtual Queue' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E18 Governance, Approval & Accreditation | Virtual Queue | Virtual Queue | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Virtual Queue' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E18 Governance, Approval & Accreditation | Virtual Queue | Virtual Queue | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Virtual Queue' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E18 Governance, Approval & Accreditation | Sandbox | Sandbox | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Sandbox' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E18 Governance, Approval & Accreditation | Sandbox | Sandbox | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Sandbox' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E18 Governance, Approval & Accreditation | Sandbox | Sandbox | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 1 | 'Sandbox' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E18 Governance, Approval & Accreditation | Sandbox | Sandbox | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Sandbox' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E18 Governance, Approval & Accreditation | Sandbox | Sandbox | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Sandbox' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Cross Platform | E19 Developer Platform & API Mgmt | Sandbox | Sandbox | Design & technical spec | Architecture, interfaces and acceptance criteria | 7 | 'Sandbox' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Cross Platform | E19 Developer Platform & API Mgmt | Sandbox | Sandbox | Implementation | Build the capability / automation | 14 | 'Sandbox' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Cross Platform | E19 Developer Platform & API Mgmt | Sandbox | Sandbox | Automation & CI integration | Pipeline, IaC and gates | 7 | 'Sandbox' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Cross Platform | E19 Developer Platform & API Mgmt | Sandbox | Sandbox | Verification & sign-off | Validate against NFR/acceptance criteria | 7 | 'Sandbox' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Cross Platform | E19 Developer Platform & API Mgmt | Accounting | Accounting | Design & technical spec | Architecture, interfaces and acceptance criteria | 1 | 'Accounting' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Cross Platform | E19 Developer Platform & API Mgmt | Accounting | Accounting | Implementation | Build the capability / automation | 3 | 'Accounting' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Cross Platform | E19 Developer Platform & API Mgmt | Accounting | Accounting | Automation & CI integration | Pipeline, IaC and gates | 1 | 'Accounting' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Cross Platform | E19 Developer Platform & API Mgmt | Accounting | Accounting | Verification & sign-off | Validate against NFR/acceptance criteria | 1 | 'Accounting' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Cross Platform | E19 Developer Platform & API Mgmt | Api Business Coverage | Api Business Coverage | Design & technical spec | Architecture, interfaces and acceptance criteria | 1 | 'Api Business Coverage' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Cross Platform | E19 Developer Platform & API Mgmt | Api Business Coverage | Api Business Coverage | Implementation | Build the capability / automation | 2 | 'Api Business Coverage' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Cross Platform | E19 Developer Platform & API Mgmt | Api Business Coverage | Api Business Coverage | Automation & CI integration | Pipeline, IaC and gates | 1 | 'Api Business Coverage' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Cross Platform | E19 Developer Platform & API Mgmt | Api Business Coverage | Api Business Coverage | Verification & sign-off | Validate against NFR/acceptance criteria | 1 | 'Api Business Coverage' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M3 - Business Features
Server Side / Backend | E20 Tenant, Subscription & Licensing | Subscription Management | Subscription Management | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Subscription Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E20 Tenant, Subscription & Licensing | Subscription Management | Subscription Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Subscription Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E20 Tenant, Subscription & Licensing | Subscription Management | Subscription Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Subscription Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E20 Tenant, Subscription & Licensing | Subscription Management | Subscription Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Subscription Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E20 Tenant, Subscription & Licensing | Subscription Management | Subscription Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Subscription Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E20 Tenant, Subscription & Licensing | Licensing Models | Licensing Models | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Licensing Models' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E20 Tenant, Subscription & Licensing | Licensing Models | Licensing Models | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Licensing Models' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E20 Tenant, Subscription & Licensing | Licensing Models | Licensing Models | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Licensing Models' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E20 Tenant, Subscription & Licensing | Licensing Models | Licensing Models | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Licensing Models' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E20 Tenant, Subscription & Licensing | Licensing Models | Licensing Models | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Licensing Models' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E20 Tenant, Subscription & Licensing | Module Marketplace And Management | Module Marketplace And Management | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Module Marketplace And Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E20 Tenant, Subscription & Licensing | Module Marketplace And Management | Module Marketplace And Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Module Marketplace And Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E20 Tenant, Subscription & Licensing | Module Marketplace And Management | Module Marketplace And Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Module Marketplace And Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E20 Tenant, Subscription & Licensing | Module Marketplace And Management | Module Marketplace And Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Module Marketplace And Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E20 Tenant, Subscription & Licensing | Module Marketplace And Management | Module Marketplace And Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Module Marketplace And Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E20 Tenant, Subscription & Licensing | Self-Service Onboarding | Self-Service Onboarding | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Self-Service Onboarding' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E20 Tenant, Subscription & Licensing | Self-Service Onboarding | Self-Service Onboarding | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Self-Service Onboarding' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E20 Tenant, Subscription & Licensing | Self-Service Onboarding | Self-Service Onboarding | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Self-Service Onboarding' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E20 Tenant, Subscription & Licensing | Self-Service Onboarding | Self-Service Onboarding | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Self-Service Onboarding' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E20 Tenant, Subscription & Licensing | Self-Service Onboarding | Self-Service Onboarding | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Self-Service Onboarding' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E20 Tenant, Subscription & Licensing | Billing And Payment | Billing And Payment | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Billing And Payment' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E20 Tenant, Subscription & Licensing | Billing And Payment | Billing And Payment | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Billing And Payment' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E20 Tenant, Subscription & Licensing | Billing And Payment | Billing And Payment | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Billing And Payment' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E20 Tenant, Subscription & Licensing | Billing And Payment | Billing And Payment | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Billing And Payment' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E20 Tenant, Subscription & Licensing | Billing And Payment | Billing And Payment | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Billing And Payment' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E21 Digital Asset Management | Digital Asset Management | Digital Asset Management | Data model & schema | Define entities, relationships, constraints and migrations | 5 | 'Digital Asset Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E21 Digital Asset Management | Digital Asset Management | Digital Asset Management | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 8 | 'Digital Asset Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E21 Digital Asset Management | Digital Asset Management | Digital Asset Management | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 10 | 'Digital Asset Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E21 Digital Asset Management | Digital Asset Management | Digital Asset Management | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 5 | 'Digital Asset Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E21 Digital Asset Management | Digital Asset Management | Digital Asset Management | Unit & integration tests | Automated tests incl. negative and concurrency cases | 5 | 'Digital Asset Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E22 Integrations & Ecosystem | Software Integration | Software Integration | Data model & schema | Define entities, relationships, constraints and migrations | 6 | 'Software Integration' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E22 Integrations & Ecosystem | Software Integration | Software Integration | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 9 | 'Software Integration' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E22 Integrations & Ecosystem | Software Integration | Software Integration | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 12 | 'Software Integration' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E22 Integrations & Ecosystem | Software Integration | Software Integration | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 6 | 'Software Integration' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Server Side / Backend | E22 Integrations & Ecosystem | Software Integration | Software Integration | Unit & integration tests | Automated tests incl. negative and concurrency cases | 6 | 'Software Integration' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E22 Integrations & Ecosystem | Hardware Integration | Hardware Integration | POS screen & flow | Build cashier/kiosk UI and transaction flow | 8 | 'Hardware Integration' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E22 Integrations & Ecosystem | Hardware Integration | Hardware Integration | Backend/API integration | Wire to pricing, catalogue, payment and sync APIs | 5 | 'Hardware Integration' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E22 Integrations & Ecosystem | Hardware Integration | Hardware Integration | Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable | 8 | 'Hardware Integration' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E22 Integrations & Ecosystem | Hardware Integration | Hardware Integration | Offline handling & sync | Local cache, queue and conflict resolution | 8 | 'Hardware Integration' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
POS App | E22 Integrations & Ecosystem | Hardware Integration | Hardware Integration | POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios | 5 | 'Hardware Integration' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P3 - Could | M4 - Integrations
Cross Platform | E23 Platform Foundations & NFR | Disaster Recovery | Disaster Recovery | Design & technical spec | Architecture, interfaces and acceptance criteria | 22 | 'Disaster Recovery' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Cross Platform | E23 Platform Foundations & NFR | Disaster Recovery | Disaster Recovery | Implementation | Build the capability / automation | 43 | 'Disaster Recovery' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Cross Platform | E23 Platform Foundations & NFR | Disaster Recovery | Disaster Recovery | Automation & CI integration | Pipeline, IaC and gates | 22 | 'Disaster Recovery' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Cross Platform | E23 Platform Foundations & NFR | Disaster Recovery | Disaster Recovery | Verification & sign-off | Validate against NFR/acceptance criteria | 22 | 'Disaster Recovery' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Cross Platform | E23 Platform Foundations & NFR | Training And Support | Training And Support | Design & technical spec | Architecture, interfaces and acceptance criteria | 15 | 'Training And Support' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Cross Platform | E23 Platform Foundations & NFR | Training And Support | Training And Support | Implementation | Build the capability / automation | 29 | 'Training And Support' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Cross Platform | E23 Platform Foundations & NFR | Training And Support | Training And Support | Automation & CI integration | Pipeline, IaC and gates | 15 | 'Training And Support' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Cross Platform | E23 Platform Foundations & NFR | Training And Support | Training And Support | Verification & sign-off | Validate against NFR/acceptance criteria | 15 | 'Training And Support' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E23 Platform Foundations & NFR | Multi-Tenant Core & Tenant Isolation | Multi-Tenant Core & Tenant Isolation | Data model & schema | Define entities, relationships, constraints and migrations | 3 | 'Multi-Tenant Core & Tenant Isolation' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E23 Platform Foundations & NFR | Multi-Tenant Core & Tenant Isolation | Multi-Tenant Core & Tenant Isolation | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 4 | 'Multi-Tenant Core & Tenant Isolation' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E23 Platform Foundations & NFR | Multi-Tenant Core & Tenant Isolation | Multi-Tenant Core & Tenant Isolation | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 6 | 'Multi-Tenant Core & Tenant Isolation' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E23 Platform Foundations & NFR | Multi-Tenant Core & Tenant Isolation | Multi-Tenant Core & Tenant Isolation | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 3 | 'Multi-Tenant Core & Tenant Isolation' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E23 Platform Foundations & NFR | Multi-Tenant Core & Tenant Isolation | Multi-Tenant Core & Tenant Isolation | Unit & integration tests | Automated tests incl. negative and concurrency cases | 3 | 'Multi-Tenant Core & Tenant Isolation' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E17 Identity, Security & Access Policy | Identity, SSO & MFA Service | Identity, SSO & MFA Service | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Identity, SSO & MFA Service' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E17 Identity, Security & Access Policy | Identity, SSO & MFA Service | Identity, SSO & MFA Service | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Identity, SSO & MFA Service' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E17 Identity, Security & Access Policy | Identity, SSO & MFA Service | Identity, SSO & MFA Service | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Identity, SSO & MFA Service' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E17 Identity, Security & Access Policy | Identity, SSO & MFA Service | Identity, SSO & MFA Service | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Identity, SSO & MFA Service' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E17 Identity, Security & Access Policy | Identity, SSO & MFA Service | Identity, SSO & MFA Service | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Identity, SSO & MFA Service' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E17 Identity, Security & Access Policy | RBAC + ABAC Policy Engine | RBAC + ABAC Policy Engine | Data model & schema | Define entities, relationships, constraints and migrations | 3 | 'RBAC + ABAC Policy Engine' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E17 Identity, Security & Access Policy | RBAC + ABAC Policy Engine | RBAC + ABAC Policy Engine | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 5 | 'RBAC + ABAC Policy Engine' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E17 Identity, Security & Access Policy | RBAC + ABAC Policy Engine | RBAC + ABAC Policy Engine | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 6 | 'RBAC + ABAC Policy Engine' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E17 Identity, Security & Access Policy | RBAC + ABAC Policy Engine | RBAC + ABAC Policy Engine | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 3 | 'RBAC + ABAC Policy Engine' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E17 Identity, Security & Access Policy | RBAC + ABAC Policy Engine | RBAC + ABAC Policy Engine | Unit & integration tests | Automated tests incl. negative and concurrency cases | 3 | 'RBAC + ABAC Policy Engine' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Cross Platform | E19 Developer Platform & API Mgmt | API Gateway & Service Framework | API Gateway & Service Framework | Design & technical spec | Architecture, interfaces and acceptance criteria | 3 | 'API Gateway & Service Framework' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Cross Platform | E19 Developer Platform & API Mgmt | API Gateway & Service Framework | API Gateway & Service Framework | Implementation | Build the capability / automation | 6 | 'API Gateway & Service Framework' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Cross Platform | E19 Developer Platform & API Mgmt | API Gateway & Service Framework | API Gateway & Service Framework | Automation & CI integration | Pipeline, IaC and gates | 3 | 'API Gateway & Service Framework' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Cross Platform | E19 Developer Platform & API Mgmt | API Gateway & Service Framework | API Gateway & Service Framework | Verification & sign-off | Validate against NFR/acceptance criteria | 3 | 'API Gateway & Service Framework' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E23 Platform Foundations & NFR | Core Data Model & Schema Migrations | Core Data Model & Schema Migrations | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Core Data Model & Schema Migrations' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E23 Platform Foundations & NFR | Core Data Model & Schema Migrations | Core Data Model & Schema Migrations | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Core Data Model & Schema Migrations' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E23 Platform Foundations & NFR | Core Data Model & Schema Migrations | Core Data Model & Schema Migrations | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 5 | 'Core Data Model & Schema Migrations' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E23 Platform Foundations & NFR | Core Data Model & Schema Migrations | Core Data Model & Schema Migrations | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Core Data Model & Schema Migrations' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E23 Platform Foundations & NFR | Core Data Model & Schema Migrations | Core Data Model & Schema Migrations | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Core Data Model & Schema Migrations' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E22 Integrations & Ecosystem | Notification Service (Email/SMS/WhatsApp/Push) | Notification Service (Email/SMS/WhatsApp/Push) | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Notification Service (Email/SMS/WhatsApp/Push)' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E22 Integrations & Ecosystem | Notification Service (Email/SMS/WhatsApp/Push) | Notification Service (Email/SMS/WhatsApp/Push) | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Notification Service (Email/SMS/WhatsApp/Push)' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E22 Integrations & Ecosystem | Notification Service (Email/SMS/WhatsApp/Push) | Notification Service (Email/SMS/WhatsApp/Push) | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 3 | 'Notification Service (Email/SMS/WhatsApp/Push)' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E22 Integrations & Ecosystem | Notification Service (Email/SMS/WhatsApp/Push) | Notification Service (Email/SMS/WhatsApp/Push) | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Notification Service (Email/SMS/WhatsApp/Push)' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E22 Integrations & Ecosystem | Notification Service (Email/SMS/WhatsApp/Push) | Notification Service (Email/SMS/WhatsApp/Push) | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Notification Service (Email/SMS/WhatsApp/Push)' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Cross Platform | E23 Platform Foundations & NFR | Observability: Logging, Metrics, Tracing, Alerting | Observability: Logging, Metrics, Tracing, Alerting | Design & technical spec | Architecture, interfaces and acceptance criteria | 2 | 'Observability: Logging, Metrics, Tracing, Alerting' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Cross Platform | E23 Platform Foundations & NFR | Observability: Logging, Metrics, Tracing, Alerting | Observability: Logging, Metrics, Tracing, Alerting | Implementation | Build the capability / automation | 5 | 'Observability: Logging, Metrics, Tracing, Alerting' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Cross Platform | E23 Platform Foundations & NFR | Observability: Logging, Metrics, Tracing, Alerting | Observability: Logging, Metrics, Tracing, Alerting | Automation & CI integration | Pipeline, IaC and gates | 2 | 'Observability: Logging, Metrics, Tracing, Alerting' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Cross Platform | E23 Platform Foundations & NFR | Observability: Logging, Metrics, Tracing, Alerting | Observability: Logging, Metrics, Tracing, Alerting | Verification & sign-off | Validate against NFR/acceptance criteria | 2 | 'Observability: Logging, Metrics, Tracing, Alerting' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Cross Platform | E23 Platform Foundations & NFR | CI/CD Pipelines & Infrastructure-as-Code | CI/CD Pipelines & Infrastructure-as-Code | Design & technical spec | Architecture, interfaces and acceptance criteria | 2 | 'CI/CD Pipelines & Infrastructure-as-Code' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Cross Platform | E23 Platform Foundations & NFR | CI/CD Pipelines & Infrastructure-as-Code | CI/CD Pipelines & Infrastructure-as-Code | Implementation | Build the capability / automation | 5 | 'CI/CD Pipelines & Infrastructure-as-Code' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Cross Platform | E23 Platform Foundations & NFR | CI/CD Pipelines & Infrastructure-as-Code | CI/CD Pipelines & Infrastructure-as-Code | Automation & CI integration | Pipeline, IaC and gates | 2 | 'CI/CD Pipelines & Infrastructure-as-Code' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Cross Platform | E23 Platform Foundations & NFR | CI/CD Pipelines & Infrastructure-as-Code | CI/CD Pipelines & Infrastructure-as-Code | Verification & sign-off | Validate against NFR/acceptance criteria | 2 | 'CI/CD Pipelines & Infrastructure-as-Code' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E23 Platform Foundations & NFR | Error Handling & Resilience Framework | Error Handling & Resilience Framework | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Error Handling & Resilience Framework' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E23 Platform Foundations & NFR | Error Handling & Resilience Framework | Error Handling & Resilience Framework | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 2 | 'Error Handling & Resilience Framework' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E23 Platform Foundations & NFR | Error Handling & Resilience Framework | Error Handling & Resilience Framework | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Error Handling & Resilience Framework' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E23 Platform Foundations & NFR | Error Handling & Resilience Framework | Error Handling & Resilience Framework | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Error Handling & Resilience Framework' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E23 Platform Foundations & NFR | Error Handling & Resilience Framework | Error Handling & Resilience Framework | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Error Handling & Resilience Framework' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E23 Platform Foundations & NFR | Configuration Management & Feature Flags | Configuration Management & Feature Flags | Data model & schema | Define entities, relationships, constraints and migrations | 1 | 'Configuration Management & Feature Flags' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E23 Platform Foundations & NFR | Configuration Management & Feature Flags | Configuration Management & Feature Flags | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 1 | 'Configuration Management & Feature Flags' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E23 Platform Foundations & NFR | Configuration Management & Feature Flags | Configuration Management & Feature Flags | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 2 | 'Configuration Management & Feature Flags' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E23 Platform Foundations & NFR | Configuration Management & Feature Flags | Configuration Management & Feature Flags | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 1 | 'Configuration Management & Feature Flags' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E23 Platform Foundations & NFR | Configuration Management & Feature Flags | Configuration Management & Feature Flags | Unit & integration tests | Automated tests incl. negative and concurrency cases | 1 | 'Configuration Management & Feature Flags' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Server Side / Backend | E14 Intelligence, Reporting & AI | Reporting & Analytics Platform | Reporting & Analytics Platform | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Reporting & Analytics Platform' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E14 Intelligence, Reporting & AI | Reporting & Analytics Platform | Reporting & Analytics Platform | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 4 | 'Reporting & Analytics Platform' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E14 Intelligence, Reporting & AI | Reporting & Analytics Platform | Reporting & Analytics Platform | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 5 | 'Reporting & Analytics Platform' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E14 Intelligence, Reporting & AI | Reporting & Analytics Platform | Reporting & Analytics Platform | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Reporting & Analytics Platform' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Server Side / Backend | E14 Intelligence, Reporting & AI | Reporting & Analytics Platform | Reporting & Analytics Platform | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Reporting & Analytics Platform' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M3 - Business Features
Cross Platform | E23 Platform Foundations & NFR | Backup, Disaster Recovery & BCP | Backup, Disaster Recovery & BCP | Design & technical spec | Architecture, interfaces and acceptance criteria | 3 | 'Backup, Disaster Recovery & BCP' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Cross Platform | E23 Platform Foundations & NFR | Backup, Disaster Recovery & BCP | Backup, Disaster Recovery & BCP | Implementation | Build the capability / automation | 6 | 'Backup, Disaster Recovery & BCP' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Cross Platform | E23 Platform Foundations & NFR | Backup, Disaster Recovery & BCP | Backup, Disaster Recovery & BCP | Automation & CI integration | Pipeline, IaC and gates | 3 | 'Backup, Disaster Recovery & BCP' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Cross Platform | E23 Platform Foundations & NFR | Backup, Disaster Recovery & BCP | Backup, Disaster Recovery & BCP | Verification & sign-off | Validate against NFR/acceptance criteria | 3 | 'Backup, Disaster Recovery & BCP' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M1 - Foundation
Cross Platform | E17 Identity, Security & Access Policy | Security Hardening & Penetration Testing | Security Hardening & Penetration Testing | Design & technical spec | Architecture, interfaces and acceptance criteria | 2 | 'Security Hardening & Penetration Testing' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M5 - Testing & UAT
Cross Platform | E17 Identity, Security & Access Policy | Security Hardening & Penetration Testing | Security Hardening & Penetration Testing | Implementation | Build the capability / automation | 5 | 'Security Hardening & Penetration Testing' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M5 - Testing & UAT
Cross Platform | E17 Identity, Security & Access Policy | Security Hardening & Penetration Testing | Security Hardening & Penetration Testing | Automation & CI integration | Pipeline, IaC and gates | 2 | 'Security Hardening & Penetration Testing' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M5 - Testing & UAT
Cross Platform | E17 Identity, Security & Access Policy | Security Hardening & Penetration Testing | Security Hardening & Penetration Testing | Verification & sign-off | Validate against NFR/acceptance criteria | 2 | 'Security Hardening & Penetration Testing' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M5 - Testing & UAT
Cross Platform | E23 Platform Foundations & NFR | Performance & Load Testing | Performance & Load Testing | Design & technical spec | Architecture, interfaces and acceptance criteria | 2 | 'Performance & Load Testing' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M5 - Testing & UAT
Cross Platform | E23 Platform Foundations & NFR | Performance & Load Testing | Performance & Load Testing | Implementation | Build the capability / automation | 4 | 'Performance & Load Testing' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M5 - Testing & UAT
Cross Platform | E23 Platform Foundations & NFR | Performance & Load Testing | Performance & Load Testing | Automation & CI integration | Pipeline, IaC and gates | 2 | 'Performance & Load Testing' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M5 - Testing & UAT
Cross Platform | E23 Platform Foundations & NFR | Performance & Load Testing | Performance & Load Testing | Verification & sign-off | Validate against NFR/acceptance criteria | 2 | 'Performance & Load Testing' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M5 - Testing & UAT
Cross Platform | E23 Platform Foundations & NFR | Automated Test Suite & QA Framework | Automated Test Suite & QA Framework | Design & technical spec | Architecture, interfaces and acceptance criteria | 4 | 'Automated Test Suite & QA Framework' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M5 - Testing & UAT
Cross Platform | E23 Platform Foundations & NFR | Automated Test Suite & QA Framework | Automated Test Suite & QA Framework | Implementation | Build the capability / automation | 7 | 'Automated Test Suite & QA Framework' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M5 - Testing & UAT
Cross Platform | E23 Platform Foundations & NFR | Automated Test Suite & QA Framework | Automated Test Suite & QA Framework | Automation & CI integration | Pipeline, IaC and gates | 4 | 'Automated Test Suite & QA Framework' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M5 - Testing & UAT
Cross Platform | E23 Platform Foundations & NFR | Automated Test Suite & QA Framework | Automated Test Suite & QA Framework | Verification & sign-off | Validate against NFR/acceptance criteria | 4 | 'Automated Test Suite & QA Framework' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M5 - Testing & UAT
Cross Platform | E23 Platform Foundations & NFR | UAT, Defect Triage & Sign-off | UAT, Defect Triage & Sign-off | Design & technical spec | Architecture, interfaces and acceptance criteria | 2 | 'UAT, Defect Triage & Sign-off' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M5 - Testing & UAT
Cross Platform | E23 Platform Foundations & NFR | UAT, Defect Triage & Sign-off | UAT, Defect Triage & Sign-off | Implementation | Build the capability / automation | 4 | 'UAT, Defect Triage & Sign-off' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M5 - Testing & UAT
Cross Platform | E23 Platform Foundations & NFR | UAT, Defect Triage & Sign-off | UAT, Defect Triage & Sign-off | Automation & CI integration | Pipeline, IaC and gates | 2 | 'UAT, Defect Triage & Sign-off' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M5 - Testing & UAT
Cross Platform | E23 Platform Foundations & NFR | UAT, Defect Triage & Sign-off | UAT, Defect Triage & Sign-off | Verification & sign-off | Validate against NFR/acceptance criteria | 2 | 'UAT, Defect Triage & Sign-off' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M5 - Testing & UAT
Server Side / Backend | E23 Platform Foundations & NFR | Data Migration & Cutover | Data Migration & Cutover | Data model & schema | Define entities, relationships, constraints and migrations | 2 | 'Data Migration & Cutover' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M6 - Production Release
Server Side / Backend | E23 Platform Foundations & NFR | Data Migration & Cutover | Data Migration & Cutover | API endpoints | Design and implement REST APIs (CRUD + actions) with contracts | 3 | 'Data Migration & Cutover' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M6 - Production Release
Server Side / Backend | E23 Platform Foundations & NFR | Data Migration & Cutover | Data Migration & Cutover | Business logic & rules engine | Implement configurable rules, workflows and edge cases | 4 | 'Data Migration & Cutover' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M6 - Production Release
Server Side / Backend | E23 Platform Foundations & NFR | Data Migration & Cutover | Data Migration & Cutover | Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging | 2 | 'Data Migration & Cutover' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M6 - Production Release
Server Side / Backend | E23 Platform Foundations & NFR | Data Migration & Cutover | Data Migration & Cutover | Unit & integration tests | Automated tests incl. negative and concurrency cases | 2 | 'Data Migration & Cutover' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M6 - Production Release
Cross Platform | E19 Developer Platform & API Mgmt | Documentation & API Reference | Documentation & API Reference | Design & technical spec | Architecture, interfaces and acceptance criteria | 2 | 'Documentation & API Reference' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M5 - Testing & UAT
Cross Platform | E19 Developer Platform & API Mgmt | Documentation & API Reference | Documentation & API Reference | Implementation | Build the capability / automation | 3 | 'Documentation & API Reference' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M5 - Testing & UAT
Cross Platform | E19 Developer Platform & API Mgmt | Documentation & API Reference | Documentation & API Reference | Automation & CI integration | Pipeline, IaC and gates | 2 | 'Documentation & API Reference' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M5 - Testing & UAT
Cross Platform | E19 Developer Platform & API Mgmt | Documentation & API Reference | Documentation & API Reference | Verification & sign-off | Validate against NFR/acceptance criteria | 2 | 'Documentation & API Reference' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P2 - Should | M5 - Testing & UAT
Cross Platform | E23 Platform Foundations & NFR | Production Deployment & Hypercare | Production Deployment & Hypercare | Design & technical spec | Architecture, interfaces and acceptance criteria | 3 | 'Production Deployment & Hypercare' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M6 - Production Release
Cross Platform | E23 Platform Foundations & NFR | Production Deployment & Hypercare | Production Deployment & Hypercare | Implementation | Build the capability / automation | 6 | 'Production Deployment & Hypercare' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M6 - Production Release
Cross Platform | E23 Platform Foundations & NFR | Production Deployment & Hypercare | Production Deployment & Hypercare | Automation & CI integration | Pipeline, IaC and gates | 3 | 'Production Deployment & Hypercare' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M6 - Production Release
Cross Platform | E23 Platform Foundations & NFR | Production Deployment & Hypercare | Production Deployment & Hypercare | Verification & sign-off | Validate against NFR/acceptance criteria | 3 | 'Production Deployment & Hypercare' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | P1 - Must | M6 - Production Release

## 5. Milestone Plan
Milestone | Goal | Primary Epics | Features | Effort (pd) | Exit / Acceptance Criteria
M1 - Foundation | Stand up the multi-tenant platform skeleton: identity, RBAC/ABAC, data model, API gateway, CI/CD, observability, DR. | E17, E19, E23 | 16 | 362 | Tenant isolation verified; auth/RBAC live; CI/CD + IaC operational; baseline observability & backup in place.
M2 - Core Platform | Revenue path end-to-end: ticketing catalogue, multi-channel sales/checkout, gate access, payments, reserved seating. | E01, E02, E03, E04, E10 | 155 | 1706 | A guest can buy (any channel), pay, receive media, and enter via gate online & offline; core reconciliation works.
M3 - Business Features | Operational depth: F&B, retail, inventory, membership, promotions, wallet, CRM/loyalty, guest app, governance. | E05-E09, E11, E12, E08, E18, E20, E21 | 125 | 1500 | F&B/retail/inventory operational; memberships billing; promotions & wallet live; guest app shipped; approvals enforced.
M4 - Integrations | External ecosystem + intelligence: gateways, OTA, ERP, gov (UAE Pass/DET/DCT/Al Hosn), telephony, hardware, device mgmt, AI/forecasting. | E14, E15, E22, E19 | 141 | 3900 | Certified integrations live; device fleet managed; AI features enabled where data sufficient (phased).
M5 - Testing & UAT | System hardening: automated tests, performance/load, security/pen-test, UAT and defect triage. | Cross-cutting (E17, E23) | 5 | 58 | Performance SLOs met; security sign-off; UAT passed with no open P1/P2 defects.
M6 - Production Release | Cutover: data migration, deployment, go-live and Hypercare stabilisation. | E23 | 2 | 26 | Production live; data migrated & reconciled; Hypercare running; handover & docs complete.
TOTAL |  |  | 444 | 7552

## 6. Delivery Roadmap
Phase | Focus | Modules / Epics in Scope | Key Activities | Outputs
Phase 1 - Discovery | Pin scope & requirements | All epics (requirement marking) | Workshops; mark each feature Out-of-the-box / Configurable / Custom; dedupe; confirm scope baseline & order of precedence; AI-phasing & biometric compliance positions. | Agreed requirement register; scope baseline; effort re-estimate.
Phase 2 - Architecture | Foundations & design | E17, E19, E23 | Multi-tenant core, data model, API framework, security model, environments, CI/CD, observability, DR design. | Architecture sign-off; foundation services; pipelines.
Phase 3 - Development | Build core + business features | E01–E12, E18, E20, E21 | Iterative build of ticketing, sales, access, payments, F&B, retail, inventory, membership, promotions, seating, CRM, guest app, governance. | Working core + business modules behind feature flags.
Phase 4 - Integration | External ecosystem & intelligence | E14, E15, E22 | Payment/gateway certification, OTA/ERP, gov-authority and telephony integrations, hardware/device mgmt, phased AI/forecasting. | Certified integrations; device fleet mgmt; enabled AI.
Phase 5 - QA | Hardening & validation | Cross-cutting | Automated regression, performance/load, security/pen-test, UAT, accessibility & localization (EN/AR) checks. | Test reports; SLO & security sign-off; UAT acceptance.
Phase 6 - Deployment | Go-live & stabilise | E23 | Data migration & reconciliation, production cutover, go-live, 6-month Hypercare. | Production release; migrated data; Hypercare & handover.

## 7. Dependency Matrix
Category | Item / Capability | Depends On | Dependency Type | Notes / Risk
Technical | All functional modules | Multi-tenant core, Core data model, Auth/RBAC, API gateway | Foundational | Nothing functional ships before M1 foundation is stable.
Technical | POS & Mobile features | Backend domain APIs | Build-order | UI cannot be completed before its service contracts exist.
Technical | Offline POS / gate validation | Local cache + sync + offline crypto validation | Architectural | High-complexity; design in Phase 2 before dependent features.
Technical | Wallet, gift cards, reconciliation | Payment layer + ledger + tax engine | Data-integrity | Financial-grade correctness; sequence after payments core.
Technical | AI: forecasting / recommendation / dynamic pricing / fraud | Reporting & Analytics platform + 6–12 months operational data | Data-maturity | Cold-start problem; cannot be real-time Phase 1 — phase to M4+.
Technical | Reserved seating | Concurrency control / seat-locking | Architectural | Must prevent double-booking under load.
Business | Scope baseline | Discovery sign-off; OOTB/Config/Custom marking | Commercial | Fixed USD 200k strategic price exposed until baseline pinned.
Business | Biometric / facial recognition (gender-gated access) | Legal/compliance position (PDPL, ethics) | Regulatory | Formal position required before commitment.
Business | AI feature commitments | Agreed phasing (Phase 1 vs 2/3) | Commercial | Matrix assumes Phase 1; proposal positions ML later — reconcile.
Business | B2B partner / OTA onboarding | Commercial agreements, commission & credit terms | Process | Needed before B2B/channel-manager go-live.
Third-party | Payments | Stripe + Network International certification | Vendor | Gateway certs on critical path for M2/M4.
Third-party | Government / tourism | UAE Pass, DET, DCT, Al Hosn approvals & APIs | Vendor/Regulatory | Authority approval lead times; sequence early in M4.
Third-party | Distribution | OTA channel managers (Viator, Klook, Headout, GetYourGuide) | Vendor | API access & contracts per partner.
Third-party | Enterprise systems | ERP (SAP) / CRM / telephony (Genesys/Avaya/Amazon Connect) | Vendor | Client-side system access & test environments.
Third-party | Hardware | Turnstiles, BOCA/Zebra/Datamax/Evolis printers, RFID/NFC, facial readers, KDS, kiosks | Vendor | Device SDKs & lead times; client-procured per scope.
Infrastructure | All environments | Cloud accounts, networking, secrets, CI/CD, IaC | Client-provided | Client procures infra (per Contractor Agreement GC6).
Infrastructure | Availability & DR | 99.9% target, RPO/RTO tiers, backups, failover | NFR | Resolve proposal 99.9% vs SLA 99.5%; DR scope (62 items) under-reflected in contracts.
Infrastructure | Security | PCI-DSS, PDPL, SIEM, WAF, encryption, key rotation | Compliance | Drives architecture & audit; security sign-off gate in M5.

## 8. Missing Components
Missing & Recommended Components — enterprise concerns checked against the matrix
Component | Matrix Status | Signal (hits) | Recommendation | Suggested Milestone | Priority
Authentication | Present (explicit) | 86 | Consolidate into a single identity service (SSO/MFA/UAE Pass); already partly specified. | M3 | P2
Authorization / RBAC | Present (explicit) | 69 | Formalise a central RBAC model; matrix references roles but no unified engine. | M3 | P2
Authorization / ABAC | Partial / implicit | 5 | Build the ABAC policy engine (matrix D3.3 implies it) with policy builder, testing, anomaly detection. | M3 | P2
Audit Logs | Present (explicit) | 87 | Platform-wide immutable audit logging service consumed by all modules. | M3 | P2
Error Handling & Resilience | Present (explicit) | 8 | Add a resilience framework (retries, timeouts, circuit breakers, idempotency) — absent from matrix. | M1 | P1
Monitoring & Alerting | Present (explicit) | 91 | Central monitoring/alerting + SLO dashboards; tie to SLA. | M3 | P2
Analytics | Present (explicit) | 173 | Stand up the analytics platform that AI/reporting depend on. | M3 | P2
Notifications | Present (explicit) | 297 | Single notification service (email/SMS/WhatsApp/push) reused everywhere. | M3 | P2
Reporting | Present (explicit) | 349 | Shared reporting platform with role-based report access. | M3 | P2
Backup Strategy | Present (explicit) | 31 | Define backup policy (full/incremental/differential) per DR sheet. | M3 | P2
Disaster Recovery / BCP | Present (explicit) | 79 | Implement DR/BCP to agreed RPO/RTO; 62 matrix items must map to SLA. | M1 | P1
Security (encryption, WAF, SIEM) | Present (explicit) | 33 | Security architecture: encryption, WAF, SIEM, secrets, key rotation, PCI/PDPL. | M1 | P1
DevOps / IaC | MISSING | 0 | MISSING — add Infrastructure-as-Code and environment automation. | M1 | P1
CI/CD | MISSING | 0 | MISSING — add CI/CD pipelines with automated gates. | M1 | P1
Logging | Present (explicit) | 33 | Structured centralised logging with retention policy. | M3 | P2
API Documentation | Partial / implicit | 6 | Developer portal + OpenAPI docs; partly implied by E19. | M3 | P2
Testing / QA | Present (explicit) | 50 | Automated test suite + QA framework across unit/integration/E2E/perf/security. | M5 | P2
Performance Optimization | Present (explicit) | 90 | Performance budget, caching strategy, load testing to SLOs. | M5 | P2
Data Migration | Partial / implicit | 2 | Add migration/ETL + cutover plan — barely referenced in matrix. | M6 | P2
User Management | Partial / implicit | 5 | Unified user lifecycle/provisioning across tenants and staff. | M3 | P2
Configuration Management | Present (explicit) | 11 | Central config + feature-flag service to support phased rollout. | M1 | P1
Multi-tenancy | Partial / implicit | 7 | Make multi-tenant isolation an explicit foundational workstream. | M1 | P1
Localization (EN/AR RTL) | Present (explicit) | 13 | Localization framework incl. Arabic RTL across web/app/POS/print. | M3 | P2
Offline Capability | Present (explicit) | 18 | Offline-first design for POS and gate validation as a cross-cutting concern. | M3 | P2

## 9. Jira Import
Issue Type | Summary | Description | Epic Link | Parent | Priority | Story Points | Component | Labels
Epic | E01 Ticketing & Product Catalogue | Single source of truth for every sellable product; reduce SKU duplication and time-to-launch for new tickets/passes. |  |  | High |  |  | epic
Epic | E02 Sales Channels & Checkout | Maximise conversion and reach across every channel (web, B2B, kiosk, POS, call-centre) with one cart and pricing engine. |  |  | High |  |  | epic
Epic | E03 Admission & Access Control | Fast, fraud-resistant, offline-capable entry that protects revenue and guest flow at the gate. |  |  | High |  |  | epic
Epic | E04 Payments, Wallet & Financial | Secure, PCI-compliant money movement; one wallet and reconciliation backbone across all channels. |  |  | High |  |  | epic
Epic | E05 F&B Operations & POS | Efficient F&B service with kitchen integration, recipe costing and table/QR ordering. |  |  | High |  |  | epic
Epic | E06 Retail Operations & POS | Unified retail selling and stock visibility across stores, kiosks and online. |  |  | High |  |  | epic
Epic | E07 Inventory & Procurement | Accurate stock and procurement to cut shrinkage and stockouts across venues. |  |  | High |  |  | epic
Epic | E08 CRM, Marketing & Loyalty | Grow guest lifetime value through a unified profile, segmentation and loyalty. |  |  | High |  |  | epic
Epic | E09 Membership & Subscriptions | Recurring revenue via memberships/annual passes with automated billing and retention. |  |  | High |  |  | epic
Epic | E10 Events, Seating & Venue Mapping | Sell reserved-seat and timed experiences with live capacity and rich seat maps. |  |  | High |  |  | epic
Epic | E11 Bundles, Promotions & Pricing | Lift average order value through bundles, promotions and demand-based pricing. |  |  | High |  |  | epic
Epic | E12 Guest Mobile Experience | A branded, self-service guest app that carries tickets, wallet and personalised offers. |  |  | High |  |  | epic
Epic | E13 Employee Mobile & Workforce | Empower frontline staff with mobile operations, scheduling and an AI assistant. |  |  | High |  |  | epic
Epic | E14 Intelligence, Reporting & AI | Turn operational data into forecasting, recommendations and governed AI decisions. |  |  | High |  |  | epic
Epic | E15 Device & Peripheral Management | Centrally manage the device fleet (POS, kiosks, gates, peripherals) and firmware. |  |  | High |  |  | epic
Epic | E16 Maintenance, Safety & Asset Mgmt | Keep assets safe and available through preventive maintenance and work orders. |  |  | High |  |  | epic
Epic | E17 Identity, Security & Access Policy | Enforce identity, least-privilege access and security across the multi-tenant platform. |  |  | High |  |  | epic
Epic | E18 Governance, Approval & Accreditation | Govern change through approval workflows, accreditation and full auditability. |  |  | High |  |  | epic
Epic | E19 Developer Platform & API Mgmt | Expose the platform safely to partners and internal teams via a managed API layer. |  |  | High |  |  | epic
Epic | E20 Tenant, Subscription & Licensing | Operate as a true multi-tenant SaaS with self-service onboarding and licensing. |  |  | High |  |  | epic
Epic | E21 Digital Asset Management | Manage brand and media assets centrally with versioning and rights control. |  |  | High |  |  | epic
Epic | E22 Integrations & Ecosystem | Connect the platform to payment, tourism-authority, ERP, OTA and hardware ecosystems. |  |  | High |  |  | epic
Epic | E23 Platform Foundations & NFR | A scalable, observable, secure and recoverable foundation meeting all NFRs. |  |  | High |  |  | epic
Story | FEAT-001 Resource Management | Covers 63 matrix requirement(s). The system should allow management of all types of resources: - Areas with limited capacity (e.g. Meeting rooms, Cabanas, etc.) - Staff (e.g. Ski School Instructors, etc.) - Objects (e.g. Strollers, T… | E01 Ticketing & Product Catalogue |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-001: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Resource Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-001 Resource Management | Medium | 8 | Server Side / Backend | M4
Task | FEAT-001: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Resource Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-001 Resource Management | Medium | 13 | Server Side / Backend | M4
Task | FEAT-001: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Resource Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-001 Resource Management | Medium | 13 | Server Side / Backend | M4
Task | FEAT-001: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Resource Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-001 Resource Management | Medium | 8 | Server Side / Backend | M4
Task | FEAT-001: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Resource Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-001 Resource Management | Medium | 8 | Server Side / Backend | M4
Story | FEAT-002 Ticket Types | Covers 61 matrix requirement(s). The system should be able to sell open-dated tickets for attractions. | E01 Ticketing & Product Catalogue |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-002: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ticket Types' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-002 Ticket Types | Medium | 8 | Server Side / Backend | M4
Task | FEAT-002: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ticket Types' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-002 Ticket Types | Medium | 13 | Server Side / Backend | M4
Task | FEAT-002: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ticket Types' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-002 Ticket Types | Medium | 13 | Server Side / Backend | M4
Task | FEAT-002: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ticket Types' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-002 Ticket Types | Medium | 8 | Server Side / Backend | M4
Task | FEAT-002: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ticket Types' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-002 Ticket Types | Medium | 8 | Server Side / Backend | M4
Story | FEAT-003 Accounting | Covers 34 matrix requirement(s). The system should validate that required A/R account fields are populated with correct length and format based on the requirements provided by ERP. | E01 Ticketing & Product Catalogue |  | Highest | 13 | Server Side / Backend | M2_Phase_3
Task | FEAT-003: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Accounting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-003 Accounting | Highest | 5 | Server Side / Backend | M2
Task | FEAT-003: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Accounting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-003 Accounting | Highest | 8 | Server Side / Backend | M2
Task | FEAT-003: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Accounting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-003 Accounting | Highest | 8 | Server Side / Backend | M2
Task | FEAT-003: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Accounting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-003 Accounting | Highest | 5 | Server Side / Backend | M2
Task | FEAT-003: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Accounting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-003 Accounting | Highest | 5 | Server Side / Backend | M2
Story | FEAT-004 Virtual Queue | Covers 18 matrix requirement(s). Multiple Queue Types: First-come-first-serve, priority/VIP, group queues. | E01 Ticketing & Product Catalogue |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-004: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Virtual Queue' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-004 Virtual Queue | Medium | 3 | Server Side / Backend | M4
Task | FEAT-004: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Virtual Queue' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-004 Virtual Queue | Medium | 5 | Server Side / Backend | M4
Task | FEAT-004: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Virtual Queue' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-004 Virtual Queue | Medium | 5 | Server Side / Backend | M4
Task | FEAT-004: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Virtual Queue' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-004 Virtual Queue | Medium | 3 | Server Side / Backend | M4
Task | FEAT-004: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Virtual Queue' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-004 Virtual Queue | Medium | 3 | Server Side / Backend | M4
Story | FEAT-005 Profile Management | Covers 15 matrix requirement(s). The system should allow creation of guest accounts. Mandatory and optional details needed for a guest account must be configurable by the System Admin user. | E01 Ticketing & Product Catalogue |  | Highest | 8 | Server Side / Backend | M2_Phase_3
Task | FEAT-005: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Profile Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-005 Profile Management | Highest | 2 | Server Side / Backend | M2
Task | FEAT-005: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Profile Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-005 Profile Management | Highest | 2 | Server Side / Backend | M2
Task | FEAT-005: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Profile Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-005 Profile Management | Highest | 3 | Server Side / Backend | M2
Task | FEAT-005: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Profile Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-005 Profile Management | Highest | 2 | Server Side / Backend | M2
Task | FEAT-005: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Profile Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-005 Profile Management | Highest | 2 | Server Side / Backend | M2
Story | FEAT-006 Authentication And Login | Covers 12 matrix requirement(s). Ticket Purchase - System shall support ticket purchases. | E01 Ticketing & Product Catalogue |  | Highest | 8 | Mobile App | M2_Phase_3
Task | FEAT-006: UI screens (iOS & Android) | Implement shared + platform UI components. Acceptance: 'Authentication And Login' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-006 Authentication And Login | Highest | 3 | Mobile App | M2
Task | FEAT-006: State & API integration | Data layer, caching and API wiring. Acceptance: 'Authentication And Login' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-006 Authentication And Login | Highest | 3 | Mobile App | M2
Task | FEAT-006: Offline & push handling | Offline storage, sync and push notifications. Acceptance: 'Authentication And Login' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-006 Authentication And Login | Highest | 2 | Mobile App | M2
Task | FEAT-006: Mobile E2E tests | Automated tests across iOS/Android. Acceptance: 'Authentication And Login' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-006 Authentication And Login | Highest | 2 | Mobile App | M2
Story | FEAT-007 Product Lifecycle | Covers 10 matrix requirement(s). The system should allow configuration of workflows to manage the creation of new tickets and products. The workflow should involve setup of different status values (e.g. disabled, approval pending, et… | E01 Ticketing & Product Catalogue |  | Highest | 8 | Server Side / Backend | M2_Phase_3
Task | FEAT-007: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Product Lifecycle' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-007 Product Lifecycle | Highest | 1 | Server Side / Backend | M2
Task | FEAT-007: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Product Lifecycle' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-007 Product Lifecycle | Highest | 2 | Server Side / Backend | M2
Task | FEAT-007: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Product Lifecycle' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-007 Product Lifecycle | Highest | 2 | Server Side / Backend | M2
Task | FEAT-007: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Product Lifecycle' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-007 Product Lifecycle | Highest | 1 | Server Side / Backend | M2
Task | FEAT-007: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Product Lifecycle' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-007 Product Lifecycle | Highest | 1 | Server Side / Backend | M2
Story | FEAT-008 Ticket Resale Marketplace | Covers 10 matrix requirement(s). System shall support a configurable ticket resale marketplace allowing eligible ticket holders to list tickets for resale through web, mobile application, partner channels, or marketplace portals. | E01 Ticketing & Product Catalogue |  | Highest | 13 | Server Side / Backend | M2_Phase_3
Task | FEAT-008: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ticket Resale Marketplace' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-008 Ticket Resale Marketplace | Highest | 2 | Server Side / Backend | M2
Task | FEAT-008: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ticket Resale Marketplace' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-008 Ticket Resale Marketplace | Highest | 3 | Server Side / Backend | M2
Task | FEAT-008: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ticket Resale Marketplace' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-008 Ticket Resale Marketplace | Highest | 5 | Server Side / Backend | M2
Task | FEAT-008: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ticket Resale Marketplace' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-008 Ticket Resale Marketplace | Highest | 2 | Server Side / Backend | M2
Task | FEAT-008: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ticket Resale Marketplace' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-008 Ticket Resale Marketplace | Highest | 2 | Server Side / Backend | M2
Story | FEAT-009 Game And Ride Payment And Redemption | Covers 9 matrix requirement(s). The system should have ability to define multiple types of readers (minimum three). The properties of the readers should be configurable: - type of credit accepted at a reader - amount of credit requi… | E01 Ticketing & Product Catalogue |  | Highest | 8 | Server Side / Backend | M2_Phase_3
Task | FEAT-009: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Game And Ride Payment And Redemption' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-009 Game And Ride Payment And Redemption | Highest | 1 | Server Side / Backend | M2
Task | FEAT-009: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Game And Ride Payment And Redemption' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-009 Game And Ride Payment And Redemption | Highest | 2 | Server Side / Backend | M2
Task | FEAT-009: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Game And Ride Payment And Redemption' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-009 Game And Ride Payment And Redemption | Highest | 2 | Server Side / Backend | M2
Task | FEAT-009: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Game And Ride Payment And Redemption' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-009 Game And Ride Payment And Redemption | Highest | 1 | Server Side / Backend | M2
Task | FEAT-009: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Game And Ride Payment And Redemption' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-009 Game And Ride Payment And Redemption | Highest | 1 | Server Side / Backend | M2
Story | FEAT-010 Digital Waiver Management | Covers 8 matrix requirement(s). To provide ability that allows Guest to fill in the form at the desk using a tablet. | E01 Ticketing & Product Catalogue |  | Highest | 5 | Server Side / Backend | M2_Phase_3
Task | FEAT-010: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Digital Waiver Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-010 Digital Waiver Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-010: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Digital Waiver Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-010 Digital Waiver Management | Highest | 2 | Server Side / Backend | M2
Task | FEAT-010: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Digital Waiver Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-010 Digital Waiver Management | Highest | 2 | Server Side / Backend | M2
Task | FEAT-010: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Digital Waiver Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-010 Digital Waiver Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-010: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Digital Waiver Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-010 Digital Waiver Management | Highest | 1 | Server Side / Backend | M2
Story | FEAT-011 Ticket Media | Covers 8 matrix requirement(s). Waiver-Ticket Linkage | E01 Ticketing & Product Catalogue |  | Highest | 5 | Server Side / Backend | M2_Phase_3
Task | FEAT-011: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ticket Media' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-011 Ticket Media | Highest | 1 | Server Side / Backend | M2
Task | FEAT-011: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ticket Media' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-011 Ticket Media | Highest | 2 | Server Side / Backend | M2
Task | FEAT-011: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ticket Media' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-011 Ticket Media | Highest | 2 | Server Side / Backend | M2
Task | FEAT-011: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ticket Media' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-011 Ticket Media | Highest | 1 | Server Side / Backend | M2
Task | FEAT-011: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ticket Media' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-011 Ticket Media | Highest | 1 | Server Side / Backend | M2
Story | FEAT-012 Portfolio And Entitlement Management | Covers 7 matrix requirement(s). Support temporary and permanent portfolio sharing while maintaining ownership controls. | E01 Ticketing & Product Catalogue |  | Highest | 8 | Server Side / Backend | M2_Phase_3
Task | FEAT-012: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Portfolio And Entitlement Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-012 Portfolio And Entitlement Management | Highest | 2 | Server Side / Backend | M2
Task | FEAT-012: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Portfolio And Entitlement Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-012 Portfolio And Entitlement Management | Highest | 3 | Server Side / Backend | M2
Task | FEAT-012: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Portfolio And Entitlement Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-012 Portfolio And Entitlement Management | Highest | 3 | Server Side / Backend | M2
Task | FEAT-012: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Portfolio And Entitlement Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-012 Portfolio And Entitlement Management | Highest | 2 | Server Side / Backend | M2
Task | FEAT-012: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Portfolio And Entitlement Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-012 Portfolio And Entitlement Management | Highest | 2 | Server Side / Backend | M2
Story | FEAT-013 Digital Waivers And Signature Management | Covers 7 matrix requirement(s). Waiver Template Builder System shall allow administrators to create and manage waiver templates, liability releases, consent forms, parental consent forms, medical declarations, activity agreements, a… | E01 Ticketing & Product Catalogue |  | Highest | 5 | Server Side / Backend | M2_Phase_3
Task | FEAT-013: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Digital Waivers And Signature Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-013 Digital Waivers And Signature Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-013: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Digital Waivers And Signature Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-013 Digital Waivers And Signature Management | Highest | 2 | Server Side / Backend | M2
Task | FEAT-013: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Digital Waivers And Signature Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-013 Digital Waivers And Signature Management | Highest | 2 | Server Side / Backend | M2
Task | FEAT-013: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Digital Waivers And Signature Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-013 Digital Waivers And Signature Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-013: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Digital Waivers And Signature Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-013 Digital Waivers And Signature Management | Highest | 1 | Server Side / Backend | M2
Story | FEAT-014 Fraud Detection | Covers 6 matrix requirement(s). System shall detect duplicate ticket usage. | E01 Ticketing & Product Catalogue |  | Highest | 5 | Server Side / Backend | M2_Phase_3
Task | FEAT-014: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Fraud Detection' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-014 Fraud Detection | Highest | 1 | Server Side / Backend | M2
Task | FEAT-014: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Fraud Detection' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-014 Fraud Detection | Highest | 1 | Server Side / Backend | M2
Task | FEAT-014: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Fraud Detection' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-014 Fraud Detection | Highest | 2 | Server Side / Backend | M2
Task | FEAT-014: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Fraud Detection' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-014 Fraud Detection | Highest | 1 | Server Side / Backend | M2
Task | FEAT-014: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Fraud Detection' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-014 Fraud Detection | Highest | 1 | Server Side / Backend | M2
Story | FEAT-015 Ticket Upgrades | Covers 5 matrix requirement(s). The system should guarantee the integrity of all pre-existing revenue by ensuring that when an amount is amended, the value of prior sales is not modified. | E01 Ticketing & Product Catalogue |  | Highest | 5 | Server Side / Backend | M2_Phase_3
Task | FEAT-015: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ticket Upgrades' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-015 Ticket Upgrades | Highest | 1 | Server Side / Backend | M2
Task | FEAT-015: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ticket Upgrades' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-015 Ticket Upgrades | Highest | 1 | Server Side / Backend | M2
Task | FEAT-015: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ticket Upgrades' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-015 Ticket Upgrades | Highest | 2 | Server Side / Backend | M2
Task | FEAT-015: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ticket Upgrades' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-015 Ticket Upgrades | Highest | 1 | Server Side / Backend | M2
Task | FEAT-015: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ticket Upgrades' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-015 Ticket Upgrades | Highest | 1 | Server Side / Backend | M2
Story | FEAT-016 Cash Handling | Covers 5 matrix requirement(s). The system should allow allocation of a deposit box for each cashier. | E01 Ticketing & Product Catalogue |  | Highest | 5 | POS App | M2_Phase_3
Task | FEAT-016: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Cash Handling' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-016 Cash Handling | Highest | 1 | POS App | M2
Task | FEAT-016: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Cash Handling' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-016 Cash Handling | Highest | 1 | POS App | M2
Task | FEAT-016: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Cash Handling' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-016 Cash Handling | Highest | 1 | POS App | M2
Task | FEAT-016: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Cash Handling' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-016 Cash Handling | Highest | 1 | POS App | M2
Task | FEAT-016: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Cash Handling' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-016 Cash Handling | Highest | 1 | POS App | M2
Story | FEAT-017 Payment Methods | Covers 2 matrix requirement(s). The system should be able to have a cover level widget on the home screen of the table management - to understand the available cover vs. engaged covers. | E01 Ticketing & Product Catalogue |  | Highest | 3 | Server Side / Backend | M2_Phase_3
Task | FEAT-017: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Payment Methods' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-017 Payment Methods | Highest | 1 | Server Side / Backend | M2
Task | FEAT-017: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Payment Methods' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-017 Payment Methods | Highest | 1 | Server Side / Backend | M2
Task | FEAT-017: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Payment Methods' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-017 Payment Methods | Highest | 1 | Server Side / Backend | M2
Task | FEAT-017: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Payment Methods' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-017 Payment Methods | Highest | 1 | Server Side / Backend | M2
Task | FEAT-017: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Payment Methods' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-017 Payment Methods | Highest | 1 | Server Side / Backend | M2
Story | FEAT-018 Portfolio Management | Covers 2 matrix requirement(s). The system should support a ticketing data model which allows a guest to purchase and manage multiple tickets (portfolio of tickets) under their account. | E01 Ticketing & Product Catalogue |  | Highest | 3 | Server Side / Backend | M2_Phase_3
Task | FEAT-018: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Portfolio Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-018 Portfolio Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-018: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Portfolio Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-018 Portfolio Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-018: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Portfolio Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-018 Portfolio Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-018: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Portfolio Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-018 Portfolio Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-018: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Portfolio Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-018 Portfolio Management | Highest | 1 | Server Side / Backend | M2
Story | FEAT-019 Receipt | Covers 2 matrix requirement(s). The system should provide a simple way to print receipts for guests depending on their purchases and their consumptions (i.e. pay‐per‐use). | E01 Ticketing & Product Catalogue |  | Highest | 3 | Server Side / Backend | M2_Phase_3
Task | FEAT-019: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Receipt' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-019 Receipt | Highest | 1 | Server Side / Backend | M2
Task | FEAT-019: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Receipt' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-019 Receipt | Highest | 1 | Server Side / Backend | M2
Task | FEAT-019: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Receipt' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-019 Receipt | Highest | 1 | Server Side / Backend | M2
Task | FEAT-019: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Receipt' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-019 Receipt | Highest | 1 | Server Side / Backend | M2
Task | FEAT-019: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Receipt' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-019 Receipt | Highest | 1 | Server Side / Backend | M2
Story | FEAT-020 Ai Engine | Covers 2 matrix requirement(s). System shall support AI-powered ticketing assistance. | E01 Ticketing & Product Catalogue |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-020: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ai Engine' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-020 Ai Engine | Medium | 1 | Server Side / Backend | M4
Task | FEAT-020: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ai Engine' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-020 Ai Engine | Medium | 2 | Server Side / Backend | M4
Task | FEAT-020: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ai Engine' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-020 Ai Engine | Medium | 2 | Server Side / Backend | M4
Task | FEAT-020: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ai Engine' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-020 Ai Engine | Medium | 1 | Server Side / Backend | M4
Task | FEAT-020: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ai Engine' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-020 Ai Engine | Medium | 1 | Server Side / Backend | M4
Story | FEAT-021 Guest Profiles And Data Management | Covers 2 matrix requirement(s). Consent Management Guest profiles shall store marketing consents, privacy preferences, opt-ins, opt-outs, waiver acknowledgements, and consent audit trails. | E01 Ticketing & Product Catalogue |  | Highest | 3 | Server Side / Backend | M2_Phase_3
Task | FEAT-021: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Guest Profiles And Data Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-021 Guest Profiles And Data Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-021: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Guest Profiles And Data Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-021 Guest Profiles And Data Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-021: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Guest Profiles And Data Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-021 Guest Profiles And Data Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-021: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Guest Profiles And Data Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-021 Guest Profiles And Data Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-021: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Guest Profiles And Data Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-021 Guest Profiles And Data Management | Highest | 1 | Server Side / Backend | M2
Story | FEAT-022 Loyalty | Covers 1 matrix requirement(s). The system should be able to integrate with a loyalty point system which would provide the guest with a list of loyalty points according to the purchase value/purchased tickets/purchased services and … | E01 Ticketing & Product Catalogue |  | Highest | 1 | Server Side / Backend | M2_Phase_3
Task | FEAT-022: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Loyalty' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-022 Loyalty | Highest | 1 | Server Side / Backend | M2
Task | FEAT-022: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Loyalty' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-022 Loyalty | Highest | 1 | Server Side / Backend | M2
Task | FEAT-022: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Loyalty' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-022 Loyalty | Highest | 1 | Server Side / Backend | M2
Task | FEAT-022: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Loyalty' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-022 Loyalty | Highest | 1 | Server Side / Backend | M2
Task | FEAT-022: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Loyalty' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-022 Loyalty | Highest | 1 | Server Side / Backend | M2
Story | FEAT-023 Ai Configuration Assistant | Covers 1 matrix requirement(s). It is possible to manage Invitations or complimentary Ticketing PLUs for which, no payment is expected. | E01 Ticketing & Product Catalogue |  | Highest | 3 | Server Side / Backend | M2_Phase_3
Task | FEAT-023: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ai Configuration Assistant' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-023 Ai Configuration Assistant | Highest | 1 | Server Side / Backend | M2
Task | FEAT-023: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ai Configuration Assistant' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-023 Ai Configuration Assistant | Highest | 1 | Server Side / Backend | M2
Task | FEAT-023: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ai Configuration Assistant' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-023 Ai Configuration Assistant | Highest | 1 | Server Side / Backend | M2
Task | FEAT-023: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ai Configuration Assistant' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-023 Ai Configuration Assistant | Highest | 1 | Server Side / Backend | M2
Task | FEAT-023: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ai Configuration Assistant' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-023 Ai Configuration Assistant | Highest | 1 | Server Side / Backend | M2
Story | FEAT-024 Recommendation Engine | Covers 1 matrix requirement(s). System shall provide personalized ticket recommendations. | E01 Ticketing & Product Catalogue |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-024: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Recommendation Engine' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-024 Recommendation Engine | Medium | 1 | Server Side / Backend | M4
Task | FEAT-024: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Recommendation Engine' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-024 Recommendation Engine | Medium | 2 | Server Side / Backend | M4
Task | FEAT-024: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Recommendation Engine' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-024 Recommendation Engine | Medium | 2 | Server Side / Backend | M4
Task | FEAT-024: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Recommendation Engine' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-024 Recommendation Engine | Medium | 1 | Server Side / Backend | M4
Task | FEAT-024: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Recommendation Engine' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-024 Recommendation Engine | Medium | 1 | Server Side / Backend | M4
Story | FEAT-025 Bi And Reporting | Covers 1 matrix requirement(s). System shall provide ticketing dashboards. | E01 Ticketing & Product Catalogue |  | Highest | 1 | Server Side / Backend | M2_Phase_3
Task | FEAT-025: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Bi And Reporting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-025 Bi And Reporting | Highest | 1 | Server Side / Backend | M2
Task | FEAT-025: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Bi And Reporting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-025 Bi And Reporting | Highest | 1 | Server Side / Backend | M2
Task | FEAT-025: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Bi And Reporting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-025 Bi And Reporting | Highest | 1 | Server Side / Backend | M2
Task | FEAT-025: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Bi And Reporting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-025 Bi And Reporting | Highest | 1 | Server Side / Backend | M2
Task | FEAT-025: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Bi And Reporting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-025 Bi And Reporting | Highest | 1 | Server Side / Backend | M2
Story | FEAT-026 Reporting And Dashboards | Covers 1 matrix requirement(s). Expiration Management System shall support temporary and permanent accreditation validity periods. | E01 Ticketing & Product Catalogue |  | Highest | 3 | Server Side / Backend | M2_Phase_3
Task | FEAT-026: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Reporting And Dashboards' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-026 Reporting And Dashboards | Highest | 1 | Server Side / Backend | M2
Task | FEAT-026: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Reporting And Dashboards' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-026 Reporting And Dashboards | Highest | 1 | Server Side / Backend | M2
Task | FEAT-026: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Reporting And Dashboards' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-026 Reporting And Dashboards | Highest | 1 | Server Side / Backend | M2
Task | FEAT-026: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Reporting And Dashboards' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-026 Reporting And Dashboards | Highest | 1 | Server Side / Backend | M2
Task | FEAT-026: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Reporting And Dashboards' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-026 Reporting And Dashboards | Highest | 1 | Server Side / Backend | M2
Story | FEAT-027 Device Integrations | Covers 1 matrix requirement(s). Printer Integration - System shall support receipt and ticket printer integration. | E01 Ticketing & Product Catalogue |  | Highest | 5 | Server Side / Backend | M2_Phase_3
Task | FEAT-027: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Device Integrations' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-027 Device Integrations | Highest | 1 | Server Side / Backend | M2
Task | FEAT-027: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Device Integrations' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-027 Device Integrations | Highest | 2 | Server Side / Backend | M2
Task | FEAT-027: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Device Integrations' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-027 Device Integrations | Highest | 2 | Server Side / Backend | M2
Task | FEAT-027: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Device Integrations' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-027 Device Integrations | Highest | 1 | Server Side / Backend | M2
Task | FEAT-027: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Device Integrations' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-027 Device Integrations | Highest | 1 | Server Side / Backend | M2
Story | FEAT-028 Module Marketplace And Management | Covers 1 matrix requirement(s). Marketplace Catalog - System shall provide a marketplace of available modules. | E01 Ticketing & Product Catalogue |  | Highest | 3 | Server Side / Backend | M2_Phase_3
Task | FEAT-028: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Module Marketplace And Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-028 Module Marketplace And Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-028: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Module Marketplace And Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-028 Module Marketplace And Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-028: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Module Marketplace And Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-028 Module Marketplace And Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-028: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Module Marketplace And Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-028 Module Marketplace And Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-028: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Module Marketplace And Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E01 Ticketing & Product Catalogue | FEAT-028 Module Marketplace And Management | Highest | 1 | Server Side / Backend | M2
Story | FEAT-029 Call Center Sales | Covers 36 matrix requirement(s). It should have the ability to have one API connecting the system to the external B2B website | E02 Sales Channels & Checkout |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-029: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Call Center Sales' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-029 Call Center Sales | Medium | 5 | Server Side / Backend | M4
Task | FEAT-029: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Call Center Sales' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-029 Call Center Sales | Medium | 8 | Server Side / Backend | M4
Task | FEAT-029: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Call Center Sales' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-029 Call Center Sales | Medium | 13 | Server Side / Backend | M4
Task | FEAT-029: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Call Center Sales' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-029 Call Center Sales | Medium | 5 | Server Side / Backend | M4
Task | FEAT-029: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Call Center Sales' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-029 Call Center Sales | Medium | 5 | Server Side / Backend | M4
Story | FEAT-030 Sales Channels | Covers 15 matrix requirement(s). The system should allow for any ticket type to be removed from sale without suspending that ticket type from use (i.e. Tickets that were already sold to guests should remain valid). | E02 Sales Channels & Checkout |  | Highest | 13 | Server Side / Backend | M2_Phase_3
Task | FEAT-030: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Sales Channels' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-030 Sales Channels | Highest | 3 | Server Side / Backend | M2
Task | FEAT-030: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Sales Channels' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-030 Sales Channels | Highest | 5 | Server Side / Backend | M2
Task | FEAT-030: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Sales Channels' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-030 Sales Channels | Highest | 5 | Server Side / Backend | M2
Task | FEAT-030: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Sales Channels' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-030 Sales Channels | Highest | 3 | Server Side / Backend | M2
Task | FEAT-030: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Sales Channels' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-030 Sales Channels | Highest | 3 | Server Side / Backend | M2
Story | FEAT-031 Work Order Management | Covers 15 matrix requirement(s). Work Order Creation - System shall support work order creation. | E02 Sales Channels & Checkout |  | Highest | 8 | Server Side / Backend | M2_Phase_3
Task | FEAT-031: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Work Order Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-031 Work Order Management | Highest | 2 | Server Side / Backend | M2
Task | FEAT-031: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Work Order Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-031 Work Order Management | Highest | 2 | Server Side / Backend | M2
Task | FEAT-031: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Work Order Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-031 Work Order Management | Highest | 3 | Server Side / Backend | M2
Task | FEAT-031: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Work Order Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-031 Work Order Management | Highest | 2 | Server Side / Backend | M2
Task | FEAT-031: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Work Order Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-031 Work Order Management | Highest | 2 | Server Side / Backend | M2
Story | FEAT-032 Order Management | Covers 10 matrix requirement(s). The system should support configuration of required access level to allow refund, exchange and/or void actions. At minimum, the system should provide: - Ability to enable/disable supervisor access req… | E02 Sales Channels & Checkout |  | Highest | 8 | Server Side / Backend | M2_Phase_3
Task | FEAT-032: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Order Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-032 Order Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-032: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Order Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-032 Order Management | Highest | 2 | Server Side / Backend | M2
Task | FEAT-032: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Order Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-032 Order Management | Highest | 2 | Server Side / Backend | M2
Task | FEAT-032: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Order Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-032 Order Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-032: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Order Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-032 Order Management | Highest | 1 | Server Side / Backend | M2
Story | FEAT-033 Usage And Quota Monitoring | Covers 7 matrix requirement(s). User Usage Monitoring - System shall monitor active user consumption. | E02 Sales Channels & Checkout |  | Highest | 5 | Cross Platform | M2_Phase_3
Task | FEAT-033: Design & technical spec | Architecture, interfaces and acceptance criteria. Acceptance: 'Usage And Quota Monitoring' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-033 Usage And Quota Monitoring | Highest | 1 | Cross Platform | M2
Task | FEAT-033: Implementation | Build the capability / automation. Acceptance: 'Usage And Quota Monitoring' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-033 Usage And Quota Monitoring | Highest | 2 | Cross Platform | M2
Task | FEAT-033: Automation & CI integration | Pipeline, IaC and gates. Acceptance: 'Usage And Quota Monitoring' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-033 Usage And Quota Monitoring | Highest | 1 | Cross Platform | M2
Task | FEAT-033: Verification & sign-off | Validate against NFR/acceptance criteria. Acceptance: 'Usage And Quota Monitoring' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-033 Usage And Quota Monitoring | Highest | 1 | Cross Platform | M2
Story | FEAT-034 Ticket Upgrades | Covers 4 matrix requirement(s). The system should allow configuration of a holding time for a capacity-based product. When a capacity-based product is added to the cart, the capacity should be reserved for configurable X minutes; if… | E02 Sales Channels & Checkout |  | Highest | 5 | Server Side / Backend | M2_Phase_3
Task | FEAT-034: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ticket Upgrades' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-034 Ticket Upgrades | Highest | 1 | Server Side / Backend | M2
Task | FEAT-034: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ticket Upgrades' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-034 Ticket Upgrades | Highest | 1 | Server Side / Backend | M2
Task | FEAT-034: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ticket Upgrades' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-034 Ticket Upgrades | Highest | 2 | Server Side / Backend | M2
Task | FEAT-034: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ticket Upgrades' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-034 Ticket Upgrades | Highest | 1 | Server Side / Backend | M2
Task | FEAT-034: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ticket Upgrades' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-034 Ticket Upgrades | Highest | 1 | Server Side / Backend | M2
Story | FEAT-035 Ticket Types | Covers 3 matrix requirement(s). Functional Requirements Fixed Donation Fixed donation amount. Multiple predefined donation values. Variable Donation Customer enters donation amount. Configurable minimum and maximum donation values. … | E02 Sales Channels & Checkout |  | Highest | 2 | Server Side / Backend | M2_Phase_3
Task | FEAT-035: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ticket Types' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-035 Ticket Types | Highest | 1 | Server Side / Backend | M2
Task | FEAT-035: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ticket Types' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-035 Ticket Types | Highest | 1 | Server Side / Backend | M2
Task | FEAT-035: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ticket Types' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-035 Ticket Types | Highest | 1 | Server Side / Backend | M2
Task | FEAT-035: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ticket Types' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-035 Ticket Types | Highest | 1 | Server Side / Backend | M2
Task | FEAT-035: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ticket Types' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-035 Ticket Types | Highest | 1 | Server Side / Backend | M2
Story | FEAT-036 Product Lifecycle | Covers 3 matrix requirement(s). System shall support creation and maintenance of products in Draft status without exposing them to sales channels. | E02 Sales Channels & Checkout |  | Highest | 5 | Server Side / Backend | M2_Phase_3
Task | FEAT-036: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Product Lifecycle' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-036 Product Lifecycle | Highest | 1 | Server Side / Backend | M2
Task | FEAT-036: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Product Lifecycle' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-036 Product Lifecycle | Highest | 1 | Server Side / Backend | M2
Task | FEAT-036: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Product Lifecycle' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-036 Product Lifecycle | Highest | 1 | Server Side / Backend | M2
Task | FEAT-036: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Product Lifecycle' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-036 Product Lifecycle | Highest | 1 | Server Side / Backend | M2
Task | FEAT-036: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Product Lifecycle' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-036 Product Lifecycle | Highest | 1 | Server Side / Backend | M2
Story | FEAT-037 B2B Sales | Covers 3 matrix requirement(s). The system should support multiple languages for the Ticketing POS, Self-Service Kiosks, websites mobile app and backend . | E02 Sales Channels & Checkout |  | Highest | 8 | Server Side / Backend | M2_Phase_3
Task | FEAT-037: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'B2B Sales' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-037 B2B Sales | Highest | 1 | Server Side / Backend | M2
Task | FEAT-037: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'B2B Sales' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-037 B2B Sales | Highest | 2 | Server Side / Backend | M2
Task | FEAT-037: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'B2B Sales' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-037 B2B Sales | Highest | 2 | Server Side / Backend | M2
Task | FEAT-037: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'B2B Sales' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-037 B2B Sales | Highest | 1 | Server Side / Backend | M2
Task | FEAT-037: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'B2B Sales' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-037 B2B Sales | Highest | 1 | Server Side / Backend | M2
Story | FEAT-038 Case Management And Sla | Covers 3 matrix requirement(s). Case Creation System shall support creation of customer service cases originating from website, mobile app, POS, kiosk, call center, CRM, email, chat, WhatsApp, API integrations, and internal users. | E02 Sales Channels & Checkout |  | Highest | 8 | Server Side / Backend | M2_Phase_3
Task | FEAT-038: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Case Management And Sla' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-038 Case Management And Sla | Highest | 1 | Server Side / Backend | M2
Task | FEAT-038: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Case Management And Sla' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-038 Case Management And Sla | Highest | 2 | Server Side / Backend | M2
Task | FEAT-038: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Case Management And Sla' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-038 Case Management And Sla | Highest | 2 | Server Side / Backend | M2
Task | FEAT-038: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Case Management And Sla' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-038 Case Management And Sla | Highest | 1 | Server Side / Backend | M2
Task | FEAT-038: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Case Management And Sla' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-038 Case Management And Sla | Highest | 1 | Server Side / Backend | M2
Story | FEAT-039 Digital Waiver Management | Covers 2 matrix requirement(s). The system should be to apply a transaction fee to ticket orders taken over specific sales channels, such as the call center. The transaction fee should also be applicable for actions like ticket modi… | E02 Sales Channels & Checkout |  | Highest | 3 | Server Side / Backend | M2_Phase_3
Task | FEAT-039: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Digital Waiver Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-039 Digital Waiver Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-039: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Digital Waiver Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-039 Digital Waiver Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-039: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Digital Waiver Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-039 Digital Waiver Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-039: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Digital Waiver Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-039 Digital Waiver Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-039: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Digital Waiver Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-039 Digital Waiver Management | Highest | 1 | Server Side / Backend | M2
Story | FEAT-040 Accounting | Covers 2 matrix requirement(s). The system should be able to validate that all transactions are balanced. Total debits must equal total credits per transaction. | E02 Sales Channels & Checkout |  | Highest | 3 | Server Side / Backend | M2_Phase_3
Task | FEAT-040: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Accounting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-040 Accounting | Highest | 1 | Server Side / Backend | M2
Task | FEAT-040: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Accounting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-040 Accounting | Highest | 1 | Server Side / Backend | M2
Task | FEAT-040: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Accounting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-040 Accounting | Highest | 1 | Server Side / Backend | M2
Task | FEAT-040: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Accounting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-040 Accounting | Highest | 1 | Server Side / Backend | M2
Task | FEAT-040: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Accounting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-040 Accounting | Highest | 1 | Server Side / Backend | M2
Story | FEAT-041 Demand Forecasting | Covers 2 matrix requirement(s). System shall forecast revenue by sales channel. | E02 Sales Channels & Checkout |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-041: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Demand Forecasting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-041 Demand Forecasting | Medium | 1 | Server Side / Backend | M4
Task | FEAT-041: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Demand Forecasting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-041 Demand Forecasting | Medium | 2 | Server Side / Backend | M4
Task | FEAT-041: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Demand Forecasting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-041 Demand Forecasting | Medium | 2 | Server Side / Backend | M4
Task | FEAT-041: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Demand Forecasting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-041 Demand Forecasting | Medium | 1 | Server Side / Backend | M4
Task | FEAT-041: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Demand Forecasting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-041 Demand Forecasting | Medium | 1 | Server Side / Backend | M4
Story | FEAT-042 Digital Waivers And Signature Management | Covers 2 matrix requirement(s). Digital Signature Capture System shall support electronic signatures through website, mobile application, kiosks, tablets, POS devices, and dedicated waiver stations. | E02 Sales Channels & Checkout |  | Highest | 3 | Server Side / Backend | M2_Phase_3
Task | FEAT-042: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Digital Waivers And Signature Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-042 Digital Waivers And Signature Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-042: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Digital Waivers And Signature Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-042 Digital Waivers And Signature Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-042: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Digital Waivers And Signature Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-042 Digital Waivers And Signature Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-042: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Digital Waivers And Signature Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-042 Digital Waivers And Signature Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-042: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Digital Waivers And Signature Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-042 Digital Waivers And Signature Management | Highest | 1 | Server Side / Backend | M2
Story | FEAT-043 Ticketing Pos And Kiosks | Covers 1 matrix requirement(s). The system should provide a sales interface that is as close to a website interface, considering UX design for a seamless journey. | E02 Sales Channels & Checkout |  | Highest | 3 | POS App | M2_Phase_3
Task | FEAT-043: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Ticketing Pos And Kiosks' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-043 Ticketing Pos And Kiosks | Highest | 1 | POS App | M2
Task | FEAT-043: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Ticketing Pos And Kiosks' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-043 Ticketing Pos And Kiosks | Highest | 1 | POS App | M2
Task | FEAT-043: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Ticketing Pos And Kiosks' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-043 Ticketing Pos And Kiosks | Highest | 1 | POS App | M2
Task | FEAT-043: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Ticketing Pos And Kiosks' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-043 Ticketing Pos And Kiosks | Highest | 1 | POS App | M2
Task | FEAT-043: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Ticketing Pos And Kiosks' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-043 Ticketing Pos And Kiosks | Highest | 1 | POS App | M2
Story | FEAT-044 Profile Management | Covers 1 matrix requirement(s). The system should be able to accept checkout for guests that do not wish to create an account in order to complete an order. Minimum required information as configured (e.g. email address) will still … | E02 Sales Channels & Checkout |  | Highest | 1 | Server Side / Backend | M2_Phase_3
Task | FEAT-044: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Profile Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-044 Profile Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-044: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Profile Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-044 Profile Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-044: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Profile Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-044 Profile Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-044: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Profile Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-044 Profile Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-044: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Profile Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-044 Profile Management | Highest | 1 | Server Side / Backend | M2
Story | FEAT-045 Virtual Queue | Covers 1 matrix requirement(s). Expose APIs for third-party systems, kiosks, apps, CRM, and partners. | E02 Sales Channels & Checkout |  | Highest | 3 | POS App | M2_Phase_3
Task | FEAT-045: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Virtual Queue' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-045 Virtual Queue | Highest | 1 | POS App | M2
Task | FEAT-045: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Virtual Queue' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-045 Virtual Queue | Highest | 1 | POS App | M2
Task | FEAT-045: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Virtual Queue' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-045 Virtual Queue | Highest | 1 | POS App | M2
Task | FEAT-045: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Virtual Queue' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-045 Virtual Queue | Highest | 1 | POS App | M2
Task | FEAT-045: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Virtual Queue' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-045 Virtual Queue | Highest | 1 | POS App | M2
Story | FEAT-046 Cash Handling | Covers 1 matrix requirement(s). The system should allow the cashier to enter a total amount counted, or to count by denomination. For denomination counts, the cashier counts and enters each denomination separately and each count is … | E02 Sales Channels & Checkout |  | Highest | 3 | POS App | M2_Phase_3
Task | FEAT-046: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Cash Handling' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-046 Cash Handling | Highest | 1 | POS App | M2
Task | FEAT-046: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Cash Handling' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-046 Cash Handling | Highest | 1 | POS App | M2
Task | FEAT-046: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Cash Handling' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-046 Cash Handling | Highest | 1 | POS App | M2
Task | FEAT-046: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Cash Handling' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-046 Cash Handling | Highest | 1 | POS App | M2
Task | FEAT-046: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Cash Handling' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-046 Cash Handling | Highest | 1 | POS App | M2
Story | FEAT-047 Recommendation Engine | Covers 1 matrix requirement(s). System shall provide checkout recommendations. | E02 Sales Channels & Checkout |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-047: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Recommendation Engine' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-047 Recommendation Engine | Medium | 1 | Server Side / Backend | M4
Task | FEAT-047: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Recommendation Engine' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-047 Recommendation Engine | Medium | 2 | Server Side / Backend | M4
Task | FEAT-047: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Recommendation Engine' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-047 Recommendation Engine | Medium | 2 | Server Side / Backend | M4
Task | FEAT-047: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Recommendation Engine' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-047 Recommendation Engine | Medium | 1 | Server Side / Backend | M4
Task | FEAT-047: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Recommendation Engine' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-047 Recommendation Engine | Medium | 1 | Server Side / Backend | M4
Story | FEAT-048 Device Integrations | Covers 1 matrix requirement(s). Kiosk Integration - System shall support kiosk integration. | E02 Sales Channels & Checkout |  | Highest | 5 | POS App | M2_Phase_3
Task | FEAT-048: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Device Integrations' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-048 Device Integrations | Highest | 2 | POS App | M2
Task | FEAT-048: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Device Integrations' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-048 Device Integrations | Highest | 1 | POS App | M2
Task | FEAT-048: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Device Integrations' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-048 Device Integrations | Highest | 2 | POS App | M2
Task | FEAT-048: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Device Integrations' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-048 Device Integrations | Highest | 2 | POS App | M2
Task | FEAT-048: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Device Integrations' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-048 Device Integrations | Highest | 1 | POS App | M2
Story | FEAT-049 Notifications And Messaging | Covers 1 matrix requirement(s). Multi-Channel Delivery Notifications shall be delivered through email, SMS, WhatsApp, mobile push notifications, in-app messages, web notifications, kiosks, digital signage, and integrated third-party… | E02 Sales Channels & Checkout |  | Highest | 1 | POS App | M2_Phase_3
Task | FEAT-049: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Notifications And Messaging' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-049 Notifications And Messaging | Highest | 1 | POS App | M2
Task | FEAT-049: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Notifications And Messaging' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-049 Notifications And Messaging | Highest | 1 | POS App | M2
Task | FEAT-049: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Notifications And Messaging' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-049 Notifications And Messaging | Highest | 1 | POS App | M2
Task | FEAT-049: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Notifications And Messaging' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-049 Notifications And Messaging | Highest | 1 | POS App | M2
Task | FEAT-049: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Notifications And Messaging' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-049 Notifications And Messaging | Highest | 1 | POS App | M2
Story | FEAT-050 Audience Segmentation | Covers 1 matrix requirement(s). Cross-Channel Attribution System shall track guest interactions across website, mobile app, email, SMS, WhatsApp, social channels, call center, POS, kiosks, APIs, and B2B channels. | E02 Sales Channels & Checkout |  | Highest | 3 | Server Side / Backend | M2_Phase_3
Task | FEAT-050: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Audience Segmentation' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-050 Audience Segmentation | Highest | 1 | Server Side / Backend | M2
Task | FEAT-050: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Audience Segmentation' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-050 Audience Segmentation | Highest | 1 | Server Side / Backend | M2
Task | FEAT-050: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Audience Segmentation' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-050 Audience Segmentation | Highest | 1 | Server Side / Backend | M2
Task | FEAT-050: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Audience Segmentation' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-050 Audience Segmentation | Highest | 1 | Server Side / Backend | M2
Task | FEAT-050: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Audience Segmentation' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E02 Sales Channels & Checkout | FEAT-050 Audience Segmentation | Highest | 1 | Server Side / Backend | M2
Story | FEAT-051 Access Control System | Covers 114 matrix requirement(s). The Ticketing PLUs shall be printed on E-tickets Ticketing PLUs shall be printed on Wristbands (paper and RFID) | E03 Admission & Access Control |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-051: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Access Control System' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-051 Access Control System | Medium | 8 | Server Side / Backend | M4
Task | FEAT-051: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Access Control System' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-051 Access Control System | Medium | 13 | Server Side / Backend | M4
Task | FEAT-051: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Access Control System' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-051 Access Control System | Medium | 13 | Server Side / Backend | M4
Task | FEAT-051: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Access Control System' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-051 Access Control System | Medium | 8 | Server Side / Backend | M4
Task | FEAT-051: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Access Control System' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-051 Access Control System | Medium | 8 | Server Side / Backend | M4
Story | FEAT-052 Front Gate Sales | Covers 36 matrix requirement(s). The operator can register the payment. | E03 Admission & Access Control |  | Medium | 13 | POS App | M4_Phase_4
Task | FEAT-052: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Front Gate Sales' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-052 Front Gate Sales | Medium | 8 | POS App | M4
Task | FEAT-052: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Front Gate Sales' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-052 Front Gate Sales | Medium | 5 | POS App | M4
Task | FEAT-052: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Front Gate Sales' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-052 Front Gate Sales | Medium | 8 | POS App | M4
Task | FEAT-052: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Front Gate Sales' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-052 Front Gate Sales | Medium | 8 | POS App | M4
Task | FEAT-052: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Front Gate Sales' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-052 Front Gate Sales | Medium | 5 | POS App | M4
Story | FEAT-053 Demand Forecasting | Covers 19 matrix requirement(s). System shall forecast attendance based on historical attendance patterns. | E03 Admission & Access Control |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-053: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Demand Forecasting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-053 Demand Forecasting | Medium | 3 | Server Side / Backend | M4
Task | FEAT-053: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Demand Forecasting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-053 Demand Forecasting | Medium | 5 | Server Side / Backend | M4
Task | FEAT-053: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Demand Forecasting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-053 Demand Forecasting | Medium | 5 | Server Side / Backend | M4
Task | FEAT-053: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Demand Forecasting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-053 Demand Forecasting | Medium | 3 | Server Side / Backend | M4
Task | FEAT-053: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Demand Forecasting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-053 Demand Forecasting | Medium | 3 | Server Side / Backend | M4
Story | FEAT-054 Ticket Types | Covers 8 matrix requirement(s). The system should be able to sell multiple day tickets for attractions. The number of days should be configurable. This type of ticket should require a start date to be specified before first entry. | E03 Admission & Access Control |  | Highest | 5 | Server Side / Backend | M2_Phase_3
Task | FEAT-054: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ticket Types' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-054 Ticket Types | Highest | 1 | Server Side / Backend | M2
Task | FEAT-054: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ticket Types' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-054 Ticket Types | Highest | 2 | Server Side / Backend | M2
Task | FEAT-054: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ticket Types' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-054 Ticket Types | Highest | 2 | Server Side / Backend | M2
Task | FEAT-054: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ticket Types' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-054 Ticket Types | Highest | 1 | Server Side / Backend | M2
Task | FEAT-054: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ticket Types' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-054 Ticket Types | Highest | 1 | Server Side / Backend | M2
Story | FEAT-055 Accounting | Covers 6 matrix requirement(s). The system should support entry and maintenance of data in accounts related information tables. The primary usage of this data will be to derive accounts for billing records and interface with the Fin… | E03 Admission & Access Control |  | Highest | 5 | Server Side / Backend | M2_Phase_3
Task | FEAT-055: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Accounting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-055 Accounting | Highest | 1 | Server Side / Backend | M2
Task | FEAT-055: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Accounting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-055 Accounting | Highest | 1 | Server Side / Backend | M2
Task | FEAT-055: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Accounting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-055 Accounting | Highest | 2 | Server Side / Backend | M2
Task | FEAT-055: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Accounting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-055 Accounting | Highest | 1 | Server Side / Backend | M2
Task | FEAT-055: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Accounting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-055 Accounting | Highest | 1 | Server Side / Backend | M2
Story | FEAT-056 Order Management | Covers 5 matrix requirement(s). The system should have the ability for order entry: - Select an item to place on an order. - Indicate quantity of item selected - Apply a name to an order (e.g. Smith Party). Each admission on the ord… | E03 Admission & Access Control |  | Highest | 5 | Server Side / Backend | M2_Phase_3
Task | FEAT-056: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Order Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-056 Order Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-056: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Order Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-056 Order Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-056: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Order Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-056 Order Management | Highest | 2 | Server Side / Backend | M2
Task | FEAT-056: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Order Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-056 Order Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-056: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Order Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-056 Order Management | Highest | 1 | Server Side / Backend | M2
Story | FEAT-057 Double-Entry Financial Ledger | Covers 5 matrix requirement(s). Provides accounting-grade financial recording of all platform transactions. | E03 Admission & Access Control |  | Highest | 5 | Server Side / Backend | M2_Phase_3
Task | FEAT-057: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Double-Entry Financial Ledger' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-057 Double-Entry Financial Ledger | Highest | 1 | Server Side / Backend | M2
Task | FEAT-057: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Double-Entry Financial Ledger' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-057 Double-Entry Financial Ledger | Highest | 1 | Server Side / Backend | M2
Task | FEAT-057: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Double-Entry Financial Ledger' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-057 Double-Entry Financial Ledger | Highest | 2 | Server Side / Backend | M2
Task | FEAT-057: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Double-Entry Financial Ledger' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-057 Double-Entry Financial Ledger | Highest | 1 | Server Side / Backend | M2
Task | FEAT-057: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Double-Entry Financial Ledger' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-057 Double-Entry Financial Ledger | Highest | 1 | Server Side / Backend | M2
Story | FEAT-058 Device Integrations | Covers 5 matrix requirement(s). Handheld Scanner Integration - System shall support handheld scanner integration. | E03 Admission & Access Control |  | Highest | 8 | POS App | M2_Phase_3
Task | FEAT-058: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Device Integrations' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-058 Device Integrations | Highest | 2 | POS App | M2
Task | FEAT-058: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Device Integrations' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-058 Device Integrations | Highest | 2 | POS App | M2
Task | FEAT-058: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Device Integrations' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-058 Device Integrations | Highest | 2 | POS App | M2
Task | FEAT-058: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Device Integrations' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-058 Device Integrations | Highest | 2 | POS App | M2
Task | FEAT-058: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Device Integrations' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-058 Device Integrations | Highest | 2 | POS App | M2
Story | FEAT-059 Asset Scanning And Lookup | Covers 5 matrix requirement(s). QR Asset Scanning - Users shall scan asset QR codes. | E03 Admission & Access Control |  | Highest | 5 | POS App | M2_Phase_3
Task | FEAT-059: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Asset Scanning And Lookup' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-059 Asset Scanning And Lookup | Highest | 1 | POS App | M2
Task | FEAT-059: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Asset Scanning And Lookup' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-059 Asset Scanning And Lookup | Highest | 1 | POS App | M2
Task | FEAT-059: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Asset Scanning And Lookup' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-059 Asset Scanning And Lookup | Highest | 1 | POS App | M2
Task | FEAT-059: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Asset Scanning And Lookup' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-059 Asset Scanning And Lookup | Highest | 1 | POS App | M2
Task | FEAT-059: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Asset Scanning And Lookup' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-059 Asset Scanning And Lookup | Highest | 1 | POS App | M2
Story | FEAT-060 Attendance And Communications | Covers 5 matrix requirement(s). Attendance Management - Users shall clock in and clock out. | E03 Admission & Access Control |  | Highest | 5 | Mobile App | M2_Phase_3
Task | FEAT-060: UI screens (iOS & Android) | Implement shared + platform UI components. Acceptance: 'Attendance And Communications' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-060 Attendance And Communications | Highest | 2 | Mobile App | M2
Task | FEAT-060: State & API integration | Data layer, caching and API wiring. Acceptance: 'Attendance And Communications' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-060 Attendance And Communications | Highest | 2 | Mobile App | M2
Task | FEAT-060: Offline & push handling | Offline storage, sync and push notifications. Acceptance: 'Attendance And Communications' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-060 Attendance And Communications | Highest | 1 | Mobile App | M2
Task | FEAT-060: Mobile E2E tests | Automated tests across iOS/Android. Acceptance: 'Attendance And Communications' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-060 Attendance And Communications | Highest | 1 | Mobile App | M2
Story | FEAT-061 Call Center Sales | Covers 4 matrix requirement(s). Post-order service 1) On the order details page, users can view the order number, amount, time, payment method, user information, refund/change policies, and the QR code of the e-ticket 2) During the … | E03 Admission & Access Control |  | Highest | 5 | Server Side / Backend | M2_Phase_3
Task | FEAT-061: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Call Center Sales' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-061 Call Center Sales | Highest | 1 | Server Side / Backend | M2
Task | FEAT-061: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Call Center Sales' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-061 Call Center Sales | Highest | 1 | Server Side / Backend | M2
Task | FEAT-061: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Call Center Sales' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-061 Call Center Sales | Highest | 2 | Server Side / Backend | M2
Task | FEAT-061: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Call Center Sales' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-061 Call Center Sales | Highest | 1 | Server Side / Backend | M2
Task | FEAT-061: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Call Center Sales' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-061 Call Center Sales | Highest | 1 | Server Side / Backend | M2
Story | FEAT-062 Ticket Media | Covers 4 matrix requirement(s). Unique Code per Ticket: Generate a unique QR code for every issued ticket or pass. | E03 Admission & Access Control |  | Highest | 8 | Server Side / Backend | M2_Phase_3
Task | FEAT-062: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ticket Media' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-062 Ticket Media | Highest | 1 | Server Side / Backend | M2
Task | FEAT-062: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ticket Media' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-062 Ticket Media | Highest | 2 | Server Side / Backend | M2
Task | FEAT-062: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ticket Media' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-062 Ticket Media | Highest | 3 | Server Side / Backend | M2
Task | FEAT-062: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ticket Media' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-062 Ticket Media | Highest | 1 | Server Side / Backend | M2
Task | FEAT-062: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ticket Media' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-062 Ticket Media | Highest | 1 | Server Side / Backend | M2
Story | FEAT-063 Resource Management | Covers 3 matrix requirement(s). The system should allow management of the schedules of the staff resources with the possibility to set the parameters such as total hours, breaks, leave plan, absences. This data can be captured via m… | E03 Admission & Access Control |  | Highest | 8 | Server Side / Backend | M2_Phase_3
Task | FEAT-063: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Resource Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-063 Resource Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-063: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Resource Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-063 Resource Management | Highest | 2 | Server Side / Backend | M2
Task | FEAT-063: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Resource Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-063 Resource Management | Highest | 2 | Server Side / Backend | M2
Task | FEAT-063: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Resource Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-063 Resource Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-063: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Resource Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-063 Resource Management | Highest | 1 | Server Side / Backend | M2
Story | FEAT-064 Virtual Queue | Covers 3 matrix requirement(s). VIP / Priority Handling: Separate or fast-track queues for premium guests. Virtual Ticketing: QR code / app-based entry into queues. | E03 Admission & Access Control |  | Highest | 8 | Server Side / Backend | M2_Phase_3
Task | FEAT-064: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Virtual Queue' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-064 Virtual Queue | Highest | 1 | Server Side / Backend | M2
Task | FEAT-064: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Virtual Queue' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-064 Virtual Queue | Highest | 2 | Server Side / Backend | M2
Task | FEAT-064: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Virtual Queue' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-064 Virtual Queue | Highest | 2 | Server Side / Backend | M2
Task | FEAT-064: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Virtual Queue' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-064 Virtual Queue | Highest | 1 | Server Side / Backend | M2
Task | FEAT-064: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Virtual Queue' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-064 Virtual Queue | Highest | 1 | Server Side / Backend | M2
Story | FEAT-065 Operations Command Center | Covers 3 matrix requirement(s). System shall display current attendance, occupancy levels, capacity utilization, and crowd distribution across parks, venues, facilities, and attractions. | E03 Admission & Access Control |  | Highest | 2 | Server Side / Backend | M2_Phase_3
Task | FEAT-065: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Operations Command Center' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-065 Operations Command Center | Highest | 1 | Server Side / Backend | M2
Task | FEAT-065: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Operations Command Center' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-065 Operations Command Center | Highest | 1 | Server Side / Backend | M2
Task | FEAT-065: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Operations Command Center' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-065 Operations Command Center | Highest | 1 | Server Side / Backend | M2
Task | FEAT-065: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Operations Command Center' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-065 Operations Command Center | Highest | 1 | Server Side / Backend | M2
Task | FEAT-065: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Operations Command Center' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-065 Operations Command Center | Highest | 1 | Server Side / Backend | M2
Story | FEAT-066 Sales Channels | Covers 2 matrix requirement(s). The system should allow the user to filter the ticket by all types and available properties. For example, dated/non-dated, single-entry/multiple-entry, adult/child, standard/VIP, attraction selection,… | E03 Admission & Access Control |  | Highest | 2 | Server Side / Backend | M2_Phase_3
Task | FEAT-066: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Sales Channels' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-066 Sales Channels | Highest | 1 | Server Side / Backend | M2
Task | FEAT-066: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Sales Channels' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-066 Sales Channels | Highest | 1 | Server Side / Backend | M2
Task | FEAT-066: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Sales Channels' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-066 Sales Channels | Highest | 1 | Server Side / Backend | M2
Task | FEAT-066: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Sales Channels' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-066 Sales Channels | Highest | 1 | Server Side / Backend | M2
Task | FEAT-066: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Sales Channels' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-066 Sales Channels | Highest | 1 | Server Side / Backend | M2
Story | FEAT-067 Parking Integration | Covers 2 matrix requirement(s). The payment can be done upfront or at exit. | E03 Admission & Access Control |  | Highest | 3 | Server Side / Backend | M2_Phase_3
Task | FEAT-067: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Parking Integration' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-067 Parking Integration | Highest | 1 | Server Side / Backend | M2
Task | FEAT-067: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Parking Integration' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-067 Parking Integration | Highest | 1 | Server Side / Backend | M2
Task | FEAT-067: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Parking Integration' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-067 Parking Integration | Highest | 1 | Server Side / Backend | M2
Task | FEAT-067: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Parking Integration' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-067 Parking Integration | Highest | 1 | Server Side / Backend | M2
Task | FEAT-067: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Parking Integration' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-067 Parking Integration | Highest | 1 | Server Side / Backend | M2
Story | FEAT-068 Profile Management | Covers 2 matrix requirement(s). The system should validate the data captured for a guest profile. Validation should include but not limited to: - Phone number is only numbers. - Name is only alphabets. | E03 Admission & Access Control |  | Highest | 3 | Server Side / Backend | M2_Phase_3
Task | FEAT-068: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Profile Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-068 Profile Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-068: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Profile Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-068 Profile Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-068: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Profile Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-068 Profile Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-068: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Profile Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-068 Profile Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-068: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Profile Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-068 Profile Management | Highest | 1 | Server Side / Backend | M2
Story | FEAT-069 Loyalty | Covers 2 matrix requirement(s). The system should support loyalty point redemption in place for the guests to redeem their earned point for either products or services under venue offerings. B2C website should support: 1. Points acq… | E03 Admission & Access Control |  | Highest | 2 | Server Side / Backend | M2_Phase_3
Task | FEAT-069: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Loyalty' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-069 Loyalty | Highest | 1 | Server Side / Backend | M2
Task | FEAT-069: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Loyalty' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-069 Loyalty | Highest | 1 | Server Side / Backend | M2
Task | FEAT-069: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Loyalty' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-069 Loyalty | Highest | 1 | Server Side / Backend | M2
Task | FEAT-069: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Loyalty' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-069 Loyalty | Highest | 1 | Server Side / Backend | M2
Task | FEAT-069: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Loyalty' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-069 Loyalty | Highest | 1 | Server Side / Backend | M2
Story | FEAT-070 Bi And Reporting | Covers 2 matrix requirement(s). System shall provide access control dashboards. | E03 Admission & Access Control |  | Highest | 5 | Server Side / Backend | M2_Phase_3
Task | FEAT-070: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Bi And Reporting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-070 Bi And Reporting | Highest | 1 | Server Side / Backend | M2
Task | FEAT-070: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Bi And Reporting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-070 Bi And Reporting | Highest | 2 | Server Side / Backend | M2
Task | FEAT-070: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Bi And Reporting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-070 Bi And Reporting | Highest | 2 | Server Side / Backend | M2
Task | FEAT-070: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Bi And Reporting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-070 Bi And Reporting | Highest | 1 | Server Side / Backend | M2
Task | FEAT-070: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Bi And Reporting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-070 Bi And Reporting | Highest | 1 | Server Side / Backend | M2
Story | FEAT-071 Game And Ride Payment And Redemption | Covers 2 matrix requirement(s). Gameplay validation Prices to be defined for each game Assign prices for the Group. Game Reader - Access to the particular game - Bonus deduction should be done first Package - To create a package wit… | E03 Admission & Access Control |  | Highest | 3 | Server Side / Backend | M2_Phase_3
Task | FEAT-071: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Game And Ride Payment And Redemption' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-071 Game And Ride Payment And Redemption | Highest | 1 | Server Side / Backend | M2
Task | FEAT-071: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Game And Ride Payment And Redemption' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-071 Game And Ride Payment And Redemption | Highest | 1 | Server Side / Backend | M2
Task | FEAT-071: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Game And Ride Payment And Redemption' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-071 Game And Ride Payment And Redemption | Highest | 1 | Server Side / Backend | M2
Task | FEAT-071: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Game And Ride Payment And Redemption' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-071 Game And Ride Payment And Redemption | Highest | 1 | Server Side / Backend | M2
Task | FEAT-071: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Game And Ride Payment And Redemption' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-071 Game And Ride Payment And Redemption | Highest | 1 | Server Side / Backend | M2
Story | FEAT-072 Gamification And Loyalty | Covers 2 matrix requirement(s). Achievement Engine System shall automatically award achievements when guests complete predefined milestones, goals, challenges, loyalty activities, purchases, or attendance requirements. | E03 Admission & Access Control |  | Highest | 3 | Server Side / Backend | M2_Phase_3
Task | FEAT-072: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Gamification And Loyalty' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-072 Gamification And Loyalty | Highest | 1 | Server Side / Backend | M2
Task | FEAT-072: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Gamification And Loyalty' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-072 Gamification And Loyalty | Highest | 1 | Server Side / Backend | M2
Task | FEAT-072: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Gamification And Loyalty' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-072 Gamification And Loyalty | Highest | 1 | Server Side / Backend | M2
Task | FEAT-072: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Gamification And Loyalty' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-072 Gamification And Loyalty | Highest | 1 | Server Side / Backend | M2
Task | FEAT-072: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Gamification And Loyalty' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-072 Gamification And Loyalty | Highest | 1 | Server Side / Backend | M2
Story | FEAT-073 Omnichannel Communications And Ai Chatbot | Covers 2 matrix requirement(s). Loyalty Integration Guests shall be able to view loyalty balances, redeem rewards, track achievements, review tier status, and receive loyalty recommendations through chat. | E03 Admission & Access Control |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-073: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Omnichannel Communications And Ai Chatbot' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-073 Omnichannel Communications And Ai Chatbot | Medium | 1 | Server Side / Backend | M4
Task | FEAT-073: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Omnichannel Communications And Ai Chatbot' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-073 Omnichannel Communications And Ai Chatbot | Medium | 2 | Server Side / Backend | M4
Task | FEAT-073: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Omnichannel Communications And Ai Chatbot' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-073 Omnichannel Communications And Ai Chatbot | Medium | 2 | Server Side / Backend | M4
Task | FEAT-073: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Omnichannel Communications And Ai Chatbot' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-073 Omnichannel Communications And Ai Chatbot | Medium | 1 | Server Side / Backend | M4
Task | FEAT-073: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Omnichannel Communications And Ai Chatbot' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-073 Omnichannel Communications And Ai Chatbot | Medium | 1 | Server Side / Backend | M4
Story | FEAT-074 Notifications And Messaging | Covers 2 matrix requirement(s). Ticketing Notifications System shall automatically send booking confirmations, tickets, reminders, seat assignments, changes, cancellations, upgrades, transfers, and attendance notifications. | E03 Admission & Access Control |  | Highest | 2 | Server Side / Backend | M2_Phase_3
Task | FEAT-074: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Notifications And Messaging' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-074 Notifications And Messaging | Highest | 1 | Server Side / Backend | M2
Task | FEAT-074: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Notifications And Messaging' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-074 Notifications And Messaging | Highest | 1 | Server Side / Backend | M2
Task | FEAT-074: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Notifications And Messaging' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-074 Notifications And Messaging | Highest | 1 | Server Side / Backend | M2
Task | FEAT-074: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Notifications And Messaging' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-074 Notifications And Messaging | Highest | 1 | Server Side / Backend | M2
Task | FEAT-074: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Notifications And Messaging' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-074 Notifications And Messaging | Highest | 1 | Server Side / Backend | M2
Story | FEAT-075 Product Lifecycle | Covers 1 matrix requirement(s). The system should propagate any changes made to the properties of a product to the already sold tickets as well. | E03 Admission & Access Control |  | Highest | 3 | POS App | M2_Phase_3
Task | FEAT-075: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Product Lifecycle' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-075 Product Lifecycle | Highest | 1 | POS App | M2
Task | FEAT-075: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Product Lifecycle' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-075 Product Lifecycle | Highest | 1 | POS App | M2
Task | FEAT-075: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Product Lifecycle' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-075 Product Lifecycle | Highest | 1 | POS App | M2
Task | FEAT-075: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Product Lifecycle' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-075 Product Lifecycle | Highest | 1 | POS App | M2
Task | FEAT-075: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Product Lifecycle' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-075 Product Lifecycle | Highest | 1 | POS App | M2
Story | FEAT-076 Ticket Upgrades | Covers 1 matrix requirement(s). The system should allow upgrade of all type of Tickets (Not redeemed, partially redeemed, fully redeemed or expired). Tickets can be upgraded to a longer duration ticket or a greater access ticket (e.… | E03 Admission & Access Control |  | Highest | 3 | Server Side / Backend | M2_Phase_3
Task | FEAT-076: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ticket Upgrades' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-076 Ticket Upgrades | Highest | 1 | Server Side / Backend | M2
Task | FEAT-076: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ticket Upgrades' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-076 Ticket Upgrades | Highest | 1 | Server Side / Backend | M2
Task | FEAT-076: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ticket Upgrades' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-076 Ticket Upgrades | Highest | 1 | Server Side / Backend | M2
Task | FEAT-076: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ticket Upgrades' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-076 Ticket Upgrades | Highest | 1 | Server Side / Backend | M2
Task | FEAT-076: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ticket Upgrades' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-076 Ticket Upgrades | Highest | 1 | Server Side / Backend | M2
Story | FEAT-077 Portfolio Management | Covers 1 matrix requirement(s). The system should be able to print media which are linked to guest's portfolios, this way multiple media can be availed/printed to the same guest portfolio. (examples: lost/soiled ticket reprints, web… | E03 Admission & Access Control |  | Highest | 3 | Server Side / Backend | M2_Phase_3
Task | FEAT-077: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Portfolio Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-077 Portfolio Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-077: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Portfolio Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-077 Portfolio Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-077: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Portfolio Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-077 Portfolio Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-077: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Portfolio Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-077 Portfolio Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-077: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Portfolio Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-077 Portfolio Management | Highest | 1 | Server Side / Backend | M2
Story | FEAT-078 Portfolio And Entitlement Management | Covers 1 matrix requirement(s). Support issuance and management of QR codes, RFID wristbands, RFID cards, NFC passes, digital tickets, and printed tickets linked to portfolios. | E03 Admission & Access Control |  | Highest | 3 | Server Side / Backend | M2_Phase_3
Task | FEAT-078: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Portfolio And Entitlement Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-078 Portfolio And Entitlement Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-078: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Portfolio And Entitlement Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-078 Portfolio And Entitlement Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-078: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Portfolio And Entitlement Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-078 Portfolio And Entitlement Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-078: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Portfolio And Entitlement Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-078 Portfolio And Entitlement Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-078: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Portfolio And Entitlement Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-078 Portfolio And Entitlement Management | Highest | 1 | Server Side / Backend | M2
Story | FEAT-079 Fraud Detection | Covers 1 matrix requirement(s). System shall detect duplicate ticket scans. | E03 Admission & Access Control |  | Highest | 3 | POS App | M2_Phase_3
Task | FEAT-079: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Fraud Detection' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-079 Fraud Detection | Highest | 1 | POS App | M2
Task | FEAT-079: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Fraud Detection' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-079 Fraud Detection | Highest | 1 | POS App | M2
Task | FEAT-079: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Fraud Detection' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-079 Fraud Detection | Highest | 1 | POS App | M2
Task | FEAT-079: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Fraud Detection' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-079 Fraud Detection | Highest | 1 | POS App | M2
Task | FEAT-079: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Fraud Detection' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-079 Fraud Detection | Highest | 1 | POS App | M2
Story | FEAT-080 Recommendation Engine | Covers 1 matrix requirement(s). System shall provide recommendations based on attendance history. | E03 Admission & Access Control |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-080: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Recommendation Engine' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-080 Recommendation Engine | Medium | 1 | Server Side / Backend | M4
Task | FEAT-080: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Recommendation Engine' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-080 Recommendation Engine | Medium | 2 | Server Side / Backend | M4
Task | FEAT-080: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Recommendation Engine' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-080 Recommendation Engine | Medium | 2 | Server Side / Backend | M4
Task | FEAT-080: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Recommendation Engine' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-080 Recommendation Engine | Medium | 1 | Server Side / Backend | M4
Task | FEAT-080: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Recommendation Engine' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-080 Recommendation Engine | Medium | 1 | Server Side / Backend | M4
Story | FEAT-081 Reporting And Dashboards | Covers 1 matrix requirement(s). Credential Generation System shall generate accreditation IDs, QR codes, NFC cards or digital credentials. | E03 Admission & Access Control |  | Highest | 3 | Server Side / Backend | M2_Phase_3
Task | FEAT-081: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Reporting And Dashboards' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-081 Reporting And Dashboards | Highest | 1 | Server Side / Backend | M2
Task | FEAT-081: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Reporting And Dashboards' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-081 Reporting And Dashboards | Highest | 1 | Server Side / Backend | M2
Task | FEAT-081: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Reporting And Dashboards' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-081 Reporting And Dashboards | Highest | 1 | Server Side / Backend | M2
Task | FEAT-081: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Reporting And Dashboards' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-081 Reporting And Dashboards | Highest | 1 | Server Side / Backend | M2
Task | FEAT-081: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Reporting And Dashboards' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-081 Reporting And Dashboards | Highest | 1 | Server Side / Backend | M2
Story | FEAT-082 Sandbox | Covers 1 matrix requirement(s). Sandbox Access Control - System shall support role-based sandbox access. | E03 Admission & Access Control |  | Highest | 3 | Server Side / Backend | M2_Phase_3
Task | FEAT-082: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Sandbox' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-082 Sandbox | Highest | 1 | Server Side / Backend | M2
Task | FEAT-082: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Sandbox' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-082 Sandbox | Highest | 1 | Server Side / Backend | M2
Task | FEAT-082: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Sandbox' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-082 Sandbox | Highest | 1 | Server Side / Backend | M2
Task | FEAT-082: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Sandbox' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-082 Sandbox | Highest | 1 | Server Side / Backend | M2
Task | FEAT-082: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Sandbox' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-082 Sandbox | Highest | 1 | Server Side / Backend | M2
Story | FEAT-083 Asset Management | Covers 1 matrix requirement(s). Asset QR Code Management - System shall generate and manage asset QR codes. | E03 Admission & Access Control |  | Highest | 3 | Server Side / Backend | M2_Phase_3
Task | FEAT-083: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Asset Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-083 Asset Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-083: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Asset Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-083 Asset Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-083: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Asset Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-083 Asset Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-083: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Asset Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-083 Asset Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-083: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Asset Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-083 Asset Management | Highest | 1 | Server Side / Backend | M2
Story | FEAT-084 Licensing Models | Covers 1 matrix requirement(s). Attendance-Based Licensing - System shall support licensing based on attendance volumes. | E03 Admission & Access Control |  | Highest | 3 | Server Side / Backend | M2_Phase_3
Task | FEAT-084: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Licensing Models' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-084 Licensing Models | Highest | 1 | Server Side / Backend | M2
Task | FEAT-084: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Licensing Models' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-084 Licensing Models | Highest | 1 | Server Side / Backend | M2
Task | FEAT-084: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Licensing Models' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-084 Licensing Models | Highest | 1 | Server Side / Backend | M2
Task | FEAT-084: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Licensing Models' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-084 Licensing Models | Highest | 1 | Server Side / Backend | M2
Task | FEAT-084: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Licensing Models' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-084 Licensing Models | Highest | 1 | Server Side / Backend | M2
Story | FEAT-085 Usage And Quota Monitoring | Covers 1 matrix requirement(s). Attendance Usage Monitoring - System shall monitor attendance volumes. | E03 Admission & Access Control |  | Highest | 3 | Cross Platform | M2_Phase_3
Task | FEAT-085: Design & technical spec | Architecture, interfaces and acceptance criteria. Acceptance: 'Usage And Quota Monitoring' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-085 Usage And Quota Monitoring | Highest | 1 | Cross Platform | M2
Task | FEAT-085: Implementation | Build the capability / automation. Acceptance: 'Usage And Quota Monitoring' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-085 Usage And Quota Monitoring | Highest | 1 | Cross Platform | M2
Task | FEAT-085: Automation & CI integration | Pipeline, IaC and gates. Acceptance: 'Usage And Quota Monitoring' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-085 Usage And Quota Monitoring | Highest | 1 | Cross Platform | M2
Task | FEAT-085: Verification & sign-off | Validate against NFR/acceptance criteria. Acceptance: 'Usage And Quota Monitoring' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-085 Usage And Quota Monitoring | Highest | 1 | Cross Platform | M2
Story | FEAT-086 Guest Profiles And Data Management | Covers 1 matrix requirement(s). Loyalty History Guest profiles shall display loyalty points earned, redeemed, adjusted, expired, rewards claimed, tier progression, and loyalty transactions. | E03 Admission & Access Control |  | Highest | 1 | Server Side / Backend | M2_Phase_3
Task | FEAT-086: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Guest Profiles And Data Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-086 Guest Profiles And Data Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-086: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Guest Profiles And Data Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-086 Guest Profiles And Data Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-086: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Guest Profiles And Data Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-086 Guest Profiles And Data Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-086: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Guest Profiles And Data Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-086 Guest Profiles And Data Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-086: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Guest Profiles And Data Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-086 Guest Profiles And Data Management | Highest | 1 | Server Side / Backend | M2
Story | FEAT-087 Reviews And Ratings | Covers 1 matrix requirement(s). Multi-Channel Review Capture Reviews may be collected through email, SMS, WhatsApp, mobile application, website, kiosks, surveys, QR codes, and third-party review platforms. | E03 Admission & Access Control |  | Highest | 1 | Server Side / Backend | M2_Phase_3
Task | FEAT-087: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Reviews And Ratings' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-087 Reviews And Ratings | Highest | 1 | Server Side / Backend | M2
Task | FEAT-087: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Reviews And Ratings' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-087 Reviews And Ratings | Highest | 1 | Server Side / Backend | M2
Task | FEAT-087: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Reviews And Ratings' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-087 Reviews And Ratings | Highest | 1 | Server Side / Backend | M2
Task | FEAT-087: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Reviews And Ratings' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-087 Reviews And Ratings | Highest | 1 | Server Side / Backend | M2
Task | FEAT-087: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Reviews And Ratings' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-087 Reviews And Ratings | Highest | 1 | Server Side / Backend | M2
Story | FEAT-088 Surveys And Feedback | Covers 1 matrix requirement(s). Multi-Channel Distribution Surveys shall be distributed through email, SMS, WhatsApp, push notifications, mobile applications, websites, kiosks, QR codes, and third-party communication channels. | E03 Admission & Access Control |  | Highest | 1 | Server Side / Backend | M2_Phase_3
Task | FEAT-088: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Surveys And Feedback' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-088 Surveys And Feedback | Highest | 1 | Server Side / Backend | M2
Task | FEAT-088: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Surveys And Feedback' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-088 Surveys And Feedback | Highest | 1 | Server Side / Backend | M2
Task | FEAT-088: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Surveys And Feedback' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-088 Surveys And Feedback | Highest | 1 | Server Side / Backend | M2
Task | FEAT-088: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Surveys And Feedback' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-088 Surveys And Feedback | Highest | 1 | Server Side / Backend | M2
Task | FEAT-088: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Surveys And Feedback' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-088 Surveys And Feedback | Highest | 1 | Server Side / Backend | M2
Story | FEAT-089 Marketing | Covers 1 matrix requirement(s). Accessibility Compliance CMS shall support accessibility standards including WCAG compliance, screen readers, keyboard navigation, alternative text, and accessibility validation. | E03 Admission & Access Control |  | Highest | 3 | Server Side / Backend | M2_Phase_3
Task | FEAT-089: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Marketing' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-089 Marketing | Highest | 1 | Server Side / Backend | M2
Task | FEAT-089: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Marketing' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-089 Marketing | Highest | 1 | Server Side / Backend | M2
Task | FEAT-089: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Marketing' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-089 Marketing | Highest | 1 | Server Side / Backend | M2
Task | FEAT-089: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Marketing' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-089 Marketing | Highest | 1 | Server Side / Backend | M2
Task | FEAT-089: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Marketing' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-089 Marketing | Highest | 1 | Server Side / Backend | M2
Story | FEAT-090 Digital Waivers And Signature Management | Covers 1 matrix requirement(s). Access Control Integration Access Control shall automatically deny or restrict entry to activities requiring valid waivers if a signed waiver is not available. | E03 Admission & Access Control |  | Highest | 5 | Server Side / Backend | M2_Phase_3
Task | FEAT-090: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Digital Waivers And Signature Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-090 Digital Waivers And Signature Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-090: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Digital Waivers And Signature Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-090 Digital Waivers And Signature Management | Highest | 2 | Server Side / Backend | M2
Task | FEAT-090: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Digital Waivers And Signature Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-090 Digital Waivers And Signature Management | Highest | 2 | Server Side / Backend | M2
Task | FEAT-090: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Digital Waivers And Signature Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-090 Digital Waivers And Signature Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-090: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Digital Waivers And Signature Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E03 Admission & Access Control | FEAT-090 Digital Waivers And Signature Management | Highest | 1 | Server Side / Backend | M2
Story | FEAT-091 Revenue Recognition | Covers 120 matrix requirement(s). Supports recognition of revenue according to accounting policies rather than immediately upon sale. | E04 Payments, Wallet & Financial |  | Highest | 13 | Server Side / Backend | M2_Phase_3
Task | FEAT-091: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Revenue Recognition' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-091 Revenue Recognition | Highest | 8 | Server Side / Backend | M2
Task | FEAT-091: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Revenue Recognition' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-091 Revenue Recognition | Highest | 13 | Server Side / Backend | M2
Task | FEAT-091: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Revenue Recognition' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-091 Revenue Recognition | Highest | 13 | Server Side / Backend | M2
Task | FEAT-091: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Revenue Recognition' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-091 Revenue Recognition | Highest | 8 | Server Side / Backend | M2
Task | FEAT-091: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Revenue Recognition' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-091 Revenue Recognition | Highest | 8 | Server Side / Backend | M2
Story | FEAT-092 Wallet | Covers 57 matrix requirement(s). The system should be EMV (Euro pay, MasterCard and Visa) certified for offline and online payments. | E04 Payments, Wallet & Financial |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-092: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Wallet' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-092 Wallet | Medium | 8 | Server Side / Backend | M4
Task | FEAT-092: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Wallet' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-092 Wallet | Medium | 13 | Server Side / Backend | M4
Task | FEAT-092: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Wallet' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-092 Wallet | Medium | 13 | Server Side / Backend | M4
Task | FEAT-092: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Wallet' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-092 Wallet | Medium | 8 | Server Side / Backend | M4
Task | FEAT-092: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Wallet' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-092 Wallet | Medium | 8 | Server Side / Backend | M4
Story | FEAT-093 Accounting | Covers 33 matrix requirement(s). The system should be able to store account information for each Offset/Balancing Account by Payment Type (e.g. cash, bank card, tax, etc.). At minimum, the below fields should be included for storage:… | E04 Payments, Wallet & Financial |  | Highest | 13 | Server Side / Backend | M2_Phase_3
Task | FEAT-093: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Accounting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-093 Accounting | Highest | 5 | Server Side / Backend | M2
Task | FEAT-093: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Accounting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-093 Accounting | Highest | 8 | Server Side / Backend | M2
Task | FEAT-093: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Accounting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-093 Accounting | Highest | 8 | Server Side / Backend | M2
Task | FEAT-093: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Accounting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-093 Accounting | Highest | 5 | Server Side / Backend | M2
Task | FEAT-093: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Accounting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-093 Accounting | Highest | 5 | Server Side / Backend | M2
Story | FEAT-094 Pricing | Covers 21 matrix requirement(s). 1.B2B Management backend should support: 1) Ability to create new B2B company master accounts, including setting the account name, password, and company information 2) Ability to group B2B company acc… | E04 Payments, Wallet & Financial |  | Highest | 13 | Server Side / Backend | M2_Phase_3
Task | FEAT-094: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Pricing' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-094 Pricing | Highest | 3 | Server Side / Backend | M2
Task | FEAT-094: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Pricing' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-094 Pricing | Highest | 5 | Server Side / Backend | M2
Task | FEAT-094: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Pricing' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-094 Pricing | Highest | 8 | Server Side / Backend | M2
Task | FEAT-094: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Pricing' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-094 Pricing | Highest | 3 | Server Side / Backend | M2
Task | FEAT-094: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Pricing' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-094 Pricing | Highest | 3 | Server Side / Backend | M2
Story | FEAT-095 Order Management | Covers 18 matrix requirement(s). The system should allow for order adjustments. Following adjustments should be supported: - Users to refund guests (with supervisor approval) - Users to manually adjust guest orders (date, time, numbe… | E04 Payments, Wallet & Financial |  | Highest | 13 | Server Side / Backend | M2_Phase_3
Task | FEAT-095: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Order Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-095 Order Management | Highest | 3 | Server Side / Backend | M2
Task | FEAT-095: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Order Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-095 Order Management | Highest | 5 | Server Side / Backend | M2
Task | FEAT-095: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Order Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-095 Order Management | Highest | 5 | Server Side / Backend | M2
Task | FEAT-095: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Order Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-095 Order Management | Highest | 3 | Server Side / Backend | M2
Task | FEAT-095: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Order Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-095 Order Management | Highest | 3 | Server Side / Backend | M2
Story | FEAT-096 Authentication And Login | Covers 16 matrix requirement(s). Digital Wallet - System shall provide a digital wallet. | E04 Payments, Wallet & Financial |  | Highest | 8 | Mobile App | M2_Phase_3
Task | FEAT-096: UI screens (iOS & Android) | Implement shared + platform UI components. Acceptance: 'Authentication And Login' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-096 Authentication And Login | Highest | 3 | Mobile App | M2
Task | FEAT-096: State & API integration | Data layer, caching and API wiring. Acceptance: 'Authentication And Login' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-096 Authentication And Login | Highest | 3 | Mobile App | M2
Task | FEAT-096: Offline & push handling | Offline storage, sync and push notifications. Acceptance: 'Authentication And Login' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-096 Authentication And Login | Highest | 2 | Mobile App | M2
Task | FEAT-096: Mobile E2E tests | Automated tests across iOS/Android. Acceptance: 'Authentication And Login' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-096 Authentication And Login | Highest | 2 | Mobile App | M2
Story | FEAT-097 Promotions | Covers 15 matrix requirement(s). The system should be able to refund transactions that contain promotions and ensure discounted amount is not refunded | E04 Payments, Wallet & Financial |  | Highest | 13 | Server Side / Backend | M2_Phase_3
Task | FEAT-097: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Promotions' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-097 Promotions | Highest | 3 | Server Side / Backend | M2
Task | FEAT-097: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Promotions' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-097 Promotions | Highest | 5 | Server Side / Backend | M2
Task | FEAT-097: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Promotions' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-097 Promotions | Highest | 5 | Server Side / Backend | M2
Task | FEAT-097: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Promotions' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-097 Promotions | Highest | 3 | Server Side / Backend | M2
Task | FEAT-097: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Promotions' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-097 Promotions | Highest | 3 | Server Side / Backend | M2
Story | FEAT-098 Ticket Types | Covers 14 matrix requirement(s). The system should allow the capacity for all type of ticket to be configurable. Capacity of a ticket can be configurable at multiple levels: 1) Sales Capacity: Allow only a fixed number of tickets to … | E04 Payments, Wallet & Financial |  | Highest | 13 | Server Side / Backend | M2_Phase_3
Task | FEAT-098: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ticket Types' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-098 Ticket Types | Highest | 3 | Server Side / Backend | M2
Task | FEAT-098: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ticket Types' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-098 Ticket Types | Highest | 3 | Server Side / Backend | M2
Task | FEAT-098: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ticket Types' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-098 Ticket Types | Highest | 5 | Server Side / Backend | M2
Task | FEAT-098: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ticket Types' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-098 Ticket Types | Highest | 3 | Server Side / Backend | M2
Task | FEAT-098: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ticket Types' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-098 Ticket Types | Highest | 3 | Server Side / Backend | M2
Story | FEAT-099 Fraud Detection | Covers 12 matrix requirement(s). System shall identify transactions with elevated chargeback risk. | E04 Payments, Wallet & Financial |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-099: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Fraud Detection' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-099 Fraud Detection | Medium | 2 | Server Side / Backend | M4
Task | FEAT-099: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Fraud Detection' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-099 Fraud Detection | Medium | 3 | Server Side / Backend | M4
Task | FEAT-099: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Fraud Detection' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-099 Fraud Detection | Medium | 5 | Server Side / Backend | M4
Task | FEAT-099: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Fraud Detection' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-099 Fraud Detection | Medium | 2 | Server Side / Backend | M4
Task | FEAT-099: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Fraud Detection' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-099 Fraud Detection | Medium | 2 | Server Side / Backend | M4
Story | FEAT-100 Call Center Sales | Covers 10 matrix requirement(s). B2C website should support: 1.Home page 1) Banners display packages, upgrades, and discounts 2) All available products are shown by category: Packages, Tickets, Experiences, Annual Passes, Others 3) P… | E04 Payments, Wallet & Financial |  | Highest | 13 | Server Side / Backend | M2_Phase_3
Task | FEAT-100: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Call Center Sales' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-100 Call Center Sales | Highest | 2 | Server Side / Backend | M2
Task | FEAT-100: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Call Center Sales' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-100 Call Center Sales | Highest | 3 | Server Side / Backend | M2
Task | FEAT-100: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Call Center Sales' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-100 Call Center Sales | Highest | 5 | Server Side / Backend | M2
Task | FEAT-100: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Call Center Sales' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-100 Call Center Sales | Highest | 2 | Server Side / Backend | M2
Task | FEAT-100: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Call Center Sales' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-100 Call Center Sales | Highest | 2 | Server Side / Backend | M2
Story | FEAT-101 Portfolio And Entitlement Management | Covers 9 matrix requirement(s). Allow configurable transfer of stored value, wallet balances, promotional credits, and vouchers between linked portfolios with full audit tracking. | E04 Payments, Wallet & Financial |  | Highest | 13 | Server Side / Backend | M2_Phase_3
Task | FEAT-101: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Portfolio And Entitlement Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-101 Portfolio And Entitlement Management | Highest | 2 | Server Side / Backend | M2
Task | FEAT-101: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Portfolio And Entitlement Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-101 Portfolio And Entitlement Management | Highest | 3 | Server Side / Backend | M2
Task | FEAT-101: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Portfolio And Entitlement Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-101 Portfolio And Entitlement Management | Highest | 3 | Server Side / Backend | M2
Task | FEAT-101: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Portfolio And Entitlement Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-101 Portfolio And Entitlement Management | Highest | 2 | Server Side / Backend | M2
Task | FEAT-101: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Portfolio And Entitlement Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-101 Portfolio And Entitlement Management | Highest | 2 | Server Side / Backend | M2
Story | FEAT-102 Virtual Queue | Covers 9 matrix requirement(s). Automatically assign guests to queues based on ticket type, attraction, capacity availability, reservation rules, guest profile, or business policies. | E04 Payments, Wallet & Financial |  | Highest | 8 | Server Side / Backend | M2_Phase_3
Task | FEAT-102: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Virtual Queue' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-102 Virtual Queue | Highest | 1 | Server Side / Backend | M2
Task | FEAT-102: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Virtual Queue' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-102 Virtual Queue | Highest | 2 | Server Side / Backend | M2
Task | FEAT-102: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Virtual Queue' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-102 Virtual Queue | Highest | 2 | Server Side / Backend | M2
Task | FEAT-102: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Virtual Queue' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-102 Virtual Queue | Highest | 1 | Server Side / Backend | M2
Task | FEAT-102: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Virtual Queue' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-102 Virtual Queue | Highest | 1 | Server Side / Backend | M2
Story | FEAT-103 Ticket Upgrades | Covers 8 matrix requirement(s). The system should display prices in multiple currencies in the B2C portal for guests comparison although the sale will be finalized always in local currency. | E04 Payments, Wallet & Financial |  | Highest | 5 | Server Side / Backend | M2_Phase_3
Task | FEAT-103: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ticket Upgrades' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-103 Ticket Upgrades | Highest | 1 | Server Side / Backend | M2
Task | FEAT-103: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ticket Upgrades' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-103 Ticket Upgrades | Highest | 2 | Server Side / Backend | M2
Task | FEAT-103: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ticket Upgrades' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-103 Ticket Upgrades | Highest | 2 | Server Side / Backend | M2
Task | FEAT-103: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ticket Upgrades' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-103 Ticket Upgrades | Highest | 1 | Server Side / Backend | M2
Task | FEAT-103: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ticket Upgrades' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-103 Ticket Upgrades | Highest | 1 | Server Side / Backend | M2
Story | FEAT-104 Profile Management | Covers 8 matrix requirement(s). The system should allow the guests to upload photos to create avatars for their profiles. | E04 Payments, Wallet & Financial |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-104: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Profile Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-104 Profile Management | Medium | 2 | Server Side / Backend | M4
Task | FEAT-104: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Profile Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-104 Profile Management | Medium | 3 | Server Side / Backend | M4
Task | FEAT-104: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Profile Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-104 Profile Management | Medium | 3 | Server Side / Backend | M4
Task | FEAT-104: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Profile Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-104 Profile Management | Medium | 2 | Server Side / Backend | M4
Task | FEAT-104: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Profile Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-104 Profile Management | Medium | 2 | Server Side / Backend | M4
Story | FEAT-105 Ticket Media | Covers 7 matrix requirement(s). The system should support multiple media types for a ticket. Expected formats: - Paper/thermal tickets with QR, Barcode, RFID - Print at home tickets with QR, Barcode - Smartphones: NFC (near-field co… | E04 Payments, Wallet & Financial |  | Highest | 8 | Server Side / Backend | M2_Phase_3
Task | FEAT-105: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ticket Media' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-105 Ticket Media | Highest | 2 | Server Side / Backend | M2
Task | FEAT-105: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ticket Media' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-105 Ticket Media | Highest | 3 | Server Side / Backend | M2
Task | FEAT-105: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ticket Media' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-105 Ticket Media | Highest | 3 | Server Side / Backend | M2
Task | FEAT-105: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ticket Media' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-105 Ticket Media | Highest | 2 | Server Side / Backend | M2
Task | FEAT-105: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ticket Media' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-105 Ticket Media | Highest | 2 | Server Side / Backend | M2
Story | FEAT-106 Guest Profiles And Data Management | Covers 7 matrix requirement(s). Unified Guest Profile System shall maintain a single consolidated guest profile containing personal information, tickets, memberships, loyalty accounts, wallet balances, reservations, purchases, visit… | E04 Payments, Wallet & Financial |  | Highest | 5 | Server Side / Backend | M2_Phase_3
Task | FEAT-106: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Guest Profiles And Data Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-106 Guest Profiles And Data Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-106: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Guest Profiles And Data Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-106 Guest Profiles And Data Management | Highest | 2 | Server Side / Backend | M2
Task | FEAT-106: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Guest Profiles And Data Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-106 Guest Profiles And Data Management | Highest | 2 | Server Side / Backend | M2
Task | FEAT-106: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Guest Profiles And Data Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-106 Guest Profiles And Data Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-106: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Guest Profiles And Data Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-106 Guest Profiles And Data Management | Highest | 1 | Server Side / Backend | M2
Story | FEAT-107 Omnichannel Communications And Ai Chatbot | Covers 7 matrix requirement(s). Unified Guest Identification System shall automatically identify guests using phone number, email, membership number, loyalty account, wallet ID, booking reference, or authenticated user session. | E04 Payments, Wallet & Financial |  | Medium | 8 | Server Side / Backend | M4_Phase_4
Task | FEAT-107: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Omnichannel Communications And Ai Chatbot' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-107 Omnichannel Communications And Ai Chatbot | Medium | 2 | Server Side / Backend | M4
Task | FEAT-107: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Omnichannel Communications And Ai Chatbot' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-107 Omnichannel Communications And Ai Chatbot | Medium | 3 | Server Side / Backend | M4
Task | FEAT-107: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Omnichannel Communications And Ai Chatbot' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-107 Omnichannel Communications And Ai Chatbot | Medium | 3 | Server Side / Backend | M4
Task | FEAT-107: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Omnichannel Communications And Ai Chatbot' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-107 Omnichannel Communications And Ai Chatbot | Medium | 2 | Server Side / Backend | M4
Task | FEAT-107: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Omnichannel Communications And Ai Chatbot' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-107 Omnichannel Communications And Ai Chatbot | Medium | 2 | Server Side / Backend | M4
Story | FEAT-108 Event Management | Covers 6 matrix requirement(s). The system should allow configuration of event details such as start time (date & time), end time, duration of event, capacity (amount of places that can be sold for an event), seating categories, num… | E04 Payments, Wallet & Financial |  | Highest | 5 | Server Side / Backend | M2_Phase_3
Task | FEAT-108: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Event Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-108 Event Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-108: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Event Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-108 Event Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-108: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Event Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-108 Event Management | Highest | 2 | Server Side / Backend | M2
Task | FEAT-108: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Event Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-108 Event Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-108: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Event Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-108 Event Management | Highest | 1 | Server Side / Backend | M2
Story | FEAT-109 Audience Segmentation | Covers 6 matrix requirement(s). Audience Segmentation Engine System shall provide a centralized segmentation engine allowing users to create, manage, and reuse guest audiences based on demographic, behavioral, transactional, loyalty… | E04 Payments, Wallet & Financial |  | Medium | 8 | Server Side / Backend | M4_Phase_4
Task | FEAT-109: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Audience Segmentation' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-109 Audience Segmentation | Medium | 2 | Server Side / Backend | M4
Task | FEAT-109: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Audience Segmentation' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-109 Audience Segmentation | Medium | 2 | Server Side / Backend | M4
Task | FEAT-109: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Audience Segmentation' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-109 Audience Segmentation | Medium | 3 | Server Side / Backend | M4
Task | FEAT-109: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Audience Segmentation' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-109 Audience Segmentation | Medium | 2 | Server Side / Backend | M4
Task | FEAT-109: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Audience Segmentation' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-109 Audience Segmentation | Medium | 2 | Server Side / Backend | M4
Story | FEAT-110 Resource Management | Covers 5 matrix requirement(s). The system should allow linking of staff resources in different combinations and time-slot capacity with individual attraction experiences such as group lessons and private lessons. | E04 Payments, Wallet & Financial |  | Highest | 5 | Server Side / Backend | M2_Phase_3
Task | FEAT-110: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Resource Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-110 Resource Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-110: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Resource Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-110 Resource Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-110: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Resource Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-110 Resource Management | Highest | 2 | Server Side / Backend | M2
Task | FEAT-110: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Resource Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-110 Resource Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-110: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Resource Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-110 Resource Management | Highest | 1 | Server Side / Backend | M2
Story | FEAT-111 Sales Channels | Covers 5 matrix requirement(s). The system should allow specification of rules and conditions associated with a ticket. These rules and conditions will govern the usage of the ticket and any transactions associated with a ticket suc… | E04 Payments, Wallet & Financial |  | Highest | 5 | Server Side / Backend | M2_Phase_3
Task | FEAT-111: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Sales Channels' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-111 Sales Channels | Highest | 1 | Server Side / Backend | M2
Task | FEAT-111: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Sales Channels' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-111 Sales Channels | Highest | 1 | Server Side / Backend | M2
Task | FEAT-111: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Sales Channels' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-111 Sales Channels | Highest | 2 | Server Side / Backend | M2
Task | FEAT-111: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Sales Channels' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-111 Sales Channels | Highest | 1 | Server Side / Backend | M2
Task | FEAT-111: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Sales Channels' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-111 Sales Channels | Highest | 1 | Server Side / Backend | M2
Story | FEAT-112 Upsell And Cross-Sell | Covers 5 matrix requirement(s). Upsell recommendations shall remain synchronized across B2C, B2B, Mobile App, POS, Kiosk, Call Center, API, Membership, Loyalty, and Wallet channels. | E04 Payments, Wallet & Financial |  | Medium | 8 | Server Side / Backend | M4_Phase_4
Task | FEAT-112: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Upsell And Cross-Sell' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-112 Upsell And Cross-Sell | Medium | 2 | Server Side / Backend | M4
Task | FEAT-112: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Upsell And Cross-Sell' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-112 Upsell And Cross-Sell | Medium | 2 | Server Side / Backend | M4
Task | FEAT-112: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Upsell And Cross-Sell' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-112 Upsell And Cross-Sell | Medium | 3 | Server Side / Backend | M4
Task | FEAT-112: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Upsell And Cross-Sell' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-112 Upsell And Cross-Sell | Medium | 2 | Server Side / Backend | M4
Task | FEAT-112: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Upsell And Cross-Sell' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-112 Upsell And Cross-Sell | Medium | 2 | Server Side / Backend | M4
Story | FEAT-113 Game And Ride Payment And Redemption | Covers 5 matrix requirement(s). The system should allow the usage of digital wallet credits for pay as you go for Redemption /Skill games /Rides /Video games | E04 Payments, Wallet & Financial |  | Highest | 8 | Server Side / Backend | M2_Phase_3
Task | FEAT-113: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Game And Ride Payment And Redemption' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-113 Game And Ride Payment And Redemption | Highest | 2 | Server Side / Backend | M2
Task | FEAT-113: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Game And Ride Payment And Redemption' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-113 Game And Ride Payment And Redemption | Highest | 2 | Server Side / Backend | M2
Task | FEAT-113: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Game And Ride Payment And Redemption' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-113 Game And Ride Payment And Redemption | Highest | 3 | Server Side / Backend | M2
Task | FEAT-113: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Game And Ride Payment And Redemption' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-113 Game And Ride Payment And Redemption | Highest | 2 | Server Side / Backend | M2
Task | FEAT-113: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Game And Ride Payment And Redemption' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-113 Game And Ride Payment And Redemption | Highest | 2 | Server Side / Backend | M2
Story | FEAT-114 Api Business Coverage | Covers 5 matrix requirement(s). APIs shall support wallet funding, spending, refunds, balance inquiry, transaction history and wallet status management. | E04 Payments, Wallet & Financial |  | Highest | 8 | Server Side / Backend | M2_Phase_3
Task | FEAT-114: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Api Business Coverage' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-114 Api Business Coverage | Highest | 2 | Server Side / Backend | M2
Task | FEAT-114: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Api Business Coverage' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-114 Api Business Coverage | Highest | 2 | Server Side / Backend | M2
Task | FEAT-114: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Api Business Coverage' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-114 Api Business Coverage | Highest | 3 | Server Side / Backend | M2
Task | FEAT-114: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Api Business Coverage' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-114 Api Business Coverage | Highest | 2 | Server Side / Backend | M2
Task | FEAT-114: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Api Business Coverage' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-114 Api Business Coverage | Highest | 2 | Server Side / Backend | M2
Story | FEAT-115 Group Reservations And Blocks | Covers 5 matrix requirement(s). Group Reservations System shall support group reservations. | E04 Payments, Wallet & Financial |  | Highest | 5 | Server Side / Backend | M2_Phase_3
Task | FEAT-115: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Group Reservations And Blocks' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-115 Group Reservations And Blocks | Highest | 1 | Server Side / Backend | M2
Task | FEAT-115: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Group Reservations And Blocks' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-115 Group Reservations And Blocks | Highest | 1 | Server Side / Backend | M2
Task | FEAT-115: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Group Reservations And Blocks' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-115 Group Reservations And Blocks | Highest | 2 | Server Side / Backend | M2
Task | FEAT-115: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Group Reservations And Blocks' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-115 Group Reservations And Blocks | Highest | 1 | Server Side / Backend | M2
Task | FEAT-115: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Group Reservations And Blocks' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-115 Group Reservations And Blocks | Highest | 1 | Server Side / Backend | M2
Story | FEAT-116 Campaign Management | Covers 5 matrix requirement(s). Campaign Approval Workflow System shall support configurable approval workflows before campaign activation, including creator, reviewer, approver, and publisher roles with full audit tracking. | E04 Payments, Wallet & Financial |  | Highest | 5 | Server Side / Backend | M2_Phase_3
Task | FEAT-116: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Campaign Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-116 Campaign Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-116: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Campaign Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-116 Campaign Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-116: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Campaign Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-116 Campaign Management | Highest | 2 | Server Side / Backend | M2
Task | FEAT-116: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Campaign Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-116 Campaign Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-116: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Campaign Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-116 Campaign Management | Highest | 1 | Server Side / Backend | M2
Story | FEAT-117 Case Management And Sla | Covers 5 matrix requirement(s). Event Trigger Engine System shall automatically trigger marketing journeys based on business events including ticket purchases, reservations, check-ins, membership renewals, membership expiration, loy… | E04 Payments, Wallet & Financial |  | Highest | 5 | Server Side / Backend | M2_Phase_3
Task | FEAT-117: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Case Management And Sla' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-117 Case Management And Sla | Highest | 1 | Server Side / Backend | M2
Task | FEAT-117: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Case Management And Sla' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-117 Case Management And Sla | Highest | 1 | Server Side / Backend | M2
Task | FEAT-117: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Case Management And Sla' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-117 Case Management And Sla | Highest | 2 | Server Side / Backend | M2
Task | FEAT-117: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Case Management And Sla' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-117 Case Management And Sla | Highest | 1 | Server Side / Backend | M2
Task | FEAT-117: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Case Management And Sla' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-117 Case Management And Sla | Highest | 1 | Server Side / Backend | M2
Story | FEAT-118 Notifications And Messaging | Covers 5 matrix requirement(s). Dynamic Personalization Notification content shall support dynamic placeholders including guest name, booking reference, event details, membership status, loyalty balance, wallet balance, venue inform… | E04 Payments, Wallet & Financial |  | Medium | 8 | Server Side / Backend | M4_Phase_4
Task | FEAT-118: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Notifications And Messaging' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-118 Notifications And Messaging | Medium | 2 | Server Side / Backend | M4
Task | FEAT-118: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Notifications And Messaging' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-118 Notifications And Messaging | Medium | 2 | Server Side / Backend | M4
Task | FEAT-118: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Notifications And Messaging' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-118 Notifications And Messaging | Medium | 3 | Server Side / Backend | M4
Task | FEAT-118: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Notifications And Messaging' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-118 Notifications And Messaging | Medium | 2 | Server Side / Backend | M4
Task | FEAT-118: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Notifications And Messaging' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-118 Notifications And Messaging | Medium | 2 | Server Side / Backend | M4
Story | FEAT-119 Product Lifecycle | Covers 4 matrix requirement(s). System shall support future publication, activation, deactivation and automatic retirement of products based on configurable dates and times. | E04 Payments, Wallet & Financial |  | Medium | 8 | Server Side / Backend | M4_Phase_4
Task | FEAT-119: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Product Lifecycle' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-119 Product Lifecycle | Medium | 1 | Server Side / Backend | M4
Task | FEAT-119: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Product Lifecycle' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-119 Product Lifecycle | Medium | 2 | Server Side / Backend | M4
Task | FEAT-119: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Product Lifecycle' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-119 Product Lifecycle | Medium | 3 | Server Side / Backend | M4
Task | FEAT-119: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Product Lifecycle' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-119 Product Lifecycle | Medium | 1 | Server Side / Backend | M4
Task | FEAT-119: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Product Lifecycle' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-119 Product Lifecycle | Medium | 1 | Server Side / Backend | M4
Story | FEAT-120 Membership | Covers 4 matrix requirement(s). Annual-pass reservation quota engine linked to biometric identity, with self-service reschedule/cancel | E04 Payments, Wallet & Financial |  | Medium | 8 | Server Side / Backend | M4_Phase_4
Task | FEAT-120: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Membership' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-120 Membership | Medium | 1 | Server Side / Backend | M4
Task | FEAT-120: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Membership' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-120 Membership | Medium | 2 | Server Side / Backend | M4
Task | FEAT-120: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Membership' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-120 Membership | Medium | 3 | Server Side / Backend | M4
Task | FEAT-120: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Membership' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-120 Membership | Medium | 1 | Server Side / Backend | M4
Task | FEAT-120: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Membership' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-120 Membership | Medium | 1 | Server Side / Backend | M4
Story | FEAT-121 Front Gate Sales | Covers 3 matrix requirement(s). Before closing the order, it is possible to have upsells / cross sells functionalities activated. | E04 Payments, Wallet & Financial |  | Highest | 8 | POS App | M2_Phase_3
Task | FEAT-121: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Front Gate Sales' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-121 Front Gate Sales | Highest | 2 | POS App | M2
Task | FEAT-121: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Front Gate Sales' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-121 Front Gate Sales | Highest | 1 | POS App | M2
Task | FEAT-121: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Front Gate Sales' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-121 Front Gate Sales | Highest | 2 | POS App | M2
Task | FEAT-121: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Front Gate Sales' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-121 Front Gate Sales | Highest | 2 | POS App | M2
Task | FEAT-121: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Front Gate Sales' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-121 Front Gate Sales | Highest | 1 | POS App | M2
Story | FEAT-122 Loyalty | Covers 3 matrix requirement(s). Configure redemption rules and conversion rates. System shall support configurable points redemption rules including points-to-currency conversion, product redemption, ticket redemption, experience re… | E04 Payments, Wallet & Financial |  | Highest | 2 | Server Side / Backend | M2_Phase_3
Task | FEAT-122: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Loyalty' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-122 Loyalty | Highest | 1 | Server Side / Backend | M2
Task | FEAT-122: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Loyalty' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-122 Loyalty | Highest | 1 | Server Side / Backend | M2
Task | FEAT-122: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Loyalty' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-122 Loyalty | Highest | 1 | Server Side / Backend | M2
Task | FEAT-122: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Loyalty' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-122 Loyalty | Highest | 1 | Server Side / Backend | M2
Task | FEAT-122: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Loyalty' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-122 Loyalty | Highest | 1 | Server Side / Backend | M2
Story | FEAT-123 Gamification And Loyalty | Covers 3 matrix requirement(s). Points-Based Activities Guests shall earn points through visits, purchases, event attendance, referrals, reviews, surveys, memberships, wallet activity, and other configurable actions. | E04 Payments, Wallet & Financial |  | Highest | 8 | Server Side / Backend | M2_Phase_3
Task | FEAT-123: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Gamification And Loyalty' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-123 Gamification And Loyalty | Highest | 1 | Server Side / Backend | M2
Task | FEAT-123: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Gamification And Loyalty' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-123 Gamification And Loyalty | Highest | 2 | Server Side / Backend | M2
Task | FEAT-123: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Gamification And Loyalty' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-123 Gamification And Loyalty | Highest | 2 | Server Side / Backend | M2
Task | FEAT-123: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Gamification And Loyalty' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-123 Gamification And Loyalty | Highest | 1 | Server Side / Backend | M2
Task | FEAT-123: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Gamification And Loyalty' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-123 Gamification And Loyalty | Highest | 1 | Server Side / Backend | M2
Story | FEAT-124 Ticket Resale Marketplace | Covers 2 matrix requirement(s). System shall allow ticket holders to create, update, activate, deactivate, cancel, and manage resale listings. Listing status shall be tracked throughout its lifecycle. | E04 Payments, Wallet & Financial |  | Highest | 2 | Server Side / Backend | M2_Phase_3
Task | FEAT-124: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ticket Resale Marketplace' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-124 Ticket Resale Marketplace | Highest | 1 | Server Side / Backend | M2
Task | FEAT-124: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ticket Resale Marketplace' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-124 Ticket Resale Marketplace | Highest | 1 | Server Side / Backend | M2
Task | FEAT-124: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ticket Resale Marketplace' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-124 Ticket Resale Marketplace | Highest | 1 | Server Side / Backend | M2
Task | FEAT-124: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ticket Resale Marketplace' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-124 Ticket Resale Marketplace | Highest | 1 | Server Side / Backend | M2
Task | FEAT-124: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ticket Resale Marketplace' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-124 Ticket Resale Marketplace | Highest | 1 | Server Side / Backend | M2
Story | FEAT-125 Unified Platform | Covers 2 matrix requirement(s). Display memberships, wallet balances, points and vouchers in one view. System shall provide a single guest wallet view combining membership status, loyalty points, stored value, gift cards, vouchers, … | E04 Payments, Wallet & Financial |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-125: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Unified Platform' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-125 Unified Platform | Medium | 1 | Server Side / Backend | M4
Task | FEAT-125: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Unified Platform' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-125 Unified Platform | Medium | 2 | Server Side / Backend | M4
Task | FEAT-125: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Unified Platform' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-125 Unified Platform | Medium | 2 | Server Side / Backend | M4
Task | FEAT-125: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Unified Platform' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-125 Unified Platform | Medium | 1 | Server Side / Backend | M4
Task | FEAT-125: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Unified Platform' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-125 Unified Platform | Medium | 1 | Server Side / Backend | M4
Story | FEAT-126 Device Registration | Covers 2 matrix requirement(s). Device Activation - System shall support device activation. | E04 Payments, Wallet & Financial |  | Highest | 3 | Server Side / Backend | M2_Phase_3
Task | FEAT-126: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Device Registration' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-126 Device Registration | Highest | 1 | Server Side / Backend | M2
Task | FEAT-126: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Device Registration' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-126 Device Registration | Highest | 1 | Server Side / Backend | M2
Task | FEAT-126: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Device Registration' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-126 Device Registration | Highest | 1 | Server Side / Backend | M2
Task | FEAT-126: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Device Registration' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-126 Device Registration | Highest | 1 | Server Side / Backend | M2
Task | FEAT-126: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Device Registration' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-126 Device Registration | Highest | 1 | Server Side / Backend | M2
Story | FEAT-127 Module Marketplace And Management | Covers 2 matrix requirement(s). Module Activation - System shall support module activation. | E04 Payments, Wallet & Financial |  | Highest | 3 | Server Side / Backend | M2_Phase_3
Task | FEAT-127: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Module Marketplace And Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-127 Module Marketplace And Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-127: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Module Marketplace And Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-127 Module Marketplace And Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-127: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Module Marketplace And Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-127 Module Marketplace And Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-127: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Module Marketplace And Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-127 Module Marketplace And Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-127: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Module Marketplace And Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-127 Module Marketplace And Management | Highest | 1 | Server Side / Backend | M2
Story | FEAT-128 Billing And Payment | Covers 2 matrix requirement(s). Subscription Invoicing - System shall generate subscription invoices. | E04 Payments, Wallet & Financial |  | Highest | 3 | Server Side / Backend | M2_Phase_3
Task | FEAT-128: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Billing And Payment' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-128 Billing And Payment | Highest | 1 | Server Side / Backend | M2
Task | FEAT-128: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Billing And Payment' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-128 Billing And Payment | Highest | 1 | Server Side / Backend | M2
Task | FEAT-128: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Billing And Payment' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-128 Billing And Payment | Highest | 1 | Server Side / Backend | M2
Task | FEAT-128: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Billing And Payment' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-128 Billing And Payment | Highest | 1 | Server Side / Backend | M2
Task | FEAT-128: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Billing And Payment' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-128 Billing And Payment | Highest | 1 | Server Side / Backend | M2
Story | FEAT-129 Newsletter And Email Marketing | Covers 2 matrix requirement(s). Product & Event Integration Newsletter content shall automatically retrieve information from Ticketing, Events, Memberships, Loyalty, Wallet, Retail, F&B, and Resource Management modules without manua… | E04 Payments, Wallet & Financial |  | Highest | 5 | Server Side / Backend | M2_Phase_3
Task | FEAT-129: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Newsletter And Email Marketing' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-129 Newsletter And Email Marketing | Highest | 1 | Server Side / Backend | M2
Task | FEAT-129: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Newsletter And Email Marketing' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-129 Newsletter And Email Marketing | Highest | 2 | Server Side / Backend | M2
Task | FEAT-129: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Newsletter And Email Marketing' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-129 Newsletter And Email Marketing | Highest | 2 | Server Side / Backend | M2
Task | FEAT-129: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Newsletter And Email Marketing' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-129 Newsletter And Email Marketing | Highest | 1 | Server Side / Backend | M2
Task | FEAT-129: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Newsletter And Email Marketing' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-129 Newsletter And Email Marketing | Highest | 1 | Server Side / Backend | M2
Story | FEAT-130 Reviews And Ratings | Covers 2 matrix requirement(s). Review Collection System shall automatically collect reviews and ratings from guests following visits, ticket usage, completed events, reservations, purchases, membership activities, and customer serv… | E04 Payments, Wallet & Financial |  | Highest | 2 | Server Side / Backend | M2_Phase_3
Task | FEAT-130: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Reviews And Ratings' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-130 Reviews And Ratings | Highest | 1 | Server Side / Backend | M2
Task | FEAT-130: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Reviews And Ratings' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-130 Reviews And Ratings | Highest | 1 | Server Side / Backend | M2
Task | FEAT-130: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Reviews And Ratings' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-130 Reviews And Ratings | Highest | 1 | Server Side / Backend | M2
Task | FEAT-130: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Reviews And Ratings' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-130 Reviews And Ratings | Highest | 1 | Server Side / Backend | M2
Task | FEAT-130: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Reviews And Ratings' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-130 Reviews And Ratings | Highest | 1 | Server Side / Backend | M2
Story | FEAT-131 Surveys And Feedback | Covers 2 matrix requirement(s). Trigger-Based Surveys Surveys shall automatically trigger based on ticket usage, event attendance, reservation completion, membership activity, wallet activity, loyalty activity, support interactions,… | E04 Payments, Wallet & Financial |  | Highest | 3 | Server Side / Backend | M2_Phase_3
Task | FEAT-131: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Surveys And Feedback' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-131 Surveys And Feedback | Highest | 1 | Server Side / Backend | M2
Task | FEAT-131: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Surveys And Feedback' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-131 Surveys And Feedback | Highest | 1 | Server Side / Backend | M2
Task | FEAT-131: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Surveys And Feedback' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-131 Surveys And Feedback | Highest | 1 | Server Side / Backend | M2
Task | FEAT-131: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Surveys And Feedback' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-131 Surveys And Feedback | Highest | 1 | Server Side / Backend | M2
Task | FEAT-131: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Surveys And Feedback' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-131 Surveys And Feedback | Highest | 1 | Server Side / Backend | M2
Story | FEAT-132 Marketing | Covers 2 matrix requirement(s). Content Scheduling Content shall support publishing schedules, expiration dates, seasonal activation, campaign activation, and future publication. | E04 Payments, Wallet & Financial |  | Highest | 5 | Server Side / Backend | M2_Phase_3
Task | FEAT-132: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Marketing' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-132 Marketing | Highest | 1 | Server Side / Backend | M2
Task | FEAT-132: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Marketing' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-132 Marketing | Highest | 2 | Server Side / Backend | M2
Task | FEAT-132: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Marketing' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-132 Marketing | Highest | 2 | Server Side / Backend | M2
Task | FEAT-132: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Marketing' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-132 Marketing | Highest | 1 | Server Side / Backend | M2
Task | FEAT-132: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Marketing' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-132 Marketing | Highest | 1 | Server Side / Backend | M2
Story | FEAT-133 Ticketing Pos And Kiosks | Covers 1 matrix requirement(s). The system should allow creation of Mobile POS, depending on the activities, activation on demand, either on site or off site. Mobile-POS should have all the same features as a normal POS. The sales j… | E04 Payments, Wallet & Financial |  | Highest | 5 | POS App | M2_Phase_3
Task | FEAT-133: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Ticketing Pos And Kiosks' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-133 Ticketing Pos And Kiosks | Highest | 2 | POS App | M2
Task | FEAT-133: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Ticketing Pos And Kiosks' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-133 Ticketing Pos And Kiosks | Highest | 1 | POS App | M2
Task | FEAT-133: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Ticketing Pos And Kiosks' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-133 Ticketing Pos And Kiosks | Highest | 2 | POS App | M2
Task | FEAT-133: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Ticketing Pos And Kiosks' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-133 Ticketing Pos And Kiosks | Highest | 2 | POS App | M2
Task | FEAT-133: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Ticketing Pos And Kiosks' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-133 Ticketing Pos And Kiosks | Highest | 1 | POS App | M2
Story | FEAT-134 Flying Pos | Covers 1 matrix requirement(s). The system should support offline mode for POS and Kiosk: - Ability to switch automatically to offline mode in case of server outage / network loss - Definition of which functionality will be lost in … | E04 Payments, Wallet & Financial |  | Highest | 5 | POS App | M2_Phase_3
Task | FEAT-134: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Flying Pos' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-134 Flying Pos | Highest | 2 | POS App | M2
Task | FEAT-134: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Flying Pos' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-134 Flying Pos | Highest | 1 | POS App | M2
Task | FEAT-134: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Flying Pos' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-134 Flying Pos | Highest | 2 | POS App | M2
Task | FEAT-134: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Flying Pos' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-134 Flying Pos | Highest | 2 | POS App | M2
Task | FEAT-134: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Flying Pos' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-134 Flying Pos | Highest | 1 | POS App | M2
Story | FEAT-135 Digital Waiver Management | Covers 1 matrix requirement(s). System shall display a detailed breakdown of all applicable fees, taxes, discounts, promotions, surcharges, and charges during checkout, order confirmation, receipts, invoices, and financial documents… | E04 Payments, Wallet & Financial |  | Highest | 1 | Server Side / Backend | M2_Phase_3
Task | FEAT-135: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Digital Waiver Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-135 Digital Waiver Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-135: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Digital Waiver Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-135 Digital Waiver Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-135: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Digital Waiver Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-135 Digital Waiver Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-135: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Digital Waiver Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-135 Digital Waiver Management | Highest | 1 | Server Side / Backend | M2
Task | FEAT-135: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Digital Waiver Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-135 Digital Waiver Management | Highest | 1 | Server Side / Backend | M2
Story | FEAT-136 Bundles | Covers 1 matrix requirement(s). Redeem gift cards at POS and digital channels. | E04 Payments, Wallet & Financial |  | Highest | 3 | POS App | M2_Phase_3
Task | FEAT-136: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Bundles' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-136 Bundles | Highest | 1 | POS App | M2
Task | FEAT-136: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Bundles' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-136 Bundles | Highest | 1 | POS App | M2
Task | FEAT-136: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Bundles' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-136 Bundles | Highest | 1 | POS App | M2
Task | FEAT-136: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Bundles' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-136 Bundles | Highest | 1 | POS App | M2
Task | FEAT-136: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Bundles' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-136 Bundles | Highest | 1 | POS App | M2
Story | FEAT-137 Payment Methods | Covers 1 matrix requirement(s). The system should be able to provide a way for central reservations where the guest should be able to place a booking from various touchpoints. The system should provide APIs to facilitate reservation… | E04 Payments, Wallet & Financial |  | Highest | 3 | Server Side / Backend | M2_Phase_3
Task | FEAT-137: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Payment Methods' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-137 Payment Methods | Highest | 1 | Server Side / Backend | M2
Task | FEAT-137: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Payment Methods' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-137 Payment Methods | Highest | 1 | Server Side / Backend | M2
Task | FEAT-137: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Payment Methods' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-137 Payment Methods | Highest | 1 | Server Side / Backend | M2
Task | FEAT-137: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Payment Methods' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-137 Payment Methods | Highest | 1 | Server Side / Backend | M2
Task | FEAT-137: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Payment Methods' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-137 Payment Methods | Highest | 1 | Server Side / Backend | M2
Story | FEAT-138 Cash Handling | Covers 1 matrix requirement(s). The system should allow print and reprint of deposit box transactions. The output should be bilingual (Arabic and English) and simplified for tax handling. | E04 Payments, Wallet & Financial |  | Highest | 3 | Server Side / Backend | M2_Phase_3
Task | FEAT-138: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Cash Handling' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-138 Cash Handling | Highest | 1 | Server Side / Backend | M2
Task | FEAT-138: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Cash Handling' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-138 Cash Handling | Highest | 1 | Server Side / Backend | M2
Task | FEAT-138: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Cash Handling' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-138 Cash Handling | Highest | 1 | Server Side / Backend | M2
Task | FEAT-138: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Cash Handling' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-138 Cash Handling | Highest | 1 | Server Side / Backend | M2
Task | FEAT-138: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Cash Handling' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-138 Cash Handling | Highest | 1 | Server Side / Backend | M2
Story | FEAT-139 Receipt | Covers 1 matrix requirement(s). The system should show all required fields on the receipt in accordance with VAT regulations. | E04 Payments, Wallet & Financial |  | Highest | 3 | Server Side / Backend | M2_Phase_3
Task | FEAT-139: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Receipt' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-139 Receipt | Highest | 1 | Server Side / Backend | M2
Task | FEAT-139: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Receipt' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-139 Receipt | Highest | 1 | Server Side / Backend | M2
Task | FEAT-139: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Receipt' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-139 Receipt | Highest | 1 | Server Side / Backend | M2
Task | FEAT-139: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Receipt' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-139 Receipt | Highest | 1 | Server Side / Backend | M2
Task | FEAT-139: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Receipt' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-139 Receipt | Highest | 1 | Server Side / Backend | M2
Story | FEAT-140 Double-Entry Financial Ledger | Covers 1 matrix requirement(s). Multi-Currency Support System shall support accounting entries across multiple currencies. | E04 Payments, Wallet & Financial |  | Highest | 3 | Server Side / Backend | M2_Phase_3
Task | FEAT-140: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Double-Entry Financial Ledger' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-140 Double-Entry Financial Ledger | Highest | 1 | Server Side / Backend | M2
Task | FEAT-140: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Double-Entry Financial Ledger' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-140 Double-Entry Financial Ledger | Highest | 1 | Server Side / Backend | M2
Task | FEAT-140: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Double-Entry Financial Ledger' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-140 Double-Entry Financial Ledger | Highest | 1 | Server Side / Backend | M2
Task | FEAT-140: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Double-Entry Financial Ledger' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-140 Double-Entry Financial Ledger | Highest | 1 | Server Side / Backend | M2
Task | FEAT-140: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Double-Entry Financial Ledger' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-140 Double-Entry Financial Ledger | Highest | 1 | Server Side / Backend | M2
Story | FEAT-141 Dynamic Pricing | Covers 1 matrix requirement(s). System shall support simulation of pricing scenarios before activation. | E04 Payments, Wallet & Financial |  | Highest | 3 | Server Side / Backend | M2_Phase_3
Task | FEAT-141: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Dynamic Pricing' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-141 Dynamic Pricing | Highest | 1 | Server Side / Backend | M2
Task | FEAT-141: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Dynamic Pricing' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-141 Dynamic Pricing | Highest | 1 | Server Side / Backend | M2
Task | FEAT-141: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Dynamic Pricing' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-141 Dynamic Pricing | Highest | 1 | Server Side / Backend | M2
Task | FEAT-141: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Dynamic Pricing' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-141 Dynamic Pricing | Highest | 1 | Server Side / Backend | M2
Task | FEAT-141: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Dynamic Pricing' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-141 Dynamic Pricing | Highest | 1 | Server Side / Backend | M2
Story | FEAT-142 Ai Configuration Assistant | Covers 1 matrix requirement(s). System shall support automatic activation of future pricing. | E04 Payments, Wallet & Financial |  | Highest | 3 | Server Side / Backend | M2_Phase_3
Task | FEAT-142: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ai Configuration Assistant' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-142 Ai Configuration Assistant | Highest | 1 | Server Side / Backend | M2
Task | FEAT-142: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ai Configuration Assistant' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-142 Ai Configuration Assistant | Highest | 1 | Server Side / Backend | M2
Task | FEAT-142: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ai Configuration Assistant' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-142 Ai Configuration Assistant | Highest | 1 | Server Side / Backend | M2
Task | FEAT-142: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ai Configuration Assistant' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-142 Ai Configuration Assistant | Highest | 1 | Server Side / Backend | M2
Task | FEAT-142: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ai Configuration Assistant' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-142 Ai Configuration Assistant | Highest | 1 | Server Side / Backend | M2
Story | FEAT-143 Operations Command Center | Covers 1 matrix requirement(s). System shall provide real-time monitoring of ticket sales, memberships, F&B sales, retail sales, refunds, upgrades, and transaction performance. | E04 Payments, Wallet & Financial |  | Highest | 5 | Cross Platform | M2_Phase_3
Task | FEAT-143: Design & technical spec | Architecture, interfaces and acceptance criteria. Acceptance: 'Operations Command Center' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-143 Operations Command Center | Highest | 1 | Cross Platform | M2
Task | FEAT-143: Implementation | Build the capability / automation. Acceptance: 'Operations Command Center' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-143 Operations Command Center | Highest | 2 | Cross Platform | M2
Task | FEAT-143: Automation & CI integration | Pipeline, IaC and gates. Acceptance: 'Operations Command Center' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-143 Operations Command Center | Highest | 1 | Cross Platform | M2
Task | FEAT-143: Verification & sign-off | Validate against NFR/acceptance criteria. Acceptance: 'Operations Command Center' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-143 Operations Command Center | Highest | 1 | Cross Platform | M2
Story | FEAT-144 Seat Tracking And Holds | Covers 1 matrix requirement(s). Seat Reservation Tracking System shall support seat reservation tracking. | E04 Payments, Wallet & Financial |  | Highest | 3 | Server Side / Backend | M2_Phase_3
Task | FEAT-144: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Seat Tracking And Holds' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-144 Seat Tracking And Holds | Highest | 1 | Server Side / Backend | M2
Task | FEAT-144: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Seat Tracking And Holds' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-144 Seat Tracking And Holds | Highest | 1 | Server Side / Backend | M2
Task | FEAT-144: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Seat Tracking And Holds' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-144 Seat Tracking And Holds | Highest | 1 | Server Side / Backend | M2
Task | FEAT-144: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Seat Tracking And Holds' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-144 Seat Tracking And Holds | Highest | 1 | Server Side / Backend | M2
Task | FEAT-144: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Seat Tracking And Holds' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E04 Payments, Wallet & Financial | FEAT-144 Seat Tracking And Holds | Highest | 1 | Server Side / Backend | M2
Story | FEAT-145 Table Reservation | Covers 69 matrix requirement(s). The system should have the ability to set mandatory or optional modifiers for items. | E05 F&B Operations & POS |  | Medium | 13 | POS App | M4_Phase_4
Task | FEAT-145: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Table Reservation' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-145 Table Reservation | Medium | 13 | POS App | M4
Task | FEAT-145: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Table Reservation' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-145 Table Reservation | Medium | 8 | POS App | M4
Task | FEAT-145: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Table Reservation' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-145 Table Reservation | Medium | 13 | POS App | M4
Task | FEAT-145: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Table Reservation' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-145 Table Reservation | Medium | 13 | POS App | M4
Task | FEAT-145: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Table Reservation' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-145 Table Reservation | Medium | 8 | POS App | M4
Story | FEAT-146 Retail Pos | Covers 62 matrix requirement(s). The system should be able to assign rights to groups and further add the users to that particular groups (which should be tier based), | E05 F&B Operations & POS |  | Medium | 13 | POS App | M4_Phase_4
Task | FEAT-146: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Retail Pos' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-146 Retail Pos | Medium | 13 | POS App | M4
Task | FEAT-146: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Retail Pos' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-146 Retail Pos | Medium | 8 | POS App | M4
Task | FEAT-146: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Retail Pos' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-146 Retail Pos | Medium | 13 | POS App | M4
Task | FEAT-146: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Retail Pos' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-146 Retail Pos | Medium | 13 | POS App | M4
Task | FEAT-146: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Retail Pos' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-146 Retail Pos | Medium | 8 | POS App | M4
Story | FEAT-147 Fandb Pos - Core Ordering | Covers 37 matrix requirement(s). The system should be able to record a sale to guests from the POS register using menu screens/buttons. | E05 F&B Operations & POS |  | High | 13 | POS App | M3_Phase_3
Task | FEAT-147: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Fandb Pos - Core Ordering' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-147 Fandb Pos - Core Ordering | High | 8 | POS App | M3
Task | FEAT-147: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Fandb Pos - Core Ordering' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-147 Fandb Pos - Core Ordering | High | 5 | POS App | M3
Task | FEAT-147: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Fandb Pos - Core Ordering' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-147 Fandb Pos - Core Ordering | High | 8 | POS App | M3
Task | FEAT-147: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Fandb Pos - Core Ordering' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-147 Fandb Pos - Core Ordering | High | 8 | POS App | M3
Task | FEAT-147: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Fandb Pos - Core Ordering' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-147 Fandb Pos - Core Ordering | High | 5 | POS App | M3
Story | FEAT-148 Fandb Pos - Menu Management | Covers 29 matrix requirement(s). The system should have the ability to add and remove multiple ingredients on one type of recipe order, while there are other recipe products on the same order without any modifications. | E05 F&B Operations & POS |  | Medium | 13 | POS App | M4_Phase_4
Task | FEAT-148: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Fandb Pos - Menu Management' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-148 Fandb Pos - Menu Management | Medium | 8 | POS App | M4
Task | FEAT-148: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Fandb Pos - Menu Management' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-148 Fandb Pos - Menu Management | Medium | 5 | POS App | M4
Task | FEAT-148: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Fandb Pos - Menu Management' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-148 Fandb Pos - Menu Management | Medium | 8 | POS App | M4
Task | FEAT-148: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Fandb Pos - Menu Management' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-148 Fandb Pos - Menu Management | Medium | 8 | POS App | M4
Task | FEAT-148: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Fandb Pos - Menu Management' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-148 Fandb Pos - Menu Management | Medium | 5 | POS App | M4
Story | FEAT-149 Inventory Management Integration | Covers 15 matrix requirement(s). Functional Requirements Ability to create and manage rental products (Bike, Kayak, Watercraft, Stroller, Cabana, Locker, Wheelchair, etc.). Configure: - Product Code - Product Name - Description - Pro… | E05 F&B Operations & POS |  | Medium | 13 | POS App | M4_Phase_4
Task | FEAT-149: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Inventory Management Integration' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-149 Inventory Management Integration | Medium | 5 | POS App | M4
Task | FEAT-149: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Inventory Management Integration' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-149 Inventory Management Integration | Medium | 3 | POS App | M4
Task | FEAT-149: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Inventory Management Integration' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-149 Inventory Management Integration | Medium | 5 | POS App | M4
Task | FEAT-149: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Inventory Management Integration' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-149 Inventory Management Integration | Medium | 5 | POS App | M4
Task | FEAT-149: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Inventory Management Integration' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-149 Inventory Management Integration | Medium | 3 | POS App | M4
Story | FEAT-150 Kitchen Display | Covers 10 matrix requirement(s). Event scheduled services such as table booking or meal delivery can be managed by the system (sales only) | E05 F&B Operations & POS |  | High | 13 | POS App | M3_Phase_3
Task | FEAT-150: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Kitchen Display' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-150 Kitchen Display | High | 3 | POS App | M3
Task | FEAT-150: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Kitchen Display' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-150 Kitchen Display | High | 2 | POS App | M3
Task | FEAT-150: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Kitchen Display' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-150 Kitchen Display | High | 3 | POS App | M3
Task | FEAT-150: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Kitchen Display' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-150 Kitchen Display | High | 3 | POS App | M3
Task | FEAT-150: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Kitchen Display' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-150 Kitchen Display | High | 2 | POS App | M3
Story | FEAT-151 Payment Methods | Covers 9 matrix requirement(s). The system should be able to allow table reservations view for the available tables in real-time, for the guests to choose/request. | E05 F&B Operations & POS |  | High | 13 | POS App | M3_Phase_3
Task | FEAT-151: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Payment Methods' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-151 Payment Methods | High | 3 | POS App | M3
Task | FEAT-151: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Payment Methods' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-151 Payment Methods | High | 2 | POS App | M3
Task | FEAT-151: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Payment Methods' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-151 Payment Methods | High | 3 | POS App | M3
Task | FEAT-151: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Payment Methods' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-151 Payment Methods | High | 3 | POS App | M3
Task | FEAT-151: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Payment Methods' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-151 Payment Methods | High | 2 | POS App | M3
Story | FEAT-152 Fandb Pos - Modifiers | Covers 8 matrix requirement(s). The system should be able to create a new Check with table and guest numbers, add items to print in kitchen or on QSR(Quick service restaurants), void items and ensure they don't appear in kitchen. | E05 F&B Operations & POS |  | High | 5 | POS App | M3_Phase_3
Task | FEAT-152: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Fandb Pos - Modifiers' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-152 Fandb Pos - Modifiers | High | 2 | POS App | M3
Task | FEAT-152: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Fandb Pos - Modifiers' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-152 Fandb Pos - Modifiers | High | 1 | POS App | M3
Task | FEAT-152: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Fandb Pos - Modifiers' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-152 Fandb Pos - Modifiers | High | 2 | POS App | M3
Task | FEAT-152: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Fandb Pos - Modifiers' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-152 Fandb Pos - Modifiers | High | 2 | POS App | M3
Task | FEAT-152: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Fandb Pos - Modifiers' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-152 Fandb Pos - Modifiers | High | 1 | POS App | M3
Story | FEAT-153 Kitchen Display And Inventory Sync | Covers 5 matrix requirement(s). The system should allow send special request comments/directions on the kitchen display/printers for the kitchen preparation guest requests/inputs. | E05 F&B Operations & POS |  | High | 8 | POS App | M3_Phase_3
Task | FEAT-153: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Kitchen Display And Inventory Sync' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-153 Kitchen Display And Inventory Sync | High | 2 | POS App | M3
Task | FEAT-153: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Kitchen Display And Inventory Sync' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-153 Kitchen Display And Inventory Sync | High | 2 | POS App | M3
Task | FEAT-153: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Kitchen Display And Inventory Sync' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-153 Kitchen Display And Inventory Sync | High | 2 | POS App | M3
Task | FEAT-153: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Kitchen Display And Inventory Sync' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-153 Kitchen Display And Inventory Sync | High | 2 | POS App | M3
Task | FEAT-153: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Kitchen Display And Inventory Sync' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-153 Kitchen Display And Inventory Sync | High | 2 | POS App | M3
Story | FEAT-154 Wallet | Covers 3 matrix requirement(s). The system should be able to work with kitchen displays, bump bar, kitchen printers and accept kitchen respective devices. | E05 F&B Operations & POS |  | High | 2 | POS App | M3_Phase_3
Task | FEAT-154: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Wallet' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-154 Wallet | High | 1 | POS App | M3
Task | FEAT-154: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Wallet' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-154 Wallet | High | 1 | POS App | M3
Task | FEAT-154: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Wallet' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-154 Wallet | High | 1 | POS App | M3
Task | FEAT-154: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Wallet' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-154 Wallet | High | 1 | POS App | M3
Task | FEAT-154: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Wallet' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-154 Wallet | High | 1 | POS App | M3
Story | FEAT-155 Sales Channels | Covers 1 matrix requirement(s). System shall allow guests to purchase food and beverage items through self-service kiosks. The kiosk shall support menu browsing, product customization, combo meals, upsell recommendations, promotions… | E05 F&B Operations & POS |  | Medium | 5 | POS App | M4_Phase_4
Task | FEAT-155: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Sales Channels' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-155 Sales Channels | Medium | 2 | POS App | M4
Task | FEAT-155: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Sales Channels' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-155 Sales Channels | Medium | 1 | POS App | M4
Task | FEAT-155: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Sales Channels' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-155 Sales Channels | Medium | 2 | POS App | M4
Task | FEAT-155: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Sales Channels' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-155 Sales Channels | Medium | 2 | POS App | M4
Task | FEAT-155: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Sales Channels' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-155 Sales Channels | Medium | 1 | POS App | M4
Story | FEAT-156 Bundles | Covers 1 matrix requirement(s). Recommend actions to reduce waste and spoilage. | E05 F&B Operations & POS |  | Medium | 5 | POS App | M4_Phase_4
Task | FEAT-156: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Bundles' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-156 Bundles | Medium | 2 | POS App | M4
Task | FEAT-156: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Bundles' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-156 Bundles | Medium | 1 | POS App | M4
Task | FEAT-156: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Bundles' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-156 Bundles | Medium | 2 | POS App | M4
Task | FEAT-156: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Bundles' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-156 Bundles | Medium | 2 | POS App | M4
Task | FEAT-156: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Bundles' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-156 Bundles | Medium | 1 | POS App | M4
Story | FEAT-157 Api Business Coverage | Covers 1 matrix requirement(s). APIs shall support menu retrieval, order creation, order status, kitchen status, inventory updates and promotions. | E05 F&B Operations & POS |  | High | 3 | POS App | M3_Phase_3
Task | FEAT-157: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Api Business Coverage' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-157 Api Business Coverage | High | 1 | POS App | M3
Task | FEAT-157: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Api Business Coverage' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-157 Api Business Coverage | High | 1 | POS App | M3
Task | FEAT-157: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Api Business Coverage' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-157 Api Business Coverage | High | 1 | POS App | M3
Task | FEAT-157: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Api Business Coverage' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-157 Api Business Coverage | High | 1 | POS App | M3
Task | FEAT-157: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Api Business Coverage' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-157 Api Business Coverage | High | 1 | POS App | M3
Story | FEAT-158 Digital Waivers And Signature Management | Covers 1 matrix requirement(s). Medical Declaration Forms System shall support collection of medical information, allergies, health declarations, emergency contacts, and special requirements when permitted by organizational policies… | E05 F&B Operations & POS |  | High | 3 | POS App | M3_Phase_3
Task | FEAT-158: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Digital Waivers And Signature Management' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-158 Digital Waivers And Signature Management | High | 1 | POS App | M3
Task | FEAT-158: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Digital Waivers And Signature Management' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-158 Digital Waivers And Signature Management | High | 1 | POS App | M3
Task | FEAT-158: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Digital Waivers And Signature Management' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-158 Digital Waivers And Signature Management | High | 1 | POS App | M3
Task | FEAT-158: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Digital Waivers And Signature Management' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-158 Digital Waivers And Signature Management | High | 1 | POS App | M3
Task | FEAT-158: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Digital Waivers And Signature Management' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E05 F&B Operations & POS | FEAT-158 Digital Waivers And Signature Management | High | 1 | POS App | M3
Story | FEAT-159 Wallet | Covers 59 matrix requirement(s). The system should share all transactions and receipts generated in the system with the external e-invoicing solution. | E06 Retail Operations & POS |  | Medium | 13 | POS App | M4_Phase_4
Task | FEAT-159: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Wallet' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-159 Wallet | Medium | 13 | POS App | M4
Task | FEAT-159: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Wallet' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-159 Wallet | Medium | 8 | POS App | M4
Task | FEAT-159: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Wallet' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-159 Wallet | Medium | 13 | POS App | M4
Task | FEAT-159: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Wallet' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-159 Wallet | Medium | 13 | POS App | M4
Task | FEAT-159: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Wallet' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-159 Wallet | Medium | 8 | POS App | M4
Story | FEAT-160 Upsell And Cross-Sell | Covers 4 matrix requirement(s). The system should allow multi-store retailing where the stores are connected with the inventory information of other stores. This should allow the guests to order items which are out of stock in the c… | E06 Retail Operations & POS |  | High | 5 | POS App | M3_Phase_3
Task | FEAT-160: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Upsell And Cross-Sell' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-160 Upsell And Cross-Sell | High | 1 | POS App | M3
Task | FEAT-160: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Upsell And Cross-Sell' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-160 Upsell And Cross-Sell | High | 1 | POS App | M3
Task | FEAT-160: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Upsell And Cross-Sell' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-160 Upsell And Cross-Sell | High | 1 | POS App | M3
Task | FEAT-160: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Upsell And Cross-Sell' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-160 Upsell And Cross-Sell | High | 1 | POS App | M3
Task | FEAT-160: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Upsell And Cross-Sell' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-160 Upsell And Cross-Sell | High | 1 | POS App | M3
Story | FEAT-161 Authentication And Login | Covers 4 matrix requirement(s). Merchandise Catalog - System shall provide merchandise browsing. | E06 Retail Operations & POS |  | High | 5 | POS App | M3_Phase_3
Task | FEAT-161: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Authentication And Login' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-161 Authentication And Login | High | 1 | POS App | M3
Task | FEAT-161: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Authentication And Login' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-161 Authentication And Login | High | 1 | POS App | M3
Task | FEAT-161: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Authentication And Login' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-161 Authentication And Login | High | 1 | POS App | M3
Task | FEAT-161: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Authentication And Login' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-161 Authentication And Login | High | 1 | POS App | M3
Task | FEAT-161: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Authentication And Login' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-161 Authentication And Login | High | 1 | POS App | M3
Story | FEAT-162 Newsletter And Email Marketing | Covers 3 matrix requirement(s). AI Subject Line Generation AI shall generate and recommend subject lines optimized for open rates, click-through rates, and conversion performance. | E06 Retail Operations & POS |  | Medium | 8 | POS App | M4_Phase_4
Task | FEAT-162: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Newsletter And Email Marketing' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-162 Newsletter And Email Marketing | Medium | 2 | POS App | M4
Task | FEAT-162: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Newsletter And Email Marketing' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-162 Newsletter And Email Marketing | Medium | 1 | POS App | M4
Task | FEAT-162: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Newsletter And Email Marketing' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-162 Newsletter And Email Marketing | Medium | 2 | POS App | M4
Task | FEAT-162: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Newsletter And Email Marketing' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-162 Newsletter And Email Marketing | Medium | 2 | POS App | M4
Task | FEAT-162: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Newsletter And Email Marketing' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-162 Newsletter And Email Marketing | Medium | 1 | POS App | M4
Story | FEAT-163 Inventory Management | Covers 2 matrix requirement(s). SKU Management - System shall support SKU management. | E06 Retail Operations & POS |  | High | 3 | POS App | M3_Phase_3
Task | FEAT-163: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Inventory Management' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-163 Inventory Management | High | 1 | POS App | M3
Task | FEAT-163: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Inventory Management' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-163 Inventory Management | High | 1 | POS App | M3
Task | FEAT-163: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Inventory Management' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-163 Inventory Management | High | 1 | POS App | M3
Task | FEAT-163: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Inventory Management' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-163 Inventory Management | High | 1 | POS App | M3
Task | FEAT-163: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Inventory Management' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-163 Inventory Management | High | 1 | POS App | M3
Story | FEAT-164 Notifications And Messaging | Covers 2 matrix requirement(s). Notification Delivery Tracking System shall track delivery status, failures, retries, opens, clicks, read receipts, engagement metrics, and communication outcomes. | E06 Retail Operations & POS |  | High | 2 | POS App | M3_Phase_3
Task | FEAT-164: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Notifications And Messaging' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-164 Notifications And Messaging | High | 1 | POS App | M3
Task | FEAT-164: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Notifications And Messaging' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-164 Notifications And Messaging | High | 1 | POS App | M3
Task | FEAT-164: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Notifications And Messaging' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-164 Notifications And Messaging | High | 1 | POS App | M3
Task | FEAT-164: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Notifications And Messaging' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-164 Notifications And Messaging | High | 1 | POS App | M3
Task | FEAT-164: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Notifications And Messaging' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-164 Notifications And Messaging | High | 1 | POS App | M3
Story | FEAT-165 Promotions | Covers 1 matrix requirement(s). Cart-level promotions & bundle logic (e.g., “Buy 4 Pay 3”, multi-park family packs) applied automatically at checkout, without new SKUs | E06 Retail Operations & POS |  | High | 3 | POS App | M3_Phase_3
Task | FEAT-165: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Promotions' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-165 Promotions | High | 1 | POS App | M3
Task | FEAT-165: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Promotions' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-165 Promotions | High | 1 | POS App | M3
Task | FEAT-165: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Promotions' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-165 Promotions | High | 1 | POS App | M3
Task | FEAT-165: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Promotions' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-165 Promotions | High | 1 | POS App | M3
Task | FEAT-165: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Promotions' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-165 Promotions | High | 1 | POS App | M3
Story | FEAT-166 Accounting | Covers 1 matrix requirement(s). The system should be able to store account information for each Revenue Account by Item or Item Type (Merchandise, etc.). At minimum, the below fields should be included for storage: - Company I Attra… | E06 Retail Operations & POS |  | High | 3 | POS App | M3_Phase_3
Task | FEAT-166: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Accounting' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-166 Accounting | High | 1 | POS App | M3
Task | FEAT-166: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Accounting' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-166 Accounting | High | 1 | POS App | M3
Task | FEAT-166: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Accounting' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-166 Accounting | High | 1 | POS App | M3
Task | FEAT-166: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Accounting' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-166 Accounting | High | 1 | POS App | M3
Task | FEAT-166: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Accounting' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-166 Accounting | High | 1 | POS App | M3
Story | FEAT-167 Seat Map Import | Covers 1 matrix requirement(s). One-Click Publishing Publish seating map. | E06 Retail Operations & POS |  | High | 3 | POS App | M3_Phase_3
Task | FEAT-167: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Seat Map Import' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-167 Seat Map Import | High | 1 | POS App | M3
Task | FEAT-167: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Seat Map Import' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-167 Seat Map Import | High | 1 | POS App | M3
Task | FEAT-167: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Seat Map Import' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-167 Seat Map Import | High | 1 | POS App | M3
Task | FEAT-167: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Seat Map Import' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-167 Seat Map Import | High | 1 | POS App | M3
Task | FEAT-167: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Seat Map Import' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-167 Seat Map Import | High | 1 | POS App | M3
Story | FEAT-168 Seo Management And Optimization | Covers 1 matrix requirement(s). SEO Analytics Dashboard System shall provide dashboards showing indexed pages, keyword rankings, organic traffic, click-through rates, conversions, search performance, and revenue generated from organ… | E06 Retail Operations & POS |  | High | 1 | POS App | M3_Phase_3
Task | FEAT-168: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Seo Management And Optimization' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-168 Seo Management And Optimization | High | 1 | POS App | M3
Task | FEAT-168: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Seo Management And Optimization' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-168 Seo Management And Optimization | High | 1 | POS App | M3
Task | FEAT-168: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Seo Management And Optimization' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-168 Seo Management And Optimization | High | 1 | POS App | M3
Task | FEAT-168: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Seo Management And Optimization' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-168 Seo Management And Optimization | High | 1 | POS App | M3
Task | FEAT-168: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Seo Management And Optimization' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E06 Retail Operations & POS | FEAT-168 Seo Management And Optimization | High | 1 | POS App | M3
Story | FEAT-169 Inventory Management | Covers 36 matrix requirement(s). Inventory Item Master - System shall support centralized inventory item management. | E07 Inventory & Procurement |  | High | 13 | Server Side / Backend | M3_Phase_3
Task | FEAT-169: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Inventory Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-169 Inventory Management | High | 5 | Server Side / Backend | M3
Task | FEAT-169: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Inventory Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-169 Inventory Management | High | 8 | Server Side / Backend | M3
Task | FEAT-169: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Inventory Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-169 Inventory Management | High | 13 | Server Side / Backend | M3
Task | FEAT-169: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Inventory Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-169 Inventory Management | High | 5 | Server Side / Backend | M3
Task | FEAT-169: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Inventory Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-169 Inventory Management | High | 5 | Server Side / Backend | M3
Story | FEAT-170 Fandb And Retail Offers And Promotions | Covers 26 matrix requirement(s). The system should be able to sync all the products and associated information from the inventory management on real-time or timed intervals, to be able to scan/search for the product and complete the … | E07 Inventory & Procurement |  | High | 13 | Server Side / Backend | M3_Phase_3
Task | FEAT-170: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Fandb And Retail Offers And Promotions' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-170 Fandb And Retail Offers And Promotions | High | 5 | Server Side / Backend | M3
Task | FEAT-170: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Fandb And Retail Offers And Promotions' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-170 Fandb And Retail Offers And Promotions | High | 5 | Server Side / Backend | M3
Task | FEAT-170: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Fandb And Retail Offers And Promotions' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-170 Fandb And Retail Offers And Promotions | High | 8 | Server Side / Backend | M3
Task | FEAT-170: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Fandb And Retail Offers And Promotions' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-170 Fandb And Retail Offers And Promotions | High | 5 | Server Side / Backend | M3
Task | FEAT-170: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Fandb And Retail Offers And Promotions' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-170 Fandb And Retail Offers And Promotions | High | 5 | Server Side / Backend | M3
Story | FEAT-171 Warehouse Management | Covers 22 matrix requirement(s). Warehouse Master - System shall support warehouse master management. | E07 Inventory & Procurement |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-171: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Warehouse Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-171 Warehouse Management | Medium | 3 | Server Side / Backend | M4
Task | FEAT-171: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Warehouse Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-171 Warehouse Management | Medium | 5 | Server Side / Backend | M4
Task | FEAT-171: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Warehouse Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-171 Warehouse Management | Medium | 8 | Server Side / Backend | M4
Task | FEAT-171: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Warehouse Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-171 Warehouse Management | Medium | 3 | Server Side / Backend | M4
Task | FEAT-171: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Warehouse Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-171 Warehouse Management | Medium | 3 | Server Side / Backend | M4
Story | FEAT-172 Procurement | Covers 18 matrix requirement(s). Supplier Master - System shall support supplier management. | E07 Inventory & Procurement |  | High | 13 | Server Side / Backend | M3_Phase_3
Task | FEAT-172: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Procurement' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-172 Procurement | High | 2 | Server Side / Backend | M3
Task | FEAT-172: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Procurement' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-172 Procurement | High | 3 | Server Side / Backend | M3
Task | FEAT-172: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Procurement' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-172 Procurement | High | 3 | Server Side / Backend | M3
Task | FEAT-172: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Procurement' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-172 Procurement | High | 2 | Server Side / Backend | M3
Task | FEAT-172: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Procurement' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-172 Procurement | High | 2 | Server Side / Backend | M3
Story | FEAT-173 Upsell And Cross-Sell | Covers 11 matrix requirement(s). The system should be able to change transaction status to Refunded after the Refund transaction is posted and the same needs to be updated in inventory as well | E07 Inventory & Procurement |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-173: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Upsell And Cross-Sell' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-173 Upsell And Cross-Sell | Medium | 2 | Server Side / Backend | M4
Task | FEAT-173: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Upsell And Cross-Sell' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-173 Upsell And Cross-Sell | Medium | 3 | Server Side / Backend | M4
Task | FEAT-173: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Upsell And Cross-Sell' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-173 Upsell And Cross-Sell | Medium | 5 | Server Side / Backend | M4
Task | FEAT-173: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Upsell And Cross-Sell' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-173 Upsell And Cross-Sell | Medium | 2 | Server Side / Backend | M4
Task | FEAT-173: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Upsell And Cross-Sell' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-173 Upsell And Cross-Sell | Medium | 2 | Server Side / Backend | M4
Story | FEAT-174 Enterprise Features | Covers 11 matrix requirement(s). Tenant-Specific Inventory - System shall support tenant-specific inventory. | E07 Inventory & Procurement |  | High | 8 | Server Side / Backend | M3_Phase_3
Task | FEAT-174: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Enterprise Features' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-174 Enterprise Features | High | 1 | Server Side / Backend | M3
Task | FEAT-174: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Enterprise Features' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-174 Enterprise Features | High | 2 | Server Side / Backend | M3
Task | FEAT-174: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Enterprise Features' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-174 Enterprise Features | High | 3 | Server Side / Backend | M3
Task | FEAT-174: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Enterprise Features' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-174 Enterprise Features | High | 1 | Server Side / Backend | M3
Task | FEAT-174: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Enterprise Features' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-174 Enterprise Features | High | 1 | Server Side / Backend | M3
Story | FEAT-175 Inventory Planning | Covers 9 matrix requirement(s). Inventory Demand Forecasting - System shall forecast inventory demand. | E07 Inventory & Procurement |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-175: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Inventory Planning' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-175 Inventory Planning | Medium | 2 | Server Side / Backend | M4
Task | FEAT-175: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Inventory Planning' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-175 Inventory Planning | Medium | 3 | Server Side / Backend | M4
Task | FEAT-175: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Inventory Planning' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-175 Inventory Planning | Medium | 3 | Server Side / Backend | M4
Task | FEAT-175: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Inventory Planning' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-175 Inventory Planning | Medium | 2 | Server Side / Backend | M4
Task | FEAT-175: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Inventory Planning' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-175 Inventory Planning | Medium | 2 | Server Side / Backend | M4
Story | FEAT-176 Device Inventory | Covers 6 matrix requirement(s). Device Inventory Management - System shall maintain device inventories. | E07 Inventory & Procurement |  | High | 5 | Server Side / Backend | M3_Phase_3
Task | FEAT-176: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Device Inventory' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-176 Device Inventory | High | 1 | Server Side / Backend | M3
Task | FEAT-176: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Device Inventory' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-176 Device Inventory | High | 1 | Server Side / Backend | M3
Task | FEAT-176: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Device Inventory' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-176 Device Inventory | High | 2 | Server Side / Backend | M3
Task | FEAT-176: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Device Inventory' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-176 Device Inventory | High | 1 | Server Side / Backend | M3
Task | FEAT-176: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Device Inventory' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-176 Device Inventory | High | 1 | Server Side / Backend | M3
Story | FEAT-177 Spare Parts And Procurement | Covers 5 matrix requirement(s). Spare Parts Management - System shall support maintenance spare parts management. | E07 Inventory & Procurement |  | High | 8 | Server Side / Backend | M3_Phase_3
Task | FEAT-177: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Spare Parts And Procurement' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-177 Spare Parts And Procurement | High | 2 | Server Side / Backend | M3
Task | FEAT-177: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Spare Parts And Procurement' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-177 Spare Parts And Procurement | High | 2 | Server Side / Backend | M3
Task | FEAT-177: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Spare Parts And Procurement' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-177 Spare Parts And Procurement | High | 3 | Server Side / Backend | M3
Task | FEAT-177: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Spare Parts And Procurement' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-177 Spare Parts And Procurement | High | 2 | Server Side / Backend | M3
Task | FEAT-177: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Spare Parts And Procurement' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-177 Spare Parts And Procurement | High | 2 | Server Side / Backend | M3
Story | FEAT-178 Sales Channels | Covers 4 matrix requirement(s). The system should provide real-time notifications for stock replenishment of wearables/consumables (e.g. receipt roll) in the POS and self-service kiosks. Entry of new stock received should be support… | E07 Inventory & Procurement |  | High | 8 | POS App | M3_Phase_3
Task | FEAT-178: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Sales Channels' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-178 Sales Channels | High | 2 | POS App | M3
Task | FEAT-178: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Sales Channels' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-178 Sales Channels | High | 1 | POS App | M3
Task | FEAT-178: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Sales Channels' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-178 Sales Channels | High | 2 | POS App | M3
Task | FEAT-178: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Sales Channels' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-178 Sales Channels | High | 2 | POS App | M3
Task | FEAT-178: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Sales Channels' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-178 Sales Channels | High | 1 | POS App | M3
Story | FEAT-179 Pricing | Covers 4 matrix requirement(s). Selling Event with a seat map, shared inventory with onsite sales. For non-dated tickets, customers must reserve an entry time after completing the purchase | E07 Inventory & Procurement |  | Medium | 8 | Server Side / Backend | M4_Phase_4
Task | FEAT-179: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Pricing' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-179 Pricing | Medium | 1 | Server Side / Backend | M4
Task | FEAT-179: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Pricing' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-179 Pricing | Medium | 2 | Server Side / Backend | M4
Task | FEAT-179: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Pricing' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-179 Pricing | Medium | 3 | Server Side / Backend | M4
Task | FEAT-179: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Pricing' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-179 Pricing | Medium | 1 | Server Side / Backend | M4
Task | FEAT-179: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Pricing' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-179 Pricing | Medium | 1 | Server Side / Backend | M4
Story | FEAT-180 Inventory And Stock Management | Covers 4 matrix requirement(s). Inventory Lookup - Users shall view inventory availability. | E07 Inventory & Procurement |  | High | 5 | Mobile App | M3_Phase_3
Task | FEAT-180: UI screens (iOS & Android) | Implement shared + platform UI components. Acceptance: 'Inventory And Stock Management' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-180 Inventory And Stock Management | High | 2 | Mobile App | M3
Task | FEAT-180: State & API integration | Data layer, caching and API wiring. Acceptance: 'Inventory And Stock Management' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-180 Inventory And Stock Management | High | 2 | Mobile App | M3
Task | FEAT-180: Offline & push handling | Offline storage, sync and push notifications. Acceptance: 'Inventory And Stock Management' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-180 Inventory And Stock Management | High | 1 | Mobile App | M3
Task | FEAT-180: Mobile E2E tests | Automated tests across iOS/Android. Acceptance: 'Inventory And Stock Management' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-180 Inventory And Stock Management | High | 1 | Mobile App | M3
Story | FEAT-181 Ticket Resale Marketplace | Covers 3 matrix requirement(s). System shall maintain real-time resale inventory and synchronize resale inventory with ticket ownership records. | E07 Inventory & Procurement |  | Medium | 8 | Server Side / Backend | M4_Phase_4
Task | FEAT-181: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ticket Resale Marketplace' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-181 Ticket Resale Marketplace | Medium | 1 | Server Side / Backend | M4
Task | FEAT-181: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ticket Resale Marketplace' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-181 Ticket Resale Marketplace | Medium | 2 | Server Side / Backend | M4
Task | FEAT-181: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ticket Resale Marketplace' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-181 Ticket Resale Marketplace | Medium | 2 | Server Side / Backend | M4
Task | FEAT-181: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ticket Resale Marketplace' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-181 Ticket Resale Marketplace | Medium | 1 | Server Side / Backend | M4
Task | FEAT-181: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ticket Resale Marketplace' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-181 Ticket Resale Marketplace | Medium | 1 | Server Side / Backend | M4
Story | FEAT-182 Ticket Types | Covers 2 matrix requirement(s). System shall support dynamic adjustment of ticket inventory and capacity based on demand forecasts, operational capacity and business rules. | E07 Inventory & Procurement |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-182: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ticket Types' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-182 Ticket Types | Medium | 1 | Server Side / Backend | M4
Task | FEAT-182: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ticket Types' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-182 Ticket Types | Medium | 2 | Server Side / Backend | M4
Task | FEAT-182: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ticket Types' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-182 Ticket Types | Medium | 2 | Server Side / Backend | M4
Task | FEAT-182: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ticket Types' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-182 Ticket Types | Medium | 1 | Server Side / Backend | M4
Task | FEAT-182: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ticket Types' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-182 Ticket Types | Medium | 1 | Server Side / Backend | M4
Story | FEAT-183 Api Business Coverage | Covers 2 matrix requirement(s). APIs shall support ticket creation, modification, cancellation, exchange, upgrade, validation, inventory, availability and pricing operations. | E07 Inventory & Procurement |  | High | 3 | Server Side / Backend | M3_Phase_3
Task | FEAT-183: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Api Business Coverage' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-183 Api Business Coverage | High | 1 | Server Side / Backend | M3
Task | FEAT-183: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Api Business Coverage' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-183 Api Business Coverage | High | 1 | Server Side / Backend | M3
Task | FEAT-183: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Api Business Coverage' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-183 Api Business Coverage | High | 1 | Server Side / Backend | M3
Task | FEAT-183: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Api Business Coverage' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-183 Api Business Coverage | High | 1 | Server Side / Backend | M3
Task | FEAT-183: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Api Business Coverage' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-183 Api Business Coverage | High | 1 | Server Side / Backend | M3
Story | FEAT-184 Resource Management | Covers 1 matrix requirement(s). The system should allow check out & check in feature for rental resources. For example, towels in the water park. Inventory management of these resources should be handled in the system. | E07 Inventory & Procurement |  | High | 3 | Server Side / Backend | M3_Phase_3
Task | FEAT-184: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Resource Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-184 Resource Management | High | 1 | Server Side / Backend | M3
Task | FEAT-184: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Resource Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-184 Resource Management | High | 1 | Server Side / Backend | M3
Task | FEAT-184: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Resource Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-184 Resource Management | High | 1 | Server Side / Backend | M3
Task | FEAT-184: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Resource Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-184 Resource Management | High | 1 | Server Side / Backend | M3
Task | FEAT-184: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Resource Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-184 Resource Management | High | 1 | Server Side / Backend | M3
Story | FEAT-185 Event Management | Covers 1 matrix requirement(s). System shall support sponsor packages, sponsor entitlements, sponsorship inventory and sponsor reporting. | E07 Inventory & Procurement |  | High | 1 | Server Side / Backend | M3_Phase_3
Task | FEAT-185: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Event Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-185 Event Management | High | 1 | Server Side / Backend | M3
Task | FEAT-185: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Event Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-185 Event Management | High | 1 | Server Side / Backend | M3
Task | FEAT-185: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Event Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-185 Event Management | High | 1 | Server Side / Backend | M3
Task | FEAT-185: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Event Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-185 Event Management | High | 1 | Server Side / Backend | M3
Task | FEAT-185: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Event Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-185 Event Management | High | 1 | Server Side / Backend | M3
Story | FEAT-186 Call Center Sales | Covers 1 matrix requirement(s). Selling Event with a seat map, shared inventory with onsite sales. | E07 Inventory & Procurement |  | High | 5 | Server Side / Backend | M3_Phase_3
Task | FEAT-186: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Call Center Sales' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-186 Call Center Sales | High | 1 | Server Side / Backend | M3
Task | FEAT-186: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Call Center Sales' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-186 Call Center Sales | High | 2 | Server Side / Backend | M3
Task | FEAT-186: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Call Center Sales' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-186 Call Center Sales | High | 2 | Server Side / Backend | M3
Task | FEAT-186: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Call Center Sales' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-186 Call Center Sales | High | 1 | Server Side / Backend | M3
Task | FEAT-186: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Call Center Sales' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-186 Call Center Sales | High | 1 | Server Side / Backend | M3
Story | FEAT-187 Ticket Media | Covers 1 matrix requirement(s). The system shall track inventory levels of RFID cards, wristbands, printed tickets, NFC cards, and other physical media across locations and warehouses. | E07 Inventory & Procurement |  | High | 3 | Server Side / Backend | M3_Phase_3
Task | FEAT-187: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ticket Media' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-187 Ticket Media | High | 1 | Server Side / Backend | M3
Task | FEAT-187: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ticket Media' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-187 Ticket Media | High | 1 | Server Side / Backend | M3
Task | FEAT-187: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ticket Media' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-187 Ticket Media | High | 1 | Server Side / Backend | M3
Task | FEAT-187: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ticket Media' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-187 Ticket Media | High | 1 | Server Side / Backend | M3
Task | FEAT-187: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ticket Media' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-187 Ticket Media | High | 1 | Server Side / Backend | M3
Story | FEAT-188 Access Control System | Covers 1 matrix requirement(s). The access control can be operated with the hardware selected by the venue. Hardware includes turnstiles and handheld devices. Any limitation coming from specific hardware must be highlighted and reco… | E07 Inventory & Procurement |  | Medium | 5 | POS App | M4_Phase_4
Task | FEAT-188: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Access Control System' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-188 Access Control System | Medium | 2 | POS App | M4
Task | FEAT-188: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Access Control System' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-188 Access Control System | Medium | 1 | POS App | M4
Task | FEAT-188: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Access Control System' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-188 Access Control System | Medium | 2 | POS App | M4
Task | FEAT-188: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Access Control System' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-188 Access Control System | Medium | 2 | POS App | M4
Task | FEAT-188: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Access Control System' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-188 Access Control System | Medium | 1 | POS App | M4
Story | FEAT-189 Bundles | Covers 1 matrix requirement(s). Each component within a bundle shall maintain independent inventory, capacity, validity period, redemption rules, and availability. The sale of a bundle must validate the availability of all included … | E07 Inventory & Procurement |  | High | 3 | Server Side / Backend | M3_Phase_3
Task | FEAT-189: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Bundles' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-189 Bundles | High | 1 | Server Side / Backend | M3
Task | FEAT-189: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Bundles' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-189 Bundles | High | 1 | Server Side / Backend | M3
Task | FEAT-189: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Bundles' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-189 Bundles | High | 1 | Server Side / Backend | M3
Task | FEAT-189: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Bundles' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-189 Bundles | High | 1 | Server Side / Backend | M3
Task | FEAT-189: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Bundles' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-189 Bundles | High | 1 | Server Side / Backend | M3
Story | FEAT-190 Promotions | Covers 1 matrix requirement(s). Discounts can be under conditions (dynamic discounts): - early birds, - subject to volume (buy one get one, 4 for 3 …), - subject to the type of tickets or - subject to the customer segment. B2B Compa… | E07 Inventory & Procurement |  | High | 1 | Server Side / Backend | M3_Phase_3
Task | FEAT-190: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Promotions' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-190 Promotions | High | 1 | Server Side / Backend | M3
Task | FEAT-190: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Promotions' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-190 Promotions | High | 1 | Server Side / Backend | M3
Task | FEAT-190: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Promotions' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-190 Promotions | High | 1 | Server Side / Backend | M3
Task | FEAT-190: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Promotions' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-190 Promotions | High | 1 | Server Side / Backend | M3
Task | FEAT-190: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Promotions' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-190 Promotions | High | 1 | Server Side / Backend | M3
Story | FEAT-191 Wallet | Covers 1 matrix requirement(s). The system should be able to extract a report for: 1.Number of repeated visits by Passes 2.Ticketed Footfall( including demographic) 3.Monthly Inventory Consumptions in Units | E07 Inventory & Procurement |  | High | 1 | POS App | M3_Phase_3
Task | FEAT-191: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Wallet' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-191 Wallet | High | 1 | POS App | M3
Task | FEAT-191: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Wallet' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-191 Wallet | High | 1 | POS App | M3
Task | FEAT-191: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Wallet' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-191 Wallet | High | 1 | POS App | M3
Task | FEAT-191: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Wallet' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-191 Wallet | High | 1 | POS App | M3
Task | FEAT-191: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Wallet' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-191 Wallet | High | 1 | POS App | M3
Story | FEAT-192 Dynamic Pricing | Covers 1 matrix requirement(s). System shall support inventory-based pricing. | E07 Inventory & Procurement |  | High | 3 | Server Side / Backend | M3_Phase_3
Task | FEAT-192: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Dynamic Pricing' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-192 Dynamic Pricing | High | 1 | Server Side / Backend | M3
Task | FEAT-192: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Dynamic Pricing' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-192 Dynamic Pricing | High | 1 | Server Side / Backend | M3
Task | FEAT-192: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Dynamic Pricing' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-192 Dynamic Pricing | High | 1 | Server Side / Backend | M3
Task | FEAT-192: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Dynamic Pricing' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-192 Dynamic Pricing | High | 1 | Server Side / Backend | M3
Task | FEAT-192: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Dynamic Pricing' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-192 Dynamic Pricing | High | 1 | Server Side / Backend | M3
Story | FEAT-193 Game And Ride Payment And Redemption | Covers 1 matrix requirement(s). The system should allow usage of redemption tickets credits in the digital wallet at redemption counter for prizes. Prizes on redemption counter, skill games, direct pay machines (e.g. cranes) should … | E07 Inventory & Procurement |  | High | 3 | Server Side / Backend | M3_Phase_3
Task | FEAT-193: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Game And Ride Payment And Redemption' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-193 Game And Ride Payment And Redemption | High | 1 | Server Side / Backend | M3
Task | FEAT-193: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Game And Ride Payment And Redemption' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-193 Game And Ride Payment And Redemption | High | 1 | Server Side / Backend | M3
Task | FEAT-193: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Game And Ride Payment And Redemption' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-193 Game And Ride Payment And Redemption | High | 1 | Server Side / Backend | M3
Task | FEAT-193: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Game And Ride Payment And Redemption' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-193 Game And Ride Payment And Redemption | High | 1 | Server Side / Backend | M3
Task | FEAT-193: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Game And Ride Payment And Redemption' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-193 Game And Ride Payment And Redemption | High | 1 | Server Side / Backend | M3
Story | FEAT-194 Seat Revenue Management And Forecasting | Covers 1 matrix requirement(s). Seat Inventory Forecasting System shall support seat inventory forecasting. | E07 Inventory & Procurement |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-194: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Seat Revenue Management And Forecasting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-194 Seat Revenue Management And Forecasting | Medium | 1 | Server Side / Backend | M4
Task | FEAT-194: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Seat Revenue Management And Forecasting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-194 Seat Revenue Management And Forecasting | Medium | 2 | Server Side / Backend | M4
Task | FEAT-194: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Seat Revenue Management And Forecasting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-194 Seat Revenue Management And Forecasting | Medium | 2 | Server Side / Backend | M4
Task | FEAT-194: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Seat Revenue Management And Forecasting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-194 Seat Revenue Management And Forecasting | Medium | 1 | Server Side / Backend | M4
Task | FEAT-194: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Seat Revenue Management And Forecasting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-194 Seat Revenue Management And Forecasting | Medium | 1 | Server Side / Backend | M4
Story | FEAT-195 Seat Reporting And Analytics | Covers 1 matrix requirement(s). Hold Inventory Reporting System shall support hold inventory reporting. | E07 Inventory & Procurement |  | High | 1 | Server Side / Backend | M3_Phase_3
Task | FEAT-195: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Seat Reporting And Analytics' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-195 Seat Reporting And Analytics | High | 1 | Server Side / Backend | M3
Task | FEAT-195: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Seat Reporting And Analytics' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-195 Seat Reporting And Analytics | High | 1 | Server Side / Backend | M3
Task | FEAT-195: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Seat Reporting And Analytics' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-195 Seat Reporting And Analytics | High | 1 | Server Side / Backend | M3
Task | FEAT-195: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Seat Reporting And Analytics' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-195 Seat Reporting And Analytics | High | 1 | Server Side / Backend | M3
Task | FEAT-195: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Seat Reporting And Analytics' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-195 Seat Reporting And Analytics | High | 1 | Server Side / Backend | M3
Story | FEAT-196 Campaign Management | Covers 1 matrix requirement(s). Ticketing Campaigns System shall support campaigns specifically for ticket sales, events, attractions, seat inventory promotions, capacity-driven offers, and last-minute sales. | E07 Inventory & Procurement |  | High | 3 | Server Side / Backend | M3_Phase_3
Task | FEAT-196: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Campaign Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-196 Campaign Management | High | 1 | Server Side / Backend | M3
Task | FEAT-196: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Campaign Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-196 Campaign Management | High | 1 | Server Side / Backend | M3
Task | FEAT-196: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Campaign Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-196 Campaign Management | High | 1 | Server Side / Backend | M3
Task | FEAT-196: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Campaign Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-196 Campaign Management | High | 1 | Server Side / Backend | M3
Task | FEAT-196: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Campaign Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E07 Inventory & Procurement | FEAT-196 Campaign Management | High | 1 | Server Side / Backend | M3
Story | FEAT-197 Case Management And Sla | Covers 17 matrix requirement(s). Case Classification System shall support configurable case categories, subcategories, priorities, severity levels, service types, business units, venues, attractions, and departments. | E08 CRM, Marketing & Loyalty |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-197: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Case Management And Sla' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-197 Case Management And Sla | Medium | 3 | Server Side / Backend | M4
Task | FEAT-197: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Case Management And Sla' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-197 Case Management And Sla | Medium | 5 | Server Side / Backend | M4
Task | FEAT-197: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Case Management And Sla' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-197 Case Management And Sla | Medium | 5 | Server Side / Backend | M4
Task | FEAT-197: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Case Management And Sla' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-197 Case Management And Sla | Medium | 3 | Server Side / Backend | M4
Task | FEAT-197: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Case Management And Sla' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-197 Case Management And Sla | Medium | 3 | Server Side / Backend | M4
Story | FEAT-198 Consent Management | Covers 14 matrix requirement(s). Consent Management Framework System shall provide a centralized framework for collecting, managing, validating, and enforcing guest consent across all modules and communication channels. | E08 CRM, Marketing & Loyalty |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-198: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Consent Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-198 Consent Management | Medium | 3 | Server Side / Backend | M4
Task | FEAT-198: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Consent Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-198 Consent Management | Medium | 3 | Server Side / Backend | M4
Task | FEAT-198: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Consent Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-198 Consent Management | Medium | 5 | Server Side / Backend | M4
Task | FEAT-198: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Consent Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-198 Consent Management | Medium | 3 | Server Side / Backend | M4
Task | FEAT-198: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Consent Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-198 Consent Management | Medium | 3 | Server Side / Backend | M4
Story | FEAT-199 Marketing | Covers 13 matrix requirement(s). Multi-Site CMS System shall support creation and management of multiple websites, portals, mobile app experiences, microsites, and landing pages from a single centralized CMS platform. | E08 CRM, Marketing & Loyalty |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-199: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Marketing' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-199 Marketing | Medium | 3 | Server Side / Backend | M4
Task | FEAT-199: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Marketing' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-199 Marketing | Medium | 3 | Server Side / Backend | M4
Task | FEAT-199: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Marketing' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-199 Marketing | Medium | 5 | Server Side / Backend | M4
Task | FEAT-199: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Marketing' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-199 Marketing | Medium | 3 | Server Side / Backend | M4
Task | FEAT-199: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Marketing' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-199 Marketing | Medium | 3 | Server Side / Backend | M4
Story | FEAT-200 Surveys And Feedback | Covers 12 matrix requirement(s). Multi-Format Questions Surveys shall support multiple question types including single choice, multiple choice, rating scales, NPS scores, text responses, rankings, matrices, images, file uploads, and … | E08 CRM, Marketing & Loyalty |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-200: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Surveys And Feedback' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-200 Surveys And Feedback | Medium | 2 | Server Side / Backend | M4
Task | FEAT-200: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Surveys And Feedback' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-200 Surveys And Feedback | Medium | 3 | Server Side / Backend | M4
Task | FEAT-200: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Surveys And Feedback' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-200 Surveys And Feedback | Medium | 5 | Server Side / Backend | M4
Task | FEAT-200: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Surveys And Feedback' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-200 Surveys And Feedback | Medium | 2 | Server Side / Backend | M4
Task | FEAT-200: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Surveys And Feedback' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-200 Surveys And Feedback | Medium | 2 | Server Side / Backend | M4
Story | FEAT-201 Omnichannel Communications And Ai Chatbot | Covers 12 matrix requirement(s). Omnichannel Inbox System shall provide a centralized inbox for managing guest conversations from WhatsApp, Web Chat, Mobile App Chat, Facebook Messenger, Instagram, Email, SMS, and future supported ch… | E08 CRM, Marketing & Loyalty |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-201: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Omnichannel Communications And Ai Chatbot' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-201 Omnichannel Communications And Ai Chatbot | Medium | 2 | Server Side / Backend | M4
Task | FEAT-201: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Omnichannel Communications And Ai Chatbot' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-201 Omnichannel Communications And Ai Chatbot | Medium | 3 | Server Side / Backend | M4
Task | FEAT-201: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Omnichannel Communications And Ai Chatbot' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-201 Omnichannel Communications And Ai Chatbot | Medium | 5 | Server Side / Backend | M4
Task | FEAT-201: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Omnichannel Communications And Ai Chatbot' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-201 Omnichannel Communications And Ai Chatbot | Medium | 2 | Server Side / Backend | M4
Task | FEAT-201: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Omnichannel Communications And Ai Chatbot' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-201 Omnichannel Communications And Ai Chatbot | Medium | 2 | Server Side / Backend | M4
Story | FEAT-202 Audience Segmentation | Covers 12 matrix requirement(s). Static Segments System shall support manually maintained static segments for operational, marketing, and reporting purposes. | E08 CRM, Marketing & Loyalty |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-202: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Audience Segmentation' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-202 Audience Segmentation | Medium | 2 | Server Side / Backend | M4
Task | FEAT-202: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Audience Segmentation' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-202 Audience Segmentation | Medium | 3 | Server Side / Backend | M4
Task | FEAT-202: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Audience Segmentation' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-202 Audience Segmentation | Medium | 5 | Server Side / Backend | M4
Task | FEAT-202: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Audience Segmentation' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-202 Audience Segmentation | Medium | 2 | Server Side / Backend | M4
Task | FEAT-202: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Audience Segmentation' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-202 Audience Segmentation | Medium | 2 | Server Side / Backend | M4
Story | FEAT-203 Loyalty | Covers 11 matrix requirement(s). The system should have the ability to integrate and exchange client information with a loyalty point system which will manage the loyalty points credited on to the loyalty account as per the offerings… | E08 CRM, Marketing & Loyalty |  | High | 13 | Server Side / Backend | M3_Phase_3
Task | FEAT-203: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Loyalty' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-203 Loyalty | High | 2 | Server Side / Backend | M3
Task | FEAT-203: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Loyalty' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-203 Loyalty | High | 3 | Server Side / Backend | M3
Task | FEAT-203: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Loyalty' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-203 Loyalty | High | 5 | Server Side / Backend | M3
Task | FEAT-203: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Loyalty' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-203 Loyalty | High | 2 | Server Side / Backend | M3
Task | FEAT-203: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Loyalty' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-203 Loyalty | High | 2 | Server Side / Backend | M3
Story | FEAT-204 Reviews And Ratings | Covers 11 matrix requirement(s). Configurable Rating Framework System shall support configurable rating scales including 5-star ratings, NPS scores, satisfaction ratings, thumbs-up/down, custom scoring models, and category-based rati… | E08 CRM, Marketing & Loyalty |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-204: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Reviews And Ratings' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-204 Reviews And Ratings | Medium | 2 | Server Side / Backend | M4
Task | FEAT-204: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Reviews And Ratings' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-204 Reviews And Ratings | Medium | 3 | Server Side / Backend | M4
Task | FEAT-204: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Reviews And Ratings' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-204 Reviews And Ratings | Medium | 5 | Server Side / Backend | M4
Task | FEAT-204: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Reviews And Ratings' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-204 Reviews And Ratings | Medium | 2 | Server Side / Backend | M4
Task | FEAT-204: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Reviews And Ratings' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-204 Reviews And Ratings | Medium | 2 | Server Side / Backend | M4
Story | FEAT-205 Notifications And Messaging | Covers 11 matrix requirement(s). Notification Template Management System shall provide centralized management of notification templates for email, SMS, WhatsApp, push notifications, mobile app notifications, web notifications, and fu… | E08 CRM, Marketing & Loyalty |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-205: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Notifications And Messaging' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-205 Notifications And Messaging | Medium | 2 | Server Side / Backend | M4
Task | FEAT-205: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Notifications And Messaging' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-205 Notifications And Messaging | Medium | 3 | Server Side / Backend | M4
Task | FEAT-205: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Notifications And Messaging' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-205 Notifications And Messaging | Medium | 5 | Server Side / Backend | M4
Task | FEAT-205: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Notifications And Messaging' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-205 Notifications And Messaging | Medium | 2 | Server Side / Backend | M4
Task | FEAT-205: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Notifications And Messaging' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-205 Notifications And Messaging | Medium | 2 | Server Side / Backend | M4
Story | FEAT-206 Guest Profiles And Data Management | Covers 9 matrix requirement(s). Guest Master Record System shall automatically create and maintain a master guest record that serves as the primary source of truth for all guest-related information across the platform. | E08 CRM, Marketing & Loyalty |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-206: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Guest Profiles And Data Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-206 Guest Profiles And Data Management | Medium | 2 | Server Side / Backend | M4
Task | FEAT-206: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Guest Profiles And Data Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-206 Guest Profiles And Data Management | Medium | 3 | Server Side / Backend | M4
Task | FEAT-206: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Guest Profiles And Data Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-206 Guest Profiles And Data Management | Medium | 3 | Server Side / Backend | M4
Task | FEAT-206: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Guest Profiles And Data Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-206 Guest Profiles And Data Management | Medium | 2 | Server Side / Backend | M4
Task | FEAT-206: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Guest Profiles And Data Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-206 Guest Profiles And Data Management | Medium | 2 | Server Side / Backend | M4
Story | FEAT-207 Newsletter And Email Marketing | Covers 7 matrix requirement(s). Subscription Management Guests shall be able to subscribe, unsubscribe, manage preferences, select communication categories, and update consent settings through self-service preference centers. | E08 CRM, Marketing & Loyalty |  | Medium | 8 | Server Side / Backend | M4_Phase_4
Task | FEAT-207: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Newsletter And Email Marketing' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-207 Newsletter And Email Marketing | Medium | 2 | Server Side / Backend | M4
Task | FEAT-207: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Newsletter And Email Marketing' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-207 Newsletter And Email Marketing | Medium | 3 | Server Side / Backend | M4
Task | FEAT-207: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Newsletter And Email Marketing' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-207 Newsletter And Email Marketing | Medium | 3 | Server Side / Backend | M4
Task | FEAT-207: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Newsletter And Email Marketing' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-207 Newsletter And Email Marketing | Medium | 2 | Server Side / Backend | M4
Task | FEAT-207: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Newsletter And Email Marketing' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-207 Newsletter And Email Marketing | Medium | 2 | Server Side / Backend | M4
Story | FEAT-208 Campaign Management | Covers 6 matrix requirement(s). Campaign Creation System shall allow authorized users to create marketing campaigns across email, SMS, WhatsApp, push notifications, mobile app, website banners, social media integrations, and third-p… | E08 CRM, Marketing & Loyalty |  | Medium | 8 | Server Side / Backend | M4_Phase_4
Task | FEAT-208: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Campaign Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-208 Campaign Management | Medium | 2 | Server Side / Backend | M4
Task | FEAT-208: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Campaign Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-208 Campaign Management | Medium | 2 | Server Side / Backend | M4
Task | FEAT-208: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Campaign Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-208 Campaign Management | Medium | 3 | Server Side / Backend | M4
Task | FEAT-208: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Campaign Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-208 Campaign Management | Medium | 2 | Server Side / Backend | M4
Task | FEAT-208: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Campaign Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-208 Campaign Management | Medium | 2 | Server Side / Backend | M4
Story | FEAT-209 Gamification And Loyalty | Covers 6 matrix requirement(s). Family Challenges System shall support family-based challenges where multiple linked family members can contribute toward shared goals, rewards, achievements, and engagement activities. | E08 CRM, Marketing & Loyalty |  | Medium | 8 | Server Side / Backend | M4_Phase_4
Task | FEAT-209: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Gamification And Loyalty' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-209 Gamification And Loyalty | Medium | 2 | Server Side / Backend | M4
Task | FEAT-209: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Gamification And Loyalty' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-209 Gamification And Loyalty | Medium | 2 | Server Side / Backend | M4
Task | FEAT-209: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Gamification And Loyalty' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-209 Gamification And Loyalty | Medium | 3 | Server Side / Backend | M4
Task | FEAT-209: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Gamification And Loyalty' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-209 Gamification And Loyalty | Medium | 2 | Server Side / Backend | M4
Task | FEAT-209: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Gamification And Loyalty' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-209 Gamification And Loyalty | Medium | 2 | Server Side / Backend | M4
Story | FEAT-210 Seo Management And Optimization | Covers 6 matrix requirement(s). AI SEO Optimization AI shall recommend SEO titles, descriptions, keywords, content improvements, internal linking opportunities, and search ranking enhancements based on page content and search trends… | E08 CRM, Marketing & Loyalty |  | Medium | 8 | Server Side / Backend | M4_Phase_4
Task | FEAT-210: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Seo Management And Optimization' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-210 Seo Management And Optimization | Medium | 2 | Server Side / Backend | M4
Task | FEAT-210: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Seo Management And Optimization' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-210 Seo Management And Optimization | Medium | 2 | Server Side / Backend | M4
Task | FEAT-210: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Seo Management And Optimization' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-210 Seo Management And Optimization | Medium | 3 | Server Side / Backend | M4
Task | FEAT-210: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Seo Management And Optimization' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-210 Seo Management And Optimization | Medium | 2 | Server Side / Backend | M4
Task | FEAT-210: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Seo Management And Optimization' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-210 Seo Management And Optimization | Medium | 2 | Server Side / Backend | M4
Story | FEAT-211 Recommendation Engine | Covers 3 matrix requirement(s). System shall provide email campaign recommendations. | E08 CRM, Marketing & Loyalty |  | Medium | 8 | Server Side / Backend | M4_Phase_4
Task | FEAT-211: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Recommendation Engine' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-211 Recommendation Engine | Medium | 1 | Server Side / Backend | M4
Task | FEAT-211: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Recommendation Engine' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-211 Recommendation Engine | Medium | 2 | Server Side / Backend | M4
Task | FEAT-211: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Recommendation Engine' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-211 Recommendation Engine | Medium | 2 | Server Side / Backend | M4
Task | FEAT-211: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Recommendation Engine' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-211 Recommendation Engine | Medium | 1 | Server Side / Backend | M4
Task | FEAT-211: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Recommendation Engine' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-211 Recommendation Engine | Medium | 1 | Server Side / Backend | M4
Story | FEAT-212 Bi And Reporting | Covers 3 matrix requirement(s). System shall provide marketing dashboards. | E08 CRM, Marketing & Loyalty |  | High | 8 | Server Side / Backend | M3_Phase_3
Task | FEAT-212: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Bi And Reporting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-212 Bi And Reporting | High | 1 | Server Side / Backend | M3
Task | FEAT-212: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Bi And Reporting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-212 Bi And Reporting | High | 2 | Server Side / Backend | M3
Task | FEAT-212: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Bi And Reporting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-212 Bi And Reporting | High | 2 | Server Side / Backend | M3
Task | FEAT-212: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Bi And Reporting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-212 Bi And Reporting | High | 1 | Server Side / Backend | M3
Task | FEAT-212: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Bi And Reporting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-212 Bi And Reporting | High | 1 | Server Side / Backend | M3
Story | FEAT-213 Authentication And Login | Covers 3 matrix requirement(s). Loyalty Balance - System shall display loyalty balances. | E08 CRM, Marketing & Loyalty |  | High | 2 | Mobile App | M3_Phase_3
Task | FEAT-213: UI screens (iOS & Android) | Implement shared + platform UI components. Acceptance: 'Authentication And Login' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-213 Authentication And Login | High | 1 | Mobile App | M3
Task | FEAT-213: State & API integration | Data layer, caching and API wiring. Acceptance: 'Authentication And Login' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-213 Authentication And Login | High | 1 | Mobile App | M3
Task | FEAT-213: Offline & push handling | Offline storage, sync and push notifications. Acceptance: 'Authentication And Login' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-213 Authentication And Login | High | 1 | Mobile App | M3
Task | FEAT-213: Mobile E2E tests | Automated tests across iOS/Android. Acceptance: 'Authentication And Login' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-213 Authentication And Login | High | 1 | Mobile App | M3
Story | FEAT-214 Profile Management | Covers 2 matrix requirement(s). Maintain auditable consent records for Email, SMS, WhatsApp, Push Notifications, Marketing Communications, Privacy Policies, Terms & Conditions, and GDPR compliance. | E08 CRM, Marketing & Loyalty |  | High | 2 | Server Side / Backend | M3_Phase_3
Task | FEAT-214: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Profile Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-214 Profile Management | High | 1 | Server Side / Backend | M3
Task | FEAT-214: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Profile Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-214 Profile Management | High | 1 | Server Side / Backend | M3
Task | FEAT-214: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Profile Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-214 Profile Management | High | 1 | Server Side / Backend | M3
Task | FEAT-214: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Profile Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-214 Profile Management | High | 1 | Server Side / Backend | M3
Task | FEAT-214: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Profile Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-214 Profile Management | High | 1 | Server Side / Backend | M3
Story | FEAT-215 Api Business Coverage | Covers 2 matrix requirement(s). APIs shall support point accrual, point redemption, balance inquiry, loyalty tier management and rewards retrieval. | E08 CRM, Marketing & Loyalty |  | High | 3 | Server Side / Backend | M3_Phase_3
Task | FEAT-215: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Api Business Coverage' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-215 Api Business Coverage | High | 1 | Server Side / Backend | M3
Task | FEAT-215: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Api Business Coverage' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-215 Api Business Coverage | High | 1 | Server Side / Backend | M3
Task | FEAT-215: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Api Business Coverage' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-215 Api Business Coverage | High | 1 | Server Side / Backend | M3
Task | FEAT-215: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Api Business Coverage' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-215 Api Business Coverage | High | 1 | Server Side / Backend | M3
Task | FEAT-215: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Api Business Coverage' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-215 Api Business Coverage | High | 1 | Server Side / Backend | M3
Story | FEAT-216 Demand Forecasting | Covers 1 matrix requirement(s). System shall forecast revenue by customer segment. | E08 CRM, Marketing & Loyalty |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-216: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Demand Forecasting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-216 Demand Forecasting | Medium | 1 | Server Side / Backend | M4
Task | FEAT-216: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Demand Forecasting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-216 Demand Forecasting | Medium | 2 | Server Side / Backend | M4
Task | FEAT-216: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Demand Forecasting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-216 Demand Forecasting | Medium | 2 | Server Side / Backend | M4
Task | FEAT-216: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Demand Forecasting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-216 Demand Forecasting | Medium | 1 | Server Side / Backend | M4
Task | FEAT-216: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Demand Forecasting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-216 Demand Forecasting | Medium | 1 | Server Side / Backend | M4
Story | FEAT-217 Fraud Detection | Covers 1 matrix requirement(s). System shall support fraud case management. | E08 CRM, Marketing & Loyalty |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-217: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Fraud Detection' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-217 Fraud Detection | Medium | 1 | Server Side / Backend | M4
Task | FEAT-217: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Fraud Detection' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-217 Fraud Detection | Medium | 2 | Server Side / Backend | M4
Task | FEAT-217: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Fraud Detection' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-217 Fraud Detection | Medium | 2 | Server Side / Backend | M4
Task | FEAT-217: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Fraud Detection' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-217 Fraud Detection | Medium | 1 | Server Side / Backend | M4
Task | FEAT-217: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Fraud Detection' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-217 Fraud Detection | Medium | 1 | Server Side / Backend | M4
Story | FEAT-218 Operations Command Center | Covers 1 matrix requirement(s). System shall provide real-time visibility of incidents, hazards, complaints, emergencies, and operational disruptions. | E08 CRM, Marketing & Loyalty |  | High | 5 | Server Side / Backend | M3_Phase_3
Task | FEAT-218: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Operations Command Center' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-218 Operations Command Center | High | 1 | Server Side / Backend | M3
Task | FEAT-218: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Operations Command Center' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-218 Operations Command Center | High | 2 | Server Side / Backend | M3
Task | FEAT-218: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Operations Command Center' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-218 Operations Command Center | High | 2 | Server Side / Backend | M3
Task | FEAT-218: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Operations Command Center' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-218 Operations Command Center | High | 1 | Server Side / Backend | M3
Task | FEAT-218: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Operations Command Center' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E08 CRM, Marketing & Loyalty | FEAT-218 Operations Command Center | High | 1 | Server Side / Backend | M3
Story | FEAT-219 Ticket Types | Covers 19 matrix requirement(s). The system should be able to sell membership passes for an attraction (e.g. annual pass, monthly pass) for configurable duration. | E09 Membership & Subscriptions |  | High | 13 | Server Side / Backend | M3_Phase_3
Task | FEAT-219: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ticket Types' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-219 Ticket Types | High | 2 | Server Side / Backend | M3
Task | FEAT-219: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ticket Types' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-219 Ticket Types | High | 3 | Server Side / Backend | M3
Task | FEAT-219: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ticket Types' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-219 Ticket Types | High | 3 | Server Side / Backend | M3
Task | FEAT-219: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ticket Types' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-219 Ticket Types | High | 2 | Server Side / Backend | M3
Task | FEAT-219: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ticket Types' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-219 Ticket Types | High | 2 | Server Side / Backend | M3
Story | FEAT-220 Membership | Covers 14 matrix requirement(s). For all sales at POS, it is possible to have an offline mode. | E09 Membership & Subscriptions |  | High | 13 | Server Side / Backend | M3_Phase_3
Task | FEAT-220: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Membership' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-220 Membership | High | 3 | Server Side / Backend | M3
Task | FEAT-220: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Membership' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-220 Membership | High | 3 | Server Side / Backend | M3
Task | FEAT-220: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Membership' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-220 Membership | High | 5 | Server Side / Backend | M3
Task | FEAT-220: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Membership' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-220 Membership | High | 3 | Server Side / Backend | M3
Task | FEAT-220: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Membership' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-220 Membership | High | 3 | Server Side / Backend | M3
Story | FEAT-221 Portfolio And Entitlement Management | Covers 11 matrix requirement(s). Support purchase, ownership, management, and consumption of multiple tickets, passes, memberships, and entitlements under a single portfolio. | E09 Membership & Subscriptions |  | High | 8 | Server Side / Backend | M3_Phase_3
Task | FEAT-221: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Portfolio And Entitlement Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-221 Portfolio And Entitlement Management | High | 1 | Server Side / Backend | M3
Task | FEAT-221: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Portfolio And Entitlement Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-221 Portfolio And Entitlement Management | High | 2 | Server Side / Backend | M3
Task | FEAT-221: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Portfolio And Entitlement Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-221 Portfolio And Entitlement Management | High | 3 | Server Side / Backend | M3
Task | FEAT-221: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Portfolio And Entitlement Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-221 Portfolio And Entitlement Management | High | 1 | Server Side / Backend | M3
Task | FEAT-221: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Portfolio And Entitlement Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-221 Portfolio And Entitlement Management | High | 1 | Server Side / Backend | M3
Story | FEAT-222 Guest Profiles And Data Management | Covers 9 matrix requirement(s). Household & Family Relationships System shall support linking family members, dependents, guardians, spouses, and household relationships while maintaining individual profiles and permissions. | E09 Membership & Subscriptions |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-222: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Guest Profiles And Data Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-222 Guest Profiles And Data Management | Medium | 2 | Server Side / Backend | M4
Task | FEAT-222: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Guest Profiles And Data Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-222 Guest Profiles And Data Management | Medium | 3 | Server Side / Backend | M4
Task | FEAT-222: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Guest Profiles And Data Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-222 Guest Profiles And Data Management | Medium | 3 | Server Side / Backend | M4
Task | FEAT-222: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Guest Profiles And Data Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-222 Guest Profiles And Data Management | Medium | 2 | Server Side / Backend | M4
Task | FEAT-222: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Guest Profiles And Data Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-222 Guest Profiles And Data Management | Medium | 2 | Server Side / Backend | M4
Story | FEAT-223 License Enforcement And Renewal | Covers 8 matrix requirement(s). License Generation - System shall generate subscription licenses. | E09 Membership & Subscriptions |  | High | 5 | Server Side / Backend | M3_Phase_3
Task | FEAT-223: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'License Enforcement And Renewal' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-223 License Enforcement And Renewal | High | 1 | Server Side / Backend | M3
Task | FEAT-223: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'License Enforcement And Renewal' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-223 License Enforcement And Renewal | High | 2 | Server Side / Backend | M3
Task | FEAT-223: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'License Enforcement And Renewal' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-223 License Enforcement And Renewal | High | 2 | Server Side / Backend | M3
Task | FEAT-223: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'License Enforcement And Renewal' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-223 License Enforcement And Renewal | High | 1 | Server Side / Backend | M3
Task | FEAT-223: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'License Enforcement And Renewal' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-223 License Enforcement And Renewal | High | 1 | Server Side / Backend | M3
Story | FEAT-224 Digital Waivers And Signature Management | Covers 8 matrix requirement(s). Multi-Activity Waivers System shall support different waiver templates for different attractions, events, activities, memberships, venues, products, and risk categories. | E09 Membership & Subscriptions |  | High | 13 | Server Side / Backend | M3_Phase_3
Task | FEAT-224: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Digital Waivers And Signature Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-224 Digital Waivers And Signature Management | High | 2 | Server Side / Backend | M3
Task | FEAT-224: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Digital Waivers And Signature Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-224 Digital Waivers And Signature Management | High | 3 | Server Side / Backend | M3
Task | FEAT-224: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Digital Waivers And Signature Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-224 Digital Waivers And Signature Management | High | 3 | Server Side / Backend | M3
Task | FEAT-224: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Digital Waivers And Signature Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-224 Digital Waivers And Signature Management | High | 2 | Server Side / Backend | M3
Task | FEAT-224: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Digital Waivers And Signature Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-224 Digital Waivers And Signature Management | High | 2 | Server Side / Backend | M3
Story | FEAT-225 Loyalty | Covers 7 matrix requirement(s). Support configurable loyalty tiers and progression rules. System shall support configurable loyalty tiers such as Bronze, Silver, Gold, Platinum, VIP, or client-defined tiers. Tier progression shall b… | E09 Membership & Subscriptions |  | Medium | 8 | Server Side / Backend | M4_Phase_4
Task | FEAT-225: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Loyalty' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-225 Loyalty | Medium | 2 | Server Side / Backend | M4
Task | FEAT-225: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Loyalty' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-225 Loyalty | Medium | 3 | Server Side / Backend | M4
Task | FEAT-225: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Loyalty' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-225 Loyalty | Medium | 3 | Server Side / Backend | M4
Task | FEAT-225: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Loyalty' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-225 Loyalty | Medium | 2 | Server Side / Backend | M4
Task | FEAT-225: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Loyalty' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-225 Loyalty | Medium | 2 | Server Side / Backend | M4
Story | FEAT-226 Authentication And Login | Covers 6 matrix requirement(s). Membership Purchase - System shall support membership purchases. | E09 Membership & Subscriptions |  | High | 5 | Mobile App | M3_Phase_3
Task | FEAT-226: UI screens (iOS & Android) | Implement shared + platform UI components. Acceptance: 'Authentication And Login' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-226 Authentication And Login | High | 2 | Mobile App | M3
Task | FEAT-226: State & API integration | Data layer, caching and API wiring. Acceptance: 'Authentication And Login' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-226 Authentication And Login | High | 2 | Mobile App | M3
Task | FEAT-226: Offline & push handling | Offline storage, sync and push notifications. Acceptance: 'Authentication And Login' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-226 Authentication And Login | High | 1 | Mobile App | M3
Task | FEAT-226: Mobile E2E tests | Automated tests across iOS/Android. Acceptance: 'Authentication And Login' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-226 Authentication And Login | High | 1 | Mobile App | M3
Story | FEAT-227 Gamification And Loyalty | Covers 6 matrix requirement(s). Challenge Management System shall allow administrators to create configurable challenges, missions, quests, activities, and engagement campaigns based on visits, purchases, attendance, loyalty actions… | E09 Membership & Subscriptions |  | High | 8 | Server Side / Backend | M3_Phase_3
Task | FEAT-227: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Gamification And Loyalty' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-227 Gamification And Loyalty | High | 2 | Server Side / Backend | M3
Task | FEAT-227: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Gamification And Loyalty' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-227 Gamification And Loyalty | High | 2 | Server Side / Backend | M3
Task | FEAT-227: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Gamification And Loyalty' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-227 Gamification And Loyalty | High | 3 | Server Side / Backend | M3
Task | FEAT-227: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Gamification And Loyalty' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-227 Gamification And Loyalty | High | 2 | Server Side / Backend | M3
Task | FEAT-227: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Gamification And Loyalty' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-227 Gamification And Loyalty | High | 2 | Server Side / Backend | M3
Story | FEAT-228 Digital Waiver Management | Covers 5 matrix requirement(s). The system should allow definition of a transaction fee as a fixed value or a percentage based value dependent on the ticket price. | E09 Membership & Subscriptions |  | High | 5 | Server Side / Backend | M3_Phase_3
Task | FEAT-228: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Digital Waiver Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-228 Digital Waiver Management | High | 1 | Server Side / Backend | M3
Task | FEAT-228: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Digital Waiver Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-228 Digital Waiver Management | High | 1 | Server Side / Backend | M3
Task | FEAT-228: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Digital Waiver Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-228 Digital Waiver Management | High | 2 | Server Side / Backend | M3
Task | FEAT-228: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Digital Waiver Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-228 Digital Waiver Management | High | 1 | Server Side / Backend | M3
Task | FEAT-228: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Digital Waiver Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-228 Digital Waiver Management | High | 1 | Server Side / Backend | M3
Story | FEAT-229 Access Control System | Covers 5 matrix requirement(s). The system should be able to validate tickets and membership passes with different rules based on entitlements, manage black and white list of tickets. Upon a scanning a valid ticket, the system shoul… | E09 Membership & Subscriptions |  | High | 8 | Server Side / Backend | M3_Phase_3
Task | FEAT-229: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Access Control System' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-229 Access Control System | High | 2 | Server Side / Backend | M3
Task | FEAT-229: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Access Control System' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-229 Access Control System | High | 2 | Server Side / Backend | M3
Task | FEAT-229: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Access Control System' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-229 Access Control System | High | 3 | Server Side / Backend | M3
Task | FEAT-229: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Access Control System' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-229 Access Control System | High | 2 | Server Side / Backend | M3
Task | FEAT-229: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Access Control System' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-229 Access Control System | High | 2 | Server Side / Backend | M3
Story | FEAT-230 Surveys And Feedback | Covers 5 matrix requirement(s). Survey Builder System shall provide a drag-and-drop survey builder allowing administrators to create questionnaires, feedback forms, operational surveys, satisfaction surveys, event surveys, membershi… | E09 Membership & Subscriptions |  | High | 8 | Server Side / Backend | M3_Phase_3
Task | FEAT-230: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Surveys And Feedback' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-230 Surveys And Feedback | High | 2 | Server Side / Backend | M3
Task | FEAT-230: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Surveys And Feedback' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-230 Surveys And Feedback | High | 2 | Server Side / Backend | M3
Task | FEAT-230: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Surveys And Feedback' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-230 Surveys And Feedback | High | 3 | Server Side / Backend | M3
Task | FEAT-230: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Surveys And Feedback' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-230 Surveys And Feedback | High | 2 | Server Side / Backend | M3
Task | FEAT-230: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Surveys And Feedback' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-230 Surveys And Feedback | High | 2 | Server Side / Backend | M3
Story | FEAT-231 Marketing | Covers 5 matrix requirement(s). Multi-Brand Management System shall support multiple brands, venues, attractions, destinations, events, and business units from a single deployment while maintaining independent branding and content. | E09 Membership & Subscriptions |  | High | 5 | Server Side / Backend | M3_Phase_3
Task | FEAT-231: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Marketing' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-231 Marketing | High | 1 | Server Side / Backend | M3
Task | FEAT-231: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Marketing' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-231 Marketing | High | 1 | Server Side / Backend | M3
Task | FEAT-231: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Marketing' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-231 Marketing | High | 2 | Server Side / Backend | M3
Task | FEAT-231: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Marketing' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-231 Marketing | High | 1 | Server Side / Backend | M3
Task | FEAT-231: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Marketing' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-231 Marketing | High | 1 | Server Side / Backend | M3
Story | FEAT-232 Virtual Queue | Covers 4 matrix requirement(s). Support First-Come-First-Served, Virtual Queue, Fast Pass, VIP Queue, Express Queue, Group Queue, Membership Queue, Accessibility Queue, and Staff Queue. | E09 Membership & Subscriptions |  | High | 5 | Server Side / Backend | M3_Phase_3
Task | FEAT-232: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Virtual Queue' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-232 Virtual Queue | High | 1 | Server Side / Backend | M3
Task | FEAT-232: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Virtual Queue' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-232 Virtual Queue | High | 1 | Server Side / Backend | M3
Task | FEAT-232: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Virtual Queue' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-232 Virtual Queue | High | 2 | Server Side / Backend | M3
Task | FEAT-232: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Virtual Queue' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-232 Virtual Queue | High | 1 | Server Side / Backend | M3
Task | FEAT-232: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Virtual Queue' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-232 Virtual Queue | High | 1 | Server Side / Backend | M3
Story | FEAT-233 Ticket And Membership Scanning | Covers 4 matrix requirement(s). Ticket Scanning - Users shall scan tickets. | E09 Membership & Subscriptions |  | High | 5 | Mobile App | M3_Phase_3
Task | FEAT-233: UI screens (iOS & Android) | Implement shared + platform UI components. Acceptance: 'Ticket And Membership Scanning' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-233 Ticket And Membership Scanning | High | 2 | Mobile App | M3
Task | FEAT-233: State & API integration | Data layer, caching and API wiring. Acceptance: 'Ticket And Membership Scanning' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-233 Ticket And Membership Scanning | High | 2 | Mobile App | M3
Task | FEAT-233: Offline & push handling | Offline storage, sync and push notifications. Acceptance: 'Ticket And Membership Scanning' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-233 Ticket And Membership Scanning | High | 1 | Mobile App | M3
Task | FEAT-233: Mobile E2E tests | Automated tests across iOS/Android. Acceptance: 'Ticket And Membership Scanning' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-233 Ticket And Membership Scanning | High | 1 | Mobile App | M3
Story | FEAT-234 Consent Management | Covers 4 matrix requirement(s). Consent Capture Workflows Consent shall be captured through website registrations, ticket purchases, memberships, mobile applications, surveys, waivers, kiosks, POS, call center interactions, and API … | E09 Membership & Subscriptions |  | High | 8 | Server Side / Backend | M3_Phase_3
Task | FEAT-234: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Consent Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-234 Consent Management | High | 1 | Server Side / Backend | M3
Task | FEAT-234: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Consent Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-234 Consent Management | High | 2 | Server Side / Backend | M3
Task | FEAT-234: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Consent Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-234 Consent Management | High | 3 | Server Side / Backend | M3
Task | FEAT-234: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Consent Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-234 Consent Management | High | 1 | Server Side / Backend | M3
Task | FEAT-234: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Consent Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-234 Consent Management | High | 1 | Server Side / Backend | M3
Story | FEAT-235 Audience Segmentation | Covers 4 matrix requirement(s). Dynamic Segments System shall support real-time dynamic segments that automatically update when guest attributes, behaviors, purchases, memberships, loyalty status, or engagement activities change. | E09 Membership & Subscriptions |  | Medium | 8 | Server Side / Backend | M4_Phase_4
Task | FEAT-235: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Audience Segmentation' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-235 Audience Segmentation | Medium | 1 | Server Side / Backend | M4
Task | FEAT-235: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Audience Segmentation' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-235 Audience Segmentation | Medium | 2 | Server Side / Backend | M4
Task | FEAT-235: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Audience Segmentation' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-235 Audience Segmentation | Medium | 3 | Server Side / Backend | M4
Task | FEAT-235: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Audience Segmentation' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-235 Audience Segmentation | Medium | 1 | Server Side / Backend | M4
Task | FEAT-235: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Audience Segmentation' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-235 Audience Segmentation | Medium | 1 | Server Side / Backend | M4
Story | FEAT-236 Front Gate Sales | Covers 3 matrix requirement(s). The POS can be connected to a ZEBRA printer or datamax printer or Evolis, for annual pass (it is expected to have the list of plastic card pass printing hardware compatible) | E09 Membership & Subscriptions |  | High | 2 | POS App | M3_Phase_3
Task | FEAT-236: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Front Gate Sales' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-236 Front Gate Sales | High | 1 | POS App | M3
Task | FEAT-236: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Front Gate Sales' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-236 Front Gate Sales | High | 1 | POS App | M3
Task | FEAT-236: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Front Gate Sales' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-236 Front Gate Sales | High | 1 | POS App | M3
Task | FEAT-236: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Front Gate Sales' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-236 Front Gate Sales | High | 1 | POS App | M3
Task | FEAT-236: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Front Gate Sales' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-236 Front Gate Sales | High | 1 | POS App | M3
Story | FEAT-237 Newsletter And Email Marketing | Covers 3 matrix requirement(s). Dynamic Personalization Newsletter content shall automatically personalize based on guest profile information including name, language, location, membership status, loyalty tier, interests, previous p… | E09 Membership & Subscriptions |  | High | 5 | Server Side / Backend | M3_Phase_3
Task | FEAT-237: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Newsletter And Email Marketing' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-237 Newsletter And Email Marketing | High | 1 | Server Side / Backend | M3
Task | FEAT-237: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Newsletter And Email Marketing' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-237 Newsletter And Email Marketing | High | 1 | Server Side / Backend | M3
Task | FEAT-237: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Newsletter And Email Marketing' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-237 Newsletter And Email Marketing | High | 1 | Server Side / Backend | M3
Task | FEAT-237: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Newsletter And Email Marketing' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-237 Newsletter And Email Marketing | High | 1 | Server Side / Backend | M3
Task | FEAT-237: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Newsletter And Email Marketing' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-237 Newsletter And Email Marketing | High | 1 | Server Side / Backend | M3
Story | FEAT-238 Reviews And Ratings | Covers 3 matrix requirement(s). Category-Based Reviews Guests shall be able to rate specific areas such as attractions, events, facilities, staff, food and beverage, retail, cleanliness, accessibility, membership experience, mobile … | E09 Membership & Subscriptions |  | High | 8 | Server Side / Backend | M3_Phase_3
Task | FEAT-238: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Reviews And Ratings' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-238 Reviews And Ratings | High | 1 | Server Side / Backend | M3
Task | FEAT-238: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Reviews And Ratings' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-238 Reviews And Ratings | High | 2 | Server Side / Backend | M3
Task | FEAT-238: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Reviews And Ratings' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-238 Reviews And Ratings | High | 2 | Server Side / Backend | M3
Task | FEAT-238: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Reviews And Ratings' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-238 Reviews And Ratings | High | 1 | Server Side / Backend | M3
Task | FEAT-238: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Reviews And Ratings' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-238 Reviews And Ratings | High | 1 | Server Side / Backend | M3
Story | FEAT-239 Omnichannel Communications And Ai Chatbot | Covers 3 matrix requirement(s). Membership Integration Guests shall be able to purchase, renew, upgrade, freeze, or inquire about memberships through supported chat channels. | E09 Membership & Subscriptions |  | Medium | 8 | Server Side / Backend | M4_Phase_4
Task | FEAT-239: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Omnichannel Communications And Ai Chatbot' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-239 Omnichannel Communications And Ai Chatbot | Medium | 1 | Server Side / Backend | M4
Task | FEAT-239: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Omnichannel Communications And Ai Chatbot' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-239 Omnichannel Communications And Ai Chatbot | Medium | 2 | Server Side / Backend | M4
Task | FEAT-239: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Omnichannel Communications And Ai Chatbot' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-239 Omnichannel Communications And Ai Chatbot | Medium | 2 | Server Side / Backend | M4
Task | FEAT-239: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Omnichannel Communications And Ai Chatbot' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-239 Omnichannel Communications And Ai Chatbot | Medium | 1 | Server Side / Backend | M4
Task | FEAT-239: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Omnichannel Communications And Ai Chatbot' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-239 Omnichannel Communications And Ai Chatbot | Medium | 1 | Server Side / Backend | M4
Story | FEAT-240 Call Center Sales | Covers 2 matrix requirement(s). System shall allow guests to save tickets, memberships, events, packages, add-ons, F&B items, retail products, and experiences to a wishlist for future purchase. Wishlist items shall remain linked to … | E09 Membership & Subscriptions |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-240: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Call Center Sales' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-240 Call Center Sales | Medium | 1 | Server Side / Backend | M4
Task | FEAT-240: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Call Center Sales' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-240 Call Center Sales | Medium | 2 | Server Side / Backend | M4
Task | FEAT-240: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Call Center Sales' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-240 Call Center Sales | Medium | 2 | Server Side / Backend | M4
Task | FEAT-240: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Call Center Sales' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-240 Call Center Sales | Medium | 1 | Server Side / Backend | M4
Task | FEAT-240: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Call Center Sales' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-240 Call Center Sales | Medium | 1 | Server Side / Backend | M4
Story | FEAT-241 Order Management | Covers 2 matrix requirement(s). Annual Pass Products 1) Customers must first fill in personal information via the annual pass registration page or can go to the ticket counter onsite to purchase Annual Pass Ticket 2) At the ticketin… | E09 Membership & Subscriptions |  | High | 3 | Server Side / Backend | M3_Phase_3
Task | FEAT-241: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Order Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-241 Order Management | High | 1 | Server Side / Backend | M3
Task | FEAT-241: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Order Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-241 Order Management | High | 1 | Server Side / Backend | M3
Task | FEAT-241: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Order Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-241 Order Management | High | 1 | Server Side / Backend | M3
Task | FEAT-241: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Order Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-241 Order Management | High | 1 | Server Side / Backend | M3
Task | FEAT-241: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Order Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-241 Order Management | High | 1 | Server Side / Backend | M3
Story | FEAT-242 Ticket Media | Covers 2 matrix requirement(s). The system shall automatically determine the most suitable media type based on product type, guest segment, sales channel, membership level, venue rules, and business policies. | E09 Membership & Subscriptions |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-242: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ticket Media' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-242 Ticket Media | Medium | 1 | Server Side / Backend | M4
Task | FEAT-242: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ticket Media' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-242 Ticket Media | Medium | 2 | Server Side / Backend | M4
Task | FEAT-242: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ticket Media' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-242 Ticket Media | Medium | 2 | Server Side / Backend | M4
Task | FEAT-242: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ticket Media' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-242 Ticket Media | Medium | 1 | Server Side / Backend | M4
Task | FEAT-242: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ticket Media' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-242 Ticket Media | Medium | 1 | Server Side / Backend | M4
Story | FEAT-243 Profile Management | Covers 2 matrix requirement(s). Maintain a complete chronological timeline of all guest interactions including ticket purchases, memberships, annual passes, retail purchases, F&B transactions, upgrades, refunds, reservations, access… | E09 Membership & Subscriptions |  | High | 3 | Server Side / Backend | M3_Phase_3
Task | FEAT-243: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Profile Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-243 Profile Management | High | 1 | Server Side / Backend | M3
Task | FEAT-243: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Profile Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-243 Profile Management | High | 1 | Server Side / Backend | M3
Task | FEAT-243: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Profile Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-243 Profile Management | High | 1 | Server Side / Backend | M3
Task | FEAT-243: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Profile Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-243 Profile Management | High | 1 | Server Side / Backend | M3
Task | FEAT-243: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Profile Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-243 Profile Management | High | 1 | Server Side / Backend | M3
Story | FEAT-244 Reporting And Dashboards | Covers 2 matrix requirement(s). Accreditation Renewal - System shall support accreditation renewal workflows. | E09 Membership & Subscriptions |  | High | 2 | Server Side / Backend | M3_Phase_3
Task | FEAT-244: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Reporting And Dashboards' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-244 Reporting And Dashboards | High | 1 | Server Side / Backend | M3
Task | FEAT-244: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Reporting And Dashboards' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-244 Reporting And Dashboards | High | 1 | Server Side / Backend | M3
Task | FEAT-244: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Reporting And Dashboards' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-244 Reporting And Dashboards | High | 1 | Server Side / Backend | M3
Task | FEAT-244: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Reporting And Dashboards' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-244 Reporting And Dashboards | High | 1 | Server Side / Backend | M3
Task | FEAT-244: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Reporting And Dashboards' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-244 Reporting And Dashboards | High | 1 | Server Side / Backend | M3
Story | FEAT-245 Api Business Coverage | Covers 2 matrix requirement(s). APIs shall support membership creation, renewal, upgrade, downgrade, freeze, entitlement validation and membership status retrieval. | E09 Membership & Subscriptions |  | High | 2 | Server Side / Backend | M3_Phase_3
Task | FEAT-245: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Api Business Coverage' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-245 Api Business Coverage | High | 1 | Server Side / Backend | M3
Task | FEAT-245: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Api Business Coverage' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-245 Api Business Coverage | High | 1 | Server Side / Backend | M3
Task | FEAT-245: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Api Business Coverage' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-245 Api Business Coverage | High | 1 | Server Side / Backend | M3
Task | FEAT-245: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Api Business Coverage' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-245 Api Business Coverage | High | 1 | Server Side / Backend | M3
Task | FEAT-245: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Api Business Coverage' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-245 Api Business Coverage | High | 1 | Server Side / Backend | M3
Story | FEAT-246 Campaign Management | Covers 2 matrix requirement(s). Dynamic Personalization Campaign content shall support dynamic personalization using guest attributes such as name, language, loyalty tier, membership type, favorite attractions, previous purchases, a… | E09 Membership & Subscriptions |  | High | 3 | Server Side / Backend | M3_Phase_3
Task | FEAT-246: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Campaign Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-246 Campaign Management | High | 1 | Server Side / Backend | M3
Task | FEAT-246: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Campaign Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-246 Campaign Management | High | 1 | Server Side / Backend | M3
Task | FEAT-246: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Campaign Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-246 Campaign Management | High | 1 | Server Side / Backend | M3
Task | FEAT-246: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Campaign Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-246 Campaign Management | High | 1 | Server Side / Backend | M3
Task | FEAT-246: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Campaign Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-246 Campaign Management | High | 1 | Server Side / Backend | M3
Story | FEAT-247 Case Management And Sla | Covers 2 matrix requirement(s). Membership Lifecycle Automation System shall automate membership acquisition, onboarding, benefit education, renewal reminders, upgrade offers, expiration warnings, and win-back campaigns. | E09 Membership & Subscriptions |  | High | 3 | Server Side / Backend | M3_Phase_3
Task | FEAT-247: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Case Management And Sla' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-247 Case Management And Sla | High | 1 | Server Side / Backend | M3
Task | FEAT-247: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Case Management And Sla' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-247 Case Management And Sla | High | 1 | Server Side / Backend | M3
Task | FEAT-247: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Case Management And Sla' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-247 Case Management And Sla | High | 1 | Server Side / Backend | M3
Task | FEAT-247: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Case Management And Sla' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-247 Case Management And Sla | High | 1 | Server Side / Backend | M3
Task | FEAT-247: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Case Management And Sla' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-247 Case Management And Sla | High | 1 | Server Side / Backend | M3
Story | FEAT-248 Seo Management And Optimization | Covers 2 matrix requirement(s). Sitemap Management System shall automatically generate and maintain XML sitemaps for websites, events, attractions, products, memberships, landing pages, and content sections. | E09 Membership & Subscriptions |  | High | 3 | Server Side / Backend | M3_Phase_3
Task | FEAT-248: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Seo Management And Optimization' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-248 Seo Management And Optimization | High | 1 | Server Side / Backend | M3
Task | FEAT-248: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Seo Management And Optimization' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-248 Seo Management And Optimization | High | 1 | Server Side / Backend | M3
Task | FEAT-248: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Seo Management And Optimization' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-248 Seo Management And Optimization | High | 1 | Server Side / Backend | M3
Task | FEAT-248: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Seo Management And Optimization' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-248 Seo Management And Optimization | High | 1 | Server Side / Backend | M3
Task | FEAT-248: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Seo Management And Optimization' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-248 Seo Management And Optimization | High | 1 | Server Side / Backend | M3
Story | FEAT-249 Ticket Resale Marketplace | Covers 1 matrix requirement(s). System shall support configurable resale eligibility rules based on ticket type, event, venue, attraction, membership level, sales channel, ticket status, purchase source, usage status, and business p… | E09 Membership & Subscriptions |  | High | 3 | Server Side / Backend | M3_Phase_3
Task | FEAT-249: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ticket Resale Marketplace' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-249 Ticket Resale Marketplace | High | 1 | Server Side / Backend | M3
Task | FEAT-249: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ticket Resale Marketplace' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-249 Ticket Resale Marketplace | High | 1 | Server Side / Backend | M3
Task | FEAT-249: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ticket Resale Marketplace' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-249 Ticket Resale Marketplace | High | 1 | Server Side / Backend | M3
Task | FEAT-249: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ticket Resale Marketplace' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-249 Ticket Resale Marketplace | High | 1 | Server Side / Backend | M3
Task | FEAT-249: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ticket Resale Marketplace' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-249 Ticket Resale Marketplace | High | 1 | Server Side / Backend | M3
Story | FEAT-250 Ticket Upgrades | Covers 1 matrix requirement(s). The system should support upgrade of: - A 1 day ticket to a multi-day ticket or membership pass. - A multi-day ticket to a membership pass. - A single attraction ticket to multiple attraction ticket. | E09 Membership & Subscriptions |  | High | 3 | Server Side / Backend | M3_Phase_3
Task | FEAT-250: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ticket Upgrades' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-250 Ticket Upgrades | High | 1 | Server Side / Backend | M3
Task | FEAT-250: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ticket Upgrades' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-250 Ticket Upgrades | High | 1 | Server Side / Backend | M3
Task | FEAT-250: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ticket Upgrades' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-250 Ticket Upgrades | High | 1 | Server Side / Backend | M3
Task | FEAT-250: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ticket Upgrades' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-250 Ticket Upgrades | High | 1 | Server Side / Backend | M3
Task | FEAT-250: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ticket Upgrades' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-250 Ticket Upgrades | High | 1 | Server Side / Backend | M3
Story | FEAT-251 Portfolio Management | Covers 1 matrix requirement(s). The system should provide the ability to move stored credit between portfolios linked to different accounts. For Example: each family member have their own portfolio with the possibility to transfer p… | E09 Membership & Subscriptions |  | High | 3 | Server Side / Backend | M3_Phase_3
Task | FEAT-251: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Portfolio Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-251 Portfolio Management | High | 1 | Server Side / Backend | M3
Task | FEAT-251: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Portfolio Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-251 Portfolio Management | High | 1 | Server Side / Backend | M3
Task | FEAT-251: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Portfolio Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-251 Portfolio Management | High | 1 | Server Side / Backend | M3
Task | FEAT-251: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Portfolio Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-251 Portfolio Management | High | 1 | Server Side / Backend | M3
Task | FEAT-251: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Portfolio Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-251 Portfolio Management | High | 1 | Server Side / Backend | M3
Story | FEAT-252 Demand Forecasting | Covers 1 matrix requirement(s). System shall forecast membership revenue. | E09 Membership & Subscriptions |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-252: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Demand Forecasting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-252 Demand Forecasting | Medium | 1 | Server Side / Backend | M4
Task | FEAT-252: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Demand Forecasting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-252 Demand Forecasting | Medium | 2 | Server Side / Backend | M4
Task | FEAT-252: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Demand Forecasting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-252 Demand Forecasting | Medium | 2 | Server Side / Backend | M4
Task | FEAT-252: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Demand Forecasting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-252 Demand Forecasting | Medium | 1 | Server Side / Backend | M4
Task | FEAT-252: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Demand Forecasting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-252 Demand Forecasting | Medium | 1 | Server Side / Backend | M4
Story | FEAT-253 Ai Engine | Covers 1 matrix requirement(s). System shall support semantic search across products, tickets, memberships, documents, knowledge bases, support content, assets, and operational data using vector-based retrieval and relevance ranking… | E09 Membership & Subscriptions |  | High | 3 | Server Side / Backend | M3_Phase_3
Task | FEAT-253: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ai Engine' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-253 Ai Engine | High | 1 | Server Side / Backend | M3
Task | FEAT-253: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ai Engine' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-253 Ai Engine | High | 1 | Server Side / Backend | M3
Task | FEAT-253: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ai Engine' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-253 Ai Engine | High | 1 | Server Side / Backend | M3
Task | FEAT-253: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ai Engine' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-253 Ai Engine | High | 1 | Server Side / Backend | M3
Task | FEAT-253: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ai Engine' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-253 Ai Engine | High | 1 | Server Side / Backend | M3
Story | FEAT-254 Recommendation Engine | Covers 1 matrix requirement(s). System shall provide personalized membership recommendations. | E09 Membership & Subscriptions |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-254: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Recommendation Engine' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-254 Recommendation Engine | Medium | 1 | Server Side / Backend | M4
Task | FEAT-254: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Recommendation Engine' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-254 Recommendation Engine | Medium | 2 | Server Side / Backend | M4
Task | FEAT-254: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Recommendation Engine' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-254 Recommendation Engine | Medium | 2 | Server Side / Backend | M4
Task | FEAT-254: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Recommendation Engine' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-254 Recommendation Engine | Medium | 1 | Server Side / Backend | M4
Task | FEAT-254: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Recommendation Engine' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-254 Recommendation Engine | Medium | 1 | Server Side / Backend | M4
Story | FEAT-255 Bi And Reporting | Covers 1 matrix requirement(s). System shall provide membership dashboards. | E09 Membership & Subscriptions |  | High | 1 | Server Side / Backend | M3_Phase_3
Task | FEAT-255: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Bi And Reporting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-255 Bi And Reporting | High | 1 | Server Side / Backend | M3
Task | FEAT-255: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Bi And Reporting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-255 Bi And Reporting | High | 1 | Server Side / Backend | M3
Task | FEAT-255: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Bi And Reporting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-255 Bi And Reporting | High | 1 | Server Side / Backend | M3
Task | FEAT-255: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Bi And Reporting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-255 Bi And Reporting | High | 1 | Server Side / Backend | M3
Task | FEAT-255: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Bi And Reporting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-255 Bi And Reporting | High | 1 | Server Side / Backend | M3
Story | FEAT-256 Operations Command Center | Covers 1 matrix requirement(s). System shall provide a centralized operational dashboard displaying real-time information across ticketing, access control, attractions, queues, memberships, POS, retail, F&B, devices, incidents, and … | E09 Membership & Subscriptions |  | High | 5 | Server Side / Backend | M3_Phase_3
Task | FEAT-256: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Operations Command Center' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-256 Operations Command Center | High | 1 | Server Side / Backend | M3
Task | FEAT-256: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Operations Command Center' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-256 Operations Command Center | High | 2 | Server Side / Backend | M3
Task | FEAT-256: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Operations Command Center' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-256 Operations Command Center | High | 2 | Server Side / Backend | M3
Task | FEAT-256: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Operations Command Center' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-256 Operations Command Center | High | 1 | Server Side / Backend | M3
Task | FEAT-256: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Operations Command Center' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-256 Operations Command Center | High | 1 | Server Side / Backend | M3
Story | FEAT-257 Accounting | Covers 1 matrix requirement(s). Membership Cancellation Approval Workflow - System shall support approval workflows for membership cancellation requests. | E09 Membership & Subscriptions |  | High | 3 | Server Side / Backend | M3_Phase_3
Task | FEAT-257: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Accounting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-257 Accounting | High | 1 | Server Side / Backend | M3
Task | FEAT-257: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Accounting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-257 Accounting | High | 1 | Server Side / Backend | M3
Task | FEAT-257: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Accounting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-257 Accounting | High | 1 | Server Side / Backend | M3
Task | FEAT-257: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Accounting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-257 Accounting | High | 1 | Server Side / Backend | M3
Task | FEAT-257: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Accounting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-257 Accounting | High | 1 | Server Side / Backend | M3
Story | FEAT-258 Subscription Management | Covers 1 matrix requirement(s). Subscription Renewal - System shall support automatic renewals. | E09 Membership & Subscriptions |  | High | 3 | Server Side / Backend | M3_Phase_3
Task | FEAT-258: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Subscription Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-258 Subscription Management | High | 1 | Server Side / Backend | M3
Task | FEAT-258: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Subscription Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-258 Subscription Management | High | 1 | Server Side / Backend | M3
Task | FEAT-258: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Subscription Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-258 Subscription Management | High | 1 | Server Side / Backend | M3
Task | FEAT-258: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Subscription Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-258 Subscription Management | High | 1 | Server Side / Backend | M3
Task | FEAT-258: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Subscription Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E09 Membership & Subscriptions | FEAT-258 Subscription Management | High | 1 | Server Side / Backend | M3
Story | FEAT-259 Event Management | Covers 39 matrix requirement(s). The system should allow creation of events such as performances, workshops, activities or guided-tours. | E10 Events, Seating & Venue Mapping |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-259: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Event Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-259 Event Management | Medium | 5 | Server Side / Backend | M4
Task | FEAT-259: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Event Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-259 Event Management | Medium | 8 | Server Side / Backend | M4
Task | FEAT-259: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Event Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-259 Event Management | Medium | 13 | Server Side / Backend | M4
Task | FEAT-259: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Event Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-259 Event Management | Medium | 5 | Server Side / Backend | M4
Task | FEAT-259: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Event Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-259 Event Management | Medium | 5 | Server Side / Backend | M4
Story | FEAT-260 Seat Selection And Assignment | Covers 23 matrix requirement(s). Choose My Seats System shall support choose my seats. | E10 Events, Seating & Venue Mapping |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-260: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Seat Selection And Assignment' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-260 Seat Selection And Assignment | Medium | 3 | Server Side / Backend | M4
Task | FEAT-260: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Seat Selection And Assignment' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-260 Seat Selection And Assignment | Medium | 5 | Server Side / Backend | M4
Task | FEAT-260: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Seat Selection And Assignment' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-260 Seat Selection And Assignment | Medium | 8 | Server Side / Backend | M4
Task | FEAT-260: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Seat Selection And Assignment' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-260 Seat Selection And Assignment | Medium | 3 | Server Side / Backend | M4
Task | FEAT-260: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Seat Selection And Assignment' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-260 Seat Selection And Assignment | Medium | 3 | Server Side / Backend | M4
Story | FEAT-261 Seat Map Import | Covers 16 matrix requirement(s). PDF Seat Map Import Import PDF venue plans. | E10 Events, Seating & Venue Mapping |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-261: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Seat Map Import' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-261 Seat Map Import | Medium | 3 | Server Side / Backend | M4
Task | FEAT-261: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Seat Map Import' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-261 Seat Map Import | Medium | 5 | Server Side / Backend | M4
Task | FEAT-261: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Seat Map Import' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-261 Seat Map Import | Medium | 5 | Server Side / Backend | M4
Task | FEAT-261: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Seat Map Import' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-261 Seat Map Import | Medium | 3 | Server Side / Backend | M4
Task | FEAT-261: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Seat Map Import' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-261 Seat Map Import | Medium | 3 | Server Side / Backend | M4
Story | FEAT-262 Resource Management | Covers 12 matrix requirement(s). The system should provide a calendar view for all the resources (e.g. instructors) and associated time slots (e.g. ski school session by an instructor). The calendar should support application of filt… | E10 Events, Seating & Venue Mapping |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-262: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Resource Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-262 Resource Management | Medium | 2 | Server Side / Backend | M4
Task | FEAT-262: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Resource Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-262 Resource Management | Medium | 3 | Server Side / Backend | M4
Task | FEAT-262: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Resource Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-262 Resource Management | Medium | 5 | Server Side / Backend | M4
Task | FEAT-262: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Resource Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-262 Resource Management | Medium | 2 | Server Side / Backend | M4
Task | FEAT-262: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Resource Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-262 Resource Management | Medium | 2 | Server Side / Backend | M4
Story | FEAT-263 Call Center Sales | Covers 8 matrix requirement(s). The system should support email templates for e-ticket purchase confirmation supporting dynamic parameters. The email templates should be configurable per site, per event | E10 Events, Seating & Venue Mapping |  | High | 13 | Server Side / Backend | M2_Phase_3
Task | FEAT-263: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Call Center Sales' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-263 Call Center Sales | High | 2 | Server Side / Backend | M2
Task | FEAT-263: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Call Center Sales' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-263 Call Center Sales | High | 3 | Server Side / Backend | M2
Task | FEAT-263: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Call Center Sales' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-263 Call Center Sales | High | 3 | Server Side / Backend | M2
Task | FEAT-263: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Call Center Sales' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-263 Call Center Sales | High | 2 | Server Side / Backend | M2
Task | FEAT-263: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Call Center Sales' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-263 Call Center Sales | High | 2 | Server Side / Backend | M2
Story | FEAT-264 Api Business Coverage | Covers 8 matrix requirement(s). APIs shall support access validation, entry events, exit events, occupancy management and access entitlement verification. | E10 Events, Seating & Venue Mapping |  | High | 13 | Server Side / Backend | M2_Phase_3
Task | FEAT-264: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Api Business Coverage' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-264 Api Business Coverage | High | 2 | Server Side / Backend | M2
Task | FEAT-264: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Api Business Coverage' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-264 Api Business Coverage | High | 3 | Server Side / Backend | M2
Task | FEAT-264: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Api Business Coverage' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-264 Api Business Coverage | High | 3 | Server Side / Backend | M2
Task | FEAT-264: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Api Business Coverage' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-264 Api Business Coverage | High | 2 | Server Side / Backend | M2
Task | FEAT-264: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Api Business Coverage' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-264 Api Business Coverage | High | 2 | Server Side / Backend | M2
Story | FEAT-265 Seat Map Builder | Covers 8 matrix requirement(s). Drag & Drop Venue Builder Visual designer to create venue layouts without coding. | E10 Events, Seating & Venue Mapping |  | High | 5 | Server Side / Backend | M2_Phase_3
Task | FEAT-265: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Seat Map Builder' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-265 Seat Map Builder | High | 1 | Server Side / Backend | M2
Task | FEAT-265: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Seat Map Builder' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-265 Seat Map Builder | High | 2 | Server Side / Backend | M2
Task | FEAT-265: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Seat Map Builder' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-265 Seat Map Builder | High | 2 | Server Side / Backend | M2
Task | FEAT-265: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Seat Map Builder' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-265 Seat Map Builder | High | 1 | Server Side / Backend | M2
Task | FEAT-265: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Seat Map Builder' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-265 Seat Map Builder | High | 1 | Server Side / Backend | M2
Story | FEAT-266 Seat Holds And Blocks | Covers 8 matrix requirement(s). VIP Seat Holds System shall support vip seat holds. | E10 Events, Seating & Venue Mapping |  | High | 5 | Server Side / Backend | M2_Phase_3
Task | FEAT-266: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Seat Holds And Blocks' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-266 Seat Holds And Blocks | High | 1 | Server Side / Backend | M2
Task | FEAT-266: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Seat Holds And Blocks' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-266 Seat Holds And Blocks | High | 2 | Server Side / Backend | M2
Task | FEAT-266: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Seat Holds And Blocks' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-266 Seat Holds And Blocks | High | 2 | Server Side / Backend | M2
Task | FEAT-266: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Seat Holds And Blocks' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-266 Seat Holds And Blocks | High | 1 | Server Side / Backend | M2
Task | FEAT-266: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Seat Holds And Blocks' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-266 Seat Holds And Blocks | High | 1 | Server Side / Backend | M2
Story | FEAT-267 Preventive Maintenance Planning | Covers 7 matrix requirement(s). Maintenance Plans - System shall support preventive maintenance plans. | E10 Events, Seating & Venue Mapping |  | High | 5 | Server Side / Backend | M2_Phase_3
Task | FEAT-267: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Preventive Maintenance Planning' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-267 Preventive Maintenance Planning | High | 1 | Server Side / Backend | M2
Task | FEAT-267: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Preventive Maintenance Planning' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-267 Preventive Maintenance Planning | High | 2 | Server Side / Backend | M2
Task | FEAT-267: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Preventive Maintenance Planning' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-267 Preventive Maintenance Planning | High | 2 | Server Side / Backend | M2
Task | FEAT-267: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Preventive Maintenance Planning' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-267 Preventive Maintenance Planning | High | 1 | Server Side / Backend | M2
Task | FEAT-267: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Preventive Maintenance Planning' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-267 Preventive Maintenance Planning | High | 1 | Server Side / Backend | M2
Story | FEAT-268 Layout And Templates | Covers 7 matrix requirement(s). Layout Templates System shall support layout templates. | E10 Events, Seating & Venue Mapping |  | High | 5 | Server Side / Backend | M2_Phase_3
Task | FEAT-268: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Layout And Templates' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-268 Layout And Templates | High | 1 | Server Side / Backend | M2
Task | FEAT-268: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Layout And Templates' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-268 Layout And Templates | High | 2 | Server Side / Backend | M2
Task | FEAT-268: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Layout And Templates' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-268 Layout And Templates | High | 2 | Server Side / Backend | M2
Task | FEAT-268: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Layout And Templates' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-268 Layout And Templates | High | 1 | Server Side / Backend | M2
Task | FEAT-268: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Layout And Templates' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-268 Layout And Templates | High | 1 | Server Side / Backend | M2
Story | FEAT-269 Seat Tracking And Holds | Covers 7 matrix requirement(s). Seat Status Management System shall support seat status management. | E10 Events, Seating & Venue Mapping |  | High | 5 | Server Side / Backend | M2_Phase_3
Task | FEAT-269: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Seat Tracking And Holds' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-269 Seat Tracking And Holds | High | 1 | Server Side / Backend | M2
Task | FEAT-269: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Seat Tracking And Holds' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-269 Seat Tracking And Holds | High | 2 | Server Side / Backend | M2
Task | FEAT-269: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Seat Tracking And Holds' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-269 Seat Tracking And Holds | High | 2 | Server Side / Backend | M2
Task | FEAT-269: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Seat Tracking And Holds' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-269 Seat Tracking And Holds | High | 1 | Server Side / Backend | M2
Task | FEAT-269: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Seat Tracking And Holds' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-269 Seat Tracking And Holds | High | 1 | Server Side / Backend | M2
Story | FEAT-270 Seat Recommendations | Covers 7 matrix requirement(s). Best Seat Recommendations System shall support best seat recommendations. | E10 Events, Seating & Venue Mapping |  | Medium | 8 | Server Side / Backend | M4_Phase_4
Task | FEAT-270: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Seat Recommendations' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-270 Seat Recommendations | Medium | 2 | Server Side / Backend | M4
Task | FEAT-270: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Seat Recommendations' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-270 Seat Recommendations | Medium | 3 | Server Side / Backend | M4
Task | FEAT-270: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Seat Recommendations' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-270 Seat Recommendations | Medium | 3 | Server Side / Backend | M4
Task | FEAT-270: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Seat Recommendations' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-270 Seat Recommendations | Medium | 2 | Server Side / Backend | M4
Task | FEAT-270: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Seat Recommendations' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-270 Seat Recommendations | Medium | 2 | Server Side / Backend | M4
Story | FEAT-271 Product Lifecycle | Covers 6 matrix requirement(s). AI should significantly streamline the creation and configuration of venue seat maps by automating design, validation, categorization, and optimization tasks. | E10 Events, Seating & Venue Mapping |  | Medium | 8 | Server Side / Backend | M4_Phase_4
Task | FEAT-271: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Product Lifecycle' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-271 Product Lifecycle | Medium | 2 | Server Side / Backend | M4
Task | FEAT-271: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Product Lifecycle' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-271 Product Lifecycle | Medium | 2 | Server Side / Backend | M4
Task | FEAT-271: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Product Lifecycle' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-271 Product Lifecycle | Medium | 3 | Server Side / Backend | M4
Task | FEAT-271: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Product Lifecycle' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-271 Product Lifecycle | Medium | 2 | Server Side / Backend | M4
Task | FEAT-271: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Product Lifecycle' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-271 Product Lifecycle | Medium | 2 | Server Side / Backend | M4
Story | FEAT-272 Accounting | Covers 6 matrix requirement(s). The system allow general ledger revenue rules to be configured to trigger account allocation based on product sale and redemption events. Revenue allocation rules can be defined for all products and s… | E10 Events, Seating & Venue Mapping |  | High | 5 | Server Side / Backend | M2_Phase_3
Task | FEAT-272: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Accounting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-272 Accounting | High | 1 | Server Side / Backend | M2
Task | FEAT-272: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Accounting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-272 Accounting | High | 1 | Server Side / Backend | M2
Task | FEAT-272: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Accounting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-272 Accounting | High | 2 | Server Side / Backend | M2
Task | FEAT-272: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Accounting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-272 Accounting | High | 1 | Server Side / Backend | M2
Task | FEAT-272: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Accounting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-272 Accounting | High | 1 | Server Side / Backend | M2
Story | FEAT-273 Reporting And Dashboards | Covers 6 matrix requirement(s). Event-Specific Accreditation - System shall support accreditations linked to specific events. | E10 Events, Seating & Venue Mapping |  | High | 5 | Server Side / Backend | M2_Phase_3
Task | FEAT-273: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Reporting And Dashboards' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-273 Reporting And Dashboards | High | 1 | Server Side / Backend | M2
Task | FEAT-273: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Reporting And Dashboards' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-273 Reporting And Dashboards | High | 1 | Server Side / Backend | M2
Task | FEAT-273: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Reporting And Dashboards' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-273 Reporting And Dashboards | High | 2 | Server Side / Backend | M2
Task | FEAT-273: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Reporting And Dashboards' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-273 Reporting And Dashboards | High | 1 | Server Side / Backend | M2
Task | FEAT-273: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Reporting And Dashboards' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-273 Reporting And Dashboards | High | 1 | Server Side / Backend | M2
Story | FEAT-274 Seating Rules And Buffer | Covers 6 matrix requirement(s). Seat Kill Rules System shall support seat kill rules. | E10 Events, Seating & Venue Mapping |  | High | 5 | Server Side / Backend | M2_Phase_3
Task | FEAT-274: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Seating Rules And Buffer' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-274 Seating Rules And Buffer | High | 1 | Server Side / Backend | M2
Task | FEAT-274: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Seating Rules And Buffer' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-274 Seating Rules And Buffer | High | 1 | Server Side / Backend | M2
Task | FEAT-274: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Seating Rules And Buffer' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-274 Seating Rules And Buffer | High | 2 | Server Side / Backend | M2
Task | FEAT-274: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Seating Rules And Buffer' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-274 Seating Rules And Buffer | High | 1 | Server Side / Backend | M2
Task | FEAT-274: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Seating Rules And Buffer' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-274 Seating Rules And Buffer | High | 1 | Server Side / Backend | M2
Story | FEAT-275 Seat Platform And Api | Covers 6 matrix requirement(s). Multi-Tenant Support System shall support multi-tenant support. | E10 Events, Seating & Venue Mapping |  | High | 5 | Server Side / Backend | M2_Phase_3
Task | FEAT-275: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Seat Platform And Api' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-275 Seat Platform And Api | High | 1 | Server Side / Backend | M2
Task | FEAT-275: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Seat Platform And Api' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-275 Seat Platform And Api | High | 1 | Server Side / Backend | M2
Task | FEAT-275: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Seat Platform And Api' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-275 Seat Platform And Api | High | 2 | Server Side / Backend | M2
Task | FEAT-275: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Seat Platform And Api' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-275 Seat Platform And Api | High | 1 | Server Side / Backend | M2
Task | FEAT-275: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Seat Platform And Api' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-275 Seat Platform And Api | High | 1 | Server Side / Backend | M2
Story | FEAT-276 Ticket Types | Covers 5 matrix requirement(s). The system should be able to sell time-slot based tickets for attractions. The system should support: - Creation of timeslots for a whole day or for a period - Configuration of capacity for each times… | E10 Events, Seating & Venue Mapping |  | High | 5 | Server Side / Backend | M2_Phase_3
Task | FEAT-276: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ticket Types' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-276 Ticket Types | High | 1 | Server Side / Backend | M2
Task | FEAT-276: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ticket Types' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-276 Ticket Types | High | 1 | Server Side / Backend | M2
Task | FEAT-276: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ticket Types' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-276 Ticket Types | High | 2 | Server Side / Backend | M2
Task | FEAT-276: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ticket Types' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-276 Ticket Types | High | 1 | Server Side / Backend | M2
Task | FEAT-276: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ticket Types' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-276 Ticket Types | High | 1 | Server Side / Backend | M2
Story | FEAT-277 Seat Reporting And Analytics | Covers 5 matrix requirement(s). Seat Occupancy Reporting System shall support seat occupancy reporting. | E10 Events, Seating & Venue Mapping |  | High | 5 | Server Side / Backend | M2_Phase_3
Task | FEAT-277: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Seat Reporting And Analytics' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-277 Seat Reporting And Analytics | High | 1 | Server Side / Backend | M2
Task | FEAT-277: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Seat Reporting And Analytics' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-277 Seat Reporting And Analytics | High | 1 | Server Side / Backend | M2
Task | FEAT-277: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Seat Reporting And Analytics' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-277 Seat Reporting And Analytics | High | 2 | Server Side / Backend | M2
Task | FEAT-277: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Seat Reporting And Analytics' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-277 Seat Reporting And Analytics | High | 1 | Server Side / Backend | M2
Task | FEAT-277: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Seat Reporting And Analytics' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-277 Seat Reporting And Analytics | High | 1 | Server Side / Backend | M2
Story | FEAT-278 Access Control System | Covers 4 matrix requirement(s). The system should be able to expire a ticket if it is not used within a specified time (e.g. 20 minutes) from the admission time specified on the ticket or based on the time of the performance/event. … | E10 Events, Seating & Venue Mapping |  | Medium | 8 | Server Side / Backend | M4_Phase_4
Task | FEAT-278: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Access Control System' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-278 Access Control System | Medium | 1 | Server Side / Backend | M4
Task | FEAT-278: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Access Control System' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-278 Access Control System | Medium | 2 | Server Side / Backend | M4
Task | FEAT-278: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Access Control System' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-278 Access Control System | Medium | 3 | Server Side / Backend | M4
Task | FEAT-278: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Access Control System' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-278 Access Control System | Medium | 1 | Server Side / Backend | M4
Task | FEAT-278: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Access Control System' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-278 Access Control System | Medium | 1 | Server Side / Backend | M4
Story | FEAT-279 Demand Forecasting | Covers 4 matrix requirement(s). System shall forecast attendance by event. | E10 Events, Seating & Venue Mapping |  | Medium | 8 | Server Side / Backend | M4_Phase_4
Task | FEAT-279: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Demand Forecasting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-279 Demand Forecasting | Medium | 1 | Server Side / Backend | M4
Task | FEAT-279: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Demand Forecasting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-279 Demand Forecasting | Medium | 2 | Server Side / Backend | M4
Task | FEAT-279: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Demand Forecasting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-279 Demand Forecasting | Medium | 3 | Server Side / Backend | M4
Task | FEAT-279: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Demand Forecasting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-279 Demand Forecasting | Medium | 1 | Server Side / Backend | M4
Task | FEAT-279: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Demand Forecasting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-279 Demand Forecasting | Medium | 1 | Server Side / Backend | M4
Story | FEAT-280 Accessible Seating | Covers 4 matrix requirement(s). Wheelchair Seating System shall support wheelchair seating. | E10 Events, Seating & Venue Mapping |  | High | 5 | Server Side / Backend | M2_Phase_3
Task | FEAT-280: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Accessible Seating' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-280 Accessible Seating | High | 1 | Server Side / Backend | M2
Task | FEAT-280: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Accessible Seating' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-280 Accessible Seating | High | 1 | Server Side / Backend | M2
Task | FEAT-280: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Accessible Seating' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-280 Accessible Seating | High | 2 | Server Side / Backend | M2
Task | FEAT-280: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Accessible Seating' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-280 Accessible Seating | High | 1 | Server Side / Backend | M2
Task | FEAT-280: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Accessible Seating' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-280 Accessible Seating | High | 1 | Server Side / Backend | M2
Story | FEAT-281 Ticket Resale Marketplace | Covers 3 matrix requirement(s). System shall prevent duplicate usage, duplicate resale, credential sharing, ticket cloning, and unauthorized ownership changes. | E10 Events, Seating & Venue Mapping |  | High | 2 | Server Side / Backend | M2_Phase_3
Task | FEAT-281: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ticket Resale Marketplace' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-281 Ticket Resale Marketplace | High | 1 | Server Side / Backend | M2
Task | FEAT-281: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ticket Resale Marketplace' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-281 Ticket Resale Marketplace | High | 1 | Server Side / Backend | M2
Task | FEAT-281: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ticket Resale Marketplace' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-281 Ticket Resale Marketplace | High | 1 | Server Side / Backend | M2
Task | FEAT-281: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ticket Resale Marketplace' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-281 Ticket Resale Marketplace | High | 1 | Server Side / Backend | M2
Task | FEAT-281: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ticket Resale Marketplace' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-281 Ticket Resale Marketplace | High | 1 | Server Side / Backend | M2
Story | FEAT-282 Ticket Media | Covers 3 matrix requirement(s). Dynamic QR Code Supports: 1. Registration: Customers select "Digital Ticket" via the confirmation page, email, or ticket PDF to begin the enrollment process. 2.Activation: After registration, the tick… | E10 Events, Seating & Venue Mapping |  | Medium | 8 | Server Side / Backend | M4_Phase_4
Task | FEAT-282: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ticket Media' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-282 Ticket Media | Medium | 1 | Server Side / Backend | M4
Task | FEAT-282: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ticket Media' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-282 Ticket Media | Medium | 2 | Server Side / Backend | M4
Task | FEAT-282: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ticket Media' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-282 Ticket Media | Medium | 2 | Server Side / Backend | M4
Task | FEAT-282: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ticket Media' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-282 Ticket Media | Medium | 1 | Server Side / Backend | M4
Task | FEAT-282: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ticket Media' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-282 Ticket Media | Medium | 1 | Server Side / Backend | M4
Story | FEAT-283 Shift Opening And Closing | Covers 3 matrix requirement(s). The system should allow automatic closing of a cashier's session after a configurable time period. The supervisor should be notified on closing of the session. | E10 Events, Seating & Venue Mapping |  | High | 2 | POS App | M2_Phase_3
Task | FEAT-283: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Shift Opening And Closing' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-283 Shift Opening And Closing | High | 1 | POS App | M2
Task | FEAT-283: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Shift Opening And Closing' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-283 Shift Opening And Closing | High | 1 | POS App | M2
Task | FEAT-283: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Shift Opening And Closing' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-283 Shift Opening And Closing | High | 1 | POS App | M2
Task | FEAT-283: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Shift Opening And Closing' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-283 Shift Opening And Closing | High | 1 | POS App | M2
Task | FEAT-283: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Shift Opening And Closing' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-283 Shift Opening And Closing | High | 1 | POS App | M2
Story | FEAT-284 Campaign Management | Covers 3 matrix requirement(s). Campaign Scheduling System shall support immediate, scheduled, recurring, event-triggered, and timezone-aware campaign execution with configurable send windows and blackout periods. | E10 Events, Seating & Venue Mapping |  | Medium | 8 | Server Side / Backend | M4_Phase_4
Task | FEAT-284: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Campaign Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-284 Campaign Management | Medium | 1 | Server Side / Backend | M4
Task | FEAT-284: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Campaign Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-284 Campaign Management | Medium | 2 | Server Side / Backend | M4
Task | FEAT-284: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Campaign Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-284 Campaign Management | Medium | 2 | Server Side / Backend | M4
Task | FEAT-284: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Campaign Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-284 Campaign Management | Medium | 1 | Server Side / Backend | M4
Task | FEAT-284: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Campaign Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-284 Campaign Management | Medium | 1 | Server Side / Backend | M4
Story | FEAT-285 Gamification And Loyalty | Covers 3 matrix requirement(s). Digital Badges System shall support creation and management of digital badges that can be awarded to guests for completing activities, visiting attractions, attending events, reaching loyalty mileston… | E10 Events, Seating & Venue Mapping |  | High | 5 | Server Side / Backend | M2_Phase_3
Task | FEAT-285: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Gamification And Loyalty' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-285 Gamification And Loyalty | High | 1 | Server Side / Backend | M2
Task | FEAT-285: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Gamification And Loyalty' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-285 Gamification And Loyalty | High | 1 | Server Side / Backend | M2
Task | FEAT-285: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Gamification And Loyalty' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-285 Gamification And Loyalty | High | 1 | Server Side / Backend | M2
Task | FEAT-285: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Gamification And Loyalty' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-285 Gamification And Loyalty | High | 1 | Server Side / Backend | M2
Task | FEAT-285: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Gamification And Loyalty' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-285 Gamification And Loyalty | High | 1 | Server Side / Backend | M2
Story | FEAT-286 Cash Handling | Covers 2 matrix requirement(s). The system should only allow one session per user. | E10 Events, Seating & Venue Mapping |  | High | 2 | Server Side / Backend | M2_Phase_3
Task | FEAT-286: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Cash Handling' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-286 Cash Handling | High | 1 | Server Side / Backend | M2
Task | FEAT-286: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Cash Handling' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-286 Cash Handling | High | 1 | Server Side / Backend | M2
Task | FEAT-286: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Cash Handling' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-286 Cash Handling | High | 1 | Server Side / Backend | M2
Task | FEAT-286: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Cash Handling' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-286 Cash Handling | High | 1 | Server Side / Backend | M2
Task | FEAT-286: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Cash Handling' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-286 Cash Handling | High | 1 | Server Side / Backend | M2
Story | FEAT-287 Ai Governance | Covers 2 matrix requirement(s). System shall prevent unauthorized access to AI functions. | E10 Events, Seating & Venue Mapping |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-287: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ai Governance' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-287 Ai Governance | Medium | 1 | Server Side / Backend | M4
Task | FEAT-287: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ai Governance' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-287 Ai Governance | Medium | 2 | Server Side / Backend | M4
Task | FEAT-287: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ai Governance' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-287 Ai Governance | Medium | 2 | Server Side / Backend | M4
Task | FEAT-287: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ai Governance' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-287 Ai Governance | Medium | 1 | Server Side / Backend | M4
Task | FEAT-287: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ai Governance' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-287 Ai Governance | Medium | 1 | Server Side / Backend | M4
Story | FEAT-288 Recommendation Engine | Covers 2 matrix requirement(s). System shall provide personalized event recommendations. | E10 Events, Seating & Venue Mapping |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-288: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Recommendation Engine' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-288 Recommendation Engine | Medium | 1 | Server Side / Backend | M4
Task | FEAT-288: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Recommendation Engine' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-288 Recommendation Engine | Medium | 2 | Server Side / Backend | M4
Task | FEAT-288: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Recommendation Engine' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-288 Recommendation Engine | Medium | 2 | Server Side / Backend | M4
Task | FEAT-288: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Recommendation Engine' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-288 Recommendation Engine | Medium | 1 | Server Side / Backend | M4
Task | FEAT-288: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Recommendation Engine' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-288 Recommendation Engine | Medium | 1 | Server Side / Backend | M4
Story | FEAT-289 Seat Revenue Management And Forecasting | Covers 2 matrix requirement(s). Seat Demand Forecasting System shall support seat demand forecasting. | E10 Events, Seating & Venue Mapping |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-289: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Seat Revenue Management And Forecasting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-289 Seat Revenue Management And Forecasting | Medium | 1 | Server Side / Backend | M4
Task | FEAT-289: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Seat Revenue Management And Forecasting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-289 Seat Revenue Management And Forecasting | Medium | 2 | Server Side / Backend | M4
Task | FEAT-289: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Seat Revenue Management And Forecasting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-289 Seat Revenue Management And Forecasting | Medium | 2 | Server Side / Backend | M4
Task | FEAT-289: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Seat Revenue Management And Forecasting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-289 Seat Revenue Management And Forecasting | Medium | 1 | Server Side / Backend | M4
Task | FEAT-289: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Seat Revenue Management And Forecasting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-289 Seat Revenue Management And Forecasting | Medium | 1 | Server Side / Backend | M4
Story | FEAT-290 Case Management And Sla | Covers 2 matrix requirement(s). Visual Journey Builder System shall provide a drag-and-drop visual journey builder allowing marketing users to design automated customer journeys using events, conditions, actions, delays, approvals, … | E10 Events, Seating & Venue Mapping |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-290: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Case Management And Sla' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-290 Case Management And Sla | Medium | 1 | Server Side / Backend | M4
Task | FEAT-290: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Case Management And Sla' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-290 Case Management And Sla | Medium | 2 | Server Side / Backend | M4
Task | FEAT-290: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Case Management And Sla' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-290 Case Management And Sla | Medium | 2 | Server Side / Backend | M4
Task | FEAT-290: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Case Management And Sla' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-290 Case Management And Sla | Medium | 1 | Server Side / Backend | M4
Task | FEAT-290: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Case Management And Sla' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-290 Case Management And Sla | Medium | 1 | Server Side / Backend | M4
Story | FEAT-291 Newsletter And Email Marketing | Covers 2 matrix requirement(s). Newsletter Builder System shall provide a drag-and-drop newsletter designer allowing marketing users to create responsive newsletters without technical knowledge. The editor shall support text blocks,… | E10 Events, Seating & Venue Mapping |  | High | 2 | Server Side / Backend | M2_Phase_3
Task | FEAT-291: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Newsletter And Email Marketing' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-291 Newsletter And Email Marketing | High | 1 | Server Side / Backend | M2
Task | FEAT-291: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Newsletter And Email Marketing' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-291 Newsletter And Email Marketing | High | 1 | Server Side / Backend | M2
Task | FEAT-291: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Newsletter And Email Marketing' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-291 Newsletter And Email Marketing | High | 1 | Server Side / Backend | M2
Task | FEAT-291: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Newsletter And Email Marketing' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-291 Newsletter And Email Marketing | High | 1 | Server Side / Backend | M2
Task | FEAT-291: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Newsletter And Email Marketing' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-291 Newsletter And Email Marketing | High | 1 | Server Side / Backend | M2
Story | FEAT-292 Notifications And Messaging | Covers 2 matrix requirement(s). Operational Alerts System shall support operational notifications to staff regarding incidents, capacity thresholds, device failures, approvals, escalations, maintenance events, and workflow activitie… | E10 Events, Seating & Venue Mapping |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-292: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Notifications And Messaging' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-292 Notifications And Messaging | Medium | 1 | Server Side / Backend | M4
Task | FEAT-292: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Notifications And Messaging' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-292 Notifications And Messaging | Medium | 2 | Server Side / Backend | M4
Task | FEAT-292: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Notifications And Messaging' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-292 Notifications And Messaging | Medium | 2 | Server Side / Backend | M4
Task | FEAT-292: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Notifications And Messaging' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-292 Notifications And Messaging | Medium | 1 | Server Side / Backend | M4
Task | FEAT-292: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Notifications And Messaging' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-292 Notifications And Messaging | Medium | 1 | Server Side / Backend | M4
Story | FEAT-293 Marketing | Covers 2 matrix requirement(s). AI Mobile App Content Builder AI shall generate mobile app homepages, menus, banners, announcements, event sections, and content structures based on available products and branding. | E10 Events, Seating & Venue Mapping |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-293: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Marketing' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-293 Marketing | Medium | 1 | Server Side / Backend | M4
Task | FEAT-293: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Marketing' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-293 Marketing | Medium | 2 | Server Side / Backend | M4
Task | FEAT-293: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Marketing' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-293 Marketing | Medium | 2 | Server Side / Backend | M4
Task | FEAT-293: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Marketing' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-293 Marketing | Medium | 1 | Server Side / Backend | M4
Task | FEAT-293: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Marketing' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-293 Marketing | Medium | 1 | Server Side / Backend | M4
Story | FEAT-294 Digital Waiver Management | Covers 1 matrix requirement(s). The system should be to apply a transaction fee to orders for a specific ticket (e.g. Event Ticket). The transaction fee should also be applicable for actions like ticket modification and cancellation… | E10 Events, Seating & Venue Mapping |  | High | 3 | Server Side / Backend | M2_Phase_3
Task | FEAT-294: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Digital Waiver Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-294 Digital Waiver Management | High | 1 | Server Side / Backend | M2
Task | FEAT-294: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Digital Waiver Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-294 Digital Waiver Management | High | 1 | Server Side / Backend | M2
Task | FEAT-294: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Digital Waiver Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-294 Digital Waiver Management | High | 1 | Server Side / Backend | M2
Task | FEAT-294: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Digital Waiver Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-294 Digital Waiver Management | High | 1 | Server Side / Backend | M2
Task | FEAT-294: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Digital Waiver Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-294 Digital Waiver Management | High | 1 | Server Side / Backend | M2
Story | FEAT-295 Profile Management | Covers 1 matrix requirement(s). Maintain detailed access validation history including gate entries, exits, attraction validations, RFID scans, QR scans, and turnstile events. | E10 Events, Seating & Venue Mapping |  | High | 3 | POS App | M2_Phase_3
Task | FEAT-295: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Profile Management' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-295 Profile Management | High | 1 | POS App | M2
Task | FEAT-295: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Profile Management' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-295 Profile Management | High | 1 | POS App | M2
Task | FEAT-295: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Profile Management' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-295 Profile Management | High | 1 | POS App | M2
Task | FEAT-295: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Profile Management' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-295 Profile Management | High | 1 | POS App | M2
Task | FEAT-295: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Profile Management' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-295 Profile Management | High | 1 | POS App | M2
Story | FEAT-296 Loyalty | Covers 1 matrix requirement(s). Reward customers for successful referrals. System shall allow guests to refer new customers and receive rewards when referral conditions are met. Rules shall define referral code, eligibility, reward … | E10 Events, Seating & Venue Mapping |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-296: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Loyalty' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-296 Loyalty | Medium | 1 | Server Side / Backend | M4
Task | FEAT-296: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Loyalty' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-296 Loyalty | Medium | 2 | Server Side / Backend | M4
Task | FEAT-296: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Loyalty' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-296 Loyalty | Medium | 2 | Server Side / Backend | M4
Task | FEAT-296: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Loyalty' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-296 Loyalty | Medium | 1 | Server Side / Backend | M4
Task | FEAT-296: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Loyalty' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-296 Loyalty | Medium | 1 | Server Side / Backend | M4
Story | FEAT-297 Portfolio And Entitlement Management | Covers 1 matrix requirement(s). Support schools, tour operators, travel agencies, corporate groups, and event organizers. | E10 Events, Seating & Venue Mapping |  | High | 3 | Server Side / Backend | M2_Phase_3
Task | FEAT-297: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Portfolio And Entitlement Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-297 Portfolio And Entitlement Management | High | 1 | Server Side / Backend | M2
Task | FEAT-297: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Portfolio And Entitlement Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-297 Portfolio And Entitlement Management | High | 1 | Server Side / Backend | M2
Task | FEAT-297: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Portfolio And Entitlement Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-297 Portfolio And Entitlement Management | High | 1 | Server Side / Backend | M2
Task | FEAT-297: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Portfolio And Entitlement Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-297 Portfolio And Entitlement Management | High | 1 | Server Side / Backend | M2
Task | FEAT-297: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Portfolio And Entitlement Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-297 Portfolio And Entitlement Management | High | 1 | Server Side / Backend | M2
Story | FEAT-298 Ai Configuration Assistant | Covers 1 matrix requirement(s). The AI assistant can configure: Operating hours Performances Blackout periods Special opening hours Example: "Add evening slots from 6 PM to 10 PM every Friday for Ladies Night event." | E10 Events, Seating & Venue Mapping |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-298: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ai Configuration Assistant' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-298 Ai Configuration Assistant | Medium | 1 | Server Side / Backend | M4
Task | FEAT-298: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ai Configuration Assistant' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-298 Ai Configuration Assistant | Medium | 2 | Server Side / Backend | M4
Task | FEAT-298: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ai Configuration Assistant' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-298 Ai Configuration Assistant | Medium | 2 | Server Side / Backend | M4
Task | FEAT-298: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ai Configuration Assistant' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-298 Ai Configuration Assistant | Medium | 1 | Server Side / Backend | M4
Task | FEAT-298: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ai Configuration Assistant' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-298 Ai Configuration Assistant | Medium | 1 | Server Side / Backend | M4
Story | FEAT-299 Operations Command Center | Covers 1 matrix requirement(s). System shall provide dashboards, reports, drill-down analytics, alerts, and historical operational performance analysis. | E10 Events, Seating & Venue Mapping |  | High | 1 | Server Side / Backend | M2_Phase_3
Task | FEAT-299: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Operations Command Center' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-299 Operations Command Center | High | 1 | Server Side / Backend | M2
Task | FEAT-299: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Operations Command Center' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-299 Operations Command Center | High | 1 | Server Side / Backend | M2
Task | FEAT-299: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Operations Command Center' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-299 Operations Command Center | High | 1 | Server Side / Backend | M2
Task | FEAT-299: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Operations Command Center' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-299 Operations Command Center | High | 1 | Server Side / Backend | M2
Task | FEAT-299: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Operations Command Center' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-299 Operations Command Center | High | 1 | Server Side / Backend | M2
Story | FEAT-300 Sandbox | Covers 1 matrix requirement(s). Performance Testing - System shall support performance testing. | E10 Events, Seating & Venue Mapping |  | High | 3 | Cross Platform | M2_Phase_3
Task | FEAT-300: Design & technical spec | Architecture, interfaces and acceptance criteria. Acceptance: 'Sandbox' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-300 Sandbox | High | 1 | Cross Platform | M2
Task | FEAT-300: Implementation | Build the capability / automation. Acceptance: 'Sandbox' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-300 Sandbox | High | 1 | Cross Platform | M2
Task | FEAT-300: Automation & CI integration | Pipeline, IaC and gates. Acceptance: 'Sandbox' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-300 Sandbox | High | 1 | Cross Platform | M2
Task | FEAT-300: Verification & sign-off | Validate against NFR/acceptance criteria. Acceptance: 'Sandbox' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-300 Sandbox | High | 1 | Cross Platform | M2
Story | FEAT-301 Device Monitoring | Covers 1 matrix requirement(s). Device Performance Monitoring - System shall monitor device performance. | E10 Events, Seating & Venue Mapping |  | High | 3 | Cross Platform | M2_Phase_3
Task | FEAT-301: Design & technical spec | Architecture, interfaces and acceptance criteria. Acceptance: 'Device Monitoring' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-301 Device Monitoring | High | 1 | Cross Platform | M2
Task | FEAT-301: Implementation | Build the capability / automation. Acceptance: 'Device Monitoring' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-301 Device Monitoring | High | 1 | Cross Platform | M2
Task | FEAT-301: Automation & CI integration | Pipeline, IaC and gates. Acceptance: 'Device Monitoring' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-301 Device Monitoring | High | 1 | Cross Platform | M2
Task | FEAT-301: Verification & sign-off | Validate against NFR/acceptance criteria. Acceptance: 'Device Monitoring' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-301 Device Monitoring | High | 1 | Cross Platform | M2
Story | FEAT-302 Device Maintenance | Covers 1 matrix requirement(s). Preventive Maintenance - System shall support preventive maintenance schedules. | E10 Events, Seating & Venue Mapping |  | High | 3 | Server Side / Backend | M2_Phase_3
Task | FEAT-302: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Device Maintenance' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-302 Device Maintenance | High | 1 | Server Side / Backend | M2
Task | FEAT-302: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Device Maintenance' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-302 Device Maintenance | High | 1 | Server Side / Backend | M2
Task | FEAT-302: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Device Maintenance' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-302 Device Maintenance | High | 1 | Server Side / Backend | M2
Task | FEAT-302: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Device Maintenance' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-302 Device Maintenance | High | 1 | Server Side / Backend | M2
Task | FEAT-302: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Device Maintenance' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-302 Device Maintenance | High | 1 | Server Side / Backend | M2
Story | FEAT-303 Maintenance Reporting And Analytics | Covers 1 matrix requirement(s). Asset Performance Reporting - System shall provide asset performance reports. | E10 Events, Seating & Venue Mapping |  | High | 1 | Server Side / Backend | M2_Phase_3
Task | FEAT-303: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Maintenance Reporting And Analytics' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-303 Maintenance Reporting And Analytics | High | 1 | Server Side / Backend | M2
Task | FEAT-303: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Maintenance Reporting And Analytics' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-303 Maintenance Reporting And Analytics | High | 1 | Server Side / Backend | M2
Task | FEAT-303: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Maintenance Reporting And Analytics' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-303 Maintenance Reporting And Analytics | High | 1 | Server Side / Backend | M2
Task | FEAT-303: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Maintenance Reporting And Analytics' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-303 Maintenance Reporting And Analytics | High | 1 | Server Side / Backend | M2
Task | FEAT-303: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Maintenance Reporting And Analytics' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-303 Maintenance Reporting And Analytics | High | 1 | Server Side / Backend | M2
Story | FEAT-304 Authentication And Login | Covers 1 matrix requirement(s). Interactive Venue Map - System shall provide interactive venue maps. | E10 Events, Seating & Venue Mapping |  | High | 3 | Mobile App | M2_Phase_3
Task | FEAT-304: UI screens (iOS & Android) | Implement shared + platform UI components. Acceptance: 'Authentication And Login' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-304 Authentication And Login | High | 1 | Mobile App | M2
Task | FEAT-304: State & API integration | Data layer, caching and API wiring. Acceptance: 'Authentication And Login' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-304 Authentication And Login | High | 1 | Mobile App | M2
Task | FEAT-304: Offline & push handling | Offline storage, sync and push notifications. Acceptance: 'Authentication And Login' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-304 Authentication And Login | High | 1 | Mobile App | M2
Task | FEAT-304: Mobile E2E tests | Automated tests across iOS/Android. Acceptance: 'Authentication And Login' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-304 Authentication And Login | High | 1 | Mobile App | M2
Story | FEAT-305 Reviews And Ratings | Covers 1 matrix requirement(s). Review Analytics Dashboard System shall provide dashboards displaying review volume, average ratings, sentiment trends, category ratings, response times, unresolved issues, and service performance met… | E10 Events, Seating & Venue Mapping |  | High | 1 | Server Side / Backend | M2_Phase_3
Task | FEAT-305: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Reviews And Ratings' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-305 Reviews And Ratings | High | 1 | Server Side / Backend | M2
Task | FEAT-305: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Reviews And Ratings' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-305 Reviews And Ratings | High | 1 | Server Side / Backend | M2
Task | FEAT-305: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Reviews And Ratings' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-305 Reviews And Ratings | High | 1 | Server Side / Backend | M2
Task | FEAT-305: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Reviews And Ratings' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-305 Reviews And Ratings | High | 1 | Server Side / Backend | M2
Task | FEAT-305: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Reviews And Ratings' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-305 Reviews And Ratings | High | 1 | Server Side / Backend | M2
Story | FEAT-306 Omnichannel Communications And Ai Chatbot | Covers 1 matrix requirement(s). Chat Analytics Dashboard System shall provide analytics including conversation volumes, response times, resolution times, sentiment trends, conversion rates, sales generated, agent performance, and cu… | E10 Events, Seating & Venue Mapping |  | High | 1 | Server Side / Backend | M2_Phase_3
Task | FEAT-306: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Omnichannel Communications And Ai Chatbot' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-306 Omnichannel Communications And Ai Chatbot | High | 1 | Server Side / Backend | M2
Task | FEAT-306: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Omnichannel Communications And Ai Chatbot' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-306 Omnichannel Communications And Ai Chatbot | High | 1 | Server Side / Backend | M2
Task | FEAT-306: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Omnichannel Communications And Ai Chatbot' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-306 Omnichannel Communications And Ai Chatbot | High | 1 | Server Side / Backend | M2
Task | FEAT-306: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Omnichannel Communications And Ai Chatbot' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-306 Omnichannel Communications And Ai Chatbot | High | 1 | Server Side / Backend | M2
Task | FEAT-306: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Omnichannel Communications And Ai Chatbot' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-306 Omnichannel Communications And Ai Chatbot | High | 1 | Server Side / Backend | M2
Story | FEAT-307 Seo Management And Optimization | Covers 1 matrix requirement(s). SEO Metadata Management System shall allow administrators to manage SEO titles, meta descriptions, keywords, canonical URLs, social sharing metadata, and Open Graph properties for all content, product… | E10 Events, Seating & Venue Mapping |  | High | 3 | Server Side / Backend | M2_Phase_3
Task | FEAT-307: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Seo Management And Optimization' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-307 Seo Management And Optimization | High | 1 | Server Side / Backend | M2
Task | FEAT-307: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Seo Management And Optimization' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-307 Seo Management And Optimization | High | 1 | Server Side / Backend | M2
Task | FEAT-307: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Seo Management And Optimization' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-307 Seo Management And Optimization | High | 1 | Server Side / Backend | M2
Task | FEAT-307: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Seo Management And Optimization' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-307 Seo Management And Optimization | High | 1 | Server Side / Backend | M2
Task | FEAT-307: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Seo Management And Optimization' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-307 Seo Management And Optimization | High | 1 | Server Side / Backend | M2
Story | FEAT-308 Digital Waivers And Signature Management | Covers 1 matrix requirement(s). Event Waiver Management Events shall support event-specific waivers and liability acknowledgements linked directly to event registrations and attendance. | E10 Events, Seating & Venue Mapping |  | High | 3 | Server Side / Backend | M2_Phase_3
Task | FEAT-308: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Digital Waivers And Signature Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-308 Digital Waivers And Signature Management | High | 1 | Server Side / Backend | M2
Task | FEAT-308: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Digital Waivers And Signature Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-308 Digital Waivers And Signature Management | High | 1 | Server Side / Backend | M2
Task | FEAT-308: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Digital Waivers And Signature Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-308 Digital Waivers And Signature Management | High | 1 | Server Side / Backend | M2
Task | FEAT-308: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Digital Waivers And Signature Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-308 Digital Waivers And Signature Management | High | 1 | Server Side / Backend | M2
Task | FEAT-308: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Digital Waivers And Signature Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-308 Digital Waivers And Signature Management | High | 1 | Server Side / Backend | M2
Story | FEAT-309 Consent Management | Covers 1 matrix requirement(s). Privacy Incident Tracking System shall support recording, tracking, investigation, and reporting of privacy incidents, consent violations, data access issues, and compliance-related events. | E10 Events, Seating & Venue Mapping |  | High | 1 | Server Side / Backend | M2_Phase_3
Task | FEAT-309: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Consent Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-309 Consent Management | High | 1 | Server Side / Backend | M2
Task | FEAT-309: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Consent Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-309 Consent Management | High | 1 | Server Side / Backend | M2
Task | FEAT-309: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Consent Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-309 Consent Management | High | 1 | Server Side / Backend | M2
Task | FEAT-309: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Consent Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-309 Consent Management | High | 1 | Server Side / Backend | M2
Task | FEAT-309: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Consent Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-309 Consent Management | High | 1 | Server Side / Backend | M2
Story | FEAT-310 Audience Segmentation | Covers 1 matrix requirement(s). Marketing ROI Dashboard System shall provide dashboards displaying campaign ROI, cost per acquisition, revenue attribution, conversion rates, customer acquisition cost, and lifetime value performance. | E10 Events, Seating & Venue Mapping |  | High | 1 | Server Side / Backend | M2_Phase_3
Task | FEAT-310: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Audience Segmentation' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-310 Audience Segmentation | High | 1 | Server Side / Backend | M2
Task | FEAT-310: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Audience Segmentation' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-310 Audience Segmentation | High | 1 | Server Side / Backend | M2
Task | FEAT-310: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Audience Segmentation' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-310 Audience Segmentation | High | 1 | Server Side / Backend | M2
Task | FEAT-310: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Audience Segmentation' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-310 Audience Segmentation | High | 1 | Server Side / Backend | M2
Task | FEAT-310: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Audience Segmentation' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E10 Events, Seating & Venue Mapping | FEAT-310 Audience Segmentation | High | 1 | Server Side / Backend | M2
Story | FEAT-311 Promotions | Covers 47 matrix requirement(s). Integration with Identity: Tie QR code validity to user identity (Account ID, email address, or device). | E11 Bundles, Promotions & Pricing |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-311: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Promotions' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-311 Promotions | Medium | 8 | Server Side / Backend | M4
Task | FEAT-311: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Promotions' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-311 Promotions | Medium | 8 | Server Side / Backend | M4
Task | FEAT-311: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Promotions' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-311 Promotions | Medium | 13 | Server Side / Backend | M4
Task | FEAT-311: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Promotions' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-311 Promotions | Medium | 8 | Server Side / Backend | M4
Task | FEAT-311: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Promotions' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-311 Promotions | Medium | 8 | Server Side / Backend | M4
Story | FEAT-312 Dynamic Pricing | Covers 44 matrix requirement(s). System shall support dynamic ticket pricing. | E11 Bundles, Promotions & Pricing |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-312: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Dynamic Pricing' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-312 Dynamic Pricing | Medium | 5 | Server Side / Backend | M4
Task | FEAT-312: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Dynamic Pricing' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-312 Dynamic Pricing | Medium | 8 | Server Side / Backend | M4
Task | FEAT-312: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Dynamic Pricing' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-312 Dynamic Pricing | Medium | 13 | Server Side / Backend | M4
Task | FEAT-312: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Dynamic Pricing' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-312 Dynamic Pricing | Medium | 5 | Server Side / Backend | M4
Task | FEAT-312: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Dynamic Pricing' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-312 Dynamic Pricing | Medium | 5 | Server Side / Backend | M4
Story | FEAT-313 Pricing | Covers 42 matrix requirement(s). For BtoB online sales, the following points shall be available online: | E11 Bundles, Promotions & Pricing |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-313: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Pricing' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-313 Pricing | Medium | 5 | Server Side / Backend | M4
Task | FEAT-313: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Pricing' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-313 Pricing | Medium | 8 | Server Side / Backend | M4
Task | FEAT-313: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Pricing' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-313 Pricing | Medium | 13 | Server Side / Backend | M4
Task | FEAT-313: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Pricing' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-313 Pricing | Medium | 5 | Server Side / Backend | M4
Task | FEAT-313: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Pricing' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-313 Pricing | Medium | 5 | Server Side / Backend | M4
Story | FEAT-314 Bundles | Covers 35 matrix requirement(s). Encrypted Payload: QR codes contain encrypted or tokenized identifiers (not raw PII). | E11 Bundles, Promotions & Pricing |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-314: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Bundles' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-314 Bundles | Medium | 5 | Server Side / Backend | M4
Task | FEAT-314: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Bundles' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-314 Bundles | Medium | 8 | Server Side / Backend | M4
Task | FEAT-314: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Bundles' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-314 Bundles | Medium | 8 | Server Side / Backend | M4
Task | FEAT-314: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Bundles' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-314 Bundles | Medium | 5 | Server Side / Backend | M4
Task | FEAT-314: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Bundles' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-314 Bundles | Medium | 5 | Server Side / Backend | M4
Story | FEAT-315 Upsell And Cross-Sell | Covers 21 matrix requirement(s). The system should be able to support and create bundles managed by external destinations, Online travel aggregators and Hotel chains | E11 Bundles, Promotions & Pricing |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-315: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Upsell And Cross-Sell' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-315 Upsell And Cross-Sell | Medium | 3 | Server Side / Backend | M4
Task | FEAT-315: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Upsell And Cross-Sell' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-315 Upsell And Cross-Sell | Medium | 5 | Server Side / Backend | M4
Task | FEAT-315: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Upsell And Cross-Sell' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-315 Upsell And Cross-Sell | Medium | 8 | Server Side / Backend | M4
Task | FEAT-315: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Upsell And Cross-Sell' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-315 Upsell And Cross-Sell | Medium | 3 | Server Side / Backend | M4
Task | FEAT-315: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Upsell And Cross-Sell' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-315 Upsell And Cross-Sell | Medium | 3 | Server Side / Backend | M4
Story | FEAT-316 Ai Configuration Assistant | Covers 15 matrix requirement(s). For no-shows, the revenue attached to this ticket is moved from differed to earned revenue AI Discount Assistant: 1) For seasonal, early bird, bulk discounts, last minute discounts: Provide AI-driven … | E11 Bundles, Promotions & Pricing |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-316: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ai Configuration Assistant' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-316 Ai Configuration Assistant | Medium | 3 | Server Side / Backend | M4
Task | FEAT-316: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ai Configuration Assistant' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-316 Ai Configuration Assistant | Medium | 5 | Server Side / Backend | M4
Task | FEAT-316: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ai Configuration Assistant' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-316 Ai Configuration Assistant | Medium | 5 | Server Side / Backend | M4
Task | FEAT-316: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ai Configuration Assistant' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-316 Ai Configuration Assistant | Medium | 3 | Server Side / Backend | M4
Task | FEAT-316: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ai Configuration Assistant' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-316 Ai Configuration Assistant | Medium | 3 | Server Side / Backend | M4
Story | FEAT-317 Sales Channels | Covers 11 matrix requirement(s). The system should store and manage all rules for product compatibility, eligibility and pricing that will be applicable to for each sales channel. These rules will be part of the system and not extern… | E11 Bundles, Promotions & Pricing |  | Medium | 13 | POS App | M4_Phase_4
Task | FEAT-317: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Sales Channels' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-317 Sales Channels | Medium | 3 | POS App | M4
Task | FEAT-317: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Sales Channels' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-317 Sales Channels | Medium | 2 | POS App | M4
Task | FEAT-317: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Sales Channels' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-317 Sales Channels | Medium | 3 | POS App | M4
Task | FEAT-317: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Sales Channels' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-317 Sales Channels | Medium | 3 | POS App | M4
Task | FEAT-317: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Sales Channels' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-317 Sales Channels | Medium | 2 | POS App | M4
Story | FEAT-318 Ticket Upgrades | Covers 11 matrix requirement(s). The system should provide a service to enable the dynamic composition of the shop cart. The system must provide back all the information in real time, such as the performance availabilities of an even… | E11 Bundles, Promotions & Pricing |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-318: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ticket Upgrades' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-318 Ticket Upgrades | Medium | 2 | Server Side / Backend | M4
Task | FEAT-318: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ticket Upgrades' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-318 Ticket Upgrades | Medium | 3 | Server Side / Backend | M4
Task | FEAT-318: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ticket Upgrades' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-318 Ticket Upgrades | Medium | 5 | Server Side / Backend | M4
Task | FEAT-318: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ticket Upgrades' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-318 Ticket Upgrades | Medium | 2 | Server Side / Backend | M4
Task | FEAT-318: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ticket Upgrades' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-318 Ticket Upgrades | Medium | 2 | Server Side / Backend | M4
Story | FEAT-319 Ticket Types | Covers 10 matrix requirement(s). System shall allow administrators to create reusable ticket templates containing pricing, validity, capacity, access rights, add-ons, restrictions and approval workflows. | E11 Bundles, Promotions & Pricing |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-319: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ticket Types' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-319 Ticket Types | Medium | 2 | Server Side / Backend | M4
Task | FEAT-319: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ticket Types' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-319 Ticket Types | Medium | 3 | Server Side / Backend | M4
Task | FEAT-319: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ticket Types' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-319 Ticket Types | Medium | 5 | Server Side / Backend | M4
Task | FEAT-319: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ticket Types' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-319 Ticket Types | Medium | 2 | Server Side / Backend | M4
Task | FEAT-319: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ticket Types' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-319 Ticket Types | Medium | 2 | Server Side / Backend | M4
Story | FEAT-320 Recommendation Engine | Covers 9 matrix requirement(s). System shall provide upsell recommendations. | E11 Bundles, Promotions & Pricing |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-320: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Recommendation Engine' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-320 Recommendation Engine | Medium | 2 | Server Side / Backend | M4
Task | FEAT-320: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Recommendation Engine' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-320 Recommendation Engine | Medium | 3 | Server Side / Backend | M4
Task | FEAT-320: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Recommendation Engine' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-320 Recommendation Engine | Medium | 3 | Server Side / Backend | M4
Task | FEAT-320: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Recommendation Engine' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-320 Recommendation Engine | Medium | 2 | Server Side / Backend | M4
Task | FEAT-320: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Recommendation Engine' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-320 Recommendation Engine | Medium | 2 | Server Side / Backend | M4
Story | FEAT-321 Fandb And Retail Offers And Promotions | Covers 7 matrix requirement(s). Track expiration dates and generate alerts. | E11 Bundles, Promotions & Pricing |  | High | 5 | Server Side / Backend | M3_Phase_3
Task | FEAT-321: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Fandb And Retail Offers And Promotions' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-321 Fandb And Retail Offers And Promotions | High | 1 | Server Side / Backend | M3
Task | FEAT-321: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Fandb And Retail Offers And Promotions' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-321 Fandb And Retail Offers And Promotions | High | 2 | Server Side / Backend | M3
Task | FEAT-321: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Fandb And Retail Offers And Promotions' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-321 Fandb And Retail Offers And Promotions | High | 2 | Server Side / Backend | M3
Task | FEAT-321: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Fandb And Retail Offers And Promotions' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-321 Fandb And Retail Offers And Promotions | High | 1 | Server Side / Backend | M3
Task | FEAT-321: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Fandb And Retail Offers And Promotions' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-321 Fandb And Retail Offers And Promotions | High | 1 | Server Side / Backend | M3
Story | FEAT-322 Marketing | Covers 7 matrix requirement(s). Component-Based Design System System shall provide reusable content components including banners, event widgets, ticket widgets, membership widgets, loyalty widgets, galleries, videos, maps, forms, co… | E11 Bundles, Promotions & Pricing |  | Medium | 8 | Server Side / Backend | M4_Phase_4
Task | FEAT-322: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Marketing' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-322 Marketing | Medium | 2 | Server Side / Backend | M4
Task | FEAT-322: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Marketing' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-322 Marketing | Medium | 3 | Server Side / Backend | M4
Task | FEAT-322: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Marketing' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-322 Marketing | Medium | 3 | Server Side / Backend | M4
Task | FEAT-322: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Marketing' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-322 Marketing | Medium | 2 | Server Side / Backend | M4
Task | FEAT-322: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Marketing' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-322 Marketing | Medium | 2 | Server Side / Backend | M4
Story | FEAT-323 Event Management | Covers 6 matrix requirement(s). The system should allow a seating plan to be created for each space. Different type of seats can be configured within the seating plan and a space can have multiple seating arrangements. The system sh… | E11 Bundles, Promotions & Pricing |  | High | 8 | Server Side / Backend | M3_Phase_3
Task | FEAT-323: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Event Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-323 Event Management | High | 2 | Server Side / Backend | M3
Task | FEAT-323: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Event Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-323 Event Management | High | 2 | Server Side / Backend | M3
Task | FEAT-323: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Event Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-323 Event Management | High | 3 | Server Side / Backend | M3
Task | FEAT-323: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Event Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-323 Event Management | High | 2 | Server Side / Backend | M3
Task | FEAT-323: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Event Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-323 Event Management | High | 2 | Server Side / Backend | M3
Story | FEAT-324 Product Lifecycle | Covers 6 matrix requirement(s). System shall maintain version history of all product configurations including pricing, rules, entitlements and capacities. | E11 Bundles, Promotions & Pricing |  | Medium | 8 | Server Side / Backend | M4_Phase_4
Task | FEAT-324: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Product Lifecycle' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-324 Product Lifecycle | Medium | 2 | Server Side / Backend | M4
Task | FEAT-324: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Product Lifecycle' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-324 Product Lifecycle | Medium | 2 | Server Side / Backend | M4
Task | FEAT-324: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Product Lifecycle' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-324 Product Lifecycle | Medium | 3 | Server Side / Backend | M4
Task | FEAT-324: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Product Lifecycle' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-324 Product Lifecycle | Medium | 2 | Server Side / Backend | M4
Task | FEAT-324: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Product Lifecycle' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-324 Product Lifecycle | Medium | 2 | Server Side / Backend | M4
Story | FEAT-325 Call Center Sales | Covers 6 matrix requirement(s). - Upsells / cross sells functionalities are expected | E11 Bundles, Promotions & Pricing |  | Medium | 8 | Server Side / Backend | M4_Phase_4
Task | FEAT-325: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Call Center Sales' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-325 Call Center Sales | Medium | 2 | Server Side / Backend | M4
Task | FEAT-325: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Call Center Sales' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-325 Call Center Sales | Medium | 2 | Server Side / Backend | M4
Task | FEAT-325: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Call Center Sales' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-325 Call Center Sales | Medium | 3 | Server Side / Backend | M4
Task | FEAT-325: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Call Center Sales' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-325 Call Center Sales | Medium | 2 | Server Side / Backend | M4
Task | FEAT-325: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Call Center Sales' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-325 Call Center Sales | Medium | 2 | Server Side / Backend | M4
Story | FEAT-326 Loyalty | Covers 6 matrix requirement(s). The system should support loyalty point system to provide access to products, promotions and prices which are meant to be for guests based on their loyalty profile tier and also customize the journey … | E11 Bundles, Promotions & Pricing |  | Medium | 8 | Server Side / Backend | M4_Phase_4
Task | FEAT-326: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Loyalty' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-326 Loyalty | Medium | 2 | Server Side / Backend | M4
Task | FEAT-326: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Loyalty' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-326 Loyalty | Medium | 2 | Server Side / Backend | M4
Task | FEAT-326: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Loyalty' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-326 Loyalty | Medium | 3 | Server Side / Backend | M4
Task | FEAT-326: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Loyalty' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-326 Loyalty | Medium | 2 | Server Side / Backend | M4
Task | FEAT-326: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Loyalty' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-326 Loyalty | Medium | 2 | Server Side / Backend | M4
Story | FEAT-327 Accounting | Covers 6 matrix requirement(s). The system should be able to sell multi-attraction and combination tickets with configurable revenue split. Revenue rules should apply financial clearings based on products and client behaviors. The s… | E11 Bundles, Promotions & Pricing |  | Medium | 8 | Server Side / Backend | M4_Phase_4
Task | FEAT-327: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Accounting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-327 Accounting | Medium | 2 | Server Side / Backend | M4
Task | FEAT-327: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Accounting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-327 Accounting | Medium | 2 | Server Side / Backend | M4
Task | FEAT-327: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Accounting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-327 Accounting | Medium | 3 | Server Side / Backend | M4
Task | FEAT-327: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Accounting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-327 Accounting | Medium | 2 | Server Side / Backend | M4
Task | FEAT-327: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Accounting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-327 Accounting | Medium | 2 | Server Side / Backend | M4
Story | FEAT-328 Ai Engine | Covers 6 matrix requirement(s). System shall support AI-assisted promotion configuration. | E11 Bundles, Promotions & Pricing |  | High | 5 | Server Side / Backend | M3_Phase_3
Task | FEAT-328: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ai Engine' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-328 Ai Engine | High | 1 | Server Side / Backend | M3
Task | FEAT-328: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ai Engine' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-328 Ai Engine | High | 1 | Server Side / Backend | M3
Task | FEAT-328: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ai Engine' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-328 Ai Engine | High | 2 | Server Side / Backend | M3
Task | FEAT-328: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ai Engine' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-328 Ai Engine | High | 1 | Server Side / Backend | M3
Task | FEAT-328: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ai Engine' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-328 Ai Engine | High | 1 | Server Side / Backend | M3
Story | FEAT-329 Membership | Covers 5 matrix requirement(s). 1.General Annual card User Journey: 1) Customers need to visit the annual card information registration page to fill in their personal information 2) After the customer arrives at the counter, if the … | E11 Bundles, Promotions & Pricing |  | High | 5 | Server Side / Backend | M3_Phase_3
Task | FEAT-329: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Membership' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-329 Membership | High | 1 | Server Side / Backend | M3
Task | FEAT-329: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Membership' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-329 Membership | High | 1 | Server Side / Backend | M3
Task | FEAT-329: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Membership' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-329 Membership | High | 2 | Server Side / Backend | M3
Task | FEAT-329: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Membership' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-329 Membership | High | 1 | Server Side / Backend | M3
Task | FEAT-329: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Membership' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-329 Membership | High | 1 | Server Side / Backend | M3
Story | FEAT-330 Front Gate Sales | Covers 3 matrix requirement(s). The discounts,coupon or voucher redeem functionalities shall be available. | E11 Bundles, Promotions & Pricing |  | Medium | 8 | POS App | M4_Phase_4
Task | FEAT-330: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Front Gate Sales' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-330 Front Gate Sales | Medium | 2 | POS App | M4
Task | FEAT-330: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Front Gate Sales' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-330 Front Gate Sales | Medium | 1 | POS App | M4
Task | FEAT-330: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Front Gate Sales' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-330 Front Gate Sales | Medium | 2 | POS App | M4
Task | FEAT-330: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Front Gate Sales' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-330 Front Gate Sales | Medium | 2 | POS App | M4
Task | FEAT-330: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Front Gate Sales' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-330 Front Gate Sales | Medium | 1 | POS App | M4
Story | FEAT-331 Game And Ride Payment And Redemption | Covers 3 matrix requirement(s). Dynamic pricing for games - System should provide an ability to set up peak / nonpeak pricing for all the games / rides based on specific date / time | E11 Bundles, Promotions & Pricing |  | Medium | 8 | Server Side / Backend | M4_Phase_4
Task | FEAT-331: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Game And Ride Payment And Redemption' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-331 Game And Ride Payment And Redemption | Medium | 1 | Server Side / Backend | M4
Task | FEAT-331: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Game And Ride Payment And Redemption' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-331 Game And Ride Payment And Redemption | Medium | 2 | Server Side / Backend | M4
Task | FEAT-331: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Game And Ride Payment And Redemption' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-331 Game And Ride Payment And Redemption | Medium | 2 | Server Side / Backend | M4
Task | FEAT-331: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Game And Ride Payment And Redemption' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-331 Game And Ride Payment And Redemption | Medium | 1 | Server Side / Backend | M4
Task | FEAT-331: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Game And Ride Payment And Redemption' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-331 Game And Ride Payment And Redemption | Medium | 1 | Server Side / Backend | M4
Story | FEAT-332 Campaign Management | Covers 3 matrix requirement(s). Campaign Templates System shall provide reusable campaign templates for ticket sales, memberships, annual passes, loyalty promotions, events, seasonal promotions, abandoned carts, birthday campaigns, … | E11 Bundles, Promotions & Pricing |  | High | 8 | Server Side / Backend | M3_Phase_3
Task | FEAT-332: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Campaign Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-332 Campaign Management | High | 1 | Server Side / Backend | M3
Task | FEAT-332: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Campaign Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-332 Campaign Management | High | 2 | Server Side / Backend | M3
Task | FEAT-332: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Campaign Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-332 Campaign Management | High | 2 | Server Side / Backend | M3
Task | FEAT-332: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Campaign Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-332 Campaign Management | High | 1 | Server Side / Backend | M3
Task | FEAT-332: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Campaign Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-332 Campaign Management | High | 1 | Server Side / Backend | M3
Story | FEAT-333 Case Management And Sla | Covers 3 matrix requirement(s). Cross-Sell & Upsell Automation System shall automatically recommend products, memberships, packages, upgrades, F&B offers, retail items, experiences, and loyalty rewards based on guest behavior and pu… | E11 Bundles, Promotions & Pricing |  | Medium | 8 | Server Side / Backend | M4_Phase_4
Task | FEAT-333: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Case Management And Sla' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-333 Case Management And Sla | Medium | 1 | Server Side / Backend | M4
Task | FEAT-333: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Case Management And Sla' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-333 Case Management And Sla | Medium | 2 | Server Side / Backend | M4
Task | FEAT-333: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Case Management And Sla' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-333 Case Management And Sla | Medium | 2 | Server Side / Backend | M4
Task | FEAT-333: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Case Management And Sla' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-333 Case Management And Sla | Medium | 1 | Server Side / Backend | M4
Task | FEAT-333: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Case Management And Sla' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-333 Case Management And Sla | Medium | 1 | Server Side / Backend | M4
Story | FEAT-334 Newsletter And Email Marketing | Covers 3 matrix requirement(s). Newsletter Templates System shall provide reusable templates for ticket promotions, events, memberships, loyalty campaigns, seasonal campaigns, surveys, announcements, operational updates, and venue c… | E11 Bundles, Promotions & Pricing |  | Medium | 8 | Server Side / Backend | M4_Phase_4
Task | FEAT-334: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Newsletter And Email Marketing' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-334 Newsletter And Email Marketing | Medium | 1 | Server Side / Backend | M4
Task | FEAT-334: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Newsletter And Email Marketing' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-334 Newsletter And Email Marketing | Medium | 2 | Server Side / Backend | M4
Task | FEAT-334: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Newsletter And Email Marketing' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-334 Newsletter And Email Marketing | Medium | 2 | Server Side / Backend | M4
Task | FEAT-334: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Newsletter And Email Marketing' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-334 Newsletter And Email Marketing | Medium | 1 | Server Side / Backend | M4
Task | FEAT-334: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Newsletter And Email Marketing' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-334 Newsletter And Email Marketing | Medium | 1 | Server Side / Backend | M4
Story | FEAT-335 Ticket Media | Covers 2 matrix requirement(s). The system should allow configuration of ticket templates. Tickets can have fixed elements and dynamic fields. There should be possibility to insert visuals and 2D codes and hide the price of the tick… | E11 Bundles, Promotions & Pricing |  | High | 2 | Server Side / Backend | M3_Phase_3
Task | FEAT-335: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ticket Media' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-335 Ticket Media | High | 1 | Server Side / Backend | M3
Task | FEAT-335: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ticket Media' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-335 Ticket Media | High | 1 | Server Side / Backend | M3
Task | FEAT-335: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ticket Media' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-335 Ticket Media | High | 1 | Server Side / Backend | M3
Task | FEAT-335: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ticket Media' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-335 Ticket Media | High | 1 | Server Side / Backend | M3
Task | FEAT-335: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ticket Media' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-335 Ticket Media | High | 1 | Server Side / Backend | M3
Story | FEAT-336 Virtual Queue | Covers 2 matrix requirement(s). Support queue privileges based on memberships, annual passes, loyalty tiers, and promotions. | E11 Bundles, Promotions & Pricing |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-336: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Virtual Queue' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-336 Virtual Queue | Medium | 1 | Server Side / Backend | M4
Task | FEAT-336: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Virtual Queue' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-336 Virtual Queue | Medium | 2 | Server Side / Backend | M4
Task | FEAT-336: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Virtual Queue' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-336 Virtual Queue | Medium | 2 | Server Side / Backend | M4
Task | FEAT-336: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Virtual Queue' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-336 Virtual Queue | Medium | 1 | Server Side / Backend | M4
Task | FEAT-336: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Virtual Queue' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-336 Virtual Queue | Medium | 1 | Server Side / Backend | M4
Story | FEAT-337 Ai Governance | Covers 2 matrix requirement(s). System shall require approval before AI-driven pricing changes. | E11 Bundles, Promotions & Pricing |  | High | 3 | Server Side / Backend | M3_Phase_3
Task | FEAT-337: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ai Governance' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-337 Ai Governance | High | 1 | Server Side / Backend | M3
Task | FEAT-337: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ai Governance' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-337 Ai Governance | High | 1 | Server Side / Backend | M3
Task | FEAT-337: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ai Governance' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-337 Ai Governance | High | 1 | Server Side / Backend | M3
Task | FEAT-337: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ai Governance' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-337 Ai Governance | High | 1 | Server Side / Backend | M3
Task | FEAT-337: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ai Governance' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-337 Ai Governance | High | 1 | Server Side / Backend | M3
Story | FEAT-338 Api Business Coverage | Covers 2 matrix requirement(s). APIs shall expose pricing calculations, price recommendations and pricing rule management. | E11 Bundles, Promotions & Pricing |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-338: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Api Business Coverage' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-338 Api Business Coverage | Medium | 1 | Server Side / Backend | M4
Task | FEAT-338: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Api Business Coverage' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-338 Api Business Coverage | Medium | 2 | Server Side / Backend | M4
Task | FEAT-338: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Api Business Coverage' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-338 Api Business Coverage | Medium | 2 | Server Side / Backend | M4
Task | FEAT-338: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Api Business Coverage' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-338 Api Business Coverage | Medium | 1 | Server Side / Backend | M4
Task | FEAT-338: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Api Business Coverage' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-338 Api Business Coverage | Medium | 1 | Server Side / Backend | M4
Story | FEAT-339 Branding And White-Label Configuration | Covers 2 matrix requirement(s). Banner Management - System shall support configurable promotional banners. | E11 Bundles, Promotions & Pricing |  | High | 3 | Mobile App | M3_Phase_3
Task | FEAT-339: UI screens (iOS & Android) | Implement shared + platform UI components. Acceptance: 'Branding And White-Label Configuration' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-339 Branding And White-Label Configuration | High | 1 | Mobile App | M3
Task | FEAT-339: State & API integration | Data layer, caching and API wiring. Acceptance: 'Branding And White-Label Configuration' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-339 Branding And White-Label Configuration | High | 1 | Mobile App | M3
Task | FEAT-339: Offline & push handling | Offline storage, sync and push notifications. Acceptance: 'Branding And White-Label Configuration' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-339 Branding And White-Label Configuration | High | 1 | Mobile App | M3
Task | FEAT-339: Mobile E2E tests | Automated tests across iOS/Android. Acceptance: 'Branding And White-Label Configuration' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-339 Branding And White-Label Configuration | High | 1 | Mobile App | M3
Story | FEAT-340 Authentication And Login | Covers 2 matrix requirement(s). Dynamic Pricing Display - System shall display dynamic pricing. | E11 Bundles, Promotions & Pricing |  | Medium | 5 | Mobile App | M4_Phase_4
Task | FEAT-340: UI screens (iOS & Android) | Implement shared + platform UI components. Acceptance: 'Authentication And Login' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-340 Authentication And Login | Medium | 2 | Mobile App | M4
Task | FEAT-340: State & API integration | Data layer, caching and API wiring. Acceptance: 'Authentication And Login' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-340 Authentication And Login | Medium | 2 | Mobile App | M4
Task | FEAT-340: Offline & push handling | Offline storage, sync and push notifications. Acceptance: 'Authentication And Login' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-340 Authentication And Login | Medium | 1 | Mobile App | M4
Task | FEAT-340: Mobile E2E tests | Automated tests across iOS/Android. Acceptance: 'Authentication And Login' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-340 Authentication And Login | Medium | 1 | Mobile App | M4
Story | FEAT-341 Seat Revenue Management And Forecasting | Covers 2 matrix requirement(s). Dynamic Seat Pricing System shall support dynamic seat pricing. | E11 Bundles, Promotions & Pricing |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-341: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Seat Revenue Management And Forecasting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-341 Seat Revenue Management And Forecasting | Medium | 1 | Server Side / Backend | M4
Task | FEAT-341: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Seat Revenue Management And Forecasting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-341 Seat Revenue Management And Forecasting | Medium | 2 | Server Side / Backend | M4
Task | FEAT-341: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Seat Revenue Management And Forecasting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-341 Seat Revenue Management And Forecasting | Medium | 2 | Server Side / Backend | M4
Task | FEAT-341: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Seat Revenue Management And Forecasting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-341 Seat Revenue Management And Forecasting | Medium | 1 | Server Side / Backend | M4
Task | FEAT-341: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Seat Revenue Management And Forecasting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-341 Seat Revenue Management And Forecasting | Medium | 1 | Server Side / Backend | M4
Story | FEAT-342 Reviews And Ratings | Covers 2 matrix requirement(s). AI Topic Detection AI shall automatically identify recurring topics including pricing, staff service, wait times, cleanliness, ticketing experience, memberships, loyalty programs, food quality, events… | E11 Bundles, Promotions & Pricing |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-342: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Reviews And Ratings' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-342 Reviews And Ratings | Medium | 1 | Server Side / Backend | M4
Task | FEAT-342: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Reviews And Ratings' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-342 Reviews And Ratings | Medium | 2 | Server Side / Backend | M4
Task | FEAT-342: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Reviews And Ratings' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-342 Reviews And Ratings | Medium | 2 | Server Side / Backend | M4
Task | FEAT-342: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Reviews And Ratings' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-342 Reviews And Ratings | Medium | 1 | Server Side / Backend | M4
Task | FEAT-342: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Reviews And Ratings' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-342 Reviews And Ratings | Medium | 1 | Server Side / Backend | M4
Story | FEAT-343 Notifications And Messaging | Covers 2 matrix requirement(s). Loyalty Notifications System shall automatically notify guests regarding points earned, points redeemed, tier changes, reward availability, promotions, point expirations, and loyalty campaigns. | E11 Bundles, Promotions & Pricing |  | High | 2 | Server Side / Backend | M3_Phase_3
Task | FEAT-343: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Notifications And Messaging' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-343 Notifications And Messaging | High | 1 | Server Side / Backend | M3
Task | FEAT-343: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Notifications And Messaging' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-343 Notifications And Messaging | High | 1 | Server Side / Backend | M3
Task | FEAT-343: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Notifications And Messaging' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-343 Notifications And Messaging | High | 1 | Server Side / Backend | M3
Task | FEAT-343: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Notifications And Messaging' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-343 Notifications And Messaging | High | 1 | Server Side / Backend | M3
Task | FEAT-343: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Notifications And Messaging' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-343 Notifications And Messaging | High | 1 | Server Side / Backend | M3
Story | FEAT-344 Seo Management And Optimization | Covers 2 matrix requirement(s). Dynamic SEO Generation SEO metadata shall be automatically generated for events, attractions, memberships, ticket types, promotions, and dynamically generated pages based on configurable templates. | E11 Bundles, Promotions & Pricing |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-344: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Seo Management And Optimization' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-344 Seo Management And Optimization | Medium | 1 | Server Side / Backend | M4
Task | FEAT-344: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Seo Management And Optimization' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-344 Seo Management And Optimization | Medium | 2 | Server Side / Backend | M4
Task | FEAT-344: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Seo Management And Optimization' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-344 Seo Management And Optimization | Medium | 2 | Server Side / Backend | M4
Task | FEAT-344: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Seo Management And Optimization' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-344 Seo Management And Optimization | Medium | 1 | Server Side / Backend | M4
Task | FEAT-344: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Seo Management And Optimization' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-344 Seo Management And Optimization | Medium | 1 | Server Side / Backend | M4
Story | FEAT-345 B2B Sales | Covers 1 matrix requirement(s). The system should expose APIs. Systems allowing the guest to perform online ticket purchasing from Web-sites / mobile applications. The functionalities should include: - Selling all the type of ticket… | E11 Bundles, Promotions & Pricing |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-345: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'B2B Sales' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-345 B2B Sales | Medium | 1 | Server Side / Backend | M4
Task | FEAT-345: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'B2B Sales' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-345 B2B Sales | Medium | 2 | Server Side / Backend | M4
Task | FEAT-345: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'B2B Sales' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-345 B2B Sales | Medium | 2 | Server Side / Backend | M4
Task | FEAT-345: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'B2B Sales' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-345 B2B Sales | Medium | 1 | Server Side / Backend | M4
Task | FEAT-345: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'B2B Sales' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-345 B2B Sales | Medium | 1 | Server Side / Backend | M4
Story | FEAT-346 Digital Waiver Management | Covers 1 matrix requirement(s). The system should allow sales of free tickets. These tickets can be configured as a standard ticket with a price of zero or as a full price ticket with a 100% discount. | E11 Bundles, Promotions & Pricing |  | High | 1 | Server Side / Backend | M3_Phase_3
Task | FEAT-346: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Digital Waiver Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-346 Digital Waiver Management | High | 1 | Server Side / Backend | M3
Task | FEAT-346: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Digital Waiver Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-346 Digital Waiver Management | High | 1 | Server Side / Backend | M3
Task | FEAT-346: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Digital Waiver Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-346 Digital Waiver Management | High | 1 | Server Side / Backend | M3
Task | FEAT-346: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Digital Waiver Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-346 Digital Waiver Management | High | 1 | Server Side / Backend | M3
Task | FEAT-346: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Digital Waiver Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-346 Digital Waiver Management | High | 1 | Server Side / Backend | M3
Story | FEAT-347 Order Management | Covers 1 matrix requirement(s). Order Sales 1) The POS home page displays available products by category, for the current POS. 2) Staff can click a specific product to add it to the cart; quantity can be adjusted 3) The system displ… | E11 Bundles, Promotions & Pricing |  | High | 1 | POS App | M3_Phase_3
Task | FEAT-347: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Order Management' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-347 Order Management | High | 1 | POS App | M3
Task | FEAT-347: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Order Management' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-347 Order Management | High | 1 | POS App | M3
Task | FEAT-347: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Order Management' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-347 Order Management | High | 1 | POS App | M3
Task | FEAT-347: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Order Management' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-347 Order Management | High | 1 | POS App | M3
Task | FEAT-347: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Order Management' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-347 Order Management | High | 1 | POS App | M3
Story | FEAT-348 Access Control System | Covers 1 matrix requirement(s). One QR to rule them all—single barcode that grants park entry, ride entitlement, meal voucher, coupon, Photo Voucher download, and re-entry rights | E11 Bundles, Promotions & Pricing |  | High | 3 | Server Side / Backend | M3_Phase_3
Task | FEAT-348: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Access Control System' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-348 Access Control System | High | 1 | Server Side / Backend | M3
Task | FEAT-348: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Access Control System' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-348 Access Control System | High | 1 | Server Side / Backend | M3
Task | FEAT-348: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Access Control System' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-348 Access Control System | High | 1 | Server Side / Backend | M3
Task | FEAT-348: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Access Control System' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-348 Access Control System | High | 1 | Server Side / Backend | M3
Task | FEAT-348: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Access Control System' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-348 Access Control System | High | 1 | Server Side / Backend | M3
Story | FEAT-349 Profile Management | Covers 1 matrix requirement(s). Generate AI insights such as predicted next visit, churn risk, preferred products, preferred attractions, lifetime value, and upsell recommendations. | E11 Bundles, Promotions & Pricing |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-349: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Profile Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-349 Profile Management | Medium | 1 | Server Side / Backend | M4
Task | FEAT-349: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Profile Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-349 Profile Management | Medium | 2 | Server Side / Backend | M4
Task | FEAT-349: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Profile Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-349 Profile Management | Medium | 2 | Server Side / Backend | M4
Task | FEAT-349: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Profile Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-349 Profile Management | Medium | 1 | Server Side / Backend | M4
Task | FEAT-349: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Profile Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-349 Profile Management | Medium | 1 | Server Side / Backend | M4
Story | FEAT-350 Portfolio And Entitlement Management | Covers 1 matrix requirement(s). Generate AI-driven recommendations, expiring entitlement alerts, cross-sell opportunities, and portfolio optimization suggestions. | E11 Bundles, Promotions & Pricing |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-350: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Portfolio And Entitlement Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-350 Portfolio And Entitlement Management | Medium | 1 | Server Side / Backend | M4
Task | FEAT-350: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Portfolio And Entitlement Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-350 Portfolio And Entitlement Management | Medium | 2 | Server Side / Backend | M4
Task | FEAT-350: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Portfolio And Entitlement Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-350 Portfolio And Entitlement Management | Medium | 2 | Server Side / Backend | M4
Task | FEAT-350: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Portfolio And Entitlement Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-350 Portfolio And Entitlement Management | Medium | 1 | Server Side / Backend | M4
Task | FEAT-350: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Portfolio And Entitlement Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-350 Portfolio And Entitlement Management | Medium | 1 | Server Side / Backend | M4
Story | FEAT-351 Ai Governance And Explainability | Covers 1 matrix requirement(s). Approval Before Execution AI recommendations affecting pricing or financial operations shall require approval before execution | E11 Bundles, Promotions & Pricing |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-351: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ai Governance And Explainability' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-351 Ai Governance And Explainability | Medium | 1 | Server Side / Backend | M4
Task | FEAT-351: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ai Governance And Explainability' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-351 Ai Governance And Explainability | Medium | 2 | Server Side / Backend | M4
Task | FEAT-351: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ai Governance And Explainability' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-351 Ai Governance And Explainability | Medium | 2 | Server Side / Backend | M4
Task | FEAT-351: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ai Governance And Explainability' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-351 Ai Governance And Explainability | Medium | 1 | Server Side / Backend | M4
Task | FEAT-351: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ai Governance And Explainability' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-351 Ai Governance And Explainability | Medium | 1 | Server Side / Backend | M4
Story | FEAT-352 Module Marketplace And Management | Covers 1 matrix requirement(s). Module Pricing - System shall support module-specific pricing. | E11 Bundles, Promotions & Pricing |  | High | 3 | Server Side / Backend | M3_Phase_3
Task | FEAT-352: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Module Marketplace And Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-352 Module Marketplace And Management | High | 1 | Server Side / Backend | M3
Task | FEAT-352: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Module Marketplace And Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-352 Module Marketplace And Management | High | 1 | Server Side / Backend | M3
Task | FEAT-352: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Module Marketplace And Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-352 Module Marketplace And Management | High | 1 | Server Side / Backend | M3
Task | FEAT-352: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Module Marketplace And Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-352 Module Marketplace And Management | High | 1 | Server Side / Backend | M3
Task | FEAT-352: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Module Marketplace And Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-352 Module Marketplace And Management | High | 1 | Server Side / Backend | M3
Story | FEAT-353 Seat Map Builder | Covers 1 matrix requirement(s). Section Builder Manage venue sections and pricing zones. | E11 Bundles, Promotions & Pricing |  | High | 3 | Server Side / Backend | M3_Phase_3
Task | FEAT-353: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Seat Map Builder' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-353 Seat Map Builder | High | 1 | Server Side / Backend | M3
Task | FEAT-353: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Seat Map Builder' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-353 Seat Map Builder | High | 1 | Server Side / Backend | M3
Task | FEAT-353: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Seat Map Builder' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-353 Seat Map Builder | High | 1 | Server Side / Backend | M3
Task | FEAT-353: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Seat Map Builder' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-353 Seat Map Builder | High | 1 | Server Side / Backend | M3
Task | FEAT-353: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Seat Map Builder' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-353 Seat Map Builder | High | 1 | Server Side / Backend | M3
Story | FEAT-354 Seat Selection And Assignment | Covers 1 matrix requirement(s). Price Filters System shall support price filters. | E11 Bundles, Promotions & Pricing |  | High | 3 | Server Side / Backend | M3_Phase_3
Task | FEAT-354: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Seat Selection And Assignment' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-354 Seat Selection And Assignment | High | 1 | Server Side / Backend | M3
Task | FEAT-354: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Seat Selection And Assignment' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-354 Seat Selection And Assignment | High | 1 | Server Side / Backend | M3
Task | FEAT-354: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Seat Selection And Assignment' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-354 Seat Selection And Assignment | High | 1 | Server Side / Backend | M3
Task | FEAT-354: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Seat Selection And Assignment' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-354 Seat Selection And Assignment | High | 1 | Server Side / Backend | M3
Task | FEAT-354: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Seat Selection And Assignment' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-354 Seat Selection And Assignment | High | 1 | Server Side / Backend | M3
Story | FEAT-355 Surveys And Feedback | Covers 1 matrix requirement(s). AI Topic Detection AI shall automatically identify recurring topics, operational issues, service gaps, staff performance concerns, pricing feedback, attraction feedback, and guest preferences. | E11 Bundles, Promotions & Pricing |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-355: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Surveys And Feedback' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-355 Surveys And Feedback | Medium | 1 | Server Side / Backend | M4
Task | FEAT-355: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Surveys And Feedback' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-355 Surveys And Feedback | Medium | 2 | Server Side / Backend | M4
Task | FEAT-355: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Surveys And Feedback' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-355 Surveys And Feedback | Medium | 2 | Server Side / Backend | M4
Task | FEAT-355: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Surveys And Feedback' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-355 Surveys And Feedback | Medium | 1 | Server Side / Backend | M4
Task | FEAT-355: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Surveys And Feedback' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-355 Surveys And Feedback | Medium | 1 | Server Side / Backend | M4
Story | FEAT-356 Omnichannel Communications And Ai Chatbot | Covers 1 matrix requirement(s). Marketing Integration Chat interactions shall integrate with marketing campaigns, promotions, abandoned cart recovery, loyalty offers, and personalized guest engagement initiatives. | E11 Bundles, Promotions & Pricing |  | High | 5 | Server Side / Backend | M3_Phase_3
Task | FEAT-356: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Omnichannel Communications And Ai Chatbot' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-356 Omnichannel Communications And Ai Chatbot | High | 1 | Server Side / Backend | M3
Task | FEAT-356: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Omnichannel Communications And Ai Chatbot' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-356 Omnichannel Communications And Ai Chatbot | High | 2 | Server Side / Backend | M3
Task | FEAT-356: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Omnichannel Communications And Ai Chatbot' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-356 Omnichannel Communications And Ai Chatbot | High | 2 | Server Side / Backend | M3
Task | FEAT-356: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Omnichannel Communications And Ai Chatbot' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-356 Omnichannel Communications And Ai Chatbot | High | 1 | Server Side / Backend | M3
Task | FEAT-356: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Omnichannel Communications And Ai Chatbot' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-356 Omnichannel Communications And Ai Chatbot | High | 1 | Server Side / Backend | M3
Story | FEAT-357 Consent Management | Covers 1 matrix requirement(s). Marketing Consent Management Guests shall be able to provide, modify, withdraw, and manage consent for marketing communications including email, SMS, WhatsApp, push notifications, newsletters, surveys… | E11 Bundles, Promotions & Pricing |  | High | 1 | Server Side / Backend | M3_Phase_3
Task | FEAT-357: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Consent Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-357 Consent Management | High | 1 | Server Side / Backend | M3
Task | FEAT-357: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Consent Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-357 Consent Management | High | 1 | Server Side / Backend | M3
Task | FEAT-357: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Consent Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-357 Consent Management | High | 1 | Server Side / Backend | M3
Task | FEAT-357: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Consent Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-357 Consent Management | High | 1 | Server Side / Backend | M3
Task | FEAT-357: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Consent Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-357 Consent Management | High | 1 | Server Side / Backend | M3
Story | FEAT-358 Audience Segmentation | Covers 1 matrix requirement(s). AI Upgrade Opportunities AI shall identify guests likely to purchase memberships, loyalty upgrades, premium experiences, packages, annual passes, or upsell products. | E11 Bundles, Promotions & Pricing |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-358: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Audience Segmentation' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-358 Audience Segmentation | Medium | 1 | Server Side / Backend | M4
Task | FEAT-358: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Audience Segmentation' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-358 Audience Segmentation | Medium | 2 | Server Side / Backend | M4
Task | FEAT-358: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Audience Segmentation' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-358 Audience Segmentation | Medium | 2 | Server Side / Backend | M4
Task | FEAT-358: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Audience Segmentation' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-358 Audience Segmentation | Medium | 1 | Server Side / Backend | M4
Task | FEAT-358: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Audience Segmentation' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E11 Bundles, Promotions & Pricing | FEAT-358 Audience Segmentation | Medium | 1 | Server Side / Backend | M4
Story | FEAT-359 Authentication And Login | Covers 39 matrix requirement(s). User Registration - System shall support user registration. | E12 Guest Mobile Experience |  | Medium | 13 | Mobile App | M4_Phase_4
Task | FEAT-359: UI screens (iOS & Android) | Implement shared + platform UI components. Acceptance: 'Authentication And Login' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-359 Authentication And Login | Medium | 13 | Mobile App | M4
Task | FEAT-359: State & API integration | Data layer, caching and API wiring. Acceptance: 'Authentication And Login' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-359 Authentication And Login | Medium | 13 | Mobile App | M4
Task | FEAT-359: Offline & push handling | Offline storage, sync and push notifications. Acceptance: 'Authentication And Login' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-359 Authentication And Login | Medium | 8 | Mobile App | M4
Task | FEAT-359: Mobile E2E tests | Automated tests across iOS/Android. Acceptance: 'Authentication And Login' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-359 Authentication And Login | Medium | 8 | Mobile App | M4
Story | FEAT-360 Branding And White-Label Configuration | Covers 22 matrix requirement(s). Logo Management - System shall allow changing the mobile app logo through configuration. | E12 Guest Mobile Experience |  | High | 13 | Mobile App | M3_Phase_3
Task | FEAT-360: UI screens (iOS & Android) | Implement shared + platform UI components. Acceptance: 'Branding And White-Label Configuration' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-360 Branding And White-Label Configuration | High | 5 | Mobile App | M3
Task | FEAT-360: State & API integration | Data layer, caching and API wiring. Acceptance: 'Branding And White-Label Configuration' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-360 Branding And White-Label Configuration | High | 5 | Mobile App | M3
Task | FEAT-360: Offline & push handling | Offline storage, sync and push notifications. Acceptance: 'Branding And White-Label Configuration' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-360 Branding And White-Label Configuration | High | 3 | Mobile App | M3
Task | FEAT-360: Mobile E2E tests | Automated tests across iOS/Android. Acceptance: 'Branding And White-Label Configuration' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-360 Branding And White-Label Configuration | High | 3 | Mobile App | M3
Story | FEAT-361 Safety And Incident Reporting | Covers 6 matrix requirement(s). Hazard Reporting - Users shall submit hazard reports. | E12 Guest Mobile Experience |  | High | 5 | Mobile App | M3_Phase_3
Task | FEAT-361: UI screens (iOS & Android) | Implement shared + platform UI components. Acceptance: 'Safety And Incident Reporting' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-361 Safety And Incident Reporting | High | 2 | Mobile App | M3
Task | FEAT-361: State & API integration | Data layer, caching and API wiring. Acceptance: 'Safety And Incident Reporting' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-361 Safety And Incident Reporting | High | 2 | Mobile App | M3
Task | FEAT-361: Offline & push handling | Offline storage, sync and push notifications. Acceptance: 'Safety And Incident Reporting' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-361 Safety And Incident Reporting | High | 1 | Mobile App | M3
Task | FEAT-361: Mobile E2E tests | Automated tests across iOS/Android. Acceptance: 'Safety And Incident Reporting' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-361 Safety And Incident Reporting | High | 1 | Mobile App | M3
Story | FEAT-362 Mobile App Core (Ios And Android) | Covers 5 matrix requirement(s). iOS Mobile Application - System shall provide a native iOS application. | E12 Guest Mobile Experience |  | High | 8 | Mobile App | M3_Phase_3
Task | FEAT-362: UI screens (iOS & Android) | Implement shared + platform UI components. Acceptance: 'Mobile App Core (Ios And Android)' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-362 Mobile App Core (Ios And Android) | High | 3 | Mobile App | M3
Task | FEAT-362: State & API integration | Data layer, caching and API wiring. Acceptance: 'Mobile App Core (Ios And Android)' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-362 Mobile App Core (Ios And Android) | High | 3 | Mobile App | M3
Task | FEAT-362: Offline & push handling | Offline storage, sync and push notifications. Acceptance: 'Mobile App Core (Ios And Android)' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-362 Mobile App Core (Ios And Android) | High | 2 | Mobile App | M3
Task | FEAT-362: Mobile E2E tests | Automated tests across iOS/Android. Acceptance: 'Mobile App Core (Ios And Android)' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-362 Mobile App Core (Ios And Android) | High | 2 | Mobile App | M3
Story | FEAT-363 Media Capture And Notes | Covers 5 matrix requirement(s). Photo Capture - Users shall capture photos. | E12 Guest Mobile Experience |  | High | 5 | Mobile App | M3_Phase_3
Task | FEAT-363: UI screens (iOS & Android) | Implement shared + platform UI components. Acceptance: 'Media Capture And Notes' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-363 Media Capture And Notes | High | 2 | Mobile App | M3
Task | FEAT-363: State & API integration | Data layer, caching and API wiring. Acceptance: 'Media Capture And Notes' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-363 Media Capture And Notes | High | 2 | Mobile App | M3
Task | FEAT-363: Offline & push handling | Offline storage, sync and push notifications. Acceptance: 'Media Capture And Notes' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-363 Media Capture And Notes | High | 1 | Mobile App | M3
Task | FEAT-363: Mobile E2E tests | Automated tests across iOS/Android. Acceptance: 'Media Capture And Notes' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-363 Media Capture And Notes | High | 1 | Mobile App | M3
Story | FEAT-364 Ai Assistant And Voice Interface | Covers 5 matrix requirement(s). AI Assistant - System shall provide an AI assistant for employees. | E12 Guest Mobile Experience |  | Medium | 8 | Mobile App | M4_Phase_4
Task | FEAT-364: UI screens (iOS & Android) | Implement shared + platform UI components. Acceptance: 'Ai Assistant And Voice Interface' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-364 Ai Assistant And Voice Interface | Medium | 3 | Mobile App | M4
Task | FEAT-364: State & API integration | Data layer, caching and API wiring. Acceptance: 'Ai Assistant And Voice Interface' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-364 Ai Assistant And Voice Interface | Medium | 3 | Mobile App | M4
Task | FEAT-364: Offline & push handling | Offline storage, sync and push notifications. Acceptance: 'Ai Assistant And Voice Interface' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-364 Ai Assistant And Voice Interface | Medium | 2 | Mobile App | M4
Task | FEAT-364: Mobile E2E tests | Automated tests across iOS/Android. Acceptance: 'Ai Assistant And Voice Interface' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-364 Ai Assistant And Voice Interface | Medium | 2 | Mobile App | M4
Story | FEAT-365 Approvals And Notifications | Covers 4 matrix requirement(s). Approval Inbox - Users shall view pending approvals. | E12 Guest Mobile Experience |  | High | 5 | Mobile App | M3_Phase_3
Task | FEAT-365: UI screens (iOS & Android) | Implement shared + platform UI components. Acceptance: 'Approvals And Notifications' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-365 Approvals And Notifications | High | 2 | Mobile App | M3
Task | FEAT-365: State & API integration | Data layer, caching and API wiring. Acceptance: 'Approvals And Notifications' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-365 Approvals And Notifications | High | 2 | Mobile App | M3
Task | FEAT-365: Offline & push handling | Offline storage, sync and push notifications. Acceptance: 'Approvals And Notifications' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-365 Approvals And Notifications | High | 1 | Mobile App | M3
Task | FEAT-365: Mobile E2E tests | Automated tests across iOS/Android. Acceptance: 'Approvals And Notifications' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-365 Approvals And Notifications | High | 1 | Mobile App | M3
Story | FEAT-366 Virtual Queue | Covers 3 matrix requirement(s). SMS, email, or whats app , app push notifications when it’s nearly their turn. Allow guests to reserve time slots in advance. | E12 Guest Mobile Experience |  | High | 2 | Mobile App | M3_Phase_3
Task | FEAT-366: UI screens (iOS & Android) | Implement shared + platform UI components. Acceptance: 'Virtual Queue' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-366 Virtual Queue | High | 1 | Mobile App | M3
Task | FEAT-366: State & API integration | Data layer, caching and API wiring. Acceptance: 'Virtual Queue' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-366 Virtual Queue | High | 1 | Mobile App | M3
Task | FEAT-366: Offline & push handling | Offline storage, sync and push notifications. Acceptance: 'Virtual Queue' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-366 Virtual Queue | High | 1 | Mobile App | M3
Task | FEAT-366: Mobile E2E tests | Automated tests across iOS/Android. Acceptance: 'Virtual Queue' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-366 Virtual Queue | High | 1 | Mobile App | M3
Story | FEAT-367 Recommendation Engine | Covers 1 matrix requirement(s). System shall provide mobile app recommendations. | E12 Guest Mobile Experience |  | Medium | 5 | Mobile App | M4_Phase_4
Task | FEAT-367: UI screens (iOS & Android) | Implement shared + platform UI components. Acceptance: 'Recommendation Engine' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-367 Recommendation Engine | Medium | 2 | Mobile App | M4
Task | FEAT-367: State & API integration | Data layer, caching and API wiring. Acceptance: 'Recommendation Engine' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-367 Recommendation Engine | Medium | 2 | Mobile App | M4
Task | FEAT-367: Offline & push handling | Offline storage, sync and push notifications. Acceptance: 'Recommendation Engine' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-367 Recommendation Engine | Medium | 1 | Mobile App | M4
Task | FEAT-367: Mobile E2E tests | Automated tests across iOS/Android. Acceptance: 'Recommendation Engine' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-367 Recommendation Engine | Medium | 1 | Mobile App | M4
Story | FEAT-368 Accounting | Covers 1 matrix requirement(s). Mobile Approvals - System shall support approval actions through mobile applications. | E12 Guest Mobile Experience |  | High | 3 | Mobile App | M3_Phase_3
Task | FEAT-368: UI screens (iOS & Android) | Implement shared + platform UI components. Acceptance: 'Accounting' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-368 Accounting | High | 1 | Mobile App | M3
Task | FEAT-368: State & API integration | Data layer, caching and API wiring. Acceptance: 'Accounting' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-368 Accounting | High | 1 | Mobile App | M3
Task | FEAT-368: Offline & push handling | Offline storage, sync and push notifications. Acceptance: 'Accounting' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-368 Accounting | High | 1 | Mobile App | M3
Task | FEAT-368: Mobile E2E tests | Automated tests across iOS/Android. Acceptance: 'Accounting' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-368 Accounting | High | 1 | Mobile App | M3
Story | FEAT-369 Reporting And Dashboards | Covers 1 matrix requirement(s). Accreditation Branding - System shall support tenant-specific accreditation branding. | E12 Guest Mobile Experience |  | High | 3 | Mobile App | M3_Phase_3
Task | FEAT-369: UI screens (iOS & Android) | Implement shared + platform UI components. Acceptance: 'Reporting And Dashboards' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-369 Reporting And Dashboards | High | 1 | Mobile App | M3
Task | FEAT-369: State & API integration | Data layer, caching and API wiring. Acceptance: 'Reporting And Dashboards' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-369 Reporting And Dashboards | High | 1 | Mobile App | M3
Task | FEAT-369: Offline & push handling | Offline storage, sync and push notifications. Acceptance: 'Reporting And Dashboards' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-369 Reporting And Dashboards | High | 1 | Mobile App | M3
Task | FEAT-369: Mobile E2E tests | Automated tests across iOS/Android. Acceptance: 'Reporting And Dashboards' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-369 Reporting And Dashboards | High | 1 | Mobile App | M3
Story | FEAT-370 Api Business Coverage | Covers 1 matrix requirement(s). APIs shall support email, SMS, push notifications, WhatsApp notifications and notification status retrieval. | E12 Guest Mobile Experience |  | High | 1 | Mobile App | M3_Phase_3
Task | FEAT-370: UI screens (iOS & Android) | Implement shared + platform UI components. Acceptance: 'Api Business Coverage' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-370 Api Business Coverage | High | 1 | Mobile App | M3
Task | FEAT-370: State & API integration | Data layer, caching and API wiring. Acceptance: 'Api Business Coverage' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-370 Api Business Coverage | High | 1 | Mobile App | M3
Task | FEAT-370: Offline & push handling | Offline storage, sync and push notifications. Acceptance: 'Api Business Coverage' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-370 Api Business Coverage | High | 1 | Mobile App | M3
Task | FEAT-370: Mobile E2E tests | Automated tests across iOS/Android. Acceptance: 'Api Business Coverage' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E12 Guest Mobile Experience | FEAT-370 Api Business Coverage | High | 1 | Mobile App | M3
Story | FEAT-371 Shift Opening And Closing | Covers 7 matrix requirement(s). The system should be able to manage end of day shift closing and provide the ability to close out each cash register. | E13 Employee Mobile & Workforce |  | Medium | 5 | Mobile App | M3_Phase_3
Task | FEAT-371: UI screens (iOS & Android) | Implement shared + platform UI components. Acceptance: 'Shift Opening And Closing' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E13 Employee Mobile & Workforce | FEAT-371 Shift Opening And Closing | Medium | 2 | Mobile App | M3
Task | FEAT-371: State & API integration | Data layer, caching and API wiring. Acceptance: 'Shift Opening And Closing' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E13 Employee Mobile & Workforce | FEAT-371 Shift Opening And Closing | Medium | 2 | Mobile App | M3
Task | FEAT-371: Offline & push handling | Offline storage, sync and push notifications. Acceptance: 'Shift Opening And Closing' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E13 Employee Mobile & Workforce | FEAT-371 Shift Opening And Closing | Medium | 1 | Mobile App | M3
Task | FEAT-371: Mobile E2E tests | Automated tests across iOS/Android. Acceptance: 'Shift Opening And Closing' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E13 Employee Mobile & Workforce | FEAT-371 Shift Opening And Closing | Medium | 1 | Mobile App | M3
Story | FEAT-372 Demand Forecasting | Covers 7 matrix requirement(s). System shall forecast staffing requirements by venue. | E13 Employee Mobile & Workforce |  | Medium | 8 | Mobile App | M4_Phase_4
Task | FEAT-372: UI screens (iOS & Android) | Implement shared + platform UI components. Acceptance: 'Demand Forecasting' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E13 Employee Mobile & Workforce | FEAT-372 Demand Forecasting | Medium | 3 | Mobile App | M4
Task | FEAT-372: State & API integration | Data layer, caching and API wiring. Acceptance: 'Demand Forecasting' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E13 Employee Mobile & Workforce | FEAT-372 Demand Forecasting | Medium | 3 | Mobile App | M4
Task | FEAT-372: Offline & push handling | Offline storage, sync and push notifications. Acceptance: 'Demand Forecasting' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E13 Employee Mobile & Workforce | FEAT-372 Demand Forecasting | Medium | 2 | Mobile App | M4
Task | FEAT-372: Mobile E2E tests | Automated tests across iOS/Android. Acceptance: 'Demand Forecasting' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E13 Employee Mobile & Workforce | FEAT-372 Demand Forecasting | Medium | 2 | Mobile App | M4
Story | FEAT-373 Virtual Queue | Covers 1 matrix requirement(s). Recommend staffing adjustments, ride allocation, and queue balancing. | E13 Employee Mobile & Workforce |  | Medium | 5 | Mobile App | M4_Phase_4
Task | FEAT-373: UI screens (iOS & Android) | Implement shared + platform UI components. Acceptance: 'Virtual Queue' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E13 Employee Mobile & Workforce | FEAT-373 Virtual Queue | Medium | 2 | Mobile App | M4
Task | FEAT-373: State & API integration | Data layer, caching and API wiring. Acceptance: 'Virtual Queue' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E13 Employee Mobile & Workforce | FEAT-373 Virtual Queue | Medium | 2 | Mobile App | M4
Task | FEAT-373: Offline & push handling | Offline storage, sync and push notifications. Acceptance: 'Virtual Queue' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E13 Employee Mobile & Workforce | FEAT-373 Virtual Queue | Medium | 1 | Mobile App | M4
Task | FEAT-373: Mobile E2E tests | Automated tests across iOS/Android. Acceptance: 'Virtual Queue' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E13 Employee Mobile & Workforce | FEAT-373 Virtual Queue | Medium | 1 | Mobile App | M4
Story | FEAT-374 Bi And Reporting | Covers 1 matrix requirement(s). System shall support report scheduling. | E13 Employee Mobile & Workforce |  | Medium | 1 | Mobile App | M3_Phase_3
Task | FEAT-374: UI screens (iOS & Android) | Implement shared + platform UI components. Acceptance: 'Bi And Reporting' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E13 Employee Mobile & Workforce | FEAT-374 Bi And Reporting | Medium | 1 | Mobile App | M3
Task | FEAT-374: State & API integration | Data layer, caching and API wiring. Acceptance: 'Bi And Reporting' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E13 Employee Mobile & Workforce | FEAT-374 Bi And Reporting | Medium | 1 | Mobile App | M3
Task | FEAT-374: Offline & push handling | Offline storage, sync and push notifications. Acceptance: 'Bi And Reporting' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E13 Employee Mobile & Workforce | FEAT-374 Bi And Reporting | Medium | 1 | Mobile App | M3
Task | FEAT-374: Mobile E2E tests | Automated tests across iOS/Android. Acceptance: 'Bi And Reporting' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E13 Employee Mobile & Workforce | FEAT-374 Bi And Reporting | Medium | 1 | Mobile App | M3
Story | FEAT-375 Operations Command Center | Covers 1 matrix requirement(s). AI shall identify operational risks, anomalies, congestion, capacity issues, device failures, staffing shortages, and service disruptions and provide recommendations. | E13 Employee Mobile & Workforce |  | Medium | 5 | Mobile App | M4_Phase_4
Task | FEAT-375: UI screens (iOS & Android) | Implement shared + platform UI components. Acceptance: 'Operations Command Center' ui screens (ios & android) complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E13 Employee Mobile & Workforce | FEAT-375 Operations Command Center | Medium | 2 | Mobile App | M4
Task | FEAT-375: State & API integration | Data layer, caching and API wiring. Acceptance: 'Operations Command Center' state & api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E13 Employee Mobile & Workforce | FEAT-375 Operations Command Center | Medium | 2 | Mobile App | M4
Task | FEAT-375: Offline & push handling | Offline storage, sync and push notifications. Acceptance: 'Operations Command Center' offline & push handling complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E13 Employee Mobile & Workforce | FEAT-375 Operations Command Center | Medium | 1 | Mobile App | M4
Task | FEAT-375: Mobile E2E tests | Automated tests across iOS/Android. Acceptance: 'Operations Command Center' mobile e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E13 Employee Mobile & Workforce | FEAT-375 Operations Command Center | Medium | 1 | Mobile App | M4
Story | FEAT-376 Reporting And Dashboards | Covers 97 matrix requirement(s). Allows management of credentials and access rights for staff, contractors, VIPs, media personnel and special guests. | E14 Intelligence, Reporting & AI |  | Medium | 13 | Server Side / Backend | M3_Phase_3
Task | FEAT-376: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Reporting And Dashboards' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-376 Reporting And Dashboards | Medium | 8 | Server Side / Backend | M3
Task | FEAT-376: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Reporting And Dashboards' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-376 Reporting And Dashboards | Medium | 13 | Server Side / Backend | M3
Task | FEAT-376: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Reporting And Dashboards' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-376 Reporting And Dashboards | Medium | 13 | Server Side / Backend | M3
Task | FEAT-376: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Reporting And Dashboards' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-376 Reporting And Dashboards | Medium | 8 | Server Side / Backend | M3
Task | FEAT-376: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Reporting And Dashboards' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-376 Reporting And Dashboards | Medium | 8 | Server Side / Backend | M3
Story | FEAT-377 Fraud Detection | Covers 34 matrix requirement(s). System shall detect abnormal payment activity. | E14 Intelligence, Reporting & AI |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-377: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Fraud Detection' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-377 Fraud Detection | Medium | 5 | Server Side / Backend | M4
Task | FEAT-377: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Fraud Detection' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-377 Fraud Detection | Medium | 8 | Server Side / Backend | M4
Task | FEAT-377: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Fraud Detection' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-377 Fraud Detection | Medium | 8 | Server Side / Backend | M4
Task | FEAT-377: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Fraud Detection' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-377 Fraud Detection | Medium | 5 | Server Side / Backend | M4
Task | FEAT-377: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Fraud Detection' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-377 Fraud Detection | Medium | 5 | Server Side / Backend | M4
Story | FEAT-378 Accounting | Covers 30 matrix requirement(s). Support account roll-up reporting. | E14 Intelligence, Reporting & AI |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-378: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Accounting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-378 Accounting | Medium | 5 | Server Side / Backend | M4
Task | FEAT-378: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Accounting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-378 Accounting | Medium | 8 | Server Side / Backend | M4
Task | FEAT-378: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Accounting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-378 Accounting | Medium | 8 | Server Side / Backend | M4
Task | FEAT-378: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Accounting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-378 Accounting | Medium | 5 | Server Side / Backend | M4
Task | FEAT-378: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Accounting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-378 Accounting | Medium | 5 | Server Side / Backend | M4
Story | FEAT-379 Ai Engine | Covers 29 matrix requirement(s). System shall provide a conversational AI assistant across all platform modules. | E14 Intelligence, Reporting & AI |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-379: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ai Engine' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-379 Ai Engine | Medium | 5 | Server Side / Backend | M4
Task | FEAT-379: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ai Engine' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-379 Ai Engine | Medium | 8 | Server Side / Backend | M4
Task | FEAT-379: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ai Engine' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-379 Ai Engine | Medium | 8 | Server Side / Backend | M4
Task | FEAT-379: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ai Engine' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-379 Ai Engine | Medium | 5 | Server Side / Backend | M4
Task | FEAT-379: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ai Engine' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-379 Ai Engine | Medium | 5 | Server Side / Backend | M4
Story | FEAT-380 Bi And Reporting | Covers 26 matrix requirement(s). System shall provide executive dashboards. | E14 Intelligence, Reporting & AI |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-380: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Bi And Reporting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-380 Bi And Reporting | Medium | 5 | Server Side / Backend | M4
Task | FEAT-380: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Bi And Reporting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-380 Bi And Reporting | Medium | 5 | Server Side / Backend | M4
Task | FEAT-380: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Bi And Reporting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-380 Bi And Reporting | Medium | 8 | Server Side / Backend | M4
Task | FEAT-380: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Bi And Reporting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-380 Bi And Reporting | Medium | 5 | Server Side / Backend | M4
Task | FEAT-380: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Bi And Reporting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-380 Bi And Reporting | Medium | 5 | Server Side / Backend | M4
Story | FEAT-381 Ai Governance | Covers 25 matrix requirement(s). System shall log all AI prompts. | E14 Intelligence, Reporting & AI |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-381: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ai Governance' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-381 Ai Governance | Medium | 5 | Server Side / Backend | M4
Task | FEAT-381: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ai Governance' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-381 Ai Governance | Medium | 5 | Server Side / Backend | M4
Task | FEAT-381: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ai Governance' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-381 Ai Governance | Medium | 8 | Server Side / Backend | M4
Task | FEAT-381: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ai Governance' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-381 Ai Governance | Medium | 5 | Server Side / Backend | M4
Task | FEAT-381: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ai Governance' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-381 Ai Governance | Medium | 5 | Server Side / Backend | M4
Story | FEAT-382 Demand Forecasting | Covers 24 matrix requirement(s). System shall provide forecast accuracy measurements. | E14 Intelligence, Reporting & AI |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-382: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Demand Forecasting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-382 Demand Forecasting | Medium | 3 | Server Side / Backend | M4
Task | FEAT-382: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Demand Forecasting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-382 Demand Forecasting | Medium | 5 | Server Side / Backend | M4
Task | FEAT-382: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Demand Forecasting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-382 Demand Forecasting | Medium | 8 | Server Side / Backend | M4
Task | FEAT-382: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Demand Forecasting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-382 Demand Forecasting | Medium | 3 | Server Side / Backend | M4
Task | FEAT-382: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Demand Forecasting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-382 Demand Forecasting | Medium | 3 | Server Side / Backend | M4
Story | FEAT-383 Recommendation Engine | Covers 17 matrix requirement(s). System shall provide personalized attraction recommendations. | E14 Intelligence, Reporting & AI |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-383: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Recommendation Engine' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-383 Recommendation Engine | Medium | 3 | Server Side / Backend | M4
Task | FEAT-383: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Recommendation Engine' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-383 Recommendation Engine | Medium | 5 | Server Side / Backend | M4
Task | FEAT-383: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Recommendation Engine' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-383 Recommendation Engine | Medium | 5 | Server Side / Backend | M4
Task | FEAT-383: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Recommendation Engine' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-383 Recommendation Engine | Medium | 3 | Server Side / Backend | M4
Task | FEAT-383: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Recommendation Engine' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-383 Recommendation Engine | Medium | 3 | Server Side / Backend | M4
Story | FEAT-384 Ai Governance And Explainability | Covers 6 matrix requirement(s). Provides control, transparency and accountability over AI-generated outputs. | E14 Intelligence, Reporting & AI |  | Medium | 8 | Server Side / Backend | M4_Phase_4
Task | FEAT-384: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ai Governance And Explainability' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-384 Ai Governance And Explainability | Medium | 2 | Server Side / Backend | M4
Task | FEAT-384: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ai Governance And Explainability' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-384 Ai Governance And Explainability | Medium | 2 | Server Side / Backend | M4
Task | FEAT-384: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ai Governance And Explainability' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-384 Ai Governance And Explainability | Medium | 3 | Server Side / Backend | M4
Task | FEAT-384: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ai Governance And Explainability' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-384 Ai Governance And Explainability | Medium | 2 | Server Side / Backend | M4
Task | FEAT-384: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ai Governance And Explainability' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-384 Ai Governance And Explainability | Medium | 2 | Server Side / Backend | M4
Story | FEAT-385 Customer Support And Helpdesk | Covers 5 matrix requirement(s). AI Subscription Recommendations - System shall recommend optimal subscription plans. | E14 Intelligence, Reporting & AI |  | Medium | 8 | Server Side / Backend | M4_Phase_4
Task | FEAT-385: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Customer Support And Helpdesk' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-385 Customer Support And Helpdesk | Medium | 2 | Server Side / Backend | M4
Task | FEAT-385: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Customer Support And Helpdesk' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-385 Customer Support And Helpdesk | Medium | 2 | Server Side / Backend | M4
Task | FEAT-385: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Customer Support And Helpdesk' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-385 Customer Support And Helpdesk | Medium | 3 | Server Side / Backend | M4
Task | FEAT-385: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Customer Support And Helpdesk' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-385 Customer Support And Helpdesk | Medium | 2 | Server Side / Backend | M4
Task | FEAT-385: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Customer Support And Helpdesk' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-385 Customer Support And Helpdesk | Medium | 2 | Server Side / Backend | M4
Story | FEAT-386 Virtual Queue | Covers 4 matrix requirement(s). Automatically recommend or redirect guests to alternative attractions or queues. | E14 Intelligence, Reporting & AI |  | Medium | 8 | Server Side / Backend | M4_Phase_4
Task | FEAT-386: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Virtual Queue' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-386 Virtual Queue | Medium | 1 | Server Side / Backend | M4
Task | FEAT-386: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Virtual Queue' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-386 Virtual Queue | Medium | 2 | Server Side / Backend | M4
Task | FEAT-386: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Virtual Queue' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-386 Virtual Queue | Medium | 3 | Server Side / Backend | M4
Task | FEAT-386: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Virtual Queue' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-386 Virtual Queue | Medium | 1 | Server Side / Backend | M4
Task | FEAT-386: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Virtual Queue' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-386 Virtual Queue | Medium | 1 | Server Side / Backend | M4
Story | FEAT-387 Maintenance Reporting And Analytics | Covers 4 matrix requirement(s). Maintenance Dashboard - System shall provide maintenance dashboards. | E14 Intelligence, Reporting & AI |  | Medium | 5 | Server Side / Backend | M3_Phase_3
Task | FEAT-387: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Maintenance Reporting And Analytics' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-387 Maintenance Reporting And Analytics | Medium | 1 | Server Side / Backend | M3
Task | FEAT-387: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Maintenance Reporting And Analytics' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-387 Maintenance Reporting And Analytics | Medium | 1 | Server Side / Backend | M3
Task | FEAT-387: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Maintenance Reporting And Analytics' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-387 Maintenance Reporting And Analytics | Medium | 2 | Server Side / Backend | M3
Task | FEAT-387: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Maintenance Reporting And Analytics' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-387 Maintenance Reporting And Analytics | Medium | 1 | Server Side / Backend | M3
Task | FEAT-387: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Maintenance Reporting And Analytics' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-387 Maintenance Reporting And Analytics | Medium | 1 | Server Side / Backend | M3
Story | FEAT-388 Enterprise Features | Covers 3 matrix requirement(s). Device Dashboards - System shall provide device management dashboards. | E14 Intelligence, Reporting & AI |  | Medium | 2 | Server Side / Backend | M3_Phase_3
Task | FEAT-388: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Enterprise Features' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-388 Enterprise Features | Medium | 1 | Server Side / Backend | M3
Task | FEAT-388: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Enterprise Features' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-388 Enterprise Features | Medium | 1 | Server Side / Backend | M3
Task | FEAT-388: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Enterprise Features' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-388 Enterprise Features | Medium | 1 | Server Side / Backend | M3
Task | FEAT-388: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Enterprise Features' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-388 Enterprise Features | Medium | 1 | Server Side / Backend | M3
Task | FEAT-388: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Enterprise Features' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-388 Enterprise Features | Medium | 1 | Server Side / Backend | M3
Story | FEAT-389 Safety And Compliance | Covers 3 matrix requirement(s). Hazard Reporting - System shall support hazard reporting. | E14 Intelligence, Reporting & AI |  | Medium | 2 | Server Side / Backend | M3_Phase_3
Task | FEAT-389: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Safety And Compliance' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-389 Safety And Compliance | Medium | 1 | Server Side / Backend | M3
Task | FEAT-389: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Safety And Compliance' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-389 Safety And Compliance | Medium | 1 | Server Side / Backend | M3
Task | FEAT-389: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Safety And Compliance' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-389 Safety And Compliance | Medium | 1 | Server Side / Backend | M3
Task | FEAT-389: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Safety And Compliance' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-389 Safety And Compliance | Medium | 1 | Server Side / Backend | M3
Task | FEAT-389: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Safety And Compliance' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-389 Safety And Compliance | Medium | 1 | Server Side / Backend | M3
Story | FEAT-390 Ai Configuration Assistant | Covers 2 matrix requirement(s). It is possible to register who has offered the Invitation. | E14 Intelligence, Reporting & AI |  | Medium | 3 | Server Side / Backend | M3_Phase_3
Task | FEAT-390: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Ai Configuration Assistant' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-390 Ai Configuration Assistant | Medium | 1 | Server Side / Backend | M3
Task | FEAT-390: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Ai Configuration Assistant' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-390 Ai Configuration Assistant | Medium | 1 | Server Side / Backend | M3
Task | FEAT-390: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Ai Configuration Assistant' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-390 Ai Configuration Assistant | Medium | 1 | Server Side / Backend | M3
Task | FEAT-390: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Ai Configuration Assistant' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-390 Ai Configuration Assistant | Medium | 1 | Server Side / Backend | M3
Task | FEAT-390: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Ai Configuration Assistant' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-390 Ai Configuration Assistant | Medium | 1 | Server Side / Backend | M3
Story | FEAT-391 Operations Command Center | Covers 2 matrix requirement(s). System shall display queue lengths, estimated wait times, queue utilization, queue alerts, and queue prediction metrics. | E14 Intelligence, Reporting & AI |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-391: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Operations Command Center' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-391 Operations Command Center | Medium | 1 | Server Side / Backend | M4
Task | FEAT-391: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Operations Command Center' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-391 Operations Command Center | Medium | 2 | Server Side / Backend | M4
Task | FEAT-391: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Operations Command Center' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-391 Operations Command Center | Medium | 2 | Server Side / Backend | M4
Task | FEAT-391: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Operations Command Center' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-391 Operations Command Center | Medium | 1 | Server Side / Backend | M4
Task | FEAT-391: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Operations Command Center' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-391 Operations Command Center | Medium | 1 | Server Side / Backend | M4
Story | FEAT-392 Sandbox | Covers 1 matrix requirement(s). Sandbox Usage Analytics - System shall provide sandbox usage reporting. | E14 Intelligence, Reporting & AI |  | Medium | 1 | Server Side / Backend | M3_Phase_3
Task | FEAT-392: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Sandbox' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-392 Sandbox | Medium | 1 | Server Side / Backend | M3
Task | FEAT-392: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Sandbox' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-392 Sandbox | Medium | 1 | Server Side / Backend | M3
Task | FEAT-392: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Sandbox' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-392 Sandbox | Medium | 1 | Server Side / Backend | M3
Task | FEAT-392: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Sandbox' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-392 Sandbox | Medium | 1 | Server Side / Backend | M3
Task | FEAT-392: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Sandbox' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-392 Sandbox | Medium | 1 | Server Side / Backend | M3
Story | FEAT-393 Self-Service Onboarding | Covers 1 matrix requirement(s). AI Setup Wizard - System shall provide AI-assisted onboarding. | E14 Intelligence, Reporting & AI |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-393: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Self-Service Onboarding' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-393 Self-Service Onboarding | Medium | 1 | Server Side / Backend | M4
Task | FEAT-393: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Self-Service Onboarding' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-393 Self-Service Onboarding | Medium | 2 | Server Side / Backend | M4
Task | FEAT-393: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Self-Service Onboarding' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-393 Self-Service Onboarding | Medium | 2 | Server Side / Backend | M4
Task | FEAT-393: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Self-Service Onboarding' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-393 Self-Service Onboarding | Medium | 1 | Server Side / Backend | M4
Task | FEAT-393: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Self-Service Onboarding' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-393 Self-Service Onboarding | Medium | 1 | Server Side / Backend | M4
Story | FEAT-394 Enterprise Features | Covers 7 matrix requirement(s). Multi-Tenant Device Management - System shall support tenant-specific device management. | E15 Device & Peripheral Management |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-394: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Enterprise Features' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E15 Device & Peripheral Management | FEAT-394 Enterprise Features | Medium | 1 | Server Side / Backend | M4
Task | FEAT-394: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Enterprise Features' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E15 Device & Peripheral Management | FEAT-394 Enterprise Features | Medium | 2 | Server Side / Backend | M4
Task | FEAT-394: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Enterprise Features' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E15 Device & Peripheral Management | FEAT-394 Enterprise Features | Medium | 2 | Server Side / Backend | M4
Task | FEAT-394: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Enterprise Features' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E15 Device & Peripheral Management | FEAT-394 Enterprise Features | Medium | 1 | Server Side / Backend | M4
Task | FEAT-394: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Enterprise Features' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E15 Device & Peripheral Management | FEAT-394 Enterprise Features | Medium | 1 | Server Side / Backend | M4
Story | FEAT-395 Device Configuration | Covers 5 matrix requirement(s). Device Configuration Management - System shall support device configuration management. | E15 Device & Peripheral Management |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-395: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Device Configuration' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E15 Device & Peripheral Management | FEAT-395 Device Configuration | Medium | 1 | Server Side / Backend | M4
Task | FEAT-395: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Device Configuration' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E15 Device & Peripheral Management | FEAT-395 Device Configuration | Medium | 1 | Server Side / Backend | M4
Task | FEAT-395: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Device Configuration' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E15 Device & Peripheral Management | FEAT-395 Device Configuration | Medium | 2 | Server Side / Backend | M4
Task | FEAT-395: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Device Configuration' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E15 Device & Peripheral Management | FEAT-395 Device Configuration | Medium | 1 | Server Side / Backend | M4
Task | FEAT-395: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Device Configuration' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E15 Device & Peripheral Management | FEAT-395 Device Configuration | Medium | 1 | Server Side / Backend | M4
Story | FEAT-396 Device Monitoring | Covers 5 matrix requirement(s). Device Health Monitoring - System shall monitor device health. | E15 Device & Peripheral Management |  | Medium | 5 | Cross Platform | M4_Phase_4
Task | FEAT-396: Design & technical spec | Architecture, interfaces and acceptance criteria. Acceptance: 'Device Monitoring' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E15 Device & Peripheral Management | FEAT-396 Device Monitoring | Medium | 1 | Cross Platform | M4
Task | FEAT-396: Implementation | Build the capability / automation. Acceptance: 'Device Monitoring' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E15 Device & Peripheral Management | FEAT-396 Device Monitoring | Medium | 2 | Cross Platform | M4
Task | FEAT-396: Automation & CI integration | Pipeline, IaC and gates. Acceptance: 'Device Monitoring' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E15 Device & Peripheral Management | FEAT-396 Device Monitoring | Medium | 1 | Cross Platform | M4
Task | FEAT-396: Verification & sign-off | Validate against NFR/acceptance criteria. Acceptance: 'Device Monitoring' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E15 Device & Peripheral Management | FEAT-396 Device Monitoring | Medium | 1 | Cross Platform | M4
Story | FEAT-397 Device Maintenance | Covers 5 matrix requirement(s). Corrective Maintenance - System shall support corrective maintenance tracking. | E15 Device & Peripheral Management |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-397: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Device Maintenance' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E15 Device & Peripheral Management | FEAT-397 Device Maintenance | Medium | 1 | Server Side / Backend | M4
Task | FEAT-397: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Device Maintenance' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E15 Device & Peripheral Management | FEAT-397 Device Maintenance | Medium | 1 | Server Side / Backend | M4
Task | FEAT-397: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Device Maintenance' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E15 Device & Peripheral Management | FEAT-397 Device Maintenance | Medium | 2 | Server Side / Backend | M4
Task | FEAT-397: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Device Maintenance' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E15 Device & Peripheral Management | FEAT-397 Device Maintenance | Medium | 1 | Server Side / Backend | M4
Task | FEAT-397: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Device Maintenance' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E15 Device & Peripheral Management | FEAT-397 Device Maintenance | Medium | 1 | Server Side / Backend | M4
Story | FEAT-398 Firmware And Software Management | Covers 5 matrix requirement(s). Firmware Management - System shall support firmware management. | E15 Device & Peripheral Management |  | Medium | 8 | Server Side / Backend | M4_Phase_4
Task | FEAT-398: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Firmware And Software Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E15 Device & Peripheral Management | FEAT-398 Firmware And Software Management | Medium | 2 | Server Side / Backend | M4
Task | FEAT-398: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Firmware And Software Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E15 Device & Peripheral Management | FEAT-398 Firmware And Software Management | Medium | 2 | Server Side / Backend | M4
Task | FEAT-398: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Firmware And Software Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E15 Device & Peripheral Management | FEAT-398 Firmware And Software Management | Medium | 3 | Server Side / Backend | M4
Task | FEAT-398: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Firmware And Software Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E15 Device & Peripheral Management | FEAT-398 Firmware And Software Management | Medium | 2 | Server Side / Backend | M4
Task | FEAT-398: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Firmware And Software Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E15 Device & Peripheral Management | FEAT-398 Firmware And Software Management | Medium | 2 | Server Side / Backend | M4
Story | FEAT-399 Security | Covers 5 matrix requirement(s). Device Authentication - System shall support device authentication. | E15 Device & Peripheral Management |  | Medium | 8 | Server Side / Backend | M4_Phase_4
Task | FEAT-399: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Security' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E15 Device & Peripheral Management | FEAT-399 Security | Medium | 2 | Server Side / Backend | M4
Task | FEAT-399: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Security' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E15 Device & Peripheral Management | FEAT-399 Security | Medium | 2 | Server Side / Backend | M4
Task | FEAT-399: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Security' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E15 Device & Peripheral Management | FEAT-399 Security | Medium | 3 | Server Side / Backend | M4
Task | FEAT-399: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Security' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E15 Device & Peripheral Management | FEAT-399 Security | Medium | 2 | Server Side / Backend | M4
Task | FEAT-399: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Security' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E15 Device & Peripheral Management | FEAT-399 Security | Medium | 2 | Server Side / Backend | M4
Story | FEAT-400 Device Registration | Covers 4 matrix requirement(s). Device Registration - System shall support registration of devices. | E15 Device & Peripheral Management |  | Medium | 5 | Server Side / Backend | M4_Phase_4
Task | FEAT-400: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Device Registration' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E15 Device & Peripheral Management | FEAT-400 Device Registration | Medium | 1 | Server Side / Backend | M4
Task | FEAT-400: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Device Registration' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E15 Device & Peripheral Management | FEAT-400 Device Registration | Medium | 1 | Server Side / Backend | M4
Task | FEAT-400: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Device Registration' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E15 Device & Peripheral Management | FEAT-400 Device Registration | Medium | 2 | Server Side / Backend | M4
Task | FEAT-400: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Device Registration' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E15 Device & Peripheral Management | FEAT-400 Device Registration | Medium | 1 | Server Side / Backend | M4
Task | FEAT-400: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Device Registration' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E15 Device & Peripheral Management | FEAT-400 Device Registration | Medium | 1 | Server Side / Backend | M4
Story | FEAT-401 Device Integrations | Covers 3 matrix requirement(s). POS Device Integration - System shall support POS device integration. | E15 Device & Peripheral Management |  | Medium | 8 | Server Side / Backend | M4_Phase_4
Task | FEAT-401: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Device Integrations' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E15 Device & Peripheral Management | FEAT-401 Device Integrations | Medium | 1 | Server Side / Backend | M4
Task | FEAT-401: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Device Integrations' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E15 Device & Peripheral Management | FEAT-401 Device Integrations | Medium | 2 | Server Side / Backend | M4
Task | FEAT-401: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Device Integrations' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E15 Device & Peripheral Management | FEAT-401 Device Integrations | Medium | 2 | Server Side / Backend | M4
Task | FEAT-401: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Device Integrations' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E15 Device & Peripheral Management | FEAT-401 Device Integrations | Medium | 1 | Server Side / Backend | M4
Task | FEAT-401: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Device Integrations' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E15 Device & Peripheral Management | FEAT-401 Device Integrations | Medium | 1 | Server Side / Backend | M4
Story | FEAT-402 Asset Management | Covers 7 matrix requirement(s). Asset Master - System shall support centralized asset management. | E16 Maintenance, Safety & Asset Mgmt |  | Medium | 5 | Server Side / Backend | M3_Phase_3
Task | FEAT-402: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Asset Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E16 Maintenance, Safety & Asset Mgmt | FEAT-402 Asset Management | Medium | 1 | Server Side / Backend | M3
Task | FEAT-402: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Asset Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E16 Maintenance, Safety & Asset Mgmt | FEAT-402 Asset Management | Medium | 2 | Server Side / Backend | M3
Task | FEAT-402: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Asset Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E16 Maintenance, Safety & Asset Mgmt | FEAT-402 Asset Management | Medium | 2 | Server Side / Backend | M3
Task | FEAT-402: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Asset Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E16 Maintenance, Safety & Asset Mgmt | FEAT-402 Asset Management | Medium | 1 | Server Side / Backend | M3
Task | FEAT-402: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Asset Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E16 Maintenance, Safety & Asset Mgmt | FEAT-402 Asset Management | Medium | 1 | Server Side / Backend | M3
Story | FEAT-403 Corrective Maintenance And Incident | Covers 7 matrix requirement(s). Maintenance Requests - System shall support maintenance requests. | E16 Maintenance, Safety & Asset Mgmt |  | Medium | 5 | Server Side / Backend | M3_Phase_3
Task | FEAT-403: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Corrective Maintenance And Incident' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E16 Maintenance, Safety & Asset Mgmt | FEAT-403 Corrective Maintenance And Incident | Medium | 1 | Server Side / Backend | M3
Task | FEAT-403: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Corrective Maintenance And Incident' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E16 Maintenance, Safety & Asset Mgmt | FEAT-403 Corrective Maintenance And Incident | Medium | 2 | Server Side / Backend | M3
Task | FEAT-403: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Corrective Maintenance And Incident' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E16 Maintenance, Safety & Asset Mgmt | FEAT-403 Corrective Maintenance And Incident | Medium | 2 | Server Side / Backend | M3
Task | FEAT-403: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Corrective Maintenance And Incident' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E16 Maintenance, Safety & Asset Mgmt | FEAT-403 Corrective Maintenance And Incident | Medium | 1 | Server Side / Backend | M3
Task | FEAT-403: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Corrective Maintenance And Incident' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E16 Maintenance, Safety & Asset Mgmt | FEAT-403 Corrective Maintenance And Incident | Medium | 1 | Server Side / Backend | M3
Story | FEAT-404 Safety And Compliance | Covers 7 matrix requirement(s). Safety Inspections - System shall support safety inspections. | E16 Maintenance, Safety & Asset Mgmt |  | Medium | 5 | Server Side / Backend | M3_Phase_3
Task | FEAT-404: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Safety And Compliance' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E16 Maintenance, Safety & Asset Mgmt | FEAT-404 Safety And Compliance | Medium | 1 | Server Side / Backend | M3
Task | FEAT-404: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Safety And Compliance' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E16 Maintenance, Safety & Asset Mgmt | FEAT-404 Safety And Compliance | Medium | 2 | Server Side / Backend | M3
Task | FEAT-404: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Safety And Compliance' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E16 Maintenance, Safety & Asset Mgmt | FEAT-404 Safety And Compliance | Medium | 2 | Server Side / Backend | M3
Task | FEAT-404: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Safety And Compliance' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E16 Maintenance, Safety & Asset Mgmt | FEAT-404 Safety And Compliance | Medium | 1 | Server Side / Backend | M3
Task | FEAT-404: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Safety And Compliance' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E16 Maintenance, Safety & Asset Mgmt | FEAT-404 Safety And Compliance | Medium | 1 | Server Side / Backend | M3
Story | FEAT-405 Accounting | Covers 1 matrix requirement(s). System shall support Asset, Liability, Equity, Revenue, and Expense account types. | E16 Maintenance, Safety & Asset Mgmt |  | Medium | 3 | Server Side / Backend | M3_Phase_3
Task | FEAT-405: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Accounting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E16 Maintenance, Safety & Asset Mgmt | FEAT-405 Accounting | Medium | 1 | Server Side / Backend | M3
Task | FEAT-405: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Accounting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E16 Maintenance, Safety & Asset Mgmt | FEAT-405 Accounting | Medium | 1 | Server Side / Backend | M3
Task | FEAT-405: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Accounting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E16 Maintenance, Safety & Asset Mgmt | FEAT-405 Accounting | Medium | 1 | Server Side / Backend | M3
Task | FEAT-405: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Accounting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E16 Maintenance, Safety & Asset Mgmt | FEAT-405 Accounting | Medium | 1 | Server Side / Backend | M3
Task | FEAT-405: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Accounting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E16 Maintenance, Safety & Asset Mgmt | FEAT-405 Accounting | Medium | 1 | Server Side / Backend | M3
Story | FEAT-406 Compliance And Security | Covers 11 matrix requirement(s). Privacy & Compliance Management | E17 Identity, Security & Access Policy |  | Medium | 13 | Server Side / Backend | M1_Phase_3
Task | FEAT-406: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Compliance And Security' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E17 Identity, Security & Access Policy | FEAT-406 Compliance And Security | Medium | 2 | Server Side / Backend | M1
Task | FEAT-406: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Compliance And Security' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E17 Identity, Security & Access Policy | FEAT-406 Compliance And Security | Medium | 3 | Server Side / Backend | M1
Task | FEAT-406: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Compliance And Security' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E17 Identity, Security & Access Policy | FEAT-406 Compliance And Security | Medium | 5 | Server Side / Backend | M1
Task | FEAT-406: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Compliance And Security' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E17 Identity, Security & Access Policy | FEAT-406 Compliance And Security | Medium | 2 | Server Side / Backend | M1
Task | FEAT-406: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Compliance And Security' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E17 Identity, Security & Access Policy | FEAT-406 Compliance And Security | Medium | 2 | Server Side / Backend | M1
Story | FEAT-407 Profile Management | Covers 2 matrix requirement(s). Allow authorized users to maintain internal notes, VIP indicators, accessibility requirements, blacklist flags, security alerts, and custom tags. | E17 Identity, Security & Access Policy |  | Highest | 2 | Server Side / Backend | M1_Phase_3
Task | FEAT-407: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Profile Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E17 Identity, Security & Access Policy | FEAT-407 Profile Management | Highest | 1 | Server Side / Backend | M1
Task | FEAT-407: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Profile Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E17 Identity, Security & Access Policy | FEAT-407 Profile Management | Highest | 1 | Server Side / Backend | M1
Task | FEAT-407: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Profile Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E17 Identity, Security & Access Policy | FEAT-407 Profile Management | Highest | 1 | Server Side / Backend | M1
Task | FEAT-407: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Profile Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E17 Identity, Security & Access Policy | FEAT-407 Profile Management | Highest | 1 | Server Side / Backend | M1
Task | FEAT-407: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Profile Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E17 Identity, Security & Access Policy | FEAT-407 Profile Management | Highest | 1 | Server Side / Backend | M1
Story | FEAT-408 Security | Covers 1 matrix requirement(s). Device Authorization - System shall support device authorization. | E17 Identity, Security & Access Policy |  | Highest | 3 | Server Side / Backend | M1_Phase_3
Task | FEAT-408: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Security' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E17 Identity, Security & Access Policy | FEAT-408 Security | Highest | 1 | Server Side / Backend | M1
Task | FEAT-408: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Security' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E17 Identity, Security & Access Policy | FEAT-408 Security | Highest | 1 | Server Side / Backend | M1
Task | FEAT-408: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Security' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E17 Identity, Security & Access Policy | FEAT-408 Security | Highest | 1 | Server Side / Backend | M1
Task | FEAT-408: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Security' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E17 Identity, Security & Access Policy | FEAT-408 Security | Highest | 1 | Server Side / Backend | M1
Task | FEAT-408: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Security' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E17 Identity, Security & Access Policy | FEAT-408 Security | Highest | 1 | Server Side / Backend | M1
Story | FEAT-409 Accounting | Covers 56 matrix requirement(s). System shall maintain account type audit history. | E18 Governance, Approval & Accreditation |  | High | 13 | Server Side / Backend | M3_Phase_3
Task | FEAT-409: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Accounting' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E18 Governance, Approval & Accreditation | FEAT-409 Accounting | High | 8 | Server Side / Backend | M3
Task | FEAT-409: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Accounting' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E18 Governance, Approval & Accreditation | FEAT-409 Accounting | High | 13 | Server Side / Backend | M3
Task | FEAT-409: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Accounting' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E18 Governance, Approval & Accreditation | FEAT-409 Accounting | High | 13 | Server Side / Backend | M3
Task | FEAT-409: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Accounting' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E18 Governance, Approval & Accreditation | FEAT-409 Accounting | High | 8 | Server Side / Backend | M3
Task | FEAT-409: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Accounting' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E18 Governance, Approval & Accreditation | FEAT-409 Accounting | High | 8 | Server Side / Backend | M3
Story | FEAT-410 Profile Management | Covers 1 matrix requirement(s). Support retention policies, anonymization, guest deletion requests, right-to-be-forgotten workflows, GDPR compliance, and privacy audits. | E18 Governance, Approval & Accreditation |  | High | 3 | Server Side / Backend | M3_Phase_3
Task | FEAT-410: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Profile Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E18 Governance, Approval & Accreditation | FEAT-410 Profile Management | High | 1 | Server Side / Backend | M3
Task | FEAT-410: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Profile Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E18 Governance, Approval & Accreditation | FEAT-410 Profile Management | High | 1 | Server Side / Backend | M3
Task | FEAT-410: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Profile Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E18 Governance, Approval & Accreditation | FEAT-410 Profile Management | High | 1 | Server Side / Backend | M3
Task | FEAT-410: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Profile Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E18 Governance, Approval & Accreditation | FEAT-410 Profile Management | High | 1 | Server Side / Backend | M3
Task | FEAT-410: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Profile Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E18 Governance, Approval & Accreditation | FEAT-410 Profile Management | High | 1 | Server Side / Backend | M3
Story | FEAT-411 Virtual Queue | Covers 1 matrix requirement(s). Allow authorized users to transfer guests between queues with audit logging. | E18 Governance, Approval & Accreditation |  | High | 1 | Server Side / Backend | M3_Phase_3
Task | FEAT-411: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Virtual Queue' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E18 Governance, Approval & Accreditation | FEAT-411 Virtual Queue | High | 1 | Server Side / Backend | M3
Task | FEAT-411: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Virtual Queue' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E18 Governance, Approval & Accreditation | FEAT-411 Virtual Queue | High | 1 | Server Side / Backend | M3
Task | FEAT-411: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Virtual Queue' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E18 Governance, Approval & Accreditation | FEAT-411 Virtual Queue | High | 1 | Server Side / Backend | M3
Task | FEAT-411: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Virtual Queue' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E18 Governance, Approval & Accreditation | FEAT-411 Virtual Queue | High | 1 | Server Side / Backend | M3
Task | FEAT-411: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Virtual Queue' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E18 Governance, Approval & Accreditation | FEAT-411 Virtual Queue | High | 1 | Server Side / Backend | M3
Story | FEAT-412 Sandbox | Covers 1 matrix requirement(s). Sandbox Audit Logs - System shall maintain sandbox audit logs. | E18 Governance, Approval & Accreditation |  | High | 1 | Server Side / Backend | M3_Phase_3
Task | FEAT-412: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Sandbox' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E18 Governance, Approval & Accreditation | FEAT-412 Sandbox | High | 1 | Server Side / Backend | M3
Task | FEAT-412: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Sandbox' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E18 Governance, Approval & Accreditation | FEAT-412 Sandbox | High | 1 | Server Side / Backend | M3
Task | FEAT-412: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Sandbox' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E18 Governance, Approval & Accreditation | FEAT-412 Sandbox | High | 1 | Server Side / Backend | M3
Task | FEAT-412: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Sandbox' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E18 Governance, Approval & Accreditation | FEAT-412 Sandbox | High | 1 | Server Side / Backend | M3
Task | FEAT-412: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Sandbox' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E18 Governance, Approval & Accreditation | FEAT-412 Sandbox | High | 1 | Server Side / Backend | M3
Story | FEAT-413 Sandbox | Covers 16 matrix requirement(s). Sandbox Environment Provisioning - System shall provide isolated sandbox environments. | E19 Developer Platform & API Mgmt |  | Medium | 13 | Cross Platform | M3_Phase_3
Task | FEAT-413: Design & technical spec | Architecture, interfaces and acceptance criteria. Acceptance: 'Sandbox' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E19 Developer Platform & API Mgmt | FEAT-413 Sandbox | Medium | 3 | Cross Platform | M3
Task | FEAT-413: Implementation | Build the capability / automation. Acceptance: 'Sandbox' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E19 Developer Platform & API Mgmt | FEAT-413 Sandbox | Medium | 8 | Cross Platform | M3
Task | FEAT-413: Automation & CI integration | Pipeline, IaC and gates. Acceptance: 'Sandbox' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E19 Developer Platform & API Mgmt | FEAT-413 Sandbox | Medium | 3 | Cross Platform | M3
Task | FEAT-413: Verification & sign-off | Validate against NFR/acceptance criteria. Acceptance: 'Sandbox' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E19 Developer Platform & API Mgmt | FEAT-413 Sandbox | Medium | 3 | Cross Platform | M3
Story | FEAT-414 Accounting | Covers 2 matrix requirement(s). An API must deliver the sales transactions to the FE accounting system which will be in charge of the invoicing. | E19 Developer Platform & API Mgmt |  | Medium | 3 | Cross Platform | M3_Phase_3
Task | FEAT-414: Design & technical spec | Architecture, interfaces and acceptance criteria. Acceptance: 'Accounting' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E19 Developer Platform & API Mgmt | FEAT-414 Accounting | Medium | 1 | Cross Platform | M3
Task | FEAT-414: Implementation | Build the capability / automation. Acceptance: 'Accounting' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E19 Developer Platform & API Mgmt | FEAT-414 Accounting | Medium | 2 | Cross Platform | M3
Task | FEAT-414: Automation & CI integration | Pipeline, IaC and gates. Acceptance: 'Accounting' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E19 Developer Platform & API Mgmt | FEAT-414 Accounting | Medium | 1 | Cross Platform | M3
Task | FEAT-414: Verification & sign-off | Validate against NFR/acceptance criteria. Acceptance: 'Accounting' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E19 Developer Platform & API Mgmt | FEAT-414 Accounting | Medium | 1 | Cross Platform | M3
Story | FEAT-415 Api Business Coverage | Covers 1 matrix requirement(s). All business functionality available through the TAIS user interface shall be exposed through documented APIs unless restricted by security, compliance or operational considerations. | E19 Developer Platform & API Mgmt |  | Medium | 3 | Cross Platform | M3_Phase_3
Task | FEAT-415: Design & technical spec | Architecture, interfaces and acceptance criteria. Acceptance: 'Api Business Coverage' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E19 Developer Platform & API Mgmt | FEAT-415 Api Business Coverage | Medium | 1 | Cross Platform | M3
Task | FEAT-415: Implementation | Build the capability / automation. Acceptance: 'Api Business Coverage' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E19 Developer Platform & API Mgmt | FEAT-415 Api Business Coverage | Medium | 1 | Cross Platform | M3
Task | FEAT-415: Automation & CI integration | Pipeline, IaC and gates. Acceptance: 'Api Business Coverage' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E19 Developer Platform & API Mgmt | FEAT-415 Api Business Coverage | Medium | 1 | Cross Platform | M3
Task | FEAT-415: Verification & sign-off | Validate against NFR/acceptance criteria. Acceptance: 'Api Business Coverage' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E19 Developer Platform & API Mgmt | FEAT-415 Api Business Coverage | Medium | 1 | Cross Platform | M3
Story | FEAT-416 Subscription Management | Covers 7 matrix requirement(s). Subscription Plans - System shall support configurable subscription plans. | E20 Tenant, Subscription & Licensing |  | High | 5 | Server Side / Backend | M3_Phase_3
Task | FEAT-416: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Subscription Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E20 Tenant, Subscription & Licensing | FEAT-416 Subscription Management | High | 1 | Server Side / Backend | M3
Task | FEAT-416: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Subscription Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E20 Tenant, Subscription & Licensing | FEAT-416 Subscription Management | High | 2 | Server Side / Backend | M3
Task | FEAT-416: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Subscription Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E20 Tenant, Subscription & Licensing | FEAT-416 Subscription Management | High | 2 | Server Side / Backend | M3
Task | FEAT-416: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Subscription Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E20 Tenant, Subscription & Licensing | FEAT-416 Subscription Management | High | 1 | Server Side / Backend | M3
Task | FEAT-416: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Subscription Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E20 Tenant, Subscription & Licensing | FEAT-416 Subscription Management | High | 1 | Server Side / Backend | M3
Story | FEAT-417 Licensing Models | Covers 6 matrix requirement(s). Venue Size Index - System shall support licensing based on Venue Size Index. | E20 Tenant, Subscription & Licensing |  | High | 5 | Server Side / Backend | M3_Phase_3
Task | FEAT-417: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Licensing Models' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E20 Tenant, Subscription & Licensing | FEAT-417 Licensing Models | High | 1 | Server Side / Backend | M3
Task | FEAT-417: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Licensing Models' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E20 Tenant, Subscription & Licensing | FEAT-417 Licensing Models | High | 1 | Server Side / Backend | M3
Task | FEAT-417: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Licensing Models' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E20 Tenant, Subscription & Licensing | FEAT-417 Licensing Models | High | 2 | Server Side / Backend | M3
Task | FEAT-417: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Licensing Models' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E20 Tenant, Subscription & Licensing | FEAT-417 Licensing Models | High | 1 | Server Side / Backend | M3
Task | FEAT-417: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Licensing Models' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E20 Tenant, Subscription & Licensing | FEAT-417 Licensing Models | High | 1 | Server Side / Backend | M3
Story | FEAT-418 Module Marketplace And Management | Covers 6 matrix requirement(s). Module Discovery - System shall allow customers to browse modules. | E20 Tenant, Subscription & Licensing |  | High | 5 | Server Side / Backend | M3_Phase_3
Task | FEAT-418: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Module Marketplace And Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E20 Tenant, Subscription & Licensing | FEAT-418 Module Marketplace And Management | High | 1 | Server Side / Backend | M3
Task | FEAT-418: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Module Marketplace And Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E20 Tenant, Subscription & Licensing | FEAT-418 Module Marketplace And Management | High | 1 | Server Side / Backend | M3
Task | FEAT-418: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Module Marketplace And Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E20 Tenant, Subscription & Licensing | FEAT-418 Module Marketplace And Management | High | 2 | Server Side / Backend | M3
Task | FEAT-418: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Module Marketplace And Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E20 Tenant, Subscription & Licensing | FEAT-418 Module Marketplace And Management | High | 1 | Server Side / Backend | M3
Task | FEAT-418: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Module Marketplace And Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E20 Tenant, Subscription & Licensing | FEAT-418 Module Marketplace And Management | High | 1 | Server Side / Backend | M3
Story | FEAT-419 Self-Service Onboarding | Covers 5 matrix requirement(s). Customer Registration - System shall support self-service customer registration. | E20 Tenant, Subscription & Licensing |  | High | 5 | Server Side / Backend | M3_Phase_3
Task | FEAT-419: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Self-Service Onboarding' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E20 Tenant, Subscription & Licensing | FEAT-419 Self-Service Onboarding | High | 1 | Server Side / Backend | M3
Task | FEAT-419: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Self-Service Onboarding' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E20 Tenant, Subscription & Licensing | FEAT-419 Self-Service Onboarding | High | 1 | Server Side / Backend | M3
Task | FEAT-419: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Self-Service Onboarding' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E20 Tenant, Subscription & Licensing | FEAT-419 Self-Service Onboarding | High | 2 | Server Side / Backend | M3
Task | FEAT-419: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Self-Service Onboarding' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E20 Tenant, Subscription & Licensing | FEAT-419 Self-Service Onboarding | High | 1 | Server Side / Backend | M3
Task | FEAT-419: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Self-Service Onboarding' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E20 Tenant, Subscription & Licensing | FEAT-419 Self-Service Onboarding | High | 1 | Server Side / Backend | M3
Story | FEAT-420 Billing And Payment | Covers 5 matrix requirement(s). Online Payments - System shall support online payments. | E20 Tenant, Subscription & Licensing |  | High | 5 | Server Side / Backend | M3_Phase_3
Task | FEAT-420: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Billing And Payment' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E20 Tenant, Subscription & Licensing | FEAT-420 Billing And Payment | High | 1 | Server Side / Backend | M3
Task | FEAT-420: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Billing And Payment' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E20 Tenant, Subscription & Licensing | FEAT-420 Billing And Payment | High | 1 | Server Side / Backend | M3
Task | FEAT-420: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Billing And Payment' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E20 Tenant, Subscription & Licensing | FEAT-420 Billing And Payment | High | 2 | Server Side / Backend | M3
Task | FEAT-420: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Billing And Payment' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E20 Tenant, Subscription & Licensing | FEAT-420 Billing And Payment | High | 1 | Server Side / Backend | M3
Task | FEAT-420: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Billing And Payment' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E20 Tenant, Subscription & Licensing | FEAT-420 Billing And Payment | High | 1 | Server Side / Backend | M3
Story | FEAT-421 Digital Asset Management | Covers 15 matrix requirement(s). System shall provide a centralized repository for storing and managing digital assets including images, videos, documents, PDFs, marketing materials, brand assets, audio files, templates, and creative… | E21 Digital Asset Management |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-421: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Digital Asset Management' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E21 Digital Asset Management | FEAT-421 Digital Asset Management | Medium | 3 | Server Side / Backend | M4
Task | FEAT-421: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Digital Asset Management' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E21 Digital Asset Management | FEAT-421 Digital Asset Management | Medium | 5 | Server Side / Backend | M4
Task | FEAT-421: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Digital Asset Management' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E21 Digital Asset Management | FEAT-421 Digital Asset Management | Medium | 5 | Server Side / Backend | M4
Task | FEAT-421: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Digital Asset Management' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E21 Digital Asset Management | FEAT-421 Digital Asset Management | Medium | 3 | Server Side / Backend | M4
Task | FEAT-421: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Digital Asset Management' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E21 Digital Asset Management | FEAT-421 Digital Asset Management | Medium | 3 | Server Side / Backend | M4
Story | FEAT-422 Software Integration | Covers 19 matrix requirement(s). UAE Pass | E22 Integrations & Ecosystem |  | Medium | 13 | Server Side / Backend | M4_Phase_4
Task | FEAT-422: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Software Integration' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E22 Integrations & Ecosystem | FEAT-422 Software Integration | Medium | 3 | Server Side / Backend | M4
Task | FEAT-422: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Software Integration' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E22 Integrations & Ecosystem | FEAT-422 Software Integration | Medium | 5 | Server Side / Backend | M4
Task | FEAT-422: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Software Integration' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E22 Integrations & Ecosystem | FEAT-422 Software Integration | Medium | 5 | Server Side / Backend | M4
Task | FEAT-422: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Software Integration' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E22 Integrations & Ecosystem | FEAT-422 Software Integration | Medium | 3 | Server Side / Backend | M4
Task | FEAT-422: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Software Integration' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E22 Integrations & Ecosystem | FEAT-422 Software Integration | Medium | 3 | Server Side / Backend | M4
Story | FEAT-423 Hardware Integration | Covers 16 matrix requirement(s). Emirates ID Reader Integration | E22 Integrations & Ecosystem |  | Medium | 13 | POS App | M4_Phase_4
Task | FEAT-423: POS screen & flow | Build cashier/kiosk UI and transaction flow. Acceptance: 'Hardware Integration' pos screen & flow complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E22 Integrations & Ecosystem | FEAT-423 Hardware Integration | Medium | 5 | POS App | M4
Task | FEAT-423: Backend/API integration | Wire to pricing, catalogue, payment and sync APIs. Acceptance: 'Hardware Integration' backend/api integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E22 Integrations & Ecosystem | FEAT-423 Hardware Integration | Medium | 3 | POS App | M4
Task | FEAT-423: Peripheral & device integration | Printers, scanners, RFID, cash drawer, KDS as applicable. Acceptance: 'Hardware Integration' peripheral & device integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E22 Integrations & Ecosystem | FEAT-423 Hardware Integration | Medium | 5 | POS App | M4
Task | FEAT-423: Offline handling & sync | Local cache, queue and conflict resolution. Acceptance: 'Hardware Integration' offline handling & sync complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E22 Integrations & Ecosystem | FEAT-423 Hardware Integration | Medium | 5 | POS App | M4
Task | FEAT-423: POS unit & E2E tests | Lane tests incl. offline and peripheral scenarios. Acceptance: 'Hardware Integration' pos unit & e2e tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E22 Integrations & Ecosystem | FEAT-423 Hardware Integration | Medium | 3 | POS App | M4
Story | FEAT-424 Disaster Recovery | Covers 62 matrix requirement(s). Automated Backups - System shall perform automated backups. | E23 Platform Foundations & NFR |  | Highest | 13 | Cross Platform | M1_Phase_2
Task | FEAT-424: Design & technical spec | Architecture, interfaces and acceptance criteria. Acceptance: 'Disaster Recovery' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-424 Disaster Recovery | Highest | 13 | Cross Platform | M1
Task | FEAT-424: Implementation | Build the capability / automation. Acceptance: 'Disaster Recovery' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-424 Disaster Recovery | Highest | 13 | Cross Platform | M1
Task | FEAT-424: Automation & CI integration | Pipeline, IaC and gates. Acceptance: 'Disaster Recovery' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-424 Disaster Recovery | Highest | 13 | Cross Platform | M1
Task | FEAT-424: Verification & sign-off | Validate against NFR/acceptance criteria. Acceptance: 'Disaster Recovery' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-424 Disaster Recovery | Highest | 13 | Cross Platform | M1
Story | FEAT-425 Training And Support | Covers 40 matrix requirement(s). Administrator Training | E23 Platform Foundations & NFR |  | Highest | 13 | Cross Platform | M1_Phase_2
Task | FEAT-425: Design & technical spec | Architecture, interfaces and acceptance criteria. Acceptance: 'Training And Support' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-425 Training And Support | Highest | 8 | Cross Platform | M1
Task | FEAT-425: Implementation | Build the capability / automation. Acceptance: 'Training And Support' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-425 Training And Support | Highest | 13 | Cross Platform | M1
Task | FEAT-425: Automation & CI integration | Pipeline, IaC and gates. Acceptance: 'Training And Support' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-425 Training And Support | Highest | 8 | Cross Platform | M1
Task | FEAT-425: Verification & sign-off | Validate against NFR/acceptance criteria. Acceptance: 'Training And Support' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-425 Training And Support | Highest | 8 | Cross Platform | M1
Story | FEAT-426 Multi-Tenant Core & Tenant Isolation | ENGINEERED FOUNDATION ITEM (under-specified or absent in client matrix; required for enterprise delivery). Multi-Tenant Core & Tenant Isolation | E23 Platform Foundations & NFR |  | Highest | 8 | Server Side / Backend | M1_Phase_2
Task | FEAT-426: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Multi-Tenant Core & Tenant Isolation' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-426 Multi-Tenant Core & Tenant Isolation | Highest | 2 | Server Side / Backend | M1
Task | FEAT-426: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Multi-Tenant Core & Tenant Isolation' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-426 Multi-Tenant Core & Tenant Isolation | Highest | 2 | Server Side / Backend | M1
Task | FEAT-426: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Multi-Tenant Core & Tenant Isolation' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-426 Multi-Tenant Core & Tenant Isolation | Highest | 3 | Server Side / Backend | M1
Task | FEAT-426: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Multi-Tenant Core & Tenant Isolation' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-426 Multi-Tenant Core & Tenant Isolation | Highest | 2 | Server Side / Backend | M1
Task | FEAT-426: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Multi-Tenant Core & Tenant Isolation' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-426 Multi-Tenant Core & Tenant Isolation | Highest | 2 | Server Side / Backend | M1
Story | FEAT-427 Identity, SSO & MFA Service | ENGINEERED FOUNDATION ITEM (under-specified or absent in client matrix; required for enterprise delivery). Identity, SSO & MFA Service | E17 Identity, Security & Access Policy |  | Highest | 8 | Server Side / Backend | M1_Phase_2
Task | FEAT-427: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Identity, SSO & MFA Service' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E17 Identity, Security & Access Policy | FEAT-427 Identity, SSO & MFA Service | Highest | 1 | Server Side / Backend | M1
Task | FEAT-427: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Identity, SSO & MFA Service' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E17 Identity, Security & Access Policy | FEAT-427 Identity, SSO & MFA Service | Highest | 2 | Server Side / Backend | M1
Task | FEAT-427: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Identity, SSO & MFA Service' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E17 Identity, Security & Access Policy | FEAT-427 Identity, SSO & MFA Service | Highest | 2 | Server Side / Backend | M1
Task | FEAT-427: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Identity, SSO & MFA Service' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E17 Identity, Security & Access Policy | FEAT-427 Identity, SSO & MFA Service | Highest | 1 | Server Side / Backend | M1
Task | FEAT-427: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Identity, SSO & MFA Service' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E17 Identity, Security & Access Policy | FEAT-427 Identity, SSO & MFA Service | Highest | 1 | Server Side / Backend | M1
Story | FEAT-428 RBAC + ABAC Policy Engine | ENGINEERED FOUNDATION ITEM (under-specified or absent in client matrix; required for enterprise delivery). RBAC + ABAC Policy Engine | E17 Identity, Security & Access Policy |  | Highest | 8 | Server Side / Backend | M1_Phase_2
Task | FEAT-428: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'RBAC + ABAC Policy Engine' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E17 Identity, Security & Access Policy | FEAT-428 RBAC + ABAC Policy Engine | Highest | 2 | Server Side / Backend | M1
Task | FEAT-428: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'RBAC + ABAC Policy Engine' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E17 Identity, Security & Access Policy | FEAT-428 RBAC + ABAC Policy Engine | Highest | 3 | Server Side / Backend | M1
Task | FEAT-428: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'RBAC + ABAC Policy Engine' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E17 Identity, Security & Access Policy | FEAT-428 RBAC + ABAC Policy Engine | Highest | 3 | Server Side / Backend | M1
Task | FEAT-428: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'RBAC + ABAC Policy Engine' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E17 Identity, Security & Access Policy | FEAT-428 RBAC + ABAC Policy Engine | Highest | 2 | Server Side / Backend | M1
Task | FEAT-428: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'RBAC + ABAC Policy Engine' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E17 Identity, Security & Access Policy | FEAT-428 RBAC + ABAC Policy Engine | Highest | 2 | Server Side / Backend | M1
Story | FEAT-429 API Gateway & Service Framework | ENGINEERED FOUNDATION ITEM (under-specified or absent in client matrix; required for enterprise delivery). API Gateway & Service Framework | E19 Developer Platform & API Mgmt |  | Highest | 8 | Cross Platform | M1_Phase_2
Task | FEAT-429: Design & technical spec | Architecture, interfaces and acceptance criteria. Acceptance: 'API Gateway & Service Framework' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E19 Developer Platform & API Mgmt | FEAT-429 API Gateway & Service Framework | Highest | 2 | Cross Platform | M1
Task | FEAT-429: Implementation | Build the capability / automation. Acceptance: 'API Gateway & Service Framework' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E19 Developer Platform & API Mgmt | FEAT-429 API Gateway & Service Framework | Highest | 3 | Cross Platform | M1
Task | FEAT-429: Automation & CI integration | Pipeline, IaC and gates. Acceptance: 'API Gateway & Service Framework' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E19 Developer Platform & API Mgmt | FEAT-429 API Gateway & Service Framework | Highest | 2 | Cross Platform | M1
Task | FEAT-429: Verification & sign-off | Validate against NFR/acceptance criteria. Acceptance: 'API Gateway & Service Framework' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E19 Developer Platform & API Mgmt | FEAT-429 API Gateway & Service Framework | Highest | 2 | Cross Platform | M1
Story | FEAT-430 Core Data Model & Schema Migrations | ENGINEERED FOUNDATION ITEM (under-specified or absent in client matrix; required for enterprise delivery). Core Data Model & Schema Migrations | E23 Platform Foundations & NFR |  | Highest | 8 | Server Side / Backend | M1_Phase_2
Task | FEAT-430: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Core Data Model & Schema Migrations' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-430 Core Data Model & Schema Migrations | Highest | 1 | Server Side / Backend | M1
Task | FEAT-430: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Core Data Model & Schema Migrations' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-430 Core Data Model & Schema Migrations | Highest | 2 | Server Side / Backend | M1
Task | FEAT-430: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Core Data Model & Schema Migrations' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-430 Core Data Model & Schema Migrations | Highest | 3 | Server Side / Backend | M1
Task | FEAT-430: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Core Data Model & Schema Migrations' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-430 Core Data Model & Schema Migrations | Highest | 1 | Server Side / Backend | M1
Task | FEAT-430: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Core Data Model & Schema Migrations' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-430 Core Data Model & Schema Migrations | Highest | 1 | Server Side / Backend | M1
Story | FEAT-431 Notification Service (Email/SMS/WhatsApp/Push) | ENGINEERED FOUNDATION ITEM (under-specified or absent in client matrix; required for enterprise delivery). Notification Service (Email/SMS/WhatsApp/Push) | E22 Integrations & Ecosystem |  | Highest | 5 | Server Side / Backend | M1_Phase_3
Task | FEAT-431: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Notification Service (Email/SMS/WhatsApp/Push)' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E22 Integrations & Ecosystem | FEAT-431 Notification Service (Email/SMS/WhatsApp/Push) | Highest | 1 | Server Side / Backend | M1
Task | FEAT-431: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Notification Service (Email/SMS/WhatsApp/Push)' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E22 Integrations & Ecosystem | FEAT-431 Notification Service (Email/SMS/WhatsApp/Push) | Highest | 1 | Server Side / Backend | M1
Task | FEAT-431: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Notification Service (Email/SMS/WhatsApp/Push)' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E22 Integrations & Ecosystem | FEAT-431 Notification Service (Email/SMS/WhatsApp/Push) | Highest | 2 | Server Side / Backend | M1
Task | FEAT-431: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Notification Service (Email/SMS/WhatsApp/Push)' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E22 Integrations & Ecosystem | FEAT-431 Notification Service (Email/SMS/WhatsApp/Push) | Highest | 1 | Server Side / Backend | M1
Task | FEAT-431: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Notification Service (Email/SMS/WhatsApp/Push)' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E22 Integrations & Ecosystem | FEAT-431 Notification Service (Email/SMS/WhatsApp/Push) | Highest | 1 | Server Side / Backend | M1
Story | FEAT-432 Observability: Logging, Metrics, Tracing, Alerting | ENGINEERED FOUNDATION ITEM (under-specified or absent in client matrix; required for enterprise delivery). Observability: Logging, Metrics, Tracing, Alerting | E23 Platform Foundations & NFR |  | Highest | 5 | Cross Platform | M1_Phase_2
Task | FEAT-432: Design & technical spec | Architecture, interfaces and acceptance criteria. Acceptance: 'Observability: Logging, Metrics, Tracing, Alerting' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-432 Observability: Logging, Metrics, Tracing, Alerting | Highest | 1 | Cross Platform | M1
Task | FEAT-432: Implementation | Build the capability / automation. Acceptance: 'Observability: Logging, Metrics, Tracing, Alerting' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-432 Observability: Logging, Metrics, Tracing, Alerting | Highest | 3 | Cross Platform | M1
Task | FEAT-432: Automation & CI integration | Pipeline, IaC and gates. Acceptance: 'Observability: Logging, Metrics, Tracing, Alerting' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-432 Observability: Logging, Metrics, Tracing, Alerting | Highest | 1 | Cross Platform | M1
Task | FEAT-432: Verification & sign-off | Validate against NFR/acceptance criteria. Acceptance: 'Observability: Logging, Metrics, Tracing, Alerting' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-432 Observability: Logging, Metrics, Tracing, Alerting | Highest | 1 | Cross Platform | M1
Story | FEAT-433 CI/CD Pipelines & Infrastructure-as-Code | ENGINEERED FOUNDATION ITEM (under-specified or absent in client matrix; required for enterprise delivery). CI/CD Pipelines & Infrastructure-as-Code | E23 Platform Foundations & NFR |  | Highest | 5 | Cross Platform | M1_Phase_2
Task | FEAT-433: Design & technical spec | Architecture, interfaces and acceptance criteria. Acceptance: 'CI/CD Pipelines & Infrastructure-as-Code' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-433 CI/CD Pipelines & Infrastructure-as-Code | Highest | 1 | Cross Platform | M1
Task | FEAT-433: Implementation | Build the capability / automation. Acceptance: 'CI/CD Pipelines & Infrastructure-as-Code' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-433 CI/CD Pipelines & Infrastructure-as-Code | Highest | 3 | Cross Platform | M1
Task | FEAT-433: Automation & CI integration | Pipeline, IaC and gates. Acceptance: 'CI/CD Pipelines & Infrastructure-as-Code' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-433 CI/CD Pipelines & Infrastructure-as-Code | Highest | 1 | Cross Platform | M1
Task | FEAT-433: Verification & sign-off | Validate against NFR/acceptance criteria. Acceptance: 'CI/CD Pipelines & Infrastructure-as-Code' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-433 CI/CD Pipelines & Infrastructure-as-Code | Highest | 1 | Cross Platform | M1
Story | FEAT-434 Error Handling & Resilience Framework | ENGINEERED FOUNDATION ITEM (under-specified or absent in client matrix; required for enterprise delivery). Error Handling & Resilience Framework | E23 Platform Foundations & NFR |  | Highest | 5 | Server Side / Backend | M1_Phase_2
Task | FEAT-434: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Error Handling & Resilience Framework' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-434 Error Handling & Resilience Framework | Highest | 1 | Server Side / Backend | M1
Task | FEAT-434: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Error Handling & Resilience Framework' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-434 Error Handling & Resilience Framework | Highest | 1 | Server Side / Backend | M1
Task | FEAT-434: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Error Handling & Resilience Framework' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-434 Error Handling & Resilience Framework | Highest | 1 | Server Side / Backend | M1
Task | FEAT-434: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Error Handling & Resilience Framework' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-434 Error Handling & Resilience Framework | Highest | 1 | Server Side / Backend | M1
Task | FEAT-434: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Error Handling & Resilience Framework' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-434 Error Handling & Resilience Framework | Highest | 1 | Server Side / Backend | M1
Story | FEAT-435 Configuration Management & Feature Flags | ENGINEERED FOUNDATION ITEM (under-specified or absent in client matrix; required for enterprise delivery). Configuration Management & Feature Flags | E23 Platform Foundations & NFR |  | Highest | 3 | Server Side / Backend | M1_Phase_2
Task | FEAT-435: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Configuration Management & Feature Flags' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-435 Configuration Management & Feature Flags | Highest | 1 | Server Side / Backend | M1
Task | FEAT-435: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Configuration Management & Feature Flags' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-435 Configuration Management & Feature Flags | Highest | 1 | Server Side / Backend | M1
Task | FEAT-435: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Configuration Management & Feature Flags' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-435 Configuration Management & Feature Flags | Highest | 1 | Server Side / Backend | M1
Task | FEAT-435: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Configuration Management & Feature Flags' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-435 Configuration Management & Feature Flags | Highest | 1 | Server Side / Backend | M1
Task | FEAT-435: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Configuration Management & Feature Flags' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-435 Configuration Management & Feature Flags | Highest | 1 | Server Side / Backend | M1
Story | FEAT-436 Reporting & Analytics Platform | ENGINEERED FOUNDATION ITEM (under-specified or absent in client matrix; required for enterprise delivery). Reporting & Analytics Platform | E14 Intelligence, Reporting & AI |  | High | 8 | Server Side / Backend | M3_Phase_3
Task | FEAT-436: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Reporting & Analytics Platform' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-436 Reporting & Analytics Platform | High | 1 | Server Side / Backend | M3
Task | FEAT-436: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Reporting & Analytics Platform' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-436 Reporting & Analytics Platform | High | 2 | Server Side / Backend | M3
Task | FEAT-436: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Reporting & Analytics Platform' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-436 Reporting & Analytics Platform | High | 3 | Server Side / Backend | M3
Task | FEAT-436: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Reporting & Analytics Platform' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-436 Reporting & Analytics Platform | High | 1 | Server Side / Backend | M3
Task | FEAT-436: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Reporting & Analytics Platform' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E14 Intelligence, Reporting & AI | FEAT-436 Reporting & Analytics Platform | High | 1 | Server Side / Backend | M3
Story | FEAT-437 Backup, Disaster Recovery & BCP | ENGINEERED FOUNDATION ITEM (under-specified or absent in client matrix; required for enterprise delivery). Backup, Disaster Recovery & BCP | E23 Platform Foundations & NFR |  | Highest | 8 | Cross Platform | M1_Phase_2
Task | FEAT-437: Design & technical spec | Architecture, interfaces and acceptance criteria. Acceptance: 'Backup, Disaster Recovery & BCP' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-437 Backup, Disaster Recovery & BCP | Highest | 2 | Cross Platform | M1
Task | FEAT-437: Implementation | Build the capability / automation. Acceptance: 'Backup, Disaster Recovery & BCP' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-437 Backup, Disaster Recovery & BCP | Highest | 3 | Cross Platform | M1
Task | FEAT-437: Automation & CI integration | Pipeline, IaC and gates. Acceptance: 'Backup, Disaster Recovery & BCP' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-437 Backup, Disaster Recovery & BCP | Highest | 2 | Cross Platform | M1
Task | FEAT-437: Verification & sign-off | Validate against NFR/acceptance criteria. Acceptance: 'Backup, Disaster Recovery & BCP' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-437 Backup, Disaster Recovery & BCP | Highest | 2 | Cross Platform | M1
Story | FEAT-438 Security Hardening & Penetration Testing | ENGINEERED FOUNDATION ITEM (under-specified or absent in client matrix; required for enterprise delivery). Security Hardening & Penetration Testing | E17 Identity, Security & Access Policy |  | Highest | 5 | Cross Platform | M5_Phase_5
Task | FEAT-438: Design & technical spec | Architecture, interfaces and acceptance criteria. Acceptance: 'Security Hardening & Penetration Testing' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E17 Identity, Security & Access Policy | FEAT-438 Security Hardening & Penetration Testing | Highest | 1 | Cross Platform | M5
Task | FEAT-438: Implementation | Build the capability / automation. Acceptance: 'Security Hardening & Penetration Testing' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E17 Identity, Security & Access Policy | FEAT-438 Security Hardening & Penetration Testing | Highest | 3 | Cross Platform | M5
Task | FEAT-438: Automation & CI integration | Pipeline, IaC and gates. Acceptance: 'Security Hardening & Penetration Testing' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E17 Identity, Security & Access Policy | FEAT-438 Security Hardening & Penetration Testing | Highest | 1 | Cross Platform | M5
Task | FEAT-438: Verification & sign-off | Validate against NFR/acceptance criteria. Acceptance: 'Security Hardening & Penetration Testing' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E17 Identity, Security & Access Policy | FEAT-438 Security Hardening & Penetration Testing | Highest | 1 | Cross Platform | M5
Story | FEAT-439 Performance & Load Testing | ENGINEERED FOUNDATION ITEM (under-specified or absent in client matrix; required for enterprise delivery). Performance & Load Testing | E23 Platform Foundations & NFR |  | Highest | 5 | Cross Platform | M5_Phase_5
Task | FEAT-439: Design & technical spec | Architecture, interfaces and acceptance criteria. Acceptance: 'Performance & Load Testing' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-439 Performance & Load Testing | Highest | 1 | Cross Platform | M5
Task | FEAT-439: Implementation | Build the capability / automation. Acceptance: 'Performance & Load Testing' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-439 Performance & Load Testing | Highest | 2 | Cross Platform | M5
Task | FEAT-439: Automation & CI integration | Pipeline, IaC and gates. Acceptance: 'Performance & Load Testing' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-439 Performance & Load Testing | Highest | 1 | Cross Platform | M5
Task | FEAT-439: Verification & sign-off | Validate against NFR/acceptance criteria. Acceptance: 'Performance & Load Testing' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-439 Performance & Load Testing | Highest | 1 | Cross Platform | M5
Story | FEAT-440 Automated Test Suite & QA Framework | ENGINEERED FOUNDATION ITEM (under-specified or absent in client matrix; required for enterprise delivery). Automated Test Suite & QA Framework | E23 Platform Foundations & NFR |  | Highest | 8 | Cross Platform | M5_Phase_5
Task | FEAT-440: Design & technical spec | Architecture, interfaces and acceptance criteria. Acceptance: 'Automated Test Suite & QA Framework' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-440 Automated Test Suite & QA Framework | Highest | 2 | Cross Platform | M5
Task | FEAT-440: Implementation | Build the capability / automation. Acceptance: 'Automated Test Suite & QA Framework' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-440 Automated Test Suite & QA Framework | Highest | 3 | Cross Platform | M5
Task | FEAT-440: Automation & CI integration | Pipeline, IaC and gates. Acceptance: 'Automated Test Suite & QA Framework' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-440 Automated Test Suite & QA Framework | Highest | 2 | Cross Platform | M5
Task | FEAT-440: Verification & sign-off | Validate against NFR/acceptance criteria. Acceptance: 'Automated Test Suite & QA Framework' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-440 Automated Test Suite & QA Framework | Highest | 2 | Cross Platform | M5
Story | FEAT-441 UAT, Defect Triage & Sign-off | ENGINEERED FOUNDATION ITEM (under-specified or absent in client matrix; required for enterprise delivery). UAT, Defect Triage & Sign-off | E23 Platform Foundations & NFR |  | Highest | 5 | Cross Platform | M5_Phase_5
Task | FEAT-441: Design & technical spec | Architecture, interfaces and acceptance criteria. Acceptance: 'UAT, Defect Triage & Sign-off' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-441 UAT, Defect Triage & Sign-off | Highest | 1 | Cross Platform | M5
Task | FEAT-441: Implementation | Build the capability / automation. Acceptance: 'UAT, Defect Triage & Sign-off' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-441 UAT, Defect Triage & Sign-off | Highest | 2 | Cross Platform | M5
Task | FEAT-441: Automation & CI integration | Pipeline, IaC and gates. Acceptance: 'UAT, Defect Triage & Sign-off' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-441 UAT, Defect Triage & Sign-off | Highest | 1 | Cross Platform | M5
Task | FEAT-441: Verification & sign-off | Validate against NFR/acceptance criteria. Acceptance: 'UAT, Defect Triage & Sign-off' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-441 UAT, Defect Triage & Sign-off | Highest | 1 | Cross Platform | M5
Story | FEAT-442 Data Migration & Cutover | ENGINEERED FOUNDATION ITEM (under-specified or absent in client matrix; required for enterprise delivery). Data Migration & Cutover | E23 Platform Foundations & NFR |  | Highest | 5 | Server Side / Backend | M6_Phase_6
Task | FEAT-442: Data model & schema | Define entities, relationships, constraints and migrations. Acceptance: 'Data Migration & Cutover' data model & schema complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-442 Data Migration & Cutover | Highest | 1 | Server Side / Backend | M6
Task | FEAT-442: API endpoints | Design and implement REST APIs (CRUD + actions) with contracts. Acceptance: 'Data Migration & Cutover' api endpoints complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-442 Data Migration & Cutover | Highest | 2 | Server Side / Backend | M6
Task | FEAT-442: Business logic & rules engine | Implement configurable rules, workflows and edge cases. Acceptance: 'Data Migration & Cutover' business logic & rules engine complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-442 Data Migration & Cutover | Highest | 2 | Server Side / Backend | M6
Task | FEAT-442: Validation, security & audit | Input validation, RBAC/ABAC checks, audit logging. Acceptance: 'Data Migration & Cutover' validation, security & audit complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-442 Data Migration & Cutover | Highest | 1 | Server Side / Backend | M6
Task | FEAT-442: Unit & integration tests | Automated tests incl. negative and concurrency cases. Acceptance: 'Data Migration & Cutover' unit & integration tests complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-442 Data Migration & Cutover | Highest | 1 | Server Side / Backend | M6
Story | FEAT-443 Documentation & API Reference | ENGINEERED FOUNDATION ITEM (under-specified or absent in client matrix; required for enterprise delivery). Documentation & API Reference | E19 Developer Platform & API Mgmt |  | High | 5 | Cross Platform | M5_Phase_5
Task | FEAT-443: Design & technical spec | Architecture, interfaces and acceptance criteria. Acceptance: 'Documentation & API Reference' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E19 Developer Platform & API Mgmt | FEAT-443 Documentation & API Reference | High | 1 | Cross Platform | M5
Task | FEAT-443: Implementation | Build the capability / automation. Acceptance: 'Documentation & API Reference' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E19 Developer Platform & API Mgmt | FEAT-443 Documentation & API Reference | High | 2 | Cross Platform | M5
Task | FEAT-443: Automation & CI integration | Pipeline, IaC and gates. Acceptance: 'Documentation & API Reference' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E19 Developer Platform & API Mgmt | FEAT-443 Documentation & API Reference | High | 1 | Cross Platform | M5
Task | FEAT-443: Verification & sign-off | Validate against NFR/acceptance criteria. Acceptance: 'Documentation & API Reference' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E19 Developer Platform & API Mgmt | FEAT-443 Documentation & API Reference | High | 1 | Cross Platform | M5
Story | FEAT-444 Production Deployment & Hypercare | ENGINEERED FOUNDATION ITEM (under-specified or absent in client matrix; required for enterprise delivery). Production Deployment & Hypercare | E23 Platform Foundations & NFR |  | Highest | 8 | Cross Platform | M6_Phase_6
Task | FEAT-444: Design & technical spec | Architecture, interfaces and acceptance criteria. Acceptance: 'Production Deployment & Hypercare' design & technical spec complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-444 Production Deployment & Hypercare | Highest | 2 | Cross Platform | M6
Task | FEAT-444: Implementation | Build the capability / automation. Acceptance: 'Production Deployment & Hypercare' implementation complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-444 Production Deployment & Hypercare | Highest | 3 | Cross Platform | M6
Task | FEAT-444: Automation & CI integration | Pipeline, IaC and gates. Acceptance: 'Production Deployment & Hypercare' automation & ci integration complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-444 Production Deployment & Hypercare | Highest | 2 | Cross Platform | M6
Task | FEAT-444: Verification & sign-off | Validate against NFR/acceptance criteria. Acceptance: 'Production Deployment & Hypercare' verification & sign-off complete, reviewed, and meeting acceptance criteria; tests green; no P1/P2 defects. | E23 Platform Foundations & NFR | FEAT-444 Production Deployment & Hypercare | Highest | 2 | Cross Platform | M6